UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 4894 |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Implementation of the POPs Monitoring Plan in the Asian Region |  |  |
| Duration months | Planned |  | 48 months |  |  |
|  | Extension(s) |  | 30 June 2021 |  |  |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste |  |  |
| Name of co-implementing Agency |  |  |  |  |  |
| Executing Agency(ies) |  |  | Chemicals and Health Branch, Economy Division, UN Environment |  |  |
| Names of Other Project Partners |  |  | MTM-Research Center School of Science and Technology, Oerebro University (MTM-Oerebro) |  |  |
|  |  |  | Department of Environment and Health, Vrije Universiteit (Netherlands) |  |  |
|  |  |  | Chemisches und Veterinaeruntersuchungsamt Freiburg (CVUA, UN Environment/WHO Reference Laboratory for Human Milk) |  |  |
|  |  |  | Research Centre for Toxic Compounds in the Environment (RECETOX, Czech Republic) |  |  |
|  |  |  | Spanish National Research Council (CSIC) |  |  |
|  |  |  | Basel Convention Coordinating Centre, Stockholm Convention Regional Centre, for Capacity Building and Transfer of Technology hosted by Uruguay (BCCC-SCRC-LATU) |  |  |
|  |  |  | Japan Environmental Sanitation Center (JESC); as well as the National Institute for Environmental Studies (NIES), Japan |  |  |
|  |  |  | World Health Organization (WHO) |  |  |
|  |  |  | Secretariat of the Basel, Rotterdam and Stockholm conventions |  |  |
| Project Type |  |  | FSP |  |  |
| Project Scope |  |  | Regional |  |  |
| Region (delete as appropriate) |  |  | EAP |  |  |
| Names of Beneficiary Countries |  |  | Indonesia, Cambodia, Lao PDR, Mongolia, Philippines, Thailand, Vietnam |  |  |
| Programme of Work |  |  | Chemicals and Health Programme of Work |  |  |
| GEF Focal Area(s) |  |  | POPs |  |  |
| UNDAF linkages |  |  |  |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Goal 3: Ensure healthy lives and promote well-being for all at all ages Target 3.9: By 2030, substantially reduce the number of deaths and illnesses from hazardous chemicals and air, water and soil pollution and contamination; Target 3.13: Strengthen the capacity of all countries for early warning, risk reduction and management of national and global health risks; Goal 6: Ensure availability and sustainable management of water and sanitation for all Target 6.3: By 2030, improve water quality by reducing pollution, eliminating dumping and minimizing release of hazardous chemicals and materials, halving the proportion of untreated wastewater and substantially increasing recycling and safe reuse globally Goal 12: Responsible consumption and production Target 12.4: By 2020, achieve the environmentally sound management of chemicals and all wastes throughout their life cycle, in accordance with agreed international frameworks, and significantly reduce their release to air, water and soil in order to minimize their adverse impacts on human health and the environment. Goal 17: Partnerships for the goals Target 17.6: Enhance North-South, South-South and triangular regional and international cooperation on and access to science, technology and innovation and enhance knowledge sharing on mutually agreed terms, including through improved coordination among existing mechanisms, in particular at the United Nations level, and through a global technology facilitation mechanism; Target 17.18: By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts. |  |  |
| GEF financing amount |  |  | 3,936,000 USD |  |  |
| Co-financing amount |  |  | 13,164,900 USD |  |  |
| Date of CEO Endorsement |  |  | 15.12.2014 |  |  |
| Start of Implementation |  |  | 01.09.2015 |  |  |
| Date of first disbursement |  |  | [to be completed by FMO] |  |  |
| Total disbursement as of 30 June 2019 |  |  | 2,834,943 USD |  |  |
| Total expenditure as of 30 June 2019 |  |  | 792,805 USD |  |  |
| Expected Mid-Term Date |  |  | 31.08.2018 |  |  |
| Completion Date |  | Planned | 31.08.2019 |  |  |
|  |  | Revised | 30 June 2021 |  |  |
| Expected Terminal Evaluation Date |  |  | July 2021 |  |  |
| Expected Financial Closure Date |  |  | 30 June 2021 |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Chemicals and Health Subprogramme | Specify the relevant Expected Accomplishment(s) & Indicator(s) a(i) Increase in the number of countries that have used UNEP analysis or guidance, and where possible are applying a multi-sectoral approach, in developing or implementing legislation, policies or action plans that promote sound chemicals management and implementation of the relevant multilateral environmental agreements and SAICM |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] PoW indicator a(i): National Governmental Agencies and Universities in 7 countries have implemented activities for deleting, managing hazardous substances and monitoring their impact on the environment and human health in Asia. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. [Section to be shared with Monitoring Unit within PPD] |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes [section to be shared with SDG unit] While contributing to the Stockholm Convention Effectiveness Evaluation, the GMP projects also contribute to achieving SDG Goal 3, 12and Goal 17. Specifically, data generated on the existence of POPs in air, water and human milk will support decision making regarding achieving SDG Goal 3 Target 3.9. Activities on building national capacity on POPs monitoring and analysis will contribute to achieving Target 3.13 of SDG Goal 3. The results of the projects will also reflect whether the commitments to the Stockholm Convention are achieved as planned, which will contribute to Target 12.4. Monitoring of POPs in water contributes to SDG Goal 6: Ensure availability and sustainable management of water and sanitation for all. Information generated helps to control and eventually eliminate the release of POPs into water, as requested by Target 6.3. Through engaging multiple stakeholders in all UN regions such as governmental institutes, research institutes and IGOs, and through providing national capacity building on POPs monitoring and analysis, the projects also contribute to SDG Goal 17, especially Target 17.6 and Target 17.18. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | … PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | MS | MS |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. The conditions for successful project implementation have been established and measures are in place to strengthen the capacity of countries, including their national laboratories, where appropriate, to sample and analyse POPs in biotic and abiotic matrices. Legal agreements with all the seven countries have already been signed. All relevant nominations for the national counterparts have been gathered and the roles clearly allocated at the national level. Sampling materials and targeted hands-on training courses have been provided to countries; samples of abiotic and biotic matrices have been collected and initial results are being generated in laboratories. The 3rd round of the global interlaboratory assessment was successfully completed, with 175 laboratories from all UN regions registered. The 4th round interlaboratory assessment has received 147 registrations as of June 2019. It is expected to conclude its work by 3rd quarter 2019 with reports prepared. The GMP Asia project midterm workshop and several expert consultation meetings have been organized to share progress of the projects and plan for next steps. Good progress has been made on the development of strategies for sustainable POPs global monitoring in the long run. Most notably, this will include increased capacity of the Parties to the Stockholm Convention to make informed decisions and set appropriate priorities regarding the phase out, management and disposal of POPs, which will result in decreased exposure and reduced adverse effects to humans and the environment. The data generated through the activities of the project will make an important contribution to the effectiveness evaluation of the Stockholm Convention and thus allow future Conferences of the Parties (COP) to evaluate and adopt strategies, as necessary, for enhanced progress in achieving the Convention objectives. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | MS | MS |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. FY19: The project has on-going in all participating countries and is making good progress in securing the continuous successful implementation of the project as well as generating high quality data from the sampling of biotic and abiotic core matrices. Most notable are the following measures and activities: - Technical and administrative supports have been provided for the implementation of the project. All the 7 countries from the Asia Region have signed the Small Scale Funding Agreements (SSFAs) with UN Environment. Sampling activities started in the Asia Region since 2017. - The GMP Asia project midterm workshop was successfully held on 8-10 August 2018 in Ulaanbaatar, Mongolia. Project participating countries, representatives of the GMP Global Coordination Group, BRS, expert laboratories and representatives of other regional monitoring networks participated in the workshop. The workshop reviewed progress of the project and shared good practices, and planned for next steps especially milestones to be achieved in 2019 and 2020. A steering committee meeting was held during the workshop. - Until June 2019, eight expert consultation meetings for the GMP projects in Asia, Africa, Pacific and GRULAC regions have been held to update progress and plan for appropriate next steps. The seventh expert coordination meeting is held on 10-11 August in Ulaanbaatar, Mongolia. The meeting summarised the conclusions and lessons learnt from midterm workshops of the GMP projects, and planned to conduct a fact-based review of rounds of GMP projects and to develop a tool to support the sustainable monitoring of POPs beyond the GMP2 projects. Following the decisions of the Ulaanbaatar meeting, a follow-up expert consultation meeting was organized from 12-14 February 2019 in Brno, Czech Republic to further develop the sustainable monitoring framework. - During the Stockholm Convention COP9, UNEP Chemicals and Health Branch, together with the Stockholm Convention Regional Center in Uruguay and the Stockholm Convention Regional Center in Czech Republic, organized a side event on 1 May 2019 to present the achievements of 15-years of POPs global monitoring projects and strengthen stakeholder engagement in support of sustainable monitoring of POPs., with a progress report of the GMP2 project accepted by the COP9. A project progress consultation meeting was organized during the BRS COP9 among delegates of GMP participating countries to discuss challenges and inform the upcoming deadlines for deliverables. - A revised webpage, containing the finalized tutorial videos for active air sampling and human milk survey in English, French and Spanish, as well as Standard Operating Procedures (SOPs) for passive air sampling, human milk survey, water and matrices of national interest in English, French and Spanish have been shared with participating countries and are publicly available online at https://www.unenvironment.org/explore-topics/chemicals-waste/what-we-do/persistent-organic-pollutants/guidance-and-standard. - The POPs laboratory databank has been updated and is publicly available at http://informea.pops.int/HgPOPsLabs/index.html. - The 4th interlaboratory assessment has been launched in September 2018 with 147 laboratories from all UN regions registered. Until June 2019, results from 92 laboratories have been received. The report of the 4th interlab assessment is being prepared. Besides, a review of the four rounds of interlaboratory assessments is planned to be developed to conclude the impacts of this global cross calibration study and discuss about future steps. - Out of the 6 trainings planned for national laboratories on the analysis of POPs depending on their existing analytical capacity, five have been completed until June 2019. Except for Vietnam, which rescheduled the training due to personnel change, the other trainings have been delivered in Mongolia, the Philippines, Indonesia, Thailand and Cambodia. Besides, with support from the Indonesia Basel Convention Regional Center, some countries, namely Myanmar and Malaysia that are not in the GMP project, and LAO PDR which has just established the national laboratory but has not obtained analytical capacity, also joined and benefited from the training in Indonesia. - The last round of air sampling has concluded its work by 30 June 2019. Most of the samples collected have been or will soon be sent to the expert laboratories for the analysis of 23 POPs under the Stockholm Convention. A few initial results have been generated and presented in the COP9 side event. Samples for mirror analysis were sent to national laboratories. - The two-year water sampling program has been completed in the two countries undertaking this program in the Asia region, namely Mongolia and Vietnam. Samples have been sent to the expert laboratory for the analysis of PFOS. Some initial results have been generated and presented in several occasions such as the GMP side event at COP9. - Five countries have completed the sampling of matrices of national interest and sent to IVM for analysis; the activities are ongoing in the other countries. - Four countries have completed the human milk survey, and the other three countries are on the last stage. The survey in Indonesia is suspended due to national administrative challenges. - Active air sampling is implemented in Vietnam with instrument and technical assistance from the Ministry of Environment of Japan. - Active air sampling is implemented in Mongolia with technical assistance from CSIC. - A suggested template for the project national final report has been shared with countries during the midterm workshop. Content, format and timeline for the preparation of the national report has been discussed. - Planning of sustainable monitoring of POPs beyond GMP2 has started and some draft content has been prepared, including screening regional and national priorities, challenges and opportunities, identifying key pillars and developing the draft framework for sustainable monitoring of POPs. An outreaching plan has been prepared, with a variety of communication materials being prepared, including videos, webpages and press lease, etc. - Support has been provided to the midterm review of the project, which was conducted from Dec 2017 to Oct 2018. The suggestions in the review report has been considered into the planning of next steps as well as the development of sustainable framework and strategies, including further activities to be considered within the GMP2 project. - A global stakeholder consultation meeting on the sustainable monitoring of POPs is scheduled in December 2019 in Brisbane, Australia. It aims to develop a sustainable framework and strategy for POPs global monitoring in the long run. Overall, countries and other partners are in a good position to continue implementing the substantive activities of the project. Samples and analysis results are expected to be delivered on time. UN Environment are in close cooperation with the Asian countries and other partners on the successful implementation of the project. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | L | L | L |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 The POPs Global Monitoring Plan is implemented in the Asia Region for the first time. A project involves seven countries has obvious logistical risks. Through close monitoring the project progress and frequent communication with the steering committee to plan in advance, mitigation actions were taken at early stages to solve or prevent risks. As four out of the seven countries have experience with implementing NIPs project, and the others conducted monitoring of POPs under the POPSEA network, the project builds on an already existing network with proven capacity to carry out the project activities. During the implementation, unexpected difficulties and delays occurred. Two countries delayed in signing the legal agreement with UNEP due to internal administrative reasons. With in-kind contributions from countries and support from other executing partners, the project is on good track to catch up on lost time. Besides, custom control of shipment of biota matrices prevented the shipping of certain matrices of national interest. Custom clearance letters, importing approvals issued by the custom of the countries where the expert labs locate as well as official supporting letters from UNEP were provided to solve the issues. In addition, difficulties occurred in most countries for the ethical clearance for human milk survey. Official and technical support from UNEP and WHO and expert labs have been provided to support the obtaining of ethical clearance. Taking into consideration of above delays, the steering committee decided to extend the deadline for the arrangements of milk samples. Indonesia withdrew from human milk survey due to difficulties in obtaining national clearance for the collection of human biota samples. The other major risk identified in the Project Document is the ability to do the laboratory work. For quality assurance purpose, a number of samples are analyzed in experienced partner laboratories. A capacity screening was conducted at the beginning of the project. To improve and maintain the national capacity, countries having basic capacity and essential infrastructure were provided with hands-on training for the analysis of certain POPs. Two rounds of interlaboratory assessment were organized for the purpose of quality assurance/quality control. |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] All project stakeholders are committed to accomplish the project outcomes and outputs. So far, during the execution and implementation period: - The expert laboratories, namely MTM-Research Center School of Science and Technology, Oerebro University (MTM-Oerebro), Department of Environment and Health, Vrije Universiteit (Netherlands) have organized training and mirror analysis of samples, and two rounds of inter‐calibration studies. MTM Centre Örebro also serves as reference laboratory for PFOS in human milk. - Chemisches und Veterinaeruntersuchungsamt Freiburg (CVUA, UN Environment/WHO Reference Laboratory for Human Milk) has undertaken the analysis of lipophilic POPs in human milk and assists in matters related to this core matrix - Research Centre for Toxic Compounds in the Environment (RECETOX, Czech Republic) and Spanish National Research Council (CSIC) have provide assistance in matters related to air monitoring - The Basel Convention Coordinating Centre, Stockholm Convention Regional Centre, for Capacity Building and Transfer of Technology hosted by Uruguay (BCCC-SCRC-LATU), the co-executing agency for the GMP GRULAC project, has provided support to the four GMP projects on the development of strategies for sustainable monitoring of POPs and assistance to the implementation in LAO PDR and the Philippines. - Participating countries from the Asia Region have provide significant inputs to the project through the establishment and maintenance of the air and water networks; collect/organize the collection of human milk samples for the GMP through the mothers donating the breast milk; provide human milk donors with results of the analysis and the interpretation of it, and will further contribute to Article 16 of the Stockholm Convention by providing sub‐regional data to the effectiveness evaluation and the Global Monitoring Plan for POPs. Besides, the project countries also provided staff support on operating the networks together with other countries in the region, such as maintaining the sampling network for ambient air; receive training and consumables/spares; generate national data if applicable in a systematic and comparable way that will characterize their exposure to POPs. - Japan Environmental Sanitation Center (JESC), as well as the National Institute for Environmental Studies (NIES), Japan has supported the GEF GMP2 project with in‐kind co-financing in the form of personnel, office facilities and equipment, laboratory infrastructure and equipment, as well as bilateral assistance through collaboration and coordination with other projects in relation to POPs (i.e., POPSEA). Through the implementation of POPSEA, they will play an important role in the post-GEF project’s sustainability of monitoring activities in the region. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] The project is of a scientific nature and does not directly impact people’s productive activities. However, the gender aspects are indirectly addressed through different dimensions such as contribution to POPs emissions reductions. The particular vulnerability to POPs exposure of women in childbearing age is taken into account in the design of the monitoring activities, notably by the incorporation of mother’s milk as one of the core matrices of the POPs GMP. The collection of human milk samples will be conducted on the basis of the ethical clearance as required by WHO, and after signature of the statement of interest by both, health and environment sector. |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval [section will be uploaded into the GEF Portal] The main activities of the POPs GMP projects are to generate data on the presences of POPs at global level, and to strengthen capacity for the sampling and analysis of POPs. Sampling activities under the GMP Asia project include sampling of abiotic air and water, biotic human milk, and matrices of national interest. Samples collected are analyzed in expert laboratories and in national laboratories with existing capacity. Results generated will eventually contribute to the POPs GMP data warehouse and further support the Stockholm Convention Effectiveness Evaluation. Besides, various capacity building activities have been delivered under the GMP Asia project. Standard operating procedures and guidelines for the sampling and analysis of POPs are developed and published online at https://www.unenvironment.org/explore-topics/chemicals-waste/what-we-do/persistent-organic-pollutants/guidance-and-standard. Trainings have been planned for six national laboratories on the analysis of POPs. In addition, as a tool for quality control/quality assurance (QA/QC), two rounds of international inter-laboratory assessments of POPs laboratories have been conducted. A databank of POPs laboratories have been established and is publicly available online at http://informea.pops.int/HgPOPsLabs/index.html. |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. [section to be shared with communication division/ GEF communication] The four parallel POPs Global Monitoring Plan are developed in response to requests for assistance from Parties to the Stockholm Convention. The first phase had been implemented in the Africa Region, the Latin America and the Caribbean (GRULAC) Region and the Pacific Region. It is the first time to be implemented in the Asia Region. The project design foresees the development of a regional sustainable monitoring plan going far beyond project duration. With concrete results generated, both on-the-ground and normative, and new scientific and technological standards being disseminated via training and interlaboratory assessment which involves both governmental and private laboratories, this project will contribute to increasing the capacity of the Parties to the Stockholm Convention to make informed decisions and set appropriate priorities regarding the phase out, management and disposal of POPs, which will result in decreased exposure and reduced adverse effects to humans and the environment. Air, water and human milk sampling networks are being established and will continue to be operated beyond the project duration. In addition, national laboratories will be in a position to independently analyse various POPs in selected biotic and abiotic matrices. At the global level, the data gathered through this and the sister projects will feed into the effectiveness evaluation of the Stockholm Convention and help the Parties to identify challenges and set priorities thus allow future COPs to evaluate and adapt their efforts, as necessary. At the national level, stakeholders will have an improved understanding of the main challenges in their countries and increased capacity to fulfil their obligations under Article 16 of the Convention, i.e. to periodically evaluate the effectiveness of the Convention, including in the context of future reviews/updates of their National Implementation Plans (NIPs). |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective | To strengthen the capacity for implementation of the updated POPs Global Monitoring Plan (GMP) and to create the conditions for sustainable monitoring of POPs in the Asian Region |  |  |  |  |  |
| Outcome 1: National capacities for implementing the updated POPs Global Monitoring Plan (GMP) are strengthened, high quality data on the presence and transport of POPs are generated, and conditions for sustainable monitoring of POPs are in place in the Asia Region | 1. # of countries capable to undertake sampling in the core and other matrices for POPs analysis | Baseline: 0 | Na | Target: 6 | By 30 June 2019, 7 countries have undertaken the sampling activities under legal agreements signed with UNEP | MS |
|  | 2. # of countries with reported data on up to 23 POPs | Baseline: 0 | Na | Target: 5 | By 30 June 2019, initial results from 5 countries have been generated. More samples are being analysed | S |
|  | 3. # of regional roadmap for sustainable POPs monitoring published | Baseline: 0 | Na | Target: 1 | By 30 June, the plan for sustainable monitoring of POPs has been discussed in regional midterm workshop and several expert consultation meetings. More detailed plan are being developed with joint efforts from all GMP regions. | MS |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | The project has made a lot of progress towards meeting its objectives |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | - Some delays occurred in signing the legal agreements due to bureaucracy in two project countries, and in starting the sampling activities due to personnel changes in some countries - Difficulties occurred in some countries on the shipment of national biota samples - Due to personnel change and regional issues, Vietnam Environment Agency could not coordinate regional activities as planned. | - The steering committee decided to extend the sampling period to compensate the time loss. - Custom clearance letters, importing approvals issued by the custom of the countries where the expert labs locate as well as official supporting letters from UNEP have been provided to solve the issues. - BCCC-SCRC-Uruguay, the executing agency in the GRULAC Region, was involved to assist with the implantation in LAO PDR and the Philippines. |
| on stakeholder engagement | No issue identified |  |
| on gender actions | No major sensitivities occurred |  |
| on safeguards | Sampling of human milk is relatively sensitive especially in certain countries. | Official and technical support from UNEP and WHO and expert labs were provided to support the obtaining of ethical clearance. |
| on delivering GEF Core Indicators | Not applicable |  |
| on delivering of PoW EA | None observed |  |
| on sustainability of results | Frequent change of national staff, lack of political will and inadequate allocation/availability of funds can be potential risks for sustainability | The development of sustainable monitoring of POPs beyond the project has taken these into consideration |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1: Technical and administrative support provided for the implementation of the project and organization of process established in the Asia Region |  |  |  |  | S |
| Activity 1.1: Key stakeholders sign legal documents to carry out activities. | 30.04.2018 | 85% | 100% | All partners signed legal agreements with UNEP | S |
| Activity 1.2: Organise inception workshop, with project workplan and budget assigned. | 31.05.2016 | 100% | 100% | Inception workshop took place in 2016, with project launched and workplan and budget assigned. | S |
| Activity 1.3. Update POPs laboratory databank. | 30.04.2020 | 90% | 100% | The POPs laboratory databank has been updated, with new registered labs included. It is available online at http://informea.pops.int/HgPOPsLabs/index.html | S |
| Output 2: Training reports and sectoral reports on POPs analysis undertaken on two abiotic core matrices (i.e., air and water) in the Asia Region |  |  |  |  | MS |
| Activity 2.1: Identify sampling sites for air monitoring and make them operational. | 30.11.2017 | 100% | 100% | With guidance document provided by UNEP, sampling sites for air monitoring have been identified in all project countries. Air monitoring has been undertaken in all project countries | S |
| Activity 2.2: Identify sampling sites for water monitoring and make them operational. | 30.11.2017 | 100% | 100% | With guidance document provided by UNEP, sampling sites for water monitoring have been identified in the countries assigned to undertake water monitoring. Monitoring activities have been undertaken in all project countries | S |
| Activity 2.3: Make national laboratories operational for undertaking analysis of abiotic matrices. | 30.08.2018 | 80% | 100% | National analytical capacity screening have been conducted at the beginning of the project. National labs with existing capacity have been assigned to analyse certain POPs according to their capacity. Mirror analysis is planned in reference labs to ensure the generation of high quality international comparable data. Trainings have been provided to selected national laboratories, and two rounds of interlaboratory assessment have been organized for quality assurance/quality control. | S |
| Activity 2.4: Analyse national samples for air and water, and report high quality data. | 31.05.2019 | 30% | 60% | Air and water samples collected have been sent to reference labs for analysis. Initial results have been generated and presented in the project midterm workshop and expert consultation meetings | MU |
| Activity 2.5: Summarize results of analysis in two distinctive sectoral reports. | 30.04.2020 | 0% | 0% | Will start after all results are available |  |
| Output 3: Training reports and sectoral report on POPs analysis undertaken on one biotic core matrix (6th round of human milk survey) in the Asia Region |  |  |  |  | MS |
| Activity 3.1: Make countries in the region capable to undertake sampling of human milk for the 6th round of UNEP/WHO survey. | 30.11.2017 | 100% | 100% | Standard Operating Procedures and video tutorials have been provided to guide the implantation of human milk survey. National coordinator for human milk survey were nominated by each project country. Additional support have been provided to countries to obtain ethical clearance. Due to difficulties in obtaining national clearance, Indonesia withdrew from the human milk survey. | S |
| Activity 3.2: Make national laboratories operational for undertaking analysis of human milk samples. | 28.02.2018 | 70% | 100% | National laboratory capacity screening have been conducted to identify labs that can analyse human milk samples. | S |
| Activity 3.3: Implement the 6th round of human milk survey. | 28.02.2018 | 55% | 70% | All project countries have received sampling materials. Except for Indonesia that withdrew from human milk survey, four countries have completed human milk survey, two others almost conclude the work. | MS |
| Activity 3.4: Compare results from earlier rounds, and report them to the GMP. | 30.04.2020 | 0% | 20% | Will start after all results are available | MS |
| Output 4: Assessment report of existing analytical capacities prepared and report on POPs analysis undertaken in samples of national priority (other than core matrices) in the Asia Region |  |  |  |  | MS |
| Activity 4.1: Undertake two rounds of the global interlaboratory assessment. | 31.05.2017 and 31.05.2019 | 100% and 30% | 100% and 90% | Following the two rounds of interlaboratory assessments under GMP1, the GMP2 projects supported the 3rd round of interlaboratory assessments in 2016-2017 with 175 registrations from all UN regions and the 4th round in 2018-2019 with 147 registrations. The 4th round interlab is wrapping up its work and finalizing the report. | S |
| Activity 4.2: Identify and analyse samples of major national interest. | 28.02.2019 | 60% | 65% | In collaboration with VU Amsterdam, support have been provided to all project countries to identify the list of matrices of national interest, including standard operating procedures for sampling. Samples collected have been shipped to reference labs for analysis. In spite of extended support some countries so far have not succeeded in sending the national samples of interest. | MS |
| Output 5: Assessment reports contributing to regional report for the GMP undertaken, and a roadmap for sustainable POPs monitoring developed for the Asia region |  |  |  |  | S |
| Activity 5.1: Develop conclusions, lessons learned and recommendations from GMP2 for future monitoring plan. | 30.04.2020 | 20% | 35% | Steering committee meetings and expert consultation meetings have been organized to discuss lessons learnt and recommendations. Factual review, historical review and assessment of technical feasibilities and opportunities have been organized to advice future monitoring of POPs. | S |
| Activity 5.2: Prepare a state-of-the-art report to picture the present situation of POPs in the region’s environment and humans. | 30.04.2020 | 20% | 35% | The preparation of national report has been launched in the regional midterm workshop, with a template provided to all project countries. Report will be completed once date is generated | S |
| Activity 5.3: Develop a roadmap for sustainable POPs monitoring. | 30.04.2020 | 20% | 35% | Initial work has been undertaken to plan for the sustainable monitoring of POPs in the future, including meetings organized and substantive work being undertaken. | MS |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | Project implementation has greatly improved this reporting period |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Delays occurred on signing of the legal agreement due to internal administration in two countries | The schedule of delivery of outputs were adjusted | UNEP and respective partner | 2017 |
| Delays on starting the sampling activities due to personnel changes in some countries | Extended the sampling period to compensate the time loss | Steering committee | June 2018 |
| Delays occurred in some countries to obtain ethical clearance for human milk survey, and Indonesia withdrew from human milk survey because of rejection of ethical clearance | Official and technical support from UNEP and WHO and expert labs were provided to support the obtaining of ethical clearance. Extended the sampling time to support the human milk survey. | UNEP, partners, steering committee | June 2018 |
| Difficulties occurred in some countries on the shipment of national biota samples | Custom clearance letters, importing approvals issued by the custom of the countries where the expert labs located as well as official supporting letters from UNEP were provided to solve the issues. | UNEP, partners, steering committee | 2018 |
| Due to personnel change and regional issues, Vietnam Environment Agency could not coordinate regional activities as planned. | BCCC-SCRC-Uruguay, the executing agency in the GRULAC Region, was involved to assist with the implantation in LAO PDR and the Philippines. | UNEP, partners | 2017 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Logistical risks inherent to a programme involving seven countries | - The liaison work will be facilitated by VEA; - The project will also build on the POPSEA network - Lessons learned from the 1st POPs monitoring project concerning administrative issues and technical orientation will be taken into account in this project. For this reason, UNEP has been assigned as executing agency | - Steering committee meetings were held to adjust workplan and timeline for the sampling activities. Custom clearance letters, importing approvals issued by the custom of the countries where the expert labs located as well as official supporting letters from UNEP have been provided to support the shipment of national samples. - Delays occurred in signing the legal agreements in two countries due to bureaucratic reasons. With co-finance and in-kind contributions from countries, and support from other executing partners, the project is on good track to catch up on lost time. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM:M |
| Inability to conduct laboratory work | - The capacity of POPs laboratories has not yet been assessed. Therefore, the knowledge about the real situation of the capacities and performance of most laboratories is unknown (exception are the three laboratories in Vietnam). For quality assurance purpose, a number of samples will be analyzed in an experienced partner laboratory. | - A capacity screening was conducted at the beginning of the project. Countries having basic capacity and essential infrastructure were provided with hands-on training for the analysis of certain POPs. Two rounds of interlaboratory assessment were organized for the purpose of quality assurance/quality control | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM:M |
| Delays on the approval of ethical clearance for the human milk survey |  | Upon request, official and technical support from UNEP and WHO and expert labs were provided to countries to support the obtaining of ethical clearance. The steering committee extended the deadline for the arrangements of milk samples. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM:M |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | Although some risks remain, as the project is reaching its final phase, these will reduce. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : No issues could be identified regarding the roles and responsibilities. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : The first steering committee meeting for the four parallel GMP projects have been held on 26 October 2018 in Montevideo, Uruguay. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Good communication between team members. Some communication issues between implementing and executing partners sorted out. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | X |  |  |  |  |  | PM: Slight delay in proceeding with the project activities was registered due to signing of small scale funding agreements with the countries and to slow administrative procedures | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: In kind co-funding by project countries and partners (UN Environment, BRS Conventions Secretariat and other project partners in place (co-funding report provided). | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | X |  |  |  |  |  | PM: Initial components of the initial budget table was designed by POPs while partners undertake activities according to the workstream. Budget revisions were conducted to better manage the expenditures and the progress of activities. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  | X |  |  |  |  | PM: Guidance have been provided to partners on reporting on time. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: lots of positive progress this period |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  | X |  |  |  |  | PM: Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Reporting is now consistently timely |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: All project stakeholders are committed to accomplish the project outcomes and outputs. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: The project concept, outcomes and outputs were disseminated beyond implementation partners. Outputs of the project have been presented at the Stockholm Convention GMP GCG meetings, side event at the SC COP9, and other academic and international conferences. Communication materials have been prepared to support outreaching activities. Details of the project are presented on the dedicated webpage on UN Environment website: https://www.unenvironment.org/explore-topics/chemicals-waste/what-we-do/persistent-organic-pollutants/national-implementation-1 | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: no issues identified. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: no issues identified. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: no attempts to influence identified. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  | X |  |  |  |  |  | PM: None observed. |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: None observed. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions | X |  |  |  |  |  | PM: None observed. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | X |  |  |  |  | PM: no major sensitivities occurred | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: Frequent personnel changes at national levels might be a risk to remain the capacity building outcomes in the country. UNEP is coordinating the development of a sustainable mechanism to enhance political buy-in and technical stability. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | Project remain at low risk. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.