UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | Insert GEF ID.: 9696 | Insert Umoja no.: S1-32GFL-000621 SB-008431 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Enabling Transactions – Market Shift to Deforestation Free Beef, Palm Oil and Soy |  |  |
| Duration months | Planned |  | 48 |  |  |
|  | Extension(s) |  |  |  |  |
| Division(s) Implementing the project |  |  | GEF Biodiversity and Land Degradation Unit, Ecosystems Division |  |  |
| Name of co-implementing Agency |  |  | UNEP |  |  |
| Executing Agency(ies) |  |  | UNEP Finance Initiative |  |  |
| Names of Other Project Partners |  |  | IFC, UNDP, WWF USA, WWF Indonesia and Conservation International |  |  |
| Project Type |  |  | FSP (Child Project) |  |  |
| Project Scope |  |  | Global; National |  |  |
| Region (delete as appropriate) |  |  | Africa, Asia Pacific, Latin America, |  |  |
| Names of Beneficiary Countries |  |  | Indonesia, Liberia, Paraguay and Brazil |  |  |
| Programme of Work |  |  | This project contributes to the Programme of work for the biennium 2018-2019, more specifically to subprogramme 1 on climate change (accomplishments b and c) and subprogramme 3 on healthy and productive ecosystems (accomplishment b) |  |  |
| GEF Focal Area(s) |  |  | This is an IAP Program child project that intersect multiple focal areas across the landscape (climate change, biodiversity and land degradation) |  |  |
| UNDAF linkages |  |  | Indonesia Priority Area 3: Environmental sustainability and enhanced resilience to shocks Outcome: By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disasters and other shocks. Paraguay Priority Area 3: Advancing nature protection, reducing environmental degradation and strengthening disaster risk management Outcome 3.2: Significant advances in reducing deforestation and desertification, through better conservation practices and sustainable use of biodiversity, as well as climate change mitigation and adaptation Brazil Priority Area 2: Sustainable management of natural resources for current and future generations Outcome 2: Participatory governance models for sustainable and effective management of natural resources and ecosystem services, seeking integrated, resilient and inclusive territories |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | SDG Goals 2, 5, 11, 12, 15 and 17 2.4.1 Proportion of agricultural area under productive and sustainable agriculture 5.a.1(a) Proportion of total agricultural population with ownership or secure rights over agricultural land, by sex; and (b) share of women among owners or rights-bearers of agricultural land, by type of tenure 11.3.1 Ratio of land consumption rate to population growth rate 12.1.1 Number of countries with sustainable consumption and production (SCP) national action plans or SCP mainstreamed as a priority or target into national policies 15.1.1 Forest area as a proportion of total land area 15.1.2 Proportion of important sites for terrestrial and freshwater biodiversity that are covered by protected areas, by ecosystem type 15.2.1 Progress towards sustainable forest management 15.3.1 Proportion of land that is degraded over total land area 17.14.1 Number of countries with mechanisms in place to enhance policy coherence of sustainable development |  |  |
| GEF financing amount |  |  | USD 2,125,457 |  |  |
| Co-financing amount |  |  | USD 3,778,419 |  |  |
| Date of CEO Endorsement |  |  | 4 April, 2017 |  |  |
| Start of Implementation |  |  | 8 Feb 2018 |  |  |
| Date of first disbursement |  |  | 23 Feb 2018 |  |  |
| Total disbursement as of 30 June |  |  | USD 721,166 |  |  |
| Total expenditure as of 30 June |  |  | USD 509,180 |  |  |
| Expected Mid-Term Date |  |  | December 2019 |  |  |
| Completion Date |  | Planned | 30 Sept 2022 |  |  |
|  |  | Revised |  |  |  |
| Expected Terminal Evaluation Date |  |  | December 2021 |  |  |
| Expected Financial Closure Date |  |  | June 2022 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) This project contributes to the Programme of work for the biennium 2018-2019, more specifically to Subprogramme 1 on Climate Change and Subprogramme 3 on Healthy and Productive Ecosystems | Specify the relevant Expected Accomplishment(s) & Indicator(s) For S1, relevant accomplishment are b (“Countries increasingly adopt and/or implement low greenhouse gas emission development strategies and invest in clean technology”, indicator ii) and c (“Increase in climate finance invested by countries of institutions for clean energy, energy efficiency and/or amount of decarbonized assets”, indicator i) For S3, relevant accomplishment is b (“Policymakers in the public and private sectors test the inclusion of health and productivity of ecosystems in economic decision-making”, indicator ii) |
| --- | --- |
| In Paraguay, the project supported research and development of a new norm mandating the integration of environmental, social and governance criteria in the financing processes of all financial institutions in Paraguay. Research to better understand the gaps in environmental regulation related to deforestation and how financial institutions were complying with regulations resulted in a series of papers identifying current gaps in capacity within financial institutions to comply with the existing legislation and the requirement of enforcement of the legislation by the Brazilian government. In collaboration with Forest Trends, the project developed new metrics through several data partnerships to track corporate commitments to sourcing sustainable palm oil. The findings are to be presented in a webinar possibly at the Roundtable for Sustainable Palm Oil in November 2019 and other events in Asia Pacific. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results N/A |
| --- | --- |
|  | Indicative expected Results |
| This is an IAP Program that intersect multiple core indicators, with a strong emphasis on core indicators 1, 3 and 4. The transaction child project, due to its supportive nature, cannot be attributed any direct change in the targets set for these indicators but rather indirectly contribute through the increased availability of financial instruments to their achievement by the other child projects. In accordance with the objectives of the Production and Demand child projects, priority has been given to indicator 1.2, indicator 3.1, indicator 4.3 and indicator 4.4 |  |

| Planned linkages with UNDAF | As indicated above the project contributes to UNDAF Strategic objective 2 (in Brazil) and 3 (in Paraguay and Indonesia) : this includes integrating economic, environmental and social sustainability and risk management into programming, and strengthening national capacities to address these issues. In Indonesia, the project will help the government and the country achieve their 2020 target of sustainability managing their natural resources by increasing the amount of financing in support of increased resilience to the effects of climate change, disasters and other shocks. In Brazil, the project aims to pilot training programs for the financial sector reinforcing participatory governance models for sustainable and effective management of natural resources and ecosystem services, seeking integrated, resilient and inclusive territories. In Paraguay, the project contributes to the development and advancement of a new national financial framework promoting activities that reduce deforestation and desertification, through better conservation practices and sustainable use of biodiversity, as well as climate change mitigation and adaptation |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | SDG Goals 2, 5, 11, 12, 15 and 17 2.4.1 Proportion of agricultural area under productive and sustainable agriculture This the project’s main priority and “raison d’etre” to promote the emergence and adoption of production systems capable of combining productivity and sustainability. If successful, the project shall pave the way for a radical transformation of the beef, soy and palm oil sectors in leading producing countries, which should encourage other markets to follow in their wake. 5.a.1(a) Proportion of total agricultural population with ownership or secure rights over agricultural land, by sex; and (b) share of women among owners or rights-bearers of agricultural land, by type of tenure Project will leverage finance to incentivize farmers to respect and enforce land tenure policies and good practices, including by requiring the demonstration of land ownership rights prior to obtaining loans or investments. Gender considerations will be highlighted and promoted in trainings and to ensure their effective inclusion in financial decisions. 11.3.1 Ratio of land consumption rate to population growth rate Project is advocating for a model of increased productivity with neutral or preferably negative land expansion. The project is expected to reduce areas under cultivation in the four project countries while increasing produced commodities to meet the needs of these countries’ growing populations 12.1.1 Number of countries with sustainable consumption and production (SCP) national action plans or SCP mainstreamed as a priority or target into national policies Through the use of finance, the project supports political dialogues established and facilitated by UNDP in the form of national action plans. In Indonesia for instance, the project helped facilitate the adoption of the National regulation on Essential Ecosystems Zones by the Ministry of Environment and Forestry’s legal bureau. In Paraguay, the project has contributed to the formulation of the Chaco vision project between the government of Paraguay and ranchers seeking to incentivize the adoption of productivity measures in the beef sector. 15.1.1 Forest area as a proportion of total land area Project aims to establish new guidance and recommendations on lending requirements related to forest protection with the ambition to create powerful financial incentives to encourage companies to increase level of forest protection in concession and along their supply chains. 15.1.2 Proportion of important sites for terrestrial and freshwater biodiversity that are covered by protected areas, by ecosystem type Like the above, the project actively engages and advocates the financial sector for the inclusion of provisions on the management of protected areas in recommended policies and principles. The core set of recommendations will be informed by and harmonized with existing frameworks and standards to ensure a high level of consistency. 15.2.1 Progress towards sustainable forest management Through supporting new and harmonized legislation and compliance of legislation by the finance sector the project will ensure that: - capital allocation by financial institutions will take into account forest management and sustainable agriculture as key lending criteria - diversify their lending practices to include capital to sustainable productive landscapes. The project has made progress on the first area of focus by supporting legislation in Paraguay which mandates the inclusion of environmental and social governance in lending practices. We are currently working with the Central Bank of Paraguay, the Sustainable Finance Roundtable and the Ministry of Environment on a plan of implementation for this new legislation in early 2020. The project is also supporting the establishment of new funds and credit facilities that support sustainable productive landscapes, for example the new responsible soy facility in Brazil. The project is also collaborating with a number of new initiatives to harmonize the understanding of various stakeholders around the requirements for accessing these new forms of capital. 15.3.1 Proportion of land that is degraded over total land area Like the above, the project actively engages and advocates the financial sector to make better use of degraded areas as viable substitute for increased natural land conversion in recommended policies and principles. The core set of recommendations will be informed by and harmonized with existing frameworks and standards to ensure a high level of consistency. 17.14.1 Number of countries with mechanisms in place to enhance policy coherence of sustainable development Benefiting from the dialogues established by the sustainable commodity platforms spearheaded by UNDP and reinforced by the activities of GGP, project countries are expected to strengthen existing interministerial dialogue mechanisms to better address sustainable development objectives and challenges |
| --- | --- |

| Implementation Status | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | … PIR | … PIR | … PIR |

| Development Objective Rating FY | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | S |  |  |  |
| - In Paraguay, through a collaborative effort with the Government of Paraguay, UNEP FI supported research and development of a new norm mandating the integration of environmental, social and governance criteria in the financing processes of all financial institutions in Paraguay. The new standard, Norm 8, will build on existing environmental and financial legislation in the country and was adopted by the Government in February 2019. As a first step in supporting implementation, UNEP FI hosted training on basic ESG risk management with the Sustainable Finance Roundtable in May 2018. The training was well received and additional training will be developed focused on deforestation risk management. UNEP FI will continue to support the Government of Paraguay’s Central Bank, Ministry of Finance and Environments to develop a roadmap for implementation of Norm 8. We have dedicated resources to the process to ensure the continuity in the form of a needs assessment preceding the training development. We are working on signing a letter of Intent for cooperation with the Central Bank of Paraguay. This is great achievement as the Central Bank would commit to not only dedicating resources to delivery of training but also mainstreaming the training in their own curriculum at the training institute. - In Brazil, UNEP FI undertook research to better understand the gaps in environmental regulation related to deforestation and how financial institutions were complying with regulations. The result was a series of papers that identified current gaps in capacity within financial institutions to comply with the existing legislation and the requirement of enforcement of the legislation by Government. In July 2019, UNEP FI in partnership with the Brazil Banking Association FEBRABAN hosted a seminar with financial institutions and other stakeholders to discuss how financial institutions can go beyond national compliance in a changing political environmental and meet international best practice. The financial institutions expressed a need for additional tools, guidance and capacity building to support implementation of ESG risk management measures which UNEP FI will facilitate going forward. - We partnered with Forest Trends in Indonesia to develop a report that will be released October 2019 on corporate commitments to sourcing sustainable palm oil. Forest Trends developed new metrics through a number of data partnerships to track these commitments. We aim to present the findings in a webinar likely at the Roundtable for Sustainable Palm Oil in November and other events in Asia Pacific. - NGO’s, financial institutions and service providers have invested considerable resources in understanding and mitigating deforestation risk through the lending practices of banks and investors. The result has been a plethora of tools to manage risk, in order to understand how these tools are used by Banks, in particular and how capital allocation decisions are made taking into account deforestation risk, UNEP FI developed a series of technical briefs outlining deforestation risks in three key commodities, Soy, Beef and Palm oil. The briefs outlined the drivers of risk in the commodities, current tools used to assess the risk and an assessment of the tools to manage deforestation risk within financial institutions. Key changes since the last reporting period include: - While the Government of Paraguay adopted Norm 8 to mandate integration of extra-financial criteria in lending practices, the broader financial ecosystem was slow to uptake the implications of the law on their operations. We were asked by the sustainable finance roundtable and the central bank to wait a few months on the development of the training program until a stakeholder consultation process was underway and then concluded before proceeding. - In Brazil the Government has rolled back legislation regarding environmental and forestry protections, much of the environmental and financial community adopted a wait-and-see approach. Similar to Paraguay we have dedicated resources to better understanding the new regulatory scenarios in Brazil and how capacity development can continue to contribute to the application of international best practices in sustainable productive landscapes. - We commenced an early engagement in Liberia with stakeholders on component 3 of the project related to results-based payments under REDD+, due to the changing political climate many companies have since ceased operations in Liberia. We are currently collecting information and redefine our Liberia engagement approach in the coming months. - The project has made very positive headway in Indonesia by securing a partnership with the IKBI secretariat that gives a clear mandate to UNEP FI to provide leading banks with techniques and models to lend more sustainably. This engagement will be the first opportunity the project has to train the sector in more sophisticated, more quantitative methods of land use assessment. - The situation in Liberia has recently deteriorated, as indicated by the decision from Sime Darby, one of the largest palm oil trader and processor and an instrumental project partner, to leave the country and sell their concessions. This is expected to detrimentally affect the project by rendering the activities of the Production team increasingly difficult to implement. It echoes repeated warnings by the IFC that they cannot carry out any activity in Liberia due to the absence of companies and financial institutions in position to satisfy the IFC’s performance standards. As a result of this increased instability, UNEP FI has decided to postpone most of the activities intended to be carried out during the current reporting cycle and will re-evaluate the situation at the end of 2019. |  |  |  |  |  |

| Implementation Progress Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | S |  |  |  |
| The key progress made in the GGP Transaction project has been manifold: - Building a base of dedicated stakeholders in each of our partner countries to roll out the implementation of the project. In Paraguay we’ve identified and secured commitments from the Central Bank of Paraguay and the Sustainable Finance Roundtable as key project partners for the implementation of the training program. - Identifying the key gaps and synergies in regulation related to deforestation risk management in Brazil and Paraguay, this resulted in a series of papers and in the case of Paraguay (legislation) that was widely discussed. In Brazil we held a breakfast roundtable with the FEBRABAN to discuss the published findings. This work will help lay the foundation for work on public and private economic instruments in each of our partner countries. - Regarding progress on components 2- ESG Risk tools, we discussed the development of the decision support tool with a number of NGO’s such as World Resources Institute, Proforest and Global Canopy on how to operationalize a toolkit and the potential for partnership with one or more of these organizations. Proforest is working on a proposal, this would leverage the work that Proforest undertook for WWF US on the Soy Buyers toolkit under the Demand Child project. - During a mission to Brazil and Paraguay we identified project partners for the implementation of component 3 on fiscal and other economic incentives. In Brazil we are in discussions with BVRio and CEBDS, the Brazilian Chapter of the WBCSD to jointly deliver a project through the Brazilian Coalition for Forest, Climate and Agriculture which convenes key players from industry (commodity traders), finance sector and NGO’s around sustainable agriculture issues. - Establishment of an engagement strategy in Indonesia in support of the implementation of the project’s activities Key Challenges related to the need to taking a wait and see approach in many countries where we are aiming or ready to implement the project, political climate, changing regulation and economic considerations mean that we need to adjust the planning and engagement strategy to better align with the local needs and capacities. |  |  |  |  |  |

| Risk Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | M | L |  |  |  |
| In 2018 the PIR reported that most internal and external factors are rated as Medium. The project team is now in place so most of the internal risk factors are reduced. However, the external factors need to be monitored, e.g. how to mitigate the effects of volatile political commitment on delivering results. Since the last PIR report a number of actions have been addressed to mitigate the risk, including: - Hiring local consultants to facilitate the implementation of the project, this will aid in the monitoring of the political and regulatory conditions, which continue to change in countries like Paraguay, Brazil and Liberia. - The other external factor reported was environmental conditions, this may impact the project indirectly through volatile commodity prices, stranded assets within the portfolio of a financial institution and increased regulation and pricing of ecosystem services. |  |  |  |  |  |

| Stakeholder engagement | During the last year tremendous efforts and progress was made in establishing a strong network of stakeholders for project support and implementation. In Paraguay, Brazil and Indonesia we’ve: - secured the buy-in and participation of the national sustainable financial associations - Identified sustainable finance workstreams at the local level to contribute to such as the Brazilian Finance Lab supported by GIZ - Engaged with national and local NGO’s and financial institutions to continue to develop the work program of the project. - In Paraguay we will be leading a national process of stakeholder engagement on the implementation of Norm 8 in collaboration with the Central Bank - In Brazil we aim to hold regular roundtable discussions on topics of relevance for the finance sector on deforestation risk. We held the first event on July 5th at the FEBRABAN. Some of the challenges include: - Perceived competition on delivering similar workplans by local stakeholders (after in-depth engagement the perception is mitigated). - Lack of capacity by local stakeholders to engage with the project, capacity can include lack of staff, lack of mandate and lack of financial resources. |
| --- | --- |

| Gender mainstreaming | Gender mainstreaming is being achieved through two mutually reinforcing channels: - An active contribution, both from a substantive and programmatic perspective, to the preparation of the first gender-focus GGP knowledge management product aimed at offering lessons and best practices to operators interested in promoting gender considerations alongside the adoption of best sustainability practices in their supply chains. The role of finance as a catalyst for gender equality and inclusiveness has been highlighted. - An active attempt to achieve gender parity in the project execution, by placing a strong emphasis on ensuring representation and visibility of women, both in the activities and in the governance and management structures of the project. - We are planning to develop a gender specific module to be integrated into our country training program. |
| --- | --- |

| Knowledge activities and products | In 2019 we produced a series of knowledge products namely: - series of papers examining environmental regulation in Brazil, the final paper in the series resulted in a published briefing note on the implications for the finance sector. We discussed the outcomes in a breakfast roundtable hosted by the FEBRABAN on July 5th in Sao Paulo, Brazil. - We also developed a series of papers that served as background to the drafting and adoption of Norm 8 in Paraguay (new regulation on integration of extra-financial considerations in lending). - We are in the midst of planning for a webinar in November or December 2019 that will provide an overview of financial mechanisms and credit facilities that financial institutions can contribute to. It is hoped that this discussion will spur the harmonization of approaches, enable capacity development among beneficiaries of these funds and highlight key challenges in accessing capital. We will partner with Conservation International, BV Rio and WWF to deliver this. |
| --- | --- |

| Stories to be shared |  |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To strengthen the financing environment for sustainable commodity production through design and pilot sustainable commercial transactions and risk management tools |  |  |  |  |  |  |
| Outcome 1: Outcome 2.1: Increased funds (loans and investments) subjected to enhanced deforestation risk policies | 1. 2.1.1 20 Financial Institutions / 0Investors trained using risk management tools that reduce deforestation | 0 |  |  |  |  |
|  |  |  | 5 | 20 | 8 FIs engaged in Indonesia under the leadership of the IKBI initiative | S |
|  | 2.1.2 Technical capacity and operational modalities established among 50 financial institutions with significant deforestation exposure to implement Deforestation-Free, Zero Net Deforestation or equivalent policies | 0 | 20 | 50 | No bank has been formally trained yet but infrastructures (including relay partnerships) have been established to facilitate and leverage the delivery of the training programs in Brazil, Paraguay and Indonesia | MS |
|  | 2.1.3 Provide guidance, tools and capacity building for effective application of major new emerging markets | 0 | 2 toolkits (Paraguay and Brazil) | 4 toolkits (Paraguay, Brazil, Indonesia and Liberia | 2 comprehensive reports with roadmap and practical best practices have been produced, for Brazil and Paraguay | S |
| Outcome 2: Outcome 3.1: Increased public incentives and public and private financing for reduced deforestation practices | 3.1.1 Production country analyses developed on fiscal incentives, including those targeting smallholders | 0 | 3 analyses (Paraguay, Brazil and Indonesia | 4 analyses (Paraguay, Brazil, Indonesia and Liberia), including sensitization and outreach | No activity undertaken to date, as a response to the rapidly evolving political conditions, which require to revisit our assumptions on the existing political support for these activities | MS |
|  | 3.1.2 Assessments on how to reinforce linkages between reduced deforestation commodity production and REDD+ national programs | 0 | 2 analyses (Paraguay and Brazil) | 4 analyses (Paraguay, Brazil, Indonesia and Liberia), including sensitization and outreach | 3 reports finalized: - one global report produced looking at the GCF RBPs window, in its capacity of first operational RBP instrument. - one report documenting best practices and important considerations in the context of GGP production countries planning to leverage RBPs to bring their activities to scale. - A third report taking stock of REDD+ opportunities in Liberia for commercial activities linked to drivers of deforestation | S |
|  | 3. |  |  |  |  |  |

Overall rating of project progress towards meeting project Result(s)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | S | At the time of the previous PIR, project had been crippled by administrative and financial issues that resulted in significant delays in the delivery of the activities. At the time of this PIR, UNEP FI’s project management was able to catch up on the delayed activities and has managed to successfully establish partnerships and relays in the countries that will lay the foundation for an increasingly efficient and streamlined delivery of the project’s results. In Paraguay, Brazil and Indonesia, the project can now count on the support of key institutional stakeholders (Central Bank in Paraguay, Febraban in Brazil and IKBI in Indonesia) to sensitize and promote the project’s products. Therefore, UNEP FI’s aim to strategically seek out collaborations with carefully selected partners is likely to pay off in the form of increased visibility and legitimacy, which should give longevity to the project and increase its chance to achieve the target outcomes. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | In a shifting political landscape in some of our project countries, some of the core areas of work identified will need to be refined based on the new political realities. | Work programme should be sufficiently flexible to adjust to changes in the political, institutional and economic contexts of each country. Greater latitude and importance should be given to the mechanism of budget revision to institutionally recognize the need for project of this size to be agile and reactive. Adjustments to the work programme should be tabled with the TM and/or the PSC. |
| on stakeholder engagement | Local stakeholders have different set of timelines and priorities than UNEP FI, we often rely on these stakeholders for the implementation of the project. | Ensure that outputs/deliverables are well embedded in stable and recognized organizations who have the mandate and legitimacy to carry the work forward |
| on gender actions | Need to understand the gender linkages to workstreams that don’t easily lend themselves to gender mainstreaming, eg: fiscals incentives, environmental policy reviews, etc. | Work collaboratively with the other child projects to better understand how finance can directly and indirectly influence gender mainstreaming in production supply chains. Most probable scenario is that finance is an underlying driver, which can foster the adoption of best gender practices by providing appropriate incentives at scale |
| on safeguards | Safeguards need to be integrated into the financial products that we will develop, developing new safeguard systems for each financial product is time and resource intensive. | The project seeks an active collaboration with the Land Use Finance Unit at Ecosystems, which houses a dedicated team of safeguards experts with emerging expertise on E&S frameworks for sustainable finance facilities (BNPP’s Tropical Landscape Finance Facility, Rabobank’s Agri3), to benefit from their insights and advices. By relying on new sectoral standards, it will ensure time and resource effective application of safeguard principles across products |
| on delivering GEF Core Indicators | No problem/risk identified to date |  |
| on delivering of PoW EA | No problem/risk identified to date |  |
| on sustainability of results | Key risk is the development of financial products that align with the new production models initiated by the production child project. This is an issue of timing of development and harmonization. | Project’s workplan has been sequenced to address and mitigate this risk, by deploying capacity building activities laying the foundations upon which more technical and sophisticated interventions can be built. The aim is to align it with the work of the Production team and in particular with the validation of new production systems to ensure that the financial products have clear investment prospects. |
| others |  |  |

  - Rating of progress implementation towards delivery of outputs

| Outputs |  | Expected date of delivery |  | Implement-ation status as of 30 June 2018 (%) | Implement-ation status as of 30 June 2019 (%) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 2.1: Increased funds (loans and investments) subjected to enhanced deforestation risk policies |  |  |  |  |  |  |  |
| Output 2.1.1: 20 Financial Institutions / Investors trained using risk management tools that reduce deforestation |  |  |  |  |  |  |  |
| Activity 1: Design of a deforestation hazard model |  | 2019 |  | 0% | 5% | We’ve had dialogue with organizations such as Global Canopy Programme to explore collaboration around development of Value at Risk models. | MS |
| Activity 2: Development of a vulnerability model for the supply chain |  | 2020 |  | 0% | 15% | A prototype model has been in development for Indonesian palm oil and has been benefited from several rounds of consultations. | S |
| Activity 3: Development of a toolbox to allow FIs, companies and governments to integrate this new risk type into their risk management processes |  | 2021 |  | 0% | 0% |  | N/A |
| Activity 4: Coordinating outreach efforts and engagement with supply chain stakeholders to disseminate the models’ results |  | 2020 |  | 0% | 0% |  | N/A |
| Activity 5: Engage with FIs and ESG experts to explore options to integrate the new risk class into existing ESG tools. |  | 2021 |  | 0% | 25% | FIs engaged in Indonesia through a partnership with WWF Indonesia, which hosts the IKBI initiative. Similar engagement processes are underway in Brazil (Febraban) and Paraguay (Sustainabe Finance Roundtable). Coordination established with the ESG workstream to explore modalities of integration. | S |
| Activity 6: Train financial institution on how to use the tool and on how to incorporate deforestation risk in their risk models |  | 2020 |  | 0% | 0% |  | MS |
| Output 2.1.2: Technical capacity and operational modalities established among 50 financial institutions with significant deforestation exposure to implement Deforestation-Free, Zero Net Deforestation or equivalent policies |  |  |  |  |  |  |  |
| Activity 1: Develop a brief describing current limitations and gaps of current ESG integration strategies as they relate to the inclusion of deforestation risk |  | Q4 2018 |  | 15% | 100% | Developed a concept note, brief and presentation outlining state of current ESG tools, gaps and needs to integrate deforestation in ESG risk management at the product level for banks. | S |
| Activity 2: Develop a toolkit for financial institutions to support the implementation of deforestation risk across their organization |  | Q1-2 2020 |  | 0% | 25% | Currently working on framework paper that would outline the key components of the toolkit | S |
| Activity 3: Develop practical deforestation risk implementation strategies for a selection of financial products |  | Q3 2020 |  | 0% | 25% | This is related to the training under 2.1.1, we aim to develop a series of modules that will help banks with their implementation strategies on deforestation risk. | S |
| Output 2.1.3: Provide guidance, tools and capacity building for effective application of major new emerging markets |  |  |  |  |  |  |  |
| Activity 1: Perform a stock-taking analysis of the legal, regulatory and policy frameworks determining roles and responsibilities of the financial sector in relation to deforestation risk |  | Q4 2018 |  | 0% | 100% | Completed for Brazil and Paraguay. Ongoing in Indonesia | S |
| Activity 2: Carry out a gap analysis highlighting policy and legal areas necessitating greater harmonization and alignment |  | Q4 2018 |  | 0% | 100% | Completed for Brazil and Paraguay | S |
| Activity 3: Develop roadmaps for the financial sector on best way to comply with existing/new laws and policies |  | Q1 2019 |  | 0% | 100% | Completed for Brazil and Paraguay | S |
| Output 2.1.4: New financial products supporting the production of reduced deforestation commodities identified and their potential role in funding the transition to zero-deforestation commodity production clearly delineated |  |  |  |  | Output has been reintroduced for this reporting cycle after discussion with IFC that led to an agreement that the activity was meant to be delivered jointly. However, no transfer of funds between the organization is expected and UNEP FI is envisioned to have a limited and technical contribution (centered on leveraging resources of UNEP-supported sustainable finance facilities) Project team will seek approval for this reintroduction at next Steering Committee |  |
| Activity 1: Facilitate the identification of innovative financial products and services supportive of the work of the IFC |  | Q2-Q4 2020 | 0% | 0% |  | MS |
| Outcome 3.1: Increased public incentives and public and private financing for reduced deforestation practices |  |  |  |  |  |  |  |
| Output 3.1.1: Production country analyses developed on fiscal incentives, including those targeting smallholders |  |  |  |  |  |  |  |
| Activity 1: Conduct scoping study analysing current fiscal policies and their potential to support shift to zero-deforestation commodity production |  | 2020 |  | 0% | 0% |  | N/A |
| Activity 2: Facilitate governmental dialogue on the establishment of progressive fiscal policies aligned with zero-deforestation commodity production objectives |  | 2020-2021 |  | 0% | 0% |  | N/A |
| Output 3.1.2: Assessments on how to reinforce linkages between reduced deforestation commodity production and REDD+ national programs |  |  |  |  |  |  |  |
| Activity 1: Develop a set of guidelines clarifying eligibility criteria for receiving REDD+ Results-Based Payments |  | Q4 2018 |  | 0% | 100% | Two papers drafted, survey sent out to GGP projects and paper drafted resulted in criteria for RBP’s | S |
| Activity 2: Contribute to the formulation of sustainable commodity production models compatible with REDD+ Results-Based Payments |  | Q3 2020 |  | 0% | 0% |  | N/A |

Overall project implementation progress :

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | S | The project team made good progress on catching up on the initial delays. Most activities are now back on track or can be expected to be delivered on time. The key progress made in the GGP Transaction project has been manifold: - Building a base of dedicated stakeholders in each of our partner countries to roll out the implementation of the project. In Paraguay we’ve identified and secured commitments from the Central Bank of Paraguay and the Sustainable Finance Roundtable as key project partners for the implementation of the training program. - Identifying the key gaps and synergies in regulation related to deforestation risk management in Brazil and Paraguay, this resulted in a series of papers and in the case of Paraguay (legislation) that was widely discussed. In Brazil we held a breakfast roundtable with the FEBRABAN to discuss the published findings. This work will help lay the foundation for work on public and private economic instruments in each of our partner countries. - Regarding progress on components 2- ESG Risk tools, we discussed the development of the decision support tool with a number of NGO’s such as World Resources Institute, Proforest and Global Canopy on how to operationalize a toolkit and the potential for partnership with one or more of these organizations. Proforest is working on a proposal, this would leverage the work that Proforest undertook for WWF US on the Soy Buyers toolkit under the Demand Child project. - During a mission to Brazil and Paraguay we identified project partners for the implementation of component 3 on fiscal and other economic incentives. In Brazil we are in discussions with BVRio and CEBDS, the Brazilian Chapter of the WBCSD to jointly deliver a project through the Brazilian Coalition for Forest, Climate and Agriculture which convenes key players from industry (commodity traders), finance sector and NGO’s around sustainable agriculture issues. - Establishment of an engagement strategy in Indonesia in support of the implementation of the project’s activities |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Stakeholder risks (needing to harmonize across different workstreams in country) | Increased resource allocation to country activities (recruitment of country focal points in charge of managing and harmonizing stakeholder engagement). Consolidation of partnerships with key institutional actors to ensure appropriation and adoption | UNEP FI | 2019 |
| Emerging developments in ESG risk management and necessity to integrate risk management tools into our training program | Programmatic and operational integration of ESG risk activities into training programs rendered possible by the fact that oversight is performed by same project manager | UNEP FI | 2019 |
| Political risks (adopting a wait and see approach in Brazil, Indonesia and Paraguay regarding our fiscal incentives work) | Work program deployed according to a timeline that reflects changes in exposure to the political risks and which enables project managers to adjust the project’s structure | UNEP FI | 2019 |
| Procurement delays (hiring consultants in shallow talent pools) | Whenever possible, attempts are made to leverage the network and reputation of our country partners to alleviate some of the identified recruitment challenges | UNEP FI | 2019 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Limited appetite from individual financial institutions in target countries to adopt more stringent environmental and social risk management systems given perception that they will be at a competitive disadvantage | Work closely with banking associations and financial regulators in target countries, such as Febraban in Brazil and OJK in Indonesia, to promote industry wide uptake of risk management systems that consider deforestation in commodity production. Develop shared, pre-competitive tools to enable transparency, better decision-making and a more level playing field in FI management of deforestation and other risks. | Mitigation proposed at CEO approval is taken up and implemented with great intermediate results, ensuring active engagement and meaningful participation from key financial institutions | CEO: L to M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Evidence of corruption practices that can complicate the deployment of our theory of change by creating substantial transactions costs, hindering our push for transparency and redirecting investments towards non-vetted activities | This can be mitigated by working with financial institutions with strong commitment to fully transparent operations, robust and enforced internal safeguards and stated anti-corruption policies. We expect a strong correlation between a FI’s sensibility towards the issue of deforestation and its application of high standards of anticorruption compliance, for the simple reason that the two are elements of best-in-class operational practices. Risk of corruption in the different production supply chains will be addressed by the Production Child Project. | By design and necessity, project has complied with recommended mitigation actions, which has until now ensured the project is insulated against cases of serious corruption practices and scandals. | CEO: L to M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| With respect to the value at risk model, companies and financial institutions may not be willing to contribute and share business sensitive data | This can be mitigated by signing non-disclosure agreements with relevant actors (with anonymized data sets; or encrypted data), and communicate to companies and financial institutions about previous non-disclosure agreements carried by UNEP FI with financial institutions as well as by the methods used by Forest Trends to receive and store sensitive company data. Other modes of data collection (anonymized data sets) and results dissemination can also be explored, which leverage the tool but are less reliant on proprietary company data. | Proposition mitigation action is intended to be taken. At this stage of the project, considering this part of the work has yet to be undertaken, it is impossible to predict how financial institutions will react to the proposal to sign NDAs | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| With respect to the work on financial regulation – limited interest from financial regulators in examining what are the regulatory levers that can contribute to remove deforestation from supply chains. | Work with the UNEP Inquiry to build on the momentum created they have created for placing sustainability issues into the agenda of financial regulators. Leverage WWF’s recently signed partnership with OJK, the Indonesian financial super-regulator. | Given that the Inquiry mandate wasn’t renewed, and that the inquiry no longer operates with the structure and capacity it had when the mitigation plan was formulated, the proposed mitigation strategy had to be revised. To alleviate risks, project has decided to forge direct partnerships with the institutions engaged in the work of the Inquiry, which has ensured continuity and provided increased visibility and legitimacy for the project (in comparison to a scenario in which the Inquiry would have continued to play an intermediary role) | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| With respect to the work on fiscal policy limited interest from ministries of agriculture and finance in examining and addressing deforestation issues | Work closely with the production child project to ensure that fiscal incentives are placed on the agendas of the National Commodity Roundtables created and to the attention of relevant policymakers early on in the process. | Recommendation has been taken up and integration has been sought with UNDP to capitalize on the agendas of the National Commodity Roundtables. However, heightened general political instability has materially increased the risk that these agendas don’t get politically supported past the design stage and never reach implementation. Internal risk factors are well mitigated, while external risk factors receive adequate monitoring. | CEO: M to H |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Corporate Reneging on Sourcing Commitments - Lack of progress on sourcing targets at the corporate level leads to revision or backsliding on stated sourcing goals, limiting producer/supply chain/FI interest in financing opportunities associated with the program | Work closely with both Production and Demand teams on timely support to program partners so progress is made. Continue to build on early momentum of BEI, RSPO’s FITF, and PRI’s Oil Palm Working Group to promote the agenda. Work closely with research institutions to demonstrate the value of adopting standards/best practices from an economic, environmental and social standpoint. | Recommendation implemented through the work of the AML child project, which has been seeking to ensure effective and operational integration between the project’s child projects through the use of dependency workplan across components. It remains that companies have expressed difficulties in achieving their target commitments as a result of interplaying internal and external factors. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Prolonged Commodity Downturn – The cyclical nature of commodities will often result in periods where commodity pricing/margins are low and investments from corporates in sustainability sourced commodities are reduced. | Improving the business case for adoption of best practices will often lead to cost savings, productivity improvements that in turn make producers more resilient to price fluctuations and more bankable. | Business case has yet to be made for scenarios of significant market downturn, especially as adoption of best practices hinges on capacity to free up additional resources for upfront investment, which is rendered increasingly difficult during periods of low profitability. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Operational/Staffing Risk – Finding the right blend of skills for the teams that will design the different components of the project | Identify appropriate staff and consulting resources during the project preparation in the key regions, Africa, Asia and Latin America. | Project has made changes to its HR strategy to increase the importance of country staff. Where resources were difficult to acquire, project has sought partnerships with well-regarded and reputable organizations to increase its attractiveness vis-à-vis the pool of desirable candidates. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | With the PM team now in place, various mitigation measures were implemented, and internal risks are mostly at a low level. However, various external factors need to be monitored and mitigation measures be planned for. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM : The integrated nature of this project and the sheer number of involved organizations have resulted in early coordination issues that are in the process of being sorted out. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Project coordination has improved |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : Overall Steering Committee is firmly in place and comprised of the people who have designed the project, which ensures until now stability and credibility in the formulation of the overall strategy for the project. A specific transaction child project Steering Committee will be established soon. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Coordination is made easy by the supportive and cordial nature of the exchanges between people involved in the GGP. There is a productive sense of trust and respect between all parties that has promoted a collegial approach to solving problems | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: Project has almost fully caught up on workplan, although it has required to make several modifications to the original plan, to respond to changes in the political and socio-economic contexts (e.g. Brazil) and to better recognize the operational demands of running a comprehensive training program in three countries. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: SECO has committed more than half of their pledge | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: Small budget revision was necessary to reflect changes in country conditions as well as changes in the potential applicability of certain key mechanisms (i.e. REDD+). The revision was however prepared proactively and didn’t affect the progress of the project |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: Funds are transparently managed and in accordance with presented and approved budget. Revisions and requests for cash allocation have been done in compliance with the organization’s rules and procedures | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: Against the backdrop of an increase in the amount of information demanded and several changes in the reporting format, information provided has consistently remained substantive, comprehensive, accurate and transparent. In the future, we note a need to prepare reports earlier to fully satisfy the project’s reporting deadlines. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: As indicated repeatedly above, the project has made an conscious decision to strategically concentrate on stakeholder engagement, with visible and positive results. We do not anticipate a decrease in the level nor the quality of that engagement for the foreseeable future | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: Project is paving the way for an heightened communication effort in 2020, permitted by the combined effects of the engagement strategy mentioned earlier and the availability of more substantive KM products to feed our communication strategy. However, and as a result of that strategy, communication didn’t deliver concrete evidence commensurate with the size, scope and ambition of the project over this reporting cycle | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: While short-term tactical decisions are being made on a regular basis to ensure the greatest adoption by stakeholders and alignment with changing priorities of the countries, project’s core objective remains to achieve long-term (and lasting) transformation of the sector, which is why the project is concentrating on actions which can have a long-lasting influence (one evidence is the mandatory training program developed with the Central bank of Paraguay and aimed to be used for years to come by the local banks) | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: Project benefits from its proximity, physical as well as programmatic, to the UNEP Land Use Finance team, who has been able to provide useful and practical insights on technological innovation in the fields of remote sensing, satellite imagery and carbon accounting. The project will also soon rely on the expertise of the World Conservation Monitoring Center and build on its recognized experience in ecosystem management and natural capital assessments | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: This is perceived as one of the project’s largest risks, mostly as a result of the political change in Brazil, which has provided signs of dwindling interest in the protection of its forest assets. However, project benefits from a natural hedge, since the financial sector continues to be committed to making their business more sustainable. Even in Brazil, the interest Febraban and their members have demonstrated towards the project has not abated in the wake of the new government | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; however, political volatility has already caused some delays and mainstreaming efforts from the public to the private sector and vice versa might be negatively affected. |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  |  | X |  |  |  | PM: Political context is increasingly volatile, with a marked rise in nationalistic, isolationist platforms, which may encourage politicians to concentrate on short-term strategies at the expense of more long-term objectives, including environmental ones |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: Paraguay and Brazil have suffered from unprecedented forest fires, which have irremediably damaged the ecosystems that the project is trying to protect and improve. While the extent of the losses is not yet clear and will necessitate to be jointly assessed with the Production child project, it will likely have an impact on future policies and the type of investments the project recommends going forward (Ex: zero-deforestation vs. reforestation) |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: There are no evident social, cultural and/or economic issues that may affect project performance and results, given that the financial sector is the project’s primary target group | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | X |  |  |  |  |  | PM: No capacity issue in the three countries in which the project has operated this year. Liberia, which hasn’t been fully activated, remains the biggest question mark. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| M | L | Due to the adoption of a mitigation plan, revolving around a strategic and voluntary engagement process with key institutional stakeholders and the proactive monitoring of political and institutional changes in the countries (permitted by the recruitment of country focal points), the risk profile of the project has materially diminished and should stabilize, provided that the macroeconomic conditions don’t deteriorate further. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs and activities as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

Provided by GEF Task manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.