WWF GEF Agency

Project Implementation Report

Lake Naivasha Ecosystem Based Management (GEF ID 10755)

Project Report information:

| Report Author(s) | Peter Scheren, Astrid Breuer |
| --- | --- |
| Report Completion Date | September 15, 2025 |

| 1. General Information | PIR Submission Date | September 15, 2025 |
| --- | --- | --- |
|  | Agency Approval Date | June 1, 2023 |
|  | Fiscal Year | FY25 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 1st PIR |
| 2. Current Year Ratings | Overall DO rating | U |
|  | Overall IP rating | U |
|  | Overall Risk rating | L |
| 3. Key dates | Actual Implementation Start Date | March 21, 2024 |
|  | First Disbursement Date | September 30, 2025 |
|  | Expected Mid-Term Review Date | NA |
|  | Expected Completion Date | December 31, 2027 |
|  | Expected Financial Closure | December 31, 2027 |
|  | Actual Completion Date |  |
| 4. BUDGET | Total Project Budget (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | $ 1,785,422 |
|  | Total GEF disbursement (USD) through June 30 of the FY for project that has been in implementation for at least 1 FY (Please indicate amounts under GEF Trust Fund, LDCF, and SCCF) | $ 513,210.6 |
|  | Committed Co-finance | $10,525,689 |
|  | Materialized Co-finance | $ 4,000 |

PMU Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| NETFUND Project Manager | Michael Okok | michael.okok@netfund.go.ke |
| Project Coordinator / Food Systems Specialist | Alfred Asengi | Alfred.asengi@netfund.go.ke |
| Monitoring, Evaluation and Learning (MEL) Officer / Safeguards specialist | Andrew Cheboi | andrew.cheboi@netfund.go.ke |
| Finance and Operations Officer | George Luke Nyamai | george.luke@netfund.go.ke |
| Field Officer - Community Engagement and Gender | Isaac Soita | isaac.soita@netfund.go.ke |

WWF GEF Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Astrid Breuer | astrid.breuer@wwfus.org |
| Project Supervisor | Peter Scheren | pscheren@wwfint.org |
| Safeguards and Gender Specialist | Edmond Odaba | edmond.odaba@wwfus.org |
| M&E and RBM Specialist | Amelia Kissick | amelia.kissick@wwfus.org |

Instructions:

The WWF GEF Project Manager is responsible for completing the PIR in coordination with the Project Management Unit. It may be necessary to consult with other experts for current data (e.g. Safeguards, Gender, RBM, etc). Please include the following annexed documents:

- Completed Tracking Tool with Results Framework and Annual Work Plan and Budget Tracking (for project year)

- Tracking tools (eg. METT), if applicable

- Knowledge Management products (if links were not provided in the section directly)

- Other supporting documents: meeting minutes, stakeholder consultation, photos, maps, reports, etc.

### Ratings

Fill in all ratings based on the Rating Scale provided in Annex I.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year X |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development Objective | U |  |  |  |  |  |  |
| Implementation Progress | U |  |  |  |  |  |  |
| Risk | L |  |  |  |  |  |  |

Justification for Current Year Ratings:

Delays in administrative sign-off of the grant agreement, as well as lengthy PMU recruitment process, resulted in considerable delays in project start-up. However, with the PMU fully confirmed from 1 April 2025, the team expects no further delays. The project achieved 100% of the indicator targets of the Results Framework in Y1 (mainly relating to reporting and communication events). However, as in reality project activities are only just in start-up phase, the performance of the project against its objectives is considered Unsatisfactory. Most of the indicator targets originally planned for Y1 of the project were shifted to Y2 for the reasons mentioned above. Based on 27% achievement of the AWPB targets in Y1, the rating is U. The targets that were not achieved due to delays in signing the Project Agreement, setting up project accounts and in the recruitment of the PMU. The Risk rating is considered low on average, despite three residual risks that are rated as medium (these are: the ability to mobilize to raise adequate financial resources for the PES scheme, the impacts of climate change and the risk of unwanted infrastructure developments in the project landscape). All other risks are mitigated are reduced to low level.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

Progress: The project activities only started up in earnest in April 2025 as the PMU was only fully recruited in March 2025. Activities undertaken and completed in year 1 are limited to recruitment of the PMU, the development of an AWPB, mandatory progress reporting, and three stakeholder consultation workshops held as part of the project launch preparations (see further below). Challenges: - Recruitment of the desired project management unit team took longer than planned. NEFTUND had to re-advertise the position of the project coordinator to attract a suitable candidate for the position. Overall, the PMU recruitment process took approximately 6 months. Outcomes: - Buy-in of the government and political leadership, basin stakeholders and local community following the official launch of the project and successful inception workshop (April 2025). The project aligns with both national environmental strategies and county-level development plans, ensuring institutional support and sustainability - There is a committed Technical Advisory Committee providing guidance on project implementation, with membership of the key project partners and community organizations: Kenya Forest Service, National Environmental Management Authority, the County Governments of Nyandarua and Nakuru, Lake Naivasha Basin Umbrella Water Resource Users Association, Lake Naivasha Basin Riparian Association, Lake Naivasha Growers Group, Njambini Farmers Training Centre and Lake Naivasha Basin Landscape Association. The Committee met one time during the reporting period, for an inception workshop on 15th April 2025. - NETFUND has developed and operationalized key policies, including Environmental and Social Safeguards (ESS), Gender Policy, Grants Management Manual, and a Grievance Redress Mechanism. During the inception workshop, further steps were discussed to ensure compliance with WWF/GEF agency’s ESSF and Gender policies.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

The main stakeholder engagement activity undertaken was the official launch of the project, including three preparatory stakeholder meetings. The Project was launched in April 2025 through a public forum with the objective of sensitizing and securing stakeholders’ buy-in and support for the project objective and particularly the integrated landscape management in Lake Naivasha Basin (LNB). This was a high-level event with participation of the Cabinet Secretary for Environment, Climate Change and Forestry, governors for the county governments of Nyandarua and Nakuru counties, Principal Secretary for the State Department of Environment and Climate Change, and leaders of the Civil Society Organizations and local communities. A total of 395 participants attended the launch where males made up to 68% while females were 32%. Key outcomes of this engagement include commitment by political leadership and local communities to support the initiative.

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

Completion date for the gender assessment gender action plan: 16 /12 /2022. Summarize progress, challenges, and/or outcomes: The project management unit was sensitized and trained on the gender responsive implementation of the project during an inception training session with WWF GEF Agency’s Gender and Safeguards Specialist. To date, the key challenge related to gender has been the low participation of women and youth in stakeholders’ engagement forums held so far, a result of the male dominated leadership of many organizations in the region. This will require a deliberate affirmative action to encourage participation of these critical groups through targeting female representatives for meeting invitations and other forms of stakeholder engagement.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

Aside from the stakeholder engagement sessions mentioned above to increase project awareness, no knowledge activities were included in the Y1 workplan. In Y2, it is expected that knowledge sessions on the main components of work (ILM, sustainable agricultural practices, restoration) will be organized as part of the capacity building efforts of the project.

### Reflows (for NGIs only)

Note: This field is not publicly disclosed.

N/A

### Adaptive Management

Please check all applicable modifications made to the project during this reporting period noting a description of the change, justification for the change and the date of No-Objection given by the WWF GEF Agency. If not applicable, please leave blank. Please see guidance on definitions and procedures for Major and Minor Amendments. Note: it is recommended that all changes be discussed in advance with the GEF Program Manager. Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☒ Results framework; Majority of Y1 indicator targets were shifted to project Y2.; Delays in project start-up due to grant agreement signature and PMU recruitment resulted in limited time for PMU to carry out activities on the ground.; April 30, 2025. ☐ Components and cost. ☒Institutional and implementation arrangements; Replacement of Imarisha Lake Naivasha by National Environment Management Authority to lead on Component 1 of the project; Imarisha Lake Naivasha has seized to exist due to non-support by the Government. After a comparative analysis, the National Environment Management Authority was selected by NETFUND, after a thorough assessment of options, to replace Imarisha, with the support of the Lake Naivasha Riparian Association for the facilitation of stakeholder engagement.; 8th May 2025. ☐Financial management. ☐Implementation schedule. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☐ Safeguards. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other: <fill in>. For any proposed or anticipated changes to the project this coming year, please describe below what those changes would be (e.g., in the workplan or results framework) and provide justification. Note: It may be helpful to reference project lessons, challenges, strengths and/or the project theory of change.

### Geolocation Information

Please provide a location name, latitude and longitude for key locations of GEF-financed activities. Depending on the scope of the project, it may only be necessary to provide geolocation of the capital city. The format should be in Decimal Degrees WGS84 format only – e.g. not degrees, minutes or seconds. Please use ‘-‘ instead of ‘S’ and avoid inserting ‘°’). As an alternative, you may enter a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide for additional details. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Kenya Wildlife Training Institute; -0.740899; 36.431851; Hippo Camp; Project launch event on the shores of Lake Naivasha.

Annex I: Rating Scales and Guidance

### Development Objective Rating

The project Development Objective (DO) rating is quantified by analyzing progress against the Results Framework according to the rating scale below. Note that the average is not taken across component averages, but rather across all indicators in the Results Framework. No percent achieved should surpass 100% even if the target is exceeded.

DO Rating scale

| Rating | % Achievement of Results Framework targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100% |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate DO Rating from Results Framework

| Objective/Component/ Outcome | Indicator | Unit | Target Y1 | Achieved Y1 | Percent achieved Y1 |
| --- | --- | --- | --- | --- | --- |
| Project Objective | Indicator 1 | # policies | 5 | 4 | 80 |
|  | Indicator 2 | # ha | 1,000,000 | 900,354 | 90 |
| Component 1 |  |  |  |  |  |
| Outcome 1.1 | Indicator 3 | # beneficiaries | 500 | 410 | 82 |
| Outcome 1.2 | Indicator 4 | # sites | 10 | 12 | 100 |
| Component 2 |  |  |  |  |  |
| Outcome 2.1 | Indicator 5 | % score | 80% | 75% | 93.75 |
| Average of total |  |  |  |  | 89.15 |

### Implementation Progress Rating

The project Implementation Progress (IP) rating is based on progress against the annual workplan, based on the rating scale provided below.  Note that the average is not taken of the component averages, but rather across all indicators in the workplan. No percent achieved should surpass 100% even if the target is exceeded.

IP Rating scale

| Rating | % Achievement of annual workplan targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100 |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate IP Rating from AWP&B

| Project Activities Y1 | Unit | Target | Achieved | Percent Achieved |
| --- | --- | --- | --- | --- |
| Component 1 |  |  |  |  |
| Activity 1.1.1 | Sites | 5 | 4 | 80 |
| Activity 1.1.2 | Households | 120 | 122 | 100 |
| Average Component 1 |  |  |  | 90 |
| Component 2 |  |  |  |  |
| Activity 2.1.1 | Plans | 6 | 5 | 83 |
| Activity 2.1.2 | Reports | 2 | 2 | 100 |
| Activity 2.1.3 | Proposals | 10 | 7 | 70 |
| Average Component 2 |  |  |  | 84.3 |
| Component 3 |  |  |  |  |
| Activity 3.1.1 | Trips | 2 | 0 | 0 |
| Activity 3.1.2 | Trainings | 4 | 3 | 75 |
| Average Component 3 |  |  |  | 37.5 |
| Average achievement of all activities in workplan |  |  |  | 72.57 |

### Risks

Examine whether the project faces substantial risks in terms of the achievement and sustainability of project results. First identify the individual risks (internal and external) that the project is facing and rate those according to the rating scale (you may take both probability and impact into consideration). These are the inherent risks (or baseline risks). All of the risks will have mitigation actions to either manage or reduce the risk. After reviewing the mitigation plan for the individual risk, please project what the resulting risk would be, the residual risk – and rate according to the same scale. After assessing all individual residual risks, please determine the overall risk by averaging the individual risk ratings. In this example, the overall rating is identified as Modest given that one risk is substantial, one is modest and one is low. This rating is subjective and considered the best estimate for the average risk the project is facing in terms of achievement of outcomes. The risk rating should take into account the country setting and ambition of the project. See additional details here.

Risk Rating Scale

| Rating |  |
| --- | --- |
| High Risk (H) | There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. |
| Substantial Risk (S) | There is a probability of between 51% and 75% that assumptions may fail to hold, and/or the project may face substantial risks. |
| Modest Risk (M) | There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |
| Low Risk (L) | There is a probability of up to 25% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |

Guiding example: How to determine Risk Rating from Risk Analysis in PPR

| Risk Description | Inherent Risk | Mitigation | Residual Risk Rating |
| --- | --- | --- | --- |
| Elections – change of leadership lead to not holding up to commitments | High | Engage and establish rapport with opposition parties, explain MOUs and consequences of non-commitment. | Substantial |
| The newly established coordination mechanism does not meet regularly, and coordination fails | Modest | Ensure only most interested participants become members, engage regularly with members and monitor progress. | Modest |
| The new equipment given to rangers will fail at some point and there will be no expert or replacement parts available to fix. | Modest | The project is developing extension services that will be resourced with government contracts to provide the rangers the support needed. | Low |
| Average risk rating |  |  | Modest |

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

Total GEF disbursement defined as amount of project budget spent by the Executing Agency, as a total from project start until June 30 of reporting FY.