UN Environment GEF PIR Fiscal Year 2019

(1 July 2018 to 30 June 2019)

| 1. Identification |  | GEF ID: 5017 | Umoja no.: SB-000778.26 |
| --- | --- | --- | --- |
| Project Number + Project Title |  | Developing Core Capacity for Decentralized MEA Implementation and Natural Resources Management in Afghanistan |  |
| Duration in months | Planned | 36 (30 September 2017) |  |
|  | Extension(s) | 21 months extension approved on 25 July 2017 |  |
| Division(s) Implementing the project |  | Science Division (formerly DEWA), Climate services and Capacity Building Unit, Capacity Development and Innovations Branch. |  |
| Name of co-implementing Agency |  | NA |  |
| Executing Agency(ies) |  | The National Environment Protection Agency (NEPA) of Afghanistan |  |
| Names of Other Project Partners |  | UNEP Afghanistan Programme Office (UNEP Crises Management Branch – formerly PCDMB) |  |
| Project Type |  | Medium Size Project (MSP) |  |
| Project Scope |  | National |  |
| Region (delete as appropriate) |  | Asia Pacific |  |
| Names of Beneficiary Countries |  | Afghanistan |  |
| Programme of Work |  | 2018-2019; UNEP SP7 EA(a)(ii) |  |
| GEF Focal Area(s) |  | Multi Focal Areas (MFAs) |  |
| UNDAF linkages |  | Where appropriate, insert the UNDAF strategic objective to which achievement the project contributes. UNDAF Afghanistan 2015-2019 Priority Area: Equitable Economic Development Priority Statement: Inclusive, more equitable and sustainable economic growth with reduced dependency on the illicit economy. UN programmes under this priority area will combine support for the Government and relevant stakeholders, to achieve results in the following areas: inclusive job rich growth and economic development policies and programmes; agricultural development for food security, access to sustainable livelihoods and productive assets; and a transition to a green economy based on the sustainable and transparent management of natural resources, adaptation to climate change, and affordable environment-friendly energy sources. |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  | Although this GEF CCCD project has been designed to create enabling environment and enhance the implementation, monitoring and reporting of all SDGs with an environmental dimension, majority of the project interventions primarily contribute to the following SDGs, targets and indicators: 15.9.2; 15.10.1; 16.10.2; 17.16.1; 17.18.1/2/3 |  |
| GEF financing amount |  | USD 910,000 |  |
| Co-financing amount |  | USD 1,575,000 |  |
| Date of CEO Endorsement |  | 2 May 2014 |  |
| Start of Implementation |  | 18 September 2014 |  |
| Date of first disbursement |  | 29th September 2014 |  |
| Total disbursement as of 30 June |  | USD 860,000 |  |
| Total expenditure as of 30 June |  | USD 793,178 |  |
| Expected Mid-Term Date |  | MTR completed in March 2017 |  |
| Completion Date | Planned | 31 December 2017 |  |
|  | Revised | 31 December 2019 |  |
| Expected Terminal Evaluation Date |  | 30 June 2020 |  |
| Expected Financial Closure Date |  | 31 December 2020 |  |

2. OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) 2018-2019 UNEP SP7 EA(a)(ii) | Specify the relevant Expected Accomplishment(s) & Indicator(s) SP7 EA(a): Governments and other stakeholders use quality open environmental data, analyses and participatory processes that strengthen the science-policy interface to generate evidence-based environmental assessments, identify emerging issues and foster policy action SP7 EA(a)(ii): Increase in the number of countries reporting on the environmental dimension of sustainable development through shared environmental information systems with country-level data made discoverable through UNEP |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global Sub Programme Coordinators] SP7 EA (a): Afghanistan Environmental Data Centre at Kabul University that aims to provide geospatial knowledge, technologies and infrastructure to all stakeholders engaged and interested in Afghanistan’s sustainable future was launched with the support from UNEP projects including the MEA-CCCD project. AEDC is based on several pillars with different state of the art approach for capacity building, technological support, and networking in the environmental context. AEDC has been equipped with IT resources such as computers, workstation, printers, projector, screens and other tools to help students and professors’ access online/offline publications and materials. Data platforms such as MapX, OARE will be connected to the computers in AEDC for access to faculty members and visitors. An MoU between UNEP and Kabul University has been drafted and will be signed to ensure sustainability of the AEDC initiative in Afghanistan. SP7 EA(a)(ii): The project invited a team of experts in 2017 from the Sustainable Development Goal Data and Information Unit of UNEP and UNESCAP to deliver training to key stakeholders from the government on monitoring and report on the environmental dimension of SDGs. The training modules 1) an overview of the environment related SDGs and the statistical standards related to compiling environment statistics, 2) Land accounting, 3) Water accounts, 4) How Afghanistan could move forward with improving environments statistics and environment SDG monitoring. Another training was conducted in May 2019 on data gathering, management and reporting. |  |

For all GEF 6 and later projects:

| GEF Core Indicators NA | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
| NA | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. [Section to be shared with Monitoring Unit within PPD] UNDAF Afghanistan 2015-2019 Priority Area: Equitable Economic Development Priority Statement: Inclusive, more equitable and sustainable economic growth with reduced dependency on the illicit economy. UN programmes under this priority area will combine support for the Government and relevant stakeholders, to achieve results in the following areas: inclusive job rich growth and economic development policies and programmes; agricultural development for food security, access to sustainable livelihoods and productive assets; and a transition to a green economy based on the sustainable and transparent management of natural resources, adaptation to climate change, and affordable environment-friendly energy sources. The following project activities could contribute to this UNDAF expected outcome - Solar technologies including solar system, solar water heaters, solar pump, solar dries have been distributed to local communities in Bamyan and Daikundi. These technologies are meant to provide environment friendly energy for the communities. - Green Grant Funding Agreement were given to local communities through the Community Development Councils to manage small scale natural resources management and climate change adaptation projects. Reflecting on the concept of the UNDAF, a specific mutual accountability framework OneUN document was developed for Afghanistan for the period of 2918-2021 OneUN Thematic Area: Normative Outcome 2: The Government of Afghanistan shapes national policies and programmes observing international norms and standards, including multilateral agreements and the Sustainable Development Agenda. - The project provided inputs and technical support to government strategies such as Natural Resources Management (NRM) strategy, Climate Change Strategy and Action Plan, Forest Fire Strategic Plan, National Biodiversity Strategy and Action Plan, Afghanistan’s Intended Nationally Determined Contribution and Multilateral Environmental Agreements- Strategy and Action Plan. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | 15.9.2; 15.10.1 15.1 By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements - Forest area as a proportion of total land area - Proportion of important sites for terrestrial and freshwater biodiversity that are covered by protected areas, by ecosystem type - Although the project has not directly implemented huge forest restoration project but has supported with the development of a project titled “Forest Restoration for Enhanced Ecosystem Services Function in Afghanistan”. - The project has directly supported with the establishment of biodiversity demonstration plots and education centres. - A number of solar technologies, hydropower rehabilitation, greenhouse construction was supported to reduce pressure on native plants and biodiversity in the Shah Foladi Protected Area. - By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts - Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011–2020 - The project provided inputs and technical support to Afghanistan’s National Biodiversity and Action Plan and 5th National Report on CBD. - The project provided technical and financial support to Biodiversity Working Group to develop the national reports on Cartagena and Nagoya Protocols - SPEAK – Biodiversity that includes modules on introduction to biodiversity and ecosystem services, impact of climate change on biodiversity, biodiversity related MEAs, mainstreaming MEAs into national policies and strategies, NBSAP and Stakeholder engagement was finalised and delivered to Biodiversity Working Group members. 16.10.2 - Ensure public access to information and protect fundamental freedoms, in accordance with national legislation and international agreements 16.10.2 Number of countries that adopt and implement constitutional, statutory and/or policy guarantees for public access to information - Afghanistan Environmental Data Canter at Kabul University was equipped with IT resources such as computers, workstation, printers, projector, screens and other tools to help students and professors’ access online/offline publications and materials. Data platforms such as MapX, OARE will be connected to the computers in AEDC for access to faculty members, visitors and the general public through online platform. 17.16; 17.18 - Enhance the Global Partnership for Sustainable Development, complemented by multi-stakeholder partnerships that mobilize and share knowledge, expertise, technology and financial resources, to support the achievement of the Sustainable Development Goals in all countries, in particular developing countries 17.16.1 Number of countries reporting progress in multi-stakeholder development effectiveness monitoring frameworks that support the achievement of the Sustainable Development Goals The project supported NEPA to prepare national report for the environmental indicators of SDGs 17.18 By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts - Proportion of sustainable development indicators produced at the national level with full disaggregation when relevant to the target, in accordance with the Fundamental Principles of Official Statistics - Number of countries that have national statistical legislation that complies with the Fundamental Principles of Official Statistics - Number of countries with a national statistical plan that is fully funded and under implementation, by source of funding - SPEAK Data course curriculum developed and delivered to key stakeholders including NEPA, MAIL, Central Statistics Organisation, Ministry of Economy. SPEAK Data included modules on 1) An overview of the environment related SDGs and the statistical standards related to compiling environment statistics, 2) Land accounting, 3) Water accounts, 4) How Afghanistan could move forward with improving environments statistics and environment SDG monitoring, 5) data gathering, management and reporting. The training was delivered by experts from the Sustainable Development Goal Data and Information Unit of UNEP and UNESCAP |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating, FY | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- |
|  | S | S | S | S |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. - Since the last report period a number of hands-on and practical trainings were provided to government officials particularly NEPA to build their capacity in monitoring of land health and ecosystem management interventions in Shah Foladi Protected Area. - An MEA Strategy and Action Plan was drafted to guide the government in implementing and report on MEAs in Afghanistan. - Good progress was made with the capacity building initiates of community development councils (CDCs) and NGOs in implementing field interventions. - Support provided to government to prepare and participate at Conferences of Parties on UNFCCC, CBD and BRS conventions. |  |  |  |  |

| [complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more column if needed] |  |  |  |  |
| --- | --- | --- | --- | --- |
| Implementation Progress Rating | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
|  | S | S | S | S |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. - A number of trainings and exposure visit were conducted for government officials from NEPA, MAIL, MRRD, MEW, ANDAMA and Kabul University on MEAs for policy makers, MEAs for practitioners, biodiversity Conservation for policy makers and practitioner, data management, climate change and MEA financing in order to build the capacity of partners. - Afghanistan Environmental Data Centre (AEDC) was supported with IT equipment and furniture. Also, over 1500 copies of various environmental publications were deliver to the MEAs library of AEDC. - Regular MEA monthly coordination meetings were held to discuss, plan and implement MEAs related projects and activities. - Consultation meetings were conducted with partners to get their inputs on the draft MEA strategy and action plan. - NEPA was supported to develop national reports on Cartagena and Nagoya protocols and Rotterdam convention. - An MEA conference was conducted on 11 June 2019 to raise awareness and engage high level and technical officials from line ministries and agencies, NGOs and Academia to discuss on the MEAs implementation at the national and sub-national level in - Afghanistan. At the end of the conference training certificates were distributed to around 150 training participants from various government and non-government organizations. - Targeted trainings and capacity building activities were designed to build the capacity of NGOs in MEA implementation - An MOU has been drafted with Kabul University to collaborate on “Afghanistan Environmental Data centre”, curriculum development and research on environmental issues including MEAs. Challenges - The mid-term review noted that the original project document referenced the old NPPs, but since the original 22 NPPs recently replaced by 10 new NPPs, and only four of these are currently available from the MoF, it has not been possible to deliver fully on this output. The mid-term review also recommended that the project cannot be held accountable for the preparation of financial and operational plans for the NPPs that are directly relevant to the Rio priorities (Activity 1.3.1.2) as this is the responsibility of relevant GIRoA line Ministries - Though the project has taken efforts to provide capacity building support to stakeholders, the wide scope of stakeholders from national to provincial to district and local levels has made it difficult to achieve the desired result. |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting.

Add more columns if needed]

| Risk Rating | FY 2016 | FY 2017 | FY 2018 | FY 2019 |
| --- | --- | --- | --- | --- |
|  | M | M | M | M |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 The overall risk for the project has been rated as “Medium”: - Security wise: Originally, Kabul districts were chosen as demonstration sites, however due to high security risks, the mid-term review (MTR) suggested to shift the sites to provinces where stakeholders could easily be taken for training. Therefore, at the project steering committee meeting it was decided that the project could work in Bamyan, Badakhshan and Daikundi to establish demonstration sites. Project sites were selected on the basis of their strong working relationships between communities and the local administration. In addition, project staff monitored the evolving security situation closely and always applied internal UN security standards (MOSS standards) to ensure the safety of project staff, community members and, insofar as possible, the delivery of project objectives. - For data collection related risks, the project has involved key data partners for environment such as Central Statistics Organization and NEPA in developing project results. Extensive trainings on data collection and sharing mechanisms has been delivered to relevant organizations. Also, Afghanistan Environmental Data Centre aims to establish create a new platform for creating and sharing environmental data particularly geospatial data. - To enhance partner commitment, the project established inter-ministerial working groups whose mandate are to plan, report and advise on MEAs implementation. Also, MEA monthly coordination meeting were used to track the progress on MEA implementation. A project steering committee was also established, operationalised, and organised regular meetings to fast track implementation and provide strategic leadership to both the management team and national stakeholders. - To strengthen enforcement of legislation and policy mainstreaming, the project conducted a number of consultation meetings with high level government officials as well as the technical staff to make sure stakeholders’ needs and priorities are captured in the MEA strategy and action plan. Also, consultation and endorsement workshops are being held to make sure the MEA SAP is given a legal status and is implemented buy stakeholders. The project also provided inputs and technical support on draft legislation processes led by the government, to make sure MEA commitments are included such as Natural Resources Management (NRM) strategy and climate change strategy and action plan. |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] Project Stakeholders have been engaged through various means, particularly through: - MEA monthly coordination meetings: most of the meeting partners were division directors and technical staff of NEPA and UNEP. Other partners found it difficult to participate in such meetings regularly due to lack of transportation facility and workload. - Biodiversity Working Group: this group only met when an action needed to be taken on biodiversity. This group met during the development of Cartagena and Nagoya Protocols’ reporting - Climate Change Study teams: this team met when a decision needed to be taken on climate change. Also, provided relevant data from the agencies and ministries for reporting - NEPA: project team worked from allocated office in NEPA twice a week and interacted with NEPA regularly - PSC meeting: senior government officials were updated in detail about the progress of the project through PSC meetings - Consultation Workshops: project partners also received updates on the project through consultation workshops and meetings for specific outputs such as MEA Strategy and Action Plan - Trainings and site visits: partners were also updated and received information on MEAs and the project objective during trainings and field visits. |
| --- | --- |
| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] Specific consideration has been put on gender mainstreaming. For instance, the project has prepared a publication on Gender Resilience, Integrating Gender to influence policy makers to consider women’s role in the management of natural resources. Also, target interventions were designed and implemented by women and women NGOs, such as establishment of women conservation center, kitchen garden etc. Gender participation has been also encouraged in receiving trainings and other capacity building activities. Specific awareness raising events have been conducted for women in the workforces such as a conference on “Gender Resilience” was conducted on women’s day in 2018. |
| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval [section will be uploaded into the GEF Portal] Building Resilience, Integrating Gender; the publication includes a synopsis of the expected impacts of climate change on Afghanistan’s natural resources, exploration of how Afghan women are involved in managing these natural resources, as well as what the implications of climate change will be for these women’s lives and livelihoods. The focus the publication is around four themes, agriculture, forests and rangelands, energy, and water. Finally, a number of policy recommendations and practical actions were outlined on how gender concerns might be integrated into current and future development initiatives as a fundamental aspect of building adaptive capacity to climate change and disasters in Afghanistan. MEA Handbook: the publication aims to introduce key MEAs and MEA implementation in Afghanistan. The potential audience of this knowledge product are technical staff of the government, NGOs and students. |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. [section to be shared with communication division/ GEF communication] The project shared resources to establish and strengthen the Afghanistan Environmental Data Centre (AEDC) at Kabul University. AEDC was established as a functional platform for the collection, storing, sharing, and analysis of key environmental data in Afghanistan, utilizing Kabul University as a neutral platform that can be accessed by Government, UN, NGOs, civil society, and academia. It will serve as a central data hub for linking with existing global data management initiatives, such as MAP-X, IRIS, UNEP-Live, etc. The knowledge created through AEDC will be stored in a technical library, taught to students via improved curriculum, shared with professionals via short technical courses, and generated via research activities and the generation of knowledge products (reports, posters, info graphics) and events. AEDC will assist with the collation of environmental data as needed for various environmental inventories as part of responsibilities and obligations under various MEAs, e.g. GHG inventory under UNFCCC, POPs inventory under Stockholm Convention, ODS inventory under Montreal Protocol. Thus, the AEDC combines research, education, outreach, and policy support on a wide range of environmental issues, including climate change, biodiversity, natural hazards, and multilateral environmental agreements. This will help ensure that Afghanistan’s decision-makers have access to scientifically rigorous data to help address the country’s urgent environmental issues and promote sustainable development. AEDC also aims to help achieve the objectives of the Kabul University’s Strategic Plan (2017-2021) in terms of capacity building, academic research, and quality education based on market needs. The project is advocating to raise funding for further development of AEDC in order to achieve its strategic objective to support the management of environmental data in Afghanistan. |
| --- | --- |

# RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of: (i) 	Progress towards achieving the project Results(s)- see section 3.1 (ii) 	Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

3.1 	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Building core capacity for decentralized MEA implementation and natural resources management in Afghanistan | Decentralized MEA Capacity in Afghanistan is improved across line ministries and key stakeholders by Year 4 | MEA unit at national government level has been created but still core capacity for MEA decentralized implementation is not in evidence | MEA units in government understand general work plans for MEA implementation | Clear evidence of decentralized core capacity for MEA implementation in seven provinces in Afghanistan is achieved | Regular MEA coordination meetings, trainings and awareness raising activities at national and sub-national levels have contributed to an increased understanding of the synergies between the Rio Conventions The various inter-ministerial coordination groups such as the Climate Change National Study Teams, Biodiversity Working Group and Chemicals Working were trained on environmental issues and now support the government in meeting its reporting requirements under various MEAs. Provincial government authorities in Bamyan have taken the lead in developing the Shah Foladi Protected Area Management Plan. | S |
| Outcome 1: Effective Inter-ministerial collaboration between NEPA, MAIL, ANDMA, MRRD and MEW through support to the operation of a national MEA Task Force and a Technical Advisory Panel (TAP) | 1. Existence of a national inter-ministerial MEA Task Force that meets on a quarterly to six-month basis | While there is currently a small MEA unit with the NEPA there is no standing mechanism for collaboration across the different ministries. | None | MEA Task Force meetings take place every 3 to 6 months | The MEA Task Force has a TOR, has been formally established, and meets monthly to ensure coordination and communication across Afghanistan’s implementation of its MEAs | S |
|  | 2. Existence of a Technical Advisory Panel (TAP) that meets every 1 to 2 months | There is currently a national climate change technical advisory panel, but none for MEAs generally. Climate panel will be used as baseline. | None | TAP meetings take place every 1 to 2 months | The MEA TAP has a TOR, but its membership overlaps greatly with the MEA TF as well as the monthly MEA coordination meetings; thus, the TAP and TF have been merged in order to deepen engagement with institutions via thematic MEA working groups. The government has established various inter-ministerial coordination mechanisms that advise on thematic environmental issues. These committees include; the High Council on Land, Water and Environment usually chaired by H.E the President and H.E the Chief of Staff. Others include the National Climate Change Committee, the Inter-Ministerial Committee on Food Security, the Committee for Environmental Coordination, the Biodiversity Working Group, High Level Commission on Air Pollution Control, High Commission of Disaster Management The project has technical and financial support to the various inter-ministerial groups to develop MEAs reports of the Cartagena Protocol, Nagoya Protocol, CMS, Rotterdam Convention and Basel Convention |  |
|  | 3. Existence of costed MEA implementation road map | MEA Road Map developed in 2012 | MEA Road Map explained to the MEA Task Force | Costed MEA implementation Road Map has been adopted by the MEA Task Force | Building off the MEA road map that was developed in 2012, a draft MEA Unit Strategy has been developed, which provides the foundation for including strategic actions and coordination in revisions to the MEA road map. A report on MEA strategy was developed by the Mid-Term review consultant, which will be used in Strategy and Action Plan with that would include recent update on MEA implementation. |  |
| Outcome 2: Effective integration of Rio Convention objectives into agricultural policy and national development strategy | Number of MEA objectives reflected in iterations of the agricultural policy and national development strategy | Both the current agricultural policy and the national development strategy mention environmental issues but there is insufficient attention to issues of climate change, biodiversity and desertification | None | MEA objectives on climate change, biodiversity and desertification fully integrated in the adopted agricultural policy and national development strategy. | Biodiversity, climate, and land degradation issues have been integrated into Government strategies including the Natural Resources Management Strategy and Climate Change Strategy and Action Plan. Also, three project concept notes on the agriculture, water and energy sectors were developed to help the government mainstream climate change into their current work-streams. | S |
| Outcome 3: Effective integration of Rio convention objectives through the creation of a framework for environmental valuation to support integration into national planning. | 1. Use of environmental valuation techniques in the development of new national and provincial planning documents. | Typically, national and provincial planning documents incorporate formulaic references to the environment, but these are rarely informed by rigorous environmental valuation. |  | Environmental valuation techniques are piloted as part of the development of national and provincial plans. | Alternative mechanisms for financial support for MEA implementation and integration into national planning have been sought out. The concept of payment for ecosystem services and environmental valuation was included in the SPEAK Biodiversity training curriculum and was delivered to Biodiversity Working Group that includes technical officials from environment line ministries and agencies as well as academia. This concept is being added to other training curriculum packages on MEAs. The aim is to raise awareness of this issue among professionals to adapt the concept in their national environmental management planning. Environmental valuation techniques have been considered as part of the village/valley management plans. | MS |
|  | 2. Research output on role of women as natural resources managers in the achievement of the Rio convention objectives is made available for MEA Taskforce and TAP. | There is limited understanding of the role of women as natural resources managers in the achievement of the Rio convention objectives. | None | Final report on role of women as natural resources managers in achieving the Rio conventions is prepared and submitted to the MEA Taskforce and TAP. | A publication on Gender and Resilience consisting of chapters on Climate Change and Natural resources in Afghanistan, Agriculture, Forest and Rangelands, Energy, Water and Gender and Resilience Planning was developed and disseminated among government, and academic institutions. A Gender Leadership, and Opportunities for Women (GLOW) initiative has been developed to increase collaboration between UN Environment, government, nongovernment partners on gender issues vis-à-vis the environment, natural resources management, and MEAs. In addition, a section on the role of women in environment is being included in the MEA Handbook, and women’s group interventions have been supported by the project at the sub-national level. |  |
| Outcome 4: Local authorities have the capacity to translate MEA commitments into practice | Number of local authorities that are in the process of incorporating MEA commitments into practical annual and multi-annual plans and action. | Ecosystem management practices are rarely used to support biodiversity and land management across the country. | None | 3 new local government plans are approved visibly incorporating MEA commitments | With the technical support and in close coordination of UNEP, some Government Authorities have included MEAs commitments into their national plans and strategies. MEA commitments have been added to the Shah Foladi Protected Area Management Plan which will mainly be implemented by NEPA Bamyan offices, the Directorate of Agriculture, Irrigation and Livestock as well as the provincial and district governor offices of Bamyan. 3 other village/community management plans were drafted in close collaboration with community members and MEAs commitment on biodiversity, climate change and land management have been included. MAIL in coordination with other partners and close consultation with provincial authorities particularly member of the community development councils and provincial authorities have developed Natural Resources Management Strategy. CBD, CMS, CITIES related objectives have been included in the Natural Resources Management (NRM) Strategy (2017-2021) the main goal of the strategy is Community based management of the natural resources through science-based interventions, enabling policies, and partnership, aligned to the global conservation, development and climate smart agendas for job creation, food security and economic growth. NRM strategy has mostly provincial level commitments and plans. The National Chemicals Working Group with support from UNEP developed the National Implementation Plan on POPs that include Action Plans which will feed into the various organizations’ plans. NEPA published the National Climate Change Strategy and Action Plan (NCCSAP) in May 2017 that includes commitments under the UNFCCC; MEAs and MEA commitments were added to the curriculums of three departments of Environmental Sciences Faculty of Kabul University. These departments syllabus included specific courses on MEAs objectives. These course curriculums are likely to be replicated at the provincial level higher education and universities. | S |
| Outcome 5: Local stakeholders effectively participate in MEA implementation | Number of stakeholders that are involved in MEA related project activities. | No baseline assessments exist but will conducted as a reference point for subsequent work in field sites. | None | 5 community groups and 5 local government units (MAIL, NEPA, MRRD, ANDMA, MEW) stakeholders are involved in MEA related project activities. | 23 community Development Councils (CDCs) and NGOs are involved in implementation of natural resources management interventions; MAIL, NEPA, MRRD, ANDMA, and MEW are all involved in climate change and resilience activities related to MEAs, through the mainstreaming of resilience into their work streams and/or via participation in MEA coordination bodies; partnership with ACBAR established to increase NGO and civil society involvement in environmental management and MEAs. | S |
| Outcome 6: Through enhanced capacities stakeholders are monitoring environmental degradation and services at a provincial level (mapping, EWS, data collection) | 1. No of field sites that are using supplied equipment to monitor environmental degradation and services. | NEPA staff and stakeholder organizations at a provincial level do not have adequate capacities and methods of monitoring Environmental degradation, desertification and the loss of biodiversity. | None | 3 local field sites have been supplied monitoring equipment and use it to monitor environmental degradation and services. | CDCs and NGOs that manage the field intervention have been given tools to manage and monitor their interventions. For instance, tracking sheets were created and NEPA provincial staff were trained to regular visit the project sites, monitor and record progress. Similarly, community development council who manage field interventions have been trained to monitor the health of the land they manage and report back. Best practices and lessons learned from community-based interventions was harvested and included in the publication EcoTech Handbook. The handbook that aims to provide details of the methods and techniques used for community level interventions, will be further distributed among stakeholders. The project has provided inputs to the Land Health Monitoring Framework (LHMF) Manual that provides detailed information on monitoring of environment degradation. The manual has been shared with partners for their review and inputs. It will be a great resource for environment resource users. The “Early Warning, Disasters, and Climate Systems in Afghanistan: Improving Systems and Networking for Natural Disasters and Climate Change Assessment” conference was conducted at the Ministry of Agriculture, Irrigation and Livestock (MAIL). This event, the first of its kind in Afghanistan, brought together a diverse group of actors on EWS in Afghanistan in order to harmonise activities, develop an EWS roadmap for Afghanistan, and support the Government to follow a holistic approach to integrating climate change into EWS. The event was co-organized by MAIL, the United Nations Environment Programme (UNEP), and the World Bank. Additional financial, technical, and logistical support was provided by the UN Food and Agriculture Organisation (FAO). | MS |
|  | 2. No of stakeholders with enhanced capacities to conduct environmental monitoring. |  | None | 100 staff from NEPA and stakeholder organizations acknowledge having enhanced capacities in environmental monitoring. | National and local stakeholders in government and local communities have been provided with hands-on training to monitor environmental degradation and change. Also training packages on biodiversity, climate change and chemicals have practical modules to increase their knowledge on applying environmental monitoring principles. Through project partner COAM, specific trainings on Early Warning systems were delivered to community members in Shah Foladi Protected Area. Also, seven modular training packages on LEARN (Local Environmental Advocacy, Research and Knowledge) was developed by project partner BORDA and delivered to local communities and authorities. The LEARN package included specific modules on village mapping based on community watersheds. These tracking packages are meant to be widely used by government partners and NGOs in future as well. |  |
| Outcome 7: Stemming from training provided, government planners are demonstrating ecosystem management technologies and approaches for synergistic implementation on MEA commitments (e.g. Integrated Water Resources Management, (IWRM) & environmental benefits analysis (EBA) | Number of demonstration training events delivered to NEPA and other project stakeholders at the provincial level. | NEPA staff and stakeholder organizations at a provincial level are insufficiently trained in methods of ecosystem management. | None | 3 training programmes developed and delivered to 100 NEPA staff and 5 community group stakeholders. | Training programmes on climate change, biodiversity, and ecoDRR have been designed and delivered to government staff and NGOs at both national and sub-national levels. A further training programme on MEA is currently under development, which has a module on synergistic approaches to MEA implementation for their mainstreaming. Around 150 training participants received certificates during MEA conference in June 2019. Also, 2 officials from government and 1 national staff from UN Environment attended a regional Red Listing and Protected Area Workshop in Sharjah, UAE. | S |
| Outcome 8: As a result of the MEA project and capacity support provided for NGOs, CBOs and academic organizations, new projects are being set up which show understanding and implementation of MEA requirements for poverty reduction (including support to small NGO-led pilots) | Number of NGOs and CBOs receiving support on MEA requirements. | Few NGOs and CBOs specifically address MEA requirements in their projects. | None | 9 NGOs and CBOs receive a package of support. | A partnership has been established with the “Agency Coordinating Body for Afghan Relief and Development” (ACBAR), which represents a network of more than 100 NGOs, for increasing NGO and civil society involvement in environmental issues via trainings, outreach events, and research activities. In addition, day-to-day and strategic level engagement with the Afghanistan Resilience Consortium (ARC) that consists of 4 international NGOs is ongoing, as are packages of support being provided to national NGOs including the Rural Green Environment Organization (RGEO) and the Conservation Organization for Afghanistan Mountains (COAM), community development councils (CDCs) and women’s groups, which include grants and trainings to integrate climate and biodiversity into their existing portfolio of work on watershed management and restoration. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY 2018 rating | FY 2019 rating | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project has achieved good progress towards the overall objective and outcomes through amongst others regular MEA coordination meetings and a variety of activities with partners such as NEPA, Kabul University and NGO networks. Despite political and security challenges, the project has continued to catalyse commitment and action towards MEA implementation in Afghanistan. However, the project activities are very diverse and broad for the relatively small size of the project. The project includes capacity building activities that target beneficiaries from the national level to provincial, district and community levels. With hindsight, the project would have been able to achieve better results in the challenging context of Afghanistan if the focus of the capacity building had been more narrowed in keeping with the timeframe and the resources available. |

## Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | The project scope is very broad making it difficult to achieve the desired results at all levels. | The project divided capacity building needs into groups and clusters and prepared and delivered targeted trainings and hands-on support. |
| on stakeholder engagement | Lack of interest and commitment from stakeholders’ delays project implementation. | The project engages with stakeholders regularly through established inter-ministerial working groups whose mandate are to plan, report and advise on MEAs implementation. Also, MEA monthly coordination meeting was used to track the progress on MEA implementation. |
| on gender actions | Lack of gender consideration result in the design of interventions that negatively impact women. | The project has designed specific interventions for women groups such as through establishing women training centres, biodiversity project etc Also, a publication on Gender has been developed targeting policy makers to take gender issues into consideration. |
| on safeguards | Lack of proper assessment of project activities may result in unintentional harm to people or ecosystems. | Project activities are communicated with the right partners/stakeholders at every stage of implementation |
| on delivering GEF Core Indicators | NA |  |
| on delivering of PoW EA | NA |  |
| on sustainability of results | Lack of available funding in the government result in discontinuation of such projects and established results. | Project team in consultation with government stakeholders particularly NEPA to design a new MEA project and seek funding from multilateral financial mechanisms. |
| others |  |  |

## Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date6 | Implementation status as of 30 June 2018 | Implementation status as of 30 June 2019 | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating8 |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: Establishment of an operational national MEA Task Force, supported by a Technical Advisory Panel (TAP). | 30 Jun 2015 | 100% | 100% | At the beginning of the project implementation, TORs for the MEA Task Force and TAP were developed and meetings conducted. However, later MEA TF and TAP merged into MEA Coordination group who had regular monthly meetings. At the MEA monthly meetings NEPA division directors and technical staff as well as various projects teams participated. This was one of the main meeting to coordinate MEA issues such as preparation for COPs, review of MEA reports. Also, technical working groups were created for each cluster of MEAs such as Biodiversity Working Group, Climate Change Study Teams, Chemicals Working Group who looked at thematic issues around MEA implementation and reporting in Afghanistan. Each of the thematic working group were provided with several targeted trainings on MEAs and were actively engaged in preparing the national reports on various MEAs. After the MEA CCCD project, the MEA coordination meetings will be led and chaired by the MEA Division of NEPA. | S |
| Output 1.1.2: A costed MEA implementation road map at national and subnational level | 30 Mar 2019 | 75% | 100% | The mid-term review proposed that instead of a costed MEA road map which was already developed in 2012, a MEA Strategy and Action Plan to be drafted. Therefore, the project supported the development of an MEA SAP which includes; MEAs in Afghanistan, MEA governance and coordination, roles and responsibilities of key role players, institutional arrangements and coordination and reporting of MEAs, challenges, gaps and needs in MEA implementation, nomination of focal points, participation at the COPs, cross-cutting issues – nexus approach, strategic framework and action plan for Afghanistan’s MEAs. Many constructive feedbacks received from partners and the final draft is to be presented at national consultation workshop on 22 August 2019. The MEA SAP will be finalised and endorsed by the government. Also, MEAs have been included in the revised curriculum frameworks of Environmental Sciences, Natural Resources Management and Disaster Management departments of Environmental Sciences faculty of Kabul University. A National Conference on MEAs in Afghanistan was held at Kabul University on 28 December 2015, and attended by 60 representatives from government, the UN, and NGOs, and covered the following topics: overview of MEAs and Afghanistan’s obligations, UNFCCC, UNCDB, UNCCD, Stockholm Convention, Montreal Protocol, and the future of MEAs in Afghanistan. A seven modules course curriculum on MEA Financing that included modules on MEA Financing, available funding mechanisms for MEA implementation and reporting, projects monitoring, and evaluation was developed and delivery to participants from key government organisations. An assessment of women’s inclusion in environmental management was conducted in Bamyan in order to better understand their role and influence in implementing projects related to natural resources management and ecosystem based DRR. Furthermore, UN Environment, in coordination with NEPA’s Gender Department, conducted a survey with 100 women on alternative sources of fuel and the impact of coal on health. The results of the assessments were included in a policy recommendation on Gender Resilience that focuses on background, status and recommendation for improving women’s participation in agriculture, water, forest and during rangeland was developed and finalized. This document was published and distributed widely in the events for International Women Day. | S |
| Output 1.2.1: Integration of MEA objectives into sectoral priority programmes, such as the National Priority Programme framework. | 31st Dec 2018 | N/A | N/A | The mid-term review noted that the original project document referenced the old NPPs, but since the original 22 NPPs recently replaced by 10 new NPPs, and only four of these are currently available from the MoF, it has not been possible to deliver fully on this Output. The mid-term review also recommended that the project cannot be held accountable for the preparation of financial and operational plans for the NPPs that are directly relevant to the Rio priorities (Activity 1.3.1.2) as this is the responsibility of relevant GIRoA line Ministries. However, the project is working with ANDMA on the development of a proposed new NPP on DRR but approval for the development of this NPP has not yet been given by the President’s Office, and so it is not yet listed on the MoF website. In terms of identification of entry points for specific MEAs, the project provided inputs in the following areas:1) a revision plan for the country’s NBSAP has been completed, which clearly identifies areas for further mainstreaming of biodiversity into development planning; 2) the completion of Afghanistan’s INDC to the UNFCCC involving multiple consultation workshops to build national capacity to meet international MEA obligations; 3) data collection, analysis, and synthesis for improving the effectiveness of the SNC under the UNFCCC and, more generally, programming on climate change adaptation and mitigation; 4) completion and finalization of Afghanistan’s Climate Change Strategy and Action Plan (ACCSAP); and 5) completion of an institutional assessment of relevant government institutions for management of chemicals for the National Implementation Plan on POPs. A guidance chart on “Action for Climate in Afghanistan” was developed as a briefing document and tool for providing succinct technical environ-mental data to leaders and decision-makers on climate change. | N/A |
| Output 1.2.2: Strengthened existing national financial and executing mechanisms for Rio conventions priorities connected to the Ministry of Finance mechanisms and trust funds | 31 Dec 2019 | 80% | 100% | A portfolio review of UNEP projects including the MEA-CCCD project was conducted together with the senior management of Ministry of Finance (MoF) and NEPA. MoF does not have systems in place to receive vertical funds from global environment instruments due to Presidential degree for a single treasury account. Nevertheless, MoF is looking at the possibility of establishing sub-fund codes or an Environmental Fund that can receive funds. SPEAK MEA Finances curriculum which is developed and delivered to key agencies including Ministry of Finance, Ministry of Economy and NEPA on how they could work together to access funds for MEAs implementation in Afghanistan including project design and formulation and monitoring mechanism and evaluation of impacts within a 4days’ workshop. The MEA Strategy and Action Plan contains information on financial mechanism to implement MEAs as well as the MEA handbook contain information on technical assistance on green accounting principles and MEA financing and execution. A new project proposal entitled “Forest Restoration for Enhancing Ecosystem Services in Afghanistan” was developed and support by the MEA team. The project received USD six million in funding from the Ministry of Foreign Affairs of South Korea. FREESIA is implementing the objectives of MEAs particularly CBD, UNCCD and UNFCCC. The project also aims to implement the NRM strategy of the government that was developed last year. | S |
| Output 2.1.1: Delivery of hands-on training for local government, communities, civil society partners, mosques, elders and youth groups on ecosystem management practices in three locations in Kabul province. | 30 May 2019 | 80% | 100% | During the lifetime of the project, several theoretical and hands-on trainings were delivered to local government, communities, civil society partners and youth groups. The project supported an NGO called ACBAR who provided trainings in provinces. 718 individuals have participated in three main activities (trainings, events and workshops). Although, there were more men participants (464 men) than women participants (254 women), this was expected due to security issues and cultural restrictions. At the trainings, events and workshops at least 36% of the total participants was women. Practical hands-on trainings on CBNRM/CCA interventions completed with each community as needed during the implementation of field activities. A team from NEPA, MAIL and UNEP were taken to Bamyan to provide them with hands-on training by assessing the environment and ecosystems in the Shah Foladi Protected Area and prepared management plan for the area. In addition, 8 seven-modular training curricula were developed and delivered to various levels of the government officials at national and subnational levels. The course curriculums for followed the SPEAK package models called “Strengthening Professionals Environmental Advocacy and Knowledge” on 1) MEAs for practitioners, 2) MEAs for Policy Makers, 3) MEA Financing, 4) Data, 5) GIS, 6) Climate Change, 7) Biodiversity for practitioners, 8) Biodiversity for Policy makers. On 22 April 2017, to mark the World Earth Day, a provincial workshop on core MEA capacity was organized in Mazar-e-Sharif Balkh province. Present at the workshop were senior government officials including Provincial Governor’s Chief of Staff and Head of Provincial Council for Balk. Talks, speeches and presentation were delivered on MEAs. | S |
| Output 2.1.2: Improved technical capacity for monitoring environmental degradation and services (mapping, early warning system, data collection) provided to National Environment Agency (NEPA) for its Geo spatial Data Monitoring unit | 30 Jun 2019 | 80% | 100% | Air pollution equipment calibration system was procured and handed over to NEPA for monitoring of air quality in Kabul City. The system is placed on the roof of NEPA building and also used as learning tool for NEPA staff. IT equipment including computers, workstation, adapters have been procured and handed over to the IT/GIS department of NEPA. This will help GIS team to develop geospatial data and maintain databases. SPEAK (Strengthening Professionals Environmental Advocacy and Knowledge) training on Geospatial was delivered to NEPA GIS staff and other key divisions as well GIS staff of line ministries. The goal of the training was to enhance the capacity of the participants to assess climate and ecological change using geospatial tools and methods. Approaches include well-developed GIS technology and remote sensing as well as providing a clear overview of the rapidly developing opportunities with open-source and commercial tools. NEPA GIS team has been using the knowledge and templates and create regular map on various environmental issues. The maps are usually posted on a public board in NEPA. Central government staff, two from MAIL and five from NEPA were taken to the project sites in Bamyan to conduct monitoring of land health and ecosystem management interventions in Shah Foladi Protected Area. Officials from government provided feedback and guidance to the local community representatives on how they can improve and maintain the project sites and protected areas. SPEAK Biodiversity course curriculums developed and delivered to NEPA and other officials from other line ministries included modules on 1) introduction to biodiversity, ecosystem services and conservation, 2) the principle of ecosystem management, 3) implementing national biodiversity strategy and action plan, 4) mainstreaming biodiversity at the local level, 5) the causes and consequences of biodiversity loss in Afghanistan, 6) ecosystem based adaptation, 7) monitoring and evaluation of biodiversity and ecosystems. The course curriculum will be used by partner agencies to further train their staff at the national and subnational levels. SPEAK Data course curriculum developed and delivered to key stakeholders including NEPA, MAIL, Central Statistics Organisation, Ministry of Economy. SPEAK Data included modules on 1) An overview of the environment related SDGs and the statistical standards related to compiling environment statistics, 2) Land accounting, 3) Water accounts, 4) How Afghanistan could move forward with improving environments statistics and environment SDG monitoring, 5) data gathering, management and reporting. The training was delivered by experts from the Sustainable Development Goal Data and Information Unit of UNEP and UNESCAP. In addition, Afghanistan Environmental Data Centre at Kabul University was equipped with IT resources such as computers, workstation, printers, projector, screens and other tools to help students and professors’ access online/offline publications and materials. Data platforms such as MapX, OARE will be connected to the computers in AEDC for access to faculty members and visitors. Another list of publications prepared together with Environmental Sciences faculty professors is ready for procurement. The library section of the Afghanistan Environmental Data Centre at Kabul University was enriched by handing-over about 300 publications covering topics on climate change, biodiversity, land and desertification, chemicals and waste, environmental laws and policies. Another list of publications has been prepared for procurement for the library. | MS |
| Output 2.1.3: Technical and scientific capacity for ecosystem management approaches in use at sub-national level (visualization techniques, watershed planning, landscape assessments and physical land use mapping) | 30 Jun 2019 | 80% | 100% | Over 15 Community Development Councils (CDCs) and NGOs were supported technically and financially to build their capacity and carry environmental projects in Bamyan, Daikundi and Badakhshan provinces. Green Grant Agreements (GGFAs) were given to CDCs and NGOs to deliver project for environment and ecosystem management. Specific interventions included; building of eco-sanitation toilets, trail rehabilitation, development of green schools, distribution of solar power system as well as solar dries and solar water heaters, bee keeping, establishing water reservoirs, ram pumps, hydropower rehabilitation, establishing training centers and conservation area for local communities and students, watershed management, construction of greenhouses and kitchen gardens for women, training on early warning systems, establishing biodiversity demonstration plots, non-fruit botanic demonstration plots. Best practices and lessons learned from community-based interventions was harvested for inclusion in the publication EcoTech Handbook. In addition, the project supported the Afghanistan In addition, the project provided technical and financial support to an NGO BORDA together with the Afghanistan Biogas Consortium to develop a wastewater treatment plant at the Kabul University’s Faculty of Environmental Science as a demonstration and learning project for professors and students on decentralized water resource management. BORDA also supported with the construction of three Decentralized Wastewater Treatment System (DEWATS) in Daikundi, Bamyan and Kabul provinces. These DEWTAS systems can handle flows as high as 1000 cubic meters per day, are tolerant to flow fluctuations, require low maintenance, and are durable. They treated wastewater can be safely reused for agriculture, construction etc., which reduces competition for clean potable water | MS |
| Output 2.2.1: Increased capacity among nongovernmental organizations (NGOs) and community-based organizations (CBOs) to understand and implement MEA requirements in line with existing provincial development plans | 30 Dec 2019 | 90% | 100% | A Green Grant Funding Agreement (GGFA) has been signed with the Agency Coordinating Body for Afghan Relief and Development (ACBAR) which is a national, independent, non-government organization that provides a platform for information-sharing and networking for nongovernmental organizations in Afghanistan. The main aim of the partnership was to increase civic engagement in environmental management in Afghanistan through a combination of research, capacity-building, and awareness-raising activities. The GGFA serves precisely to provide technical support on environmental issues, including accessing finances and international environmental standards, to NGOs in Afghanistan via trainings, outreach events, and research activities. ACBAR conducted a baseline stakeholder mapping and assessment of current and ongoing environment work streams within NGOs and CSO, created an environment library at their website, delivered one national and 5 provincial trainings on climate change, resilience and ecosystem-based adaption and delivered community-based advocacy and awareness raising activities at local level. In addition, UN Environment and NEPA engage on regularly with the Afghanistan Resilience Consortium (ARC), comprised of 4 other NGOs (Afghanaid, ActionAid, Concern, and Save the Children), to build awareness and technical capacity on MEA implementation, particularly related to climate change and biodiversity in the area of ecosystem services. The project team supported the development of a course curriculum on DRR and included modules on MEAs and ecosystem management. Furthermore, NEPA has capitalized on public events, such as Earth Day and World Environment Day, to raise considerable awareness through civil society networks about environmental conservation and climate change adaptation, which has also included high-level government support from the office of the President and CEO for these areas. NEPA also continues to lead on the inclusion of NGOs, civil society, and academia in government-led processes for MEA implementation and reporting requirements, particularly for the CBD and UNFCCC. | S |
| Output 2.2.2: Mentoring for 3 NGOs in how to design a project, to the point where written project proposals, are drafted and submitted to bilateral donors producing practical implementation projects in at least three provinces | 30 June 2019 | 85% | 100% | The project provided financial, technical and capacity building support to several NGOs and CSOs in at the national and sub-national level. Some of these NGOs included Bremen Oversees Research and Development Association (BORDA), Conservation Organisation for Afghan Mountains (COAM), Environment, Health and Development Organisation (EHDO), Afghan Social Welfare and Development Organisation (ASWDO) and RUPANI. Extensive guidance was provided to these NGOs to develop small scale project proposals and received funding from UNEP to implement their projects in Bamyan, Daikundi and Badakhshan. Also, technical support and guidance was provided to COAM to develop project proposal and successfully access funding from the Darwin Initiative in the UK. The project titled “Reducing environmental degradation through sustainable fuel interventions in Afghanistan is currently being implemented by COAM in Bamyan. Through partnership with ACBAR, trainings and awareness raising events were delivered to many other NGOs and CSOs on the topics of climate change, resilience and ecosystem management. | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project has continued to operate in a challenging environment due to political and security challenges in Afghanistan. In addition, there has bene a period of instability on the management of the UNEP Afghanistan Programme Office. Despite these challenges, the project team has continued to work with dedication and overall delivered satisfactorily on the outputs and activities. |

## Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc). The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Limited technical capacity at the project sites may undermine the monitoring of project lessons and the ability of the project to synthesize those lessons for policy- related processes | The project will ensure that a proper communication and awareness strategy is in place so that lessons learned can be transformed into local Dari and Pashto language. Also, national government staff are taken to project sites to conduct monitoring and document lessons learnt. | Project team, mid-term review consultant | Since September 2017 |
| A lack of coordination among different ministerial initiatives may affect the project timeline | The project management committee will be a critical mechanism to bring together stakeholders at all levels and will serve to raise levels of MEA awareness. | Project team, mid-term review consultant | Since September 2017 |
| Lack of government capacity to report on MEAs and participate in COPs | The project has been advised to consider the desired levels of attainment for capacity and understanding, and report on progress made accordingly | Project team, mid-term review consultant | Since September 2017 |
| Many scientific and /or technological uncertainties | This project uses scientific and technological resources and innovative approaches to deliver the project ultimate objectives such as developing and connecting reporting systems, CBNRM approaches etc | Project team | June 2018 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| The security situation in Afghanistan deteriorates to the point at which operations in Kabul and Kabul province are no longer possible | The project has selected sites that have a history of relative security and good governance. Project sites have also been selected on the basis of their strong working relationships between communities and the local administration. In addition, project staff will monitor the evolving security situation closely and always apply internal UN security standards (MOSS standards) to ensure the safety of project staff, community members and, insofar as possible, of project objectives. | In Afghanistan, there is a higher than average level of security and other risks, and mitigation measures are designed accordingly. Originally, Kabul districts were chosen as demonstration sites, however due to high security risks, the mid-term review suggested to shift the sites to provinces where stakeholders could easily be taken for training. Therefore, at the project steering committee meeting it was decided that the project could work in Bamyan, Badakhshan and Daikundi to establish demonstration sites. Project sites were selected on the basis of their strong working relationships between communities and the local administration. In addition, project staff monitored the evolving security situation closely and always applied internal UN security standards (MOSS standards) to ensure the safety of project staff, community members and, insofar as possible, the delivery of project objectives. | CEO: H |
|  |  |  | TM:M |
|  |  |  | PM: M |
| A lack of coordination among different ministerial initiatives may affect the project timeline | The project will engage government officials at high levels to formalize a multi-sector Project Steering Committee which will oversee the project and its deliverables. | The project has established inter-ministerial working groups whose mandate are to plan, report and advise on MEAs implementation. Also, MEA monthly coordination meeting was used to track the progress on MEA implementation. Regular MEA monthly coordination meetings were also held to discuss, plan and implement MEAs related projects and activities. | CEO: M |
|  |  |  | TM:M |
|  |  |  | PM: M |
| Integration of MEA commitments is limited due to a lack of understanding or interest among relevant stakeholders at national and local levels. In particular ongoing violent conflict, poppy-driven drug trade and natural disasters are identified as issues with significant likelihood of disrupting project progress. A lack of coordination between the national policy level and provincial implementation may impact the project timeline. Limited technical capacity at the project sites may undermine the monitoring of project lessons and the ability of the project to synthesise those lessons for policy related processes. | This risk will be mitigated through dedicated capacity development outputs (technical and policy) and creating strong linkages to the mandate of the National Environment Protection agency, ensuring continued sustainability. National stakeholders and partners participating in this project have sufficient experience in bilateral and multilateral projects and will make everything possible to avoid delays. The timeframe for this project will be managed with special attention. The project management committee will be a critical mechanism to bring together stakeholders at all levels and will serve to raise levels of MEA awareness. The project will establish strong linkages with ongoing UNEP capacity building programmes of UNEP in Afghanistan. The project will ensure that a proper communication and awareness strategy is in place so that lessons learned can be transformed into local Dari and Pashto language. | The project has involved key data partners for environment such as Central Statistics Organization and NEPA in developing project results. Extensive trainings on data collection and sharing mechanisms has been delivered to relevant organisations. Also, Afghanistan Environmental Data Centre aims to establish create a new platform for creating and sharing environmental data particularly geospatial data. | CEO: M |
|  |  |  | TM:M |
|  |  |  | PM: M |
|  |  | The project has provided inputs and technical support on legislation led and drafted by the government to make sure MEA commitments are included such as Natural Resources Management (NRM) strategy and climate change strategy and action plan. A project steering committee was also established, and organised regular meetings to fast track implementation and provide strategic leadership The project conducted a number of consultation meetings with high level government officials as well as the technical staff to make sure stakeholders’ needs and priorities are captured in the MEA strategy and action plan. Also, consultation and endorsement workshops are being held to make sure the MEA SAP is given a legal status and is implemented buy stakeholders. | CEO: M |
|  |  |  | TM:M |
|  |  |  | PM: M |
|  |  | Overall Risk Rating Project Manager | M |
|  |  | Overall Risk Rating Task Manager | M |

| FY2018 rating | FY2019 rating | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | In Afghanistan, there is a higher than average level of security and other risks, and mitigation measures are designed accordingly. Originally, Kabul districts were chosen as demonstration sites, however due to high security risks, the mid-term review suggested to shift the sites to provinces where stakeholders could easily be taken for training. Therefore, at the project steering committee meeting it was decided that the project could work in Bamyan, Badakhshan and Daikundi to establish demonstration sites. Project sites have also been selected on the basis of their strong working relationships between communities and the local administration. In addition, project staff will monitor the evolving security situation closely and always apply internal UN security standards (MOSS standards) to ensure the safety of project staff, community members and, insofar as possible, of project objectives. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks.

Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.  Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project log frame or in any updated project revision. 6 As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.  8 To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)