UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5528 | Umoja no.: S1-32GFL-000507, P1-33GFL-000593, P1-33GFL-000557 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Achieving Biodiversity Conservation through Creation and Effective Management of Protected Areas and Mainstreaming Biodiversity into Land Use Planning |  |  |
| Duration months | Planned |  | 48 months |  |  |
|  | Extension(s) |  | - |  | - |
| Division(s) Implementing the project |  |  | UN Environment Division of Environmental Policy Implementation (DEPI) |  |  |
| Executing Agency(ies) |  |  | UN Environment Regional Office for Europe (Offices in Geneva and Vienna) |  |  |
| Names of Other Project Partners |  |  | Ministry of Environment and Physical Planning of North Macedonia |  |  |
|  |  |  | Ministry of Agriculture, Forestry and Water Economy |  |  |
|  |  |  | Academy of Sciences and Arts of North Macedonia |  |  |
|  |  |  | Swiss Development Cooperation (SDC) |  |  |
|  |  |  | Spatial Planning Agency |  |  |
|  |  |  | Public Enterprise “National Forests” |  |  |
|  |  |  | National hydro-meteorological service |  |  |
|  |  |  | Ss. Cyril and Methodius University with its relevant institutes and faculties |  |  |
|  |  |  | National Institution Museum of Natural History Skopje |  |  |
|  |  |  | Hydro-biological institute Ohrid |  |  |
| Project Type |  |  | Full Size Project |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Europe |  |  |
| Names of Beneficiary Countries |  |  | North Macedonia |  |  |
| Programme of Work |  |  | PoW 2018-19 Subprogramme 3 Subprogramme 4 |  |  |
| GEF Focal Area(s) |  |  | Biodiversity BD-1: Improve Sustainability of Protected Area Systems BD-2: Mainstream Biodiversity Conservation and Sustainable Use into Production Landscapes, Seascapes and Sectors |  |  |
| UNDAF linkages |  |  | Outcome 4: Environment sustainability |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | SDG No.15 Life on Land: requires countries to protect, restore and promote the sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss. 15.3.1 Proportion of land that is degraded over total land area 15.4.1 Coverage by protected areas of important sites for mountain biodiversity 15.5.1 Red List Index 15.9.1 Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011-2020 |  |  |
| GEF financing amount |  |  | USD 3,360,731 |  |  |
| Co-financing amount |  |  | USD 21,926,500 |  |  |
| Date of CEO Endorsement |  |  | 22/03/2016 |  |  |
| Start of Implementation |  |  | 12/10/2016 |  |  |
| Date of first disbursement |  |  | 01/09/2016 |  |  |
| Total disbursement as of 30 June |  |  | US$ 2,718,824 |  |  |
| Total expenditure as of 30 June |  |  | US$ 1,684,598.47 |  |  |
| Expected Mid-Term Date |  |  | TBD |  |  |
| Completion Date |  | Planned | 12 October 2020 |  |  |
|  |  | Revised | - |  |  |
| Expected Terminal Evaluation Date |  |  | TBD |  |  |
| Expected Financial Closure Date |  |  | 12 April 2021 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) Sub-programme 3: Healthy and productive Ecosystems. Sub-programme 4: Environmental Governance | Specify the relevant Expected Accomplishment(s) & Indicator(s) EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels (i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems (ii) Increase in the number of countries and transboundary collaboration frameworks that demonstrate enhanced knowledge of the value and role of ecosystem services EA (b) Institutional capacities and policy and/or legal frameworks enhanced to achieve internationally agreed environmental goals, including the 2030 Agenda for Sustainable Development and the Sustainable Development Goals (i) Increase in the number of countries that have enhanced45 institutional capacity and legal frameworks to fully implement the multilateral environmental agreements and for the achievement of internationally agreed environmental goals including the 2030 Agenda and the Sustainable Development Goals |
| --- | --- |
| Following the negotiation period between July and September 2018, agreements have been concluded with identified local partners. A second agreement was signed with the Institute of Ecology and Technology, Tetovo and Institute of Biology, Skopje for development of the final version of Shar Mountain Valorisation Study. In addition, a separate expert team has been working with the local communities and developing a socio-economic study, that will finally accompany the main VS in terms of the mentioned aspects. The VS is expected to be finalized by the end of 2019. Meanwhile, expert team will be selected for the development of the necessary proclamation documentation to be finally submitted together with VS to the Government of North Macedonia. With the proclamation of Shar Mountain as protected area on the side of North Macedonia, and together with the protected areas on Kosovo and Albania side, it will become the largest protected area in Europe. The selected national Red Lists experts/assessors have started with field work and have been developing the assessments for Herpetofauna species (reptiles and amphibians) and 14 sub-species of vascular plants, including the introduction of such details in the Global IUCN RLs system. The IUCN RLs lists species according to their estimated risk of extinction and compiles all necessary data to support this estimate. The main goal of the RL assessment is to assign each species to one of the IUCN Categories for extinction risk, such that these assessments can be taken into account for prioritizing conservation efforts on local, regional and/or global levels, in both policy and CSO-based actions. The Red Lists for Amphibian and Reptiles will be the first documents of its kind in the country, together with list of priority species for future RLs development. As an added value, the international training and experience gained will serve national experts for development of red lists for other species during future activities. National experts have been engaged for identification of High Nature Value Forests and guidelines for their future management. Within the reporting period, experts have developed criteria for identification of HNVFs in the country, which have been discussed with a wider stakeholders’ group. Furthermore, these criteria have been tested during a practical training through a developed form for data management. Currently, experts have started with field work planning, while the final guidelines are expected to be shared by the end of 2019. Finally, all taken activities will contribute to assist Macedonian authorities in strengthening national policy and management of forest ecosystems by increasing the knowledge on remnant forest areas with high degree of naturalness that support many plants, bird and other animal species, as well as strengthen capacity for forests conservation and action planning. Terms of reference have been prepared for development of Management Plan for Shar Mountain, which finally should be adopted by the future NP managing body within 2 years from its proclamation. In addition, the project is negotiating partners for development of MP for Ohrid Lake, as well as a valorisation study for the same area. Both documents will serve the country in taking necessary measures for future protection, conservation and proper management of the natural values of both sites, in addition to the enlargement of the national PAs network. Local partners have initiated activities for updating the national soil erosion map, as well as development of soil sealing rate and forest vegetation maps for three pilot sites. During the introductory activities, the wider stakeholders’ groups have been discussing the methodology for collection and data processing, as well as selection of the most representative pilot sites. Digital maps and database of regions vulnerable to drought and soil erosion processes will provide spatial and quantitative information on areas prone to drought and erosion. This information is essential tool for evaluation of impact of the main drivers of land degradation and desertification in the country, enabling reliable, easy and efficient quantification of the extent of land degradation and desertification process. Once established, these datasets will be used in many important national, regional and local activities, related, but not limited to environmental sector, agriculture, forestry, water management, spatial and urban planning etc. Finally, forest vegetation mapping and classification has always been an essential tool for describing the distribution, structure, and composition of forest plant communities. As forest vegetation generally integrates the ecological processes acting on a site or landscape - more measurably than any other factor or set of factors and often infers soil and climate patterns, vegetation is often selected as the basis for the classification of terrestrial ecosystems. North Macedonia does not have an established system for the collection and proper management of non-timber forest products. In order to overcome such status, local experts with guidance from Bulgarian partners have been trained in different methodologies for determination of quotas for non-timber forest products, manner of collection and data processing, experience sharing, trade and control over exported and imported quantities. Experts are currently drafting reports on the current legal, economical and institutional framework analysis in order to propose recommendations for its improvements in terms of proper trade and management of non-timber forest products. Final quotas for one species (Uva ursi) will be determined for the entire country’s territory, while another methodology will be used to determine the quotas for another species (Juniperus communies) for one pilot site in the eastern part of the country. Final results are expected to be delivered by mid-2020 and will be used to undertake proper protection, conservation and management of the mentioned species, as well as an example for establishing quotas for other species during future country’s commitments and developments. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
|  | Indicative expected Results |
| N/A – GEF-5 project |  |

| Planned linkages with UNDAF | North Macedonia has set its pace for achieving the sustainable development goals through a five-year Strategy (2016-2020). Outcome 4 of the Strategy envisages that by 2020, individuals, the private sector and state institutions base their actions on the principles of sustainable development, and communities are more resilient to disasters and environmental risks. The partnership seeks to inspire a fundamental change in outlook and behaviour among policy makers, citizens and private enterprises alike as relates to climate action and the sustainable use of resources. These actions are based on 6 pillars and this is how the project will contribute in achieving the set objectives: 1. Broadening awareness of ecological treats from a narrow group of experts and policy makers to the broader public to encourage the behavioural changes that are necessary to protect the environment, address environmental determinants of health and fight climate change. The project frame envisages and implements a large number of training and experience sharing especially with local communities, including women, to increase the level of understanding of the importance to protect and properly manage natural resources, while at the same time enable socio-economic development of the regions. Activities are being taken to present the importance of certain species for human health and possibilities for its proper management. 2. Improving the management of natural protected areas, so that the country’s priceless natural beauty can be preserved and developed as a resource for sustainable tourism. This will be especially achieved through the future proclamation of Shar Mountain as PA, as well as protecting the natural beauties of the current Monument of Nature Ohrid Lake. In addition, by developing the first national red lists of reptiles and amphibians, the country will contribute to the achievement of the set objective. To this end, the identification of HNVFs and guidelines for their management, will add value on the conservation aspects in line with the proper management and use of such forests. 3. Fighting land degradation and improving waste management, including the elimination of illegal garbage dumps, the creation of an EU-standards waste-removal and landfill system and promotion of recycling. The project will give contribution to achieve such objective by determining the areas which are most prone to erosion and soil sealing and will develop forest vegetation maps for selected pilot sites. 4. Ensuring that national institutions, city and town administrations and individual men and women improve their preparedness for natural and man-made disasters. Men and women are equally involved in all project activities on the importance of protection and conservation of nature, many training activities and capacity building, which raises the level of knowledge on the importance of taking immediate actions in case of natural and man-made disasters. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | 15.3.1 Proportion of land that is degraded over total land area Land degradation in North Macedonia is considered as one of the major threats for biodiversity loss, ecosystem stability and an array of socio-economic segments. The third component of the project: Land use planning and Biodiversity mainstreaming, output 3.1.1 concerns with development of tools and databases necessary for developing guidelines for revision of National Spatial Plan relating biodiversity conservation and building capacities of spatial planners and other relevant stakeholders on mainstreaming biodiversity conservation into national planning. The ongoing activities in the scope of this output, including development of national erosion and drought sensitivity map and database of soil erosion risk, soil sealing rate and loss of organic matter, are a foundation for intervention regarding improvement of the condition with the land degradation in the country. 15.4.1 Coverage by protected areas of important sites for mountain biodiversity Component 1: Increase of Protected Areas Network and connectivity anticipate support of the expansion of the current protected area network in the country by at least 1,5 %. Output 1.1.1 includes preparation of a study for valorisation of areas proposed for protection. Shar Mountain was selected as a priority area for protection, because of its richness with biodiversity and the fact that is foreseen for protection by a number of strategic documents. Once the valorisation study is finalized, MOEPP will initiate the proclamation procedure as under the Law on Nature Protection (expected during 2020). If proclaimed as national park, together with the National Park Mavrovo, as well as protected parts on Kosovo (under UNCCR 1244/99) and Albanian side, Shar Mountain would result in one of the largest protected areas in whole Europe. In addition, the project is supporting the development of (re)valorisation study for Ohrid Lake Monument of Nature and UNESCO site. 15.5.1 Red List Index Component 2 of the project: Increased effectiveness of biodiversity management, output 1 envisages development of the first national Red Lists. Within the project frame, two taxonomic groups (amphibians and reptiles) are subject of assessment under IUCN criteria and will result in generation of Red Lists for amphibians and reptiles. This is a major step towards future measuring of the status of the taxonomic groups, and a basis for Red List Index creation. 15.9.1 Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011-2020 The whole third component of the project 'Land use planning and Biodiversity mainstreaming' is aiming at integrating the biodiversity values in the national planning processes. The output 3.1.2 concerns with development of supporting documents for proposed revision of Forest Management Plans for forests managed by PE National forests, with an aim to introduce ecologically sustainable forest management practices and inclusion of specific elements for threatened biodiversity. Furthermore, Component 2, output 2.1.3 includes drafting of management plans for future NP Shar Mt. and Monument of Nature Ohrid Lake, which also contributes to achieving the Aichi Biodiversity Target 2. |
| --- | --- |

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR 12.10.2016 -30.06.2017 | 2nd PIR | 3rd PIR | … PIR | … PIR |

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| Significant progress has been made on component and outcome level since the last reporting period. The results are related to the completion of different activities related to the following project outcomes: Component 1. Increase of protected areas network Outcome 1.1. Improved biodiversity conservation through creation of new protected areas and pilot projects on corridors implementation The second phase for development of the final valorization study has been initiated, including numerous coordination meetings of experts and field visits for collection of additional data and verification of the existing one. GIS mapping of important species and habitats has been finalized and currently experts are working on the establishment of more precise borders and zoning of the future protected area. Furthermore, negotiations have been initiated with local partners for development of valorization study for Ohrid Lake. Progress will be presented during the next reporting period. Satisfactory results have been achieved in achieving activities planned for FY under: Component 2. Increased effectiveness of biodiversity management Outcome 2.1 Improved management effectiveness and capacity building as a tool for biodiversity conservation and protection of threatened species and habitats Activities with the development of the first national red lists (amphibians and reptiles) have been progressing well. Following the necessary field work, experts are currently introducing the collected and processed data in the Global IUCN RL system. In addition, plant experts have been also trained in development of future red lists by using a sub-set of vascular plants for training purposes and in setting priority in terms of importance and urgency for future needs. In parallel, criteria for identification of high nature value forests have been set in discussion with a wider stakeholders’ group. Once field work is fully implemented, guidelines will be developed in the coming period for the purpose of improving the knowledge on threatened species and habitats and training on biodiversity conservation and PA management. Negotiations have been initiated with local partner on development of management plans for Shar Mountain and Ohrid Lake, which will also contribute to increase the effectiveness in biodiversity management. Finally, evident progress has also been made within the Component 3. Land Use planning and biodiversity mainstreaming. Introductory activities on the methodology for collection and processing of data for updating of the national erosion map and development of soil sealing rate and forest vegetation maps have been implemented. Further steps are purchasing of necessary equipment for data collection and processing and planned field work. In parallel, local partners have been working on analysis of the legal, economic and institutional framework on the status of non-timber forest products in the country. With support from the Bulgarian partners, spatial planners, forestry professors, PE National Forest, MAFWE and MOEPP have been trained in the proper collection, trade and management of non-timber forest products, as well as determining quotas for respected species. During the next phase, quotas will be determined and tested for the selected species. All mentioned activities within Component 3 will contribute in the development of guidelines/recommendations for update of the National Spatial Plan and Forest Management Plans to incorporate biodiversity conservation into land use planning. |  |  |  |  |  |

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S | S |  |  |
| The implementation of the third-year activities started with negotiation of local partners under all three project components. Output 1.1.1: Supported Establishment of at least one protected area (Shar Mountain) as a National Park Following the development of the first version of the valorization study for Shar Mountain, the same Consortium of local partners (Institute of Ecology and Technology, Tetovo State University and Institute of Biology, State University Ss. Cyril and Methodius Skopje) has been engaged to continue working on the development of the study’s final version. In line with the prepared work plan, experts have been carrying various field visits for the purpose of collection and processing of missing data and verification of the existing ones. They also did a GIS mapping of important habitats and species in Shar Mountain region and produced the very first/preliminary borders and zoning of the future protected area. Acknowledging the importance of the socio-economic aspects for the region, with support from the Italian Ministry of Environment, Land and Sea, local environmental consulting company DEKONS-EMA Skopje has been contracted to develop a separate socio-economic study for Shar Mountain. During 4-7 September 2018, the third study visit was organized on Shar Mountain and Tetovo region, with the purpose of experience and knowledge sharing in terms of on one hand proper management of the park with full involvement of local communities and providing socio-economic development and nature protection and conservation, on the other. Following the period of data collection and processing, the preliminary findings regarding biodiversity, geology and hydrology, economic aspects and urban planning, forestry, agriculture and husbandry, ethnobotanics, tourism and hunting have been presented during wider stakeholders’ workshop held on 17 June 2019 in Tetovo. Representatives from different institutions discussed about the proclamation process and management of the future PA, as well as involvement of local communities and improvement of the socio-economic status of the region, while enabling nature protection. The Socio-economic study is expected to be delivered in late summer 2019 and will provide input for the development of the main valorization study for Shar Mountain. During the upcoming year, experts will be contracted for analysis and preparation of the necessary proclamation documentation, which together with the main Shar Mountain valorization study, has to be filled to the Government for review, further processing and discussion on the proclamation procedure. In parallel, and in consultation with MOEPP and PSC, means have been allocated for development of a second valorization study for Ohrid Lake. The lake was inscribed on the World Heritage List (UNESCO) in 1979, is nationally proclaimed as a “monument of nature”, belongs in the CORINE Biotopes, is identified as an Important Plant Area, and in 2010, it was proclaimed as an Important Bird and Biodiversity Area. Additionally, the lake has a cross-border value and is one of the proposed sites for the future EU Natura2000 in the country. Acknowledging this vast importance, the main purpose of the valorization study would be to present detailed analysis of all available environmental and territorial information pertaining to the protected area, propose external boundaries and zoning of the area with GIS distribution of habitats and species, as well as socio-economic analysis for improved common management of the area. Consequently, terms of reference have been developed and local partner is currently being negotiated to start with implementing activities in the next quarter. Same activities (TOR and negotiations) have been initiated at the end of the reporting period for selection of two pilot corridors from the Macedonian Ecological Network (MAK-NEN) for development and testing of site-specific measures involving local stakeholders for management and restoration of high nature value forests and other habitats (Output 1.1.2). Most progress has been identified in the second project components: Output 2.1.1: A “Red List Index” for North Macedonia is generated, reflecting the prioritized list of threatened species within the country and guiding the creation and effective management of new and existing Protected Areas. Output 2.1.4: The first Red Data book in North Macedonia for at least one taxonomic group is developed Following the successful training on the development of national Red Lists from the IUCN Red Lists Cambridge Unit, and in consultation between MOEPP, UN Environment, IUCN and other relevant stakeholders, it was decided that the main priority of the country is the development of national red lists for reptiles and amphibians. As an added value, a small sub-set of plant species with policy relevance have been selected to be assessed according to the IUCN criteria as a first contribution to the national Red List and as a capacity building exercise. The plant species selected to undergo the RL process, will train national plant experts for future national RL assessments using a “learning by doing approach”. The experts will also produce a separate list that will help prioritize plant species for such future Red List assessments. After an open call and selection of national experts/assessors, existing data and information have been analyzed and the field work was initiated in the second quarter of 2019. Relevant data are currently being entered in the Global IUCN Red List system. First introductory brochure on the national Red Lists has been developed in three languages, Macedonian, English and Albanian and is available on request at http://ebiblioteka.moepp.gov.mk:8080/library/home and it will be uploaded, once the web designer is selected and the separate national RL web site is developed. The brochure constitutes details on the significance of the national red lists, their usage, influence on resource allocation, conservation planning, decision making, health case and awareness and education. After finalizing the red lists, activities will follow in the last project year for preparation of Red Data Book for reptiles and amphibians. Output 2.1.2: High Nature Value Forests are identified and at least two (2) guidelines for their management are developed in favor of biodiversity conservation The NGO Macedonian Ecological Society has been contracted for the implantation of the planned activities. Engaged experts have performed a thorough analysis of the existing literature and other available data on national and international level and have analyzed the trends in identification of HNVFs. Based on the performed analysis, 21 criteria have been proposed to be used for identification of such forests. These criteria have been discussed on a separate workshop, followed by a separate report with updates of the primarily identified criteria. A data form was developed and tested on the field with relevant stakeholders (mainly planners) to set the pace and methodology for data collection from the field and processing. Based on the available data and identified criteria, several pilot sites have been identified and are currently being negotiated with MOEPP, MAFWE, PE National Forests and other relevant stakeholders. Once the pilot sites are selected, experts will initiate the planned field research, while the guidelines are expected in late 2019 or first quarter of 2020. Output 2.1.3: Protected areas management plans are prepared according to new methodologies and PA staff, environmental inspectors, ranges and forest guards are trained under the updated biodiversity management regime Terms of reference for management plans for Ohrid Lake and Shar Mountain have been developed and consulted with MOEPP and other relevant stakeholders, while negotiations with local partner are initiated. The activities are expected to start during October 2019. Certain progress has been identified in the implementation of planned activities under the third project component: Output 3.1.1: Guidelines are prepared for proposed revision of National Spatial Plan that relates to biodiversity conservation and a spatial planning database (spatial and urban planning) is developed, and capacities of spatial planners on mainstreaming biodiversity conservation into national planning is built The Balkan Foundation for Sustainable Development (BFSD) was contracted at the main local partner in updating the national soil erosion plan, and development of soil sealing rate database and forest vegetation maps for three pilot sites. Two introductory workshops have been held for the purpose of presenting the project team, methodology for collection and processing of data and results to be achieved. Technical specification is identified and necessary terrain equipment purchase is ongoing, while experts have been analyzing the existing literature and other sources data and started with field work planning activities. Output 3.1.2: Supporting documents for proposed revision of Forest Management Plans for areas managed by National Forests are developed with an aim to introduce ecologically sustainable forest management practices and inclusion of specific elements for threatened biodiversity The NGO Connecting Natural Values and People (CNVP) have been selected to lead the implementation of the planned activities under this output. Initially, several consultation meetings have been held with MOEPP and representatives from the PE National Forests (PENF) and Ministry of Agriculture, Forestry and Water Economy (MAFWE). The purpose of these meetings was to present the methodology for development of the planned results, as well as collection of available data from all relevant institutions. Afterwards, experts continued with analysis of the legal, economic and institutional framework in the country in terms of determining the status with the non-timber forest products, the local knowledge on the proper collection and processing of such products and further trade and management with the same. The analysis results are expected to be shared in end of August or in September 2019. In parallel, several trainings have been organized on national and local level, to present the meaning and importance of NTFPs, the status in the country, other countries experiences and practical testing. Bulgarian experts have also been engaged to contribute and share their EU experience on this topic. A study visit was organized in the period 15-18 April 2019 in Central Balkan National Park Bulgaria with participants from MOEPP, Faculty of Forestry, PE National Forests and national experts. The objective of the study visit was to demonstrate positive examples for sustainable use of non-timber forest products (NTFPs), legal basis, management, control and to increase the knowledge of relevant stakeholders related to NTFPs management. Some of the conclusions from the study visit include: - All relevant EU directives are transposed in both countries; however, it is of crucial importance to look at the specifics how this functions in practice. It is the responsibility of the Ministry of Environment same as with the National Nature Protection Service in Bulgaria, to do their best in order to conserve the biodiversity but in the same time ensure the balance between the economic interests and the nature conservation. In this line the main recommendation is to put all efforts in improvement of the processing capacities in the areas from where the NTFPs are collected. This will enable adding value to NTFPs. Local communities would provide support to conservation of the localities only if they have a livelihood based on the sustainable use of NTFPs. - Data is crucial for nature conservation. Without data, it would be very difficult to reach the conservation goals and all nature conservation efforts will be chaotic. - Joining the forces of different national and local authorities (especially MOEPP and PE National Forests), institutions, local people and businesses will contribute to protection and sustainable use of the so-called healing gold or non-timber forest products in the Republic of North Macedonia. And Bulgaria, with its practical experience and knowledge is definitely a good example of protection and economizing the forest and its NTF products in a sustainable manner. - To study the Bulgarian NTFPs legislation and select relevant examples for adoption in North Macedonia. - To study the Bulgarian biodiversity monitoring system and adopt relevant for North Macedonia approaches, documents, etc. - Presentation and discussion on the e-system of issuance of permits for NTFPs in North Macedonia - Clear indication that North Macedonia does not have quotas and thus, permits are issued for all requested quantities. - There are no proper cross-border controls, which raises the question of required training on control and registration. - The general public needs to be informed on the meaning of quotas, how they are identified and how they are used, what are NTFPs and their sustainable use and similar topics. Further on, the expert team organized a training on the methodology for determining quantities for sustainable use of medicinal plants and wild berries. The training was attended by representatives from national parks, PE National Forests – local office, UNEP, CNVP, Faculty of Forestry, expert team, as well as local collectors of NTFPs and further producers in the processing chain. In addition to the theoretical knowledge, there was a practical testing for collection of Juniperus communis and discussions on the existing problems with collection and trade in the country, which finally impacts the nature conservation process. Finally, similar conclusions have been made during the national workshop on the sustainable use of NTFPs (5 June 2019, Skopje), whereby all present institutions, experts and concerned parties expressed their positive attitude and are prepared for a long term cooperation and involvement on this topic. Collection of NTFPs in North Macedonia is considered a tradition. But, the country is facing with many problems, such as: lack of consolidated legal and institutional framework; lack of proper collection control; lack of quotas for collection and trade with NTFPs; no methodology for calculation or payment of taxes for export, while there is also a lack of precise data on the national market; currently licenses are issued for any quantities and the country does not have a control mechanism and so on. In the following period and in addition to the reports on the legal, economic and institutional framework on NTFPs, the experts will continue with field work and establishing quotas for one species Uva ursi for the entire territory of the country and will use another methodology for another species (Juniperus communis) in one pilot area in the eastern part of the country. Following the great political turmoil in the country, the Project Steering Committee had its first meeting in February 2019. The objective of this Project Steering Committee meeting was to present an overview of the previous years’ outlining the project activities, any challenges experienced during implementation, as well as the way forward with the project implementation. Some of the conclusions and how they were addressed is presented below: - PSC requested from the project team to review to possibility and propose necessary budget for development of valorization study for Ohrid Lake, as suggested by MOEPP and the Macedonian Government, while MOEPP to provide more details on the same suggestion, with possible partners and possible duration. – Necessary budget was allocated; TOR has been developed and is being negotiated with identified partner. Implementation activities to start in October 2020. - The project team to review and adapt the project work plan based on the current developments and indicate whether these changes will have impact on the project outcomes – The work plan has been reviewed and at this point no major delays are expected. - It is necessary to establish a communication platform in order to enable greater transparency and improve the coordination with PSC members. Since the Vienna Programme Office is developing such platform, it is necessary to find a way to properly present the STAR5 results (and other previous project results). – The project team is currently developing information on the project and implementing activities, which will soon be available on the UN Environment Vienna platform. In addition, some information on the national red lists and in general about the project will be presented on the national RLs web site, once developed. Next PSC is planned in the second half of October 2020. |  |  |  |  |  |

| Risk Rating | FY 2018 | FY 2019 | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | L |  |  |  |
| Project’s overall risk is low and major changes are not expected to have a significant impact on the planned for deliverables of the project. |  |  |  |  |  |

| Stakeholder engagement | As specified in the Project Communication Strategy developed during the first year, the relevant activities have to ensure commitment of all stakeholders at all stages of the project; ensure that their expectations are met through negotiation and continuous communication and anticipate possible problems and address potential concerns through the entire project span. The following activities have been taken in the reporting period: - Numerous coordination meetings within different project components with representatives from MOEPP, MAFWE, PE National Forests and other relevant stakeholders, - Organization of study visit for development of the Shar Mountain Socio-Economic Study with local communities, experts and university staff, - Trainings to build institutional capacities and facilitate knowledge and technology transfer, with particular focus on public participation, assessment and knowledge management, and special consideration on gender equality and minority rights (for example, VS and SES meetings, HNVFs and QNTFPs workshops, IUCN meetings and workshops), - Enhancement and capacity building on state and local level representatives in terms of involvement of local communities in the daily management of protected areas, development of planning documents, financial management. In addition, particular attention will be placed on this topic during the pilot testing activities within different project components, promoting of Shar Mountain as future protected area, as well as improved access to information through the UN Environment web hub, MOEPP web site and through the special RLs web site on national level. |
| --- | --- |

| Gender mainstreaming | Stakeholder engagement in the reporting period included appropriate gender responsive measures that resulted in following gender related statistics: Activity; Men; Women. Steering Committee; 12; 7. Third Italian Study visit; 10; 9. SES workshop; 15; 12. RL assessment workshops; 5; 5. First HNVFs workshop; 16; 13. Second HNVFs workshop; 58; 40. Forest vegetation maps workshop; 12; 9. Soil erosion and soil sealing workshop; 10; 12. National QNTFPs workshop; 15; 12. Training in Pehchevo; 10; 10. Bulgaria Study visit; 7; 8. Total; 170; 137. It can be concluded that involvement of appropriate ratio of women / men has been applied in the project activities (55,4% of men and 44,6% of women). |
| --- | --- |

| Knowledge activities and products | Consultation meetings conducted with experts, decision makers, CSOs and general public/individuals. Promotional material (banners, leaflets) have been printed and distributed on various occasions, including online materials. |
| --- | --- |

| Stories to be shared | The country has initiated the process of identification of quotas for non-timber forest products for the purpose of providing its protection while enabling sustainable use and trade. To increase the knowledge of national stakeholders and for capacity building purposes, the project has organized a study visit to Bulgaria, to the National Park Central Balkan. The story was published on UN Environment News and Stories and is available at: https://www.unenvironment.org/news-and-stories/story/rooting-sustainable-future-how-forest-resources-can-help-tackle-climate The project is receiving a significant support in capacity building of key stakeholders from Italian Ministry of Environment, Land and Sea, which granted a contribution through one more study visit in September 2018 on Shar Mountain and Tetovo Region. The exchange of knowledge and information on management of protected areas with the Italian colleagues is assessed as a positive example for future cooperation and use of useful ideas in current and upcoming projects. In addition, national experts have gained knowledge on total economic values of ecosystem services to be used during the development of socio-economic study for Shar Mountain. Similar future activities will provide further capacity development of government officials, protected area management staff and rangers, environmental inspectors, forest guards and public raising awareness. In addition to the received international trainings on the assessment procedure for development of national Red Lists, the project has developed an introductory brochure on the first National Red Lists for North Macedonia. The brochure is available in three languages, Macedonian, English and Albanian (http://ebiblioteka.moepp.gov.mk:8080/library/home) and has been shared with numerous stakeholders. It will also be uploaded on the special RL web site, once developed. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s) [copy and paste the CEO Endorsement (or latest formal Revision) approved Results Framework, adding/deleting outcome rows, as appropriate]

| Project objective and Outcomes | Indicator | Baseline level | Mid-term target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To support the expansion of national protected areas system and enabling capacity conditions for effective management and mainstreaming of biodiversity conservation into production landscape | 1. Number and ha of new protected areas | Insufficient network of national protected areas (8.9% of area protected or 230, 083ha), the process of establishment of national PA network is not completed |  | Increased national protected area network by about 1.5% of the country territory (about additional 50,000 ha or 280,083ha)). | Second phase of the development of the final version of the valorisation study for Shar Mountain ongoing. The development of a second valorisation study for Ohrid Lake is being negotiated. | S |
|  | 2. Increased capacities for effective management of protected areas | Limited capacities for effective management of protected areas |  | Strengthened capacities of at least 30 officials (♂ and ♀) and developed biodiversity information/policy for effective management. | One study visit concerning effective management of protected areas conducted. The process of creation of Red List Index in the country is ongoing. One international IUCN red list training conducted. Different coordination meetings with national experts on RLs, HNVFs, QNTFPs and VS organized. | S |
|  | 3. Number of background documents and database relevant for mainstreaming biodiversity | Limited background information and database for biodiversity mainstreaming (no Red List Index of Species) | n.a. | Supporting documents for biodiversity mainstreaming in 2 policy documents and planning processes 1 biodiversity database supporting mainstreaming | Activities on identification of quotas for non-timber forest products, identification of high nature value forests and pilot testing, as well as development of national soil erosion map, soil sealing rate database and forest vegetation maps for pilot sites, are ongoing. | S |
| Outcome 1.1: Improved biodiversity conservation through creation of new protected areas and pilot projects on corridors implementation | Network of PAs increased from existing 8,9% to 10.4% of the country territory (about 50,000 ha), Criteria for prioritization of PAs developed to support expansion of PAs Guidelines and methodologies for management of 2 corridors | Insufficient network of national protected areas, the process of establishment of national PA network is not completed Proposed areas for protection are not prioritized Testing of developed guidelines, methodologies and action plans is often missing, such as the case of corridors of MAK-NEN. | MT: Indicators/criteria for prospective PA prioritization developed, harmonized and agreed upon with decision makers including women and socially vulnerable groups At least 2 valorization studies with gender consideration of PAs prepared | ET: 2 Valorization Studies, legislation on the new PA adopted and set of national documents and requirements fulfilled to initiate proclamation procedure of new protected areas submitted with due consideration of gender issues 2 Guidelines and methodologies for pilot corridor management are tested on the ground with due consideration of gender issues. | Second phase of the development of the final version of the Shar Mountain valorisation study is ongoing Valorisation study for Ohrid Lake is under negotiation with identified partner MAK-NEN TOR developed and under negotiation with local partners | S |
| Outcome 2.1: Improved management effectiveness and capacity building as a tool for biodiversity conservation and protection of threatened species and habitats | Protected areas management capacities increased through improved knowledge of threatened species and habitats and training on biodiversity conservation and PA management. | Low management capacities to support conservation of threatened species and habitats Threatened species and habitats have not been identified (no Red List of Endangered Species) Low capacities of environment/nature inspectors, rangers, forest guards | MT: Assessment of management capacities of PAs including the role of women and vulnerable and minority ethnic and religious groups. Identified important forest habitats (High Nature Value forests). | ET: Management priorities which give due consideration to gender issues for at least one Protected Area drafted and submitted for official promulgation At least 30 officials (from existing PAs as well as to be engaged in the new PA management) and stakeholders (♂ and ♀) trained in PA management approaches Recommendations which give consideration to gender issues for conservation of identified threatened species/groups and/or habitats to be protected within new PAs. | Capacity building of national and local authorities, as well as NGOs representatives, in terms of effective management continued with a third study visit on Shar Mountain with Italian support and involvement of Italian partners Training activities of the process of creation of Red List, identification of high nature value forests, ongoing Gender balance considered | S |
| Outcome 3.1: Biodiversity conservation mainstreamed in national planning |  |  |  |  |  | S |
|  | National Spatial Plan and Forest Management Plan processes incorporate biodiversity conservation At least 10 spatial planners incorporating new methodologies recognizing biodiversity in spatial planning processes | Low level of mainstreaming of biodiversity conservation into national land use planning strategies and plans. Underdeveloped spatial planning database (does not include biodiversity aspects). | MT: Recommendations for biodiversity consideration developed to be used in the process of revision of National Spatial Plan and Forest Management Plan | ET: Spatial planning database and guidelines which give due consideration to gender issues developed to support biodiversity mainstreaming in policy processes Facilitation of at least 10 spatial planners (♂ and ♀) to incorporate new methodologies related to biodiversity in spatial planning processes | Spatial planners are being trained in identification of high nature value forests and testing of quotas for non-timber forest products under Component 2 and 3. In addition, spatial planners and foresters are also involved in the development of the national soil erosion map, soil sealing rate database and forest vegetation maps for pilot sites. The results of all these activities will present the basis for development of guidelines for revision of the National Spatial Plan and Forest Management Plan that should be initiated in the coming period. | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project is well on track and is delivering results in line with the anticipated pace and impact. With regard to the overall objective indicator –number and ha of new protected areas – the final version of the valorisation study for Shar Mountain PA is ongoing, and the development of a second valorisation study for Ohrid Lake is being negotiated. The project is further conducting a PA management study, supports the creation of a Red List Index and engages actively in coordinating national experts and entities for PA management, including through erosion, soil sealing and forest vegetation mapping, identifying high value forests, or training spatial planners. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk. Projects should complete only the relevant sections and are free to add/delete problems/risks. This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets |  |  |
| on stakeholder engagement |  |  |
| on gender actions |  |  |
| on safeguards |  |  |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| on sustainability of results |  |  |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implementation status as of 30 June 2018 | Implementation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc.) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: Supported Establishment of at least One Protected Area (Shara Mountain – 42,000 ha) as National Park | End of September 2019 | 40% | 70% | Final version of the Shar Mt VS is expected to be delivered by the end of 2019. Local partners are being negotiated for development of VS for the second agreed area – Ohrid Lake. | S |
| Activity 1: Develop criteria for prioritization and identify areas to be elaborated and proposed for protections | End of March 2017 | 100% | 100% |  | S |
| Activity 2: Conduct workshop with relevant stakeholders (national consultations on defining territory/area coverage and location of proposed protected area, taking into consideration gender equality socially vulnerable groups) | End of June 2017 | 100% | 100% |  | S |
| Activity 3: Prepare studies for valorisation of selected sites proposed for protection according to national legislation | End of December 2018 | 30% | 60% | Final Shar Mt VS is expected to be delivered by the end of 2019. TOR for development of VS for Ohrid Lake is being negotiated with local partners. Activities are planned to start in the third quarter of 2019. | S |
| Activity 4: Conduct series of meetings with local communities regarding new protected areas, taking gender equality and vulnerable groups into consideration | End of December 2017 End of June 2018 End of December 2018 | 30% | 60% | Meetings with different stakeholders held during the development of the second draft version of the valorisation study. Additional meetings conducted during the preparation of the socio-economic study to accompany the main valorisation study for Shar Mt. | S |
| Activity 5: Preparation of all necessary documentation and submission for approval/adoption by the Government | End of September 2019 | 30% | 40% | The process of preparation of the Shar Mt. VS is underway. The development of Ohrid Lake VS is planned to start in the third quarter of 2019. Experts are being negotiated for development of necessary documentation for submission to GO. | S |
| Output 1.1.2: Two pilot corridors from the proposed National ecological Network (MAK-NEN) selected for development and testing of site-specific measures involving local stakeholders for management and restoration of High Nature Value Forests and other habitats | End of March 2020 | 0% | 10% | Negotiations with MOEPP and local partners ongoing TOR drafted Agreement to be concluded during September/October 2019; afterwards, initiate with activities | MS |
| Activity 6: Desk analysis of MAK-NEN corridors and overlapping with identified HNV forests and rural areas | End of June 2018 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 7: National consultations for selection of 2 pilot corridors | End of September 2018 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 8: Development of management measures for selected pilot corridors | End of January 2019 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 9: Testing of site specific management measures in cooperation with local stakeholders | End of September 2019 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 10: Presentation of results and possibilities for replication to other sites | End of December 2019 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 11: Approval of management measures for MAK NEN corridors that will encompass forests or rural areas | End of January 2020 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Output 2.1.1: A “Red List Index” for Macedonia is generated, reflecting the prioritized list of threatened species within the country and guiding the creation and effective management of new and existing Protected Areas | End of project 2020 | 40% | 60% |  | S |
| Activity 12: Desk analyses of the status of species assessment and develop criteria for prioritization of taxonomic groups to be addressed | End of June 2017 | 100% | 100% |  | S |
| Activity 13: National consultation – presentation of criteria and most prioritized groups for development of red list (in cooperation with IUCN), taking gender equality and vulnerable ethnic and religious groups into consideration | End of September 2017 | 100% | 100% |  | S |
| Activity 14: Establish working teams for each selected taxonomic group and selection of species | End of June 2018 | 80% | 100% | Expert working groups established | S |
| Activity 15: Conduct training of national experts for developing red lists according to IUCN criteria | End of June 2018 | 100% | 100% | National experts trained in developing RLs, already showing positive results through the RLs assessment process. | HS |
| Activity 16: Expert consultation – presentation/discussion of selected species | End of June 2018 | 100% | 100% |  | S |
| Activity 17: Conduct field work and collect all relevant information/mapping for preparation of red list of selected groups/species using IUCN criteria | End of December 2019 | 0% | 70% | Field work ongoing | S |
| Activity 18: Design and development of database for red-listing of species with web application and fill in with collected national data | End of December 2018 End of December 2019 | 10% | 50% | Negotiations on the manner of development of the database ongoing Process of selection of web developer ongoing | S |
| Activity 19: Develop methodology and fact sheet for Red list index | End of January 2020 | 0% | 50% | Ongoing | S |
| Activity 20: Presentation of results and consistency check with IUCN during national stakeholder workshop | End of January 2020 | 0% | 0% | Planned for the end of 2019 | N/A |
| Activity 21: Preparation of all relevant documentation of adoption process by the Government | End of project 2020 | 0% | 0% | Planned for the end of 2019 or early 2020 | N/A |
| Activity 22: Review of lists of strictly protected and protected species based on developed red lists | End of September 2020 | 0% | 0% | Planned for the end of 2019 or early 2020 | N/A |
| Output 2.1.2: High Nature Value Forests are identified and at least two (2) guidelines for their management are developed in favor of biodiversity conservation | End of September 2020 | 0% | 50% | Local partner engaged Two stakeholders’ workshops organized Pilot sites being negotiated Field work planning | S |
| Activity 23: Develop criteria for identification of High Nature Value forests in the country | End of September 2017 | 0% | 100% |  | S |
| Activity 24: Presentation and discussion of developed criteria with relevant stakeholders (mainly scientific community) | End of September 2017 | 0% | 100% |  | S |
| Activity 25: Conduct research of forest ecosystems to identify High Nature Value forests and delineate important sites to support biodiversity conservation | End of September 2019 | 0% | 100% |  | S |
| Activity 26: National stakeholder consultation to present results and select 2 pilot sites, including gender balance and socially vulnerable groups | End of September 2018 End of June 2019 | 0% | 30% | Consultation workshop to be organized at the beginning of July for selection of pilot sites | S |
| Activity 27: Develop guidelines for management of at least 2 High Nature Value forests through involvement of local stakeholders to be used during revision of Forest management plans | End of September 2019 | 0% | 0% | Guidelines are expected to be developed by the end of 2019 | N/A |
| Activity 28: Conduct training for implementation of management measures for these sites | End of January 2020 | 0% | 0% | Planned for Y4 | N/A |
| Activity 29: Presentation of the pilot testing results and lessons learned | End of September 2020 | 0% | 0% | Planned for Y4 | N/A |
| Output 2.1.3: Protected areas management plans are prepared according to new methodologies and PA staff, environmental inspectors, ranges and forest guards are trained under the updated biodiversity management regime | End of project 2020 | 0% | 10% | PAs identified Local partners identified and negotiations ongoing TORs for MPs for Ohrid Lake and Shar Mountain developed Once agreement is signed, implementation activities to start | MS |
| Activity 30: Stakeholder meeting to initialize the process of preparation of management plan for selected PAs | End of September 2018 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 31: Developed draft management plan with special focus on revitalizing tourism revenue and eco-system services, taking into consideration gender balance and inclusion of vulnerable groups and ethnic and religious minorities | End of June 2019 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 32: Public presentation of the draft management plan for protected area and consultations with relevant stakeholders, including gender balance and inclusion of vulnerable groups and ethnic and religious minorities | End of June 2019 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 33: Developed study assessing economic values of ecosystem services in the new protected area | End of January 2020 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 34: Selection of other priority protected areas and development/amendment of management plans | End of January 2020 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 35: Raise capacities of environmental inspectors, rangers and forest guards analysis in regards to PA management | End of December 2018 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 36: National consultations with all relevant stakeholders presenting results of capacity analysis and identifying needs for development of guidelines for training | End of December 2018 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 37: Develop training programme related to protected area management regime, HNV forests, corridors, NTFP, etc., including gender balance and inclusion of vulnerable groups and ethnic and religious minorities | End of December 2019 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 38: Pilot implementation of developed training programme, training of at least 30 stakeholders | End of June 2020 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Activity 39: Summary of the results and dissemination | End of project 2020 | 0% | 0% | As soon as the agreement is signed, local partner will start working | N/A |
| Output 2.1.4. The first Red Data Book in Macedonia for at least one taxonomic group is developed | End of project 2020 | 0% | 30% | Output depends on the selection of RLI taxonomic group | S |
| Activity 40: Selection of taxonomic group(s) for which red data book will be prepared through national expert consultation | End of September 2017 | 0% | 100% | TG selected (reptiles and amphibians) | S |
| Activity 41: Collect all relevant information for red book development | End of December 2019 | 0% | 20% | RLs for reptiles and amphibians are currently being developed | S |
| Activity 42: Red book edition | End of January 2020 | 0% | 0% | Planned for Y3-Y4 | N/A |
| Activity 43: Presentation of the results during national stakeholder workshop | End of January 2020 | 0% | 0% | Planned for Y4 | N/A |
| Activity 44: Publishing and promotion of Red Data Book | End of project 2020 | 0% | 0% | Planned for Y4 | N/A |
| Output 3.1.1: Guidelines are prepared for proposed revision of National Spatial Plan that relates to biodiversity conservation and a spatial planning database (spatial and urban planning) is developed, and capacities of spatial planners on mainstreaming biodiversity conservation into national planning is built | End of January 2020 | 0% | 15% |  | S |
| Activity 45: Preparation of national erosion and draught sensitivity map, and identification of high-risk zones and their impact to biodiversity | End of June 2019 | 0% | 30% | Purchase of necessary equipment ongoing Field work planning | S |
| Activity 46: Develop database of soil erosion risk, soil sealing rate and loss of soil organic matter on 3 pilot sites in Macedonia and analysis their impact to biodiversity | End of December 2019 | 0% | 30% | Purchase of necessary equipment ongoing Field work planning | S |
| Activity 47: Develop guidelines for revision of NSP relating to biodiversity conservation and develop training programme that links spatial planning with mainstreaming biodiversity conservation | End of January 2020 | 0% | 0% | Activities to start once preliminary results from activities 45-46 and 49-54 are developed | N/A |
| Activity 48: Conduct training of Government officials and other stakeholders on above activities, considering gender balance and inclusion of vulnerable groups and ethnic and religious minorities | End of January 2020 | 0% | 0% | Planned for Y3-Y4 | N/A |
| Output 3.1.2: Supporting documents for proposed revision of Forest Management Plans for areas managed by Macedonian Forests are developed with an aim to introduce ecologically sustainable forest management practices and inclusion of specific elements for threatened biodiversity | End of June 2020 | 0% | 50% | Planned for Y2-Y3-Y4 | S |
| Activity 49: Preparation of forest vegetation maps for 3 pilot sections as supporting documents for proposed revision of Forest management plans | End of June 2019 | 0% | 30% | Local partner engaged Introductory workshop held First pilot site selected Field work planning | MS |
| Activity 50: Identification of species of economic importance (medicinal and aromatic plants, mushrooms, forest fruits, etc.) and/or vegetation threatened by uncontrolled or unsustainable use | End of December 2017 | 0% | 100% |  | S |
| Activity 51: Conduct analyses of legal regulation for use of wild species and selection of most important species to assess annual biomass production | End of January 2018 | 0% | 80% | Draft analysis developed and under consultation with MOEPP and other relevant stakeholders | S |
| Activity 52: Results validation meeting with relevant institutions and other stakeholders | End of June 2018 | 0% | 0% | Planned for the third quarter of 2019 | N/A |
| Activity 53: Quantitative analysis of annual non timber forest products of selected wild species | End of January 2020 | 0% | 50% | Field work ongoing | S |
| Activity 54: Identify quotas for sustainable use of non-timber forest products and recommendations for monitoring | End of January 2020 | 0% | 50% | Field work ongoing | S |
| Activity 55: Develop recommendations for establishing system of sustainable use of NTFP including proposal for amendment of legislation, revision of lists of species under export permit regime, compensation fees, and institutional set up, considering gender balance and inclusion of vulnerable groups and ethnic and religious minorities | End of January 2020 | 0% | 70% | Results analysis ongoing Recommendations expected to be delivered in August-September 2019 | S |
| Activity 56: National consultation and presentation of recommendations to responsible ministries and other stakeholders | End of June 2020 | 0% | 0% | Planned for Y4 | N/A |
| Output 3.1.3: Identified quotas for sustainable use of non-timber forest products are piloted in at least one region with highest potential and need | End of project 2020 | 0% | 15% | Planned for Y3-Y4 Negotiations with MOEPP and local partners initiated TOR drafted | S |
| Activity 57: Identification of region for pilot testing of proposed quotas for use of selected NTFP with relevant stakeholders | End of December 2019 | 0% | 50% | Negotiation with MOEPP and stakeholders for selection of pilot areas | S |
| Activity 58: Conduct pilot testing of defined quotas involving relevant stakeholders and users | End of June 2020 | 0% | 0% | Planned for Y3-Y4 | N/A |
| Activity 59: Capture lessons learned for replication in other regions | End of project 2020 | 0% | 0% | Planned for Y4 | N/A |
| Output 3.1.4: Lessons learned and Sustainability Strategy Developed | End of project 2020 | 0% | 0% | Planned for Y3-Y4 | N/A |
| Activity 55: Analyse the results and lessons learned from implemented pilot projects | End of September 2020 | 0% | 0% | Planned for Y3-Y4 | N/A |
| Activity 56: Identify needs and recommendations for further development of different components considering gender balance and inclusion of vulnerable groups and ethnic and religious minorities | End of project 2020 | 0% | 0% | Planned for Y3-Y4 | N/A |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | Project activities are mostly on track. The declaration of the first new PA, Shar Mountain, is being negotiated with Government and its completion is expected for the end of 2019. ToR for the second new PA are negotiated with local stakeholders to gain their support, while negotiations on two pilot corridors are advancing only slowly (output 1.1.2), and PA management plan development has to begin soon (output 2.1.3). Activities for generating a Red List Index (output 2.1.1), while the First Red Data Book (output 2.1.4) development is prepared according to plan and selection of taxa is completed, including national consultations and related capacity development is advancing well and is equally well appreciated by stakeholders. The identification of High Nature Value Forests is advancing according to plan and respective guidelines are expected to be developed by the end of 2019 (output 2.1.2). Guidelines for spatial planning and revisions of forest management plans (outputs 3.1.1 and 3.1.2) are being prepared, their completion and implementation not yet being planned during the reporting period. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| 1. Communication among stakeholders: Evidence of poor communication across different stakeholder groups exists, which could ultimately affect a multi-focal area project | Two key mitigation tools will be employed. First, UNEP as the GEF Executing Agency through its Vienna Office will support MoEPP in the design of stakeholder workshops including the inception meeting and ensure that information is communicated fairly and openly across all groups. Second, there will be numerous national and local consultations, trainings and communication platforms created including representatives from a number of relevant sectors. In addition, at least four Inter-Sectoral Working Groups shall be designed and assigned during the project implementation: three to coordinate the project components, and one overall for administrative management of project outcomes. | At the beginning of the project, a communication strategy was developed to propose the manner of further communication with all relevant stakeholders' groups. PSC is consisted of representatives from different institutions (MOEPP, MAFWE, MANU, Ministry of Economy, Spatial Planning Agency, PE National Forests, PE Pastures Management and SDC). Mayors of targeted municipalities are being contacted and presented with the different project activities. Different local partners have been engaged for implementation of different project activities. Throughout these activities, all relevant stakeholders have been involved and communicating. | CEO: M to L |
|  |  |  | TM: L |
|  |  |  | PM: L |
| 2. Lack of Political Will: Politically appointed policy makers that lack environmental knowledge or interest may threaten sustained long-term outcomes of the project | Project component 2, output 2.1.3 was specifically designed to mitigate this risk and build the capacity of key decision makers to seriously address environmental management responsibilities. Also, other two components contain large raising awareness and capacity building trainings. In addition, special attention will be paid to equal involvement of ethnic Albanians and Macedonians to all project components. | The project enjoys political support since its development and during the entire project implementation. Monthly reports are being shared and monthly meetings are being held with MOEPP GEF Operational Focal Point and CBD Focal Point, as well as representatives from the Nature Department on the progress of implementation. All municipalities’ mayors and relevant local stakeholders have been contacted during the implementation of the different project activities in terms of pilot testing and field research. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| 3. Challenge of reforms within the forest management regime: As the arbiter of forest management plans for 75% of national forests, the PE National Forests (PENF) exercises significant power over any changes or reforms towards sustainable forest management. | This risk will be mitigated through the inter-sectoral working groups (see Risk #1). A forest working group (of which PEMF would be a part) would naturally allow other stakeholders to have say in the strategic interventions on forest management. Secondly, component three will include PEMF, which will benefit its institutional capacity as well as its relationship with civil society. | PE National Forests are members of PSC and have been involved in the project implementation since the beginnings of the project implementation. Representatives have been invited and participated on different workshops and meetings, especially in terms of development of forest vegetation maps, quotas for non-timber forest products and identification and piloting of high nature value forests. | CEO: M to L |
|  |  |  | TM: M-L |
|  |  |  | PM: M to L |
| 4. Lack of community support for local-level interventions: Community support will be critical for proclamation of protected area(s) and sustainable use of NTFPs etc. | The key factor to mitigating this risk is to have the full participation of local governments and CSOs active parts of the project. As such, including key local stakeholders in the working groups can mitigate this risk. Through involvement of local government and relative CSOs in the project activities, especially the pilot project foreseen by this GEF project the risk will be mitigated. | Full involvement and support of local communities and authorities has been provided, especially through the implementation of activities on local level (such as Shar Mt. VS, piloting of HNVFs and QNTFPs). | CEO: L |
|  |  |  | TM: L |
|  |  |  | PM: L |
| 5. Lacking institutional capacities to manage and mainstream biodiversity conservation into relevant sectoral policies | The existing low knowledge and capacity levels for the implementation of relevant biodiversity conservation and protected area management methodologies is taken into account by the project implementation strategy, through a) a focus on developing knowledge tools such as a red list index, PA management guidelines and related capacity development measures in component 2, and b) through the project’s efforts to mainstream biodiversity conservation into other sectoral plans and processes (component 3). | Existing capacities of national and local authorities, public institutions and other relevant stakeholders are fully involved in the project implementation and have been taking part in different meetings and trainings. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| 6. Climate change as a direct driver affecting ecosystems in Macedonia | North Macedonia is a very exposed to climate change, being one of the most vulnerable in the region. However, its adaptation capacities are considered very weak due to many different reasons, some of which are outlined above in the text. Climate change vulnerability will be an integral part of the training activities and awareness to be conducted in all three components of the project. Also, the mitigation measures will be more focused after the assessment of biodiversity vulnerability to climate change in the country to be conducted in the context of development of management and land use planning. | Aspects of impacts of climate change on biodiversity are being taken into consideration through different trainings and workshops in all three project components. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | Project’s overall risk is low, and the project is flexibly implementing mitigation measures to keep the risks at this low level, while there are no project-internal risks to be reported. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | X |  |  |  |  |  | PM: Project team is established and in operation. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM: Due to the political situation in the country, the first PSC meeting was held at the beginning of February 2019. It is operational and provided effective directions on work done so far and further activities. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | X |  |  |  |  |  | PM: Communication and coordination in place | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation | X |  |  |  |  |  | PM: Most of the activities are initiated on time and are well progressing. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize | X |  |  |  |  |  | PM: Additional co-financing received from the Italian Ministry of Environment, Land and Sea, for third study visit and development of socio-economic study to accompany Shar Mountain VS. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | X |  |  |  |  |  | PM: So far, activities are progressing within planned budget | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds |  | X |  |  |  |  | PM: Agreements and payments processed have been managed properly and transparently |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: financial reporting could benefit from more expedient and timely delivery |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | X |  |  |  |  |  | PM: Reports are being prepared and presented on timely manner. In addition to continuous communication, project office distributes monthly report on taken and planned activities to MOEPP. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Stakeholder involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | X |  |  |  |  |  | PM: The process of constant involvement of identified and new stakeholders is on-going. Positive feedback received from key stakeholders and partners. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | X |  |  |  |  |  | PM: Consultation meetings conducted with experts, decision makers, CSOs and general public/individuals. Promotional material (banners, leaflets) has been printed and distributed on various occasions. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: Project empowers data availability and fosters data exchange by building sustainable enabling environment for monitoring, exchange and reporting. Field research and data analysis is ongoing. Capacity building is part of each component activities. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | X |  |  |  |  |  | PM: The choice of methods is based on sound analysis of options and risks and on scientifically well-established practice. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives | X |  |  |  |  |  | PM: Since mid-2017, the political situation in the country has been stable. The project receives full political support. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | X |  |  |  |  |  | PM: The political conditions in the country have been stable since mid-2018. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions | X |  |  |  |  |  | PM: Some parts of the project area have been impacted by major floods at the end of 2016, being the reason to initiate a new LD/SLM project in the country. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | X |  |  |  |  |  | PM: No evident social, cultural and/or economic issues that may affect project performance and results. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance | X |  |  |  |  |  | PM: Sound technical and managerial capacities | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | The project’s overall risks remain low |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your project has more than 4 objective-level indicators. Same applies for the number of outcome-level indicators.

Outputs are described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent). The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.