UN Environnent GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | 5532 | SB-001062.01.05 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Disposal of PCB oils contained in transformers and disposal of capacitors containing PCB in Southern Africa |  |  |
| Duration months | Planned |  | 60 months |  |  |
|  | Extension(s) |  |  |  |  |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste |  |  |
| Executing Agency(ies) |  |  | Africa Institute |  |  |
| Names of Other Project Partners |  |  | Southern African Power Pool |  |  |
| Project Type |  |  | FSP |  |  |
| Project Scope |  |  | Regional |  |  |
| Region |  |  | AFR |  |  |
| Names of Beneficiary Countries |  |  | Botswana, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, Swaziland, Tanzania, Zambia, Zimbabwe |  |  |
| Programme of Work |  |  | Chemicals and Health Programme of Work |  |  |
| GEF Focal Area(s) |  |  | POPs |  |  |
| UNDAF linkages |  |  | Where appropriate, insert the UNDAF strategic objective to which achievement the project contributes. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Where appropriate, insert the most relevant SDG target(s) and indicator(s) to which the project contributes |  |  |
| GEF financing amount |  |  | 7710000 |  |  |
| Co-financing amount |  |  | 33661319 |  |  |
| Date of CEO Endorsement |  |  | 01-Jun-16 |  |  |
| Start of Implementation |  |  | Sep-16 |  |  |
| Date of first disbursement |  |  | Nov-16 |  |  |
| Total disbursement as of 30 June |  |  | 1462363 |  |  |
| Total expenditure as of 30 June |  |  | 1250452 |  |  |
| Expected Mid-Term Date |  |  | Mar-19 |  |  |
| Completion Date |  | Planned | Sep-21 |  |  |
|  |  | Revised | na |  |  |
| Expected Terminal Evaluation Date |  |  | na |  |  |
| Expected Financial Closure Date |  |  | Sep-22 |  |  |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

| UN Environment Subprogramme(s) Chemicals and Health Subprogramme | Specify the relevant Expected Accomplishment(s) & Indicator(s) |
| --- | --- |
| Describe any progress made towards delivering the stated PoW Expected Accomplishments and Indicators. State key changes since previous reporting period. [Section to be shared with relevant Regional and Global SubProgramme Coordinators] During the last year, the project has confirmed the presence of just over 800 tonnes of contaminated oils and equipment, of which approximately 600 tonnes is ready for disposal in the coming year. This is well below the project target of 4,300 tonnes but does not include in-service equipment which will have to be phased out gradually in line with the Stockholm Convention deadlines of 2025 and 2028 for stopping use and elimination of equipment respectively. National regulations reviews have been initiated with engagement of a regional consultant and national consultants in 8 of the 12 project countries. The BRS Secretariat has provided technical support in reviewing the regional consultant inception report. A Management Review was initiated during the project period and has made the following recommendations for consideration and confirmation by an Extraordinary Steering Committee Meeting (Pretoria, 10-11 Oct 2019). - Rebalancing of target quantities of PCB equipment for overseas disposal and in-country dichlorination of waste, in recognition of the lower-than-anticipated amounts of highly contaminated wastes identified during the inventory phase - Review of expected dates of achievement of targets; - Restructuring of logical framework to distinguish between inventory of equipment for disposal (new Output 3.1) and inventory of in-use equipment for long term phase out (Output 2.1) - Budget revision including re-allocation of funds between components - Additional support to the Executing Agency and project countries to allow acceleration of delivery - Update of legal instruments with countries to include country-specific budgets, workplans and commitments including registration of project with Government. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
| Core Indicator 9: Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products - 9.1: Solid and liquid Persistent Organic Pollutants (POPs) removed or disposed (POPs type) - 9.4: Number of countries with legislation and policy implemented to control chemicals and waste | Indicative expected Results The project will dispose of 4,300 tonnes of transformers, capacitors, and PCB contaminated oil . The project will produce national regulations in 12 countries on the environmentally sound management of PCB and PCB wastes in the context of the Stockholm Convention.” |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. In the previous reporting period (2017-2018), the only activity started was Inventory verification and related training. None of the other planned activities were started or completed. As a result the expenditures were lower than planned. In the current reporting period, the project initiated a Management review as the expenditure was below 15% and none of the previously planned activities were completed. Component 1: Legal review Legal review process has taken off with 8 countries having national lead persons or consultants. The remaining countries are Botswana, Seychelles and Zambia which are expected to start in quarter 3. A regional legal consultant is engaged and is submitting the inception report on the 15th July, which shall include both the assessment framework that will help the national consultants and the ESMP for collection and transportation of oils. Component 2: Inventory verification The Inventory verification had been slow and upon submission of all countries the Inventory verification has since yielded a database that reflect only 99 639 kg of contaminated oil and a total of 818 368 kg oils and equipment that includes 7289 capacitors from Cahora Bassa (CHB) Mozambique. Processes of removing the above for disposal may be started. Based on the results to date, it should be appreciated that the quantity of contaminated oil may not come close to the expected and set target of 4300 tonnes. Further consultations have been started with all countries to cover pole mounted distribution in service equipment in order to get closer to the targets. Madagascar and Tanzania have already started in this phase. Madagascar and Mozambique coverage of inventory verification was questionable and need to be taken further. Tanzania has submitted further 400 sample which are still with the laboratory at the time of reporting. Zimbabwe samples indicated no contamination above 50 ppm and this is also questionable and need to be verified. Component 3 on disposal has not yet been initiated. Under the proposed restructure of the project logframe, a new Output 3.1 is proposed, on the inventory of stocks to be disposed. If this is approved, the project has completed that output with approx. 800 tonnes of wastes inventoried. The call for Expressions of Interest for this initial disposal tender has been prepared, along with an initiatl Component 4: Awareness raising and Information sharing All the countries have started the program of Risk communication strategy development and rollout, except Seychelles. The exercise is mainly driven by governments’ teams except in Mozambique where African Foundation for Sustainable Development (AFSD) has been engaged. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. The objective of the UNDAF is to maximize individual and collective impact of all UN programmes of assistance in support of the national plans and priorities of recipient Governments. Chemicals and waste are integral to almost all sectors of society, and their sound management is essential for protecting human and environmental health. This is the case in the participating countries The projects also aims to enhance the collaboration and coordination of system wide operations in improving efficiency and effectiveness of UN development assistance to all participating countries, it brings together Environment, power supply and the general national governance in environmental management. Botswana: under the Environmental goal, the project is directly Fulfilling ratified conventions; Sustainable natural resources management; Pollution control; Institutional strengthening; Mainstreaming environment; Environmental education and Public awareness. Eswatini: out of the 5 thematic areas, the PCB elimination contributes to Environmental management and disaster preparedness as well as Good governance and Human rights. Lesotho: The project is strongly contributing to increased community participation in environmental management through its wide awareness program and training. Madagascar: Issues of governance and capacity for environmental management are relevant. Malawi: The pillars of UNDAF in Malawi respond to the identified root causes of development challenges in Malawi. The PCB projects is directly linked to 3 of them: 1 Poor governance and 2. Climate change and 5. Negative social norms. Mauritius: Both the UNDAF objectives for Mauritius are covered. These are sustainable management of natural resources and integrated waste management, cleaner production, emission reductions and pollution control. Mozambique: In Mozambique the UNDAF targets among others the area of disaster risk reduction, with linked concerns of disaster risk reduction, adaptation to climate change, and environment and natural resource management, with the aim of strengthening the legislative framework as well as planning and management capacities of national-level institutions as well as of local governments. Namibia: of the 4 pillars, environmental sustainability and natural resources management speaks to and includes hazardous chemicals such as PCBs. Seychelles is focusing on High-quality, inclusive and results-oriented development strategies for countries’ ownership over their development and the implementation of the 2030 Agenda and the Sustainable Development Goals (SDGs) in general. This project in the phase out plans, awareness and capacity building contributes to this. Tanzania: In Tanzania again, the PCB elimination project contributes to Environmental management and disaster preparedness as well as Good governance and Human rights. Zambia: out of the 5 broad UNDAF outcomes, the PCB elimination contributes also to Environmental management and disaster risk reduction response as well as Good governance and Human rights Zimbabwe: in the 6 priority goals, the PCB project is linked to issue of governance and participation to a limited extend. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes Chemicals and waste management play an important and increasingly significant role in every economic and social sector. Sound management of chemicals throughout their lifecycle is essential to avoiding complex risks to human health and ecosystems, and substantial costs to national economies. Similarly, sound management of chemicals and waste is necessary to maximize the potential benefits of their contribution to human well-being. Chemicals and waste management are reflected explicitly in a number of goals and targets, including those addressing health, water, cities and human settlements, and responsible consumption and production. Moreover, they relate implicitly to the goals on poverty, agriculture, oceans, decent work, climate change, and while less pronounced, their contribution is also important in areas such as education and gender equality. Sound management of chemicals and waste underpins the effective implementation and achievement of the Goals at the country level. Mainstreaming the sound management of chemicals and waste within national development plans is therefore vital. Failing such integration, the complex and interlinked range of hazards and risks of chemicals will continue to cause adverse impacts on the environment, human health, and economic development. |
| --- | --- |

[complete the fiscal year and select: 1st PIR; 2nd PIR; …. Final PIR.  Add more columns if needed]

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MU | MU |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. The GEF strategic Priorities and Targets are to destroy 4,300 tonnes of PCB equipment and oils. In this reporting period inventory verification has been completed in all participating countries. The inventory conducted to date suggests a far lower amount of highly contaminated waste PCB oil and out of service equipment exists in the countries than was indicated by the NIPs and estimated at the project design phase. The original targets can only be met if the project addresses in-service equipment. Secondly, the regulatory framework for ESM of POPs will be reviewed and regulations developed as per the needs of the countries. Legislation review towards closing the existing gaps have just started and almost all countries are in the process, and this is the same for risk communication or awareness raising. All these activities are now running with the expected dates being Q4 of 2019. The overall review of the project status and future direction to be taken in October 2019 at Extra Ordinary PSC meeting. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MU | MS |  |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. The first two years of Implementation of planned activities were unsatisfactory as a result of slow absorption of the project in participating countries. Focus in all countries was on Inventory verification (Component 2) as the core activity hence legal reviews (Component 1), awareness raising and capacity building (Component 4) were given low priority in previous years. Following the 3rd PSC meeting in February 2019 and the management review, some adjustments to execution arrangements were made and the Components 1 and 4 have been accelerated. A six months action plan was developed that focussed on Legal reviews and awareness raising. Funds were disbursed for both activities upfront and started in June 2019 and will continue in Q3 as proposals are received. Thus out of the 12 participating countries, 10 have received funds for risk communication development and roll out, 8 have engaged national legal review lead persons/consultants and these activities are planned to be completed in the 4th quarter of 2019. Training of the Customs and Chemicals Inspectors (Component 1) was undertaken, together with Inventory technical meeting that led to more attention being given to execution of Inventory verification. The Inventory verification exercise was accelerated in most countries and partially completed in the reporting period, and with additional support from Africa Institute in sampling analysis and compilation of data. A database of confirmed contaminated oils, indicating coordinates and quantities has been developed and included into a GIS platform, enabling a rapid environmental screening to be performed of the numerous sites of contaminated equipment. An extraordinary PSC meeting with additional participation of GEF operational Focal person was planned for October 2019. The major challenge of the regional project remain the low capacity to draft proposals and plans of national activities. Submission of these in order to release funds remain the real bottleneck and time is lost through the process. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | Low | M | M |  |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/ high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 Two of the countries that remained behind with PCA signature, finally signed and started inventory verification. These are Zambia and Tanzania. The risk rating of last year had increased from low to Medium mainly due to the persisting slow response of the countries to execute activities. Following the 3rd PSC meeting and subsequent Management review, a clear identification of activities to be executed by countries were established with national work plans drawn from the approved regional one. Additionally funds were then disbursed for those activities. This has had an effect of getting the countries to be engaged in execution. More consultants were even appointed and some cases like Mozambique, an NGO was brought in to execute awareness program. The Risk rating is kept at Medium because while activities seem to be engaged, they are yet to be reported end of Q3, hence the real improvement will be assessed then. It is however evident that countries had challenges in requesting for funds through proposals, once this was simplified, the challenge fell off. |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) All relevant stakeholders have been part of the project and continue to be engaged in the improvement of implementation. These include Utility management, Utility association, NGOs and Heavy industries like mining and manufacturing. SAPP has been contributing to the Steering Committee. In the reporting period, the Implementing Agency reached out to its management to increase their engagement especially in bringing its members to provide technical and infrastructure for safeguarding PCBs. Mozambique and Tanzania have engaged NGO in their awareness program. In Botswana, Mining and defence were trained and undertook their own inventories. In Namibia, the Regional Electricity Distributors (REDs) and Windhoek city council were fully engaged with consultant in the Inventory verification. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/ Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. Gender mainstreaming has to a lesser degree been evaluated and only in so far as the vulnerable groups are assessed at country levels. The most vulnerable groups have been found to be workers/technicians in the utility companies and school children who may be exposed to leaking transformers in their own yards. Opportunity exist in the project to target these groups with risk communication roll out |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/ products (when applicable), as outlined in knowledge management approved at CEO Endorsement/ Approval The database developed following the Inventory verification is being mapped through the MapX program and good practices in the ESM of PCBs is being documented for sharing in various platforms. These shall be the main knowledge products for sustainability of PCB phase out. They can be accessed (after approval of account) at https://app.mapx.org/?project=MX-U83-0SB-Y2T-A48-GFS&language=en Press releases were done with interviews after the RSC meeting and at the BRS COPs in May 2019. These can be accessed at https://www.unenvironment.org/news-and-stories/story/dangers-modern-magic |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. There are a few stories of interest that can be shared with the world from this project: 1. Extent of PCB contamination and vulnerable groups in the sub region 2. Bad and Good practices of the PCB containing equipment owners in the sub region 3. Cost benefit analysis of replacement of old electrical equipment |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To reduce environmental and human health risks from PCB releases through the demonstration of a regional approach to the introduction of cost-effective and socially acceptable environmentally sound management (ESM) of PCB oils, equipment and wastes held by electrical utilities and other PCB owners in participating countries. | 1. Number of participating countries with legislative framework for ESM of PCB in place | Lack of legal background, administrative and technical capacities for ESM of PCB at national level limiting from participating countries to fulfil their obligations Legislative review completed to varying extent in each country’s NIP | Legislation in 12 countries reviewed; | Legislation in 12 countries developed; | 8 countries have engaged national consultants and 2 inception reports have been submitted by Lesotho and Zimbabwe. A regional Consultant has also been engaged and introduced to participating countries. These occurred towards the end of Q2 hence progress rating of MU. | MU |
|  | 2. NO of countries with strengthened administrative and technical capacities as well as PCB disposal plans in line with Stockholm convention | Lack of administrative and technical capacities for ESM of PCB at national level limiting from participating countries to fulfil their obligations | All inventories verified and Database populated in full | Inventory verification conducted and documented in databases of 12 countries; Regional disposal plan developed and approved; | Inventory verification is completed in Botswana, Lesotho, and Tanzania. The rest of the countries have not covered pole mounted distribution equipment. The regional Disposal plan has been established. | MU |
|  | 3. Number of tonnes contaminated equipment disposed of from 12 countries | No disposal of contaminated equipment done; Risks for human health and environment remains | Items to be disposed have all been collected into national temporary storages | 4,300 tonnes of PCB oils, equipment and wastes successfully disposed of | Not yet started, this activity is the last part of the project | N/A |
| Outcome 1A National regulation and international requirements identified in 12 participating countries including infrastructure and enforcement capacities Outcome 1 B Regionally harmonized approach for the environmentally sound management of PCB oils, equipment and wastes | No. of countries submit for adoption national regulation with minimum requirements of Stockholm and Basel Conventions supported by Guidance documents for different aspects of ESM of PCB No. of regional action plan developed and adopted through appropriate means and processes at the regional level; No. of application of regional action plan in participating countries | 12 countries are without proper legislative framework for management of PCB No regional approach; NO ESM of PCB in 12 countries | NCCs established 12 countries submit for adoption PCB regulations | NCCs established and executed the project 12 countries submit for adoption PCB regulations | Regulatory review is well underway in 8 participating countries and will be expected to complete in December 2019. 3 more are expected to start in August 2019.. | MS |
|  |  |  | Regional scheme in place | Regional scheme in place | Regional scheme to be developed following verified inventories | N/A |
| Outcome 2 12 countries monitoring PCB containing equipment in service and tracking system established to follow until final phase out of PCB in electrical equipment | No. of regional template for inventory and tracking system development; No. of countries to adopt and use template; No. of countries develop and adopt inventory verification plans; Regional phase out plan detailed until 2025 in accordance with the phasing out priories of Stockholm convention and Code of practice for the safe use of fully enclosed askarel‐filled electrical equipment | Limited activities on PCB in the countries; No detailed inventories available ; No phase out plan | Year 1: 6 countries complete inventories; Year 3: 12 countries complete Inventories; 12 countries with information included in national databases; 6 countries’ phase‐out plans endorsed at national level by utility companies and other PCB containing equipment owners | 6 countries complete inventories; 12 countries complete Inventories; 12 countries with information included in national databases; 12 countries’ phase‐out plans endorsed at national level by utility companies and other PCB containing equipment owners; | All countries have undertaken inventory verification to varying degrees. 3 countries-Zimbabwe, Madagascar and Mozambique would need follow up actions to verify the coverage. | U |
| Outcome 3 PCB and PCB containing equipment disposed of in an environmentally sound manner in accordance with the Stockholm Convention from 12 countries | Number of utilities with trained personnel and procedures in place to perform collection, drainage and transport of PCB No of Companies licenced to collect, drain and transport PCB hazardous waste available in the region No of pieces of equipment exported for destruction No. of tonnes destruction in dedicated facility; | No licenced PCB waste handling companies; PCB contaminated transformers and capacitors not managed and disposed in ESM; No independent monitoring PCB contaminated transformers and capacitors not managed according to ESM | Year 3: 1 licences database established; 12 facilities for national storage of PCB wastes available; 6 service providers for collection, draining and transport available; 1000 capacitors collected and transported; Year 4: 3,800t contaminated oil drained, and transported to national storage; 1 agreed international transport and disposal tender; Year 5: 3,800t of PCB contaminated oil dechlorinated. 500t of PCB oil and PCB equipment disposed of in licensed facility abroad. | Licences database established; 12 facilities for national storage of PCB wastes available; 6 service providers for collection, draining and transport available; 1000 capacitors collected and transported; 3,800t contaminated oil drained, and transported to national storage; 1 agreed international transport and disposal tender; 3,800t of PCB contaminated oil dechlorinated. 500t of PCB oil and PCB equipment disposed of in licensed facility abroad. | Activities will only start after Inventory approval | N/A |
| Outcome 4 Stakeholders are aware of the need to phase out PCBs in an environmentally sound manner and best practices developed for implementing ESM for ongoing management of in-use transformers in project countries, and for subsequent projects | Vulnerable groups identified across the region, and risks of PCBs communicated PCB project website developed and maintained Regional workshop held including participation of private sector, regional agencies and regional associations and other stakeholders, to share lessons learned | No regional PCB ESM reports, some regional learning and advice through SAPP Minimal Communication of risks associated with PCBs to vulnerable people. Vulnerable communities remain unidentified. | Year 1: 1 Project website developed and maintained; Regional communication strategy in place. Year 2: National communication strategies and identification of vulnerable groups; Year 3: Implementation of risk communications and risk reduction awareness programs implemented; Year 4: Ongoing implementation of risk communications and risk reduction awareness programs implemented; Disseminated best practices for introduction of ESM taken up regionally and internationally Year 5: Ongoing implementation of risk communications and risk reduction awareness programs implemented; | Project website developed and maintained; Regional communication strategy in place. National communication strategies and identification of vulnerable groups; Implementation of risk communications and risk reduction awareness programs implemented; Ongoing implementation of risk communications and risk reduction awareness programs implemented; Disseminated best practices for introduction of ESM taken up regionally and internationally Ongoing implementation of risk communications and risk reduction awareness programs implemented; | Project webpage in place within the www.africainstitrute.info . Page updates will be done after PIR submission to indicate progress levels SAPP is preparing their proposal after which submission consultations will engage the web link. | MS |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MU | MU | Summarize the annual progress towards meeting project results. Describe any significant [expected and unexpected] environmental or other changes (Results) negative and or positive attributable to project implementation. State any key changes since previous reporting period. Also, please discuss any major challenges to meet the objectives or specific project outcomes. Whenever possible, please provide evidence of attribution between the UNEP/GEF project’s intervention and observed changes towards the achievement of direct outcomes. In cases where several actors are collaborating to achieve common outcomes, evidence of the nature and magnitude of the UNEP/GEF project’s ‘substantive contribution’ and/or ‘credible association’ should be described. This information provides the rationale for the Development Objective Rating in Section 2. While project implementation has picked up in the reporting period, the results in terms of contaminated equipment disposed or treated, and of new legislation and policy, has not been achieved during the last year. The inventory that has been completed is a significant step forward but indicates that the amount of contaminated wastes is likely to be lower than anticipated, with less than a third of samples of suspect equipment containing PCB >50 ppm. The Management Review proposes to address this gap by additional efforts on phase out of in-service equipment, including through working with sectoral investments on grid upgrades in the project countries. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Less than expected contaminated oils and equipment | Revision of targets for overseas disposal of waste and in-country dichlorination of waste, in recognition of the lower-than-anticipated amounts of highly contaminated wastes identified during the inventory phase Continue with 2nd phase/extended inventory for second phase of disposal in Y4 or Y5 Stop trading in scrap equipment with the assistance of SAPP and via regulations |
| on stakeholder engagement | Less interested/non-cooperative equipment owners | Accelerate Component 1 to promulgate regulation that puts responsibilities on owners for Stockholm convention obligations More strategic partnership with SAPP and investment projects in the region to engage utilities |
| on gender actions | No gender disaggregation of stakeholder analysis | Undertake robust risk assessment following confirmed contamination and provide additional technical support from UNEP Chemicals and Health branch under Component 4 on best practices |
| on safeguards | Lack of capacity in the countries | Train utility technicians in safeguarding and sustainable ESM of PCBs Provide technical support to ensure supervision of contractor during field operations |
| on delivering GEF Core Indicators | See ‘targets’ above |  |
| on delivering of PoW EA | See ‘targets’ above |  |
| on sustainability of results | Low levels of commitment/political support | Keep advocating for governments commitment and partnerships and ensure legal reviews result in updated regulations |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc) | Progress rating |
| --- | --- | --- | --- | --- | --- |
| 1.1 National regulations in 12 countries on the ESM of PCB and PCB wastes in the context of the Stockholm and Basel Conventions reviewed | Sept. 2019 | 0% | Started in June 2019 | The legislation review started late in Q2 but shall be delivered in good time for the project | MS |
| 1.2 Improved administrative capacity for controlling PCB in 12 participating countries – customs training | Sept 2018 | 0% | Completed in Sept 2018 | Project output delivered | S |
| 2.1 Detailed inventories of PCB containing oils and equipment held by utility companies in 12 participating countries developed (in use and in waste) | March 2019 | 0% | First batch of inventories completed | Most countries have not yet covered distribution equipment | MS |
| 2.2 Detailed inventories of PCB containing oils and equipment held by other sectors in 12 countries developed | March 2019 | 0% | First batch of inventories completed | Most countries have not yet covered distribution equipment | MS |
| 2.3 Phase out plan endorsed by utility companies and other PCB containing equipment owners | March 2020 | 0% | Discussion paper developed | Not due in period | MS |
| 3.1 Training of utilities for collection, draining and transport of PCB contaminated transformers | March 2020 | 0% | 0% | Not due in period | N/A |
| 3.2 At least 4,300t of PCB contaminated oil and associated transformers collected at national storage facilities | Dec 2020 | 0% | Partial Database available | Not due in period | N/A |
| 3.3 At least 1,000 capacitors containing PCB oil identified and collected at the central interim storage site before export/treated | Dec 2020 | 0% | Partial Database available | Not due in period | N/A |
| 3.4 3,800t of PCB contaminated oil dechlorinated | Dec 2020 | 0% | Partial Database available | Not due in period | N/A |
| 3.5 PCB from transformers and full capacitors (expected 500t) exported for destruction at a dedicated facility | Dec 2020 | 0% | Partial Database available | Not due in period | N/A |
| 4.1 National and regional communications / outreach / awareness strategies developed and implemented | Dec 2019 | 0% | Started in Q2 2019 | All countries submitted proposals and started work | MS |
| 4.2. Lessons learnt framework developed for replication and extension at national level following adoption by national authorities. | Sep 2021 | 0% | 0% | Not due in period | N/A |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MU | MS | The rating of progress in the delivery of outputs should be assessed in terms of both quantity and quality. The assessment must consider ownership by, and usefulness to, intended beneficiaries and the timeliness of their delivery. Use the comments column to explain the reasons behind the success or shortcomings of the project in delivering its programmed outputs and meeting expected quality standards. After a slow start in Jul – Dec 2018, the initiation of the Management Review and the regional Steering Committee meeting resulted in a noticeable acceleration of delivery, both in terms of activities and expenditures in Q1 and Q2 of 2019. The inventory completed is essential for the development of the disposal strategy and tender. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Late implementation that may lead to non-attainment of other targets | Project coordination to provide continuous support through demonstration and monitoring visits, | UNEP technical support | Quarterly |
| National management structure does not efficiently assign responsibility for actions leading to late response and implementation | Development of a simplified national delivery structure with revised legal instruments with countries and registration of the project with all participating Governments. | Project manager and country focal points | Dec 2019 |
| Late and non-reporting of financials leading to Quarterly reports not including all disbursed funds which remain unliquidated | Continuous reminder and requests for quarterly reports | Project manager | Monthly |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Lack of national government engagement | Focal points have been closely consulted during project development and will be members of national steering committees, playing instrumental roles in coordinating actions at the national level between governments and electrical utilities. | Governments signed Project Cooperation Agreement to fully engage, provide participation and undertake all national activities as may be scheduled and particularly financial reporting. However, PCAs are based on the regional workplans and budget and not registered at a Government level. This will be corrected in 2019. All issues discussed at PSC meetings. | CEO: M |
|  |  |  | TM: H |
|  |  |  | PM: M |
| In‐service transformers identified as PCB contaminated equipment | Utilities have committed significant co‐finance to the project, this co‐finance is for both staff time, and the cost of replacing transformers In instances where the transformer cannot be decommissioned and replaced within the lifespan of the project, the transformer will be included in the PCB phase‐out plan, with an agreed timeframe for taking the transformer offline, and for safeguarding the oil, and transformer casing | Negotiations undertaken with Utilities and SAPP to replace highly contaminated transformers, but where this is not feasible the equipment will be included in the PCB phase‐out plan, with an agreed timeframe for taking the transformer offline, and for safeguarding the oil, and transformer casing. Engagement with SAPP investors in the sector will ensure sustainability of these phase out plans. | CEO: M |
|  |  |  | TM: H |
|  |  |  | PM:M |
| Handling, storage, transport and treatment of PCB wastes leads to environmental releases | Environmental safeguards including independent monitoring of project activities and disposal plans based on international guidance standards, including training for personnel handling PCB. | The international technical assistance for the project will ensure that best practices are adhered to. | CEO: L-M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Impacts of climate change on the project | Ensure PCBs are not stockpiled within the vicinity of coastal areas susceptible to storm surge and that storage facilities and located on all weather roads | Cyclone Idai in Mozambique and Zimbabwe in 2019 contributed to the difficulty in completing field verifications of inventories of the equipment. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM:M |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/ or the drivers are not in place. Please refer to the GEF risk rating table below The main assumption from the CEO Endorsement stage which has proven to be flawed is the proportion of contaminated equipment, which has been found to be less than a third of all equipment. The Management Review proposes to mitigate this finding by scaling up the sampling and screening of in-service equipment compared to the initial plan. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems |  | X |  |  |  |  | PM : Some countries still have no NCC and existing ones are not cohesive enough and have not been meeting |  |  |  | x |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Lack of clear management structure and roles at country level has led to long delays in inventory field work |  |  |  |  |  |  |
| Governance structure | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | X |  |  |  |  |  | PM : PSC is comprehensive enough representing all stakeholders |  |  | x |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Lack of high level commitment and prioritisation of the project in countries has contributed to delays |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment |  | X |  |  |  |  | PM: Communication is effective through the PCU/EA. PSC meets once a year. Coordination at country levels remains a risk factor as NFP seem not competent in Project management |  |  | x |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Remote communication between the EA and the countries has contributed to delays. |  |  |  |  |  |  |
| Work flow | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | X |  |  |  |  | PM: There are always delays from other countries due to structural issues; |  |  |  | x |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The action plans approved at the 2018 PSC continue to not be met and are continually being updated/ extended |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | X |  |  |  |  | PM: Stakeholder management still do not understand/ appreciate the co-financing model hence reporting not done |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Cofinance does not yet include investment in grids and can be expanded |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | X |  |  |  |  | PM: Some activities have been over budgeted while others are under budgeted, Budget review requested |  |  |  | x |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Reallocation between components required in recognition of the need for a comprehensive inventory and increased M&E |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | X |  |  |  |  |  | PM: Africa Institute processes are transparent and highly controlled |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Procurement assessment conducted in 2018 identified flaws and proposed corrective actions which are being implemented. |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  |  | X |  |  |  | PM: There are dedicated Project managers at regional level. However at national level reporting is always late and incomplete |  |  | x |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Reporting by regional project manager is timely but lacks critical and strategic analysis and proactive proposals for addressing risks. |  |  |  |  |  |  |
| Stakeholder involvement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders |  | X |  |  |  |  | PM: Some PCB equipment owners and practitioners seem to be left out in some countries |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: In some countries, utilities are not strongly supporting activities or proactively changing practices, e.g. auctioning of old equipment |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  |  | X |  |  |  | PM: Besides the project website in Africa Institute, external communications with stakeholders is minimal at country levels |  | x |  |  | x |  |
|  |  |  |  |  |  |  |  |  |  | TM: Press release done by IA and active presence at COPs |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | X |  |  |  |  |  | PM: Short term actions are meant for long term impacts and activities are still in progress | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Long term phase out plan and associated activities including inventory are being prioritized in the Management Review process |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  |  |  |  |  |  | PM: Well defined scientific basis | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Well established technologies for disposal. Trial to be conducted in 2019 for treatment of low-contaminated wastes within the region. |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  |  | X |  |  |  | PM: Political interferences is evidenced upon choices and changes of personnel and as such continuity suffers |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Political changes at senior levels of both government and utilities has contributed to delays |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile |  |  | X |  |  |  | PM: Regular changing of policy makers is unsettling in most countries | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Change of senior leadership requires repeated explanation and justification of project activities |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | X |  |  |  |  | PM: Situations are known, though maybe difficult to address |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Delays caused by cyclone in 2019 may be repeated in the coming years. |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers |  | X |  |  |  |  | PM: Disposal and replacement of PCB contaminated equipment may not be achieved due to economic reasons. Existing sale of scrap metals and used oils shall continue as a means of income |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Disposal of transformers as scrap metal has contributed to the lower than anticipated quantities of wastes confirmed |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | X |  |  |  |  | PM: All partners have adequate capacities, however their national engagement in other activities may exert pressure on the project |  |  | x |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Regional project management capacity requires close oversight and additional technical support |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| 1 | Capacity and momentum of Execution | Late implementation that may lead to non-attainment of other targets | Project coordination to provide continuous support through demonstration and monitoring visits, | UNE support | Quarterly |
| 1 | National management structure does not efficiently assign responsibility for actions including financial reporting | Key project tasks and actions are not delivered | Development of a simplified national legal instrument with clear allocation of funds, workplan, and responsibility, for signature by countries and EA. | Project manager | Dec 2019 |
|  |  |  | Engagement of utilities via improved partnerships with SAPP and regional projects investing in grid upgrades | Project manager, technical support | Mar 2020 |
| 1 | Low amount of waste confirmed as contaminated with PCB | Inability to meet project targets | Increase the resources and focus on inventory of in-service equipment as part of a long term phase out plan | Technical support, UNEP | Dec 2019 |
| 2 | Environmental releases during repackaging and treatment of wastes | Environmental contamination and exposure of people | Ensure environmental management is completed by the contractor, including risks of climate change and extreme weather events | Project manager, Technical support UNEP | Oct 2019 |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2017 rating | FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- | --- |
| Low | Medium | Medium | Continued delays in execution of preparatory steps (inventory, legal reviews) have been resolved in the notice period. Most countries show evidence of engaging to planned activities better than before; legal reviews and risk communication activities have taken off, samples for contaminated oils were submitted even though coverage is still questionable. |
|  |  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation The Management review is in progress and has produced an initial set of recommendations to be endorsed by an Extraordinary Steering committee meeting in October 2019. Among others, the draft recommendations include: - Update the project logframe, including risks and assumptions, adding mitigation recommendations, and revising target dates for the outcomes in the logframe, and updating the Theory of Change to distinguish between long term phase out planning and immediate disposal or treatment of available units - Substantive budget revision including modification of the distribution of GEF resources between the different components of the project; - Establish additional targeted technical support including on national phase out plans under Component 2 (e.g. review of processes for asset write off at national level and the fate of recently decommissioned equipment, including audit visits to countries to confirm current practices, map best practices and propose remedial actions, gender action plan, , supporting detailed country planning for disposal under Component 3, and country information sharing under Component 4. - Update of national legal instruments with more detail on country level budgets, workplans and responsibilities, to be used to officially register the project with country government These interventions are guiding the notice period activities and will be evaluated at 2019 Extraordinary PSC meeting. The IA provided support through two consultants and high level letters were written to both Government authorities and Utility management, followed with face to face meetings by the EA executive director. |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your project has more than 4 objective-level indicators. Same applies for the number of outcome-level indicators.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.