UNEP GEF PIR Fiscal Year 2025

Reporting from 1 July 2024 to 30 June 2025

# 1. PROJECT IDENTIFICATION

# 1.1. Project details

1. IDENTIFICATION

| Identification Table |  | GEF ID.: 10103 | Umoja WBS: SB-017872 |
| --- | --- | --- | --- |
|  |  | SMA IPMR ID: 86069 | Grant ID: S1-32LDL-000051 |
|  |  | Project Short Title: Mauritania AMSTRA |  |
| Project Title |  | Climate Change Adaptation and Livelihoods in Three Arid Regions of Mauritania |  |
| Duration months | Planned | 48 |  |
|  | Age | 40 |  |
| Project Type |  | Full-Sized Project |  |
| Parent Programme if child project |  | N/A |  |
| Project Scope |  | National |  |
| Region |  | Africa |  |
| Countries |  | Mauritania |  |
| GEF Focal Area(s) |  | Climate Change Adaptation |  |
| GEF financing amount |  | USD 4,416,000 |  |
| Co-financing amount |  | USD 13,770,374 |  |
| Date of CEO Endorsement/Approval |  | 28 May 2021 |  |
| UNEP Project Approval Date (on Decision Sheet) |  | Insert the date as per Decision Sheet (As per date on the project approval sheet signed by the Divisional Director approving the UNEP GEF Project) |  |
| Start of Implementation (PCA entering into force) |  | 23 October 2021 |  |
| Date of Inception Workshop, if available |  | Political / high-level inception workshop: 24 February 2022 Technical inception workshop: 9 August 2022 |  |
| Date of First Disbursement |  | 3 March 2022 |  |
| Total disbursement as of 30 June 2025 |  | USD 3,849,233 |  |
| Total expenditure as of 30 June 2025 |  | USD 3,347,078 |  |
| Midterm undertaken? |  | No |  |
| Actual Mid-Term Date, if taken |  | N/A |  |
| Expected Mid-Term Date, if not taken |  | October 2025 |  |
| Completion Date | Planned – original PCA | 31 March 2026 |  |
|  | Revised – Current PCA | N/A |  |
| Expected Terminal Evaluation Date |  | October 2026 |  |
| Expected Financial Closure Date |  | March 2027 |  |

# 1.2. Project description

Climate Change Adaptation and Livelihoods in Three Arid Regions of Mauritania (AMSTRA) project was designed to increase the adaptive capacity of the populations of the arid wilayas (regions) of Mauritania (Adrar, Inchiri and Trarza) by strengthening local and regional institutional capacities through the introduction of ecosystem-based adaptation approaches (EbA). The areas targeted by the project are characterized by high temperatures and erratic rainfall. Indeed, the average annual rainfall in these areas is less than 100 mm. These arid conditions are exacerbated by a northeast trade wind, the Harmattan – a hot, dry wind that originates in the Sahara and persists throughout the long dry season. The main objective of the project is to strengthen the adaptive capacity and climate resilience of rural communities in the wilayas of Adrar, Inchiri and Trarza. This specifically involves (i) strengthening the institutional and technical capacities of actors in charge of rural development planning, in order to promote better integration of reflection on adaptation to climate change, and in particular the ecosystem-based adaptation (EbA); (ii) improve sustainable access to drinking water; (iii) promote resilience of livelihoods to climate change through EbA interventions and diversification of livelihoods; and (iv) strengthen knowledge and management of ecosystem-based adaptation (EbA). The AMSTRA project has four components, namely: Component 1: Institutional and technical capacity development for the planning and implementation of climate change adaptation in arid ecosystems. The outcome under this component will lead to the increased technical and institutional capacity for climate change adaptation, particularly EbA in arid ecosystems. Four outputs are envisaged (i) Climate change impact and vulnerability assessments undertaken, and adaptation options identified and validated by stakeholders in each of the 3 target wilayas and 8 project sites; (ii) 575 representatives of regional governments, private sector, civil society organizations and community-based organization across the 3 target wilayas trained on adaptation approaches including EbA; (iii) 3 Regional Development Plans, integrating adaptation into climate change and gender, revised or developed and shared with stakeholders; (iv) An upscaling strategy and action plan for climate change adaptation in arid ecosystems of Mauritania developed in collaboration with national stakeholders, focusing on EbA approaches. Component 2 on sustainable access to and efficient use of water has one outcome: Enhanced sustainable access to and efficient use of water for increased drought-resilience of local communities and ecosystems in the wilayas of Adrar, Inchiri and Trarza. This outcome has four outputs: (i) 16 new efficient water provisioning systems (e.g. new wells, boreholes, solar pumps, desalination units) and 4 water collection and storage systems installed in the 8 project sites; (ii) Small-scale infrastructures implemented on 4 water courses to increase infiltration and to reduce erosion and flooding; (iii) 8 efficient irrigation water distribution systems established (one in each project site); (iv) 8 community associations (e.g. cooperatives, AGPOs) trained on sustainable and efficient water management and distribution (one in each project site) Component 3: Protection, productivity, and diversification of local livelihoods. The planned outcome under this component is the protection, productivity and diversification of livelihoods enhanced through EbA interventions to increase climate-resilience in the wilayas of Adrar, Inchiri and Trarza. Four outputs are planned: (i) Regional community nurseries specialized in plant production for arid ecoregions established and operational, and training for their sustainable management provided to local communities or cooperatives in 3 wilayas; (ii) EbA interventions implemented on 400 hectares of dunes to protect vulnerable communities, livelihoods and ecosystems from dune-migration; (iii) EbA interventions implemented on 150 hectares to shelter vulnerable communities from dune migration, heat and wind and to provide forage for livestock and non-timber forest products; (iv) Additional natural resource-based livelihoods introduced for local populations Component 4: Knowledge for action on climate change and EbA in arid ecosystems. The only outcome will see stakeholder demonstrate strengthened knowledge and action-oriented attitudes on climate change and adaptation approaches, particularly EbA. This outcome has 3 outputs: (i) 5 publications on policy-relevant research findings published based on monitoring of adaptation results generated under Components 2 and 3, and disseminated to at least 45 decision-makers; (ii) A series of 4 EbA handbooks detailing best practices for arid ecosystems developed and shared with at least 550 members of local implementation structures across the 3 target wilayas; (iii) At least 750 local stakeholders informed of climate change adaptation and good EbA practices in the three target wilayas The project targets 37,867 beneficiaries in the municipalities of Chinguetti, Aoujeft and Tawaz (Adrar), Akjoujt, Bénichab and M’Heijératt (Inchiri), and Boutilimit and Ajouer (Trarza).

# 1.3. Project Contacts

| Division(s) Implementing the project | Climate Change Division |
| --- | --- |
| Executing Agency(ies) | Ministry of Environment and Sustainable Development (MEDD), Mauritania |
| Names of Other Project Partners | Ministry of Agriculture and Food Sovereignty Ministry of Hydraulics and Sanitation Ministry of Social Action, Children and Family National Agency for the Great Green Wall Ministry of Interior, Decentralization and Local Development Awleigatt National Park Directorate of Programming, Cooperation and Statistics |
| UNEP Portfolio Manager(s) | Jessica Troni |
| UNEP Task Manager(s) | Anna Kontorov |
| UNEP Budget/Finance Officer | Priscillah Kaara, Fatma Twahir |
| UNEP Support/Assistants | Evans Madiri, Catherine Goreti Okoch |
| EA Manager/Representative | Moussa BA |
| EA Project Manager | Amadou Diam BA |
| EA Finance Manager | Hanan Wadady |
| EA Communications Lead, if relevant | N/A |

# 2. OVERVIEW OF PROJECT STATUS

2.1 UNEP PoW and UN

| UNEP Current Subprogramme(s) | Climate action, Nature action |
| --- | --- |
| PoW Indicator(s) | Strategic objective 1: “Climate stability”. PoW 2022-2023 Indicators: (i) Number of national, subnational and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support (ii) Amounts provided and mobilized in $ per year in relation to the continued existing collective mobilization goal of the $100 billion commitment through to 2025 with UNEP support (iv) Positive shift in public opinion, attitudes and actions in support of climate action as a result of UNEP action Strategic Objective 2: “Living in harmony with nature”. PoW 2022-2023 Indicators: (i) Number of national or subnational entities that, with UNEP support, adopt integrated approaches to address environmental and social issues and/or tools for valuing, monitoring and sustainably managing biodiversity (iii) Number of countries and national, regional and subnational authorities and entities that incorporate, with UNEP support, biodiversity and ecosystem-based approaches into development and sectoral plans, policies and processes for the sustainable management and/or restoration of terrestrial, freshwater and marine areas (iv) Increase in territory of land- and seascapes that is under improved ecosystem conservation and restoration |
| UNEP previous Subprogramme(s) | Climate change sub-programme |
| UNSDCF / UNDAF linkages | UNDAF Pillar 1 Outcome 3: Environmental Sustainability and Disaster Risk Reduction Systems and Services Operationalized |
| Link to relevant SDG Goal(s) | Goal 6: Clean Water and Sanitation Goal 13: Climate Action Goal 15: Life on Land |
| Link to relevant SDG Target(s) | Goal 6: Targets 6.1 and 6.6 Goal 13: Targets 13.1, 13.2, 13.3, 13.a and 13.b Goal 15: Targets 15.1, 15.2, 15.3, 15.5, 15.9, 15.a and 15.b |

2.2. GEF Core Indicators:

| Indicators | Targets – Expected Value |  |  | Materialized to date |
| --- | --- | --- | --- | --- |
|  | Mid-term | End-of-project | Total target |  |
| Total no. of direct beneficiaries | 19,700 | 37,292 | 37,292 | 30,834 beneficiaries, of whom 16,990 (i.e. 55%) women |
| Area of land managed for climate resilience (ha) | N/A | 550 ha | 550 ha | 229 ha (181 ha of dune stabilization and 48 ha of agroecology systems) |
| Total no. of policies/plans that will mainstream climate resilience | N/A | 11 | 11 | 3 |
| Total no. of people trained | N/A | 575 | 575 | 225 |

2.3. Implementation Status and Risk

|  | FY 2023 | FY 2024 | FY 2025 | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
| PIR # | 1st | 2nd | 3rd | 4th | …. |
| Rating towards outcomes (DO) (section 3.1) | S | S | S |  |  |
| Rating towards outputs (IP) (section 3.2) | S | S | S |  |  |
| Risk rating (section 4.2) | M | M | M |  |  |

Progress: Although the Project Cooperation Agreement (PCA) between MEDD and UNEP was signed in October 2021, due to many changes in government, the project activities only effectively started in the second quarter of 2022. In February 2022, MEDD organized the high-level political inception of the project, but technical inception workshop could only be organized in August 2022. In the project inception phase, a Project Management Unit (PMU) was instituted, with the MEDD regional delegations being in charge of the day-to-day project oversight and support on the ground. The project governance structure was also put in place, with a national level Project Steering Committee (PSC) and eight commune-level management committees. Despite the initial delays in project inception, the project has made good progress in its activities in its first 3 years of implementation, as outlined below. The rating for progress towards the project’s outcomes in this third reporting period is assessed as satisfactory. In terms of Outcome 1 (“Increased technical and institutional capacity of stakeholders for climate change adaptation – particularly EbA – in arid ecosystems”), the capacity of the targeted institutions and other project stakeholders to plan and implement adaptation (including EbA) interventions has continued to be strengthened in this reporting period, through several approaches. The planning capacity of municipal staff was enhanced through their engagement in the elaboration of the Local Development Plans (PDLs), which have been completed for 3 of the project communes to date (and are underway in the 5 others). Furthermore, the staff at the regional delegations of MEDD (DREDDs) have continued to engage in and support the project interventions, at the same time increasing their own capacity to plan and implementation EbA and other adaptation interventions. Through the additional training workshops for private sector actors in Adrar and for communities in Inchiri, the capacity of an additional 35 training participants to plan and implement adaptation interventions in arid and hyper-arid environments was increased. This brings the total number of training participants to date to 225. Finally, the capacity of local communities and community-based organizations has continued to be strengthened through their interaction with the project team (Regional Delegations and PMU) during their monitoring missions and through their extensive engagement in the planning and implementation of the project activities on the ground. For Outcome 2 (“Enhanced sustainable access to and efficient use of water for increased drought-resilience of local communities and ecosystems”), access to water has been improved for an additional 2,781 beneficiaries. This brings the total number of people benefiting from improved access to water to 18,224 (56% women). In this reporting period, access to water was further improved through the rehabilitation of a well in Akjoujt (Inchiri), and its connection to a small irrigation network. An additional water basin was also constructed in Benichab (Inchiri), and water storage tanks were distributed to all dune fixation and agroecology sites. Small-scale infrastructures (CES/DRS interventions) were established in two additional watersheds in this reporting period, to increase infiltration and reduce erosion and flooding. In addition, the installation of irrigation water distribution systems was completed at 7 additional agroecology sites, bringing the total number of sites to 12. Furthermore, all the remaining dune fixation sites in Adrar were connected to existing wells, boreholes or urban water distribution networks for irrigation. Progress towards Outcome 3 (“Protection, productivity and diversification of livelihoods enhanced through EbA interventions to increase climate-resilience”) has also continued. As indicated in the last PIR, considering the very arid conditions in most of the project sites and the significant underbudgeting at project design stage, the original dune stabilization target of 400 ha and the agroecology target of 150 ha will not be realistic with the budget available. A formal revision of these targets will be undertaken following the completion of the project’s Mid-Term Review (MTR). To date, dune stabilization and agroecology interventions have been implemented on a total of 229 hectares (181 ha for dune stabilization and 48 ha for agroecology), of which 80 ha were additional in this reporting period (70 ha for dune stabilization and 10 ha for agroecology). Following the exceptionally low rainfall in the previous reporting period, in particular in Adrar, the rainfall in this reporting period was somewhat better. Nonetheless, the arid nature of the project areas remains a challenge for seedling survival, and much effort has been put into the provision of irrigation water for the dune stabilization and agroecology sites in this reporting period (see under Outcome 2). Finally, in terms of alternative income-generating activities, approximately 705 cooperative members (almost exclusively women) participate as direct beneficiaries in the 41 activities established by the project to date across all project sites, of which 2 are additional ones launched in the current reporting period. For Outcome 4 (“Stakeholders demonstrate strengthened knowledge and action-oriented attitudes on climate change and adaptation approaches (particularly EbA))”, in this reporting period, the project contributed to the awareness-raising events during the August 2024 Tree Week (Semaine de l’Arbre) in the 3 target wilayas. In addition, it contributed to environmental and climate change awareness raising at the Festival de Chinguetti event in Adrar (in December 2024). Key stakeholders, including local administrative and municipal authorities, community-based groups and community members, have continued to be sensitized on climate change adaptation and the EbA approach through their interaction with the project team during their field monitoring missions, and through their engagement in the planning and implementation of the project activities on the ground. The rating for progress towards the project’s outputs is assessed as satisfactory for this third reporting period. Under project Component 1 (“Institutional and technical capacity development for the planning and implementation of climate change adaptation in arid ecosystems”), the main progress in this reporting period has been on the development of Local Development Plans (PLDs) under project Output 1.3. This was undertaken and completed for the 3 project communes in Adrar and validated by the communes. In addition, PDL development is currently underway for the remaining 5 project communes – 3 in Inchiri and 2 in Trarza. Through this process, site-level vulnerability assessments and identification of adaptation options were also advanced, thus contributing to project Output 1.1. In terms of the training and capacity building activities under Output 1.2, in this reporting period, the project organized two additional training workshops on adaptation to climate change in arid and hyper-arid environments. The first training workshop targeted private sector actors in Adrar, and was attended by 20 participants. The second training workshop took place in Inchiri and built capacity for the establishment of nurseries for the production of forest plant. It was attended by 15 participants. As such, the total number of stakeholders trained under Output 1.2 to date was increased to 225, with participants from civil society and community-based organizations (cooperatives, associations, NGOs, AGPOs), local communities and administrations, and the private sector. For Component 2 (“Sustainable access to and efficient use of water”), good progress continued to be made in this reporting period under all the outputs. Under Output 2.1, in this reporting period, the project rehabilitated one well in Akjoujt (Inchiri), equipped it and connected it to a small irrigation network to supply water to gardens and date-palm groves. Furthermore, an additional water basin was constructed in Benichab (Inchiri), and water storage tanks were distributed to all dune fixation and agroecology sites. For Output 2.2, CES/DRS techniques were installed in 2 additional watersheds in Adrar, bringing the final total number of these infrastructures to 4. Establishment of efficient irrigation systems (Output 2.3) continued at the project’s agroecology sites (under Output 3.3). 7 new irrigation water distribution systems were completed in this reporting period, bringing the total number of systems to 12. In addition, during this reporting period, all the remaining dune fixation sites in Adrar were connected to existing wells, boreholes or urban water distribution networks for irrigation. Finally, under Output 3.4, a series of workshops were organized in to train local communities on efficient and sustainable water use and management, and climate change challenges. One workshop took place in each of the project’s target communes (8 workshops in total), and they were attended by a total of 60 participants (including 37 women). Under Component 3 (“Protection, productivity, and diversification of local livelihoods”), the project’s three regional nurseries (one in each project Wilaya) have produced a total of 290,000 plants to date, of which 75,000 in current reporting period. These seedlings have been distributed mainly to regional administrations in the context of annual Tree Week celebrations, as well as to communities and community-based organizations. The project has also completed dune stabilization works on 181 hectares with mechanical and biological fixation, of which 70 ha in current reporting period. Preparations for stabilizing an additional 19 hectares of dunes have been undertaken, with the production of 9,500 plants and fencing of the sites. Furthermore 95,000 plants were produced for replenishment planting at existing sites with poor survival rates. 48 hectares of agroecological systems have been established on 11 sites across the three Wilayas, of which an additional 10 ha in 1 site in current reporting period. Finally, approximately 705 cooperative members (almost exclusively women) participate in the 41 alternative income-generating activities (IGAs) established by the project to date, as direct beneficiaries. Two additional IGAs were launched in this reporting period, and additional support was provided to the IGAs established in previous periods. As for Component 4 (“Knowledge for action on climate change and EbA in arid ecosystems”), in this reporting period, Terms of References were completed for the engagement of a research institution under Output 4.1 and for the identification of approaches to be included in the EbA manuals under Output 4.2. As for Output 4.3, the project contributed to the awareness-raising events during the August 2024 Tree Week (Semaine de l’Arbre) in the 3 target wilayas. In addition, it contributed to environmental and climate change awareness raising at the Festival de Chinguetti event in Adrar (in December 2024). The more structured knowledge and awareness-raising activities of the project are planned to be launched in Q4 2025. Key stakeholders, including local administrative and municipal authorities, as well as local communities and community-based organizations, have continued to be sensitized on climate change adaptation and the EbA approach through their interaction with the project team during their field monitoring missions, and through their engagement in the planning and implementation of the project activities on the ground. The engagement of young people and women in the production of plants and in dune stabilization interventions has served a specific awareness-raising function, in addition to contributing to the restoration of the natural and living environment as well as to the promotion of green jobs. Challenges: The main challenges encountered during this implementation period are outlined below. 1. The arid conditions in the project sites and distances between community water points have remained challenges for seedling survival. Particular attention has therefore been given in this reporting period to the provision of access to irrigation systems at the project’s dune stabilization and agroecology sites. 2. Social conflicts and a lack of mobilization have posed challenges at certain project sites in this reporting period: - At a dune stabilization site in Aoujeft (in Adrar), a group opposed the planned cultivation of henna at the site, claiming that the farmers of this crop would appropriate the land; - A conflict at the Sourour agroecological site (in Trarza), where a leadership problem arose among the members of the women's cooperative that operates the site; and - Lack of commitment and engagement at the Bénichab agroecology site (in Inchiri), which led to a delay in the site's operation. The PMU has taken a very proactive approach to resolving these issues, with full support from the Executing Agency (MEDD) and the engagement of the local authorities, including Walis at the regional and Mayors at the commune level. In addition, some of the moderate-level risks identified in previous reporting periods have remained - Lack of funds available for ensuring the sustainability of certain activities beyond the duration of the project; and - Limited participation of women in some project activities (formal off-site trainings). Overall risk rating: The overall project risk level remains moderate in this reporting period. At the same time, it should be noted that the ratings for the national-level risks have remained low. For all the identified risks, the project will continue to implement the mitigation measures identified, as outlined in PIR Section 4. The key risks will be revisited every year so that adequate measures can be identified and put in place on time.

2.4. Co-financing

| Planned Co-finance Total: Actual to date: | Planned total: USD 13,770,374 This is composed of: MEDD in-kind: USD 660,000 PAMB initiative: USD 1,940,000 GCF National Adaptation Plan (NAP) project: USD 2,670,374 PRCPNA (Parc National d’Awleigatt): USD 7,200,000 GIE 3P Action Carbone: USD 1,000,000 Actual to date: USD 9,484,808 (69%), as of 30 June 2025 This is composed of: MEDD in-kind: USD 550,000 PAMB initiative: USD 1,940,000 GCF National Adaptation Plan (NAP) project: USD 994,808 PRCPNA (Parc National d’Awleigatt): USD 6,000,000 |
| --- | --- |
| Progress | The planned and mobilized co-finance are summarized in the table below: Co-finance source; Planned amount (USD); Actual amount to date (USD). Ministry of Environment and Sustainable Development MEDD; 660,000; 550,000. PAMB initiative; 1,940,000; 1,940,000. GCF National Adaptation Plan (NAP) project; 2,670,374; 994,808. PRCPNA (Parc National d’Awleigatt):; 7,200,000; 6,000,000. GIE 3P Action Carbone:; 1,000,000; 0. Total:; 13,770,374; 9,484,808. From the in-kind co-financing provided by MEDD, USD 550,000 has been mobilized to date. This has been through the provision of office space, equipment, materials, utilities, staff time at national and regional levels, and the occasional use of regional delegation vehicles for the project activities. From the Project Agropole Maraicher of Benichab (PAMB) initiative, the full co-finance amount of USD 1,940,000 has been mobilized. PAMB was a market gardening community-level initiative being implemented in Benichab, in the Wilaya of Inchiri. The AMSTRA project is building on its results and lessons learned, and is upscaling some of its improved water management and irrigation technologies implemented in small collective and individual market gardening areas. From the GCF-funded National Adaptation Plan (NAP) project, the amount of co-finance mobilized to date is USD 994,808. Specifically, the training and awareness-raising on climate change adaptation provided by the NAP project for state and non-state actors at the national and regional levels complement the proposed project’s trainings on EbA measures. Finally, co-financing mobilized from the Awleigatt National Park project (PRCPNA) amounts to USD 6,000,000 to date. This has contributed mainly to the restoration of the ecosystems and to the strengthening of their resilience to the impacts of climate change. |

2.5. Stakeholder engagement

| Date of project steering committee meeting | Project Steering Committee meetings have been convened three (3) times to date: 20 July 2022, 16 February 2023 and most recently in 15 March 2024. |
| --- | --- |
| Stakeholder engagement | The project has a Stakeholder Engagement Plan, elaborated during the project development phase. Its implementation is overseen by the Project Coordinator. The project has identified, consulted and engaged multiple stakeholders since its design phase, ranging from national stakeholders to the local communities. At the national level, in addition to MEDD, other relevant ministries and government institutions engaged include the Ministry of Agriculture and Food Sovereignty, the Ministry of Hydraulics and Sanitation, the National Meteorological Office, the Ministry of Social Action, Children and Family, and the Ministry of Interior, Decentralization and Local Development. The various ministries are represented in the membership of the Project Steering Committee. At the regional level, the Regional Delegations for Environment and Sustainable Development (DREDDs) in the three projects Wilayas play a key role in the monitoring and support to project implementation. The Walis as presidents of the Regional Development Committees, the Regional Councils, and the Regional Delegations of Hydraulics and Sanitation and the Regional Delegations of Agriculture are consulted and engaged. At the local level, local authorities and leaders, including regional commissions and delegations, Hakems, Councils and Mayors are involved. Also engaged in the planning and implementation of the interventions are the local communities, as well as local associations including cooperatives and producers’ organizations, NGOs, and the private sector. The stakeholders consulted by the project during this reporting period also include particularly vulnerable groups such as women, youth and people with disabilities. Some of these key stakeholders are members of the Project Steering Committee, which is the overarching supervisory body that ensures that the project’s activities are implemented as planned. For each of the 8 communes, the project has also established a management committee to guide and manage project activities, with 7 members (at least one from each site within the commune). All the key stakeholders attended the project inception workshop, during which the project details were discussed, and the roles and responsibilities clarified. At the start of the field activities, the project initiated a series of introductory meetings with the beneficiary communities across the regions, with the view of presenting and discussing the project objectives, main activities, and associated benefits, as well as the expected contributions from the communities. |

2.6. Gender

| Does the project have a gender action plan? | Yes |
| --- | --- |
| Gender mainstreaming | A Gender Action Plan (GAP) was designed and submitted as part of the CEO Endorsement Request. The GAP outlines actions for gender mainstreaming in the project activities to ensure that men and women participate in and fully benefit from the project’s activities. A national Gender Expert is currently under recruitment -- following a previous failed round of recruitment. They will be in charge of updating the Gender Action Plan, integrating specific gender-related activities into the project work plan and budget, and providing concrete recommendations for strengthening gender mainstreaming in all project interventions and in its exit strategy. In the project’s implementation to date, gender mainstreaming has included ensuring the full engagement of women both in the technical aspects of project implementation, and as the beneficiaries of the project interventions. Approximately 75% of the actions identified in the GAP have been implemented (for the project activities advanced to date). Gender aspects have been incorporated in project trainings, and women’s participation in training events has been ensured as much as possible (see last paragraph below). Women have also fully participated in the implementation of almost all project interventions, including the ecosystem restoration activities (dune stabilisation, nurseries). Gender-sensitivity and consideration of women’s specific needs have been incorporated in the project’s water provisioning activities, which mainly benefit women and other vulnerable groups, especially at the agroecology sites. Most of the participants at the water management training organized in this reporting period were women. Dune stabilisation activities have also mainly engaged women, as they are in charge of the nurseries and planting activities. In terms of benefits, currently 55% of the project beneficiaries are women. Some project activities, in particular the agroecological systems and the support for alternative income-generating activities, target specifically women. The project has been successful in including women’s participation in the eight commune-level project management committees put in place. The average women’s participation rate in these committees is about 40%, and some of them have women as presidents or vice presidents. In general, women’s participation in formal project training workshops and traditional decision-making processes can be a challenge, although women do generally influence decision-making through more informal channels. In terms of the training workshops under Component 1, approximately 33% of the participants in the training workshops targeting civil society organizations have been women, whereas the corresponding figure for the private sector workshop is 40% to date. For the on-site training events, women’s participation usually reaches 75-80%. |

2.7. Environmental and social safeguards management

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk CEO Endorsement/Approval Stage? Yes If yes, what specific safeguard risks were identified in the SRIF/ESERN? Moderate safeguards risks were identified in relation to Standard 1 (Biodiversity, Ecosystems and Sustainable Natural Resource Management), Standard 2 (Climate Change and Disaster Risks), and Standard 8 (Labour and Working Conditions). |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? No |
| Complaints and grievances related to social and/or environmental impacts (to be filled in by TM and EA) | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? No |
| Environmental and social safeguards management | The project has undertaken an environmental and social safeguards assessment and an Environmental and Social Management Plan (ESMP) was developed. The ESMP underlines that AMSTRA is a project of major importance in the context of the development of the three regions. The ESMP specifies that the impact of the project will be generally positive in the long-term in this area, both in terms of quality of life and the resilience of targeted populations and ecosystems. The Project Coordinator is tasked with monitoring and managing the implementation of the ESMP recommendations. The impact assessment of the project indicates that majority of the impacts will be positive, and that no significant negative impacts are expected. The application of specific risk mitigation measures will help minimize any minor potential adverse environmental impacts caused by the project. In terms of the safeguards risks rated as moderate at CEO endorsement stage, for Standard 1 (Biodiversity, Ecosystems and Sustainable Natural Resource Management), the use of the potentially-invasive alien species prosopis juliflora for the dune stabilization has been limited to only two sites (at the request of populations, due to its fast growth and effectiveness). These sites are at the entrance to the town Aoujeft (Adrar), where dune stabilization has been undertaken to protect the paved road, and at the ZemZem site in Trarza. As water availability in these sites is low, invasive spread of the species is very unlikely. Nonetheless, the situation is monitored. For Standard 2 (Climate Change and Disaster Risks), in terms of the arid environment and concerns regarding seedling survival, this risk has fully materialized in this reporting period. Extremely low rainfall (20mm) was experienced in the past year in the North (Wilaya of Adrar), which resulted in poor seedling survival rate in the dune stabilization sites. Species selection and location of water provisioning infrastructure have been undertaken with the arid conditions in mind. Specifically, water supply infrastructure provided under project Component 2 has been co-located with those project interventions that require irrigation, in particular the agroecological systems and market gardens under Component 3. Additional provision of water to the hyper-arid dune stabilization sites has been organized and has been further enhanced in the current reporting period, both through water deliveries and through providing connections to existing water sources (where these are close enough). In particular, several dune stabilization sites have been connected to the irrigation networks at the project’s agroecology sites, and solar pumping systems have been provided at sites close to wells. Regarding possible risk of depletion of groundwater reserves by the water infrastructure interventions, the hydrological and geophysical studies undertaken ensured adequate water levels in the areas where these interventions were recommended. The boreholes installed by the project are located on large aquifers (notably those of Trarza and Benichab / Inchiri) which are known for their water reserves. Authorization acquired from the Ministry of Hydraulics and Sanitation ensures that the boreholes are located in areas indicated for this purpose by the Government. The installation of small-scale infrastructure (gabions or thresholds) by the project to slow down the flow of water in four watersheds in Adrar, where groundwater reserves are more limited, enhances infiltration and groundwater recharge, which contributes to the availability of water for the (less deep) wells installed or equipped by the project. To ensure efficient water use, in the current reporting period, training has been provided to communities at all 8 projects sites in efficient and sustainable water management and use (under project Output 2.4). Furthermore, the project has undertaken measures to reduce evapotranspiration and water loss by using an organic fertilizer that retains water, as well as applying mulch and/or straw around seedlings. This reduces the amount of irrigation water required, as well as helping to reduce seedling mortality. |

2.8. Knowledge management

| Knowledge activities and products | Since the beginning of the project, several studies have been carried out by the project to support the implementation of certain activities. A baseline study and an environmental and social safeguards risk assessment were conducted. The project has undertaken a hydraulic study of the intervention areas to assess the water needs, a stocktake of existing water infrastructure, and propose measures to be implemented to resolve water-related challenges at each site. In addition, a second geophysical and hydrogeological study was undertaken to support the identification of appropriate sites and approaches for the establishment of boreholes by the project. Other technical feasibility studies undertaken include ones on value chains for alternative income generating activities, on the stabilization of dunes and on small infrastructure for increasing water infiltration and reducing erosion and flooding risk (DRS/CES interventions). In terms of knowledge dissemination, the project has participated in the organization of various awareness-raising events throughout its implementation phase. In this reporting period, it contributed to awareness-raising activities as part of the Tree Week (Semaine de l’Arbre) and the Festival de Chinguetti. Furthermore, a local level awareness-raising campaign focusing on climate change adaptation in arid environments is planned to be implemented by the project in its last year of implementation. The project website (www.amstra.mr), which was finalized in 2023, is still to be populated and reactivated. In the current reporting period, the project attempted, unsuccessfully, to re-engage the original technical service provider to support this. Recruitment of another service provide is currently underway. |
| --- | --- |
| Main learning during the period | In this reporting period, further efforts were successfully implemented to address the challenge of seedling survival at dune stabilization sites due to the arid conditions, through the improved provision of water. First of all, several of these sites were connected to the irrigation systems of nearby agroecology sites established by the project. Secondly, existing wells close to the dune stabilization sites were equipped with solar pumps, to enhance access to irrigation water. |

2.9. Stories to be shared

| Stories to be shared | The enclosure of agroecology sites, particularly in the wilaya of Adrar and specifically in the Commune of Tawaz, has made it possible to cultivate wheat and watermelons outside the vegetable production / market gardening season. |
| --- | --- |

# 3. PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

3.1	Rating of progress towards achieving the project outcomes (Development Objectives)

| Project Objective and Outcomes | Indicator | Baseline level | Mid-term target | End-of-project target | Progress as of current period | Summary by the EA of attainment of the indicator & target as of 30 June 2025 | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To increase the adaptive capacity of rural communities in the wilayas of Adrar, Inchiri and Trarza | Number of beneficiaries; % of women | Number of beneficiaries to be determined in the baseline study | 19,700 | 37,867, of which 60% women | 81% | To date, the project interventions have reached 30,834 beneficiaries, of whom 16,990 (i.e. 55%) are women. | S |
| Outcome 1: Stakeholders demonstrate increased technical and institutional capacity for climate change adaptation – particularly EbA – in arid ecosystems | 1.1 Degree to which the capacity of targeted institutions is strengthened to identify, plan, implement and monitor adaptation (including EbA) interventions | Baseline study to be conducted at the project inception stage to define the baseline level of capacity of targeted institutions to identify, plan, implement and monitor adaptation (including EbA) | N/A | Increase of 5 in the capacity score of each institution | 39% (based on number of training participants vs Output 1.2 target) | The capacity of the targeted institutions and other project stakeholders to plan and implement adaptation (including EbA) interventions in arid ecosystems has continued to be strengthened in this reporting period, through several approaches. In this reporting period, the planning capacity of municipal staff was enhanced through their engagement in the elaboration of the Local Development Plans (PDLs), which have been completed for 3 of the project communes to date (and are under development in the 5 others). An additional training workshop for private sector actors was organized in this reporting period (Q2 2025) under project Output 1.2, reaching an additional 20 training participants (of whom 8 women) in the Wilaya of Adrar. This complemented similar workshops organized for the private sector in Inchiri and Trarza in previous reporting periods. Furthermore, a training was organized in Inchiri in this reporting period to build capacity for the establishment of nurseries for the production of forest plants. The workshop targeted a women’s group in Akjoujt and was also attended by DREDD personnel. The 15 participants included 7 women. As a result of the various training workshops provided under Output 1.2 throughout the project implementation period, the capacity of a total of 225 training participants (to date) to plan and implement adaptation interventions in arid and hyper-arid environments has been increased. The feedback on the workshops from local authorities, DREDDs and the workshops participants (through post-training questionnaires) has been positive. Additional training sessions on the EbA approach are scheduled for the second half of 2025. In previous reporting periods, a series of workshops on adaptation and EbA approaches in arid and hyper-arid environments have been organized (as outlined in previous PIR reports). In addition to private sector actors, these have targeted grassroots civil society and community-based organizations (cooperatives, associations, NGOs, AGPOs) and local administrations. The capacity of local communities and community-based organizations has also continued to be increased through their interaction with the project team (Regional Delegations and PMU) during their monitoring missions and through their engagement in the planning and implementation of the project activities on the ground. As the project baseline study did not successfully establish the baseline level for the indicator (“capacity of targeted institutions”), the indicator will need to be revised at the project Mid-Term Review (MTR). Since there is no baseline, progress towards the original indicator cannot be measured. Nonetheless, considering the progress made in the project’s capacity building activities, progress towards the outcome is estimated as satisfactory at this stage. | S |
| Outcome 2: Enhanced sustainable access to and efficient use of water for increased drought-resilience of local communities and ecosystems in the wilayas of Adrar, Inchiri and Trarza | 2.1 Estimated number of beneficiaries with improved access to water (disaggregated by gender) | 0 | 10,000 | 20,047 (50% men and 50% female) | 91% | The number of community members benefitting from the project’s water access interventions to date is 18,224, of whom 10,240 (56%) are women. This represents an increase of 2,781 beneficiaries in this reporting period. In this reporting period, the project rehabilitated one well in Akjoujt (Inchiri), equipped it and connected it to a small irrigation network to supply water to gardens and date-palm groves located along the wadi. Furthermore, an additional water basin was constructed in Benichab (Inchiri), and water storage tanks were distributed to all dune fixation and agroecology sites. A program was also launched in this reporting period to drill three (3) new wells Akjoujt (Inchiri). These wells will be equipped with solar pumping systems and small water towers. The El Ménar borehole (in Trarza) will also have its own water tower with a small water supply network to supply the village with drinking water. In previous reporting periods, the project had installed a total of sixteen (16) water provisioning structures across the project sites: Following a geophysical and hydrogeological study, six (6) sites for drilling new boreholes were identified and borehole installed. Eight (8) water storage facilities, including water towers and water basins, were installed in previous reporting periods. In addition, two (2) standpipes were installed in the town of Zem Zem (Trarza) for domestic water use purposes. Furthermore, the project has equipped several existing wells and boreholes with solar pumping systems: Four existing boreholes and two wells were equipped with solar pumping systems (pumps and solar panels) at sites where the project is undertaken agroecology interventions under its Component 3 (or dune stabilization in the case of Aoujeft). In addition, sixteen (16) cooperatives focused on vegetable gardening and date cultivation in the municipality of Tawaz (Adrar) have also benefited from the installation of smaller solar pumping equipment on one artisanal well for each cooperative. A hydraulic study was carried out in the intervention area to assess the water needs, take stock of the existing water infrastructure, and propose measures to be implemented to resolve water-related challenges at each site In this reporting period, CES/DRS infrastructures (gabions to slow down the flow of water) were installed in two (2) additional sites in the Wilaya of Adrar (in Aoujeft commune). The works were already completed at the Dakhlet Hel Abdawa site and are close to completion at the Loudeye site. In the previous reporting period, CES/DRS structures were installed at Dhaya and Haye Daira, in the Tawaz commune in Adrar. This followed a study undertaken in previous reporting period to identify CES/DRS techniques and appropriate sites in four watersheds in Adrar. Furthermore, in this reporting period, the installation of irrigation water distribution systems was completed for 7 additional agroecology sites, bringing the total number of sites to 12. The additional sites are 1 in Trarza, 2 in Inchiri and 4 in Adrar. 3 additional irrigation systems are being installed in Inchiri, to be completed in the second half of 2025. In addition, during this reporting period, all the dune fixation sites in Adrar (Aoujeft, Toungad, Tenyall, Médina Ghadima and Misrata) were connected to existing wells, boreholes or urban water distribution networks for irrigation (except for the Tekemkount site, which was completed in 2022). This also enables the irrigation of adjacent date palm plantations. The project has also provided plastic tanks across all project sites for water storage and transport. Finally, in this reporting period, a series of workshops were organized to train local communities on efficient and sustainable water use and management. One workshop took place in each of the project’s target communes (8 workshops in total), and they were attended by a total of 60 participants (including 37 women). The main topics covered included water management challenges in relation to climate change and innovative solutions for sustainable water management. | S |
| Outcome 3: Protection, productivity and diversification of livelihoods enhanced through EbA interventions to increase climate-resilience in the wilayas of Adrar, Inchiri and Trarza | 3.1 Extent to which EbA measures generate livelihood protection benefits for communities | To be determined in the baseline study | To be determined | Livelihoods of 30% of the communities in the three target wilayas protected against dune invasion, heat and wind through EbA measures implemented on 550 hectares | 42% | To date, dune stabilization and agroecology interventions have been implemented on a total of 229 hectares, of which 80 ha are additional in this reporting period. It should be noted that, considering the very arid conditions in most of the project sites, the target of 550 ha will not be realistic with the budget available. A revised target, including also the % of population protected, will be adopted following the project’s Mid-Term Review (MTR). In this reporting period, the project’s dune stabilization interventions were expanded onto an additional 70 hectares, resulting in a total achievement to date of 181 ha. This was accompanied by the production and installation of 6,000 linear meters of wattle in this reporting period (for a total achievement of 81,000 meters to date). Preparations for dune stabilization on an additional 19 ha in the second half of 2025 were also undertaken, with the production of 9,500 plants and the fencing of the sites. In addition, 95,000 plants were produced for replenishment at the sites, considering the poor survival rate in the previous reporting period due to extremely low rainfall. Although in this reporting period rainfall was better than in the previous one, the arid nature of the project areas remains a challenge for seedling survival. This risk has continued to be mitigated in this reporting period through the provision of access to irrigation water from existing water points (as reported under Output 2.3). The installation of 10 additional hectares of agroecological systems was initiated in this reporting period, at 1 additional site in Inchiri. This has resulted in the total achievement to date of 48 hectares of agroecological systems across 12 sites. These systems are connected to boreholes, reservoirs or water towers for watering, provided by the project under Component 2. | MS |
|  | 3.2 Increase in the income of 800 producer cooperative participants as a result of the introduction of alternative income-generating activities (gender disaggregated) | Zero | To be established by the baseline study | To be established by the baseline study | 88% | Approximately 705 cooperative members (almost exclusively women) participate as direct beneficiaries in the alternative income-generating activities (IGAs) established by the project to date. In this reporting period, the project introduced 2 additional alternative income-generating activities, with the provision of equipment and materials. These were one additional community store, and one plant nursery for youth. In addition, in this reporting period the focus remained on consolidating and supporting the IGAs established in the previous reporting period. The activities supported to date are as follows: Community shops: 24 Butcher’s shops: 5 Couscous production: 6 Fishmongers: 1 Gas depot: 2 Vegetable trade: 1 Plant production nursery for young people: 2 In a previous reporting period, a value chain feasibility study was carried out by the project to inform the selection of the livelihoods to be developed. Some of the recommendations of the study included the processing of dates and NTFPs. Depending on the interest of the communities, the project may provide training and support for these value chains. As reported under Component 2, to support alternative income-generating activities, the project has also installed two new wells for a vegetable gardening cooperative in Akjoujt (Inchiri) and equipped them with solar pumping systems. Fourteen cooperatives focused on vegetable gardening and date cultivation in the municipality of Tawaz (Adrar) also benefited from the installation of solar pumping equipment on one well for each cooperative. | S |
| Outcome 4: Stakeholders demonstrate strengthened knowledge and action-oriented attitudes on climate change and adaptation approaches (particularly EbA) | 4.1 Proportion of the population in the three target wilayas with knowledge and action-oriented attitudes on climate change and adaptation approaches | There is limited knowledge and action-oriented attitudes on climate change and adaptation approaches in the three wilayas (less than 5%, to be confirmed by the baseline study) | To be established | At least 5 out of 10 people in the target population with knowledge and action-oriented attitude on climate change and adaptation approaches (of which ~50% are women) | 40% | In this reporting period, the project contributed to the awareness-raising events during the August 2024 Tree Week (Semaine de l’Arbre) in the 3 target wilayas. In addition, it contributed to environmental and climate change awareness raising at the Festival de Chinguetti event in Adrar (in December 2024). The more structured knowledge and awareness-raising activities of the project are planned to be launched in Q4 2025. Key local stakeholders including local administrative and municipal authorities, community-based organizations, as well as community members, have been sensitized on climate change adaptation and the EbA approach through their interaction with the project team (Regional Delegations and PMU) during their field monitoring missions and through full engagement in the planning and implementation of the project activities on the ground. Indeed, the arid nature of the project intervention area has made it easier to illustrate to the various stakeholders the impacts of climate change and the relevance of healthy ecosystems in addressing its impacts. The engagement of young people and women in the production of plants and dune stabilization interventions has served a specific awareness-raising function, in addition to contributing to the restoration of the natural and living environment as well as to the promotion of green jobs. | S |

3.2	Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Outputs/Activities | Expected completion date | Implementation status as of 30 June 2024 (%) | Implementation status as of 30 June 2025 (%) | Progress rating justification, description of challenges faced and explanations for any delay | Progress rating |
| --- | --- | --- | --- | --- | --- |
| COMPONENT 1: Institutional and technical capacity development for the planning and implementation of climate change adaptation in arid ecosystems |  |  |  |  |  |
| Output 1.1: Climate change impact and vulnerability assessments undertaken, and adaptation options identified and validated by stakeholders in each of the 3 target wilayas and 8 project sites | Q4 2022 | 15% | 50% | Following the restructuring of the activities under this output in the previous reporting period, the site-level vulnerability assessments and identification of adaptation options were in this period advanced through Local Development Plans (PDLs) process under Output 1.3. The activities focused on the regional (wilaya) level will be undertaken in conjunction with the climate risk assessment process under the GCF-funded NAP project. The consultant firm procurement process (undertaken by UNEP) has been very lengthy, resulting in a delay. The activities are now planned to be launched in Q4 2025. The initiation of the activities under this output was originally delayed due to insufficient budget allocated to them in project design, which necessitated a budget revision and restructuring of the activities. | MS |
| Output 1.2: 575 representatives of regional governments, private sector, civil society organizations and community-based organizations (e.g., cooperatives, AGPOs) across the 3 target wilayas trained on adaptation approaches (including EbA) | Q4 2023 | 33% | 39% | In current reporting period, two additional training workshops were organized under this output, bringing the total number of participants to 225. In this reporting period, an additional training workshop for private sector actors was organized in Q2 2025, reaching 20 training participants (of whom 8 women) in the Wilaya of Adrar. This complemented similar workshops organized for the private sector in Inchiri and Trarza in previous reporting periods. Furthermore, a training was organized in Inchiri in this reporting period to build capacity for the establishment of nurseries for the production of forest plants. The workshop targeted a women’s group in Akjoujt and was also attended by DREDD personnel. The 15 participants included 7 women. Additional training sessions on the EbA approach are scheduled for the second half of 2025. A consultant has been recruited to facilitate the workshops and a service provider has been selected to organize the workshops in each of the three Wilayas in the project intervention area. In previous reporting periods, a series of workshops on adaptation and EbA approaches in arid and hyper-arid environments have been organized (as outlined in previous PIR reports). In addition to private sector actors, these have targeted grassroots civil society and community-based organizations (cooperatives, associations, NGOs, AGPOs) and local administrations. | S |
| Output 1.3: 3 Regional Development Plans (PDRs) and 8 Local Development Plans (PDLs), integrating adaptation to climate change and gender, revised, or developed and shared with stakeholders | Q2 2025 | 5% | 80% | In this reporting period, the development of Local Development Plans (PLDs) was undertaken and completed for the 3 project communes in Adrar: Aoujeft, Chinguetti and Tawaz, and validated by the communes. The development of PDLs was initiated and is currently underway for the remaining 5 project communes, 3 in Inchiri: Akjoujt, Benichab and M’Heijeratt, and 2 in Trarza: Boutilimit and Ajouer. The PDLs are developed with support from consultants, who work closely with the Mayors, Communal Councils and communities in the concerned communes. Biophysical and socioeconomic data, including on the climate vulnerability of the communities have been collected, inter alia through community consultations. Consultation meetings were held with the Mayors, Communal Councils and communites to define priorities in terms of local development and adaptation. | S |
| Output 1.4: An upscaling strategy and action plan for climate change adaptation in arid ecosystems of Mauritania developed in collaboration with national stakeholders, focusing on EbA approaches | Q3 2025 | 0% | 0% | Activities under this output will be initiated in Q4 2025. To ensure that the lessons learnt and best practices collected from the project are disseminated widely, including across the Sahel region, the project will liaise closely with the Great Green Wall (GGW) Regional Program (coordinated by UNEP) to share this information. | S |
| COMPONENT 2: Sustainable access to and efficient use of water |  |  |  |  |  |
| Output 2.1: 16 new efficient water provisioning systems (e.g., new wells, boreholes, solar pumps, desalination units) and 4 water collection and storage systems installed in the 8 project sites | Q2 2023 | 90% | 95% | Overall, the project’s attainments under this output have exceeded the originally-planned 16 new water provisioning systems, due to the importance of water provision for livelihoods in these arid areas. In this reporting period, the project rehabilitated one well in Akjoujt (Inchiri), equipped it and connected it to a small irrigation network to supply water to gardens and date-palm groves located along the wadi. Furthermore, an additional water basin was constructed in Benichab (Inchiri), and water storage tanks were distributed to all dune fixation and agroecology sites. A program was also launched in this reporting period to drill three (3) new wells Akjoujt (Inchiri). These wells will be equipped with solar pumping systems and small water towers and are distributed as follows: 2 wells in Akjoujt (Inchiri) and 1 well in Lemdemna. The El Ménar borehole (in Trarza) will also have its own water tower with a small water supply network to supply the village with drinking water. In previous reporting periods, the project had installed a total of sixteen (16) water provisioning structures across the project sites: Following a geophysical and hydrogeological study, six (6) sites for drilling new boreholes were identified. Boreholes were installed in the following sites: one in Benichab (Inchiri), three in Chinguetti (two in Tindwali and one in Tekemkount sites) (Adrar), one in El Menar (Trarza), and one in Dakhlet Hel Abdawa (Adrar). These sites are also associated with the project’s agroecology interventions (see Output 3.3). Eight (8) water storage facilities were installed in previous reporting periods: water towers were completed in Bénichab (Inchiri) and Zem Zem (Trarza), as well as in Chinguetti (two), Aoujeft and Dakhlet Hel Abdawa (Adrar). Water basins were constructed in Dhaya (Adrar) and Zem Zem (Trarza). In addition, two (2) standpipes were installed in the town of Zem Zem (Trarza) for domestic water use purposes. It should also be noted that under Output 3.4, the project has installed two (2) new wells for a vegetable gardening cooperative in Akjoujt (Inchiri) and equipped them with smaller solar pumping systems. Furthermore, although not counted as “new water provisioning systems”, the project has equipped several existing wells and boreholes with solar pumping systems: Four existing boreholes and two wells were equipped with solar pumping systems (pumps and solar panels) at the following project sites: Zem Zem and Sourour (Trarza), Bénichab (Inchiri), and Dhaya, Tindwali and Aoujeft (Adrar). These are sites where the project is undertaken agroecology interventions under its Component 3 (or dune stabilization in the case of Aoujeft, where further valorization of the site is planned with cultivation of henna with the water accessed). In addition, sixteen (16) cooperatives focused on vegetable gardening and date cultivation in the municipality of Tawaz (Adrar) have also benefited from the installation of smaller solar pumping equipment on one artisanal well for each cooperative. A hydraulic study was carried out in the intervention area to assess the water needs, take stock of the existing water infrastructure, and propose measures to be implemented to resolve water-related challenges at each site. | HS |
| Output 2.2: Small-scale infrastructures implemented on 4 water courses to increase infiltration and to reduce erosion and flooding | Q4 2025 | 50% | 95% | In this reporting period, CES/DRS infrastructures (gabions to slow down the flow of water) were installed in two (2) additional sites in the Wilaya of Adrar (in Aoujeft commune). The works were already completed at the Dakhlet Hel Abdawa site and are close to completion at the Loudeye site. In the previous reporting period, CES/DRS structures were installed at Dhaya and Haye Daira, in the Tawaz commune in Adrar. Also in previous reporting periods, a study was undertaken to identify CES/DRS techniques in four watersheds. This study was carried out on around ten sites throughout the Wilaya of Adrar and resulted in the selection of four priority sites according to well-defined criteria. | S |
| Output 2.3: 8 efficient irrigation water distribution systems established (one in each project site) | Q2 2023 | 70% | 90% | In this reporting period, the installation of irrigation water distribution systems was completed for 7 additional agroecology sites, bringing the total number of sites to 11. The additional sites are 1 in Trarza, 2 in Inchiri and 4 in Adrar. 3 additional irrigation systems are being installed in Inchiri, to be completed in the second half of 2025. In previous reporting periods, irrigation water distribution systems were installed within 5 agroecology sites (2 in Trarza, 1 in Inchiri and 2 in Adrar). In addition, during this reporting period, all the dune fixation sites in Adrar were connected to existing wells, boreholes or urban water distribution networks for irrigation (except for the Tekemkount site, which was completed in 2022). The project has also provided plastic tanks across all project sites for water storage and transport. These are used for providing irrigation to project interventions, where those interventions are far from other sources of water. As the plastic tanks are mobile, they can be easily moved around to provide irrigation support where most needed. | S |
| Output 2.4: 8 community associations (e.g. cooperatives, AGPOs) trained on sustainable and efficient water management and distribution (one in each project site) | Q4 2025 | 0% | 90% | In this reporting period, a series of workshops were organized in May-June 2025 to train local communities on efficient and sustainable water use and management. One workshop took place in each of the project’s target communes (8 workshops in total), and they were attended by a total of 60 participants (including 37 women). The main topics covered included water management challenges in relation to climate change and innovative solutions for sustainable water management. | S |
| COMPONENT 3: Protection, productivity, and diversification of local livelihoods |  |  |  |  |  |
| Output 3.1: Regional community nurseries specialized in plant production for arid ecoregions established and operational, and training for their sustainable management provided to local communities or cooperatives in 3 wilayas | Q2 2023 | 75% | 95% | In this reporting period, 75,000 additional plants were produced in the project’s 3 regional nurseries (25,000 in each project Wilaya). This brings the total number of plants produced in the regional nurseries to date to 290,000. In the previous reporting period, the project established three regional nurseries, one in each project Wilaya, managed by the regional delegations of MEDD. The three nurseries produced 65,000 plants in 2022 (20,000 in Adrar, 20,000 in Inchiri and 25,000 in Trarza), 75,000 plants in 2023 (25,000 in each site), and another 75,000 plants in 2024. The plants have been distributed mainly to regional administrations in the context of annual Tree Week celebrations, as well as to communities and community-based organizations, as the project’s contribution to national reforestation efforts. Most of the plants were distributed during the National Tree Weeks in 2022, 2023, 2024 and 2025. | S |
| Output 3.2: EbA interventions implemented on 400 hectares of dunes to protect vulnerable communities, livelihoods, and ecosystems from dune-migration | Q4 2025 | 28% | 45% | In this reporting period, dune stabilization interventions were expanded onto an additional 70 hectares, resulting in a total dune stabilization achievement to date of 181 ha. This was accompanied by the production and installation of 6,000 linear meters of wattle in this reporting period. The sites covered in the second half of 2024 were Zem Zem, El Menar and El Ain in Trarza, and Tenyall, Medina Ghadima and Aoujeft in Adrar. All dune stabilization sites are fenced to protect the seedlings. Furthermore, preparations for dune stabilization on an additional 19 ha, accompanied by 6,000 meters of wattle, were undertaken in this reporting period. The sites to be covered in the second half of 2025 include Chinguetti in Adrar and Zem Zem in Trarza. 9,500 plants have been produced for this purpose, as well as 95,000 additional plants for replenishment at existing sites with poor survival rate. Considering the very arid conditions in most of the project sites, the target of 400 ha will not be realistic with the budget available. A revised target in the order of 200 ha will be set following the completion of the project’s Mid-Term Review (MTR). | MS |
| Output 3.3: EbA interventions implemented on 150 hectares to shelter vulnerable communities from dune migration, heat, and wind and to provide forage for livestock and non-timber forest products | Q4 2025 | 25% | 32% | In this reporting period, the establishment of an additional 10 hectares of agroecological systems was initiated on 1 additional site in Inchiri. This results in a total achievement to date of 38 hectares across 11 sites. In previous reporting periods, 20 hectares of agroecological systems were established in 2024 across 6 sites: Tabrenkount / Benichab (Inchiri), Tekemkount, Chinguetti, Tindwali and Dakhlett Hel Abdawa (Adrar), and El Menar (Trarza), and in 2022 across 5 sites: Zem Zem and Sourour (Trarza), Bénichab (Inchiri), and Dhaya and Tindwali (Adrar). The agroecology sites are set up with a perimeter windbreak and interior windbreaks consisting of various tree species (many of which can be also used for fodder and other products). In the more recent sites, larger (30-50m wide) forest tree perimeters are established, for optimizing soil conservation benefits and the protection of the market gardening interventions inside the perimeter. Fruit trees are planted inside the blocks, and the spaces between the trees are used for market gardening. These agroecological systems are connected to boreholes or other water sources for irrigation, provided by the project under Component 2. In this reporting period, the Tabrenkount site in Inchiri was equipped with a pump and solar panels, and the village was connected to the irrigation system of the agroecology site for its water supply. Considering the very arid conditions in most of the project sites, the focus of the activities was shifted somewhat during the project implementation phase, from agroforestry and NTFPs to a broader agroecological system approach. The NTFP potential is very limited or even non-existent in the project intervention area, with the exception of Trarza, where they may be introduced depending on the interest of the communities. Most NTFPs sold on local markets come from other Wilayas. Furthermore, the target of 150 ha will not be realistic with the budget available, and a revised target in the order of 75 ha will be adopted following the completion of the project Mid-Term Review (MTR). | MS |
| Output 3.4: Additional natural resource-based livelihoods introduced for local populations | Q4 2025 | 73% | 88% | In this reporting period, two additional income-generating activities were introduced: one community shop and one plant nursery for youth. This brought the total number of IGAs supported by the project to 41. In this reporting period, the focus remained on consolidating and supporting the IGAs established in previous reporting periods. At present, approximately 705 cooperative members (almost exclusively women) participate in the alternative income-generating activities established by the project, as direct beneficiaries. The activities supported to date are as follows: Community shops: 24 Butcher’s shops: 5 Couscous production: 6 Fishmongers: 1 Gas depot: 2 Vegetable trade: 1 Plant production nursery for young people: 2 In a previous reporting period, a value chain feasibility study was carried out by the project to inform the selection of the livelihoods to be developed. Some of the recommendations of the study included the processing of dates and NTFPs. Depending on the interest of the communities, the project may provide training and support for these value chains. As reported under Component 2, to support alternative income-generating activities, the project has also installed two new wells for a vegetable gardening cooperative in Akjoujt (Inchiri) and equipped them with solar pumping systems. Sixteen cooperatives focused on vegetable gardening and date cultivation in the municipality of Tawaz (Adrar) have also benefited from the installation of solar pumping equipment on one small artisanal well for each cooperative. | S |
| COMPONENT 4: Knowledge for action on climate change and EbA in arid ecosystems |  |  |  |  |  |
| Output 4.1: 5 publications on policy-relevant research findings published based on monitoring of adaptation results generated under Components 2 and 3, and disseminated to at least 45 decision-makers | Q4 2025 | 10% | N/A | Due to the significant underbudgeting for activities under Outputs 3.1 and 3.2 (dune stabilization and agroecology sites), it was decided to remove this output from the project work plan and allocate the funds to those outputs. This was done in the current reporting period, as part of the 2025 budget revision, and before the recruitment of the partner research institution was finalized. | N/A |
| Output 4.2: A series of 4 EbA handbooks detailing best practices for arid ecosystems developed and shared with at least 550 members of local implementation structures across the 3 target wilayas | Q4 2023 | 10% | 10% | In this reporting period, the Terms of Reference for the identification of the EbA approaches to be included in the handbooks were further developed. The timeline for this output has been pushed back compared with the original plan, and the activities will be launched in Q4 2025. | MS |
| Output 4.3: At least 750 local stakeholders informed of climate change adaptation and good EbA practices in the three target wilayas | Q4 2025 | 30% | 50% | In this reporting period, the project contributed to the awareness-raising events during the August 2024 Tree Week (Semaine de l’Arbre) in the 3 target wilayas. In addition, it contributed to environmental and climate change awareness raising at the Festival de Chinguetti event in Adrar (in December 2024). The more structured knowledge and awareness-raising activities of the project are planned to be launched in Q4 2025. Overall, the knowledge, awareness and capacity of local communities and community-based organizations have continued to be increased in this reporting period through their engagement in the planning and implementation of project activities on the ground. Local stakeholders have also continued to be sensitized on climate change adaptation and the EbA approach through their continued interaction with the project team (Regional Delegations and PMU), during their technical support and field monitoring missions. Indeed, the arid nature of the project intervention area has made it easier to illustrate to stakeholders the impacts of climate change and the relevance of healthy ecosystems in building resilience to them. The engagement of young people and women in the production of plants and in dune stabilization interventions has served a specific awareness-raising function, in addition to contributing to the restoration of the natural and living environment as well as to the promotion of green jobs. | S |

4. Risk Rating

4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating.

| Risk Factor | EA’s Rating | TM’s Rating |
| --- | --- | --- |
| 1. Management structure – Roles and responsibilities | L | L |
| 2. Governance structure – Oversight | L | L |
| 3. Implementation schedule | L | L |
| 4. Budget | H | S |
| 5. Financial Management | L | L |
| 6. Reporting | L | L |
| 7. Capacity to deliver | L | L |

If any of the risk factors is rated a Moderate or higher, please include it in table B below.

4.2 Table B. Risk-Log

| Risk | Risk affecting: | Risk Rating |  |  |  |  |  |  | Variation respect to last rating |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Outcome / outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 (this PIR) | MTR | PIR 4 | PIR 5 | Δ | Justification |
| Risks at the national level |  |  |  |  |  |  |  |  |  |  |
| High turnover of staff in the project team or on the project steering committee. | All outcomes and outputs | L | L | L | L |  |  |  | = | The project is housed in the Climate and Green Economy Directorate at the Ministry of Environment and Sustainable Development (MEDD) and is managed by a Project Management Unit (PMU). In the field, the monitoring of activities is ensured by the Regional Delegations in the three project Wilayas. The project is governed by the Project Steering Committee (PSC), chaired by the MEDD Secretary General. In this reporting period, the project’s Monitoring and Evaluation expert resigned and moved to a Project Coordinator position for another project at MEDD. However, this has been the only departure from the core project team to date. At the central level, there have been significant changes in senior MEDD positions in the course of its implementation to date (Minister, SG, Director). Furthermore, at the regional / local level, there have been most recently changes in the environment delegate in Adrar and Inchiri, as well as new environment inspectors in Akjoujt (Inchiri) and Aoujeft (Adrar). However, these changes have not had a major impact on project operations, and the risk on project implementation remains low. |
| Possible differences in practices, procedures, mandates and visions between key project partners and non-governmental stakeholders. | All outcomes and outputs | L | L | L | L |  |  |  | = | No change observed at this stage (the risk remains low). |
| Unwillingness to collaborate or to share information, and disagreement among stakeholders on the distribution of roles in the proposed project. | All outcomes and outputs | M | L | L | L |  |  |  | = | This risk has remained low since the project inception stage. During the project inception workshop, the roles, responsibilities, and priorities of all the stakeholders were clarified. Synergies and collaboration between all project stakeholders are facilitated by the PMU at national, regional, and local levels. |
| Limited technical capacity to develop and implement the project interventions. | All outcomes and outputs | M | L | L | L |  |  |  | = | This risk remained low since the project inception stage. A series of training events were undertaken during the first two years of project implementation, significantly strengthening the capacity of national, regional and local implementing partners to plan and implement EbA measures. Specifically, the DREDDs and other institutions participated in the formal trainings provided project under Component 1, but also in more informal trainings conducted by key experts and specialized NGOs. In addition, PMU supervision missions have helped to reduce this risk. |
| Procurement delays due to inefficient or overly complex administrative procedures. | All outcomes and outputs | M | L | L | L |  |  |  | = | An internal commission was set up to handle procurement issues. Only acquisitions exceeding the thresholds set by law are submitted to the Central Procurement Commission. These thresholds are approximately USD 41,500 for consulting services and 70,000 USD for the acquisition of equipment. As such, procurement delays are not expected to constitute a significant risk to the project, nor have any issues been faced to date. |
| Climate change adaptation priorities undermined by political events, national emergencies or civil unrest. | All outcomes and outputs | M | L | L | L |  |  |  | = | There have been some changes at the local level, which have resulted in shifting political priorities (for example, the turnover of the Mayor positions in all the 8 project communes). However, these have not posed a major risk to project implementation to date. |
| Risks at the local level |  |  |  |  |  |  |  |  |  |  |
| Limited acceptance and/or adoption of adaptation interventions by local communities. | All outcomes and outputs | M | L | L | L |  |  |  | = | No major issues have been identified at this stage and the risk level has remained low since project inception stage. Local communities have been involved in the design and implementation of the adaptation technologies, which are being implemented in an equitable manner. In addition, the project has focused on raising awareness of the local communities on the risks associated with the continuous degradation of ecosystems and associated impacts on community livelihoods, on climate change and potential impacts, and on the benefits of adaptation and EbA approaches through activities under Components 1 and 4. Interventions generating tangible benefits (including water provisioning infrastructure and income-generating alternative livelihoods) were prioritized in the first years of the project, to ensure benefits for community and optimal community buy-in. Although some challenges related to social conflict within the communities have been observed in the current reporting period, these have been addressed proactively by the PMU, with full support from MEDD and the regional and local administrations. As such, they have not resulted in major impacts in terms of the adoption of the project interventions. |
| Lack of funds available for ensuring the sustainability of certain activities beyond the duration of the project. | All outcomes and outputs | M | M | M | M |  |  |  | = | The risk level remains moderate until the project partners (MEDD, UNEP, etc.) have developed a project exit strategy and/or a sustainability plan to ensure the sustainability of project interventions beyond the project lifetime. |
| Natural hazards and climate shocks. | All outcomes and outputs | M | M | H | S |  |  |  | ↓ | This risk has been reduced from high to significant. Following the major negative impacts on seedling survival rates experienced in last reporting period in the Wilaya of Adrar, as a result of lack of rainfall, in this reporting period the rainfall situation has been somewhat better. Overall, the project areas and indeed the entire country continue to be exposed to natural hazards and climate shocks, even though apart from drought, other challenges have not materialized to date . |
| Arid conditions in the project sites and distances between community water points. | All outcomes and outputs | H | H | H | S |  |  |  | ↓ | This risk has been reduced from high to significant, with the somewhat improved rainfall in this reporting period. Furthermore, much emphasis has been placed in this reporting period in improving access to irrigation water at the project dune stabilization and agroecology sites, which has contributed to reducing the risk level. Nonetheless, due to the arid nature of the project areas and the unpredictability of rainfall, the risk is still significant and must be monitored closely. |
| Limited participation of women in project activities and/or limited access to its benefits by women, associated with a gender inequitable national context. | All outcomes and outputs | M | M | M | M |  |  |  | = | This risk remains moderate. The engagement of women in almost all project activities is high. Nonetheless, women’s participation in formal project training workshops and decision-making processes remains a challenge, which needs to be continuously addressed. |
| Continued presence of the COVID-19 pandemic in Mauritania (and/or a resurgence of the pandemic), resulting in restrictions on in-person meetings and on in-country and international travel | All outcomes and outputs | H | L | L | L |  |  |  | = | The risks associated with the COVID-19 pandemic no longer affect the project or the implementation of its activities. |
| Consolidated project risk |  | M | M | M | M |  |  |  | = |  |

4.3 Table C. Outstanding Moderate, Significant, and High risks

| Risk | Actions decided during the previous reporting instance (PIRt-1, MTR, etc.) | Actions effectively undertaken this reporting period | Additional mitigation measures for the next periods |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | What | When | By whom |
| Lack of funds available for ensuring the sustainability of certain activities beyond the duration of the project. | CEO ER: Financing needs and possible funding options for ensuring the long-term sustainability of project results will be identified in the sustainability strategy. Adaptation measures will also be integrated into policies and awareness raising will be conducted for decision makers. The participation of key stakeholders in implementation will be progressive and their responsibility for site management will increase by 25% each year. Last PIRs: Discussions with participating institutions and beneficiaries on the possible sources and types of support needed to maintain the project investments beyond the lifetime of the project. The participation of key stakeholders in project implementation will be continued and their responsibility increased. Linkages with the ongoing NAP process in Mauritania will be strengthened, to ensure the integration of arid lands adaptation measures in its capacity building, awareness raising and policy mainstreaming activities. | In this reporting period, discussions on how to sustain the project activities have continued with various stakeholders, with a view to making the project’s restoration sites future development hubs. In particular, the development of other productive uses for the water resources provided at dune stabilization sites is the key for their long-term maintenance. Options for this has been explored at several sites. Furthermore, the project’s support to alternative income-generating activities will help to increase the income of target groups, as well as enabling them to become self-financing. | In the upcoming last year of project implementation, an exit strategy or a sustainability plan should be put in place by the project partners, covering the maintenance needs at all project sites. Discussions will be continued with participating institutions and beneficiaries on the possible sources and types of support needed to maintain the project investments beyond the lifetime of the project. Concrete options such as inclusion of maintenance costs in commune budgets will be explored. Training on financial and business management will be offered to the beneficiaries of the income-generating activities, to strengthen their sustainability. Linkages with the ongoing NAP process in Mauritania will be strengthened, to ensure the integration of arid lands adaptation measures in its capacity building, awareness raising and policy mainstreaming activities. | By Q1-Q2 2026 | Project Management Unit/MEDD, administrative authorities, village management committees |
| Natural hazards and climate shocks. | CEO ER and last PIR: Activities will take into account and integrate climate and early warning information. EbA interventions will be designed to withstand the climate (for example, best practices will be followed in terms of climate-resilient planting operations, species selection, etc.). | Activities have continued to be designed and implemented keeping in mind potential climate shocks, in particular drought. Most importantly, in areas with very limited rainfall, access to irrigation water has been significantly improved in the current reporting period to enhance seedling survival rates. | The risk mitigation measures identified and implemented previously will be continued. | Continuously | Project Management Unit and partners |
| Arid conditions in the project sites and distances between community water points. | CEO ER: Sufficient watering and protection of the seedlings will be ensured by the project teams in all target wilayas. Last PIR: The establishment of water provisioning infrastructure will be continued. Seedlings will continue to be protected in the nurseries and after planting. | The implementation of water provisioning activities has continued in this reporting period. In particular, emphasis has been put on connecting dune stabilization sites to existing sources of irrigation wates, including from the irrigation systems of the agroecology sites. This has resulted in an improved and continuous supply of water to the plantations. For details on the infrastructures put in place across all the target Wilayas to date, please see reporting under Component 2. | The establishment of water provisioning infrastructure will be continued. Seedlings will continue to be protected in the nurseries and after planting. | Continuously and specifically at the nursery and planting stages | Project Management Unit and partners |
| Limited participation of women in project activities and/or limited access to its benefits by women, associated with a gender inequitable national context. | CEO ER: The project will adopt a locally-adapted participatory approach to include women in project activities as much as possible, informed by the gender consultant, and work towards women’s empowerment while respecting local cultural norms (to ensure transparency and acceptance). Last PIR: The participation of women in the project activities will continue to be ensured. In particular, their full participation in the project trainings and decision-making will be encouraged. | Participatory approaches taking into account of gender and age have been continued across the target wilayas. Women’s participation in almost project activities is high, including ecosystem restoration interventions. Women make up 55% of the current project beneficiaries, and almost all beneficiaries of the income-generating activities are women. Furthermore, around 33% and 40% of the participants in the regionally-organized civil-society and private sector training workshops, respectively, have been women, which is a relatively high percentage in the context in question. For the on-site training events, women’s participation reaches 75-80%. | The recruitment of the project gender expert will be relaunched and completed. The participation of women in the project activities will continue to be ensured. In particular, their full participation in the project trainings, awareness-raising activities and decision-making will continue to be encouraged. | Continuously | Project Management Unit and partners |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Significant Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Project Minor Amendments

5.1 Table A: Listing of all Minor Amendment

|  | Results framework |
| --- | --- |
|  | Components and cost |
|  | Institutional and implementation arrangements |
|  | Financial management |
|  | Implementation schedule |
|  | Executing Entity |
|  | Executing Entity Category |
|  | Minor project objective change |
|  | Safeguards |
|  | Risk analysis |
|  | Increase of GEF project financing up to 5% |
|  | Co-financing |
|  | Location of project activity |
|  | Other |

| Minor amendments |  |
| --- | --- |

5.2 Table B: History of project revisions and/or extensions

| Version | Type | Signed/Approved by UNEP | Entry into Force (last signature Date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |
| Original legal instrument | PCA | 1 October 2021 | 23 October 2021 | 31 March 2026 |  |

GEO Location Information:

The Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com Please see the Geocoding User Guide by clicking here

| Location Name Required field | Latitude Required field | Longitude Required field | Geo Name ID Required field if the location is not an exact site | Location Description Optional text field | Activity Description Optional text field |
| --- | --- | --- | --- | --- | --- |
| Zem Zem | 17.527102 | -14.695564 |  |  |  |
| Demame | 17.501246 | -14.625869 |  |  |  |
| Sourour | 17.252003 | -14.318798 |  |  |  |
| Ajouer | 17.28818 | -14.346318 |  |  |  |
| El Mabrouk 2 | 17.572689 | -14.731836 |  |  |  |
| Boutilimitt | 17.546923 | -14.696407 |  |  |  |
| Chinguetti | 20.461645 | -12.362244 |  |  |  |
| Toukoumkount | 20.490961 | -12.329126 |  |  |  |
| Tindewaly | 20.473167 | -12.352099 |  |  |  |
| Tawaz | 20.683978 | -12.884158 |  |  |  |
| Amder | 20.542766 | -12.944925 |  |  |  |
| Dhaya | 20.653502 | -13.007621 |  |  |  |
| Talhayatt | 20.142131 | -13.051096 |  |  |  |
| Loudeye Bodiamoz | 20.014362 | -13.058954 |  |  |  |
| Dakhlet Elhel Abdawo | 20.045523 | -13.063045 |  |  |  |
| Aoujeft | 20.037739 | -13.043681 |  |  |  |
| Aboyra | 20.488329 | -12.319720 |  |  |  |
| Toueizikt | 20.621173 | -13.030973 |  |  |  |
| Toungade | 20.060508 | -12.982162 |  |  |  |
| Akjoujt | 19.752136 | -14.385979 |  |  |  |
| Benichab | 19.97634 | -15.395135 |  |  |  |
| M'heijératt | 19.02943 | -16.183086 |  |  |  |
| Tiwilit | 18.885776 | -16.183086 |  |  |  |
| Lemcid | 18.688622 | -16.13852 |  |  |  |
| Bellewakh | 18.516964 | -16.071685 |  |  |  |

Please provide any further geo-referenced information and map where the project interventions is taking place as appropriate. *

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Level 0: TBD in baseline study; Level 1: 200 hectares of land stabilised or under agro-forestry; Level 2: 400 hectares of land stabilised or under agro-forestry; Level 3: 65% survivorship of plants achieved; Level 4: Dunes are fixed and livelihoods protected for 30% of people living in the three target wilayas against dune invasion, heat and wind through EbA measures implemented on 550 hectares.

Outputs and activities (or deliverables) as described in the project logframe (and workplan) or in any updated project revision.

The completion dates should be as per latest workplan (latest project revision).

As much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc.

To be provided by the UNEP Task Manager

DRS : Défense et Restauration des Sols : diguettes, digues filtrantes, gabions, seuils, corrections de ravines, cordons pierreux (i.e. water speed deceleration infrastructure that increases infiltration, such as check dams, gabions, bunds, stone rows…).