Mid-Term Evaluation Report

Management Response

From WWF GEF Agency

Coral Reef Rescue: Resilient Coral Reefs, Resilient Communities (GEF ID#10575)

World Wildlife Fund

2023 – 2025

Structure of Management Response ;

Introduction and Background;

1	Part I. Assessment of Quality of the Report and Findings, and WWF GEF Agency Feedback

2	Part II. Corrections

3	Part III Response to recommendations, as applicable

Background;

This project’s objective is to build capacity and solutions for safeguarding globally significant, climate-resilient coral reefs, ensuring the long-term survival of coral reef ecosystems in the Philippines, Solomon Islands, Fiji, Indonesia, Tanzania, and Madagascar (with Cuba included through non-GEF funds). The project creates global knowledge and capacity-building networks to share, identify, and target solutions, as well as enable real-time monitoring for coral reef conservation, thereby strengthening capacities across all seven countries. The project supports countries in identifying key threats to coral reefs and developing national strategies that provide clear pathways to address those threats. This is achieved through a participatory process that establishes national platforms and ensures meaningful engagement of local coral reef communities. The project also facilitates alignment of co-financing opportunities with priorities identified in the national strategies and supports countries in mobilizing additional public and private investments. This includes developing investment portfolios focused on sustainable businesses and long-term livelihood opportunities for local communities in priority climate-resilient coral reef areas.

Introduction :

This document provides the WWF GEF Implementation Agency's feedback on the Mid-Term Evaluation Report for the "Coral Reef Rescue: Resilient Coral Reefs, Resilient Communities” project in Fiji, Indonesia, Madagascar, Philippines, Solomon Islands, and Tanzania (ID#10575)". Prepared in collaboration with the Project Management Unit (PMU) at the University of Queensland International Development (UQID), the Project Executing Agency, this response highlights key takeaways and lessons learned and how to integrate them into the remaining Year of project implementation and a potential Phase 2 of this International Waters project.

Part I. Assessment of Quality of the Report and Findings, and WWF GEF Agency Feedback

The quality of this report is considered satisfactory. The findings align with the issues and topics previously identified by the PMU staff located in UQID and sub-executing partners located within the National Technical Facilities. There were no new areas of concern or risks that had not previously been identified.

Noting the many recommendations and some areas for improvement, the WWF GEF Agency agrees with the report’s findings that the project is performing strongly and is highly relevant to national and global coral reef conservation priorities. Stakeholders across all participating countries have received the project positively, and the establishment of National Hubs and National Action Plans is effectively helping governments convene partners and prioritize coral reef protection. The evaluation confirms that the project is well aligned with national biodiversity commitments and has elevated the importance of coral reefs on national agendas in a handful of countries. The scientific foundation identifying resilient bio-climatic reef units was validated by stakeholders, and communities near reef areas have responded positively because the project addresses their concerns about reef degradation.

The report also highlights strong project management and coordination. WWF GEF Agency agrees that the PMU within the University of Queensland has been an exceptional executing partner. The project has produced numerous high-quality knowledge products and tools—such as Coral Huddle, MOOCs, and the Data Portal—that are widely used. Performance results are also encouraging, with seven of twelve outcome indicators already exceeded at mid-term and nearly 5,000 beneficiaries reached, including strong participation of women.

Overall, the project was rated Satisfactory with a Highly Satisfactory relevance rating. The sustainability outlook for project outcomes is rated Likely, with increased awareness and commitment to coral reef conservation expected to endure beyond the life of the project. The evaluation recommends considering a Phase 2 of the project accessing GEF9 resources to continue the momentum of the first project including the National Action Plans for Coral Conservation, strengthening sustainability of the National Hubs, and making the courses and tools created more accessible. WWF GEF Agency agrees with these high-level report findings

Part II. Corrections

| Evaluation Statement | WWF GEF Agency Correction |
| --- | --- |
| Delays in the Philippines and Madagascar were beyond the control of PMU and NTFs. | WWF GEF Agency agrees that the implementation delays in the Philippines were largely beyond the control of the PMU and the NTF. However, in the case of Madagascar, while national political instability in project year 3 created challenges for engagement with government counterparts, an agreement between the UQID PMU and WCS Madagascar was already in place and funding had been disbursed to support activities; therefore, the implementation delays cannot be attributed solely to external factors, as several activities could still have proceeded despite the limited functioning of national government structures. |

3	Part III Response to recommendations, as applicable

Management response matrix

| Core Criteria | Management response to the Terminal Evaluation Recommendations for Coral Reef Rescue: Resilient Coral Reefs, Resilient Communities (GEF ID#10575) |  |  |  |  | August, 2025 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Evaluation Recommendation (a) | Management response (b) Accepted, Partially Accepted or Rejected | Management plan |  |  |  |
|  |  |  | Actions to be taken, and/or comments about partial acceptance or rejection (c) | Responsible unit (d) | Time frame (e) | Further funding required (Y or N) (f) |
| Relevance | Rescale Component 3 (Coral Friendly Businesses) to better match socio-economic conditions in BCU communities. Assess community preparedness, private sector involvement, and financial best practices before financing. Refocus the outcome to support different scales of businesses or livelihoods and set realistic expectations, particularly in remote areas. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU address these considerations during the development and refinement of Component 3 activities within the annual work plan for the final year of implementation, in consultation with the NTFs. | UQID, NTFs | During the final year of implementation | N |
| Relevance | Explore implications of the updated WCS 50 Reef Plus research to refine targeting of climate-resilient reefs and understand how new research may affect beneficiaries and conservation priorities in the six implementing countries. | Rejected | WWF GEF Agency does not accept this recommendation at this time, as the project is in its final year of implementation. Consideration of the WCS 50-Reefs Plus research and any new scientific data will be more appropriately explored during the design of a potential Phase II CRR project rather than during the remaining implementation period. Additionally, it is unknown as to when the 50 Reefs Plus research will be published. |  |  |  |
| Coherence | Improve coordination with other coral reef initiatives and government programs to clarify overlapping mandates and strengthen collaboration with regional and private sector initiatives. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU integrate this topic into discussions with NTFs especially promoting bringing this topic up during national hub meetings and opening the floor to other initiatives or aligned projects. This is key for the PMU to action with NTFs during and shortly after the preparation of the annual work plans for the final year of implementation. | UQID, NTFs | Within the next 6 months | N |
| Coherence | Strengthen implementation of the communication strategy, including country-specific communication strategies, documentation of good practices, and increased communication with the public. | Accepted | This recommendation has already been implemented and will continue to be implemented by the communications consultant newly hired by the project management unit in UQ. It will ultimately be a year for the project to increase visibility on a global scale, and we look forward to working towards that by increasing NTF engagement in Component 4 and support from WWF GEF in promoting the project on WWF websites. | UQID, NTFs, WWF GEF Agency | Within the next year | N |
| Efficiency | Reallocate budgets from under-spent allocations to support cross-country visits, learning exchanges, and collaboration among project countries. | Accepted | WWF GEF Agency encourages the PMU to hold these important conversations around final funding allocation for project Year 4 and unspent funding reallocation as soon as possible and to be clear about expectations from NTFs regarding unspent funding that is disbursed, noting it will need to be returned. | UQID, NTFs | Immediately | N |
| Efficiency | Adjust the co-finance target to approximately $27 million USD to reflect realistic commitments. | Accepted | WWF GEF Agency will work with UQID during preparation of the Year 3 Project Progress Report to revise and document the updated co-financing estimate, which will then be reflected in the Project Implementation Report submitted to GEF. | UQID | Within the next 6 months | N |
| Efficiency | Provide clearer guidance to partners on what qualifies as GEF co-financing and how it should be documented. | Accepted | WWF GEF Agency will share with UQID a guidance document explaining what co-financing commitments are for UQID to share with project partners as they gather co-financing letters. | WWF GEF Agency | Within the next 2 months | N |
| Effectiveness | Revise all 12 Results Framework indicators to ensure they accurately measure progress and reflect country-level implementation realities. | Accepted | WWF-GEF Agency recommends that the PMU at UQ ID work to make this adjustment for the final year RF and reporting on the results framework, as this is an optimal time to adjust targets and rethink how we are displaying results for the project. The annual work plan and budget is due within the next two months to the GEF Agency. | UQID | Within the next 2 months | N |
| Effectiveness | Provide additional third-party support (communications, language translation for reporting up to the PMU or facilitation) where needed in Indonesia, Madagascar and the Philippines. | Partially Accepted | WWF-GEF Agency recommends that the PMU at UQ ID work to make this adjustment for the final year workplan and activity planning as this is an optimal time to adjust activities with NTFs. The partial acceptance is due to the fact that a consultant in Philippines would not be appropriate or possible at this time due to delay in implementation in the Philippines. The annual work plan and budget is due within the next two months to the GEF Agency. | NTFs led, supported by UQID | Within the next 2 months | N |
| Effectiveness | Improve report quality by ensuring outputs include executive summaries, maps, photos in PPRs and clear analytical conclusions. | Rejected | While more guidance could be provided on how to write formal reports, WWF-GEF agency disagrees with the recommendation to improve report quality (PPRs) and the unsatisfactory rating given in Annex 5.6 to these listed reports; - 1.1.1.3 national Hub for Coral Reef Conservation 1st meeting - 2.1.1.3 MPRU Management Meeting _ Validations of CRR and NAPCRCR, - 2.1.1.5 National Hub for Conservation 1st meeting - 2.1.1.6 nhcrc_reflection_1st meeting The documents referenced primarily consist of meeting notes intended to capture discussions and outcomes rather than formal analytical reports. The level of documentation provided has been sufficient to support project monitoring and evaluation. These reports also meet the “evidence” required as listed in the AWPB and the Coral Huddle. This is satisfactory for the WWF-GEF agency. The project progress reports (PPR) continue to be thorough and extensive. PPRs are formatted into Project Implementation Reports (PIRs) that are submitted to the GEF, these reports are expected to be brief and do not allow the ability to upload photos within the report. |  |  |  |
| Effectiveness | Develop communication tools such as mobile video storytelling (Vox Pop) training using a train-the-trainer approach to increase community voices. | Rejected | The project is currently in its final year of implementation, and introducing a new activity such as mobile video storytelling training would create additional workload for country teams at a stage when implementation efforts are focused on consolidating results and completing planned deliverables. While strengthening communication and community voice is recognized as valuable, global communications activities will already be prioritized under Component 4 during the final year of the project. |  |  |  |
| Effectiveness | Improve visibility and promotion of the project website across partner organizations. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU integrate this topic into discussions with NTFs especially encouraging WCS to publicize the project, and working on internal UQID website publicity to ensure the project website is easily found through a google search. | UQID, NTFs | Within the next 6 months | N |
| Effectiveness | Strengthen annual reflection meetings so they focus on learning and cross-country synthesis rather than only reporting. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU discusses with NTFs how they hold their annual reflections, including how to better encourage countries to cross-share and possibly host more meetings focused on regional collaboration. | UQID | during the final year of implementation | N |
| Results/Impact | Approve a six-month no-cost extension plus three-month closure period to compensate for delays and consolidate outcomes. | Accepted | WWF GEF Agency has initiated a No-Cost Extension for the project execution agreement with UQID extending the end date of the project. | WWF GEF Agency | Immediately | N |
| Sustainability | Develop sustainability strategies in each country and define exit strategies for global assets such as MOOCs and the Data Portal. | Accepted | WWF-GEF Agency recommends that the PMU at UQID work to make this adjustment for the final year workplan and activity planning as this is an optimal time to adjust activities with NTFs. Some work is already taking place to develop sustainability strategies for the National Hubs, National Action Plans, and Global assets. This recommendation is accepted for the coutnries where there are systems established and adequate resources to develop a sustainbility strategy. | UQID, NTFs | Within the next 2 months | N |
| Sustainability | Increase availability of project materials in local languages and develop additional multimedia resources to improve engagement. | Rejected | The project is currently in its final year of implementation, and introducing a new activity such as translating materials and developing additional unplanned materials would be extremely burdensome. While strengthening communication and community voice is recognized as valuable, global communications activities will already be prioritized under Component 4 during the final year of the project. |  |  |  |
| Adaptive Capacity | Strengthen cross-country learning exchanges among NTFs and National Hub members. | Accepted | WWF-GEF Agency recommends that the PMU at UQ ID work to make this adjustment for the final year workplan and activity planning as this is an optimal time to adjust activities with NTFs. This will also be taken into consideration during the IWC 11 conference, ICRS and Bali Reflection workshop when NTFs will be encouraged to share cross-country learning. | UQID, NTFs and WWF GEF Agency | Within the next 6 months | N |
| Adaptive Capacity | Organize a project symposium with IW:Learn to exchange lessons, research findings and sustainability strategies. | Accepted | WWF GEF Agency is working together with PMU UQID to arrange a “twinning” event for the upcoming IWC 11. Additionally, the project will have an engaging Session at IWC 11 by inviting participants from each country to participate in the hosting of an educational and sharing session for all participants at IWC 11. | UQID, NTFs and WWF GEF Agency | October 2026 | N |
| Adaptive Capacity | Establish Communities of Practice and assess how they can emerge from technical working groups or training participants. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU integrate this topic into discussions with NTFs especially promoting bringing this topic up during national hub meetings. It is important to note that NTFs may not have the bandwidth to incorporate CoPs into their Y4 Workplan. | UQID, NTFs | Within the next 6 months | N |
| Adaptive Capacity | Hold a meeting of all NTFs, PMU and GEF WWF US six months before project closure to strengthen monitoring and evaluation. | Rejected | WWF GEF Agency does not agree that a monitoring-evaluation meeting needs to be held six months prior to close of the project as the scheduled global workshop in Q1 2026 will review some M&E topics. Additionally, the NTFs in country have demonstrated strong ability to report utilizing the coral reef huddle platform developed for inputting project progress. A reflection workshop may be considered near project end. |  |  |  |
| GEF Criteria – Gender & Safeguards | Hire additional GEDSI consultants to review emerging NAPs and assess potential power dynamics. | Rejected | WWF GEF Agency does not agree with this recommendation at this time as the project enters its final year of implementation. Consideration of a new activity focused on a product that has not been completed by more than half of the countries currently would not be a recommendation at this time. This will be more appropriately explored during the design of a potential Phase II CRR project rather than during the remaining implementation period. |  |  |  |
| GEF Criteria – Gender & Safeguards | Include women’s organizations, youth groups and vulnerable community representatives in National Hubs or working groups. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU integrate this topic into discussions with NTFs as they finalize their Y4 Workplans and start to organize further national hub meetings. | UQID, NTFs | Within the next 2 months | N |
| GEF Criteria – Gender & Safeguards | Provide separate consultation forums if needed to ensure meaningful participation of women and vulnerable groups. | Accepted |  |  |  |  |
| GEF Criteria – Gender & Safeguards | Ensure consultant Terms of Reference include gender and inclusion considerations. | Accepted | WWF GEF Agency accepts this recommendation and asks UQID to draft Consultant TORs with this lens going forward. | UQID, NTFs | during the final year of implementation | N |
| GEF Criteria – Gender & Safeguards | Standardize gender and youth participation reporting across project activities. | Accepted | WWF GEF Agency accepts this recommendation and understands the importance of updating the Results Framework. WWF GEF and UQID will work together to update the Results Framework for the final project year to include accounting for gender and age when reporting. | UQID, WWF GEF Agency | Within the next 2 months | N |
| GEF Criteria – Gender & Safeguards | Improve awareness of grievance mechanisms by communicating them clearly in local languages.Additionally, EA should check that measures are put in place to ensure that the GRM is gender sensitive and responsive to issues of SEAH. | Accepted | WWF GEF Agency accepts this recommendation and suggests that the PMU integrate this topic into discussions with NTFs as the PMU revisits grant agreements with NTFs for the final Year of Implementation and the GRM being fully accessible is a requirement within the WWF GEF Policies and procedures. | UQID, NTFs | Within the next 2 months | N |