## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | #NAME?
#NAME?

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards Achieving Project Objective(s) (Development Objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary on progress, challenges, and outcomes
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Latin America and the Caribbean (RLC)
Country(ies): | Guyana, Suriname, Trinidad & Tobago
Project Title: | Enhancing capacity for the adoption and implementation of EAF in the shrimp and groundfish fisheries of the North Brazil Shelf Large Marine Ecosystem (EAF4SG)
FAO Project Symbol: | GCP /SLC/220/GFF
GEF ID: | 10919
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | International Waters
Project Executing Partners: | The University of the West Indies
Initial project duration (years): | 4 Years
Project Dates
GEF CEO Endorsement Date: | 2023-04-01
Actual Agency Approval Date | 2023-03-16
Project Implementation Start Date/EOD: | 2023-08-01
First Disbursement Date | 2023-12-31
Planned Project End Date/NTE1: | 2027-07-30
Revised project implementation End date (if approved)2: | N/A
Actual Completion Date: | N/A
Expected Financial Closure Date: | 2028-07-30
Funding
GEF Grant Amount (USD): | 1776484
Total GEF grant delivery (as of June 30, 2025 (USD): | 977438
Total Co-financing amount (USD)3: | 7814157
Total estimated co-financing materialized as of June 30, 2025: | 995215.2094
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | 2025-01-24
Expected Mid-term Review date5: | N/A (MSP)
Actual Mid-term review date (if already completed): | N/A
Expected Terminal Evaluation Date: | 2027-01-31
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Moderately Satisfactory
Overall implementation progess rating: | Moderately Satisfactory
Overall risk rating: | Moderate
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 1st PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Ms. Nerissa Lucky, Technical and Project Coordinator, UWI |  | tpc_fisheries.proj@outlook.com
Budget Holder (BH) | Ms. Renata Clarke, Sub Regional Coordinator FAO-RLC |  | Renata.Clarke@fao.org
GEF Operational Focal Point (GEF OFP) | Mr. Kemraj Parsram, Environmental Protection Agency, Guyana Mr. Hayden Romano, EMA, Trinidad and Tobago Ms. Vanuessa Gefferie, Ministry of Spatial Planning and Environment, Suriname |  | kparsram@epaguyana.org hromano@ema.co.tt vanuessa.gefferie@gov.sr
Lead Technical Officer (LTO) | Mr. Marcelo Vasconcellos, FAO |  | Marcelo.Vasconcellos@fao.org
GEF Technical Officer (GTO) | Mr. Lorenzo Galbiatti, Natural Resources Officer, FAO-GEF Coordination Unit, CBC |  | lorenzo.galbiatti@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
Technical Project Co-ordinator | Yes | Nerissa Lucky, January 2024
Administrative and Operations Support Officer | Yes | Thara Gabriel, October 2023
Knowledge Management and Communications Officer | Yes | Allison Ali, January 2024
Monitoring and Evaluation Specialist | Yes | Rayanna Boodram, January 2024
Gender Specialist | Yes | Rayanna Boodram, March 2024

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
To advance adoption and implementation of the Ecosystem Approach to Fisheries (EAF) in the shrimp and groundfish fisheries in the North Brazil Shelf Large Marine Ecosystem, supporting country implementation of the CLME+ SAP | Outcome 1.1: Improved national and sub-regional data and data management systems supporting EAF fisheries management | Indicator 1: Improved scores of FAO EAF Implementation Monitoring Tool (IMT) for target shrimp and groundfish fisheries | Baseline for the EAF Monitoring tool will be undertaken during first 9 months of project implementation. None of the countries routinely collect socio- economic data. | All countries show improved scores (>25% of all attributes) in all 3 main components of EAF (ability to achieve, ecological well-being and human well-being). | All countries show improved scores (>50% of attributes) in all 3 main components of EAF (ability to achieve, ecological well-being and human well- being). | Regional EAF IMT training was provided to 20 participants from Guyana, Suriname, Barbados and Trinidad and Tobago provided. Guyana completed their baseline IMT Scoring. SUR: EAF IMT scoring completed TTO- Identified staffing constraints. Consultants to assist | 20% | Satisfactory (S)
|  | Outcome indicator 2: Number of countries with information systems (FMIS) hosting information on target fisheries (e.g. on gender disaggregated socio-economic data and SSF, including catch effort, etc) feeding into EAF management decisions | Current Fisheries Management Information Systems (FMIS) lack data on key areas required for effective EAF management and currently none of the countries has a completely operational FMIS. None of the countries routinely collects socio- economic data. | 1 country | 3 countries | Calipseo upgraded in Guyana. Upgrades in progress for TTO and Suriname. Socio economic data incorporated into design of Calipseo. Suriname collecting some socio economic data. | 30% | Satisfactory (S)
|  | Indicator 3: Increase in number of updated stock assessments for target species prepared in support of national and subregional management plans | 2 formal assessments for Atlantic seabob | 6 (At least 2 stocks assessments per country) and 6 management recommendations (2 per country) based on stock assessment results. | 12 (At least 4 stocks assessments per country) 3 stock assessments completed at the subregional level. 12 management recommendations (4 per country) based on stock assessment results 3 harmonized subregional management recommendations | 2 stock assessments for seabob in Guyana and Suriname completed in collaboration with CRFM in 2024.18 shared management recommendations. 1 updated stock assesment for seabob in Suriname in April 2025 in collaboration with CRFM and Fish4ACP. Management recommendations developed in collaboration with CRFM. 5 preliminary stock assessments developed in 2025 and capacity to develop these built in TTO , Guy and Sur | 50% | Satisfactory (S)
| Outcome 2.1: Strengthened stakeholder engagement in national decision- making for EAF fisheries management | Indicator 4: Number multi- stakeholder/ multisectoral EAF management NICs | T&T – 0 Suriname – only seabob Working Group (WG) Guyana – only seabob WG | 1 - Suriname – National Intersectoral Committee (NIC ) (Shrimp and Groundfish WG). | 3 - NICs in each country are fully operational. | Review of NICs completed. GUY- Seabob WG operational, Fishery Advisory Committee (FAC) being established. SUR - Seabob working group functional and re-activation of National shrimp and groundfish working group in progress. | 30% | Satisfactory (S)
|  | Indicator 5: Number of FFOs in target communities involved in co-management pilot projects | 0 (as no FFOs involved in project) and target communities to be fully defined at inception. | Minimum 1 per country | Minimum 2 per country | Sur - Galibi engaged and discussions on branding of indigenous smoked fish for sale. GUY: Training to be provided to women and other stakeholders in collaboration with FISH4ACP. TTO - A co-opertaive and business hub is being developed for Future Fishers on the NE coast of Trinidad. It is expected that training and sales of fish, gear and other business ideas will generate from this initiative. | 20% | Satisfactory (S)
| Outcome 2.2: Improved EAF management planning and implementation for shared resource management at national and sub- regional levels | Indicator 6: Updated Fisheries Management Plans for target fisheries. | 2 seabob managements plans updated in Guyana and Suriname and one national fisheries management plan updated in Suriname. | One national fisheries management plan updated for Guyana and one fisheries management plan developed for Trinidad and Tobago (TTO). | Updated fisheries management plans for Guyana and Suriname and endorsed and operational fisheries management plan for TTO. | SUR: Review on implementation of national FMP is ongoing. GUY- Review of Legal framework completed TTO- has identified staffing shortages that results in delays. Assessments of the fisheries management frameworks have been completed for Guyana and Suriname with support from REBYC III. Work is expected to continue with consultants to finalize National FMPs in the target countries. Capacity for monitoring of FMPs enhanced through training, institutional strengthening and tools for enhanced monitoring | 20% | Satisfactory (S)
|  | Indicator 7: Number of harmonized management technical measures for shared resources (e.g. minimum sizes) developed and adopted nationally | No harmonized management measures have been adopted. | 1 | 2 | WECAFC SGWG has not convened for regional discussions. Recommendation will be made at the 20th WECAFC Meeting in July 2025 to revitalize this working group. The Project has been collaborating with CRFM to undertake national stock assessments with management some harmonized recommendations for seabob and for some groundfish species. | 15% | Moderately Satisfactory (MS)
|  | Indicator 8: Number of harmonised sub-regional SG fisheries management recommendations developed as part of updating of sub-regional SG management plan | No harmonized management recommendations have been developed. | Identification of main stocks for stock assessment and development of harmonized management measures. | Minimum of 3 harmonized subregional management recommendations developed. | WECAFC Shrimp and Groundfish Working Group has not met in some time. Difficulty engaging this WG. Recommendation to re-energize this WG will be made to the WECAFC Commission for discussion at their July 2025 meeting as part of a paper on Bycatch and By Products. The Project has been collaborating with CRFM to undertake national stock assessments with management recommendations for seabob and for some groundfish species.The EAF4SG project collaborated with the CRFM to support the establishment of a Technical Committee to review the stock assessment methodology used for Suriname’s seabob stock assessment. Suriname was flagged by the Marine Stewardship Council as needing an independent assessment to continue their certification status. The Committee presented their findings to stakeholders on April 4th 2025 where additional recommendations were made to manage the seabob fishery at a CRFM Continental Shelf Fisheries Working Group meeting Technical committee for the assessment of seabob shrimp successfully completed its work which was also presented to the MSC assessment team during a fisheries surveillance audit in May 2025. Guyana and Suriname both had their MCS certification passed and re-instated respectively As part of a FISH4ACP research project on the reasons for declining seabob stocks, EAF4SG will support a consultant in Suriname to support inclusion of Suriname’s data in this review study and provide training and logistical support as needed | 20% | Moderately Satisfactory (MS)
| Outcome 2.3: Strengthened legal and regulatory frameworks for EAF-focused fisheries management | Indicator 9: Number of target fisheries with updated national regulatory frameworks supporting EAF-focused shrimp and groundfish fisheries management | There are incomplete national regulatory EAF frameworks for the target fisheries. | Recommendations for improving regulatory EAF frameworks for at least 2 target fisheries drafted and shared with stakeholders. | 5 target fisheries with recommendations incorporated into revised regulatory frameworks supporting EAF- focused shrimp and groundfish fisheries management | Regional EAF IMT training was provided to 20 participants from Guyana, Suriname, Barbados and Trinidad and Tobago GUY - Draft Review of the Legal Framework prepared by the EAF Consultant and under review by the Govt of Guyana. SUR: Review of legal and policy framework in progress. Further recommendations are expected from report by EU DG-MARE delegation next reporting period. | 20% | Satisfactory (S)
| Outcome 3.1: New gender-sensitive businesses opportunities to promote EAF management developed and available in target SSF communities in target NBSLME fisheries | Indicator 10: Number of new fisheries products piloted in target SSF communities in target fisheries (including opportunities for women, youth and minority groups). | 0 | 3 | 6 | TTO contract awarded and research being conducted on value chain of the Gillnet Fishery. Training provided by CFTDI to 80 students on new product development as part of a Ministry of Youth initiative. SUR: ToRs for local consultant to provide capacity building training and support to pilot projects of Galibi FFO was prepared. GUY- Preliminary discussions held with University of Guyana to execute this Component in Guyana. | 15% | Moderately Satisfactory (MS)
|  | Indicator 11: Number of male and female project beneficiaries with improved skills and knowledge on new businesses opportunities to promote EAF management working in the harvesting and post- harvest sectors | 0 | 60 (minimum 33% women) | 200 (minimum 33% women) | TTO contract awarded and research being conducted on value chain of the Gillnet Fishery. Establishment of a Co-operative on the NE Coast being facilitated to promote business opportunities. SUR: ToRs for local consultant to conduct a value chain assessment, provide capacity building training and support pilot branding of smoked Galibi fish was prepared. GUY- Preliminary discussions held with University of Guyana to execute this Component. Activities expected to accelerate in 2026 | 15% | Moderately Satisfactory (MS)
| Outcome 3.2: Policy and investment environment supportive of new business opportunities that encourage EAF management in SSF | Indicator 12: Number of new or improved gender- sensitive policies, measures and/or financial instruments (investments, grants, loans) established enabling the transition to EAF - compatible fisheries practices. | 0 | 1 | 3 | TTO: Consultant hired and work is in progress SUR: ToRs for local consultant to provide capacity building training and support to pilot projects of Galibi FFO was prepared. Preliminary discussions held with University of Guyana to execute this Component in Guyana. Some mechanisms currently exisiting can be built upon to meet targets. Activities expected to accelerate in 2026 | 15% | Moderately Satisfactory (MS)
|  | Indicator 13: Number of fisher folk organisations accessing new or improved financial instruments (investments, grants, loans) in support of sustainable fishing practices and value chain improvements. | 0 | 0 | 3 | TTO contract awarded and research being conducted. SUR: ToRs for local consultant to provide capacity building training and support to pilot projects of Galibi FFO was prepared. GUY-Preliminary discussions held with University of Guyana to execute this Component. Some programs exisit in country that can be built upon to meet targets. | 15% | Moderately Satisfactory (MS)
| Outcome 4.1: Knowledge of processes, measures, options and incentives for effective EAF management to improve sustainability of fisheries increased among key stakeholder groups | Indicator 14: Percentage increase in knowledge on EAF principles and practices among national fisheries staff compared with baseline levels at start of project implementation according to project surveys. | Baseline measured through surveys at inception. | 20% | 50% | Survey instrument developed and forwarded to the countries to measure baseline.Consultant to conduct one week training on extension and communicating EAF messages etc each, in Guyana, Trinidad and Tobago and Suriname identified and workshop being planned for July and August 2025. | 40% | Satisfactory (S)
|  | Indicator 15: Level of engagement in IW:LEARN activities through participation and delivery of key products (GEF Indicator 7.451). | No engagement in IW:LEARN. | Level 2 engagement (website in line with IW:LEARN guidance active). | Level 3 engagement (participation of project staff in training/twinning events and production of at least one experience note and one results note. | PMU staff registered with IW:LEARN Virtual Campus. Two PMU staff participated in the IW10 Conference in Uruguay from 21-26 September 2024. The PMU participated in the FAO led Thematic Session D on Sustainable Fisheries and Aquaculture. A new game “Fishing for Words” was tested and used as an interactive learning tool to introduce the project. The TPC participated in a question and answer panel discussion on the Projects. PMU engaged African Waters Project in follow-up dialogue providing technical support and materials to support execution of some of their project activities. TCP participated in IWLEARN LME24 in Athens Greece. | 50% | Highly Satisfactory (HS)
| Outcome 4.2: Effective gender- responsive project implementation based on adaptive management | Indicator 16: Recommendations from operational M&E system (including PSC and PIR recommendations) fed back into project implementation. | No project M&E system operational. | Project M&E system established and operational and any recommendations for adapting project implementation identified (including PSC and PIR recommendations) and adopted. | Project M&E system operational and any recommendations for adapting project implementation identified (including PSC and PIR recommendations) and adopted. | 2nd PSC completed on January 24th 2025. All Reporting Requirements met within stipulated deadlines. 1st LTO visit completed in April 2025. The LTO participated in a Stock Assessment Workshop and met with stakeholders including the indigenous Galibi Tribe in Suriname. He held meetings with PMU Staff, C3 Consultants and UWI executives in Trinidad and Tobago to address any bottlenecks or issues with project implementation. 1 Independent Project Spot Check completed and queries addressed. | 50% | Satisfactory (S)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
26.56% | 52.78% | 55.02%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
|  | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer | GEF Operational Focal Point | GEF Technical Officer (GTO)
| FY2025 Development Objective rating | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) |  | Moderately Satisfactory (MS)
| Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | A reasonable amount of work has been completed since the last PIR in June 2024. Initial challenges were encountered where project activties were delayed pending resolution of a difference in UWI's interpretation of spent vs committed funds as oulined in the OPA. This resulted in delays in spending. Large contract amounts were held as "committed funds" and were therefore unavialable for project activities resulting in delays in reaching a 75% target spend treshold. This significantly affected the PMU's ability to use exisiting funds and request additional funds to execute project activities. This matter was resolved in April 2025, subsequent to a meeting of the Project's LTOs and UWI's top financial team to address the matter as part of the LTO Supervisory Visit. Collaboration with regional partners such as CRFM and Fish4ACP has resulted in enhanced delivery of outputs. There have been challenges engaging with WECAFC SGWG which has not been convened since project inception resulting in significant delays in delivery of these subregional output targets. This significantly impacts outcome progress direcly linked to WECAFC engagement. Most national activities are delayed or behind schedule. International Consultants have now been hired and are working with project staff to accelerate execution of in country activities. The implementation EAF4SG activities has benefitted from the staff hired under REBYC III who support the Fisheries Departments across both projects. However, as the budget line for Hiring personel under EAF4SG Component 1 is limited and there is no assigned staff or ability to hire national consultants to support component 2, execution of these activties are delayed due to heavy work loads of national focal points and competing priorities of the staff of the Fisheries Departments There are some challenges in implementing Component 3 as there is a limited pool of consultants to undertake these works. Measures are being put in place to address this via developing partnerships with local Universities to undertake the work There is no change in the rating of Moderately Satisfactory in 2024 as compared to the 2025 rating. | Project made a good progress in strengthening governance and fisheries management (Comp. 2). However, financial impediments and delays in consultant hiring continue to be challenges that are slowing down progress in certain areas. Delays persist in the implementation of component 2, specifically in the outcome: improved planning and implementation of EAF management for shared resource management at the national and subregional levels. In component 3, the following outcomes have been delayed: new gender-sensitive business opportunities to promote AEF management developed and available in selected artisanal fishing communities in selected NBSLME fisheries, and a Policy and investment environment supportive of new business opportunities that encourage EAF management in SSF. Mitigation measures have been adopted, such as the participation and collaboration of the WECAFC Working Group on Shrimp and Groundfish in the Subregional Plan (comp. 2) and an agreement with the local university in the case of Guyana (comp. 3). | The project has made reasonable progress towards outcomes. Earlier delays due to funding interpretation issues slowed implementation but were resolved in April 2025, enabling renewed progress. Component 1 has advanced well and benefitted from synergies with REBYC III, while Components 2 and 3 have faced delays due to consultant mobilization challenges and limited expertise. Regional collaboration with CRFM and Fish4ACP has been positive, though progress remains constrained by the inactivity of the WECAFC SGWG. Despite uneven progress, proactive measures are being taken to address challenges and sustain outcome achievement. |  | The project maintains a Moderately Satisfactory (MS) rating, with progress recorded despite early financial constraints. Resolution of the funds disbursement issue in April 2025 has allowed activities to move forward more effectively, and collaboration with partners such as CRFM and Fish4ACP has enhanced delivery. Positive advances include regional EAF training for 20 practitioners, upgrades to fisheries information systems in Guyana, and seabob stock assessments completed in Guyana and Suriname. International consultants have been engaged, and synergies with REBYC III are providing added technical support to fisheries departments. However, challenges remain. National activities are still behind schedule, and the WECAFC Shrimp and Groundfish Working Group has not convened, delaying subregional outputs critical for harmonized management. Component 2 suffers from limited staffing capacity, while Component 3 faces shortages in available consultants, though partnerships with universities are being explored. Co-financing is particularly low at 13%, with most partners having yet to contribute. Corrective measures are essential in FY2026 to improve this rate.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
Outcome 2.2 |  | Output 2.2.1: National and sub- regional Fisheries Management Plans updated as part of EAF management cycle Engage WECAFC on Sub Regional Plans. Review Plans National Workshops to be held |  | PMU, NTCs, national fisheries agency partners |  | 2026-03-01
Outcome 3.1 : New gender-sensitive businesses opportunities to promote EAF management developed and available in target SSF communities in target NBSLME fisherie |  | Engage with local University to undertake C3 activities |  | PMU, NTCs, national fisheries agency partners |  | 2026-03-01
Outcome 3.2: Policy and investment environment supportive of new business opportunities that encourage EAF management in SSF |  | Engage with local University to undertake C3 activities |  | PMU, NTCs, national fisheries agency partners |  | 2026-03-01
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.1: Improved national and sub-regional data and data management systems supporting EAF fisheries management
Output 1.1.1: Analysis of existing fisheries management information systems (FMIS) and data in the three target countries and sub-regional level undertaken and recommendations for improvement developed. | Improved fisheries data collection and fisheries information management systems in the three countries. | Review of all aspects of fisheries data collection and information management in the three countries and at the sub-regional level completed for Guyana, Suriname and TTO. Output 1.1.1 EAF4SG Assessment report SUR_GUY.pdf, Output 1.1.1 2024-05-Assessment report Trinidad and Tobago.pdf |  |  | 100% - Completed
| Development of recommendations for improvement to fisheries data collection and information management systems. | Recommendations have been included as part of the assessment of the data and data management needs in all countries. |  |  | 100% -Completed
| Development of a sustainability plan for the fisheries management information system in each country. | Sustainability Plans were developed as part of the assessment in each country |  |  | 100% -Completed
Output 1.1.2: Technical capacity for the application of EAF-based fisheries management information systems among key fisheries stakeholders built, including data collection, fisheries statistics, analyses of fisheries data, and interpretation. | Number of capacity building for the application of EAF-based fisheries management information systems. | A Two-week sub-regional workshop was held 11-22 Nov 2024, on stratified sampling and data management in collaboration with GUY/FAO TCP and Fish 4ACP in Guyana. 2024-11-Guyana_workshop-Joint BTOR_signedLA.pdf. Output 1.1.2 EAF Capacity Building Training in Stratified Sampling and Data Review.pptx Consultants hired to upgrade Calipseo continue to meet with project partners and build capacity with fisheries and IT staff on the application of processes in Calipseo. An Inception workshop was held with the team with Suriname and Trinidad and Tobago to address concerns. A consultant has been hired by the Project in Suriname to support data clean up and preparation. A consultant has been hired for Trinidad and Tobago to support data clean up and preparation. |  |  | 30% - On track
| Number of technical fisheries personnel trained and provision of necessary software and tools | Team of international consultants has started to work to upgrade Calipseo in Suriname to streamline the ARTFISH methodology for artisanal fisheries catch estimates into the Suriname data collection methodology. Work has also started to upgrade Calipseo in TTO. Guyana Calipseo was upgraded under a FAO TCP.TTO. TTO completed the catch and effort data clean-up for 2018 and completed the standardisation of vessel names in the registration component of the catch and effort database for 2019 to 2021. A consulptant has been identified to support data needs and continue clean up of data already in progress. Guyana developed materials to facilitate training of industrial processors in the collection of seabob biological data. They sourced internal storage to facilitate proper functioning of Calipseo. Calipseo was updated as part of Guyana TCP. SUR -Three new fisheries data collectors were recruited by the fisheries department, who received training in May 2025. Check-in moments were held with all data collectors in April/May to ensure that fisheries data collection continues to be up to standard. Local consultant has started to work in support of FISMIS implementation and improvements to data collection and analysis.
30% - On track
Output 1.1.3: National and sub-regional stock assessments of selected priority species developed with relevant management recommendations | Number of Stock assessment workshops at national and subregional levels | A Sub-regional Workshop on Groundfish Stock Assessment and Stakeholder Consultation was held from March 31st - April 4th 2025 in collaboration with CRFM and FISH4ACP. The workshop objectives were: (1) to increase understanding of the theory behind stock assessment; (2) to learn how to use stock assessment tools; and (3) to perform preliminary assessments on key shrimp and groundfish species for each country. Seventeen participants from four partner organisations and the three countries attended the stock assessment workshop. 5 Preliminary Stock Assessments on various shrimp and groundfish species were completed and recommendations provided to improve data collection and robustness of future assessments. CRFM Fishery Report 2025-1 - Report of CSWG intersessional activities Apr 2024-Mar 2025 and Stakeholder Consultation of 4 Apr 2025 (final v 01.05.25) (1).pdf Report of CSWG Meeting, 31 Mar-04 Apr 2025 (23.05.25).doc |  |  | 50%- On track
| Number of improved recommendations for specific target species/stocks based on stock assessments and stakeholder consultations. | Consultant Dr Paul Medley completed an updated stock assessment in April 2025 for Seabob in Suriname. Suriname_Seabob_JABBA_HCR March 2025.docx The updated seabob stock assessment was presented and discussed during a surveillance audit of the Suriname seabob fishery in May 2025. A stakeholder Consultation was held as part of a joint EAF4SG/CRFM CSWG Stock assessment workshop in April 2025 with recommendatons reflected in the CRFM CSWG Report below. CRFM Fishery Report 2025-1 - Report of CSWG intersessional activities Apr 2024-Mar 2025 and Stakeholder Consultation of 4 Apr 2025 (final v 01.05.25) (1).pdf In June 2025 Suriname was advised that their Seabob certificate suspension was lifted, and the certificate can be reinstated. In June 2025 Guyana was also advised that they had passed their recent MSC audit. A Terms of Reference for a study on the decline of the seabob fishery in Guyana was developed by FISH4ACP and reviewed by EAF4SG Experts. The Project will provide assistance where possible, including the expansion of the study to Suriname. EAF4SG will support the inclusion of Suriname's data in this research study. A consultant has been identified to support this activity. |  |  | 50% - On track
Output 1.1.4: Fisheries-related socio-economic data for selected fisheries within national EAF- based fisheries management information systems, including value chain data, collected and analyzed. | Number of Reports on Identification of socio-economic data required for EAF management of selected fisheries. | A Draft report identifyng the socio economic data needs to support EAF Management in Guyana, Trinidad and Tobago and Suriname was completed. Countries are reviewing the Report EAF4SG_report_1.1.4.docx |  |  | 90% - Delayed as per Project doc. Currently Finalizing Report. Delay was as a result of countries engagement and training to better understand Socmon. Decision taken in Dec 2024 to undertake this Review of scocio-economic indicators in Calipseo. Finalization of Report expected after country review
| Number of improved frameworks and methodologies for collection and analysis of socio- economic data. | Suriname has started to incorporate the collection of socioeconomic data into the national data collection framework.Three new fisheries data collectors were hired by the Fisheries Department and trained in data collection, including socio-economic data. Trinidad and Tobago and Guyana to review and discuss their approach. |  |  | 30%- On track
Improved socio-economic data and its accommodation in the national Fisheries Management Information System
| Number of Pilot activities on the collection and integration of socio- economic data with other types of fisheries data to produce EAF management recommendations. | Seven subregional meetings/training sessions were held with CERMES Barbados and executing partners to discuss the SOCMON approach to monitoring socioeconomic variables from Jan - Dec 2024. Executing partners agreed that focus would be on the identification of socio-economic indicators that could be incorporated into FMIS and SOCMON would be used as needed. |  |  | 50% - On track. Countries felt that there was need to improve the collection of soci-economic data already in Calipseo. Use of Socmon and collection of adhoc socio-economic data will be done as needed.
Outcome2.1: Strengthened stakeholder engagement in national decision- making for EAF fisheries management
Output 2.1.1: National inter-sectoral coordination mechanisms for EAF in three participating countries supported and fully operational | Improved review of existing NICs for improvements to enable them to become fully operational and more effective in EAF management | Draft Reprorts on the Review of NICs for Trinidad and Tobago, Suriname and Guyana completed and under review. Draft Guyana report- Review of NIC.docx Draft Suriname report Review of NIC.docx Draft Trinidad and Tobago Review of NIC .docx |  |  | 90% - Initially delayed due to challenges in hiring the consultant. Consultant under contract, Finalizing reports for completion.
| Number of meetings supported for each established NICs, ensuring wide participation of stakeholder groups. | SUR: Seabob Working Group (SWG) is active. They host monthly meetings, including participation of all relevant stakeholders (including FFO’s). The SWG met with MSC assessment team during a surveillance audit of the seabob fishery in May 2025. Re-activation of national shrimp and groundfish WG (SGWG) in process. Nomination letters for stakeholders to select representatives for Fishery Advisory Committee (FAC) and SGWG were prepared and sent by the FD. A subcontract was signed to fund these activities in Suriname. Guyana: Through FISH4ACP artisanal fishers are now a part of the SWG. The Seabob Working Group (SWG) met monthly and the general SWG met in September and December 2024. The working group hosted the Marine Stewardship Council Audit Team from 16 - 20 December 2024. Subcontract to support on the ground activities was signed. The FAC will be established after elections in 2025 TTO - Reviewing options for the establishment of their NIC. They have provided documents for review and met with the Consultant. |  |  | 30% - On track. Elections in both countries in 2025 may impact progress towards the establishment of the SGWG and FAC in Suriname and the FAC in Guyana
| Improved communication and knowledge- sharing from outgoing to new members and among the different multi-sectoral mechanisms. | Suriname SWG has a website (www.seabob.sr) where the minutes of the meetings (among other documents) are shared. Guyana - The SWG had two meetings during the reporting period. The SWG through the Guyana Association of Trawler Owners and Seafood Processors has a website (https://guyanaseabobfishery.com/) where the minutes of the meetings (among other documents) are shared. |  |  | 30%- On track
Output 2.1.2: Capacity of SSF stakeholders from target communities/fisheries to participate in co-management of EAF fisheries assessed and developed | Capacity needs assessment of FFOs in target communities in the three project countries and national fisheries-related agencies in relation to co- management. | Consultant hired. Capacity needs assesment to be completed after Assessment of NICs above |  |  | 0% Delayed. Consultant hired Jan 2025.
| Number of training of trainers programmes, to enhance capacities to engage in participatory forms of EAF co- management. | Planned for future execution. No activities to date. |  |  | 0% - Delayed. Consultant hired Jan 2025. Expected delivery 2026
| Number of pilot projects on EAF co- management by FFOs and fishing communities. | Suriname: Engagement with Galibi FFO has started. An engagement strategy was prepared following identification that a Free and Prior Consent process (FPIC) was needed as the Galibi is an idigenous group and was not included in the original Project Document. Meetings with the community and FFO were held in November 2024 and March 2025. ToRs for a consultancy to brand and market smoked Galibi fish was developed. A consultant is being sourced. GUY - no activities to date. Awaiting results of C3 activities TTO- EAF4SG is supporting the establishment of a multipurpose co-operative and business hub on the NE Coast of Trinidad in collaboration with Future Fishers. It si expected that this would generate training and strebgthening along the gillnet value chain. Value chain assessment in progress under C3. |  |  | 20% - Delayed due to late hiring of consultant. Some activities in TTO and Sur progressing
Outcome 2.2: Improved EAF management planning and implementation for shared resource management at national and sub- regional levels
Output 2.2.1: National and sub-regional Fisheries Management Plans updated as part of EAF management cycle. | Improved Sub-regional Strategy and FMP for the shrimp and groundfish fisheries of the North Brazil- Guianas Shelf. | Consultant hired. Activities delayed. WECAFC SGWG has not met since project inception. Interventions continue with FAO to engage this group. |  |  | 15%. Likely to be delayed. WECAFC SGWG established but needs to be convened. A recommendation will be made at WECAFC 20 to revitailize this SGWG.
| Number of national workshops for the finalization of the Trinidad and Tobago draft plan for the shrimp trawl fishery and the draft integrated fisheries management plan. | TTO: A meeting was held on 13 May, 2025 with International Consultants for Component II EAF4SG Dr. Jeremy Mendoza and Dr. Robert Pomeroy and with REBYC - III CLME+ LTA2 Dr. Eric Gilman to discuss the development of Integrated Fisheries Management Plan for Trinidad and Tobago with initial focus on the shrimp and groundfish fisheries, artisanal gillnet and non-artisanal longline fisheries. Consultant Dr Jeremy Mendoza hired and will support TTO in the finalization of their Shrimp Management Plan and Integrated Fisheries Management Plan. Activities delayed because of staff shortages at the Fisheries Department |  |  | 0% -Delayed. They have identified staff shortages
| Number of national workshops for the review and updating of Guyana FMP Conducting national workshops for the review and updating of Suriname FMP.Improved Capacity for the monitoring of the implementation and effectiveness of national FMPs for shrimp and groundfish fisheries. | SUR: Review of the national FMP is in progress. Workshop to be held later in 2025 Suriname fisheries department team met with stock assessment experts from French Guiana (Ifremer) in April 2025 to discuss joint FMPs. Interest for collaboration was expressed. Guyana: Update of seabob management plan completed. Guyana Seabob Management Plan 2022-2027 (Ministry of Agriculture, 2022b) A number of assessments of the countries fisheries management frameworks have been completed from a bycatch perspective which has relevance for EAF. These were shared with the EAF4SG EAF Consultant. Assessment of the Guyana Fisheries Management Framework.docx Suriname_DRAFT_fisheries_mgmt_framework_assessment_activity_2.1.1a.docx Work is expected to continue with consultants to finalize National FMPs. |  |  | 20% - Likely to be delayed. Suriname FMP likely to be advanced and completed in in 2025. Guyana's plan is current and will need updating in 2027.
Review of Suriname's national FMP is ongoing. Guyana- Update of seabob management plan completed.
Output 2.2.2: Capacity for monitoring of implementation of Fisheries Management Plans for national Shrimp and Groundfish fisheries built. | Strengthened national technical capacity to monitor the implementation and effectiveness of the shrimp and groundfish FMPs, using the EAF Implementation Monitoring Tool. | Regional EAF IMT training was provided to 20 participants from Guyana, Suriname, Barbados and Trinidad and Tobago on February 25th 2025. Concept Note EAF IMT REfresher Training and Scoring.docx Suriname and Guyana have identified their fisheries to be assessed. Suriname has completed the scoring for one project target fishery. https://docs.google.com/document/d/1hBmGkDXi4nk0QEItlUqV7h88ojeKMmtV/edit?usp=drive_link&ouid=116999412777529593059&rtpof=true&sd=true Guyana completed their baseline EMT Scoring. EAF IMT Scoring Baseline 06.25 Guyana.docx TTO is yet to provide their IMT score. They have highlighted staff challenges. A meeting was held on 13 May, 2025 with International Consultants for Component II EAF4SG Dr. Jeremy Mendoza and Dr. Robert Pomeroy and with REBYC - III CLME+ LTA2 Dr. Eric Gilman to discuss the development of Integrated Fisheries Management Plan for Trinidad and Tobago with initial focus on the shrimp and groundfish fisheries, artisanal gillnet and non-artisanal longline fisheries. Discussions also centred on strategies to support TTO in the completion of their EAF IMT scores. |  |  | 40%. On track. Needs assessment determined that all target countries had limited or no knowledge of the FAO EAF IMT Tool. Training complete. TTO initial scores outstanding.
| Number of other monitoring frameworks for the FMPs and strengthening institutional capacity for utilizing these frameworks. | A RFP for a Pilot EM for the Gillnet fishery was advertised under REBYC III. This is being reviewed. Once implemented, real time camera systems for monitoring FMPs will be operational. Suriname: Stakeholder meetings were held (5 in total) to discuss inter-agency collaboration and developing a national plan of action for Illegal Unreported and Unregulated (IUU) fisheries, which closely links with implementation and enforcement of FMP measures. NPOA IUU was finalized and endorsed by stakeholders. IUU-NPOA Suriname 2025.pdf TTO has an NPO IUU as well as Guyana. |  |  | 40%-On track
| Provision of appropriate institutional support for EAF for strengthening inter-agency collaboration and capacity for monitoring the implementation of national FMPs. | A pilot Electronic Monitoring system for the Gillnet Fishery of Guyana, Suriname and Trinidad and Tobago has been advertised under REBYCIII and is under review. This will support monitoring in the Shrimp and Groundfish fisheries in the target countries. Training was provided to the EAF4SG country teams on EM systems. A visit of the EU DG-MARE delegation to Suriname included a review of Suriname’s capacity to enforce fisheries policy and regulations with all key authorities involved. A report containing recommendations is expected next reporting period. Total Energies Suriname approved a grant to the Fisheries Department for the value of 125K USD to equip coastal vessels with VMS. Guyana: One hundred vessel tracking devices were purchased in November 2023 by the Fisheries Department for the artisanal fishery in Regions 1 - 6, with another 50 being procured has resulted in upgraded monitoring equipment (more screens). |  |  | 30% - On track
Output 2.2.3: Management measures and plans for shared fisheries resources at sub-regional level supported (sub-regional Strategy and Management Plan for Shrimp and Groundfish), developed in participatory manner. | Organisation of a sub-regional technical advisory working group for key shared stocks and for supporting the implementation of relevant elements of the sub-regional strategy and FMP for shrimp and groundfish on the NBSLME. | The EAF4SG project collaborated with the CRFM to support the establishment of a Technical Committee to review the stock assessment methodology used for Suriname’s seabob stock assessment. Dr Jason Cope from NOAA was engaged and facilitated the technical review. Suriname was flagged by the Marine Stewardship Council as needing an independent assessment to continue their certification status. The Committee presented their findings to stakeholders on April 4th 2025 where additional recommendations were made to manage the seabob fishery at a CRFM Continental Shelf Fisheries Working Group meeting. A technical committee for the assessment of seabob shrimp successfully completed its work, the results of which was presented to the MSC assessment team during a fisheries surveillance audit in May 2025. In June 2025, Guyana was advised that they had passed their recent MSC audit. Suriname also received preliminary advice that Seabob certificate suspension was lifted, and the certificate could be reinstated. |  |  | 100% - Completed for Seabob in collaboration with CRFM CSWG. WECAFC SGWG to be engaged for groundfish species. Limited WECAFC engagement is affecting outcome progress ratings
| Development and conduct of a pilot activity for implementation of elements of the sub-regional FMP using a particular species or species group that is relevant for the three countries. | As part of a FISH4ACP a research project on the reasons for declining seabob stocks was developed. EAF4SG experts reviewed the TORs and will support a consultant in Suriname to support inclusion of Suriname’s data in this review study and provide training and logistical support as needed. EAF4SG continues to support FISH4ACP in the roll out of this research project |  |  | 15% Delayed. WECAFC SGWG to be engaged for groundfish FMPs.
| Supporting countries’ engagement in mechanisms such as the WECAFC/CRFM/ IFREMER Shrimp and Groundfish Working Group and the CRFM Continental Shelf Working Group. | Work continues in collaboration with the CRFM Shrimp and Groundfish Working Group with a Stock assesment workshop on groundfish species completed from March 31st - April 4th 2025. The PMU participated in the WECAFC's Thirteenth session of the Scientific Advisory Group (SAG), 23-24 April 2025. The work under the EAF4SG was highlighted and a request for collaboration with the the WECAFC SGW Working Group was made. IFREMER expressed willingness to partner on groundfish assessments going forward. |  |  | 30% - On track. Limited WECAFC engagement is affecting outcome progress ratings
Outcome 2.3: Strengthened legal and regulatory frameworks for EAF-focused fisheries management
Output 2.3.1: Current national legal and regulatory frameworks for EAF reviewed, particularly in relation to SSF, including for co-management. | Improved current national legal and regulatory frameworks for fisheries management in the three countries to identify the gaps and deficiencies for EAF and co-management. | Review of national legal and regulatory frameworks is ongoing. The International Consultant Component 2 (ICC2) met with all three target countries and received documentation on the current legal framework. He drafted a review of the legal framework for Guyana. The Fisheries Department reviewed the document and provided feedback. Draft EAF Legal Checklist_Guyana_13_05_25.xlsx Draft Legal Fisheries Framework_Guyana_13_05_2025.docx Consultant met with Suriname and TTO. Plan was identified on how to treat with TTO's Bill being in draft. |  |  | 20% - Delayed but Consultant hired and work is expected to advance
| Improved national frameworks aligned with the international SSF Guidelines and other related regional and international guidelines and policies. | Included in the Report for Guyana. Small scale fisheries (SSF) considerations have been incorporated in the first draft of the current legal fisheries framework of Guyana for EAF. So far, relevant international treaties and agreements to which guyana is a party have been identified, as well as an examination of the SSF protocol under the Caribbean Community Common Fisheries Policy (CCCFP). |  |  | 20%. Delayed but consultant hired and work is expected to advance.
Output 2.3.2: Recommendations for improving legal and regulatory frameworks for EAF, e.g. technical measures, CMMs and HCRs, and co-management in particular in relation to SSF, identified, advocated and adopted | Identification of opportunities and development of practical recommendations to strengthen the legal and regulatory frameworks for EAF. | Included in the Report prepared for Guyana. |  |  | 20%. Delayed but consultant hired and work is expected to advance.
| Supporting amendment and finalization of the frameworks and acceleration of the political processes for their political endorsement. | No activities to date. |  |  | 0% - Too early in project cycle. Elections scheduled for 2025 in Guyana and Suriname. New administration in TTO
| Promotion and advocacy efforts targeting fisheries-related state agencies, NICs, and SSF communities for adoption of the improved frameworks. | No activities to date. |  |  | 0% - Too early in project cycle. Elections scheduled for 2025 in Guyana and Suriname. New administration in TTO.
Outcome 3.1: New gender-sensitive businesses opportunities to promote EAF management developed and available in target SSF communities in target NBSLME fisheries
Output 3.1.1: Gender- sensitive value chain assessments (VCAs) for SSF value chains performed for target species and communities, and business opportunities identified and prioritized. Output | Number of Value Chain mapping and analysis to identify main socio-economic environmental and institutional challenges to value chain development. | International Value Chain Consultant hired. SUR - TORs completed for a value chain study and branding of smoked fish in Galibi. Discussions held with UOG to administer C3 in Guyana. TTO Contract awarded to UWI, Trinidad. Secondary data research – Now 90% complete. Data collection plan development – 100% complete (awaiting a list of longline and gillnet vessel owners) Data collection instruments – 100 % completed (Fisher survey questionnaires, actor interviews, focus group discussions, and key informant interviews). Consumer Value Chain Mapping Questionnaire developed – 100% completed. This questionnaire is to determine consumer purchasing behaviour of gillnet bycatch products and potential value-adding opportunities. Training of 6 enumerators for the Consumer Value Chain Mapping Survey – Completed 29th May 2025. Value chain actor interviews (economic, social, and functional) for wholesalers, retailers, and processors will now be completed in June/July 2025 due to the proposed start of the Consumer Value Chain Survey in June. Admininstration. All 2025 contracts are being finalized. . |  |  | 20% - Delayed. TTO progressing. Difficulty identifying consultants
| Development of recommendations for value chain upgrading & Identification of priority training needs | TTO - In progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Delayed. Difficulty identifying consultants
| Development of participatory capacity building plan for activation of value chain recommendations through output 3.1.2. | TTO - In progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Delayed. Difficulty identifying consultants
3.1.2: Capacity for target fisher folk communities to take advantage of new EAF management related business opportunities identified and built. Prioritized | Number of capacity building plans developed with target communities and enterprises. | TTO - In progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Likely to be Delayed. Difficulty identifying consultants
| Number of business plans developed and resources mobilization strategy with selected enterprises Technical support and mentoring to develop enterprises and seek further capital for business plan activation. | TTO In progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Likely to be Delayed. Difficulty identifying consultants
Outcome 3.2: Policy and investment environment supportive of new business opportunities that encourage EAF management in SSF
Output 3.2.1: Policies and financial frameworks (based on global good practices) that can support investments in SSF reviewed, and recommendations identified and promoted. Output | Improved knowledge of global regional and national financial frameworks (including informal) applicable to SSF to identify global best practice for supporting investments in SSF and recommendations for improving local enabling environment for the funding of SSF. | TTO in progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Likely to be Delayed. Difficulty identifying consultants.
3.2.2: Access to financing by SSF for EAF venture opportunities increased. | Number of awareness raising material and improved information campaign targeted at existing and potential funders of SSF ventures and potential recipients of financing for SSF . | TTO in progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Likely to be Delayed. Difficulty identifying consultants
| Number of Business plans from outcome 3.1.2 presented to financial intuitions and other relevant potential funders. | TTO in progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Likely to be Delayed. Difficulty identifying consultants
| Pilot projects implemented with selected enterprises, and first phases of resource mobilization strategy under 3.1.2 to act as demonstrations for future replication. | No activities to date. Discussions held with UOG to administer C3 in Guyana. |  |  | 0% - Too early in project cycle
Output 3.2.3: Strategies and measures to encourage fishers and markets to adopt and promote EAF management in SSF identified, developed, and disseminated. | Study of local and international demand side factors including national consumer preferences and barriers to consumption of current and potential EAF SSF products included value added products developed under output 3.1.3 and development of recommendations to address these preferences. | TTO - In progress. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Delayed. Difficulty identifying consultants
| Identification prioritisation and implementation of appropriate Innovative tools/approaches for supplier and buyer matching in local markets. | TTO progressing. Discussions held with UOG to administer C3 in Guyana. |  |  | 15% - Delayed. Difficulty identifying consultants
Outcome 4.1: Knowledge of processes, measures, options and incentives for effective EAF management to improve sustainability of fisheries increased among key stakeholder groups.
Output 4.1.1: EAF Outreach Strategy and Plan to promote greater understanding of EAF management in target fisheries developed and implemented | Improved EAF Outreach Strategy and Plan for EAF focused on the target fisheries Outreach training programme for national fisheries agency staff on effective techniques and approaches for communicating EAF. | Outreach Strategy and Plan completed and circulated to PSC. Outreach Strategy and Plan presented to Fisheries Divisions. https://drive.google.com/file/d/1IeiV9_FJA47pcNlDbL2aONp9ODmOHw75/view?usp=drive_link. Survey Instrument developed and forwarded to the countries to measure baseline.Consultant to conduct one week training on extension and communicating EAF messages etc each, in Guyana, Trinidad and Tobago and Suriname identified and workshop being planned for July and August 2025. https://docs.google.com/document/d/1RWVwu_swtIG3LxRQ5T3FYNByaTKiOX8A/edit?usp=drive_link&ouid=116999412777529593059&rtpof=true&sd=true |  |  | 100% -Completed 40%- On track. Likely to be completed Sept 2025
| Production of EAF management outreach and awareness-raising materials. | Brochure and poster being devleoped on Electronic Monitoring Systems. Gender Fact Sheet and Poster drafted.Regional communications group established. |  |  | 10% - Delayed. A Regional Communications Group has been established to advance activities
| Development of a plan with identified funding for long-term support for fisheries outreach activities. | No activities to date |  |  | 0% - Expected Year 3
Output 4.1.2: Project successes, experiences and lessons learned identified and disseminated to key EAF4SG stakeholders | Improved Knowledge Management and Communications (KMC) in target countries. | KMC Plan included in Outreach Strategy and Plan |  |  | 100% - Completed
| Improved Project- generated knowledge and communication products developed and shared through available knowledge- sharing platforms | Website and facebook pages completed and live. Media Briefs uploaded to the Website and real time activities shared to the Project's Facebook Page |  |  | 60% - On track
| Project-specific ‘visual identity’ will be developed | Visual identity developed. project logo, fact sheet, promotional material produced. |  |  | 100% -Complete
| Improved Structured lesson-learning framework will be designed and applied to the project | No activities to date |  |  | 0% -Delayed. Structured lessons learning to be discussed at Regional Communication Forum
Output 4.1.3: Roadmap and material for scaling of successful project solutions for implementation of EAF management in NBSLME fisheries and beyond to wider CLME region and beyond developed and implemented by relevant stakeholders including 1% allocation to IW:LEARN activities | Develop ‘roadmap’ for scaling up project successes and experiences. | No activities to date |  |  | 0%. Expected start Year 3
| Engagement with IW:LEARN and the CLME+HUB activities. | PMU staff registered with IW:LEARN Virtual Campus. EoI submitted for the IW10 Conference. Two staff members participated in the IW10 Conference in Uruguay from 21-26 September 2024. The PMU participated in the FAO led Thematic Session D on Sustainable Fisheries and Aquaculture. A new game “Fishing for Words” was tested and used as an interactive learning tool to introduce the project at Session D - Sustainable Fisheries and Aquaculture. The TPC participated in a round robin question/answer session to introduce the Project. Mission Report IW 10 Conference Uruguay 23- 26th September 2024.doc TPC participated in LME24 in Athens Greece from May 12th - 16th , 2025 and presented on Project successes and lessons LME24 - Session 2 Presentation NL.pptx Mission Report Greece May 14- 16, 2025 LME 25.doc |  |  | 50% - Progress advanced
Outcome 4.2: Effective gender- responsive project implementation based on adaptive management
Output 4.2.1: A gender-responsive project Monitoring and Evaluation (M&E) system using data disaggregated by sex, age and ethnicity designed and operational, and in line with FAO and GEF requirements operational | Establishment of the Project Steering Committee (PSC) Inception workshop with review and endorsement of M&E Plan by the PSC | 2nd PSC completed on January 24th 2025. All Reporting Requirements met within stipulated deadlines. 1st LTO supervision mission was completed in April 2025 with a visit to Suriname and Trinidad and Tobago to meet stakeholders, UWI executives and PMU Staff. The objective was to observe on the ground project related activities and and address any bottlenecks or issues with project implementation. One Independent Spot Check was completed by FAO and queries addressed. |  |  | 50% -On track
| Regular monitoring of project indicators and reporting (according to the M&E Plan) | Project M&E system operational and any recommendations for adapting project implementation identified (including PSC and PIR recommendations) adopted. PIRs, PPR and Quarterly reports submitted as per agreed timelines. |  |  | 100% On track
Output 4.2.2: Terminal Evaluation carried out | Terminal Evaluation undertaken before the official closure of the project. | N/A |  |  | 0% - Expected activity start December 2027
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) | Moderately Satisfactory (MS) |  | Moderately Satisfactory (MS)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | A reasonable amount of work has been completed since the last PIR in June 2024. Initial challenges were encountered where project activties were delayed pending resolution of a difference in UWI's interpretation of spent vs committed funds as oulined in the OPA. This resulted in delays in spending. Large contract amounts were held as "committed funds" and were therefore unavialable for project activities resulting in delays in reaching a 75% target spend treshold. This significantly affected the PMU's ability to use exisiting funds and request additional funds to execute project activities. This matter was resolved in April 2025, subsequent to a meeting of the Project's LTOs and UWI's top financial team to address the matter as part of the LTO Supervisory Visit. Collaboration with regional partners such as CRFM and Fish4ACP has resulted in enhanced delivery of outputs. There have been challenges engaging with WECAFC SGWG which has not been convened since project inception resulting in significant delays in delivery of these subregional output targets. This significantly impacts outcome progress direcly linked to WECAFC engagement. Most national activities are delayed or behind schedule. International Consultants have now been hired and are working with project staff to accelerate execution of in country activities. The implementation EAF4SG activities has benefitted from the staff hired under REBYC III who support the Fisheries Departments across both projects. However, as the budget line for Hiring personel under EAF4SG Component 1 is limited and there is no assigned staff or ability to hire national consultants to support component 2, execution of these activties are delayed due to heavy work loads of national focal points and competing priorities of the staff of the Fisheries Departments There are some challenges in implementing Component 3 as there is a limited pool of consultants to undertake these works. Measures are being put in place to address this via developing partnerships with local Universities to undertake the work There is no change from the rating of Moderately Satisfactory in 2024 as compared to the 2025 rating. | Overall project progress is rated as Moderately Satisfactory. Good progress has been made under Component 1, particularly on information systems, trainings, and assessments. For Component 2, some outputs are lagging due to delays in hiring consultants by the PMU; nevertheless, the administrative issue behind these delays now seems to be resolved. Steps have been taken to advance subregional discussions in collaboration with CRFM and Fish4ACP (e.g., seabob assessments), which are expected to be further strengthened once the WECAFC SGWG resumes its work. Component 3 has also faced delays, partly due to the difficulty in sourcing consultants with expertise in fisheries value chains in the target countries, compounded by limited resources to bring in external expertise. The project is actively seeking solutions, including partnerships with universities. Additionally, progress has been affected by staff shortages in national Fisheries Departments and the challenges staff face in committing time to project activities. Synergies with REBYC III have helped address some of these limitations. | The project is designed to advance adoption of EAF through increasing skills and expertise in data gathering, monitoring and reporting; and influencing behavior change to improve the management of the Caribbean Large Marine Ecosystem. The majority of target addresses increased their skills in data gathering monitoring and reporting. In this regard, satisfactory progress has been made in training and formulation of EAF monitoring tools, upgrade of Fisheries Management Information Systems to include socioeconomic data; and conducting stock assessments. However, targets reflecting engagement with the stakeholders at national and regional level were largely moderately satisfactory. Attention will be focused on this over the coming year to support the adoption of best practices. The office of the Sub-Regional Coordinator for the Caribbean will use its role in WECAFC, as far as is reasonably possible, to support the uptake of project results in the region to support the strengthening of the regulatory and regional frameworks for EAF-focused fisheries management | Comments | The project has made steady progress since the last PIR, overcoming early financial management challenges that delayed disbursements. Positive advances include regional training and the development of EAF monitoring tools, upgrades to fisheries information systems to integrate socioeconomic data, and stock assessments in Guyana and Suriname. Collaboration with partners such as CRFM and Fish4ACP further strengthened delivery. However, engagement at the regional level remains limited, as the WECAFC Shrimp and Groundfish Working Group has not convened, delaying key subregional outputs. With international consultants now engaged, activities are accelerating. Overall performance is rated Moderately Satisfactory (MS).
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The EAF4SG project is given a Moderately Satisfactory rating. Activities commenced with the Project Inception Workshop (PIW) and 1st PSC which was held in Trinidad and Tobago from 24-25 January 2024. The Project Management Unit was formally established in January 2024 and effectively commenced project activities at that time. A 2nd Project Steering Committee Meeting was held on January 24th 2005. Major achievements since the last PIR Report include the following: 1. EAFIMT Training provided to 20 participants from Guyana, Suriname, Barbados and Trinidad and Tobago and EAFIMT Scoring completed for Guyana. Suriname's and TTO's soring is in progress. 2. Upgrade of Calipseo in Guyana completed. Upgrades in Trinidad and Tobago and Suriname are progressing. 3.Two stock assessments for Seabob in Guyana and Suriname were completed in March 2024 in collaboration with the CRFM Shrimp and Groudfish Working Group (SGWG) and Fish4ACP. Targets were met for stock assessment recommendations for Guyana and Suriname (18 recommendations being reviewed and supported). A two-week sub-regional workshop was also held in Guyana from the 11-22 Nov 2024, on stratified sampling and data management in collaboration with GUY/FAO TCP and Fish4ACP. A sub-regional Workshop on Groundfish Stock Assessment and Stakeholder Consultation was held in Suriname from March 31st - April 4th 2025 in collaboration with CRFM and Fish4ACP. Preliminary stock assessments were initiated for the following species: Suriname: Acoupa weakfish (Cynoscion acoupa), barracuda (Sphyraena guachancho), and green weakfish (Cynoscion virescens). An updated seabob stock assessment was presented and discussed during a surveillance audit of the Suriname seabob fishery in May 2025. Guyana could not particpate in persons at this workshop. EAF4SG will support incountry assessments of their groundfish species. In June 2025 Guyana was advised that the has passed their MSC audit and Suriname received advice that thie Seabob certificate suspension is be lifted, and the certificate can be reinstated. 5.An assessment and identification of the socio-economic indicators that could be collected by Trinidad and Tobago, Guyana and Suriname was completed and is under review. Seven capacity building meetings were held with CERMES Barbados and executing partners to discuss the SOCMON approach to monitoring socioeconomic variables from Jan - Dec 2024. Executing partners agreed that focus would be on the identification of socio-economic indicators that could be incorporated into Calipseo and SOCMON would be used as needed. Suriname has started to incorporate the collection of socioeconomic data into the national data collection framework.Three new fisheries data collectors were hired by the Fisheries Department and trained in data collection, including socio-economic data. Trinidad and Tobago and Guyana to review and discuss their approach. 6. EAF and co-management activities have been progressing with hiring of International consultants and full engagement of country teams. A review of Guyana's Legal frame work was completed. An assessment of NICs in Guyana, Trinidad and Tobagos and Suriname has been completed and is under review. EAF4SG benefits from synergies with REBYCIII and collaboration with other partners such as the CRFM and FISH4ACP. Component 3 actvities need to be progressed. Challenges in obtaining suitable consultants for C3 activities is posing a challenge.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal
There has also been some challenges in the level of spending of project funds due to lengthy internal administrative and financial processes. Payments to National consultants in Guyana have been hampered because of difficulties in transferring USD from UWI to these Consultant's national banks in Guyana. Foreign exchange, especially payment in USD in the region is especially challenging. We have been working with National Consultants to open new bank accounts with other financial institutions and discussions continue with UWI's Internal Financial mechanisms to address this matter. This has resulted in some delays in spending. Some risk to project implementation is anticipated as elections are carded for Guyana and Suriname later in 2025. Trinidad and Tobago also recently concluded a general elections where there was a change in Political Administration. Risk will be managed in Guyana and Suriname by limiting Sub contracts and disbursements to very small tranches for in country activities. UWI will also seek to increase and administer direct payments to Contractors in each of these countries where possible in the short term to mitigate any potential delays arising from these political changes. UWI is already making all payments for TTO contractors directly so limited impact on spending is anticipated for TTO. Changes in Poltical landscape potentially also impact executing partners' ability to participate in regional and sub regional training and workshop activities or execute activities in country. In many cases Cabinet or Ministerial approval is needed for staff of the Executing partners to travel to these training events. This leads to delays and sometimes non participation by key stakeholders when new administrations need to be briefed and approvals to travel need to be obtained. Some challenges have already been experienced in this regard where staff from Guyana were not able to participate in a recent project related training activity because the necessary executive approvals could not be obtained in a timely manner. There has also been recent delays in TTO in obtaining approvals to travel due to a change in policy arising from a change in political administration. The Project will ensure that the required approvals are obtained in a time manner to support execution of future activities. We also expect some impact on the extent of co-financing available to this project by our US project partners as a result of new policies adopted by the current US administration. To mitigate this potential shortfall in cofinancing, we will be enaging with our other partners (especially fishing industry partners) who support the Project to better reflect their level of co-financing or increase it, especially as their cofinancing for on the ground at sea work may have been under assessed.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | Yes - Executing partners who are the Governments in the participating countries will continue work as part of their regular work programme
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | Training and partnership is on going with the Executing partners for sustained follow up activities

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Low
New environmental and social risks. | In view of the decision of Suriname to include indigenous communities of Galibi in some project activities, the project is re-classified as Moderate risk. Appropriate actions are being taken to support the project partners in obtaining Free, Prior and Informed Consent (FPIC) with this community.
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | Risk being managed as detailed in the ESMP. Engagement with Indigenous group may result in higher risk rating. Also Guyana, Suriname and Trinidad and Tobago wil have elections in 2025 and there may be delays as a result of possible change in administrations.
Grievance Redress Mechanism (GRM) | No grievance reports were received.

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Political |  | Moderate | Yes | The sustainability of political commitment and active participation of key institutions and stakeholders may not be maintained throughout the project’s duration due to changes in national priorities, turnover of authorities, lack of resources, or loss of partner interest, which could compromise governance, regional coordination, and the effective implementation of project activities. | Executing partners generally engaged and supporting project activities. Monthly meetings of NFPs convened to discuss progress and challenges. Staffing constraints and alternative priority obligations in some countries have resulted in initial delays in hiring of NTCs and delivery of some output activities for those partners. These issues have been resolved. Currently all NTCs are hired and working on project activities. Guyana, Sriname and TTO will have elections in 2025. This has the potential to neagtively impact project execution and create delays if not managed properly. To address this, risk will be managed through direct disbursements as far as practical and early engagement.
2 | Social |  | Moderate | Yes | SSF communities may not fully participate or benefit from project activities due to varying levels of interest, communication challenges, or limitations in delivering training and capacity-building. | FFOs have been engaged in project activities since inception. KMCO hired by the PMU expected to develop tools (website, fact sheets, promotional material) to ensure continuous communication, dissemination and feedback on project activities.
3 | Institutional |  | Moderate | Yes | The adoption and implementation of the Ecosystem Approach to Fisheries (EAF) could be limited by a lack of interest or commitment from the private sector, financial institutions, and national governments due to financial barriers, perceived risks, institutional capacity weaknesses, or shifts in political priorities (exacerbated by impacts such as the COVID-19 pandemic). | Contracting of international and national consultants to support project activities will mitigate this. The placement of these staff in the various Fisheries Departments also support national capacity building and promotes execution of project activities.
4 | Strategic |  | Moderate | Yes | The effective participation of women, youth, and other vulnerable groups in project activities may be constrained by cultural, social, or economic barriers, such as traditional gender roles, limited time availability due to family responsibilities, unequal access to resources and services, or even institutional or community resistance to their involvement in decision-making processes. These limitations may reduce the project’s expected impact in terms of empowerment, gender equity, and the sustainability of benefits. | Project will specifically target women, youth and marginalised groups. Project has a Gender Plan. Gender Focal Points identified in all target countries.
5 | Social |  | Moderate | Yes | The adoption of the Ecosystem Approach to Fisheries (EAF) and more responsible fishing practices in target shrimp and groundfish fisheries at the community level may face resistance or limited uptake due to low awareness, insufficient incentives, competing short-term economic interests, or lack of trust in project interventions. | A strong focus is placed on Component 3 activities. Previous work will be built upon.
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Low | Moderate | Risk being managed as detailed in the ESMP. Engagement with Indigenous group may result in higher risk rating. Also Guyana, Suriname and Trinidad and Tobago wil have elections in 2025 and there may be delays as a result of possible change in administrations.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1: | LTO Mission resulted in resolution of difference of opinion on interpretation of "spent" vs "committed" funds. UWI is no longer holding the total contract amounts thereby making it easier for "committed" funds to be spent on project activities.
Recommendation 2: | NA
Recommendation 3: | NA
Recommendation … | NA
Recommendation… | NA

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | NA | N/A | N/A
Components and cost | NA | N/A | N/A
Institutional and implementation arrangements | The PSC agreed that a new budget line Sub-Contract to Countries should be developed to allow funds to be disbursed for in country activties | 2025-01-01 | PSC
Financial management | NA | N/A | N/A
Implementation schedule | NA | N/A | N/A
Executing Entity | NA | N/A | N/A
Executing Entity Category | NA | N/A | N/A
Minor project objective change | NA | N/A | N/A
Safeguards | NA | N/A | N/A
Risk analysis | NA | N/A | N/A
Increase of GEF project financing up to 5% | NA | N/A | N/A
Co-financing | NA | N/A | N/A
Location of project activity | NA | N/A | N/A
Other minor project amendment (define) | NA | N/A | N/A
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Fisheries Department, Ministry of Agriculture, Guyana | Partner, Direct Beneficiary | Generally good engagement at the level of the Fisheries Department. There have been some challenges in obtaining approvals for staff to participate at regional in person training events
Government Institutions | Ministry of Agriculture, Land and Fisheries, TTO | Partner, Direct Beneficiary | Good. There have been some challenges on obtaining feedback from Executive members who are very busy with other domestic issues
Government Institutions | Department of Marine Resources and Fisheries, Tobago House of Assembly (THA) | Partner, Direct Beneficiary | Good- There have been some challenges on obtaining feedback from Executive members who are very busy with other domestic issues
Government Institutions | Fisheries Department, Ministry of Agriculture, Animal Husbandry and Fisheries, Suriname | Partner, Direct Beneficiary | Good
Government Institutions | Environmental Management Authority, TT | Resource Partner | Good
Government Institutions | Institute of Marine Affairs, TT | Resource Partner | Good
NGOs | CANARI | Partner | Good
NGOs | Future Fishers | Partner | Excellent
NGOs | Caribbean Regional Fisheries Mechanism (CRFM) | Partner | Excellent
NGOs | Cartagena Convention Secretariat | Partner | Good
NGOs | CeDePesca | Partner | Not too involved
Private Sector entities | Surinaamse Seafood Associate (S.S.A) | Cofinancing partner | Good
Private Sector entities | SUR- Sujal Trading NV | Cofinancing partner | Good
Private Sector entities | SUR- VaYu Fisheries NV | Cofinancing partner. Direct Beneficiary | Good
Private Sector entities | SUR- CARIB FISHERIES N.V | Cofinancing partner. Direct Beneficiary | Good
Private Sector entities | SUR- N.V. HOLSU | Cofinancing partner. Direct Beneficiary | Good
Private Sector entities | SUR- Marisa Fisheries NV | Cofinancing partner. Direct Beneficiary | Good
Private Sector entities | SUR-V.O.F Nathan Fisheries | Cofinancing partner. Direct Beneficiary | Good
Private Sector entities | SURINAME SEA CATCH N.V. | Cofinancing partner. Direct Beneficiary | Good

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | Yes | Targets Met under the Year 1 Gender Action Plan - Gender equal composition of the Project Steering Committee Include monitoring and evaluation of the GAP by the PSC ,Gender equal composition of the Project ,Steering Committee TARGET MET, Target: At least 50% of the member of the PSC is women TARGET MET, Regular monitoring and evaluation of the GAP for the project TARGET MET FOR YEAR 1.
b. Improving women's participation and decision making | Yes | All logged project activities when analysed showed that more than 50% of participants were women which signifies that there has been above average women's participation and active decision making during the project's lifecycle.
c. generating socio-economic benefits or services for women | Yes | Gender Action Plan Year 1 Targets and Updates Output 1.1.1: Analysis of existing fisheries management information systems (FMIS) and data in the three target countries and sub-regional level undertaken and recommendations for improvement developed. Deliverable: Determine the extent to which sex disaggregated data is collected and make recommendations for improvement, where applicable – Work in Progress by TPC and Consultant Recommendations for improvement of sex disaggregated data included in recommendations to improve FMIS – Work in progress by TPC and Consultants Output 2.1.1: National inter-sectoral coordination mechanisms for EAF in three participating countries supported and fully operational. Deliverable: 1. Identify and document what types of barriers limit the representation of women on NICs and recommend strategies to promote improved gender-balanced representation on NICs. Work in progress by TPC and consultants. 2. Influence targeted organisations to select both women and men to participate in technical capacity building activities to improve NICs. Work in progress by TPC and consultants. Types of barriers that limit the representation of women on NICs identified and recommendations to promote improved gender-balanced representation made. Proportionally number of women participated in technical capacity building activities to improve NICs. Target: At least 40% of participants are women - TARGET MET Output 2.3.1: Current national legal and regulatory frameworks for EAF reviewed, particularly in relation to SSF, including for co-management. Deliverable: Number of national legal and policy framework reviews for EAF that apply a gender-sensitive research methodology Work in progress by TPC and consultants. Output 4.1.1: EAF Outreach Strategy and Plan to promote greater understanding of EAF management in target fisheries developed and implemented Gender considerations included in the Outreach Strategy and Plan Deliverable: Target: 100% of communication products are gender-sensitive Work in progress by TPC and KMCO. Output 4.1.2 Project successes, experiences and lessons learned identified and disseminated to key EAF4SG stakeholders Deliverables: Include gender considerations in the Knowledge Management and Communications (KMC) Plan Work in progress by TPC and KMCO. 1. Disseminate lessons learned, best practices and recommendations from the project on gender mainstreaming and women's empowerment in fisheries. Work in progress by TPC and KMCO. Gender considerations included in the: - KMC Plan -Lessons learned, best practices and recommendations on gender mainstreaming and women's empowerment in fisheries disseminated. Output 4.2.1: A gender-responsive project Monitoring and Evaluation (M&E) system using data disaggregated by sex, age and ethnicity designed and operational, and in line with FAO and GEF requirements 1. Gender equal composition of the Project Steering Committee Include monitoring and evaluation of the GAP by the PSC ,Gender equal composition of the Project, Steering Committee - TARGET MET. 1. Target: At least 50% of the members of the PSC are women - TARGET MET. 2. Regular monitoring and evaluation of the GAP for the project - TARGET MET FOR YEAR 1. YEAR 2 The period started with the 2nd Capacity Building session on the Geder Action Plan with Gender Focal Points. For the period, the following gender statistics report with demographics were prepared: - CSWG 2025 - EAF IMT Refresher - EAF4SG 2nd PSC - Joint Report REBYC 111 and EAF4SG Galibi Tribe with write up - Joint Report REBYC 111 and EAF4SG Meeting of LTOs - Joint Report REBYC 111 and EAF4SG TADCO - Joint Report REBYC 111 and EAF4SG Tobago House of Assembly -REBYC111 and EAF4SG TADCO joint report.docx -REBYC111 and EAF4SG Meeting of LTOs and C3 Consultants.docx -REBYC111 and EAF4SG Galibi Tribe meeting.docx -EAF4SG 2nd PSC.docx -EAF IMT Refresher Training.docx -CSWG Workshop Gender Details 2025.docx
Any other good practices on gender | Yes | The preparation of strategic plan for Gender Action Learning Group was done and a Gender Fact sheet along with social media posts were derived for project awareness. There is active communication amongst Gender Focal Points along which ensures the targets are met according to the Gender Action Plan.

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | The KMC Plan has been 100% completed and integrated into the project's broader dissemination strategy and plan. Dissemination and awareness-raising materials have been developed. Active participation has taken place in knowledge-sharing platforms and training workshops. The development of project´s visual identity is 100% complete, inlcuding the logo, branding, banners and the creation of a Facebook account and a working website with updates on projects activities.
If NO, how does the project identify, collect and document good practices? | N/A
Please list good practices, including key-technical and/or institutional innovations, from the project thus far.
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | The EAF4SG project, while still in its relatively early stages, has demonstrated a proactive approach to communications, aiming to foster knowledge sharing and engagement among diverse stakeholders. Communications successes include - Effective Dissemination of Training and Capacity Building Opportunities: The project has successfully communicated and delivered key training initiatives. For instance, the Implementation Monitoring Tool (IMT) refresher training and the fisheries statistics and data analysis training sessions were well-advertised and attended by target national and sub-national stakeholders. This indicates a good reach for technical capacity-building communications - story on the training can be found at: https://www.ffaprojects.org/communications/eaf4sg-project-to-conduct-imt-refresher-training/ Active Engagement with Regional Bodies: The project consistently collaborates and communicates with key regional organisations like WECAFC and CRFM. This ensures that project activities and findings are integrated into broader regional discussions and policy frameworks, amplifying the project's influence and reach. Joint working groups and multi-country assessments (e.g., on groundfish resources) demonstrate successful communication channels at a regional technical level - story can be found at: https://www.ffaprojects.org/communications/eaf4sg-and-crfm-cswg-to-build-data-managers-capacity/ Initial Stakeholder Buy-in and Collaboration: The successful inception workshop and ongoing engagement with national executing partners, focal points, and fisherfolk organisations shows that the project has been effective in establishing initial relationships and securing buy-in from diverse stakeholder groups. This foundational communication is crucial for long-term project success - See story here: https://www.ffaprojects.org/communications/eaf4sg-project-convenes-second-psc-meeting/ Targeted Communication for Specific Outputs: The project has effectively communicated specific outputs, such as the development and use of the EAF IMT, ensuring that relevant stakeholders understand its purpose and how to utilise it. Challenges: Sustaining Engagement: Countries are not providing information in a timely manner for communications initiatives. Managing Expectations and Demonstrating Tangible Impact: In projects focused on capacity building and systemic change, it can be challenging to communicate immediate, tangible impacts to all stakeholders, especially in the early stages. Managing expectations and consistently demonstrating progress towards long-term goals requires careful communication. There seems to be lack of understanding on what exactly communications is and what it should do at the management level of the PMU. Resource Constraints for Broader Public Awareness Campaigns.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits. | None available at this time
Please provide links to related website, social media account | Website: www.ffaprojects.org; Facebook: https://www.facebook.com/people/FFA-Projects/61567809444369/
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | Thus far all information is published on website and facebook pages
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | Ms Allison Ali; kmco_fisheries.proj@outlook.com

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. YES In the reporting period, the project engaged with the FFO of an indigenous fishing community in Suriname (village of Galibi) to discuss issues faced in managing the fisheries in the area. Following this initial consultation, the Fisheries Department of Suriname decided to further engage with and support this FFO within the project's framework. Therefore, the project initiated consultations with FAO to seek guidance on obtaining Free, Prior, and Informed Consent (FPIC) from this community. An Engagement strategy for Galibi was developed by the Fisheries Department of Suriname. Discussions were held with the Village Chiefs and local Indigineous peoples umbrella organization to agree on this engagement. Collaboration with Galibi has now resumed with plans in place to strengthen their organization and potentially develop pilot activities under Component 3. Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. The Project will support strengthening of the Galibi Fisherfolk Organization and potentially support livelihood projects to support management measures for the gillnet fishery

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | Fisheries Department, Government of the Cooperative Republic of Guyana | In-kind | 600000 | 63091.25
Recipient Country Government | Fisheries Department, Ministry of Agriculture, Animal Husbandry and Fisheries, Government of the Republic of Suriname | Other | 215000 | 200500
|  | In-kind | 1085000 | 400000
Recipient Country Government | Fisheries Division, Ministry of Agriculture, Land and Fisheries, Government of the Republic of Trinidad and Tobago | Public Investment | 194337 | 12749
|  | Other | 3594 | 62326.82
|  | In-kind | 573471 | 217430.43
Recipient Country Government | Department of Marine Resources and Fisheries, Division of Food Security, Natural Resources, the Environment and Sustainable Development, Tobago House of Assembly | In-kind | 48810 | 21323.5294
Recipient Country Government | Institute of Marine Affairs, Trinidad and Tobago | In-kind | 42000 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) – HQ (NFIFM) | In-kind | 80000 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) – HQ (NFIMV) | In-kind | 250000 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) – HQ (NFISI) | In-kind | 828800 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) - Sub-Regional Office for the Caribbean | In-kind | 224840 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) – Country Office Guyana | In-kind | 726120 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) – Country Office Suriname | In-kind | 100000 | Awaiting feedback
GEF Agency | Food and Agriculture Organization of the United Nations (FAO) – Country Office Trinidad and Tobago | In-kind | 100000 | Awaiting feedback
Others | Caribbean Regional Fisheries Mechanism (CRFM) | In-kind | 200000 | Awaiting feedback
Others | Western Central Atlantic Fishery Commission (WECAFC) | In-kind | 62000 | Awaiting feedback
|  | Grant | 185000 | Awaiting feedback
Others | Future Fishers, Trinidad and Tobago | In-kind | 493185 | 2794.18
Others | Centre for Development and Sustainable Fisheries (CeDePesca) | In-kind | 265000 | 15000
Others | The University of the West Indies Centre for Resource Management and Environmental Studies (UWI- CERMES) | In-kind | 200000 | Awaiting feedback
Others | The University of the West Indies St. Augustine Campus, Faculty of Food and Agriculture (UWI-STA-FFA) | In-kind | 779000 | Awaiting feedback
Private Sector | Guyana Association of Trawler Owners and Seafood Processors (GATOSP) | In-kind | 300000 | Awaiting feedback
Private Sector | Surinaamse Seafood Associate (S.S.A) | In-kind | 200000 | Awaiting feedback
Others | Guyana National Fisherfolk Organization (GNFO) | In-kind | 34000 | Awaiting feedback
Others | Moruga La Ruffin Fishing Cooperative | In-kind | 9600 | NIL
Others | Claxton Bay Fishing Association | In-kind | 14400 | NIL
Total |  | Total | 7814157 | 995215.2094
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report? |  |  |  |  | first PIR
Location Name | Latitude | Longitude | Geo Name ID | Location & Activity Description*
Guyana | 6.8 | -58.1667
Suriname | 3.9193 | -56.0278
Trinidad and Tobago | 10.6711 | -61.5212

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.