Project Implementation Report

Project title: Sustainable Management of Peatland Ecosystems in Mekong Countries

Programme: ARO

Project Manager: Mr. Peter Hanington

Global thematic programme:  Global Water Programme

PIR Date: April 2021

Actual Agency Approval date: 18 April 2018

Fiscal year: 2020-21

Implementation status: Under implementation

Development objective rating: Moderately satisfactory

Implementation progress rating: Moderately unsatisfactory

Risk rating: Substantial risk

Actual implementation start date: 1 March 2019

First disbursement date: 1 December 2018

Expected mid-term review date: February 2022

Expected closing date: 30 June 2023

Cumulative disbursement as of 28 February 2021 as of given FY or Project that have been in implementation for at least one fiscal year ($): 532,031

Expected financial closure / terminal financial report date: 30 June 2024

------------------------------------------------

Information on Progress, challenges and outcomes on project implementation activities:

The overall Implementation Rating for the project to date is Moderately Satisfactory.

Overall project progress is delayed for three primary reasons; 1) the time taken to complete agreements with the Executing Agencies (EAs) in each of the three countries, 2) ongoing complication related to the COVID-19 pandemic, and 3) in Myanmar due to the coup d’état that occurred on 1 February 2021.

The agreements with all EAs are now complete. Agreements with EAs in Cambodia and Lao PDR we completed on 19 August 2019 and 20 May 2020 respectively. The final agreement with the EA in Myanmar, the Environmental Conservation Department (ECD), MoNREC, was completed on 23 October 2020.  At the request of the ECD, IUCN is supporting project execution, specifically the management and execution of the regional components of the project.  This staggered completion of the executing agreements has resulted in components of the project moving forward in some countries while being delayed in others. This mis-alignment of the project components was highlighted during the first Project Supervision Mission in November 2020, and a revised work plan was produced that outlines the detailed plan moving forward towards harmonising project execution.  Encouragingly, the project execution rate has increased in Cambodia and Lao PDR, although the impacts of the Covid-19 pandemic continue to hinder certain activities, particularly those involving field based work and gathering of large groups of people.  Project execution in Myanmar continues to be very slow due to Covid-19 and more importantly due to the coup d’état that occurred on 1 February 2021.

On 1 February 2021 the military in Myanmar seized control of the country and government, and detained the State Counsellor and other senior figures in the government.  In response, a large civil disobedience movement started and continues with regular large scale protests in many parts of the country.  Military responses to the protests have so far resulted in the loss of hundreds of lives and the detention of thousands of people. The installed military government is perceived as illegitimate by many. Several development partners have put projects on hold and many donors have asked their partners to cease all activities on the ground. Furthermore, many development partners have withdrawn all engagement with the military government at both national, state and region levels, except perhaps in the case of providing humanitarian assistance.

The political situation and social unrest in Myanmar are significantly impacting the execution of the Mekong Peatlands project in the country.  For the most part, all project activities in Myanmar are on hold.  A cash disbursement to the ECD in Myanmar is also on hold as it is not possible to transfer funds into Myanmar at this time.  IUCN continues to monitor the situation on the ground, and a meeting will be held on 22 April 2021 to again review the current situation and take decisions on next steps for the project in Myanmar.

Component 1 – Assessment and documentation of peatlands in targeted countries

Progress on Component 1 activities include the drafting and review of three training modules: (1) Definition, characterisation and identification of peatlands in the Mekong region; (2) Use of remote sensing for peatland identification and delineation; and (3) Field verification and mapping of peatlands. The fourth training module – Assessment of peatland degradation status and management issues is currently being drafted. Modules 1 and 2 are currently being translated into local languages in all three countries, while Module 3 is under revision after an initial technical review.

Training modules 1 and 2 have been used to conduct virtual trainings for the technical teams now established in each country and who are undertaking the remote sensing analysis and development of preliminary maps of potential peatlands for each country. The remote sensing analysis and peatland mapping is currently underway in each country.

Content from the training modules and summaries from past peatland surveys and reports have been used to develop communication materials for use in stakeholder engagement and awareness raining activities. Training for the peatland surveys teams are scheduled to commence in April 2021 in Lao PDR.

COVID-19 travel restrictions in all countries have forced all trainings to be held on-line and have significantly delayed the commencement of field surveys. The COVID-19 situation in Lao PDR is presently under control allowing domestic travel – the Chief Technical Advisor for the project has relocated to Lao PDR for a period to deliver training and commence field surveys while conditions allow. The ongoing COVID-19 restrictions in Cambodia, and the recent coup d’état in Myanmar, have resulted in the postponement of previously planned field based activities. When the situation allows, field-based activities will commence in both Cambodia and Myanmar.

Component 2 – Capacity development and policy and legal frameworks

Progress on Component 2 activities include the training of technical groups in all three countries on peatland types in the Mekong region and the use of remote sensing to map potential peatlands. Participation in virtual training sessions undertaken by the project included government agencies and universities in each country. Training was restricted to small technical teams, totalling 11 participants from Cambodia, 18 from Lao PDR and nine from Myanmar. In addition, the project supported the Government of Lao PDR to completed a cross-agency workshop to discuss the potential mainstreaming of peatlands into the National Water Resources Strategy.

Stakeholder communication and awareness raising materials have been drafted for each country to use with various stakeholders during future planned events. Further awareness raising materials will be developed during the course of the project.

The project has faced challenges in implementing Component 2 activities due to COVID-19 restrictions not allowing travel and therefore limiting all opportunities to undertake in-person trainings and stakeholder awareness raising events. The project has focused initially on technical trainings for small groups utilising online platforms. Once COVID-19 restrictions have eased, and the ongoing situation in Myanmar improves, the project will undertake further stakeholder capacity development and awareness raising activities. In the meantime, the project will continue to develop communication materials in preparation for future events.

Component 3 – Development and demonstration of Best Management Practices

Progress on Component 3 activities has been limited to date and mainly focused on developing stakeholder communication and engagement plans (so far for Myanmar and Cambodia), and establishing Grievance Mechanisms for use in communities that the project will pilot livelihood activities. In addition to these, the project has achieved the incorporation of peatland conservation measures into the 2019-2023 draft management plan for the Beung Kiat Ngong Ramsar site in Lao PDR. This outcome will be further supported by the project towards finalisation of the management plan.

The project continues to experience challenges to implementing Component 3 activities due to travel restrictions and safety concerns related to COVID-19 and the recent recent coup d’état in Myanmar. The project will continue to progress activities where possible and when the situation allows, engage with communities to design and implement sustainable livelihood practices. The use of virtual meetings will continue where possible to progress Component 3 activities, however, most activities rely on working in close collaboration with communities on the ground.

Component 4 – Regional Cooperation

Progress on Component 4 activities include the holding ofthe regional Project Inception Workshop during 2019 in coordination with other regional peatland programs. Participation at regional ASEAN meetings and events occurred throughout 2020 via virtual platforms. The project has participated in at least two ASEAN wide regional events each year, and other smaller Mekong Region events. Regional and National project coordination meetings and events have taken place in each of the three countries during 2020, however participation has been limited due to the ongoing COVID-19 situation. A national Inception Workshop in Myanmar is on hold until the situation in there improves.

Cooperation and coordination with other regional peatland programmes continues to take place via virtual meetings and events. A coordination group on knowledge products development has been established with the involvement of three regional peatland projects.  This group will help to harmonise and coordinate key activities and knowledge products. At the request of the Department of Water Resources in Lao PDR, IUCN will implement a grant project in Lao PDR (732,000 EUR) which directly supports and complements Mekong Peatland project activities and outcomes.  This grant project is financed by the Sustainable Use of Peatland and Haze Mitigation in ASEAN (SUPA) programme.

The political and social unrest in Myanmar, and the COVID-19 situation in all countries, continue to present challenges for moving forward regional activities due to safety concerns and travel restrictions. The project has delayed planned regional events, and where possible and practical, continues to use on-line platforms to facilitate regional activities and collaborations.

Information on Progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO Endorsement/Approval):

Stakeholder engagement plans have been drafted for Myanmar and Cambodia, with Lao PDR yet to develop a plan. The drafting of the Lao PDR stakeholder engagement plan has been delayed due to the Community Engagement Specialist (project staff) having not been recruited.

Due to delays in starting in-country activities, and complications related to the ongoing COVID-19, wider stakeholder engagement has been limited. National Project Inception workshops have been held in Cambodia and Lao PDR with the participation of key stakeholder groups. A smaller consultation event was held in Myanmar, primarily attended by government stakeholders.

The RCU has developed an initial set of stakeholder communication materials for each of the three countries, consisting of: (i) a trifold brochure (targeting general stakeholders including communities); (ii) a booklet on peatlands found in each country (targeting government, NGOs and other technical organisations); and (iii) a Grievance Mechanism poster to be used in communities that will be directly engaged during the project. The Cambodia team are also developing additional communication materials for use in local communities and schools. The RCU developed materials are currently being translated and finalised for use.

Information on Progress on gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent:

Project activities under Components 2 and 3 are designed and implemented using stakeholder participatory methods and consultation. A stakeholder engagement plan has been developed in Cambodia and Myanmar.  This plan will be operationalised for each each community engaged in the project, and is informed by socio-economic assessments and stakeholder consultations. The Community Engagement Specialist in each country will take the lead in this assessment process and stakeholder consultations. Where possible, local Women’s groups, such as the Lao Women’s Union, will be involved in project activities and implementation.

Component 3 has gender-based targets where project benefits are to be equally shared between women and men (50:50), these are prescribed in the project results framework.

Where possible, the project seeks to have a gender-balanced team with the appropriate skills and experience in gender equality and inclusion.

Knowledge activities / products (when applicable), as outlined in knowledge management approved at CEO Endorsement / Approval:

A set of four training modules are in various stages of development and translation. An initial set of communication materials have been developed, consisting of a trifold brochure and poster targeting community stakeholders, and a 6-8 page A5 booklet targeting government and other more technically minded stakeholders. Detailed community engagement and communication plans have been developed for Cambodia and Myanmar, with the Cambodia team planning to outreach using other forms of media such as film, stories and song.

The training modules are likely to receive minor refinements from knowledge gained through project implementation, therefore improvements to the current drafts are likely. Additional and complementary materials are likely to be available (and incorporated and/or adopted if appropriate) from the other regional peatland programmes - including the development of a web-based information portal that the Mekong Peatlands project will utilise once active.

ESMS implementation update :

Stakeholder engagement and communication plans and Grievance Mechanisms have been developed for Cambodia and Myanmar. Lao PDR will develop their own materials based on Cambodia and Myanmar examples. The Grievance Mechanisms have been drafted into A2 size posters for use within the communities. COVID-19 has prevented the project from undertaking consultations with communities and receiving their inputs and endorsement on the Grievance Mechanism. When the situation allows, the project will visit communities and commence consultations. The current situation in Lao PDR will allow such consultations to now take place in the coming weeks and months.

Budget showing advancement (USD) to 28 February 2021:

| Component | Budget | Expenditure |  |  |  | Total expenditure | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2018 | 2019 | 2020 | 2021 |  |  |
| Component 1: Assessment and documentation of peatlands in targeted countries | 780,744 | 705 | 30,470 | 172,498 | 5,432 | 219,104 | 561,640 |
| Component 2 – Capacity development and policy and legal frameworks | 731,000 | - | 24,067 | 23,363 | 2,387 | 49,817 | 681,182 |
| Component 3 – Development and Demonstration of Best Management Practices | 921,900 | - | - | 32,899 | 3,156 | 36,055 | 885,844 |
| Component 4 – Regional Cooperation | 335,000 | - | 95,685 | -34,381 | 3,139 | 64,442 | 270,558 |
| Project Management Cost | 138,420 | - | 8,160 | 23,450 | 2,275 | 33,885 | 104,535 |
| Total | 2,907,064 | 705 | 158,382 | 217,829 | 26,388 | 403,304 | 2,503,760 |

Highly satisfactory, satisfactory, unsatisfactory, not rated, unknown, marginally satisfactory, marginally unsatisfactory, highly unsatisfactory.

High risk, substantial, moderate risk, low risk