UN Environnent GEF PIR Fiscal Year 2019

(1 July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 5557 | Umoja no.: SB-000689.22.06 |
| --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | 5557: Developing Core Capacity for MEA Implementation in Haiti |  |
| Duration months | Planned |  | 36 months |  |
|  | Extension(s) |  | 31 August 2021 & 24 months added |  |
| Division(s) Implementing the project |  |  | Science Division (Formerly DEWA), Climate Services & Capacity Building Unit, Capacity Development & Innovations Branch. |  |
| Executing Agency(ies) |  |  | Govt. of Haiti: Ministry of Environment |  |
| Names of Other Project Partners |  |  | UNEP Crisis Management Branch (Formerly PCDMB) - Haiti, Policy and Programme Division. |  |
| Project Type |  |  | Medium Size Project |  |
| Project Scope |  |  | National |  |
| Region (delete as appropriate) |  |  | Latin America and the Caribbean |  |
| Names of Beneficiary Countries |  |  | Haiti |  |
| Programme of Work |  |  | 2018-2019; UNEP SP7 EA(a)(ii) |  |
| GEF Focal Area(s) |  |  | Multi Focal Area |  |
| UNDAF linkages |  |  | UNDAF Resilience outcome 4 Product 6 – Ministry of Environment has access to the necessary tools for the sustainable management of protected areas and biodiversity protection Product 7 - Ministry of Environment has access to decision-making tools for environmental management and cross-cutting integration of environment in other development sectors |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | Although this GEF CCCD project has been designed to create enabling environment and enhance the implementation, monitoring and reporting of all SDGs with an environmental dimension, majority of the project interventions primarily contribute to the following SDGs, targets and indicators: SDG 13 (13.b.1); SDG 15 (15.2.1, 15.9.1); SDG 16 (16.10.2); and SDG 17 (17.14.1; 17.16.1; 17.18.1) |  |
| GEF financing amount |  |  | USD 1,298,000 |  |
| Co-financing amount |  |  | USD 2,750,000 |  |
| Date of CEO Endorsement |  |  | 29 May 2015 |  |
| Start of Implementation |  |  | 15 February 2016 |  |
| Date of first disbursement |  |  | 21 July 2016 |  |
| Total disbursement as of 30 June |  |  | USD 528,544.47 |  |
| Total expenditure as of 30 June |  |  | USD 528,544.47 |  |
| Expected Mid-Term Date |  |  | N/A (MTR not designed for) |  |
| Completion Date |  | Planned | 31 December 2019 |  |
|  |  | Revised | 31 August 2021 |  |
| Expected Terminal Evaluation Date |  |  | 31 December 2021 |  |
| Expected Financial Closure Date |  |  | 30 June 2022 |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) 2018-2019 UNEP SP7 EA(a)(ii) | Specify the relevant Expected Accomplishment(s) & Indicator(s) SP7 EA(a): Governments and other stakeholders use quality open environmental data, analyses and participatory processes that strengthen the science-policy interface to generate evidence-based environmental assessments, identify emerging issues and foster policy action. SP7 EA(a)(ii): Increase in the number of countries reporting on the environmental dimension of sustainable development through shared environmental information systems with country-level data made discoverable through UNEP. SP7 EA (iii) Strengthening of the science-policy interface by countries based on the use of data, information and policy analysis in the areas of air quality, water quality, ecosystems, biodiversity, waste and hazardous chemicals, the marine environment and emerging issues. |
| --- | --- |
| Although in a context of high risks from political instability, over the last year the development of the National Environmental Information System (NEIS) has marked a significant progress (20%), and the Haitian Biodiversity Fund has been established and it will be soon fully operational. Overall, the project has contributed to the increase in the number of countries reporting on the environmental dimension of sustainable development in the Caribbean region and has been instrumental to consolidate partnerships and collaboration among key stakeholders, including UN agencies and other programmes active in the country. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes N/A | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
| N/A | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

| Planned linkages with UNDAF | The current 2017-2021 UNDAF in the Republic of Haiti focuses on the following five (5) priorities: (i) poverty reduction and the promotion of decent employment, (ii) access and use of quality basic social services, (iii) gender equality and protection, (iv) resilience, and (v) governance. Moreover, the UNDAF defines one outcome for each of the five priority areas of intervention, which will make a valuable contribution to the achievement of national priorities and SDGs. This project is linked to the working group #4 of the UNDAF in Haiti – related to Resilience strategic objective. Under this thematic, this project contributes to the sixth and seven products under the fourth outcome of the UNDAF on Resilience. 2017-2021 UNDAF in Haiti, Outcome 4: National, regional and local institutions, along with civil society strengthen sustainable management of natural resources and environment, territorial and population resilience, especially for the most vulnerable, to respond to natural disasters, to climate change and humanitarian crisis while ensuring continued sustainable development. Product 6: ‘’Ministry of Environment has access to the necessary tools for the sustainable management of protected areas and biodiversity protection’’, through the establishment and management of the Haitian Biodiversity Fund, as well as for the development of a methodological guide for riverbanks integrated management. This project also contributes to UNDAF product 7 ‘Ministry of Environment has access to decision-making tools for environmental management and cross-cutting integration of environment in other development sectors’, through the development of a National Environmental Information System (NEIS) for Haiti and of the methodological guide of the environmental audit, among others. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | SDG 13 (13.b.1); SDG 15 (15.2.1, 15.9.1); SDG 16 (16.10.2); and SDG 17 (17.14.1; 17.16.1; 17.18.1) 13.b.1 13.b Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities 13.b.1 Number of least developed countries and small island developing States that are receiving specialized support, and amount of support, including finance, technology and capacity-building, for mechanisms for raising capacities for effective climate change-related planning and management, including focusing on women, youth and local and marginalized communities A methodology guide for riverbanks management and rehabilitation through reforestation using native and endemic plants was elaborated. The document is in its final stage of validation (workshop to be organized to formally introduce the document) and training of Haiti’s Ministry of Environment (MoE) staff at local level is scheduled to implement field operations based on the methodological guide. This tool is expected to provide a contribution to the capacity of the MoE to plan and manage more efficiently activities which aim to address climate change issues. 15.2.1 15.2 By 2020, promote the implementation of sustainable management of all types of forests, halt deforestation, restore degraded forests and substantially increase afforestation and reforestation globally 15.2.1 Progress towards sustainable forest management The Haitian Biodiversity Fund (HBF) is a key product of the project and its main objective is to create a sustainable and long-term capacity to finance activities for a better management and preservation of natural resources in Haiti, including forestation management. The HBF has been legally established thanks to the project and is already receiving pledges from donors. The Trust Fund, by its nature, is an essential element for promoting the development of activities to progress towards sustainable forest management in Haiti. 15.9.1 15.9 By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts 15.9.1 Progress towards national targets established in accordance with Aichi Biodiversity Target 2 of the Strategic Plan for Biodiversity 2011–2020 With the assistance of Aube Nouvelle University of Burkina Faso, through the project a methodology guide for environmental audits has been developed and would be implemented by the Bureau National des Evaluations Environnementales (BNEE). The document has been validated and training of BNEE staff has been carried out by the consultants. Another methodological guide for Coastal Zone Environmental Assessment is also being developed. Those tools are expected to strengthen the capacity of MoE to integrate ecosystem and biodiversity values into public and private projects under development across the country, thereby, making progress towards national targets of protection and preservation of biodiversity. 16.10.2; 16.10 Ensure public access to information and protect fundamental freedoms, in accordance with national legislation and international agreements 16.10.2 Number of countries that adopt and implement constitutional, statutory and/or policy guarantees for public access to information The National Environmental Information System (NEIS) is currently being designed. Key indicators that should be integrated into the system has been identified and validated by key national stakeholders. One of the key elements to consider in the architecture of the NEIS is to make information fully accessible to the public in order to raise awareness of environmental challenges. This accessibility should be guaranteed through a Charter, which will be signed by the main national parties who will feed the information system and ensure the provision of adequate, transparent and timely data. 17.14.1 17.14 Enhance policy coherence for sustainable development 17.14.1 Number of countries with mechanisms in place to enhance policy coherence of sustainable development One of the objectives of the project is to address the lack of coordination mechanisms for the implementation of MEAs in Haiti. The Project Team was strongly involved in the preparation of the environment chapter of the Post-Disaster Needs Assessment (PDNA) after hurricane Matthew in late 2016. Key information from this assessment will be used for the elaboration of an Environmental Action Plan (EAP) for the Ministry. A consultant was hired for this purpose but political and institutional instability, associated with the changes in strategy of the Ministry of the Environment, have hindered the progress of this activity, currently on hold waiting for a new government. The elaboration of the EAP will contribute to strengthening the coherence of sustainable development policies in the country. 17.16.1 17.16 Enhance the Global Partnership for Sustainable Development, complemented by multi-stakeholder partnerships that mobilize and share knowledge, expertise, technology and financial resources, to support the achievement of the Sustainable Development Goals in all countries, in particular developing countries 17.16.1 Number of countries reporting progress in multi-stakeholder development effectiveness monitoring frameworks that support the achievement of the Sustainable Development Goals The project team is co-leading a group of actors and donors involved in the environment sector in Haiti in order to enhance coordination, to share best practices and to consistently advocate for the need of an action plan led by the MoE and monitored through the Table Sectorielle for the Environment. This structure composed of multiple stakeholders is expected to increase partnerships that will help mobilize financial resources, share knowledge and expertise to support the SDGs in Haiti. 17.18.1 17.18 By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts 17.18.1 Proportion of sustainable development indicators produced at the national level with full disaggregation when relevant to the target, in accordance with the Fundamental Principles of Official Statistics The NEIS is a coordinated and collaborative effort to enhance reporting capacity of the Country. NEIS will be instrumental for the production of indicators that will be co-produced by across different entities in Haiti. This capacity will increase data coordination and quality with all the necessary characteristics and disaggregation. |
| --- | --- |

| Implementation Status | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR |  |  |

| Development Objective Rating FY | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | MS |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1 The project is expected to deliver some key products, which will produce a significant impact on the management of the environment in Haiti. - The first National Biodiversity Fund promotes a more sustainable and coordinated approach for mobilizing resources for protected areas in the country. - The National Environmental Information System is a key mechanism to support environmental data collection, management and sharing, policy, and decision-making processes, and environmental programs formulation. - The methodological guide for riverbank management and rehabilitation innovates reforestation techniques in Haiti, which sometimes even make use of invasive plants. Moreover, it will be a tool to reinforce capacity of the departmental directorates of the MOE. - The methodological guide for the Environmental Audits as well as the Methodological Guide for Coastal Zone Environmental Assessment will strengthen the Bureau National des Evaluations Environnementales (BNEE), a young structure which needs a set of tools to fully play its role of regulation and monitoring organism. - Through the production of the documentary on the Sea and the Rio Conventions, the Ministry of Environment will have access to a key tool to raise public awareness on mountain and coastal marine ecosystems, Rio conventions and conservations. Major challenges to achieve the key project products include: - The unstable political situation has an impact on the project implementation, notably because of the recurring changes in the Ministry's orientations. - The relatively weak technical capacity of the Observatoire National de l'Environnement et de la Vulnérabilité (ONEV) to manage the NEIS. - The technical capacity of the BNEE to operationalize the tools provided by the project is another potential challenge for the project. - The technical capacity of the Watershed and Forest Directorates to operationalize the tool provided by the project is also relatively weak. - Finally, the changes in strategic priorities within the government have led to re-consider significantly and several times the nature and the scope of the Action plan for the Environment. |  |  |  |  |  |

| Implementation Progress Rating | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | MS |  |  |
| - Background information / Brief Summary to date The Project was approved in May 2015 but started in Q1 2016 with the two main agreements signed to allow fund transfer and subsequent project execution by the two co-executing agencies. An Internal Cooperation Agreement (ICA) was signed in February 2016 between the Executing Agency (UN Environment /Ecosystems Division) and the Implementing Agency (UN Environment / Science Division), while a Project Cooperation Agreement PCA) was signed in March 2016 between the two co-executing agencies: UN Environment (Ecosystems Division) and the Ministry of Environment of Haiti. In addition, a third agreement was signed in June 2016 between UN Environment (Ecosystems Division) and UNDP to support the executing Agency (UN Environment) in project back office operations, logistics and procurement. The PMU was eventually fully operational as from June 2017, though at the beginning of January 2019 the Project Manager left. A new Project Manager has been contracted by the Executing Agency, who will commence his assignment in July 2019 All project activities have been eventually launched and some of them were successfully concluded (Methodological guidelines for environmental audits) or in the process of conclusion (methodological guidelines for riverbanks and littoral reforestation). However, mainly because of political instability, other activities are experiencing significant delays. Indeed, the 2018-2019 period has been dominated by the political uncertainty (and associated insecurity) characterized by demonstrations, unrests, strikes and changes at ministerial level which generated, among other issues, changes in the governance, and violence making difficult to conduct certain project activities and, notably, those related to government approval and including field trips. In fact, since the project launch, the period considered by the current PIR (July 2018 to June 2019) has been the most unstable. Months like July, October, November, February, March and June were the most hectic months including peaks of violence that prevented the staff from going to the office for several days. Such political instability, characterized by two governments in 1-year period, had significant impacts on the Ministry of Environment with changes of Ministers and Government staff at the highest level. In addition, in March 2019, the Prime Minister and his government has been impeached by the parliament. Since then, there is no formal government in charge in Haiti. The project was officially launched in September 2016. In preparation for the official launch, several meetings were held between the Ministry of Environment, UN Environment and other stakeholders, whose aim was to analyze the project scope (goal and activities) and discuss the execution details, potential partnerships and technical adjustments related to the evolving institutional reality of the environment sector in Haiti. During the period September - December 2016, the project incurred another unexpected slow down, whose main causes are listed below: - A category 4 Hurricane, named Matthew, severely hit the country in October 2016, at the very same time of the recruitment of the Project Manager. In this emergency situation, the Ministry of Environment and UN Environment, including the Project Manager, were fully involved in the execution of a Post Disaster Needs Assessment (PDNA). - A number of key changes in the leadership of the Ministry of Environment, including the change of the designated Project Director (Government Official – Director of ONEV) combined by the overwhelming 2016 post-disaster context, and the delay in the recruitment of the admin/financial assistant, which eventually led to a general lack of coordination and support from the Ministry. This said, some key activities were carried out during this hectic period as described below. The first semester of 2017 focused on strengthening project national ownership by articulating and grouping the 16 planned activities of the project into 8 main groups of activities (i.e. focusing on 8 key products expected from the project). A concept note / road map was prepared by the 2 co-executing Agencies for each of the 8 groups of activities. Each Concept Note clearly identifies synergies between the different grouped activities towards a common objective (in line with project outcomes and outputs), as well as the strategy and different phases, expected results and executing partners. The 8 groups of activities or key project products are: - National Fund for Protected Areas and Biodiversity - National Environmental Information System (NEIS) - National Environment Strategy and Coordination Mechanism - Capacity building program for MDE staff - Awareness Raising Program on a Ridge-to-Reef perspective - Environmental Audits & Strategic Environmental Assessments - Regulatory framework for coastal zone management - Guidance for riverbank strengthening via reforestation The first 5 groups support the implementation of the Rio conventions, while groups 6, 7 and 8 are enabling activities necessary to ensure sustainability for the Rio Conventions implementation. Objective and progress for each group of activities (key products) are summarized below and detailed in the corresponding tables of this PIR report (in line with project outcomes and outputs): 1.National Fund for Protected Areas and Biodiversity (Activities 7 & 8 contributing to Outcome 1 and output 1.3) Objective: Support the establishment of a Haitian Trust Fund for the conservation of biodiversity and Protected Areas. Progress: - July 2017-June 2018 PIR Report In December 2016, several meetings were held with partners in order to develop a common strategy to design a fiduciary fund for biodiversity in general and specifically for protected areas. The strategy, whose development involved the participation of multiple stakeholders, defines a clear role (technical and financial) for each partner in the development of the Fund. An official commission for the implementation of the Haitian Trust Fund was established in January 2017 by the Ministry of Environment. Activities already implemented by partners, including UN Environment, through their participation in the Commission include: - The implementation of the Trust Fund under the coordination of the Société Audubon Haiti (SAH), a civil society organism, which has also the mandate to elaborate an Action Plan (a draft is available). (Activities are financed by a UNDP project); - An international consultancy recruited by The Nature Conservancy (TNC) with the objective to ensure the successful set up of the national fund. The consultant had a first mission in Haiti in March 2017; - A national consultant recruited by UN Environment to elaborate legal documents for the structure of the National funds. The products have been already delivered; - The participation of the Commission’s coordinator along with the Ministry of Environment in the fifth annual meeting of the Caribbean Biodiversity Fund (CBF) and in the General meeting of the Caribbean Challenge Initiative (CCI) in June 2017 in order to (i) present the initiative for establishment of a Haitian Trust Fund for Biodiversity (ii) align the initiative with CBF requirement for potential matching funds, and (iii) connect with CBF donors, not necessarily active in Haiti. - A number of meetings held with potential financial partners by different members of the Commission. - July 2018-June 2019 PIR Report Some legal adjustments took place for finalization following discussions with partners and Haitian legal bodies. In Q3-4 2018, through co-funding from UN Environment/Norway, the following objectives were achieved: - Finalization of the legal status of the Foundation - A draft operational manual for the Foundation was produced by an international consultant, expert in trust funds, - A draft agreement of collaboration with The Nature Conservancy (with support from a UNEP/Norway project) to be finalized and implemented in 2019. This 18-month agreement plans to provide the following tools/support to the Foundation: Develop a Capacity Building Plan for HBF and implement year 1, Develop an integrated Strategic Plan, Develop a Communication Plan and produce a promotional video, Development a Resource Mobilization Strategy and support to secure initial capital for an endowment. On May 2019, the implementing Commission in charge of setting up the national Trust Fund called a meeting on the occasion of the official and legal creation of the Haitian Biodiversity Fund (HBF). Several partners including the Ministry of Environment, Société Audubon Haiti, UN Environment, The Nature Conservancy (TNC), the World Bank, Interamerican Development Bank (IDB), the Swiss Embassy in Haiti, the German Cooperation, UNDP, the French Development Agency (AFD) and JP-HRO contributed to the implementation of this initiative. Financial supports from Switzerland, Norway, UN Environment, UNDP, TNC, the Global Environment Facility and USAID contributed to the successful implementation of this process. At the occasion of the International Day for Biodiversity (22 May 2019), one of the major Haitian media reported about the creation of this innovative mechanism and quoted UN Environment Haiti www.lenational.org/link In June 2019, donors met in the frame of the annual meeting of the Caribbean Biodiversity Fund, with the participation of representatives of the Haitian Biodiversity Fund (HBF). On this occasion, the French Development Agency pledged for a financial commitment amounting to 13 million USD, in addition to the 10 million USD pledged earlier this semester by the German Development Bank (KFW). In Q1-Q2 2019, UN Environment started to develop the scope of work for a contract with The Nature Conservancy to further support the HBF through Norwegian funding (co-funding). UN Environment will provide support to the HBF foundational set-up through capacity building and assistance in the development/implementation of operational guidelines, strategies for investment, resource mobilization and communications. This contract will start in Q3 2019. Partners involved: Société Audubon Haiti, World Bank, The Nature Conservancy, France, Norway, GIZ, CBF, Ministry of Environment, JP HRO, UNDP, KFW 2. National Environmental Information System (Activities 6,10,11, 12 & 13 contributing to Outcomes 1 & 2 and outputs 1.2, 2.1 & 2.2) Objective: Set up an environmental information system that will be available through an online platform and managed by trained MoE staff. Progress: 2.1 July 2017-June 2018 PIR Report The National Environmental Information System (NEIS), considered as the project flagship, is guided, since Q4 2017, by a common multi-partner action plan developed and then validated by the Commission of implementation. The action plan has integrated relevant funded initiatives from various partners and the main progress made during this reporting period can be summarized as follows: - The technical implementation commission which support the development of the NEIS has already hold 3 meetings: - August 2017, to present and discuss the initiative of developing a National Environmental Information System to potential partners invited by the Ministry of Environment (MOE) to integrate the technical commission composed by: MOE with representation in various services, MARNDR, CNIGS, CIAT, IADB, WB, SAH; - November 2017, to validate the common multi-partners action plan whose elaboration was the main conclusion of the 1st meeting; - May 2018, to present the progress in the implementation of the action plan and the activities in synergy with the NEIS and to lead up to an overview of the orientation that will be given to the technical specifications document. The identification of environmental indicators (related to the Rio Conventions and SDGs) is the second step of the action plan after the establishment of the implementation commission. One of the activities in synergy with this stage, is the development of a system of indicators common to protected areas that is being implemented by ANAP with the support of IDB. A consultant team has been recruited for this purpose and has already realized a mission in Haiti and will provide, at the end of its work, a list of indicators that will be taken into account in the specifications document of the NEIS. An international firm responsible for the overall management of the NEIS development project and the drafting of the technical specifications document (including the identification of indicators) was recruited by UN Environment in Q2 2018. A first mission has already taken place in Haiti with the objective of establishing a first contact with partners and discussing the orientation of the technical specifications. The senior consultant has also participated in the 3rd meeting of the Implementation Commission. The technical specifications document will be finalized in September 2018. Several other activities initiated by technical partners are being carried out and the connections to be established between the NEIS and these initiatives are being considered to avoid any duplication in the collection and storage of data. 2.2 July 2018 -June 2019 PIR Report The international firm, responsible for the overall development of the NEIS structure, conducted 2 technical missions in Haiti in Q3-Q4 2018. In September 2018, the first mission aimed at conducting a series of consultations with the main actors involved in the implementation of the NEIS, including the members of the Implementation Commission on environmental indicators. In November 2018, the second mission included the organization of two workshops: a technical workshop with management and environmental information producers and a second workshop focusing on the list of indicators selected for the NEIS. Two meetings of the Implementation Committee for the NEIS took place in Q3 and Q4 2018 during the missions of the international consultant. The following deliverables have been submitted by the international consultant: (1) Identification of environmental indicators to be integrated in the NEIS; (2) Technical specifications for the implementation of the NEIS including the Terms of Reference for the system development phase. The list of identified indicators as key specific and common indicators of the 3 Rio Conventions has been validated by the Implementation Commission on Environmental Indicators. A draft agreement of the co-management mechanism proposed for the NEIS, which includes the MoE through ONEV, the Ministère de la Planification et de la Coopération Externe (MPCE) through the Centre National de l'Information Géo-Spatiale (CNIGS), the Ministère de l'Agriculture, des Ressources Naturelles et du Développement Rural (MARNDR) through the Coordination Nationale de la Sécurité Alimentaire (CNSA) / Unité HydroMétéorologique (UHM) for information sharing has been produced and it is in process of validation. The NEIS development phase, which includes the procurement of a firm for its implementation, was launched at the end of April 2019 by UNON in Nairobi HQ. The delay in the commencement of the process due to several back and forth and changes both in the clarification of specifications and in the final choice of the entity to lead the recruitment process. The PMU are currently awaiting proposals from pre-qualified firms and hope that the contract will be awarded by the end of August 2019, taking into account the procurement planning schedule provided by the Nairobi Office, which is responsible for the recruitment process. The next steps for the SIE are as follows: - Starting the process of designing and implementation of the system (involving the finalization of the above-mentioned procurement process and following steps) - The finalization of the System Governance protocol - The development and implementation of a capacity building plan for the Environmental information system. Partners involved: ONEV, MARNDR, MPCE, CNIGS, UNDP, World Bank, EU 3. National Environment Strategy and Coordination Mechanism for MEAs implementation (Activities 3 & 4 contributing to Outcome 1 and output 1.2) Objective: Provide the Ministry of Environment and its financial and technical partners with a strategic guidance document (Environmental Action Plan -PAE), useful for orienting their respective actions for the next five years, while structuring and mobilizing the Environmental Sectoral Table (TSE) as a coordination and monitoring mechanism of PAE implementation. Progress: 3.1 July 2017- June 2018 PIR Report In Q2 2017 a set of 3 workshops on the development of the Environmental Action Plan in order to collect information at the Provincial level on sectoral priorities and understand the structure of the TSE have been facilitated by the national expert recruited to support the Ministry of Environment in the development of the PAE. In Q4 2017, the MOE changed its strategies and decided to move towards the development of a three-year investment plan. Several meetings took place between the MOE and UN Environment in Q1 - Q2 2018 to define the strategy for developing this plan. A concept note has been developed and proposed by UN Environment. A retreat was organized by the senior management of the MOE during which discussions took place with the MOE technical staff on the axes and strategy for implementing the Investment Plan. A strategy has been defined for the formulation of a 3-year Investment Plan. It consists of recruiting a consultant who will work with the Minister office to develop a document according to guidelines already formulated in the concept note improved by the Minister office. This plan will be broken down into six priority programs to which specific projects will be linked. Those are: - The Coastal and Urban Resilience Program - The water and watershed management program - The national program of reforestation - The waste management program - The Biodiversity and Protected Areas Program - The governance program Until the investment plan is finalized, a group of technical and financial partners, coordinated by UN Environment, have come together to better organize and coordinate their interventions. 3.2 July 2018- June 2019 PIR Report Because of the political and institutional instability and changes of strategies of the Ministry of Environment, there is no meaningful progress to report on this activity for the reporting period. However, UN Environment had identified a strategy to ensure a minimum level of coordination among environmental actors operating in Haiti, while waiting for the national environment strategy to be elaborated by the MoE. Therefore, UN Environment facilitated creation of a Donor Group on environment in Haiti called Groupe Sectoriel Environnement (GSE) whose goal – besides coordinating actions- is to share best practices and to agree on an advocacy plan to support the Ministry’s action towards various priorities. One of them being the need for the Ministry to have a plan of action to guide partners and a related Table Sectorielle (coordination mechanism) to coordinate the actors around that plan. During Q4 2018, UN Environment was formally charged with the role of leading discussions with the GSE. In this context, a new strategy has been formulated by the Minister in order to move forward with the development of Triennial Strategy of Investment and the Environmental Action Plan (EAP). However, because of the political uncertainty the process is on hold pending the arrival of a new government. Partners involved: MDE, UNDP and most of the Donors operating in Haiti. 4. Capacity building program for MDE staff for the implementation of the Environmental strategy and the MEAs implementation (Activities 5 & 14 contributing to Outcomes 1 & 2 and outputs 1.2 & 2.2) Objective: Develop a MoE capacity building program through capacity needs assessment and targeted training for MoE officers to fully ensure the implementation/monitoring by MoE of the new Action Plan and Rio Conventions. Progress: 4.1 July 2017-June 2018 PIR Report The first stage of implementation of this group of activities is the inventory of the qualifications obtained and the training received, and an analysis of the capacities required by the various technical and administrative staff of the MOE. Terms of Reference have been developed and the recruitment process is being finalized. The inventory of the qualifications will focus on 2 priority activities: Capacity building program for the implementation of the Environmental Information System and the development of Guides and protocols for Environmental Audits. 4.2 July 2018-June 2019 PIR Report Following discussions with the MoE’s project director and in an effort to create more synergies and coherence between project activities, the project steering committee (held in November 2018) suggested that the training program should be focusing on 3 main activities of the project: (a) National Environmental Information System (NEIS): To develop a capacity building plan for management and utilization of the system, discussions have been held with the international firm responsible for the overall management and development of the NEIS to amend its current contract and include the development of the capacity building plan (this will be done once the no cost extension is done). (b) support to the Bureau National des Évaluations Environnementales (BNEE), through a training on the methodological guide of environmental audit. This was done in Q1 of 2019. (c) Methodological Guide for the natural protection of riverbanks: Once the guide is validated and political issues are solved, the departmental directors of the Ministry of Environment will be trained in Q3 2019 to implement the methodological guide for riverbank strengthening through reforestation in their respective departments. 5. Awareness Raising Program on a Ridge-to-Reef perspective related to the Rio Conventions (Activities 15 & 16 contributing to Outcome 2 and output 2.3) Objective: Raise awareness amid different actors at the national level (Government, Civil Society, Private Sector, Schools and Universities) on the challenges and opportunities offered by the Haitian coastline in terms of biodiversity, climate change, desertification and integrated coastal zone management through visual, written materials and public debates. Progress: 5.1 July 2017-June 2018 PIR Report Awareness Raising Program started in Q4 2017 with the agreed terms of reference and launch of a recruitment process for the development of a documentary related to the Rio Conventions with a focus on the Haitian coast – from ridge to reef. The recruitment process is being finalized: the firm has been identified; there remains only the contract to be issued by UNDP. In addition, at the decision of the MOE management, discussions were initiated with the biodiversity directorate to define strategic tools: - Biodiversity Awareness Posters; - Training for Journalisms to cover biodiversity issues in the media; - A coffee table book on the sacred trees. 5.2 July 2018-June 2019 PIR Report In Q3-Q4 2018, the script of the documentary (related to the Rio Conventions with a focus on the Haitian coast – from ridge to reef) has been finalized by a well-known Haitian writer and a movie maker, Gary Victor and Arnold Antonin. The different shooting areas along with a list of people to be interviewed has also been identified. Pre-shooting started and 2 missions were made respectively in the south and the north of the country. In spite of delays and other inconvenience due to the political situation, the shooting activities have been successfully carried out - including a joint mission with a team specialized in underwater and drone shooting). The script has been translated in two languages. The Narration (Voice off) is done by Gessica Généus, a well-known Haitian actress. The soundtrack production and the pre-editing of the film are underway, and a first version of the film has been completed and received from the director. Partners involved: MDE, Centre Simon Bolivar is the contractor of the various artists making the movie. 6. Support to development of Guides and protocols for Environmental Audits (Activity 9 contributing to Outcome 2 and output 2.1) Objective: Support the National Bureau for Environmental Assessment (BNEE) in the identification and formulation of missing specific critical reference guides for environmental assessments, as well as associated training. Progress: 6.1 July 2017-June 2018 PIR Report An adjustment had to be made to the reinforcement to be given to the BNEE according to the allocated budget. After a few discussions, the BNEE management opted for one of the guides proposed in 2017 and chose to draw up a methodological guide for environmental audit. The recruitment process was launched in Q4 2017 and finalized in Q1 2018. The Aube Nouvelle University of Burkina Faso was selected and a 1st mission took place in Haiti in April 2018. This 1st mission allowed to discuss with BNEE members on the orientation and methodology of work and to meet several other stakeholders. The mission report is already submitted to the project management unit. The methodology and rivers proposed by the consultant has been reviewed and validated by the Ministry of the Environment. Watershed Management Division in the MOE has been selected to host this activity. In addition to general guidelines to be developed for the audits, five thematic areas have been selected as priorities to be considered in the methodology: Mining and Quarrying, Chemical Industries, Coastal Infrastructure, Gas and Oil Installations and Solid Waste. 6.2 July 2018 – June 2019 PIR Report During the first semester of the fiscal year, the Aube Nouvelle University of Burkina Faso submitted a first draft of the deliverables, notably: one general guide and five specific guides defining the following priority sectors for the government: (1) Mines and quarries, (2) Construction of coastal infrastructure, (3) Site Management or Landfill Site, (4) Industrial pollution, (5) Management of gas stations and petroleum products. A second mission took place in Haiti in December 2018, which included meetings with the Bureau National des Evaluations Environnementales (BNEE) and several other stakeholders to validate the methodological guides. Some media coverage about the second mission and technical consultations are reported below: - Renforcement des capacités du Ministère de l’Environnement à mettre en œuvre les accords environnementaux multilatéraux : www.vantbefinfo.com/link - Auditer des interventions qui sont susceptibles d’avoir un impact sur l’environnement, une priorité du Ministère de l’Environnement : www.mde.gouv.ht/link During the second semester of 2018, all deliverables were submitted, validated and launched. A training activity for more than 30 people (with 40% of female participants) from private and public sectors was conducted by the consultants on the use of the methodology. A validation and launch activity coordinated by the Ministry of Environment has been done. During this launch, the Minister of Environment officially handed the document over to the director of the BNEE, the Ministry’s department responsible for all matters related to environmental assessments. Partners involved: BNEE 7. Support to development of regulatory framework for the management of the coastal zone (Activity 2 contributing to Outcome 1 and output 1.1) Objective: Support the Government in the establishment of a regulatory framework for Integrated Coastal Zone Management (ICZM) in Haiti, taking into consideration the issues related to biodiversity, climate change, and desertification. Progress: 7.1 July 2017-June 2018 PIR Report The MoE has engaged in the Haiti's accession to the Convention on Protection and Development of the Marine Environment of the Wider Caribbean Region or the Cartagena Convention, which is a regional legal agreement for the protection of the Caribbean Sea adopted in 1983 and entered in to force in 1986. The Convention is supported by three technical agreements or protocols: (a) Protocol Concerning Co-operation in Combating Oil Spills, (b) protocol concerning Specially Protected Areas and Wildlife (SPAW), and (c) the protocol concerning pollution from Land-Based Sources and Activities (LBS). - Advocacy with the government was undertaken by UN Environment and advocacy materials were produced for the MOE and the Council of Ministers including 2 documents justifying Haiti's interest in accessing SPAW and LBS; - The Executive Secretary of the Cartagena Protocol made a visit in Haiti in Q4 2017 and a presentation of this protocol and benefits for the country was made; - The Minister of the Environment also visited UNEA, in Q4 2017, where there was the symbolic signature of the protocols. An action plan for 1 year will be developed for its implementation in Haiti. This decision should be validated by the project director. 7.2 July 2018- June 2019 PIR Report This activity is on hold. In the framework of the Macaya Grand Sud Project funded by the Norwegian Government, the Intergovernmental Committee for Territorial Planning (CIAT) is in charge of developing a coastal law. A draft updated status document on regulatory and legal framework of Haiti coastline has been developed. With the aim of aligning this external project with this activity. It has been decided to wait until the work of CIAT is finalized. This delay affected the start and scope definition of this activity. Recently, in Q4 2018 the PMU received a formal request from the Minister of Environment to develop a guide for strategic environmental assessment for coastal areas, which is a missing tool to pave the way towards the definition of a sustainable coastal zone management framework. Terms of Reference for the development of this tool are already formulated and the process for a consultant recruitment will be launched as soon as a new government is in place. 8. Support to develop Strategic tools for riverbank management and restoration through reforestation (Activity 1 contributing to Outcome 1 and output 1.1) Objective: Provide Departmental Directions of MoE with a methodological tool that can be used in each Departments by MoE partners to sustainably reforest riverbanks, from the source to the mouth, and to reforest coastline. Progress: 8.1 July 2017-June 2018 PIR Report The recruitment process for the Development of a methodological guide for riverbank strengthening through reforestation was finalized in Q2 2018: A national consultant was recruited and has already provided a methodological document defining the general direction of work and presenting a list of rivers by department to be characterized. The Methodology rivers proposed by the consultant has been reviewed and validated by the Ministry of the Environment. Field missions have been undertaken. 8.2 July 2018-June 2019 PIR Report The consultant recruited in Q2 2018 for developing a methodological guide for riverbank strengthening through reforestation carried out a series of activities during the reporting period. A list of rivers (by Department) to be included in this activity has been finalized and validated by the Forest Division in the Ministry of Environment. Several field missions have been conducted aiming at characterizing prioritized riverbanks, to meet the actors who have undertaken reforestation activities on riverbanks and identify reforestation needs. In order to strengthen departmental directorates of the MOE, a few meetings were organized with the Departmental directors. After a consultation process which involved several actors from public and private sectors, the consultant provided all deliverables. A launch workshop and training session for the departmental directors will be held in the coming months (pending the political situation) to close this process. Partner involved: MDE and Departmental Directorate |  |  |  |  |  |

| Risk Rating | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | M | M | M |  |  |
| There has been no significant change since the previous reporting period. The project is still facing the same risk level that affect the execution of some key outputs. The political instability has worsened since June 2018 with two changes of Prime Minister (August 2018 and March 2019) and as of July 2019 no government has yet been installed. The political situation has aggravated the country's socio-economic and financial problems. This situation could lead to the departure of more Ministry staff abroad or accentuate the lack of motivation of personnel and thus, impact the appropriation and use of the capacity building tools elaborated by the project. |  |  |  |  |  |

| Stakeholder engagement | Stakeholder involvement has been secured through regular meetings with the senior management of the Ministry of Environment, focal points of the 3 Rio Conventions and the Project Director, as well as through the establishment of Implementation Commissions with the involvement of relevant partners for key product. Below is a list of a Stakeholders and their link to the outputs of the project. Project Steering Committee Members: - Ministère de l’Environnement (MDE) • ONU Environnement • Conseil Interministériel sur l’Aménagement du Territoire (CIAT) • Agence Nationale des Aires Protégées (ANAP) • Observatoire National de l’Environnement et de la Vulnérabilité (ONEV) • Programme des Nations Unies pour le Développement (PNUD) • Points focaux des Conventions des Nations Unies sur les changements climatiques (CCNUCC) de lutte contre la désertification (CNULCD) et sur la biodiversité (CBD) • La Société Audubon Haïti (SAH), la Direction des Ressources en Eau (DRE) National Commission for the establishment of the Haitian Trust Fund Société Audubon Haiti (SAH), Swiss Cooperation, The Nature Conservancy (TNC), World Bank, Agence Francaise de Développement, Norway Cooperation, GIZ, CBF, Ministry of Environment, JP HRO, UNDP, KFW Engagement: Provide data; Take part in consultations and identifying financial streams. Technical Commission for the implementation of the NEIS MoE through the following services, Ministère de la Planification et de la Coopération Externe (MPCE) through the Centre National de l'Information Géo-Spatiale (CNIGS), the Ministère de l'Agriculture, des Ressources Naturelles et du Développement Rural (MARNDR), Conseil Interministériel sur l’Aménagement du Territoire (CIAT), along with IADB, WB, SAH, UDP, EU Engagement: Providing data; Defining the protocols of the information system; Receiving training on how to input, collect and use environmental data; Extracting the necessary data and information Validation of methodological guides (environmental audits and riverbank strengthening through reforestation) BNEE, ONEV, Departmental Offices of MoE Engagement: Provide input into the consultations and development of the methodologies and tools for water source protection and integrated coastal zone management; Support the use and application of the tools and methodologies; Bring forth sector-based interests and considerations |
| --- | --- |

| Gender mainstreaming | The project addresses gender mainstreaming in the following ways: - The National Environmental Information’s System will be designed to ensure maximum use of available gender disaggregated data so as to obtain quantifiable metrics on the interrelationships between women and the environment (Output 3.1) The design and development of the NEIS included a series of consultation and workshops with main actors in order to identify environmental indicators and other key features of the system architecture. At this stage, participation of women was encouraged and their level of participation accounts to 15-30% in those meetings. - Public awareness campaigns will target women and explicitly include gender dimensions into awareness materials (Output 3.2) A documentary is currently in its final stage of production, whose aim is to raise awareness on the importance of the environment for the Haitian society through a ridge-to reef narrative related to the Rio Conventions. The script takes into account the gender dimensions and one of the narrators is also a well-known Haitian actress and an activist for gender equality in Haiti. - The cross-cutting methodological frameworks (Output 1) has integrated gender considerations The methodological guide for riverbank management and restoration through reforestation includes gender dimensions considering the labour-intensive characteristics of that type of activities. Also, the elaboration of the environmental audits guide ensured the implication of women in the discussions and workshops in order to integrate gender aspects in the final document. - the project will ensure inclusion and participation of women's organizations so as to ensure that women's relations to environmental management and stewardship are included in the information gathered The project team will reach out to major women’s Organizations in Haiti interested and active in gender dimensions and environment. |
| --- | --- |

| Knowledge activities and products | So far, the key knowledge products delivered through the project are as follows: - A Methodological Guide for Environmental Audits This Guide will help the BNEE to reduce negative impacts by projects and promote an environmental mainstreaming process across sector in Haiti. - A Methodological Guide for River Bank Management and Restoration through reforestation This Guide will support practical interventions at the local level namely the Departmental Directions of MoE, promoting sustainably reforestation of riverbanks, from the source to the mouth, including coastline, using native and, in some cases, endemic plants. - A Documentary related to Rio Conventions with a focus on the Haitian Coast – From ridge to reef. The documentary will be a key sensitization tool that will be used to raise public awareness on mountain and costal marine ecosystems, Rio Conventions and conservations in Haitian context. |
| --- | --- |

| Stories to be shared | A Documentary related to Rio Conventions with a focus on the Haitian Coast – From ridge to reef. The documentary aims to educate the general Haitian public on the challenges and issues related to the conservation of the marine environment by highlighting the Haitian relationship with the sea and the coast, as well as the links between degradation of mountain ecosystems and the sea, while highlighting the challenges and opportunities that this relationship offers to the country. This documentary takes into account certain important cultural traits such as certain religious beliefs, certain habits and customs, relations with the sea, the coast and the mountains and what they represent in the Haitian popular imagination. It deals fundamentally with the coastal-marine environment in relation to the mountain and aims to inform about the 3 Rio conventions: desertification, biodiversity and climate change and to raise awareness about the importance of biodiversity and the impacts of the degradation of the biodiversity, desertification and climate change. While showing the real problems, the shadows and the essential brakes, this documentary wants to bring a message of hope to the Haitians and to show the decision-makers and the potential investors the opportunities to seize. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective To enhance the capacities of GoH for environmental decision-making & implementation in line with national priorities (with an emphasis on cross-sectoral issues such as coastal zone management and the protection of water sources and riverbanks). | (Increase in) number of agencies & ministries making allowance for use of environmental information and project tools in decision-making and environmental management in line with MEA | Capacity Scorecard: 50 Limited capacity for consistent environmental management and cooperation among environmental authorities and line ministries. Ad hoc decision making between environmental authorities at state and entity levels. | Capacity Score card 60 by midpoint and 70 by endpoint | At least 5 organizations or institutes collaborate at central level and in each region of Haiti on environmental information management. At least 2 sectoral plans make reference to and/or adopt environmental information management tools promoted by the project. | A draft of a charter (MoU) to define roles and responsibilities of the 5 main institutions engaged in the designing and development of the NEIS has been produced and it’s currently under review. This will increase data coordination and data sharing among environmental authorities resulting in stronger collaboration and information management. 2 environmental management tools have been completed, while other 2 are currently being developed. - The methodological guide for riverbank strengthening through reforestation using native plants. - The methodological guide of the environmental audit - The methodological guide for management of the coastal zone - The Ministry of Environment’s triennial plan and associated coordination mechanisms | MS |
| Outcome 1: Enhanced institutional capacities to establish government structures for the effective implementation of international environmental conventions and environmental priorities | 1. Number of new and operational government structures; | ONEV, Table Sectorielle Environnement & the Conservatoire du Littoral are not yet fully operational, financially sustainable or able to develop plans policies and legal frameworks or enforce them for the effective implementation of the MEAs. |  | At least 2 frameworks, plan or policies, sustainable financing plan; enforcement training | The Haitian Biodiversity Fund is legally constituted and has already received pledges from donors. The French Development Agency has already pledged 13 million USD, in addition to the 10 million USD pledged earlier this semester by the German Development Bank (KFW) Through a co-financing mechanism of Norwegian Fund, a contract will be signed with The Nature Conservancy (TNC) to implement some key outcomes in the action plan. The activities related to the Table Sectorielle Environnementale are directly dependent on the Three-Year Investment Plan as an implementation strategy proposed by the MoE. Despite the difficult political situation, discussions are underway with the GoH for the orientation to be given to this plan. | S |
|  | 2. Number of newly trained staff | 96 staff | n/a | Ministry of Environment's enforcement capacity is visibly strengthened through (a) trainings of personnel; (b) human resources plan; (c) increased enforcement capacity | Training in environmental audits has been completed: 36 participants (40% female – 60% male) from main Haitian institutions attended the session Training in riverbank reforestation management is to be done at the end of Q3 2019 Training on the use of the NEIS will be provided once the system is fully operational- | S |
|  | - Number of i) tools, ii) methodologies and iii) frameworks established at national level for the effective implementation of international environmental conventions | There are currently no methodological frameworks on the protection of water sources and riverbanks | N/A | At least two frameworks, plans, or policies produced; Sustainable financing plan for environmental management is adopted | 2 methodologies have been produced and completed - The methodological guide for environmental audit - Methodological guide for riverbank management and restoration A third methodology related to the management of the coastal zone will be developed by a consultant to be recruited in Q4 2019 1 sustainable financing plan for environmental management adopted with the establishment of the HBF (Haiti Biodiversity Fund) within the larger framework of the Caribbean Biodiversity Fund (CBF) and pledges from donors. | S |
| Outcome 2: Institutions and stakeholders have access to the skills and knowledge to conduct research, collect information and implement collective environmental actions. | 1. Existence of mechanism to collect, share and disseminate environmental information | Environmental information system is not operational; | N/A | Fully operational Environmental Information System | The list of identified indicators has been validated by the Implementation Commission on Environmental Indicators. A draft agreement of the co-management mechanism proposed for the NEIS for information sharing has been produced and it is in process of validation. The development of the NEIS is entering its 2nd phase of implementation. Several meetings and workshops with relevant partners and national institutions were organized to identify a set of key indicators for Haiti to be included in the NEIS. The technical requirements for the designing and implementation of the system have been completed the procurement process to contract the firm responsible for the development of the NEIS is underway and is expected to start working by the end of Q3 2019. Several delays were experienced during the considered period. Main cause is to be attributed to the political instability, the long time required to hire a new PM, and the cumbersome and time-consuming process of the procurement, this latter managed by UNON. | MS |
|  | 2. Number of institutions and stakeholders registered to access the Environmental Information System | Environmental information is not collected or disseminated in a systematic or useable way | List of indicators, Technical specifications for the NEIS | Fully operational Environmental Information System | A technical commission comprised of national and international institutions with a mandate in data production and management has been established to support the development of the NEIS and maximize its future access and use. The technical commission has already held 3 meetings. The commission includes the MoE through ONEV, the Ministère de la Planification et de la Coopération Externe- MPCE (through the Centre National de l'Information Géo-Spatiale- CNIGS), the Ministère de l'Agriculture, des Ressources Naturelles et du Développement Rural- MARNDR (through the Coordination Nationale de la Sécurité Alimentaire -CNSA) and the Unité HydroMétéorologique (UHM), the Conseil Interministériel sur l’Aménagement du Territoire (CIAT), Société Audubon Haiti (SAH) along with international partners such as IADB, WB, UNDP, EU | MS |
|  | 3. Number of government agencies participating in the inter-ministerial coordination mechanism | There is currently no organizational mechanism that provides environmental management advice/guidance to inter-ministerial partners in a systematic way. | n/a | Fully operational inter-ministerial coordination mechanism that allows a flow of environmental information | A draft of Charter (Memorandum of Understanding MOU) has been shared with the different data producing partners in order to establish the sharing rules and the role of each in the process of governance, system management and continuous data analysis in the system. | MU |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating | FY2019 rating | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | During the considered period, the project has demonstrated its capacity to advance, though a slow pace, towards the achievement of the meeting project results. The PMU’s role in streamlining the project structure in an effort to maximize traction towards the delivery of key products paid off and some significant milestones have eventually been achieved. Over the last year a reasonable number of key products have been delivered, while others have been initiated or are now entering in their final stage of production (e.g. the NEIS and the Ridge-to-Reef documentary). However, the feeble political push received from the GOH due to the high political instability in the country, slowed up the timely progress of the activities towards the meeting of results. The establishment of MoU for enhanced data sharing and co-production of information is probably the most ambitious result expected from the project. Also, in this case, the impression is that the institutions involved in the project are fully aware of the importance of this outcome for the country and, in principle, they are in agreement with the goal of this activity. Nevertheless, the political vacuum produced by the changes in the GoH is hampering the rapid achievement of this result. The impression is that the project is undoubtedly advancing, though in a context of high political uncertainty and slow implementation rate. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | Political stability and situation: some key products are linked to the involvement of senior management at MoE, therefore changes and high turnovers at this level could impact the achievement of those targets. | Actions to carry out in order to reduce impacts of political instability: - Organize regularly, Steering committee meetings (at least 1/ year) and/or meetings with 3 Rio conventions focal points (1/quarter) and project director (1/ month); - Document each resolution taken and make reports available on time - Flexibility in the project activity planning However, this seems to be an unavoidable risk for Haiti. |
| on sustainability of results | Brain drain of staff and high turn-over in the Ministry senior management which can have a negative impact of the durability and the appropriation of the tools elaborated | Validate the list of trainees by the MoE (at senior management level) with commitment to keep the trained staff to the possible extent. |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implementation status as of 30 June 2018 | Implementation status as of 30 June 2019) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| (copy & paste from approved Results Framework) Output 1.1: A set of methodologies and practical tools developed for at least two priority cross-cutting environmental issues for the country |  | 50 % | 70 % |  | MS |
| Activity 1: On the basis of the experience developed in the South, to develop a National Methodological Guide for the natural protection of riverbanks, springs and the coastline through the targeted reforestation of native and / or non-invasive species. | September 2019 | Some main activities were carried out for the Development of a methodological guide for riverbank strengthening through reforestation during this reporting period: Validation of the terms of reference by two main divisions in the Ministry of Environment: Forest division and Watershed management and Marine Coastal Zone division; Recruitment of a national consultant: the process for the Development of a methodological guide for riverbank strengthening through reforestation was finalized in Q2 2018 Development of a methodological document defining the general direction of work and presenting a list of rivers by department to be characterized. Field missions to characterize riverbanks and identify reforestation needs are being undertaken. Progress level: 35% | A Meeting was organized with the Ministry of Environment for Methodology approval; A field trip was organized and meetings with national stakeholders were held to identify and characterize the rivers where the methodology would be applied. A review document on the experiences carried out in terms of riverbanks reforestation in Haiti has been produced. Production of a draft Guide on the methodological guide (including draft awareness-raising material) Progress level: 95% |  | MS |
| Activity 2: On the basis of the work undertaken to develop a coastal law, support the formulation of a methodological guide for Coastal Zone Environmental Assessment. | June 2020 | In the framework of the Macaya Grand Sud Project funded by the Norwegian Government, under the direction of the Intergovernmental Committee for Territorial Planning (CIAT), some progress has been made in the development of the coastal law. However, the MoE has engaged in the Haiti's accession to the Convention on Protection and Development of the Marine Environment of the Wider Caribbean Region: - Advocacy with the government was undertaken by UN Environment and advocacy materials were produced for the MOE and the Council of Ministers including 2 documents justifying Haiti's interest in accessing SPAW and LBS; - The Executive Secretary of the Cartagena Protocol made a visit in Haiti in Q4 2017 and a presentation of this protocol and benefits for the country was made; - The Minister of the Environment also visited UNEA, in Q4 2017, where there was the symbolic signature of the protocols. An action plan for 1 year will be developed for its implementation in Haiti. Progress level: 10% | As a result of extensive consultation with the Ministry of Environment, the PMU was asked to work on the development of a methodological guide for coastal zone environmental assessment. The ToRs have been drafted but the activity is on hold waiting for the appointment of a new government responsible for the recruitment of a consultant to implement this activity. Progress level: 15% | The political instability has delayed the recruitment process of the consultant to produce the management tool for coastal zone assessment. | MS |
| Output 1.2: Ministry of Environment has the legal, planning, strategic and human resources available at central and department levels to implement and enforce environmental laws and policies |  | 20% | 30% |  | MS |
| Activity 3: Support the MoE in the designing of an environmental governance roadmap to better integrate multilateral conventions and the development of a new Plan d’Action pour l’Environnement (PAE) that will guide the operation of the theTable Sectorielle Environnement (TSE). The PAE will consider the post-Matthew situation. | March 2020 | From Q3 to Q4 2017, several activities were carried out in order to develop the Environmental Action Plan 2018-2023: -The report of the internal MoE four days’ workshop held in June 2017 has been prepared by the consultant; - The first set of workshops to start the elaboration of the national environmental plan and adjust coordination mechanism for implementation took place; As mentioned in the Half Yearly Progress report July-December 2017, this activity had completed at a rate of 40% of its execution. Unfortunately, the ministerial strategy has changed and since Q1 2018, some discussions were held with MOE senior management to clearly identify the new strategy and the implementation plan for the three-year investment plan. Under these new changes, a concept note has been developed by UN Environment. A mini retreat was organized by the senior management of the MOE during which discussions took place with the MOE technical staff on the scope and strategy for implementing the Investment Plan. Then, based on the concept note, a strategy has been defined for the formulation of a Three-year Investment Plan. It consists of recruiting a consultant who will work with the Minister office to develop a document according to guidelines already formulated in the concept note improved by the Minister office. This plan will be broken down into six priority programs to which specific projects will be linked. Those are: - The Coastal and Urban Resilience Program - The water and watershed management program - The national program of reforestation - The waste management program - The Biodiversity and Protected Areas Program - The governance programs In addition, an amendment is in progress to favor the consulting firm contracted to use the remaining funds for the new strategy in a cordial agreement with the previous firm that was responsible for developing the Environmental Action and three-year investment Plan. On the other hand, until the investment plan is finalized, a group of technical and financial partners, coordinated by UN Environment, have come together to better organize and coordinate their interventions. NB: Activities 3 (Environmental Action Plan development) and 4 (Coordination/Monitoring mechanism for Action Plan implementation) have been grouped to increase in synergy and coherence. Progress level: 20% | A new direction has been identified by the Ministry of Environment for the formulation of the PAE Triennial Strategic Plan. Therefore, new TORs have been developed and meetings with donors and technical partners was organized from Q1 2019 Progress level: 20% | The political instability and relative institutional weakness of the Ministry of the Environment have greatly affected the implementation of this activity. Indeed, the changes in strategic priorities within the government had a significant impact on the nature and the scope of the PAE. The lack of clear direction, related to this activity have caused delays and, overall, significant uncertainty still remains regarding the future of this activity. | MU |
| Activity 4: Develop and validate, through a participatory approach, the structure and functioning of the Table Sectorielle Environnement (TSE). At the departmental level, the TSE will help coordinate post-Matthew recovery. | March 2020 | Discussions with the MOE must also make it possible to decide on the Sectoral Table Environment. However, Until the Table Sectorielle Environnement is implemented, a group of technical and financial partners, have come together to better organize and coordinate their interventions, exchange project information in common, create synergies and formulate joint advocacy points. Progress level: 5% | The commencement of this activity is strictly related to the formulation of the PAE and the Triennial Strategic Plan development. As a propaedeutical activity, a sectorial Environment Group which includes donors and technical partners has been established. Progress level: 5% | The restructuring of the Sectorial Environment Table (TSE), also depends on the MoE’s Triennial investment plan which has been delayed as well. | MS/MU |
| Activity 5: Based on the development of the PAE (activity 3) and on the basis of the assessment of training capacities and needs (Activity 14). Develop and implement a targeted training program: biodiversity training (one of the Rio conventions), Integrated coastal management and environmental geographic information system, Provide monitoring / follow-up tools related to training | August 2020 | The training program depends on 1) the inventory and capacity assessment needs (activity 14) et on 2) the main targets of the training program. NB: Activity 5 (targeted training program) and 14 (inventory and capacity assessment needs) have been grouped to increase in synergy and coherence. Progress level: 0% | Three main areas related to the project deliverables have been identified to carry out the trainings: NEIS, Methodological Guide on riverbanks reforestation and Methodological guide on Environmental audit. In Q1 2019, training on Methodological Audit guide has been done for national public and private sectors stakeholders Progress level: 30% | The training on the NEIS is closely related to development pace of the system which have experienced delays in its implementation. | MS |
| Activity 6: Strengthen the ANAP to feed the SNIE (linked to activity 13). | June 2020 | ANAP is a member of the Implementation Commission of the Environmental Information System that will be developed. Some progress has been made: - ANAP, in synergy with the NEIS initiative, is developing a system of indicators common to protected areas. A consultant team has been recruited for this purpose and has already realized a field mission in Haiti and will provide, at the end of its work, a list of indicators that will be taken into account in the specifications document of the NEIS. - An international firm responsible for the overall management of the NEIS development project and the drafting of the technical specifications document (including the identification of indicators) was recruited by UN Environment in Q2 2018. A first field mission has already taken place in Haiti with the objective of establishing a first contact with partners and discussing the orientation of the technical specifications. The senior consultant has also participated in the 3rd meeting of the Implementation Commission. NB: Activities 6, 10, 11, 12 and 13 have been grouped to increase in synergy and coherence Progress level: 25% | ANAP is participating actively in the implementation commission of the NEIS - The first milestone (Cahier des Charges) has been submitted in Q4 2018 - TOR to build the system, approved by all the stakeholders has been elaborated - Call for proposal to develop the system has been issued The international firm, responsible for the overall development of the NEIS structure, conducted 2 technical missions in Haiti in Q3-Q4 2018: - September 2018: The objective of this mission was to conduct a series of consultations with the main actors, members of the Implementation Commission on environmental indicators to be included in the EIS; - November 2018: This mission consisted in holding two workshops: a technical workshop with management and environmental information producers and a second workshop presenting the list of indicators selected for the EIS. Two meetings of the Implementation Committee for the National Environmental Information System (NEIS) took place in Q3 and Q4 2018 during the missions of the international consultant. Based on the common action plan, the following deliverables have been submitted by the international consultant: - Identification of environmental indicators to integrate in the SIE; - The document of technical specifications for the implementation of the Environmental Information System including the Terms of Reference for the system development phase. A draft of agreement on the co-management mechanism of the NEIS by the MoE through the Observatoire National de l'Environnement et de la Vulnerabilité (ONEV), the Ministère de la Planification et de la Coopération Externe (MPCE) through the Centre National de l'Information Géo-Spatiale (CNIGS), the Ministère de l'Agriculture, des Ressources Naturelles et du Développement Rural (MARNDR) through the Coordination Nationale de la Securité Alimentaire (CNSA) / Unité HydroMétéorologique (UHM) for information sharing has been produced and is in progress of validation by the actors concerned. Progress level: 35% | Delays in the NEIS development and absence of legitimate government since March 2019 have slowed down the validation process of the MoU. | S |
| Output 1.3: Sustainable financing mechanisms developed by strengthening capacities at central government level |  | 40% | 90% |  | S |
| Activity 7: Exploratory mission and feasibility study for the establishment of a fiduciary fund for the conservation of protected areas in Haiti (as a contribution to the Fonds De Recapitalisation Des Entreprises Haïtiennes, FREH). | June 2020 | UN Environment co-coordinates the implementation process of Fonds Haïtien pour la Biodiversité (FHB) with SAH. During this reporting period, some activities are already implemented by UN Environment and partners: - In agreement with the different partners, a contract has been signed between SAH and Swiss cooperation to coordinate the implementation process of the FHB and to implement all activities in the common action plan for 2018, in particular the specific requirements for FHB to integrate CBF. It’s noted that the coordination is engaged for 2018 until the official creation of FHB (when legal process is completely done), as it was previously mentioned in the legal status document, an Administration Council is elected during a general Assembly, some operational documents to guide the work of the FHB are elaborated and validated. Once all this will be achieved, the executive direction will be put in place through a transparent recruitment process and will relay to the coordination. - The Nature Conservancy (TNC) support for an international expert to follow up and guide the whole process has been extended for a second period. His TORs have been revised to better respond to the needs of the National Commission, another expert has been recruited and contributed since Q2 2018 to the implementation of the common action plan through regular interactions with the coordinator of the National Commission and to the elaboration of TORs for each recruitment planned. The consultant will have a first mission in Haiti in Q3 2018. - With partial financial support of UN environment, several members of the National Commission have participated to the annual meeting of the Caribbean Biodiversity Fund (CBF) and the Caribbean Challenge Initiative (CCI) that have been held in 18th to 22th of June 2018 in Miami. This 3rd CCI-CBF Week includes three key parts: (i) the CBF Annual Meeting; (ii) the CCI-CBF Finance Solutions Roundtable; and (iii) a workshop for Caribbean National Conservation Trust Funds. At this meeting, discussions are underway to develop a joint UN Environment-TNC initiative to formulate a capacity plan for FHB and implement it. - The by-law is a required document to complete the legal status for the FHB and to guide its regulations. Through the coordination of the National Commission and with the support of Swiss Cooperation, the by-law is being elaborated by a national consultant. It will be discussed and revised for validation in the current period. NB: Activities 7 and 8 have been grouped to increase in synergy and coherence. Progress level: 40 % | The main activities implemented for the FY 2018-2019 are as follows: - The Foundation is legally created in Q2 2019 - The legal status of the Foundation has been finalized - An operational manual for the Foundation was produced by an international consultant, expert in trust funds, - An agreement of collaboration with The Nature Conservancy (under a UNEP/Norway project) was finalized in Q2 2019 and it’s currently under implementation. This 18-month agreement plans to provide the following tools/support to the Foundation: - Develop a Capacity Building Plan for HBF and implement year 1, - Develop an integrated Strategic Plan, - Develop a Communication Plan and produce a promotional video, - Development a Resource Mobilization Strategy and support to secure initial capital for an endowment. - Resources mobilization have been done and funds from AFD (Agence Francaise de Développement), KFW and World Bank have been secured Progress level: 90% |  | S |
| Activity 8: Development of the Financial Mechanism for the Conservation of Protected Areas in Haiti (Trust Fund). |  | See Activity 7 Progress level: 40 % | See Activity 7 Progress level: 90% |  | S |
| Output 2.1: An operational environmental system is established and managed through institutional arrangements agreed between key stakeholders (including government agencies and research institutes and universities prioritizing South- South cooperation) |  | 45 % | 100% |  | S |
| Activity 9: In order to contribute to the environmental information system (production and exchange of information) and in support of the BNEE and the priority UTES, identify and formulate the specific critical reference guides for carrying out socio-environmental impact assessment, Level of the coastal zone (development of infrastructure and economic activities along the coast). N.B. This work involves both guides to be developed and existing guides to be completed. | August 2020 | An adjustment had to be made to the reinforcement to be provided to the BNEE in term of allocated budget. After a few discussions, the BNEE management opted for one of the guides proposed in 2017 and chose to draw up a methodological guide for environmental audit. The recruitment process was launched in Q4 2017 and finalized in Q1 2018. The Aube Nouvelle University of Burkina Faso was selected and a 1st mission took place in Haiti from April 15 to 22 of 2018. This 1st mission allowed to discuss with BNEE members on the orientation and methodology of work and to meet several other stakeholders. The mission report is already submitted and validated by the project management unit. Progress level: 45% | This activity relates to the development of a methodological guide for environmental Audit that has been completed in Q1 2019. The main products provided are: - A general methodological guide for environmental audit - 5 methodological audit guides for the following sectors: Waste, mines, Oils and Gas, Industries and Coastal infrastructures - Case study and training for public and private sectors staff in particular for BNEE staff Progress level: 100% | Fully implemented | S |
| Output 2.2: Haiti´s environmental information is available users on an open platform, in French and Creole |  | 25% | 40% |  | MS |
| Activity 10: Identify and evaluate the feasibility for considering key specifics and commons indicators of the 3 Rio Conventions in order to feed the National Environmental Information System | August 2020 | ANAP, in synergy with the NEIS initiative, is being developed a system of indicators common to protected areas. A consultant team has been recruited for this purpose and has already realized a field mission in Haiti and will provide, at the end of its work, a list of indicators that will be taken into account in the specifications document of the NEIS. An international firm responsible for the overall management of the NEIS development project and the drafting of the technical specifications document (including the identification of indicators) was recruited by UN Environment in Q2 2018. Progress level: 30% | A series of consultations has been organized and coordinated by the International Firm in order to identify the key indicators to be considered for the NEIS. The list has been validated by the Technical Implementation Commission on environmental indicators and a final list of indicators have been included in the TORs of the firm that will be contracted for the development of the system. Additional activities are being conducted by other institutions: - Identification of environmental indicators related to protected areas (Consultant to be hired by IDB). The list is being finalized and validated; - Identification of environmental indicators related to climate change (Process conducted by Climate Change Division of MoE). The system of common indicators for protected areas is still under development. This process is conducted by ANAP. Progress level: 100% |  | MS |
| Activity 11: Train the 3 Rio Conventions Focal points/Entities as well as the functional UTES in collecting, analyzing information on MEAs’ indicators as identified in activity 10: Biodiversity, Desertification and Climate change (linked to Activity 10) | August 2020 | See Activities 6, 10, 12, 13. Training is the fourth phase of the environmental information system action plan. However, the inventory of the qualifications obtained, and training received by MOE staff, for which the process recruitment is finalizing, will take into consideration the capacities required to manage the Environmental information System. Progress level: 0% | See Activities 6, 10, 12, 13. Training is the fourth phase of the environmental information system action plan. A consensus has been found to focus the training on three main areas: the NEIS, the Methodological guide for environmental audit and the Methodological guide for riverbanks reforestation. Progress level: 0% |  | MS |
| Activity 12: Create a team within the ONEV as part of the implementation of the Environmental Information System. | June 2020 | See activities 6, 10, 11 & 13. Training is the fourth phase of the environmental information system action plan. However, the inventory of the qualifications obtained, and training received by MOE staff, for which the process recruitment is finalizing, will take into consideration the capacities required to manage the Environmental information System. Progress level: 0% | See activities 6, 10, 11 & 13. Training is the fourth phase of the environmental information system action plan. Progress level: 0% |  | MS |
| Activity 13: Develop and implement a National Geographic Environmental Information System (Système National d'Information Géographique Environnementale, SNIGE) through an open, dynamic, online platform. | August 2020 | See activities 6, 10, 11 & 12. The NEIS, considered as the project flagship, is guided, since Q4 2017, by a common multi-partner action plan developed and then validated by the Commission of implementation composed by: MOE with representation in various services, MARNDR, CNIGS, CIAT, IADB, WB, SAH. Four phases of implementation have been defined in the action plan: - Identification of indicators; - Development of the specifications; - Development of the SIE; - Training. The action plan has integrated relevant funded initiatives from various partners and the main progress made during this reporting period is the recruitment of an international firm by UN Environment in Q2 2018. Indeed, this firm is responsible for the overall management of the NEIS development project and the drafting of the technical specifications document (including the identification of indicators). A first mission has already taken place in Haiti with the objective of establishing a first contact with partners and discussing the orientation of the technical specifications. The senior consultant has also participated in the 3rd meeting of the Implementation Commission. The technical specifications document will be finalized in September 2018 and the system will be operational in June 2019. Progress level: 25 % | The following deliverables have been submitted by the international consultant: -Identification of environmental indicators to integrate in the NEIS; -The document of technical specifications for the implementation of the Environmental Information System included Terms of Reference for the IT development phase. Progress level: 50 % | Procurement process for the designing and development of NEIS (Phase 3) still ongoing. Expected commencement of the Phase Q3 2019 | MS |
| Activity 14: In conjunction with Activity 5 (Governance), and on the basis of the existing staff at the MoE, make an inventory of the qualifications obtained and the training received and an analysis of the capacities required to implement the Environmental Action Plan and manage the Environmental information System. |  | In order to conduct the inventory of the qualifications and training received by the MOE staff: Terms of Reference have been developed and the recruitment process is being finalized. Progress level: 20% | A consensus has been reached to focus the training on three main areas: the NEIS, the Methodological guide for environmental audit and the Methodological guide for riverbanks reforestation Progress level: 20% | Procurement process for the designing and development of NEIS (Phase 3) still ongoing. Expected commencement of the Phase Q3 2019. Therefore, the training will take place once the NEIS is operational. For the riverbanks training, it is expected to take place after the summer holidays to ensure broad participation from Haitian entities. | S |
| Output 2.3: Public awareness and environmental information program is deployed |  | 30% | 75% |  | S |
| Activity 15: Develop and implement an awareness campaign (brochure and presentation to different groups) on the Rio Convention through the lens of Ridge to Reef perspective for decision makers, parliamentarians, the private and public sector, NGOs, national and international organizations and donors. | June 2020 | The following activities were carried out: - Awareness Raising Program started in Q4 2017 with the agreed terms of reference and launch of a recruitment process for the development of a documentary related to the Rio Conventions with a focus on the Haitian coast – from ridge to reef. - The recruitment process is being finalized: The firm has been identified; it remains only the contracted to be issued by UNDP. - The proposed firm is Haitian, with a director well known internationally in the world of cinema, Arnold Antonin. After several discussion meetings with the director, a scoping note was drawn up in Q1 2018 outlining the different themes that will be discussed. In addition, at the decision of the MOE management, discussions were initiated with the biodiversity directorate to define strategic tools: - Biodiversity Awareness Posters; - Training for Journalists to cover Biodiversity in the national media; - A coffee table book on the sacred trees. Progress level: 25% | See activity 16 Progress level: 50% |  | S |
| Activity 16: To develop a series of videos related to the marine and coastal zone in the context of climate change, biodiversity and desertification (the three Rio conventions) with a dissemination and debate campaign involving decision makers, parliamentarians, private sector, general public, NGOs, national and international organizations and donors. This activity will contribute to the World Environment Day’s events. | November 2019 | See activity 15 (under output 2.3) A documentary related to the Rio Conventions with a focus on the Haitian coast is being developed and the recruitment process is launched since Q4 2017. The recruitment process is being finalized: The firm has been identified; There remains only the contract to be issued by UNDP. Progress level: 5% | In FY 2018-2019, the following activities have been developed: -A film-maker organization directed by an internationally recognized director, Arnold Antonin, has been recruited to produce a documentary related to the Rio Conventions with a focus on the Haitian coast – from ridge to reef and conduct the whole film production process; -The narrative scenario of the documentary has been elaborated by a famous Haitian writer and scenarist, Gary Victor; -The different shooting areas have been identified and a list of people to be interviewed has also been identified. Pre-shooting started and 2 missions were made respectively in the south and the north of the country. - Pre-shooting activity in the identified areas have been done - Shooting activities are completed - The film narration (Voice off) done by a Haitian actress (Gessica Geneus) is finalized - The first version of the film music done by a Haitian singer (BIC) has been submitted Progress level: 75% | First version of the documentary has been submitted and now being validated by relevant stakeholders | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating | FY2019 rating | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | The many delays that had occurred since the very beginning of the project, mainly related to the high political instability, in addition to its intrinsic cumbersome structure (2 executing agencies a PCA + ICA), and some unforeseen events (resignation of the PM, extreme weather events striking Haiti) had forced the PMU to request an extension of the project duration, which is now expected to come to an end by August 2021. Even so, during the considered period the project implementation has markedly improved, albeit at a quite reduced pace. Main milestones achieved by the project in FY2019 included: - Progress in the definition of the architecture and legal framework for the establishment of a NEIS, whose design and operational implementation should begin by Q3 2019 ; - the legal establishment of the Haitian Biodiversity Fund and the formation of a General Assembly of the Fund who already elected the President and the Treasurer; - the successful completion of the technical Guide for the management and restoration of riverbanks - the production of a first complete version of the documentary on the Sea and the Rio Conventions, as a key communication tool to spread the key principles of the 3 considered MEAs to a broad audience of stakeholders and the civil society. The successful completion of some activities included in the Work Plan, such as the formulation of the Plan d’Action Environnementale along with the formulation of the Triennial Strategic Plan and the adoption of the Policy tool for coastal governance would require a dramatic and positive change in the way the GoH participate and interact in the project implementation. For this change to take place, the country should enter in a new and more stable political situation, which as of today seems far from being reached. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc.).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Political influences: Changes in the government and political instability could affect at any time the project. | Support the active participation of the MoE technical units, the Rio Conventions Focal points as well as civil society stakeholders in the project activities planning | Project Implementation Unit, ONEV | September 2019 |
| Political stability: Political situation can change at any time and could affect the project. | Enhanced participation of MoE and more flexible planning will allow the project to face political situation | Project Implementation Unit | September 2019 |
| Capacity issues: Technical capacity of the partners is weak and has been recognized at the design stage of the project. | Regular meetings to update all partners involved in the project implementation will allow them to have a better understanding of their role and to enhance their participation in the activities | Project Implementation Unit | From July 2019 |

3.3. Risk Rating [Insert the Medium and High Risks and mitigation measures identified at CEO endorsement (e.g. Section A.5) and any relevant risk from safeguards screening and/or management plans.]  Expand the table to include medium and high risks observed during implementation, e.g. problems identified in sections 3.1. and 3.2.

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Lack of political will to support project | This project has been identified as a priority and there are expectations for proper environmental governance in Haiti, both from central and local authorities. However, it will be important to modify the prevailing perception within government that environment should always take a back seat to more important issues, such as the poverty reduction and health care. Haiti’s government recognizes that global environmental benefits are an underlying asset of national priorities. The project will address this through public awareness activities carried out under Output 2.3 which include the training of politicians, policymakers and local-level actors. These activities will include linkages between environmental protection and livelihoods. | Regular meetings including those with the senior management of the Ministry of Environment to explain the aim of the project has allowed the project to have the needed political support | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM:M |
| Potential resistance, and lack of coordination from institutions that prevents implementation of required political reforms | There is limited sharing of information or collaboration among ministries and agencies in Haiti and a great deal of competition over resources. This is particularly evident in the environment sector due to the relatively little understanding of the linkages between environmental protection and the development sectors. The consultations undertaken to develop the project and the involvement of diversified stakeholders will minimize this risk. Structures will also be established (Table Sectorielle, COTIME, UTES) as part of project activities which will enhance collaboration and coordination. Procedures, mandates, and protocols will be established through participatory processes to enhance coordination. Clear project management arrangements, participatory and transparent project implementation will mitigate against this risk. A coordination mechanism will be created to bring together all stakeholders at central and local level. | Regular meetings for activities planning and updates on the project progress with the steering committee has contributed to reduce potential resistance to the project. In addition, for several activities, multi-institutional commission has been created to reduce and mitigate the lack of coordination. | CEO: H |
|  |  |  | TM: H |
|  |  |  | PM:H |
| Political instability | There is a risk that due to ongoing political instability, the project could experience delays. The project will carefully monitor the political situation and will ensure that the capacity for delivering the project is built at multiple levels in order to avoid delays. Should the need arise, direct execution of some project elements by UNEP may be explored in discussions with relevant government | The project has monitored the political situation to anticipate some issues and reduce the delays. | CEO: M-H |
|  |  |  | TM: M |
|  |  |  | PM: H M |
| Limited capacity to effectively tackle all project components | Establishing a robust multi-disciplinary project implementation team supported with additional training if necessary, will help mitigate against this risk. Targeted capacity building will be delivered at central and local level when project starts. | To carry out the project, in addition to the core team, there is a multi-disciplinary project implementation team including UN Environment and Ministry of Environment staff who support project activities | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: H M |
| Extreme weather events | Haiti is subject to extreme weather events and as the 2010 earthquake reminded it, projects can be disrupted by such events. In such a case, coordination will be undertaken with partners in order to ensure the response is effective and relief interventions are in line with project’s outcomes. | Strong coordination mechanism with key partners and stakeholders has been created to deal with any extreme weather event. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM:M |
| Risk of corruption | Corruption is identified as a medium risk in project implementation. Project implementation design will include an approach to manage risk of corruption; alliances will be sought with lead anti-corruption agencies. The project will also seek guidelines on anti-corruption measures from the Supreme Audit Institution to ensure that the project is well aligned with national initiatives to promote accountability and decrease corruption. Persons implementing activities will be assured a regular and consistent salary. This will be taken account in all phases of project implementation. Furthermore, other strategies to avoid corruption will be adopted, such as: - Co-location of government and project premises where possible to enable constant contact and oversight. - Project jointly designed with Government of Haiti and government capacity building budgets are integrated into the project. UNEP staff time will focus on support and relationship management to ensure counterparts deliver on obligations. UNEP will also participate actively in Government led planning and coordination mechanisms | By strictly applying UN and Haitian government procurement procedures, risk of corruption has been reduced. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

| FY2018 rating | FY2019 rating | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| M | M | The project ‘s rate remains set to Modest. While the PMU doesn’t have any control on the main source of risk, i.e. the political instability of the country, significative progress has been marked to reduce other sources of risk, including enhancing coordination among institution, increasing technical collaboration and institutional dialogue and reinforcing the capacity of the MoE, especially those related to data production in the context of the establishment of the NEIS |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Optional Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Half yearly Report

- Quarterly Reports

- Risk Factor Table form previous template (recommended for substantial and high-risk projects)

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right-hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | x |  |  |  |  |  | PM: Each group clearly understood its role and responsibility. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR |  | x |  |  |  |  | PM: SC meetings should be focusing on the activities currently under implementation and those one which are pending political decision. The next SC will be in September 2019. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | x |  |  |  |  |  | PM: There is good relationship between project staff members. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: the TM has promoted open door policy and frequent communication between PMU and TM unit. More than 50 teleconferences and weekly written communication have been provided during the current period to ensure smooth implementation of the project, especially for financial reporting. |  |  |  |  |  |  |
| Workflow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | x |  |  |  |  | PM: Due to political issues mainly political instability and changes at government level, there were some delays in the implementation of some activities. This situation caused some delays in the implementation of the project. A non-cost extension has been requested to finalize those activities. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Political issues have complicated the implementation of some activities; however, the PMU has been implementing as much outputs as possible in joint collaboration with other partners from different agencies which has smoothed down conflicts. |  |  |  |  |  |  |
| Co-financing | Co-financing is secured, and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | x |  |  |  |  | PM: Additional funds such as Norwegian funds support the implementation of some project activities |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: there are no conflicts to report in this aspect. |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget | x |  |  |  |  |  | PM: Since the budget revision was approved, there haven’t been changes in the budget which is progressing as planned. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: there is a new budget that was recently approved including the workplan |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | x |  |  |  |  |  | PM: For the 2018-2019 FY, funds from both UN Environment and the Ministry of Environment accounts are correctly managed. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting | x |  |  |  |  |  | PM: Since Q3 2017, all the reports are submitted on time. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: All reports have been submitted on time. |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seem strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | x |  |  |  |  |  | PM: With regular meetings both with the senior management of the Ministry of Environment, the 3 Rio Conventions the focal points and the project director as well as the establishment of Implementation Commissions with the relevant partners for key product, stakeholder involvement has been part of the implementation process. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Several coordination meetings have promoted stakeholder’s involvement, in an effort to get a high representation of key actors. |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident | x |  |  |  |  |  | PM: Several meetings done with stakeholders by the Project Manager and the implementation commissions have facilitated a better understanding of the project and its key products. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Since the project started several communications through different channels have taken place, however it is still necessary to disseminate to different audiences the importance of producing environmental data |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long-term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | x |  |  |  |  |  | PM: Some products (The National Information System, Trainings, Methodological guides, the Haitian Fund for Biodiversity) will contribute to a long term strengthening of the MDE. | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Project is having slow progress in some activities, but once achieved, they will ensure a long-term perspective, particularly sustainability and replicability. |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well-established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties | x |  |  |  |  |  | PM: Each deliverable issued has to be validated by several and specialized stakeholders and experts to ensure sound scientific and technological quality | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The implementation of the NEIS would be based on the use of innovative tools and established technologies. Selection of the bidders (RFP) include scientific and technological criteria. |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  |  |  | x |  |  | PM: Changes in the government and political instability could affect at any time the project. |  |  |  |  | x |  |
|  |  |  |  |  |  |  |  |  |  | TM: political uncertainty is the main source of risk for this project. |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Political uncertainty is a risk identified since the beginning of the project, and some measures have been undertaken to reduce it |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | and not a threat to project implementation | Very disruptive and volatile |  |  |  | x |  |  | PM: Political situation can change at any time and could affect the project. |  |  |  | x |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: Political context is unstable but predictable |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | x |  |  |  |  | PM: The project is implemented in Haiti which is vulnerable and can be affected by weather event. |  | x |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: the location of Haiti, can change the project situation at any time. The project has experienced these situations in the past and they have been collaborating with the government in case of any emergency, there are some contingency plans where the project usually gets involved. |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation, but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | x |  |  |  |  |  | PM: There is no evident socio-economic issues or cultural barriers that could affect directly project performance and results | x |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: there are no socio, cultural and economic issues reported until now that could affect project progress. |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  |  |  | x |  |  | PM: The project is designed to improve the capacity of the partners as weak technical capacity has been recognized from the outset. During the project implementation, actions have been taken to build capacity in particular in terms of management capacity and Environmental audit |  |  |  | x |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: The project addresses this risk and aims at enhancing technical capacity in the country. |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |
| High | Capacity issues: Capacity is very low at all levels and partners require constant support and technical assistance | Implementation/Operationalization of Environmental System, methodological guides, Environmental Action plan could be limited | The project is designed to improve the capacity of the partners as weak technical capacity has been recognized from the outset. So, a sustainable plan for capacity building validated by the MoE Senior management is required. | Project Manager |  |
| High | Political stability and Political influences: Very disruptive and volatile | Political situation can change at any time and could affect the project | Actions are carried out to reduce impacts of political instability: - Organize regularly a Steering committee meeting (at least 1/ year) and/or meetings with 3 Rio conventions focal points (1/quarter) and project director (1/ month); - Document each resolution taken and make reports available on time - Flexibility in the project activity planning However, this seems to be an unavoidable risk for Haiti. | Project Manager |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| Medium | Medium | The risks which can affect the implementation of the project as well as the durability of the tools, methodologies and structures set up or reinforced within the project are the same risks already identified in the Previous PIR. It is the political instability and the weakness of the technical capacity of the MOE. While political instability may be considered inevitable in the current Haitian context, the technical capacity of the MOE can be strengthened. In addition, there is a set of training courses for MOE executives to manage and use the tools and methodological guides produced. However, MOE staff turnover and brain-drain as a result of the country's political and social instability, risks that are beyond the real control of the project. One of the means proposed since the previous PIR is to validate the list of trainees by the MoE (at senior management level) with commitment to keep the trained staff to the possible extent. Thus, the project overall risk is rated as Medium because of the Project management internal risk is estimated, in general, as low or medium. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation, please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.