UN Environment GEF PIR Fiscal Year 2019

- July 2018 to 30 June 2019)

| - Identification |  |  | GEF ID.: 9407 | Umoja no.: P1-33GFL-001310 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Healthy Ecosystems for Rangeland Development (HERD): sustainable rangeland management strategies and practices |  |  |
| Duration months | Planned |  | 48 months |  |  |
|  | Extension(s) |  | 31 July 2019 |  | 17 months |
| Division(s) Implementing the project |  |  | Ecosystem Division, GEF Biodiversity and Land Degradation Unit |  |  |
| Name of co-implementing Agency |  |  |  |  |  |
| Executing Agency(ies) |  |  | International Union for Conservation of Nature and Natural Resources, Regional Office for West Asia (IUCN-ROWA), |  |  |
| Names of Other Project Partners |  |  | Jordanian Ministry of Environment |  |  |
|  |  |  | The Hashemite Fund for Development of Jordan Badia (HFDJB) |  |  |
|  |  |  | The Royal Botanic Garden (RBG) in Jordan |  |  |
|  |  |  | Desert Research Centre (DRC) Egypt |  |  |
|  |  |  | Centre for Environment and Development for the Arab Region and Europe (CEDARE) Egypt |  |  |
| Project Type |  |  | Full Size Project |  |  |
| Project Scope |  |  | Regional |  |  |
| Region (delete as appropriate) |  |  | West Asia |  |  |
| Names of Beneficiary Countries |  |  | Jordan and Egypt |  |  |
| Programme of Work |  |  | 2018-19 Subprogramme 3 Healthy and Productive Ecosystems, EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels |  |  |
| GEF Focal Area(s) |  |  | Land Degradation: Integrated natural resources management |  |  |
| UNDAF linkages |  |  | Preserving the Environment is Priority Area 4 of Jordan’s (UNDAF), 2013-2017. UNDAF related outcome is # 5. Environmental Sustainability and Natural Resource Management is Goal 5 of Egypt’s UNDAF. This project contributes to UNDAF Outcome 5.2 and Outcome 5.3. |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | 15.3.1 Proportion of land that is degraded over total land area 17.14.1 Number of countries with mechanisms in place to enhance policy coherence of sustainable development |  |  |
| GEF financing amount |  |  | USD 3,515,982 |  |  |
| Co-financing amount |  |  | USD12,227,000 |  |  |
| Date of CEO Endorsement |  |  | November 6, 2017 |  |  |
| Start of Implementation |  |  | February 1, 2018 |  |  |
| Date of first disbursement |  |  | March 28, 2018 |  |  |
| Total disbursement as of 30 June |  |  | US$ 456,244 |  |  |
| Total expenditure as of 30 June |  |  | US$ 357,100 |  |  |
| Expected Mid-Term Date |  |  | December 2019 |  |  |
| Completion Date |  | Planned | December 31,2021 |  |  |
|  |  | Revised |  |  |  |
| Expected Terminal Evaluation Date |  |  | TBD |  |  |
| Expected Financial Closure Date |  |  | TBD |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) POW2019-2020 Subprogramme 3: Healthy and productive Ecosystems; EA(a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sector and transboundary collaboration frameworks at the national and international levels | Specify the relevant Expected Accomplishment(s) & Indicator(s) Indicator i) Increase in the number of countries and transboundary collaboration frameworks that have made progress to monitor and maintain the health and productivity of marine and terrestrial ecosystems |
| --- | --- |
| Rangelands that are subject to land degradation are the object of management interventions under this project. The concept of HERD – Healthy Ecosystems for Rangeland Development – is being consolidated through this project on the back of numerous projects, programs, initiatives, studies, scientific articles and policy papers. The current GEF intervention focuses on Jordan and Egypt and on the specific issue of desertification (or land degradation in drylands), which affects pastoral rangelands in these two countries. In addition, the project also proposes serve as a ‘catalyst’ for scaling-up of HERD, both regionally and globally. HERD builds on the sustainable management of pastoral rangelands for the provision of ecosystem services and protection of biodiversity. The project will generate global environmental benefits both at the site level and through the influence that the project will exert on countries and regional bodies to adopt policies and practices that are consistent with HERD with the ultimate intention of arresting the process of rangeland degradation through SRM. This implies policies and practices that will promote biomass growth, conservation of biodiversity and the maintenance of a suit of ecosystem services linked to water, soil and carbon – increasing thereby rangelands’ potential for food production in a sustainable way. SRM contributes to combating desertification by increasing rangeland vegetation cover and particularly perennial species that protect soils and reduce soil erosion. Well-managed rangelands have a higher capacity to trap and store water (see below) and nutrients, including soil organic carbon, sustaining primary productivity. In the first year of the project some activities were delays due to the project approval process in the Jordanian government. The Executing agency couldn’t initiate the technical activities until they received the final approval. The official approval of the Jordanian government was issued in November 12, 2018. The final negotiation meeting with the Egyptian partners was held in November 2018. Accordingly, and due to some delays by the end of year holidays, signing of national partner agreements was finalized in January, 2019. During the waiting for the project approval the focus of the project team was on capacity building for partners, developing the project methodologies and tools, developing the visibility for the project and forming regional cooperation for adoption and upscale of Sustainable Rangeland Management. The Participatory Rangeland and Grassland Assessment (PRAGA) methodology material were modified and translated to be used in the project. The Participatory Rangeland Management Planning (PRMP) was developed in August 2018 and will be translated to Arabic during last quarter of 2019. The activities that were conducted in the time waiting for the approval listed below: Capacity building - Workshop on Sustainable Management of Rangeland Ecosystems in the West Asia Region in cooperation with IUCN Commission on Ecosystems (CEM) - Training on Payment for Ecosystem in cooperation with GIZ Jordan - Conference on Pastoralism and Rangelands Restoration, Ouagadougou, Burkina Faso, 18-22 June 2019. The main objective of the forum was to contribute to strengthening regional and global dialogue on the values of rangelands, the opportunities for rangeland restoration and the role of pastoralists as stewards of rangeland landscapes. Regional Cooperation and upscaling activities - On October 2018, IUCN ROWA held a side event, as part of Africa-Arab Platform on Disaster Risk Reduction held in Tunisia, showcasing HERD as one for nature-based solutions against drought and flooding risks in drylands. - In November 2018, IUCN held a meeting with League of Arab States (LAS) introducing HERD project as an entry point for cooperation with LAS and its organizations and discussing possible cooperation to support other initiatives in the region. - Other meetings were held in November 2018 to discuss the upscale of HERD concept in the region. These meetings included GEF focal points in Jordan and Egypt, IFAD representative in Jordan and FAO office in Jordan. Partnership agreements with the local partners in Jordan and Egypt were signed and effective from the February 2019. Due to the delay the project staff had to work with the partners to reschedule the activities in the work plan to finish the project within the initial time frame. The PRAGA methodology training for partners in Jordan and Egypt were conducted in March 2019 and the assessment implementation started in April 2019 and expected to conclude in October 2019. Furthermore, realizing the importance of both the sustainable management of natural resources in the region and the sharing of knowledge, networking, mutual learning and experience as an essential tool in development, IUCN West Asia Dryland, Livelihoods and gender programme starts activate the WAMIP - WISP Regional Pastoralists representatives and in the process of registering the network under AOAD (Arab Organization for Agriculture Development that is one of LAS (League of Arab State) organizations under the Honorary presidency of Her Highness Sharifa Zain Al Sharaf Bint Nasser. The Main Goal of Building Arabian Pastoralist Communities Network is to revive, document and develop the traditional knowledge in the Arabic Region in order to invest it in the development of Bedouin pastoral groups and building their capacities for effective participation in rehabilitation and improvement of sustainable participatory management of rangelands. This can happen through mainstreaming and networking with civil society organizations, researchers, experts, decision makers and other stakeholders and networks. |  |

For all GEF 6 and later projects:

| GEF Core Indicators | Indicative expected Results |
| --- | --- |
| 1.2 Terrestrial protected areas under improved management effectiveness (hectares) 3.3 Area of natural grass and shrublands restored (hectares) 4.1 Area of landscapes under improved management to benefit biodiversity (hectares, qualitative assessment, noncertified) 11. Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 19,031 ha of the overall target (CI 3.3) are protected area in Jordan. Focal Area Indicator 1.1 Land area under effective agricultural, rangeland and pastoral management practices and/or supporting climate-smart agriculture – thus measured: Sustainable Rangeland Management (SRM) measures are applied in at least 525,563 ha of target landscapes (192,621 ha in Jordan and 332,942 ha in Egypt), departing from a baseline of 5,089 ha, corresponding to the surface of the Bani Hashim pilot site in Jordan, where some form of community-based SRM measure currently applies. Outcome 3.2: Integrated landscape management practices adopted by local communities based on gender sensitive needs. Focal Area Indicator 3.2: Application of integrated natural resource management (INRM) practices in wider landscapes – thus measured: (i) At least 10 local community groups across all target landscapes in both countries, including Rangeland User Associations and Hima Communities, adhere in SRM management practices; and (ii) An inter-sectoral planning mechanism at governorate level is in place in each of the 4 target landscapes (3 in Jordan, 1 in Egypt), departing from a baseline where SRM management practices prevail in only one site in Jordan (Bani Hashem) and one nascent community association in Egypt is willing to engage in SRM. Ca. 30,000, with a split of roughly 55% male and 45% female |
| The project progress to-date regarding the project M&E plan are: Outcome 1.1: Rangeland monitoring systems institutionalized nationally and regionally based on commonly agreed scale-dependent indicators appropriate for different end-user groups Outputs: 1.1.1 Rangeland landscape assessments conducted at local, and national levels using agreed biophysical and socio-economic indicators and participatory approaches where applicable 1.1.2 Development of Prototype National platforms for information sharing and exchange, including data on land degradation and good practices in Sustainable Rangelands The Participatory Rangeland and Grassland Assessment (PRAGA) Methodology was adapted and the local partners in Egypt and Jordan were trained. The assessment is 80% finished up till now and will be concluded in Oct 2019. The Platform that will be used to store the information is under development and for the knowledge management portal a technical team from the project partners will develop a concept paper to be discussed by the project steering committee. The original plan was to have a national platform in each country hosted by the MOE’s CHM System. However, a request was made to consider establishing a regional platform instead of a national one, to encourage regional exchange of information on rangeland management. Ensuring sustainability of the work on the platform was discussed as a defining factor, as previous experiences showed that many platforms were deactivated funding stopped. IUCN will create a page on IUCN’s website for HERD project to display HERD outcomes and milestones. This page will provide a primary regional platform for the project. Outcome 1.2: Key project stakeholders reach consensus over identification and prioritization of good practices and effective policies in sustainable rangeland management and rangeland rehabilitation 1.2.1 Review of policies and laws, including relevant international agreements, related to sustainable rangeland management, identifying opportunities and barriers policy implementation 1.2.2 Cost-benefit analysis of sustainable rangeland management policies and practices using economic methodologies 1.2.3 Good practices and policies in integrated rangeland management validated following agreed methodologies and indicators The project team discussed with the National partners the specific outputs in each country and agreed that updating the Rangeland policy in Jordan and proposing draft policy in Egypt is the main target. The ToR for the policy review were developed and the agreement that a local consultant in addition to an international one from IUCN will carry out the policy review in both countries by the end of 2019. IUCN with ICARDA held a regional experts meeting to discuss the best practices on rangeland management and agreed on developing a toolbox that will be used as background material to developing the training and awareness material for Sustainable Rangeland Management (SRM). The toolbox in under development by experts from ICARDA and the project partners along with IUCN and expected to be published by the end of November 2019. For the rest of the outcomes and outputs its planned in the coming year. |  |

| Planned linkages with UNDAF | The main strategic objectives that the project will address according to the project documents are: - Preserving the Environment is Priority Area 4 of Jordan’s United Nations Development Assistance Framework (UNDAF), 2013-2017. UNDAF outcome 5 is “Government and national institutions have operationalised mechanisms to develop and implement strategies and plans targeting key cultural, environmental and Disaster Risk Reduction issues (including a transition to a Green Economy) at national and sub-national levels.” This is consistent with the aims of the Executive Development Programme 2011-2013, including: to preserve the Kingdom's cultural heritage and market it globally; to integrate local communities into the development and planning processes; securing adequate water supplies for various sectors; and to protect environment elements and their sustainability. According to Jordan’s UNDAF, ‘“Preserving the Environment” will give support to improved integrated water resources management, climate change adaptation measures, enhanced mechanisms for disaster risk reduction, better management of ecosystems, as well as cultural and natural heritage, and support Jordan in its transition to a Green Economy. - Environmental Sustainability and Natural Resource Management is Goal 5 of Egypt’s UNDAF. This project contributes to UNDAF Outcome 5.2: “The Government of Egypt, private sector and civil society have complied with Multilateral Environmental Agreements, adopted policies, and implemented operational measures towards a green and sustainable economy and society including, EE, RE, low carbon cleaner technologies, SWM, POPs, ODS, and Carbon Finance Mechanisms”. The project also contributes to UNDAF Outcome 5.3: “The Government of Egypt and local communities have strengthened mechanisms for the sustainable management of, and access to, natural resources such as land, water and ecosystems.” IUCN developed a planning approach for the Natural Resources based on its experience in Rangeland Management to be used in HERD project in Jordan and Egypt. The Participatory Rangeland Management (PRMP) approach contain 5 phases as any planning cycle but the addition is using specific tools to Rangeland management. The first two phases; stakeholders’ analysis and partnership building and the rangeland assessment phase are nearly completed and the long-term planning for the landscape will be starting in November 2019. |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Sustainable Pastoralism is a means to deliver on the global 2030 Agenda and Sustainable Development Goals through monitoring SDG 15, Life on Land and its interlinkages with all the 17 SDGs. Specifically monitoring SDG15.3.1 Proportion of land that is degraded over total land area that is linked to LDN indicators and SDG17.14.1 Number of countries with mechanisms in place to enhance policy coherence of sustainable development. HERD Project is directly in line with the objectives of the UNCCD, and the country reports to the UNCCD. In October 2015 the UNCCD adopted LDN as a principle target for the Convention and invited Parties to set voluntary national LDN targets. Specifically HERD Output number 4.1.2 focuses on Regional dialogue to influence the design and implementation of policies and investments for SRM (especially LDN), including coordinated influence of international agreements And the project regional dimension focus on Jordan and Egypt as the main countries to work on and aspire to expand the initiative to other countries and regions as part of the project targets under component 4 |
| --- | --- |

| Implementation Status | FY 2018 | FY 2019 | FY 2020 | FY 2021 |  |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | Final PIR |  |

| Development Objective Rating FY | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S | S |  |  |  |
| The project still suffers from delays caused by the long approval processes at national level, rendering the project operational only by the end of 2018 and early 2019 in Jordan and Egypt respectively. Nevertheless, the project team used the past reporting period to actively engage and consult with stakeholders at local, national and regional levels, The good networking will allow to reach consensus on SLM good practices and policies at an accelerated pace for advancing scale-up nationally and regionally, despite being able to demonstrate achievements on the ground already. |  |  |  |  |  |

| Implementation Progress Rating | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS |  |  |  |
| The first-year activities were shifted and modified to the next year without compromising the work quality. The first year focused on capacity building of the local partners and networking locally and regionally due to the delay in approvals. In this year the main activities were: - Held Steering committee and advisory committee meeting in both countries and agree on the modified work plans - Develop the SoW and budgets for the local partners and sign the agreements with them - Update the Monitoring and Evaluation framework - Held the first meeting for the Arabian Pastoralist Communities Network in Amman and agreed on the membership procedures and internal organization and agree to register it under AOAD - Inception meetings in both Jordan and Egypt were held at the national level and at the community level. - Developing the PRAGA (Participatory Rangeland and Grassland Assessment) training material and translated to Arabic then train the local partners staff in Jordan and Egypt on the methodology. - Implementation of PRAGA Methodology on the ground. - Conduct baseline assessment for the selected landscapes - Develop ToR for the local and regional studies and reviews - Start developing SRM toolbox - Develop the training material on remote sensing, GIS, drought and land degradation modelling and mapping methods and develop the training schedule - Develop PRMP (Participatory Rangeland management Planning) methodology and set training schedule with the local partners The main challenge was to reach an understanding with the partners of the approaches and their roles in the implementation but we made a good progress by reviewing the work plans and adjust some of the activities to reach the desired outcomes. |  |  |  |  |  |

| Risk Rating | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | L | L |  |  |  |
| The overall risk assessment was reduced to Low from medium because on the implementation level mitigation measures were assessed and will be followed up. The only medium risk is “Women’s participation in the project is weak” and that can be reviewed after implementing the main activities. |  |  |  |  |  |

| Stakeholder engagement | The project works on different levels and includes a wide range of Stakeholders. From the initial stakeholders analysis in the project document the project management attracted and cooperated with most of the list and included more over the past year. At the local level: At the four target sites; three in Jordan and one in Egypt, the partner’s staff started the field assessments with a stakeholder’s analysis at each site. The initial stakeholder mapping and analysis was used to understand the local structure and the community groups to invite them to participate in the project activities. The lists is updated continuously to include new info and players at the local level. The mapping included women organizations and groups. At the national level: The core stakeholders identified through the project document were invited and comprised the steering committee and the partnerships were formalized. In addition local advisory committees were developed in both Jordan and Egypt to support the activities in each country. A wider stakeholder’s analysis is being carried out to include new stakeholders or add the ones that the project document didn’t identified such as; other projects and activities that can support and compliment the project activities. At the regional level: The project developed good relations with different regional and international organization starting with LAS (League of Arab State) where an agreement is under development between IUCN and LAS to cooperate in different initiatives and cooperation including cooperation in HERD activities. An agreement was developed with AOAD (Arab Organization for Agriculture Development) that is one of LAS organizations to sponsor and register the Arab Network for Pastoralists communities and co-financed the network first meeting in Amman in April 2019. The project is discussing with LAS the potential of further cooperation especially on cooperating in conducting the regional components and studies under the project deliverables. |
| --- | --- |

| Gender mainstreaming | Project activities will specifically target women’s groups as rangelands users, as well as women within other rangeland organizations, to ensure they are central to project delivery and to the development of scale-up initiatives and policy dialogue. This will be achieved through partnerships with women’s organizations and through insistence on effective women’s representation in dialogue at community, local government and national government levels, as well as in international dialogue. Women groups will also be targeted for PRMP based supporting activities which will aim at diversifying their income sources and act as alternative income generating activities. Collecting and drying of herbs is one such initiative that started during the revival of Hima in Bani Hashem. The project activities in this year is mostly capacity building and assessments. Women were included in the trainings as possible as the partners staff are mostly men but we requested to include women from each organization in each training. The assessments were designed taking into consideration gender sensitivity and the role of women at different levels. |
| --- | --- |

| Knowledge activities and products | The Participatory Rangeland and Grassland Assessment (PRAGA) methodology materials were modified and translated to be used in the project. The Participatory Rangeland Management Planning (PRMP) was developed in August 2018 and will be translated to Arabic during last quarter of 2019. |
| --- | --- |

| Stories to be shared | N/A |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: | To strengthen restoration and sustainable management of pastoral rangelands for the provision of ecosystem services and protection of biodiversity in Egypt and Jordan and catalyzing scale up regionally and globally. |  |  |  |  |  |
| Outcome 1.1: Rangeland monitoring systems institutionalized nationally and regionally based on commonly agreed scale-dependent indicators appropriate for different end-user groups | 1. # of institutional partners supporting rangeland monitoring system | Up to date data on land degradation assessment using participatory approaches not available. Project partners do not follow an up to date and standardized monitoring approach |  |  |  |  |
|  |  |  | National partners report are informed about the PRAGA methodology | National partners report acceptance of PRAGA methodology | (the training was concluded and the partners are doing the assessment) 80% is done | S |
|  | 2. # of institutional arrangements for rangeland monitoring | Rangeland monitoring systems are not institutionalized or systematically applied in the participating countries | Baseline data from PRAGA is communicated with relevant partners. System for sharing up to date data on land degradation are in place. | - PRAGA methodology adapted and conducted by national partners in at least four landscapes; 3 in Jordan and 1 in Egypt | Under development | S |
| Outcome 1.2: Key project stakeholders reach consensus over identification and prioritization of good practices and effective policies in sustainable rangeland management and rangeland rehabilitation | 1. # good practices and SRM policies identified and approved by project stakeholders | Lack of consensus over good practices in SRM amongst stakeholders Proposed good practices in SRM have been identified in Jordan and Egypt but they are not widely adopted by project partners. Jordan has adopted a policy supporting improved community-based SRM but the policy is not yet widely implemented | Proposed good practices in SRM with clear role for women are adopted by project partners in Jordan and Egypt Community based rangelands management governance systems is in place in all project landscape Dialogue for improved policy for community rangeland management under way in Egypt | At least one specific SRM practice (e.g. controlled grazing or reseeding) approved for implementation in each site with clear guidance over the role of women land managers Community based rangelands management is implemented in all project landscapes (192,621 ha in Jordan and 332,942 ha in Egypt) Dialogue for improved policy for community rangeland management under way in Egypt | A regional expert meeting was held in cooperation with ICARDA in April 2019 in Tunisia to Develop a Rangeland Restoration/ Rehabilitation Toolbox that define and describe key sustainable rangeland management practices. The toolbox is being finalized and will be used after translation as base for training and awareness for SRM. The on the ground practices and policy recommendation will follow the assessment phase that is anticipated to end by Oct 2019 | S |
|  | 2. # of good practices that explicitly address the roles and responsibilities of women land users | Identified good practices generally do not pay explicit attention to the role of women resource managers |  |  | The material is under development, part of the baseline study that is in the data analysis phase | MS |
| Outcome 2.1: Local organizations for rangeland management (community and government) engage in more inclusive dialogue for improved rangeland governance covering approximately 500,000 hectares | 1. # of a) Rangeland User Associations or Hima Communities and b) Local government entities at governorate and/or district levels that participate in SRM planning | SRM management practices prevail only in the pilot SRM site in Jordan, Bani Hashem: a) 1 Rangeland User Associations b) 1 Hima Community c) 2 Local government entities at governorate and/or district levels 1 site in Egypt has a nascent community association that is willing to engage in SRM | 6 Hima Communities and 4 Rangeland User Associations established Training of local government partner in Egypt and in Jordan on SRM planning | 6 Hima Communities and 4 Rangeland User Associations participate in SRM planning 1 local government partner in Egypt and 3 in Jordan participate in SRM planning | NA | N/A |
|  | 2. # of women members of participating organisations | Women are widely excluded from rangeland management | Good representation of women in Hima Communities and rangeland user associations and involvement of women’s organisations women | Women participate in all community based SRM planning, either through their membership of Hima Communities and rangeland user associations, or through membership of women’s organisations | NA | N/A |
| Outcome 2.2: Rules and regulations for improved rangelands management are established (in line with the Voluntary Guidelines on Responsible Governance of Tenure) based on PRMPs in participating communities | # of local SRM agreements developed within communities and between communities and state institutions, based on PRMPs and in line with VGGT [E.g. Hima agreements, local conventions, bylaws etc.] | 1 (in Bani Hashem site in Jordan) | At least 3 SRM agreement are developed in both countries | At least 5 SRM agreements developed across both countries | NA | N/A |
| Outcome 3.1: Local farmers / pastoralists adopt good practices in rangeland restoration and management and supporting services with support from local government agencies | 1. # communities with improved income from sustainably managed rangelands obtained by local communities as a result of implementing SRM practices | 0 | New SRM practices adopted in at least 4 project sites across both countries | New SRM practices adopted in at least 6 project sites across both countries | NA | N/A |
|  | 2. # of women participating in income generating activities related to SRM | 0 | At least 10 in both countries | At least 10 per country | NA | N/A |
|  | 3. # new SRM practices implemented by communities of rangeland managers | 1 in Bani Hashem 1 in Mersa Matrouh | At least 2 SRM practices adopted across both countries | At least 3 SRM practices adopted across both countries | NA | N/A |
| Outcome 4.1: Increased support for sustainable pastoralism in investments and public decision/policy- making, nationally, regionally and globally | 1. # new investments under development in the region or globally that draw on project lessons and partnerships | 0 | Concepts for 5 major investments are negotiated with regional partners and / or submitted. | 5 major investments in SRM under development within LAS and other participating countries | NA | N/A |
|  | 2. # regional and national policy dialogues initiated or enhanced through project actions | 0 | Holding a policy dialogue event/ workshop | 5 policy dialogues towards community based SRM are influenced by project actions | NA | N/A |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project covered ground after the delayed start of implementation by establishing good collaboration at national and regional levels, indicating that it will be able to achieve policy results at an accelerated pace. Results on the ground need to follow suit, though. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects should complete only the relevant sections and are free to add/delete problems/risks.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving targets | The project activities were delayed because of the delay in acquiring the project approval from the Jordanian government. New targets/deadlines need to be agreed on | The project workplan was modified to accommodate the change in the time frame for implementation. |
| on stakeholder engagement | The project partner’s capacity to comprehend and implement the new approaches in the new time frame and modify their activities accordingly can push the timeline over the project period. | Negotiate and adjust the approaches to be within the partners capacity with direct support from IUCN |
| on delivering GEF Core Indicators |  |  |
| on delivering of PoW EA |  |  |
| others |  |  |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implement-ation status as of 30 June 2018 | Implement-ation status as of 30 June 2019) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Output 1.1.1: Rangeland landscape assessments conducted at local, and national levels using agreed biophysical and socio-economic indicators and participatory approaches where applicable |  |  |  |  | S |
| Activity 1: Implementation of the PRAGA Methodology | End of Oct 2019 | 0% | 80% | Two trainings were conducted in Amman and Cairo in March 2019 on PRAGA methodology. The trainings target the field workers in partner institutions. The field work started on both countries in May 2019 and expected to be concluded by end of October 2019 |  |
| Activity 2: Detailed studies of target landscapes, including drought monitoring, contour mapping, rangeland characteristics, livestock production data, socio-economic data, role of Gender in rangeland management and restoration | End of October 2019 | 0% | 50% | The ToR for the studies were developed and discussed with the partners. The tools for data gathering (data checklists developed) |  |
| Output 1.1.2: Development of Prototype National platforms for information sharing and exchange, including data on land degradation and good practices in Sustainable Rangelands |  |  |  |  | S |
| Activity 3: National inception meetings | Mar/19 | 100% | 100% | Two national inception workshops in each country were conducted in March, 2019, where HERD project, its objectives, components, partners and project sites were introduced to a wider audience. |  |
| Activity 4: Annual Steering Committee Meetings |  | 25% | 100% | The Second Steering Committee meeting was conducted in April 2019, aiming at providing overall guidance and strategic direction and oversight to project management, by reviewing the work plan and the progress in the project. |  |
| Activity 5: Support to national partners to establish a knowledge management portal and information database for target landscapes | End of June 2020 | 0% | 25% | During the steering committee meeting the partners discuss the mechanisms used in establishing the knowledge management portal. The ToR of the portal and the database will be developed by the end of 2019. |  |
| Output 1.2.1: Review of policies and laws, including relevant international agreements, related to sustainable rangeland management, identifying opportunities and barriers to policy implementation |  |  |  |  | S |
| Activity 6: Desk review and consultative workshops to examine policies to achieve LDN (national rangelands strategy, implementation of HIMA, role of gender in rangeland management and range-based livelihoods) with recommendations on policy implementation, policy reform, policy contradictions and synergies with any other policies, etc. | Feb 2020 | 0% | 20% | The ToR of the desk review was developed. The local partners in Jordan and Egypt agreed on the roles and workplan to develop the review and to update/propose a national rangeland strategy. The study will be concluded by early 2020. |  |
| Output 1.2.2: Cost-benefit analysis of sustainable rangeland management policies and practices using economic methodologies |  |  |  |  | N/A |
| Activity 7: Economic valuation study and mapping of restoration opportunities combined with local and national consultative workshops (possibly conducted towards the end of the project when data on implementation methods and costs are available) | Oct 2020 | 0% | 0% | The ToRs for conducting the economic valuation studies in Jordan and Egypt were developed. The studies will be conducted at the end of year 3. |  |
| Output 1.2.3: Good practices and policies in integrated rangeland management validated following agreed methodologies and indicators |  |  |  |  | MS |
| Activity 8: Development of project monitoring strategy with agreement on indicators for evaluation of good practices | End of 2019 | 0% | 50% | The monitoring and evaluation strategy was developed, and validation during the national inception workshops. It will be revised through the upcoming months. |  |
| Activity 9: Midterm and final evaluation of project actions drawing on evidence from rangeland landscape assessments (Output 1.1.1) and economic valuations (Output 1.2.2) | Dec 2019 | 0% | 0% | It was planned to have the midterm review in July, but due to the resignation of the program manager these activities were delayed to be in December. |  |
| Activity 10: Publication of project lessons in English and Arabic | Jul 2021 | 0% | 0% | This will be developed later on. |  |
| Output 2.1.1: Capacity/needs assessment of local organizations, including community groups and local public service providers |  |  |  |  | MS |
| Activity 11: Detailed stakeholder analysis and baseline needs assessment (against key governance indicators) with strong emphasis on the capacities and needs of women and any social inclusion groups (Vulnerable groups) | End of Mar 2020 | 0% | 50% | The stakeholders were mainly identified but the baseline need assessment will be carried early next year |  |
| Output 2.1.2 Stronger organizational capacities through appropriate training, including training of partner institutions in Participatory Sustainable Rangeland Management Planning (PRMP) |  |  |  |  | N/A |
| Activity 12: Training of local partners in Sustainable Rangelands Management etc. (Pastoral Learning Forum methodology) | Continuous starting from Nov 2019 till mid 2021 | 0% | 0% | This will be conducted later on. |  |
| Activity 13: Training on remote sensing, GIS, drought and land degradation modeling and mapping methods | Starts in Nov 2019 till Mid 2020 | 0% | 20% | The TORs for GIS training were developed and the manual was drafted 2. The training will start in Nov 019 |  |
| Activity 14: Publication of brochure on SRM in Arabic and distribution to all partners and communities | Starting from December 2019 till the end of the project | 0% | 0% | This will be developed later on. |  |
| Output 2.2.1: PRMP implemented in all participating communities and updated annually |  |  |  |  | N/A |
| Activity 15: Training of trainers in PRMP in each country | Nov 2019 | 0% | 0% | the training schedule will be developed at the end of Nov |  |
| Activity 16: Publication of PRMP guidelines | Nov 2019 | 0% | 80% | The PRMP guidelines was developed in English. The guidelines will be translated to Arabic to make it easier for field workers in the project sites. |  |
| Activity 17: Implementation of PRMP methodology by trained local partners | Nov 2019 – Jan 2020 | 0% | 0% | This will be conducted later on. |  |
| Activity 18: Annual participatory monitoring of PRMPs with local committees | Feb 2020 | 0% | 0% | This will be conducted later on. |  |
| Output 2.2.2: Documentation of existing community land use practices (rules and regulations over rangeland resource management: pasture, water, trees, wildlife, livestock corridors, etc.) |  |  |  |  |  |
| Activity 19: Consultancy-led study and consultation with local stakeholders with recommendations for local agreements developed under Output 2.2.3. (study per country) | July 2020 – Dec 2020 | 0% | 0% | This will be conducted later on. |  |
| Output 2.2.3: Local agreements between communities and between communities and state institutions (Hima agreements, local conventions, bylaws etc.) developed according to national legal opportunities |  |  |  |  | N/A |
| Activity 20: Multi-stakeholder dialogue to draft local natural resource management agreements. | March 2020- Dec 2020 | 0% | 0% | This will be conducted later on based on the landscape planning activity. |  |
| Activity 21: Participation in government dialogue to pursue adoption of local agreements (where relevant) | March 2020 –Dec 2020 | 0% | 0% | This will be conducted later on. |  |
| Output 3.1.1: Training and awareness raising in rangeland restoration and management innovations and adapting services for sustainable rangeland management |  |  |  |  | N/A |
| Activity 22: Technical briefs published on community based rangelands management in local language targeting local and national level public servants | July 2020- July 2021 | 0% | 0% | This will be conducted later on. |  |
| Activity 23 Training of community beneficiaries in rangeland restoration techniques, natural regeneration, herd management strategies and related practices | Jan 2020 – August 2020 | 0% | 0% | This will be conducted later on. |  |
| Activity 24: Exchange visits to established rangeland Hima sites in Jordan/Egypt | Continuous | 0% | 25% | An exchange visit was organized in April to Hima Bani Hashem to enlighten the partners with the experience of Bani Hashem villages in declaring a Hima site. |  |
| Activity 25: Public communications on SRM, including news articles and radio broadcasts | July 2020- July 2021 | 0% | 0% | This will be conducted later on. |  |
| Output 3.1.2: PRMP based sustainable rangeland management systems are piloted |  |  |  |  | N/A |
| Activity 26: Grants to partners for implementing restoration actions identified through PRMPs and approved by the steering committee | Feb 2020 –Feb 2021 | 0% | 0% | This will be conducted later on. |  |
| Output 3.1.3: PRMP-based supporting activities are piloted. |  |  |  |  | N/A |
| Activity 27: Grants to partners to implement supporting activities identified through the PRMPs and approved by the steering committee | Feb 2020 –Feb 2021 | 0% | 0% | This will be conducted later on. |  |
| Output 4.1.1: Lessons on the value of rangeland ecosystems and good practices in SRM are documented and communicated through a regional Communal Rangelands Leadership network (of scientists, pastoralists and Civil Society Organizations for South-South learning and cooperation) |  |  |  |  | MS |
| Activity 28: Compilation and publication of validated good practices in the restoration and protection of communal rangelands in the Arab region and globally. | Nov 2019 | 0% | 50% | The Sustainable Rangelands Management Practices toolbox was drafted in cooperation with ICARDA. It will be reviewed and finalized within the upcoming months. |  |
| Activity 29: Presentation of experiences at academic and policy conferences and events regionally and globally and publication in peer reviewed journals | Continuous | 0% | 0% | This will be conducted later on. |  |
| Activity 30: Annual meetings of the Arab Regional Pastoral Network (3 meetings) | Continuous | 0% | 25% | The first annual meeting of the Arab Pastoral Communities Network was conducted in April aiming at strengthening the network, sharing sustainable rangelands management and reflecting on opportunities for rangeland restoration at national and regional level. |  |
| Activity 31: e-discussions on community rangelands management leading to the establishment of a network of resource people for championing Hima globally | Mid 2020 | 0% | 0% | This will be conducted later on. |  |
| `Activity 32: Consultations to agree on the Conceptual Framework for an expanded global HERD initiative (Theory of Change, regional situation analysis etc.) | NA | 0% | 0% | This will be conducted later on. |  |
| Output 4.1.2: Regional dialogue to influence the design and implementation of policies and investments for SRM, including coordinated influence of international agreements |  |  |  |  | N/A |
| Activity 33: One regional policy forum on the challenges and opportunities to SRM, with support for regional decisions in favor of SRM/LDN (target 50 mid-level policy makers from the LAS region and beyond) | Last quarter of 2020 | 0% | 0% | This will be conducted later on. |  |
| Activity 34: Review of regional and global policies in support of SRM (especially LDN), their value-addition to national policies, and opportunities for leveraging further funds for regional SRM initiatives | Feb 2020 | 0% | 20% | The ToR for this activity was developed and there is a negotiation with Arab Organization for Agricultural Development to conduct the study in cooperation with IUCN |  |
| Activity 35: Publication of a LAS regional rangeland situation analysis, including an overview of the state of rangeland health and estimated cost benefit of restoration and protection | End of Jan 2020 | 0% | 20% | The TOR for this activity was drafted and a dialogue with ACSAD was opened to discuss the implementation of this activity. |  |
| Activity 36: Convening of regional investment forum for SRM/LDN | Mid 2020 | 0% | 0% | This will be conducted later on. |  |
| Output 4.1.3: Sustainable Rangeland Management initiatives are submitted (regionally and outside the region) for funding under the HERD umbrella, based on “bankable” investment options and innovative financing strategies |  |  |  |  | N/A |
| Activity 37: Regional/global inception meeting for component four |  | 0% | 0% |  |  |
| Activity 38: Five baseline studies and stakeholder consultations for target initiatives (e.g. rangeland health, state of pastoral rights, existence of good practices, key actors etc.) |  | 0% | 0% | This will be conducted later on. |  |
| Activity 39: Five workshops for collaborative proposal design and fund raising strategy |  | 0% | 0% | This will be conducted later on. |  |
| Activity 40: Regional/global annual steering committee meetings |  | 0% | 0% | Meeting in Amman |  |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| S | S | The project made good progress and caught up with some of the delays from the earlier reporting period, particularly with regard to assessments, knowledge management tools and policy review. Most of the activities in conjunction with local stakeholders are behind the original schedule, but not yet due according to the newly agreed upon work programme – it is therefore too early to rate the majority of these outputs. However, good stakeholder engagement here also provides for an accelerated pace to stay within the agreed upon time frame. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Internal risks |  |  |  |
| Management structure The project manager resigned in June 2019 in a critical time of the project implementation. | IUCN ROWA regional director overseeing the project implementation and takes the necessary action to hire a new project manager ASAP | IUCN ROWA | ASAP |
| Internal communications |  |  |  |
| Work flow Partners understanding |  |  |  |
| Co-financing The partners took a long time to get the official signed co-finance paperwork. |  |  |  |
| Budget Due to the delay in the project activities because of the approval issue the budget of year 1 was not spent as allocated. | Its agreed that a Budget revision need to be done in the latest steering committee meeting, also to reflect the agreed upon project work plan | Project manager | Before the end of 2019 |
| Financial management |  |  |  |
| Reporting Delay in reporting |  |  |  |
| Stakeholder involvement |  |  |  |
| Political influences |  |  |  |
| External risks |  |  |  |
| Environmental conditions |  |  |  |
| Social, cultural and economic factors |  |  |  |
| Capacity issues |  |  |  |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation at implementation | Rank |
| --- | --- | --- | --- |
| Instability and conflicts in countries and the region | In Jordan, there may be a risk of Syrian refugees putting additional pressure on the rangelands. However, IUCN’s approach (which originated in the challenge of managing pressure from Palestinian refugees) recognizes that pressure can only be alleviated if local governance is first strengthened to ensure the implementation of rules for sustainable rangeland management. | Understanding the level of pressure on the rangeland resources is part of the assessment and baseline studies will address the need of the different groups in the planning process. As a preliminary assessment the number of Syrian refugees is declining in general and a small number is registered in the target areas. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Women’s participation in the project is weak. | During the PPG, a number of strategies have been developed for the engagement of women in the project and for ensuring that they benefit equitably from results. Various project activities are specifically targeting women’s groups as rangelands users, as well as women within other rangeland organizations, to ensure they are central to project delivery and to the development of scale-up initiatives and policy dialogue. This will be achieved through partnerships with women’s organizations and through insistence on effective women’s representation in dialogue at community, local government and national government levels, as well as in international dialogue. Women groups will also be targeted for PRMP based supporting activities which will aim at diversifying their income sources and act as alternative income generating activities. Collecting and drying of herbs is one such initiative that started during the revival of Hima in Bani Hashem. These are slated for replication. | Gender sensitive studies will be conducted to assess the vulnerable groups and then plan specific activities and initiatives that will target these groups. Women of all ages and youth will be the main target. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| The project is not able to tackle complex land tenure issues and their links to land degradation. | Currently the VGGT provides an excellent framework for the land-use governance and a common denominator for defining guiding parameters for any approach to governance tenure. It is an approach of choice, together with the PRAGA methodology for a number of activities for which land tenure issues should be taken into consideration. In addition, key activities under Component 2 will entail documenting existing rules and regulations (government and community) and developing appropriate mechanisms to strengthen their enforcement, including by-laws and local conventions. Information and policy openness will ensure that, although complicated, land tenure issues and their potential negative impact on land management can be adequately tackled. | Based on the policies review and introducing best practices the dialogue with the different stakeholders will be shared with the decision makers. Different venues in the region will be utilized to show case the benefits and assets to decision makers to understand and address land tenure issue especially when linked with economic valuation benefits. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | L |
| Overall Risk Rating Task Manager |  |  | L |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | Overall risks are predominantly assessed as being low, and two of the medium risks addressing the contextual situation were downgraded during the course of project implementation so far. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Annexes and/or Links:

- Project Steering Committee Minutes of the year reported

- Risk Factor Table form previous template

Risks Factor Table

There are two tables to assess and address risk: the first “risk factor table” to describe and rate risk factors; the second “top risk mitigation plan” should indicate what measures/action will be taken with respect to risks rated Substantial or High and who is responsible to for it.

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

RISK FACTOR TABLE

Project Managers will use this table to summarize risks identified in the Project Document and reflect also any new risks identified in the course of project implementation. The Notes column should be used to provide additional details concerning manifestation of the risk in your specific project, as relevant. The “Notes” column has one section for the Project Manager (PM) and one for the UNEP Task Manager (TM). If the generic risk factors and indicators in the table are not relevant to the project rows should be added. The UNEP Task Manager should provide ratings in the right hand column reflecting his/her own assessment of project risks.

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| INTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management structure [Roles and responsibilities] | Stable with roles and responsibilities clearly defined and understood | Individuals understand their own role but are unsure of responsibilities of others | Unclear responsibilities or overlapping functions which lead to management problems | x |  |  |  |  |  | PM : the activities were discussed and tasks redefined to the project partners and there is a high level of cooperation among partners | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree; however, focus needs to be placed on local engagement and implementation |  |  |  |  |  |  |
| Governance structure [oversight] | Steering Committee and/or other project bodies meet periodically and provide effective direction/inputs | Body(ies) meets periodically but guidance/input provided to project is inadequate. TOR unclear | Members lack commitment Committee/body does not fulfil its TOR | x |  |  |  |  |  | PM : the steering committee provide support in the meeting and in the daily basis relation | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Internal communications | Fluid and cordial | Communication process deficient although relationships between team members are good | Lack of adequate communication between team members leading to deterioration of relationships and resentment | x |  |  |  |  |  | PM: good relations and cooperation is observed by the partners | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Work flow Budget | Project progressing according to work plan | Some changes in project work plan but without major effect on overall timetable | Major delays or changes in work plan or method of implementation |  | x |  |  |  |  | PM: the delays in the project approval added a pressure on the project timetable but the new work plan can absorb the delay | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree, but new PM needs to be hired asap to maintain the current pace |  |  |  |  |  |  |
| Co-financing | Co-financing is secured and payments are received on time | Is secured but payments are slow and bureaucratic | A substantial part of pledged co-financing may not materialize |  | x |  |  |  |  | PM: the co-finance is mostly in-kind. The co-financing reporting is delayed because of bureaucratic procedures |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree, no co-finance reporting received so far |  |  |  |  |  |  |
| Budget | Activities are progressing within planned budget | Minor budget reallocation needed | Reallocation between budget lines exceeding 30% of original budget |  | x |  |  |  |  | PM: budget reallocation is required to reflect the underspending in year 1 and the distribution to the sub-grantees/partners. |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: budget revision needs to be addressed asap so as not to cause further delays in implementation |  |  |  |  |  |  |
| Financial management | Funds are correctly managed and transparently accounted for | Financial reporting slow or deficient | Serious financial reporting problems or indication of mismanagement of funds | x |  |  |  |  |  | PM: following up IUCN internal regulations that is closely monitored | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Reporting | Substantive reports are presented in a timely manner and are complete and accurate with a good analysis of project progress and implementation issues | Reports are complete and accurate but often delayed or lack critical analysis of progress and implementation issues | Serious concerns about quality and timeliness of project reporting |  | x |  |  |  |  | PM: the reporting is delayed because of the absence of a project manager shortly before the reporting period. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Stakeholder engagement | Stakeholder analysis done and positive feedback from critical stakeholders and partners | Consultation and participation process seems strong but misses some groups or relevant partners | Symptoms of conflict with critical stakeholders or evidence of apathy and lack of interest from partners or other stakeholders | x |  |  |  |  |  | PM: stakeholder mapping and analysis is continuous process and new stakeholders are invited regularly based on the updated work plan | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| External communications | Evidence that stakeholders, practitioners and/or the general public understand project and are regularly updated on progress | Communications efforts are taking place but not yet evidence that message is successfully transmitted | Project existence is not known beyond implementation partners or misunderstandings concerning objectives and activities evident |  | x |  |  |  |  | PM: the late start up and the long assessment phase built relationships with stakeholders but still the coming activities will insure wider audience/ participants will be engaged |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Short term/long term balance | Project is addressing short term needs and achieving results with a long term perspective, particularly sustainability and replicability | Project is interested in the short term with little understanding of or interest in the long term | Longer term issues are deliberately ignored or neglected | x |  |  |  |  |  | PM: it depends on the activities planned. The project aims to long term restoration and rehabilitation plans but it will include short term results to convince the target population of the approach and the overall goal |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agreed; local stakeholders need to see results so as to produce good practice for scale-up |  |  |  |  |  |  |
| Science and technological issues | Project based on sound science and well established technologies | Project testing approaches, methods or technologies but based on sound analysis of options and risks | Many scientific and /or technological uncertainties |  | x |  |  |  |  | PM: the approaches of rangeland are relatively new and under testing but its based on well-known methods and are developed based on the local knowledge along with experts in rangeland field |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Political influences | Project decisions and choices are not particularly politically driven | Signs that some project decisions are politically motivated | Project is subject to a variety of political influences that may jeopardize project objectives |  | x |  |  |  |  | PM: political influence can affect the decision but the project aims to introduce evidence based information and analysis to enrich the dialogue between stakeholders and decision makers |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Other, please specify. Add rows as necessary |  |  |  |  |  |  |  |  |  | PM: |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: |  |  |  |  |  |  |

|  |  |  |  | Project Manager Rating |  |  |  |  |  | Notes | Task Manager Rating |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Factor | Indicator of Low Risk | Indicator of Medium Risk | Indicator of High Risk | Low | Medium | Substantial | High | Not Applicable | To be determined |  | Low | Medium | Substantial | High | Not Applicable | To be determined |
| EXTERNAL RISK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project context |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Political stability | Political context is stable and safe | Political context is unstable but predictable and not a threat to project implementation | Very disruptive and volatile | x |  |  |  |  |  | PM: we are monitoring closely the situation in Egypt and working with government institution that to some extent guarantee the stability. | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Environmental conditions | Project area is not affected by severe weather events or major environmental stress factors | Project area is subject to more or less predictable disasters or changes | Project area has very harsh environmental conditions |  | x |  |  |  |  | PM: Project area is subject to more or less predictable disasters or changes |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Social, cultural and economic factors | There are no evident social, cultural and/or economic issues that may affect project performance and results | Social or economic issues or changes pose challenges to project implementation but mitigation strategies have been developed | Project is highly sensitive to economic fluctuations, to social issues or cultural barriers | x |  |  |  |  |  | PM: in the assessment phase none of the initial results indicate that there will be major issues or challenges. Minor issues are expected and within any project limitations | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Capacity issues | Sound technical and managerial capacity of institutions and other project partners | Weaknesses exist but have been identified and actions is taken to build the necessary capacity | Capacity is very low at all levels and partners require constant support and technical assistance |  | x |  |  |  |  | PM: some of the tools and approaches are new and to a minor degree challenging. The project follow up and support the partners to implement the activities. |  | X |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TM: agree |  |  |  |  |  |  |
| Others, please specify |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

If there is a significant (over 50% of risk factors) discrepancy between Project Manager and Task Manager rating, an explanation by the Task Manager should be provided below

TOP RISK MITIGATION PLAN

Rank – importance of risk Risk Statement – potential problem (condition and consequence) Action to take – action planned/taken to handle the risk Who – person(s) responsible for the action Date – date by which action needs to be or was completed

| Rank | Risk Statement |  | Action to Take | Who | Date |
| --- | --- | --- | --- | --- | --- |
|  | Condition | Consequence |  |  |  |

Project overall risk rating (Low, Medium, Substantial or High) (Please include PIR risk ratings for all prior periods, add columns as necessary):

| FY2018 rating | FY2019 rating | Comments/narrative justifying the current FY rating and any changes (positive or negative) in the rating since the previous reporting period |
| --- | --- | --- |
| L | L | The project takes good care of monitoring, assessing and mitigating risks. |
|  |  | If a risk mitigation plan had been presented for a previous period or as a result of the Mid-Term Review/Evaluation please report on progress or results of its implementation |

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Only for Substantial to High risk.