The Republic of Indonesia

# Integrated Management of Peatland Landscape in Indonesia (IMPLI)

Mid-term Review Report

| Type of mission | Mid-term Review (MTR) |
| --- | --- |
| Project Name | Integrated Management of Peatland Landscape in Indonesia (IMPLI) |
| Country | The Republic of Indonesia |
| Executing Agency | Ministry of Environment and Forestry (MoEF) Implemented by the Directorate of Peatland Degradation Control |
| Name of Project Director | M. Noor Andi Kusumah |
| Name of Project Manager | M. Askary |
| Date of mission (month/year) | 9-17 October 2024 |
| Project Area: | Sumatra Island (Riau, Jambi, South Sumatra Province) |
| Days in the field | 6 days (9-14 October 2024) |
| Field sites visited | Riau (Siak & Bengkalis District), South Sumatra (Ogan Komering Ilir, and Musi Banyuasin District) and Jambi (Muaro Jambi District) |
| Mission composition | Mr. Hani Elsadani Salem, IFAD Country Director for Indonesia, Malaysia and PNG, Prof. Damayanti Buchori, Independent Consultant and Team Leader, Mr. Praise Uke, Independent Consultant and Environment and Natural Resources Management Specialist (ENRMS), Mr. Muhammed Iskandar, Programme Analyst/ Procurement reviewer, IFAD Indonesia ICO, Ms. Rahmi Khalida, Targeting & Gender Social Inclusion Specialist, Ms. Chiara Merola, Programme Analyst/ Junior Professional Officer, IFAD Indonesia ICO, Mr. Dudy Nugroho, Natural Resources Specialist, IFAD Indonesia ICO |

Asia and the Pacific Division

Department of Country Operations

## List of acronyms

| ATFP | ASEAN Task Force on Peatlands |
| --- | --- |
| AMS | ASEAN Member State |
| APMS | ASEAN Peatland Management Strategy |
| AWPB | Annual Work Plan and Budget |
| BMP | Best Management Practices |
| BRGM | National Agency for Peat and Mangrove Restoration |
| DLH | District Environment Agency |
| DOA | Department of Agriculture |
| DPMU | District Project Management Unit |
| EA | Executing Agency |
| FA | Financial Agreement |
| FM | Financial Management |
| GEF | Global Environment Facility |
| GHG | Greenhouse Gas |
| GWL | Groundwater Level |
| IA | Implementing Agency |
| IFAD | International Fund for Agricultural Development |
| IFR | Interim Financial Report |
| IMP | Integrated Management Plan |
| IMPLI | Integrated Management of Peatland Landscapes in Indonesia |
| IP | Indigenous People |
| IPM | Integrated Peatland Management |
| KM | Knowledge Management |
| M&E | Monitoring and Evaluation |
| MoEF | Ministry of Environment & Forestry |
| MoHA | Ministry of Home Affairs |
| MoV | Ministry of Village |
| MTR NAPP | Mid Term Review National Action Plan on Peatland |
| NGO | Non-Governmental Organisation |
| NPMO | National Project Management Office |
| NPSC | National Peatland Steering Committee |
| OFP | Operational Focal Point |
| PDR | Project Design Report |
| PHU | Peatland Hydrology Unit |
| PIR | Project Implementation Report |
| PPMO | Provincial Project Management Office |
| RKM | Rencana Kerja Masyarakat (Community Work Plan) |
| RPJM | Medium-term Development Plan |
| RPPEG | Peat Ecosystem Management and Protection Plan |
| SiPPEG | System Information for Protection and Management of Peatland Ecosystems in Indonesia |
| SIMATAG | Peat Groundwater Information System |
| TK-PPEG | Community Task Force |
| TWG | Technical Working Group |

## Mission Objectives and Key Conclusions

### Background and main objectives of the mission

The “Integrated Management of Peatland Landscapes in Indonesia (IMPLI)” is a five-year project that aims to strengthen systems for sustainable management, biodiversity conservation, GHG emission reduction, and improved rural livelihoods in target peatlands of Indonesia. The project focuses on the following activities: i) strengthening institutional capacity, frameworks and partnerships for scaling-up of sustainable peatland restoration; ii) sustaining integrated management of priority Peatland Hydrological Units (PHUs) in Project provinces; and iii) developing and expanding sustainable peatland management knowledge, technologies, and markets. The project began on 22 July 2020, with an expected completion date of 30 September 2025 and financial closure on 31 March 2026. The total project cost is US$ 27,267,832, with GEF funding of US$ 4,895,872 and co-financing of US$ 22,371,960.

In 2022, the IMPLI project proposed to relocate one of the site projects from North Sumatra to South Sumatra to integrate the landscape in Riau-Jambi and South Sumatra, as these are the biggest Peat Hydrology Units (PHUs) which still have peat-dome. The proposal was approved in January 2022 by GEF Secretariat and got a No Objection from IFAD.

The Mid-term review (MTR) mission to IMPLI was conducted during 09 – 18 October 2024 in Indonesia (Jakarta, South Sumatra, Jambi & Riau). The overall objectives of the Mid-Term Review (MTR) are to: (i) assess the progress of the GEF6 IMPLI project's implementation according to its logical framework; (ii) identify challenges, best practices, and lessons learned; and (iii) support the project in expediting its implementation to meet project goals. The specific objectives are to assess the following: a) overall project management and institutional arrangements, b) achievements in technical and financial implementation, c) compliance with financial management and procurement standards, and d) monitoring and evaluation (M&E), as well as knowledge management.

The mission kick-off took place on 9 October 2024 at the MoEF Office in Jakarta, led by Mr. M. Andi Kusumah (Director of Peatland Degradation Control – MoEF). Field visits were conducted by two teams: one in Riau and another in South Sumatra & Jambi. The field mission was conducted from 9 to 14 October 2024. The MTR mission involved the national and provincial project management offices (NPMO/PPMOs), the District Project Management Unit (DPMU), and the community task force groups (TK-PPEG) across three provinces. The MTR monitored and validated the achievements of the IMPLI project, specifically in relation to integrated peatland management (IPM) within the targeted Peatland Hydrology Units (PHU).

A pre-wrap up meeting with the NPMO was held on 16 October, followed by an official wrap up meeting on 17 October chaired by Mr. M Andi Kusumah (Director of Peatland Degradation Control - MoEF). Representatives from Riau, Jambi, South Sumatra, independent consultants, the GEF OFP Indonesia, and the IFAD team attended. The mission would like to extend appreciation to the Government of Indonesia, the provinces and districts visited, line agencies, communities, and individual beneficiaries encountered for their cooperation, support, and hospitality provided to the mission.

### Mission methodology

The evaluation of the project was conducted using a comprehensive and systematic methodology designed to assess the project’s performance, outputs, and outcomes results against its objectives. The approach employed a mix of qualitative and quantitative methods to ensure a balanced and holistic understanding of the project's achievements and challenges. This section outlines the key methodological steps and tools used in the evaluation.

##### Desk Review of Project Documentation

The evaluation began with an in-depth review of key project documents, including:

  - The Project Design Report (PDR), which provided a baseline framework and initial project objectives.

  - Annual Work Plans and Budgets (AWPBs) from 2021, 2022, 2023, and 2024, which outlined planned activities, targets, and financial allocations.

  - Semi-Annual Reports (SAPRs) and Project Implementation Reports (PIRs) from 2021, 2022, 2023, and 2024, which detailed the progress, challenges, and adjustments made during implementation.

  - Audit reports, monitoring and evaluation (M&E) data, and knowledge products developed during the project.

- This desk review offered insights into the project’s design, implementation trajectory, and performance across its three components.

##### Stakeholder Consultations

Extensive consultations were conducted with a range of stakeholders to gather diverse perspectives on the project’s implementation and impact. These stakeholders included:

  - National-Level Actors: Representatives from the Ministry of Environment and Forestry (MoEF) and relevant directorates, namely Conservation & Biodiversity, and Badan Restorasi Gambut & Mangrove (National Agency for Peat & Mangrove Restoration), which contribute to co-financing this project and matching the program in the field.

  - Province-Level Authorities: Representatives from province environment and forestry departments in Riau, Jambi, and South Sumatra shared their experiences in developing the Rencana Perlindungan & Pengelolaan Ekosistem Gambut (RPPEG, or Province Action Plan for Peatlands), and District Action Plan for Peatland in Siak, Bengkalis, Muara Jambi, Tanjung Jabung Timur, Musi Banyuasin, and coordinating fire prevention strategies and the lessons learned.

  - Local Communities: Dialogues with community groups established by the GEF6 IMPLI, representatives from women’s groups, youth representatives, Indigenous Peoples (IPs), and smallholder farmers highlighted the social and economic impacts of the project at the community level.

  - Private Sector Partners: Feedback from plantation companies involved in Public-Private Partnerships (PPPs) highlighted the effectiveness of collaborative approaches to economic development, fire prevention, integrated peatland management, and sustainable agriculture.

- These consultations were conducted through structured interviews, focus group discussions, and participatory workshops. The data collected was used to validate findings from the desk review and to provide context-specific insights.

##### Field Visits and Observations

Field visits were conducted to selected project sites across the Riau, Jambi and South Sumatra Province. Three villages were visited in Riau, namely Tasik Serai, Dayun and Rawa Mekar Jaya. The villages visited in Jambi were Jebus and Sungai Aur, and in South Sumatra the mission visited Tanjung Menang and Muara Medak village. The MTR mission held meetings with provincial and district government agencies and with local private sector actors. The visits involved observing 3R project activities (Rewetting, Revegetation, Revitalization), such as canal blocking, hydrology management, land restoration, community fire patrols, sustainable agriculture, and rehabilitation efforts.

### Key mission agreements and Conclusions

- Main findings and conclusion.

The Integrated Management of Peatland Landscapes Initiative (IMPLI) project is scheduled for completion over a period of 5 years and 2 months, from July 2020 to September 2025. To date, IFAD has disbursed USD 3,065,035, representing 63% of the total GEF allocation of USD 4,895,872; while actual fund utilization has reached only USD 1.818 million, or 37% of the total budget. The project forecasts to reach a total expenditure of USD 2.5 million, or 51% of the total GEF allocation, by the end of 2024. The project experienced significant challenges in its early years due to external disruptions, including the COVID-19 pandemic, the severe El Niño event of 2023, subsequent La Niña conditions in early 2024, and restrictions related to Indonesia’s 2024 general elections. These factors were compounded by delays in finalizing the Project Implementation Manual (PIM), primarily due to the relocation of a project site from North Sumatra to South Sumatra, and by persistent staffing issues. A shortage of technical personnel continued until mid-2023, while the absence of a designated definitive project director and team leader until January 2024 further affected coordination and overall progress.

Following the resolution of these issues, including the appointment of definitive project director by the MoEF, a team leader (national project coordinator), strengthened staffing, and the completion of critical start-up requirements, the project recorded significant improvements in its implementation performance. It is now expected to progress steadily during the remaining implementation period.

Notable progress has been made in strengthening inter-agency coordination under the project. The highest budget absorption was recorded in the Workshops category at 92%, driven mainly by international activities such as regional workshops and participation in the UNFCCC COP 28 event. The Consultancy category achieved a 63% disbursement rate, reflecting the frequency of coordination and field activities. Meanwhile, expenditure for salaries and allowances reached 46%, influenced by high staff turnover, which may indicate the need for adjustments in remuneration packages. The current Salaries and Allowances Category allocation is nevertheless expected to suffice until project completion. Conversely, disbursement for goods, services, and inputs reached only 37%, falling short of expectations due to delays in procurement caused by the vacancy of a procurement officer, leading to suboptimal contract management. Certain field activities, including demonstration plots in several villages, have also been hindered by environmental factors such as saltwater intrusion and drought. Furthermore, closer coordination with Badan Restorasi Gambut & Mangrove (BRGM) is required to prevent overlapping rewetting and restoration activities. To optimize remaining funds, resources can be reallocated from underutilized categories such as operating costs and training, while project management expenses are to remain below 5% of the total budget. This strategy is expected to enhance project management efficiency and facilitate the timely completion of delayed physical development activities.

The IMPLI project has made substantial progress in promoting inter-agency coordination and establishing strategic partnerships with relevant stakeholders. The project has been collaborating with the National Agency for Peat and Mangrove Restoration (BRGM) and other stakeholders to develop and finalize Peat Ecosystem Management and Protection Plans (RPPEG) at both provincial and district levels, supporting the field implementation of the National Action Plan for Peatlands (NAPP). RPPEGs have been completed in the three target provinces, Riau, Jambi, and South Sumatra. At the district level (Siak, Bengkalis, Muaro Jambi, and Musi Banyuasin), RPPEGs are expected to be finalized by the end of 2024.

The Ministry of Environment and Forestry (MoEF) and the Ministry of Home Affairs (MoHA) have reached an agreement to integrate the regional RPPEGs into medium-term development plans (RPJM), in line with Ministerial Decree No. 600.11.1/3048/bangda, issued on May 3, 2024. Simultaneously, the MoEF and the Ministry of Villages and Transmigration (MoV) have established a partnership to optimize the use of village funds (Dana Desa) for sustainable peatland management, building on lessons learned from the GEF5 SMPEI project. This collaboration aims to scale up project interventions to the business level for greater economic and environmental impact.

Important training programs have been delivered to village facilitators. The IMPLI project provided training to village facilitators through a Technical Guidance event aimed at strengthening knowledge and skills in peat ecosystem restoration and community engagement. The training covered key topics such as peatland management policies, village fund access, community empowerment strategies, facilitator performance, and activity planning, combined with practical field visits to demonstration plots. A total of 73 facilitators (50 men, 23 women) participated. This activity contributes to Component 1 (institutional capacity and partnerships) by enhancing facilitators' ability to engage communities, disseminate policy information, and support local institutional processes, and to Component 2 (integrated PHU management) by enabling facilitators to mobilise communities for peatland restoration activities, oversee demonstration plots, and assist in planning and monitoring restoration initiatives within PHUs.

The IMPLI Project successfully advanced private sector engagement across its priority peatland landscapes, securing the participation of 14 concessionaire companies managing over 571,127 hectares. Through technical consultations and formal agreements, these companies committed to implementing mandated peatland restoration measures and contributing to national environmental performance frameworks like PROPER. The project also mobilised private sector support for peatland monitoring by facilitating data-sharing partnerships for Groundwater Level (GWL) and CO₂ emissions (via Eddy Covariance stations), while encouraging contributions to community development through CSR initiatives and multi-stakeholder coordination at the district level.

Further support is provided to demonstration plots and community enterprises managed by TK-PPEG groups in target villages. Community engagement to date has focused on promoting sustainable practices aligned with ISPO/RSPO and FSC standards. IMPLI has supported the formation of Peat Ecosystem Management Group Teams (TK-PPEG) and local farmer collectives to build land management capacity. Yet stronger, more coordinated partnerships with clear common targets and entry points are needed, especially given ongoing gaps in training and technical assistance that continue to slow implementation. Addressing remaining challenges will require ramping up field monitoring systems and extending tailored training and technical support to both communities and concessionaires.

The project also successfully supported further development and scaling of the System Information for Protection and Management of Peatland Ecosystems in Indonesia (SiPPEG) web-based communication platform, originally created through the GEF5 SMPEI project. SiPPEG now operates across the three provinces of Riau, Jambi, and South Sumatra, supporting improved stakeholder coordination, real-time data sharing, and early warning systems for fire prevention. In addition, SIMATAG is being used to monitor groundwater levels within peatland areas. The Ministry of Environment and Forestry (MoEF) introduced the SiPPEG system to the ASEAN Task Force on Peatland (ATFP) members during regional workshop events. This initiative aimed to enhance collaboration and knowledge-sharing among stakeholders involved in peatland management across ASEAN countries.

Beyond monitoring and communication platforms, IMPLI has contributed to market development initiatives for ecologically valuable peat products. In Muara Medak, South Sumatra, the village community group (TK-PPEG) has initiated marketing efforts for livestock products, which are connected to the local production and use of solid and liquid fertilizers. The revenue generated from the sale of this fertilizer is allocated to initiatives aimed at preventing peatland fires and promoting sustainable peatland management. These efforts include fire monitoring, early warning systems, community engagement programs, and ecological restoration activities, ensuring the long-term preservation and responsible use of peatland ecosystems. Similar initiatives in other villages have not yet achieved the same level of success. The District Environment Agency (DLH) of Jambi Province had intended to act as a marketing hub for TK-PPEG products by connecting them with a business incubation program. However, progress in developing high-value peatland-based products has been limited, highlighting the need for continued efforts to strengthen market opportunities and foster product innovation.

Key mission agreements are highlighted below. The mission recommends a series of follow-up actions:

- Based on discussions during the MTR with PPMO/DPMU/TK-PPEG and due to the constraints faced during the first years of implementation (COVID-19, El Nino, project site relocation and staffing issues), it was concluded that a longer project timeframe was necessary, leading to a recommendation for an extension of 18 months.

- Government Engagement: The project should organize meetings with the new governor or mayor to present the IMPLI project, seek support for the integration and execution of the RPPEG plans, and secure commitment from the new administration concerning the sustainability program.

- Address Muara Jambi's request to align RPPEG and Spatial Planning (RTRW) definitions for the peatland protection zone: RPPEG requires >3 meters, while Bappeda requires >5 meters.

- NPMO and provincial PMOs in coordination with IFAD must recruit specialized procurement and contract management officers to expedite the procurement process and ensure timely execution of all contracts.

- The finance team, NPMO, and IFAD will reassess the unutilized budget for reallocation. Unused 2024 Training funds (category IV) should be redirected to the TK-PPEG community group immediately.

- The NPMO and PPMO may need to conduct retraining for village facilitators who have difficulties in understanding the project, as well as further technical training to support field management.

- The NPMO and BRGM need to ensure the synchronization of peatland restoration activities, especially regarding the finalization and implementation of RPPEG plans in target provinces.

- Strengthen and routinely update the M&E system to ensure comprehensive reporting of project outputs and results. The project should also finalise the Tier-2 GHG monitoring methodology and begin reporting on the GEF-6 core indicators, which have not been included in monitoring activities to date.

- The project should develop an exit strategy.

- Conduct the National Steering Committee (NSC) meeting in November 2024 regarding the No Cost Extension (NCE) proposal, AWPB-2025, and national guidance under the new cabinet.

The mission recommended to maintain a Moderately Satisfactory (MS) rating for the overall project implementation performance, subject to IFAD and GEF management review.

## Overview and Project Progress

- Component 1 – Institutional Capacity, Frameworks and Partnerships for scaling up of peatland management operational.

Component 1 aims to enhance national frameworks for sustainable peatland management by improving multi-sector collaboration, policy coherence, and resource utilisation in Riau, Jambi, and South Sumatra. It focuses on implementing the National Action Plan for Peatlands (NAPP or RPPEG) and its related policies, while strengthening institutional capacities and governance systems among key stakeholders at national and sub-national levels. The Ministry of Home Affairs (MoHA) supports the Ministry of Environment and Forestry (MoEF) in ensuring that national regulations on peatland protection, particularly Government Regulations PP71/2014 and PP57/2016, are effectively aligned with provincial and district Medium-Term Development Plans (RPJMD) and operationalized through legal instruments at the local level.

A core feature of Component 1 is to support the preparation and finalization of Peatland Ecosystem Protection and Management Plans (RPPEG), which serve as the official regulatory framework governing the management of peatlands at district and provincial levels. These plans are critical instruments under Indonesia’s regulatory framework for peatland protection. Through the RPPEG process, peatlands within a Peat Hydrological Unit (PHU) are formally:

Classified into protection or conservation for peat depths greater than 3 meters and cultivation zones for peat depths less than 3 meters.

Subject to regulations on land-use zoning, protection, utilization, and hydrological management.

Positioned as a tool to operationalize national policy frameworks (PP71/2014 and PP57/2016) at the local level, ensuring that government priorities for peatland restoration and emissions reduction are translated into actionable district and provincial regulations.

By supporting RPPEG strengthening under Component 1, the IMPLI Project provides a critical policy-making, institutional planning, and regulatory capacity-building function for Indonesia’s peatland governance system. The drafting, multi-stakeholder consultation, and formal endorsement of RPPEGs ensures that enabling regulatory frameworks are in place prior to operational interventions on the ground under Component 2.

Component 1 has a total allocation of USD 1,098,460 million all financiers combined (4% of total project allocation), and a GEF grant allocation of USD 978,344 million (20% of the total GEF grant). By September 2024, the project achieved a disbursement of USD 506,145 under component 1, or 51.7% of its total GEF allocation.

Output 1.1 - Capacity Building of key stakeholders in sustainable peatland management.

The IMPLI Project supported sub-national governments in the preparation, drafting, and public consultations of Peatland Ecosystem Protection and Management Plan (RPPEG) documents in all three targeted provinces of Riau, South Sumatra, and Jambi. The three provincial RPPEGs cover a total area of 7,981,429.50 ha of peatland landscapes, disaggregated as 904,422.82 ha in Jambi, 4,984,688.74 ha in Riau, and 2,092,317.94 ha in South Sumatra. The provincial RPPEG plans have been finalized and are now being reviewed by the Ministry of Environment and Forestry (MoEF) for their approval and entry into force, expected by the end of 2025. It is important to note that these results were achieved with significant co-financing contributions from ICRAF in South Sumatra, BRGM in Jambi, and UNDP through BRGM in Riau.

The IMPLI project supported consultations and drafting of district-level RPPEGs for four priority districts within the three targeted provinces: Siak and Bengkalis (Riau Province), Muaro Jambi (Jambi Province), and Musi Banyuasin (South Sumatra Province). The district level RPPEGs cover a total area of 3,430,677 hectares, with the following details: Siak spans 782,181 hectares, Bengkalis approximately 697,300 hectares, Muaro Jambi amounts to 524,600 hectares, and Musi Banyuasin covers 1,426,596 hectares. Draft RPPEGs for all four districts are expected to be completed by the end of 2024, for their review by the Directorate of Peatland Ecosystem Degradation Control (DPEDC) of the MoEF, with formal endorsement expected by Q2 2025.

Through these RPPEG processes, the project has directly been supporting:

  - The definition of conservation and cultivation zones within peat hydrological units (PHUs), setting the legal basis for where peatlands can be protected and where limited utilization activities may occur under sustainable management principles.

  - The operationalisation of national policy frameworks (PP71/2014 and PP57/2016) at the district and provincial levels, ensuring that central government mandates for peatland restoration, hydrological management, and fire prevention are formally reflected in sub-national regulations.

  - The establishment of regulatory instruments that formally regulate land-use zoning, hydrological management regimes, protection protocols, and utilization activities in compliance with the national legal framework for peatland protection.

Key activities included socialisation meetings, focus group discussions (FGDs), and public consultations, conducted between July to October 2024. These activities are needed for the project to comply with the GoI’s and IFAD’s safeguard procedures and to ensure inclusive participation of local communities, indigenous groups, government agencies, and private sector actors in the RPPEG development process.

Multi-stakeholder coordination mechanisms have been established, including the National Steering Committee (NSC), which facilitates policy dialogues at the national, ASEAN, and international levels. The National Steering Committee (NSC) holds an annual meeting, led by the Director General (DG), with the first session initiated in 2021.

In parallel, IMPLI facilitated coordination between the Ministry of Environment and Forestry (MoEF) and the Ministry of Village (MoV) to support the incorporation of peatland management priorities into village development planning and the Village Fund allocation mechanism, as outlined in Ministry Decree No. 8 of 2022 on climate village programs. Initiated during the Inception Workshop in 2023 and followed by subsequent workshops involving MoEF and MoV throughout 2023 and 2024, this initiative resulted in villages, through the Peatland Community Group (TK-PPEG), being able to submit proposals for accessing village funds. This alignment enables village programs to be scaled for broader impact and improved outcomes. Village facilitators were trained to act as key intermediaries between project teams, local authorities, and communities, with the aim to support the dissemination of information about peat ecosystem management policies, facilitate participatory processes, and support the organisation of community groups involved in peatland restoration activities.

Complementing these governance efforts, private‑sector engagement is underway across several priority landscapes in Riau, Jambi and South Sumatra Province (including Siak, Bengkalis, Muaro Jambi, Musi Banyuasin and Ogan Komering Hilir), bringing together 14 concessionaires (11 industrial forest concessions and 3 oil palm plantations) covering 571,127 ha within the IMPLI Project’s targeted PHUs. These companies have participated in technical discussions with the Directorate of Peatland Ecosystem Protection and Management (PEPM), focusing on the preparation, review, and finalisation of their peatland recovery plans, which were subsequently formalised through Deputy-level Decrees mandating the implementation of peatland restoration measures within concession areas. Additionally, eligible companies were incorporated into the PROPER list, which represents the company performance rating assessment conducted by the Government of Indonesia. Going forward, it is advisable for the project to strengthen its field monitoring systems in order to more effectively assess the implementation and success of these restoration commitments.

Furthermore, the project deepened collaboration with major forestry concessions, as well as oil palm companies operating in Sumatra. IMPLI facilitated district-level multi-stakeholder meetings to mobilise corporate social responsibility (CSR) and Corporate Social Value (CSV) resources in support of peatland restoration and community development initiatives. The project also encouraged private sector participation in the development of a CO₂ emission monitoring methodology based on Groundwater Level (GWL) measurements, securing private sector contributions of Eddy Covariance datasets for this purpose. Additionally, concessionaires were encouraged to share GWL data through the Peat Groundwater Information System (SIMATAG) to enhance ecosystem monitoring and fire early warning systems, and improving the overall peat hydrology management capacity of the MoEF.

The project also produced over 20 technical knowledge products and publications, participated to the COP 28 UNFCCC, and facilitated Indonesia’s representation in three regional and ASEAN-level peatland governance forums to share lessons learned and policy innovations. These high-level knowledge exchange platforms strengthened Indonesia’s leadership in regional peatland restoration and climate action initiatives.

The development of investment frameworks for sustainable peatland management remains at a conceptual stage. The framework aims to mobilize funding for peatland conservation from national, international, and private sources, supporting long-term project sustainability. Initial scoping discussions and thematic consultations were held in 2024, with a structured framework development process scheduled for 2025 in alignment with the ASEAN Peatland Management Strategy (APMS) and national climate financing priorities.

Achievements and Challenges under Component 1

Component 1 has progressed in supporting the enabling environment for sustainable peatland management. Provincial regulations have been developed concerning sustainable management practices for 7,981,429.50 ha of land in the provinces of Riau, Jambi, and South Sumatra. These achievements were made possible through combined efforts and co-financing support from ICRAF in South Sumatra, BRGM in Jambi, and UNDP through BRGM in Riau. District-level plans are also being prepared in four priority districts within these provinces, with drafts of the district-level RPPEGs scheduled for completion by December 2024. Unlike the provincial plans, the preparation of these district-level RPPEGs has been fully funded by the GEF allocation under the IMPLI Project. The district-level RPPEGs cover a total area of 3,430,677 hectares, with the following details: Siak spans 782,181 hectares, Bengkalis approximately 697,300 hectares, Muaro Jambi amounts to 524,600 hectares, and Musi Banyuasin covers 1,426,596 hectares.

The preparation of these RRPEGs represents a substantial institutional achievement, as these regulatory documents provide formal mechanisms to:

  - Classify peatlands and regulate land-use zoning, hydrology, and resource use within priority PHUs.

  - Operationalize national peatland protection policies at the sub-national level, ensuring alignment between central government priorities and district-level governance.

  - Provide legal certainty and enforceable standards for peatland hydrological management, fire prevention, and sustainable use of rewetted peatlands.

The project’s work in policy-making, institutional planning, and regulatory capacity building through the RPPEG drafting, consultation, and endorsement processes has directly strengthened sub-national governance structures, improved inter-agency coordination, and built technical competencies within provincial and district administrations.

The project has successfully established multi-stakeholder coordination mechanisms, such as the National Steering Committee (NSC), which have facilitated enhanced policy dialogues and collaborative planning.

Challenges encountered under Component 1 include delays in the implementation of key policy initiatives and RPPEG finalization due to complex administrative procedures, overlapping agency mandates, and coordination bottlenecks. Limited institutional capacity at the provincial level, coupled with inadequate technical skills, have also hindered the consistent application of sustainable peatland management principles.

Moreover, efforts to engage the private sector in policy dialogue have faced barriers, such as divergent priorities and a lack of economic incentives for sustainable practices. The development of the investment framework has been delayed due to resource constraints and a need for more in-depth stakeholder consultations to secure broader ownership. Despite these challenges, there is strong government ownership of peatland policies, indicating the potential for further progress if implementation issues are resolved and private sector engagement is strengthened.

- Component 2 – Integrated management of priority Peatland Hydrological Units (PHUs) in Project Provinces sustained.

Component 2 aims to sustain integrated management of priority PHUs, addressing both conservation and sustainable utilization needs. The component has a total allocation of USD 20,540,761 million all financiers combined (75% of total project allocation), and a GEF grant amounting USD 3,054,424 million (62% of total GEF grant). As of September 2024, the project reported a disbursement of USD 1,149,579 under Component 2, or 37.6% of its GEF allocation. The component’s outputs are progressing as follows:

Output 2.1 - Sustainable integrated management of the Giam Siak Kecil-Bukit Batu Peatland Landscape

Participatory mapping of peatland hydrological units (PHUs) at a scale of 1:50,000 has been successfully completed in 2024, covering a total area of 2,567,072 ha, as shown in Annex 1. The IMPLI project directly funded the inventory of two PHUs in the Giam Siak Kecil – Bukit Batu Peatland Landscape (GSK-BB) covering a total area of 1,555,387 ha. The PHU of Sungai Siak Kecil – Sungai Siak, also part of the GSK-BB landscape, was inventoried with co-financing from the SMPEI project, for an area of 163,787 ha. The Sungai Rokan Kiri–Sungai Mandau and Sungai Bangko – Sungai Rokan Kanan PHUs cover an additional 147,335 ha of peatland area within the Riau province and were inventoried by co-financing funds.

The project supported the negotiation of concessionaire management agreements with private companies managing areas of land encompassed in the targeted peatland landscapes. The list of concessionaire agreements can be found in Annex 2. These agreements, enacted through Directorate General Decrees, require the mandatory implementation of rehabilitation measures across 571,127 hectares of peatland. In addition to committing to these restoration obligations, the private sector partners have also agreed to share data on the status of the land under their management, including groundwater level (GWL) data and CO₂ emissions data collected through Eddy Covariance stations, to strengthen integrated peatland monitoring, inform decision-making, and support transparency in reporting.

The IMPLI project also supported community engagement and rehabilitation activities in four villages in Riau Province: Tasik Serai, Rawa Mekar Jaya, Dayun, and Temiang. The activities encompassed assessments of land use, water management infrastructure, and the socio-economic profiles of local communities, providing valuable insights for sustainable peatland management. Demonstration plots for agro-silvo-fishery and paludiculture models were established in Tasik Serai, Rawa Mekar Jaya, and Dayun villages. The construction of canal blocking infrastructure was planned in Tasik Serai to restore peat hydrology and support sustainable land-use trials. These pilot sites demonstrated adaptive peatland cultivation techniques using paludiculture species and aquaculture integration on rewetted peatlands.

In addition, a total of 81 smallholders with small plantations in Riau participated in training on ISPO/RSPO standards. The details are as follows: Dayun had 96 hectares from 20 smallholder households, Rawa Mekar Jaya had 20 hectares from 20 smallholder households, Temiang had 55 hectares from 20 smallholder households, and Tasik Serai had 35 hectares from 21 smallholder households. Challenges included procurement delays for demonstration plot inputs, impacts of El Niño-induced drought and fire outbreaks in 2023.

A baseline study on peat hydrology and emissions factors was completed for the Giam Siak Kecil-Bukit Batu (GSK-BB) landscape in Riau by the end of 2023. The data and information are providing a foundational dataset for monitoring peatland health, fire risks, GHG emissions trends and for management planning. Building on this baseline, the SIMATAG and SiPPEG web-based platforms are operational in collecting, managing, and sharing data, including Eddy Covariance emissions data and groundwater level (GWL) measurements, to support ongoing monitoring, emissions estimation, fire early warning, and adaptive management decisions in peatland areas.

Output 2.2 - Support Sustainable Peatland Management in Jambi and South Sumatra provinces

Peatland inventories and mapping at a 1:50,000 scale were completed for the following PHUs in the provinces of Jambi and South Sumatra:

Sungai Batanghari – Sungai Air Hitam Laut; 183,862 ha

Sungai Air Hitam Laut-Sungai Buntu Kecil; 183,856 ha

Sungai Merang-Sungai Ngirawan; 82,021 ha

Sungai Ngirawan-Sungai Sembilang; 73,475 ha

Sungai Sembilang-Sungai Lalan; 84,670 ha

Sungai Burnai-Sungai Sibumbung; 86,679 ha

Participatory mapping and PHU-specific management plan preparation were conducted in project villages in Jambi and South Sumatra. As of September 2024, management plans for PHUs in these provinces are under review, with alignment to RPPEG processes ongoing. The management plans address zoning for conservation, sustainable land use, fire management, water management, and livelihood improvement strategies.

A baseline study for the PHUs in Jambi and South Sumatra was conducted, covering ecological, hydrological, social, and economic conditions, and completed by the IMPLI project in 2023. Plans are in place to conduct environmental and social assessments and fire and water management planning, based on national standards and community participation. Additionally, management plans aligned with RPPEG processes are under development, pending review and finalization.

Achievements and Challenges under Component 2

Component 2 made considerable progress in advancing integrated peatland landscape management practices through participatory mapping, pilot demonstration sites, baseline assessments, and the preparation of PHU-specific management plans. The inventoried PHUs cover an area of 2,567,072 ha, with details provided in Annex 1. The IMPLI project directly funded the inventory of PHUs for a total of 1,555,387 ha under the Giam Siak Kecil – Bukit Batu peatland landscape, and an additional 1,011,685 ha were inventoried by co-financing funds.

IMPLI supported the negotiation and establishment of concessionaire management agreements with private entities managing 571,127 ha of peatland, requiring the implementation of rehabilitation activities and the sharing with the MoEF of data regarding the status of the peatland area under private concession. The project established demonstration plots for sustainable livelihoods, set the foundations for improved hydrological management through the planning of key canals blocking, and introduced adaptive agricultural models appropriate for rewetted peatlands.

Village facilitators benefited from extensive capacity building activities. Facilitators within the IMPLI project are responsible for mobilising communities to implement field-based restoration activities, including the establishment and maintenance of demonstration plots and community action plans within PHUs. They support data collection, assist in identifying local issues, and help plan and monitor restoration efforts in collaboration with technical teams. Their role ensures that restoration activities are community-driven, well-coordinated, and aligned with project objectives for sustainable peatland management.

Key achievements include:

Completion of baseline mapping and inventories for all project PHUs, covering 2,567,072 ha of peatland landscapes

Formalisation via Directorate General Decrees of concessionaire management agreements regulating the rehabilitation and sustainable management monitoring of 571,127 ha of peatland area

Demonstration of agro-silvo-fishery and paludiculture models in target villages

Active community engagement in land-use planning processes

Several challenges have hindered further progress. The El Niño-induced fires in mid-2023 severely impacted peatland ecosystems, diverting resources and delaying implementation. While private sector involvement has advanced, it should be further strengthened, particularly in priority areas such as the GSK-BB Biosphere Reserve, which encompasses 76% of the IMPLI Project’s target area. Coordination complexities across administrative levels have also affected decision-making processes, slowing the adoption of action plans.

The community task force (TK-PPEG) established by the village head is currently limited to members of the village. This limitation may result in ineffective stakeholder engagement, weak involvement of the government and private sector, and missed opportunities for community capacity building. Therefore, the task force requires further enhancement by including primary stakeholders to effectively address the village’s issues and implement the community-prepared work plan. For instance, the engagement with related government entities (e.g. agriculture office), and private sectors that located surrounding the village.

Furthermore, slow disbursement rates have constrained the scaling of integrated management activities at the community level, impacting timely interventions.

Overcoming these challenges will require enhanced stakeholder collaboration, targeted capacity-building efforts, and accelerated fund disbursement to ensure sustainable impacts and replication across Indonesia’s priority peatlands.

- Component 3 – Sustainable Peatland Management Knowledge, Technologies, and Markets developed and expanded

Component 3 aims to promote innovative technologies and market development to support the sustainable use of converted peatlands and improve community livelihoods. The total allocation for this component is USD 5,165,607 million from all financiers combined, representing 19% of the total project allocation. The GEF grant amounts to USD 608,846 million, which constitutes 12% of the total GEF grant. As of September 2024, the project has reported a financial achievement of USD 1,330 under Component 3, reflecting a disbursement of 0.2% of its GEF grant allocation. The component’s outputs are progressing as follows:

Output 3.1 - Partnership platform and dissemination of best practices for peatland policy and management

The IMPLI Project supported the expansion of the SiPPEG and SiMATAG platforms, which were originally developed by MoEF with assistance from the GEF-5 SMPEI Project, to extend operational coverage to Riau, Jambi, and South Sumatra provinces. SiMATAG was updated to run on a Linux-based operating system and now includes additional reporting and PROPER evaluation modules for peat hydrology management. MoEF has also presented SiPPEG to Southeast Asian (ASEAN) member countries during two ASEAN Task Force Peatland (ATFP) meetings in 2023 and 2024, as well as at regional events such as the knowledge sharing session of the MAHFSA project.

Datalogger installation began at selected demonstration and monitoring sites to deliver real-time groundwater level data, thereby supporting data-driven decision-making for hydrological restoration and fire risk mitigation. The IMPLI project has deployed 11 automatic dataloggers across three provinces (four in Riau, four in Jambi, and three in South Sumatra), contributing valuable data to both provincial and national early warning systems for fire prevention and greenhouse gas emissions monitoring.

Jambi Province is using its provincial forum to plan the peatland information working group, promote local economic products, support marketing efforts, and develop an exit strategy. Communication and coordination forums at national, provincial, and district levels have enhanced project governance and collaboration among stakeholders.

Output 3.2 - Technology and markets for the sustainable use of already converted peatlands

The project continued developing a Tier-2 GHG emissions estimation methodology for peatlands, which began in 2023 and received modification approval from MoEF. By September 2024, multiple meetings and workshops had been held to enhance the methodology. A general model estimation was created for most land cover types; however, there remained considerable uncertainty in plantations (R²=0.49; p<0.01) and agricultural zones. The final methodology is expected to be completed by Q3-2025.

At community level, the IMPLI has established 13 task-force or community groups (TK-PPEG) involving communities in three provinces, identified the villages’ common issues, potential stakeholders and supported the community to implement the community work plans (RKM) that focus on sustainable land use, conserving biodiversity, reducing/mitigating carbon emissions, and enhancing local livelihoods through eco-friendly practices. The project involved 284 households in the community task groups, out of which 95 are reported to be women-headed.

The IMPLI project has recorded successful cases in the enhancement of commodities and markets through the RKM (community work plans), supporting the development of two high-value ecologically beneficial peatland product. These includes the development of a watermelon syrup production centre in Dayun Village (Riau) and honeybee cultivation by the community group in Muara Medak (South Sumatra), and integrating them with district-level markets. The project also promotes silvo-agro-pastoral models in Sungai Aur (Jambi) and Muara Medak to revitalize communities, prevent peatland conversion from forestry to agriculture, and reward communities for mitigating village fires.

Initial exploratory discussions were held with Javara (a socially driven agribusiness company) and a leading pulp and paper company’s CSR division to scope out potential value chain partnerships for peatland-compatible commodities. These include sago, purun grass, honey, and other rewetted peatland products. A market research study is scheduled for 2025 to assess commodity competitiveness, value chain readiness, and sustainable business model options

Achievements and Challenges under Component 3.

Despite a low disbursement rate, Component 3 has made valuable progress in upgrading digital peatland data management systems, advancing emissions monitoring methodologies, and initiating market-based livelihood development discussions. Noteworthy achievements include:

  - SiPPEG and SiMATAG platforms were expanded and put into operation, with automatic data loggers added in three provinces to support national fire mitigation via early warning systems.

  - Enhancement of advanced water monitoring systems utilizing field-installed dataloggers

  - Progress on the development of a Tier-2 emissions estimation model for peatlands

  - Early-stage private sector engagement for commodity value chain development

Market development efforts have also progressed, with initial discussions involving private sector stakeholders to establish value chains for peat-based commodities like sago, biochar, and palm sugar.

Limited access to markets, inadequate infrastructure, and high logistical costs have constrained the scale and impact of value chain development for peatland products. Moreover, the adoption of sustainable technologies has been slower than expected due to insufficient capacity among local stakeholders and technical difficulties in implementing advanced methodologies like Tier-2 GHG measurement in remote areas. Additionally, while “SiPPEG” has been successful in improving coordination and data accessibility, it has encountered issues related to user training, data integration across agencies, and sustaining engagement, particularly at the community level where digital literacy remains low.

The project must address these challenges to enhance the sustainability and scalability of its interventions. The project may consider involving relevant sectors as part of the task force (TK-PPEG) to enhance community capacity building. For example, the local Agricultural Office (Dinas Pertanian) could assist farmers with production, the Cooperative Office (Dinas Koperasi) could enhance the value chain, and financial institutions could provide access to finance. Engaging the appropriate sectors and securing their support for the TK-PPEG would enable the development and effective implementation of the proposal. Prioritizing capacity-building, investing in market linkages, and improving infrastructure will be essential to leverage the outcomes achieved under Component 3. Additionally, integrating local knowledge with advanced technologies, alongside continued engagement with private sector partners, will be critical to ensure long-term impacts and achieve the broader goals of sustainable peatland management in Indonesia.

## Project implementation

- Effectiveness and Development Focus

## Development effectiveness (rating: Moderately Satisfactory)

The IMPLI project remains committed to addressing the multifaceted challenges associated with sustainable peatland management (SPM) in Indonesia, particularly following the resolution of initial factors that contributed to implementation delays. These efforts require coordinated and complementary actions across various thematic areas at multiple geographic levels, alongside systematic monitoring. All three components of the project have initiated their key activities with varying operational effectiveness but consistently support multi-sectoral policy dialogues at regional, national, provincial, and community levels. These activities benefit local communities and engage the private sector across targeted peatland landscapes. Despite challenges with low disbursement rates and incomplete outcome-level assessments, the project has demonstrated improved implementation effectiveness of the AWPB over the years. Further improvements are anticipated if the MTR's recommendations are timely addressed.

- Targeting and outreach (rating: Moderately Satisfactory).

The overall project goal for Core Indicator 11 (Number of direct beneficiaries disaggregated by gender as a co-benefit of GEF investment) is to reach 5,000 households through direct intervention and 15,000 households through indirect intervention. The mid-term outreach target stands at 2,000 households for direct intervention and 7,000 households for indirect intervention. As of September 2024, the project has directly engaged 1,830 households, representing 90% of the mid-term target. This achievement reflects documented activities conducted through community working groups, training sessions, and workshops at national, district, and community levels. It moreover includes households receiving media campaigns and publications, and covered by water and fire prevention management activities. Of the households reached, approximately 43% are reported to be women-led.

The project may have reached more households than currently reported. Documentation is incomplete for several activities, including initial community-level socialization of the IMPLI project, the involvement of smallholders in targeted fire prevention areas, and public awareness initiatives. To address these gaps, the project team has started developing a Management Information System (MIS). An effective monitoring system is required before 2024. It is also recommended to incorporate gender indicators into the monitoring system.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Develop a targeting strategy including women and youth for the remaining targets and timeline | PMO | Q1 2025 | Agreed |

- Gender equality & women’s participation (rating: Moderately satisfactory).

The IMPLI project has demonstrated a strong commitment to gender equality and social inclusion by integrating gender-related activities into its Annual Work Plan and Budget (AWPB), with a target of 40% female participation. Out of the 1830 HHs directly benefitting from the project, 785 were headed by women, representing 43% of the outreach. This commitment is also evident in the project's initiatives to promote women's involvement in various Community Work Plan (RKM) activities, such as leadership in small business enterprises, agricultural demonstration plots, and community consultations. In Jebus Village, female members of the TK-PPEG successfully initiated a profit-sharing model for poultry farming, ensuring transparent and fair management of community enterprises. Additionally, women’s groups have partnered with TK-PPEG in field schools, harvesting, and marketing of demonstration plot products.

At the institutional level, the project has ensured female leadership within its management structure, with women serving as National Project Management Office (NPMO) Team Leaders in both 2023 and 2024, and holding key roles at the provincial level in Jambi. Impressively, 55% of decision-making positions from the National Project Management Office (PMO) down to the district level are held by women, underscoring the project's commitment to promoting women's leadership.

Despite these achievements, women's involvement in community planning, decision-making, and livelihood activities at the local level remains low, with a majority of male participants still being recorded. This indicates a gap between the project's participation targets and the actual engagement of women in these critical areas. Furthermore, gender-sensitive assessments of benefit-sharing arrangements have revealed an unequal distribution, with 79.75% of direct benefits from community working plans received by men, compared to only 20.25% by women. The absence of gender and social inclusion specialists has further hindered the development of comprehensive strategies to address these issues.

To address these challenges, the mission recognizes the need to engage gender specialists and designate gender focal points to perform a gender analysis and formulate a comprehensive gender strategy. This strategy should aim to systematically strengthen, coordinate, and expand gender equality initiatives across all project components. Additionally, enhancing women's participation in community planning, decision-making, and livelihood activities is crucial to meeting participation targets. Incorporating gender indicators into the monitoring and Project Implementation Report (PIR) will be essential for assessing progress and making informed adjustments. Furthermore, organizing workshops to improve the project team's understanding of gender issues, as outlined in the project AWPB 2024, will foster a more inclusive and equitable environment.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Engage Gender Specialists Recruit gender specialists and designate gender focal points to perform a gender analysis, formulate a gender strategy, and create an action plan aligned with GEF and IFAD gender policies. | PMO | Q1 2025 | Proposed |
| Include Gender Sensitive Indicators in the M&E system | PMO | Q1 2025 | Proposed |
| Report on Gender Analysis, Gender Strategy, and Action Plan | PMO/Gender Specialist/Gender Focal Point | Q1 2025 | Agreed |
| Conduct a GESI Workshop Organize a workshop to improve the project team's understanding of gender issues, as outlined in the project AWPB 2024, fostering a more inclusive and equitable environment. | PMO/Gender Specialist/Gender Focal Point | Q1 2025 | Proposed |

- Adaptation to Climate Change (rating: Moderately Satisfactory).

A key part of the project’s climate mitigation and adaptation approach is the ongoing peatland inventory conducted by the Ministry of Environment and Forestry (MoEF) within the IMPLI project area. The inventory is conducted at a 1:50,000 scale in accordance with Ministry Decree No. 4/2024 regarding peat restoration implementation. The process emphasizes R1 (rewetting) as it pertains to peatland management by the Government of Indonesia. This inventory serves as a basis for detailed mapping of restoration areas and systematic monitoring of peat subsidence. Conducted in collaboration with provincial and district governments, the initiative supports the establishment of an evidence-based policy framework for sustainable peatland management. The incorporation of updated spatial data into the SiPPEG peatland information system ensures that restoration planning, hydrological interventions, and climate adaptation measures utilize reliable, spatially precise, and current datasets. This contributes to informed decision-making and landscape-level peatland governance.

The project has made substantive contributions to climate change adaptation through a combination of ecosystem-based and community-centered interventions across priority peatland landscapes. Central to this approach has been the reintroduction of native peat swamp forest species, such as Ramin (Gonystylus bancanus) and Jelutong (Dyera costulata), alongside the promotion of peat-adapted rice varieties. These efforts have demonstrably enhanced the resilience of ecosystems and local communities to increasing climate-related stresses, including drought, fires, and flooding. Notably, the re-establishment of these native species has contributed to restoring habitat complexity, improving biodiversity corridors, and supporting increasing wildlife populations. In turn, this is progressively strengthening the ecological functions of these degraded ecosystems, which are essential to maintaining regional ecological stability under a changing climate regime.

The project has successfully incorporated local ecological knowledge and traditional (local wisdom) practices, such as the sonor farming system, which is traditionally applied during prolonged dry seasons. This approach, combined with the use of native plant species, not only accelerates peatland recovery but also stabilizes soils, maintains local microclimates, and gradually attracts wildlife back to rehabilitated areas, thereby restoring ecological balance.

In addition, these native species play a crucial role in restoring the natural hydrological function of peatlands by stabilizing the water table and reducing the risk of peat fires, which are increasingly frequent under prolonged drought conditions. The rehabilitated forests act as natural hydrological buffers, absorbing excess rainfall and releasing it gradually, mitigating the intensity and duration of flood events during erratic wet seasons. The project also conducted extensive consultations with local communities, district governments, provincial disaster management agencies (BPBD) and BRGM, resulting in a plan for canal blocking works designed to rewet degraded peat soils and improve overall water management in the targeted landscapes.

Complementing these interventions, the project introduced innovative land use models such as paludiculture and agro-silvo-fishery systems, promoting sustainable, peat-compatible livelihoods while supporting the natural hydrological cycle of peatlands. In their intact state, peatlands provide vital adaptation services, including absorbing excess precipitation, reducing flood risks in downstream areas, and sustaining gradual water flows during dry periods. The IMPLI project’s restoration and community-based livelihood models are therefore directly contributing to ecosystem-based climate adaptation outcomes in project areas.

Valuable lessons have been documented from project sites such as Tanjung Menang Village in South Sumatra, where the local TK-PPEG (community task force) has piloted an innovative and integrated agro-silvo-fishery model for peatland restoration. This model prioritizes biodiversity enhancement through the selection of peat-adapted tree species like Shorea balangeran and Shorea macranntha, which are particularly suited to the degraded peatland’s high sunlight exposure and moderate flooding conditions. In parallel, the TK-PPEG has combined these reforestation efforts with food security initiatives, introducing crops such as corn (Zea mays), eggplant (Solanum melongena), and pineapple (Ananas comosus) within designated utilization zones.

- Sustainability and Scaling-up

- Institutions and Policy Engagement (rating: Satisfactory)

The IMPLI Project has made substantial progress in strengthening Indonesia’s institutional frameworks for sustainable peatland management. Through its coordination with the Ministry of Environment and Forestry (MoEF) and the Ministry of Home Affairs (MoHA), the project has successfully aligned national peatland protection policies (PP71/2014 and PP57/2016) with sub-national governance systems.

A key institutional achievement has been the facilitation of RPPEG drafting processes in four districts, providing formal legal instruments for classifying peatlands, regulating land-use zoning, hydrological management, and fire prevention at the local level. These processes, completed through multi-stakeholder consultations, directly contribute to operationalizing national policy at the district scale.

The project also established effective multi-stakeholder coordination mechanisms, including the National Steering Committee (NSC) and sub-national working groups, improving policy coherence and landscape-level governance. Additionally, IMPLI successfully aligned peatland priorities with the Village Fund mechanism (Ministry Decree No. 8/2022), creating a pathway for sustainable financing of community-based restoration activities.

At the regional level, IMPLI contributed to ASEAN peatland and haze governance platforms and international events, such as the UNFCCC COP 28 annual climate conference held in Dubai, United Arab Emirates, from November 30 to December 13, 2023, sharing restoration experiences and positioning Indonesia as a regional leader in climate-resilient peatland management, and at the side event on 10 December 2023, international peatland experts, including representatives from the MoEF and the IMPLI project, emphasized the need for updated emissions factors, enhanced nature and water monitoring, and improved metrics.

Sustaining the achievements of IMPLI beyond its project cycle depends on the institutionalization of its governance frameworks. The establishment of multi-level coordination structures, such as the National Steering Committee and provincial working groups, has enhanced policy dialogue and collaborative management of peatlands. For long-term impact, these platforms should be formalized within Indonesia’s broader environmental governance frameworks, with clear mandates, dedicated resources, and regular capacity-building initiatives. Empowering local government agencies and community groups through targeted training and resource allocation will be essential to maintain and advance sustainable peatland management practices after project completion.

The long-term financial viability of IMPLI’s interventions remains a critical priority. While the project has mobilized significant GEF funds and government counterpart contributions, low disbursement rates and reliance on external financing raise concerns about continuity. Expanding public–private partnerships and exploring alternative funding sources, such as carbon financing and payments for ecosystem services, can create additional revenue streams to support conservation efforts. Establishing a dedicated peatland conservation fund at the national level, managed transparently and linked to Indonesia’s climate and sustainable development commitments, would provide a stable financial foundation for ongoing interventions and ensure that the benefits of sustainable peatland management persist beyond the project’s lifespan.

Since 2023, IMPLI has been facilitating the Ministry of Environment and Forestry (MoEF), particularly the Directorate General of Pollution and Environmental Degradation Control and the Directorate General of Natural Resources Management and Conservation, to align regulations on peat restoration in conservation areas. Through a series of meetings and discussions, both directorates have recognized the importance of peat restoration in enhancing habitat conservation and biodiversity. Instead of developing new regulations, they have agreed to review and synchronize existing regulations with the ministry decree to ensure a cohesive approach.

- Partnership building (rating: Satisfactory)

The IMPLI project has been collaborating with other national agencies, including the Ministry of Home Affairs (MoHA), to leverage Sustainable Peatland Management (SPM) in alignment with the National Action Plan on Peatland (NAPP, or RPPEG). This approach is intended for adoption by sub-national governments at the provincial and district levels. In May 2024, the MoHA disseminated a letter encouraging sub-national governments to synchronize their medium-term development plans with the RPPEG. Concurrently, the IMPLI project facilitated the Ministry of Environment and Forestry (MoEF) in consolidating their Dana Desa (Village Fund) program under managed by Ministry of Village (MoV) to support the revitalization of peatland management. Initiatives under this program include silvo-agro-pastoral activities in Muara Medak Village, beekeeping for honey production in Kepayang Village, and eco-tourism in Dayun Village. These efforts aim to bolster food security through peat community groups and micro, small, and medium enterprises (MSMEs).

In 2023, the IMPLI project supported the MoEF and South Sumatra Province in conducting collective action on fire handling in Ogan Komering Ilir District that was affected by the El-Nino. In collaboration with the National and Provincial Disaster (BNPB, BPBD), provincial agencies and the private sector, have handled the forest and peat fire that happened in the KHG/PHU Sungai Burnai-Sungai Sibumbung with about 86,679 Ha. The success of collaboration is acknowledged by the Minister as part of national commitment to reduce haze in Southeast Asia.

The project has facilitated the establishment of partnerships with the private sector for integrated peat management. It supports the detailed mapping of peat at a 1:50,000 scale, and is designed to aid the implementation of integrated peatland management in the landscape (PHU). The IMPLI project and the MoEF have engaged with 11 companies to implement best practices in sustainable peatland management and mitigate peat emissions, particularly through R-1 (rewetting) or managing the peat hydrology to stabilize the water table, ensuring it does not fall more than 0.4 meters below the surface (Annex 1). Three companies supporting IMPLI in Muara Jambi District are: (i) Jambi Batanghari Plantation, (ii) Erasakti Wira Forestama, and (iii) Bukit Bintang Sawit. These companies have agreed to support the district government in developing the RPPEG at the district level, with the intention of mainstreaming the RPPEG at both national and provincial levels.

A partnership has been established to develop a methodology for measuring greenhouse gas (GHG) emissions from peatlands through the IMPLI project. The collaboration involves the National University (IPB), the private sector represented by Riau Andalan Pulp & Paper (RAPP), and the Sumitomo group. Several meetings and workshops have been conducted to refine the tier-2 measurement methodology. The draft is scheduled for publication in Q3-2025 and will concurrently be submitted to the IPCC for review to ensure compliance with carbon certification standards.

Regional Partnership: The IMPLI project is enabling the MoEF to engage actively in the regional ASEAN Task Force on Peatland (ATFP). During the 9th ATFP meeting held in Bangkok, a recommendation was made for collaboration between MAHFSA and the IMPLI project. This cooperation aims to share knowledge on sustainable peatland management, particularly regarding the establishment of peat policy, public-private partnerships, and peat and fire monitoring systems. It has been planned that MoEF and IMPLI will facilitate field visits to their project locations in Riau Province. This event is scheduled to take place in the first quarter of 2025 and will involve all the 10 of ASEAN member states (AMS).

- Environment and Natural Resources Management (rating: Satisfactory)

The IMPLI project enhances environmental sustainability by safeguarding Indonesia’s critical peatland ecosystems, which are essential for biodiversity conservation, carbon sequestration, and water regulation. Through an integrated approach that combines policy reform, community-based interventions, and technological innovation, the project works to preserve the ecological integrity of these landscapes.

IMPLI operates across priority peatland areas in Riau, Jambi, and South Sumatra, where the development and implementation of Peat Ecosystem Management and Protection Plans (RPPEGs) are central to conserving local biodiversity. These plans are tailored to local ecological contexts and are designed to reduce anthropogenic pressures through sustainable land-use practices and habitat protection.

Peatlands serve as significant carbon sinks, and IMPLI contributes to climate change mitigation by implementing enhanced water management, hydrological restoration and fire prevention measures. The project’s efforts, such as rewetting degraded peatlands and deploying early warning systems via the SiPPEG platform, reduce peat oxidation and fire risks, thereby enhancing carbon storage capacity and improving community resilience against climate-induced hazards.

IMPLI promotes innovative, sustainable agricultural models, including paludiculture and agro-silvo-fishery systems, that enable local communities to pursue alternative livelihoods while protecting peatland ecosystems. By supporting practices that minimize land degradation and reduce reliance on destructive agricultural methods, the project fosters long-term ecological and economic sustainability.

Recognizing the critical role of water management in peatland conservation, the project has prioritized restoring natural hydrological regimes to prevent peat oxidation and limit fire incidents. Coordinated fire management efforts, including community training and the use of digital monitoring tools, have led to a notable reduction in fire occurrences, thereby protecting both ecosystem functions and human health.

The mission could visit several paludiculture demplots established via the IMPLI project. The demplot in Tasik Serai village, Bengkalis District, located on deep peat at the border with the conservation area, presents a good example of best practice for communities’ alternative livelihoods. The demplot is still in its early stages of development, however, the mission could already note good water management practices being applied: a canal was built all around the demplot, keeping a high water-table while limiting flooding, and therefore providing adequate water management conditions for the agro-silvo-fishery activities within its delimitations.

The demplot in Rawa Mekar Jaya village, Siak District, was constructed on a flood prone area, 500 m away from the ocean. This demplot showed good design, with the selection of crops suitable for a higher water table and well-planned intercropping. Due to the proximity to the ocean, the community has been faced with high salinity issues in the soil and groundwater. The community work plan, therefore, includes the construction of two canal blockings to limit salt intrusion phenomena in the production areas. The mission noted the presence of oil palm (OP) plantations in the surrounding areas, which would require limiting rewetting to a maximum water table of 30-40 cm. The surrounding land use would need to be carefully considered when attempting further paludiculture efforts.

The mission also visited a site with high risk of fire, located close to the forested national park. The mission is pleased to note the project plans to revegetate the site and to install a water data logger, with an automatic data sharing system connected to a central control unit in Jakarta. The mission noted that previous revegetation attempts had not been successful due to a lack of maintenance. Signed agreements on community maintenance and budget plans should be obtained before proceeding with the revegetation. Moreover, the handover processes between the IMPLI project to the MoEF, and from the MoEF to the local government and community have been estimated to take over one year. It is important to allocate responsibilities and budget for the maintenance of revegetated sites until they can be handed over to the community.

- Potential for Scaling-up (rating: Moderately Satisfactory)

The IMPLI project has been developing effective models, highlighting the importance of expanding localized restoration and fire prevention activities. To enhance environmental sustainability, the project should: (i) scale up hydrological restoration and fire management activities across all targeted landscapes, (ii) strengthen partnerships with private sector actors to boost investments in sustainable land use, (iii) improve data collection and monitoring systems to inform decision-making, (iv) develop a robust post-project sustainability plan that secures funding and institutional support for ongoing conservation activities.

The IMPLI demo-plots provide valuable knowledge that can facilitate knowledge exchange among ASEAN member states (AMS) regarding the implementation of the ASEAN Peatland Management Strategy (APMS), which is currently being implemented by the Government of Indonesia. These models can be adopted or replicated in other countries, such as combining canal blocking with tourism or integrating silviculture, agriculture, and pastoral practices.

The success of Integrated Peatland Management (IMP) with RPPEG in Muaro Jambi District prompted Tanjung Jabung Timur District to request IMPLI project assistance for developing its own RPPEG, ensuring alignment with Muaro Jambi’s due to their shared PHU areas. Following recommendations from the Jambi Province TWG, IMPLI will support Tanjung Jabung Timur’s RPPEG development in coordination with district-level spatial planning.

Project Management

- Quality of Project Management (rating: Moderately Satisfactory)

The complexity of the project demands that the PMO be agile and able to work synergistically with the government (across national to sub-nationals, and field), and across stakeholders (private sector, university and community). As such, the alignment of strategy and vision among PMO, PPMO and DPMU is important to achieve the targets.

The IMPLI project has shown that the established blueprint for sustainable landscape management is actively being put into practice. The multistakeholder partnership framework has been implemented, as also continual learning and adaptive management as well as clarification of rights and responsibilities and strengthening stakeholder capacity. The Project has also developed multi-stakeholder coordination mechanisms that include the National Steering Committee (NSC), which facilitates policy dialogues at the national, ASEAN, and international levels. Moreover, the Project has developed trainings and strengthened capacity building of key stakeholders in sustainable peatland management at the national and sub-national levels.

The first National Steering Committee (NSC) meeting was held in October 2022 following the project's launch. In 2023, the NSC was conducted in December. The next NSC is scheduled for December 2024.

The implementation of the project has encountered notable delays, largely attributable to the unforeseen challenges introduced by the COVID-19 pandemic in its initial years, as well as the impact of the 2023 El Niño event in Sumatra and disruptions related to the forthcoming presidential and general elections in 2024. These external circumstances have impeded the timely completion of critical activities and have constrained progress toward achieving the project’s intended objectives. Furthermore, delays in finalizing the Project Implementation Manual were principally caused by the relocation of a project site from North Sumatra to South Sumatra, alongside ongoing staffing constraints. The project faced a shortage of technical personnel until mid-2023, and the absence of an appointed team leader until January 2024 further hindered coordination and overall progress.

In light of these challenges, the IFAD supervision team, together with project management units at both national and local levels, engaged in comprehensive consultations with community groups and relevant stakeholders. Through these discussions, a consensus was reached on the necessity of extending the project period to allow sufficient time for completing outstanding activities and securing the sustainability of project results. As a result, an 18-month extension is being recommended to ensure that planned interventions can be effectively implemented and the project’s development objectives fully realized.

| Actions Project management | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Conduct the National Steering Committee (NSC) meeting of IMPLI Project | PMO, MoEF, IFAD | November 2024 | Agreed |
| Calculation of the co-financing through the tracing system in multi-levels | NPMO, MOEF | Q1 2025 | Proposed |
| Submit and process a No-cost extension request for 18 months | IFAD | 10/2024 | Agreed |

- Knowledge Management (rating: Moderately Satisfactory)

The IMPLI project has made significant strides in executing its Knowledge Management (KM) approach, designed to enhance learning, improve stakeholder engagement, and promote sustainable peatland management practices. The following sections detail the progress on key deliverables:

Knowledge and Learning Deliverables: Website/Platform Development

The IMPLI project launched a web-based platform called “System Information for Protection and Management of Peatland Ecosystems in Indonesia” (SiPPEG), which serves as a centralized hub for knowledge sharing, data management, and stakeholder coordination. The platform provides access to real-time information on peatland conditions, GHG monitoring, fire prevention systems, and sustainable land management practices.

The platform is actively used by over 32,000 stakeholders, including government officials, local communities, private sector actors, and NGOs, enhancing real-time communication and decision-making. SiPPEG has also integrated tools for early warning systems and digital maps for peatland hydrological units, supporting participatory planning and monitoring.

MoEF has facilitated IMPLI project to contribute on the peatland education and awareness. The MoEF website allocated a specific link for the IMPLI project to add and update any information to public. The link is here: http://pkgppkl.menlhk.go.id/v0/impli/

Knowledge Products and Events

The project has produced over 20 knowledge products, including technical reports, training manuals, policy briefs, videos, and research publications. These materials cover topics such as peatland restoration techniques, GHG emissions measurement, paludiculture, and sustainable livelihoods.

Several knowledge-sharing events have been conducted, including workshops, training sessions, webinars, and field demonstrations. Notable events include the International Peatland Management Symposium held in March 2024, which brought together over 300 participants from government, academia, civil society, and the private sector to discuss best practices in peatland restoration.

Regional workshops focused on participatory mapping and integrated management planning were held in Riau, Jambi, and South Sumatra, with over 65 capacity-building activities conducted between July 2023 and June 2024. These events aimed to strengthen local capacities, encourage collaborative learning, and promote the adoption of sustainable practices.

Participated in the annual ASEAN Peatland Task Force meetings, led by the ASEAN Secretariat (2022 in Singapore, 2023 in Lao PDR, 2024 in Thailand).

Communication Strategy

The project’s Communication Strategy was rolled out in early 2024 to support outreach, awareness-raising, and behaviour change related to peatland conservation. The strategy includes tailored communication tools such as social media campaigns, newsletters, infographics, and community radio broadcasts to reach diverse audiences at both local and national levels.

Social media platforms like Facebook, Instagram, and YouTube have been actively used to disseminate information and engage broader audiences. The content focuses on community success stories, sustainable land-use practices, and fire prevention measures, reaching over 500,000 online users.

In collaboration with local governments and community groups, IMPLI has implemented a communication, education, and public awareness program, engaging over 8,000 participants, with a particular focus on youth, women, and indigenous groups.

Lessons Learned and Good Practices

A key lesson learned is the importance of integrating local knowledge with modern technologies, as demonstrated by the successful implementation of the agro-silvo-fishery models and paludiculture techniques. This integration has resulted in better community acceptance and improved sustainability outcomes.

The use of the “SiPPEG” platform has revealed that digital tools can be effective in bridging communication gaps between government agencies and local communities, provided adequate training and user support are available.

A good practice identified involves peer-to-peer learning exchanges, where communities from different regions visited each other to share restoration techniques and sustainable livelihood strategies. This approach has enhanced learning, built trust, and fostered cross-community collaboration.

In Dayun Village, Riau, the project effectively bolstered the sustainability of its peat management program by integrating the IMPLI budget allocated to the village with funds from the Ministry of Villages and Transmigration, alongside Corporate Social Responsibility (CSR) contributions from the private sector.

Adaptive Management Actions

To address challenges related to slow adoption of digital tools and gaps in digital literacy, the project has implemented additional training programs focused on improving digital skills among community members and government officials. These adaptive measures have helped increase engagement with the “SiPPEG” platform.

The project has also adjusted its communication strategy to include more visual aids and local language translations to ensure wider comprehension and participation, particularly among indigenous groups and rural communities with limited formal education.

In response to feedback from stakeholder events, IMPLI has increased its emphasis on community-led knowledge generation, such as involving local farmers in the documentation of successful paludiculture models. This adaptive action has improved local ownership and relevance of knowledge products.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Develop the KM Strategy and action plan | PMO, MOEF | Q1 2025 | Agreed |
| Enhance digital literacy training for community members and government officials to improve engagement with the “SiPPEG” platform and maximize its utility for data sharing and fire prevention. | PMO | Q1 2025 | Agreed |
| - Expand the communication strategy to include more visual aids, such as posters, infographics, illustrated guides, and short videos, to help convey key messages in an accessible and engaging way. These tools, combined with local language translations and simplified content, will improve understanding and participation among indigenous groups and rural communities with limited formal education. | PMO | March 2025 | Agreed |
| - Establish regular peer-to-peer learning exchanges across different regions to facilitate knowledge sharing on restoration techniques, agro-silvo-fishery and silvo-agro-pastoral models, and community-led sustainable practices. | PMO | June 2025 | Agreed |
| - Publish the results achieved by the IMPLI project on the MOEF website | PMO, MOEF | Q! 2025 | Agreed |

- Coherence between AWPB and implementation (rating: Moderately Satisfactory).

The GEF6 IMPLI submitted the first Annual Work Plan and Budget (AWPB) in 2022, amounting to USD 626,280.70, with audited disbursements of USD 508,420.64, representing 81% of the total allocation. The second AWPB in 2023 amounted to USD 1,501,333, with audited expenditures totalling USD 796,851.51, which is 53% of the annual allocation. The third AWPB for 2024 was submitted and received no objection from IFAD, with a total amount of USD 1,360,773.33 and unaudited expenditures of USD 1,197,493.41, equating to 88% of the approved annual amount. Overall, the average annual expenditure stands at 74% of the approved annual work plans and budgets (AWPB). Over the last three years (2022-2024), the IMPLI project has shown consistent improvement in implementation.

The IMPLI project complies with the procedure, they have conducted National Project Steering Committee Meeting (NPSC) regularly in October 2022, December 2023, and the next NPSC meeting in December 2024 to review and endorse the AWPB before it submits to IFAD.

Given the anticipated extension of the project duration and insights gained from the previous AWPB performance, as well as the preparation for the 2024-AWPB, it is essential to initiate the preparation and submission of the 2025-AWPB as soon as possible in 2024. This will ensure that the approved 2025-AWPB is available 60 days prior to January 1, 2025.

- Performance of the M&E System (rating: Moderately Satisfactory).

The IMPLI project has put in place operational M&E arrangements, with routine data collection carried out by village facilitators and subsequently validated by the Provincial and National Project Management Units (PPMUs and NPMU). Semi-annual and annual progress reports (SAPRs) are submitted regularly to IFAD and have been assessed as good in quality.

A key achievement was the completion of the Management Information System (MIS) in July 2024, which will enable the project to track both financial disbursements and physical progress once fully operational. The system is currently being migrated to the MoEF’s server, which will assume ownership. To support its rollout, an MIS training is scheduled for October 2024 for national, provincial, and district staff, to be jointly delivered by the system vendor and IFAD’s M&E specialist.

The project also finalised its baseline study, with results and supporting technical documents uploaded to the MIS, including the baseline study in the 13 villages of project location, it was completed in 2023. The system is expected to be fully operational by 2025.

Despite these developments, the project’s M&E plan remains under preparation, limiting the strategic utility and coherence of the M&E system. Compilation of the project logframe has been inconsistent, with an emphasis on qualitative information and insufficient quantitative performance data, reducing the capacity to monitor progress effectively.

Moreover, while reporting systems are functioning, M&E findings have yet to play a substantive role in informing management decisions. The recent recruitment of a national M&E officer represents a positive development; however, the absence of dedicated M&E officers at the provincial level remains a notable gap in local oversight. Additionally, data collection disaggregated by gender and age, and the systematic capture of environmental, social, and climate impacts in line with SECAP requirements, as well as knowledge management activities, should be prioritised in the finalised M&E plan and future MIS functionalities.

To address these gaps, the project will need to upgrade its M&E system to fully capture the key elements required under GEF-6. The revision and finalisation of the M&E Strategy and Plan should be accelerated, ensuring full integration of MIS functionalities, baseline data, and relevant indicators.

| Actions | Responsibility | Deadline | Status |
| --- | --- | --- | --- |
| Recruit M&E officers at the provincial level | DPMU | Q1 2025 | Agreed |
| Capacitate M&E officers at national and provincial level | NPMU, PPMU | Q2 2025 | Agreed |
| - Draft a M&E Plan | NPMU | Q2 2025 | Agreed |
| - Fully operationalise the MIS and socialise the system to NPMU and PMU M&E officers | NPMU, PPMU | Q1 2025 | Agreed |
| - Integrate the logframe with GEF6 core indicators | NPMU | Q3 2025 | Agreed |

- Requirements of SECAP (rating: Moderately Satisfactory).

SECAP/ESS-related review, risks and mitigations. The IMPLI project is fully aligned with GEF Environmental Safeguard Standards and IFAD’s policies, including the Strategic Framework 2016-2025, Environmental Natural Resource Management (ENRM) Policy, Climate Change Strategy, and policies on Gender Equality, Indigenous Peoples, Land Access and Tenure, and Knowledge Management.

The project has undergone a thorough review in line with IFAD’s Social, Environmental, and Climate Assessment Procedures (SECAP), which classified the project as Category B, indicating moderate potential for social and environmental impact, details of comparison for the safeguard at design project and MTR is provided in the annex 3.

The IMPLI project significantly contributes to global environmental benefits by promoting sustainable peatland management across Indonesia. The project targets key areas such as peatland forest conservation, reducing greenhouse gas (GHG) emissions, and enhancing biodiversity. Through activities like restoring degraded peatlands, preventing fires, and supporting sustainable agriculture, the project helps sequester carbon and reduce GHG emissions linked to land degradation and fires. It also promotes biodiversity by restoring peat swamp forests, creating wildlife corridors to protect habitats and restore the endemic species through the local knowledge.

Mitigation measures have been implemented to address these risks, with a focus on climate change-related vulnerabilities, such as increased flooding and droughts that could disrupt peatland hydrology and exacerbate fire risks: Riau – The primary risks in Riau involve peat fires, water mismanagement, and landscape degradation. These risks have consistently been classified as moderate, with no significant changes to the risk level, as preventive measures have been effective. Jambi – Risks in Jambi are related to fire outbreaks, land conflicts, and social impacts from engaging indigenous communities. These risks are rated moderate, with active efforts to maintain cooperative relationships and ensure inclusive participation. South Sumatra – The risks in South Sumatra focus on peat fires, water conservation, and gender inclusion, with a consistent moderate rating. However, gender inclusion efforts have been revised to ensure broader participation, especially among women.

- Financial Management and Execution

- Disbursement Rate (rating: Satisfactory)

As of September 2024, IFAD has disturbed USD 3,065,035 or 60% of the total grant to IMPLI project. The first disbursement occurred in June 2021 with USD 150,000, the second disbursement in April 2022 with USD 600,000, the third disbursement in August 2023 with USD 1,241,838, and the fourth disbursement in June 2024 with USD 1,073,198.

The expenditure of the IMPLI project up to September 2024 is USD 1,818,097 (or 37% against its total GEF allocation) and it is projected to reach USD 2,546,217 by the end of December 2024, which is 51% of the total grant. This projection accounts for the commitment to complete ongoing activities by mid-December 2024.

- Quality of financial management (rating: Moderately Satisfactory)

The mission evaluated the IMPLI project's compliance and found it to be in good standing, with notable improvements in the financial management system, aligning well with the IFAD system. The IMPLI project has consistently conducted coordination meetings with the Finance and Management Division (FMD) for IFR purposes, ensuring timely updates on progress.

- Quality and timeliness of audit (rating: Satisfactory)

The IMPLI project has obtained satisfactory ratings for its audit reports. Three audit reports based on the BPK (Supreme Audit of Republic Indonesia) report have been submitted: the FY-2021 audit report was submitted in May 2022, the FY-2022 audit report was submitted in October 2023, and the FY-2023 audit report was submitted in June 2024. Currently, the IMPLI project is submitting the draft audit report for FY-2024, which will be reported to IFAD before 30 June 2025. Over the past three years, there have been no major findings in the audit reports, and they received a satisfactory rating (5) from IFAD.

The latest audit identified a minor issue related to the project operations. The recommendations include improving strategic planning, ensuring compliance with financial guidelines, optimizing payment verification processes, and enhancing monitoring and evaluation mechanisms to align with the Key Performance Indicators (KPIs) of the project.

- Counterpart funds (rating: Moderately Satisfactory)

The IMPLI project has documented co-financing from various entities including the Government of Indonesia's Ministry of Environment and Forestry (MOEF), BRGM, Ministry of Home Affairs (MoHA), Ministry of Villages (MoV), and local governments at both provincial and district levels. This co-financing amounts to USD 3,237,122, based on annual reports up until December 2023.

The implementation of activities at the village level involves contributions from various sectors. For instance, villagers contribute in kind by working on infrastructure development at demonstration plots, village funds are allocated for the construction of farmer roads (providing access to these plots), among other inputs. However, these contributions have not been accounted as co-finance for the project. An example is noted where a village fund amounting to IDR 100 million (approximately USD 6,500) was utilized for the development of a farmer road to access the demonstration plot of TK-PPEG in Rawa Mekar Jaya Village.

- Procurement Review (rating: Moderately Unsatisfactory)

The Procurement Plan (PP) for 2024 was submitted late, receiving No Objection from IFAD only on April 3, 2024. Additionally, the project subsequently included two procurements of goods and two procurements of consultancy services without seeking No Objection from IFAD for the revised PP. Furthermore, the procurement plan was not adequately prepared, as certain procurements were inappropriately grouped into a single package instead of being separated based on individual contracts.

Implementation of the Procurement Plan: The project has procured one package of goods (out of three planned procurements), 25 consultancy procurements (out of 31 planned packages), and four works procurements (out of seven planned packages). Some procurements exceeded the allocated budget. For instance, the procurement of data loggers in Riau Province had an allocated budget of USD 20k, but the actual contract amounted to USD 26k.

Pending Procurement: The contract for the data logger has been signed with the provider; it is expected that the installation will be completed as scheduled.

Contract Management: The project did not adequately monitor contract performance. For example, the Swakelola-Type 4 contract with Desa Tasik Serai expired in August 2024, yet implementation is still ongoing despite the contract’s expiration. This situation may lead to compliance and legal issues, as work is being performed without a valid contract. Additionally, procurement documents were difficult to obtain; for instance, only the Community Working Plan (RKM) was available for review, which poses challenges for proper oversight, compliance, and monitoring.

The implementation of self-managed procurement or force-account (Swakelola), such as Swakelola Type-4 (contract with the community), requires clear guidelines from the project to help the community understand their rights, roles, and accountability. Additionally, the implementation of Swakelola should comply with the Presidential Regulations on public procurement, including the establishment of Swakelola teams (Preparation and Supervision teams).

There is no dedicated procurement and contract management officer in the PMO. Currently, project procurement is managed by a project assistant. As a result, procurement management is not adequately handled.

| Actions | Responsibilities | Deadlines | Status |
| --- | --- | --- | --- |
| Update the procurement plan to reflect the revision and seek no-objection. | NPMO | Oct 2024 | Agreed |
| Review all contract and consult with UKPBJ (Procurement Unit) to extend or renew the expired contract with pending deliverable. | PPK (Contract manager) | Oct 2024 | Agreed |
| Establish guideline for community engagement activities. | NPMO | Oct 2024 | Agreed |
| Prepare adequate TOR for community engagement activities, included but not limited to training, selection procedures, payment terms, etc. | NPMO | At least 2 months before the activity/event | Agreed |
| Recruitment of Procurement and contract management officer | NPMO, PPK | Nov 2024 | Agreed |

## Relevance

- Relevance (rating: Satisfactory)

The IMPLI project is strategically aligned with the Global Environment Facility’s priorities, addressing critical issues such as climate change mitigation, biodiversity conservation, and the prevention of land degradation. By promoting sustainable management of Indonesia’s extensive peatland landscapes, IMPLI contributes to reducing greenhouse gas emissions and safeguarding biodiversity, which are essential components of GEF’s global mandate. The project’s integrated approach, combining institutional strengthening, innovative land-use practices (e.g., paludiculture and agro-silvo-fishery models), and the deployment of advanced monitoring systems like the SiPPEG platform, ensures that interventions not only mitigate environmental risks but also generate global environmental benefits.

IMPLI demonstrates strong alignment with Indonesia’s national and regional policy frameworks aimed at sustainable development and environmental resilience. The project supports the implementation of the National Action Plan for Peatland (NAPP) and the development of Peat Ecosystem Management and Protection Plans (RPPEGs) at both provincial and district levels. This alignment is reinforced by the active coordination among key government agencies, including the Ministry of Environment & Forestry (MoEF), Ministry of Home Affairs (MoHA), and local governments, which is critical for mainstreaming sustainable peatland management into broader development planning. Furthermore, IMPLI’s efforts to integrate environmental objectives with socio-economic priorities underscore its role in enhancing national climate resilience and sustainable land use.

In addition to its policy alignment, the IMPLI project contributes to Indonesia’s broader sustainable development agenda by linking environmental conservation with improved rural livelihoods. Through its multi-stakeholder approach, the project has initiated activities that enhance local capacities, provide economic opportunities through sustainable market development, and reduce the vulnerability of communities to climate-related risks. These integrated interventions support national commitments under international agreements, such as the Paris Agreement, by advancing low-carbon development and fostering resilient ecosystems. IMPLI thereby serves as a critical instrument for ensuring that environmental and developmental objectives are met concurrently.

## Modifications identified during the Mid-term Review mission:

| Modifications |  |  |
| --- | --- | --- |
| Extension of Project Completion Date | Yes | ☐X |
| Considering the progress of the IMPLI project, and the achievement of core indicators, it was suggested that the project should be extended for about 6 – 18 months depending on the government of Indonesia and guidance from the National Steering Committee (NSC). |  |  |
| Financial Management | Yes | ☐X |
| The project has a sufficient budget for implementation, even though it will be closed at the end of 2025. It is necessary to pursue technical targets in accordance with budget expenditure. The synchronization of the IFR with the Logical Framework Analysis (LFA) monitoring and alignment with the design of the exit strategy should be considered in order to collaborate with the private sector and local government for continued project investment. |  |  |

## Lessons Learnt

Applicability:

| Project |  | ☐X | Country | ☐ | Region | ☐ | Multiple-region | ☐ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tag(s) | Community Engagement; Knowledge Management |  |  |  |  |  |  |  |

Key lessons learned are the importance of integrating local knowledge with modern technologies, as demonstrated by the successful implementation of the agro-silvo-fishery, silvo-agro-pastoral models and paludiculture techniques. This integration has resulted in better community acceptance and improved sustainability outcomes. The use of the “SiPPEG” platform has revealed that digital tools can be effective in bridging communication gaps between government agencies and local communities, provided adequate training and user support are available. A good practice identified involves peer-to-peer learning exchanges, where communities from different regions visited each other to share restoration techniques and sustainable livelihood strategies. This approach has enhanced learning, built trust, and fostered cross-community collaboration​.

Applicability:

| Project |  | ☐X | Country | ☐ | Region | ☐ | Multiple-region | ☐ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tag(s) | Best practices |  |  |  |  |  |  |  |

Effective biowaste containment of cattle farm should using septic tanks is essential; practices such as installing zinc barriers and incorporating biodigesters can help reduce methane emissions. Additionally, placing disinfectant foot baths at the entrances of poultry and livestock facilities will improve biosafety and prevent the spread of diseases.

Applicability:

| Project |  | ☐X | Country | ☐ | Region | ☐ | Multiple-region | ☐ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tag(s) | Stakeholders and private sector engagement |  |  |  |  |  |  |  |

The IMPLI project experience has reaffirmed that effective peatland landscape management cannot be achieved without the active involvement of private sector actors, particularly in areas like the GSK-BB Biosphere Reserve, where industrial concessions manage a substantial proportion of the peatland ecosystem. While the project has succeeded in mobilizing government and community stakeholders, efforts to engage private sector entities, including forestry, plantation, and agribusiness companies, in policy dialogue and collaborative land-use management have faced persistent barriers. These include divergent commercial priorities, perceived regulatory risks, and the absence of clear economic incentives for adopting sustainable practices.

To improve the effectiveness and sustainability of integrated peatland management, the project should prioritize the establishment of structured, incentive-linked private sector engagement mechanisms. Aligning private sector participation with opportunities for fire risk reduction, climate finance access, and market-linked benefits (e.g. sustainable commodity certification) will be essential to secure their long-term commitment to peatland restoration initiatives.

## GEF Core Indicators

| No | Key Performance Indicators | Means of Verification | Responsibility | Achievement |
| --- | --- | --- | --- | --- |
| 1 | Core Indicator 3: Area of land restored Additional 120,000 ha of peatlands under an improved management regime (disaggregated by smallholder (20,000 ha, disaggregated by men/women smallholders) and concessionaire management (100,000 ha) | MoEF annual reports, Stakeholder surveys | DIt. PKEG PMO IMPLI | A total of 11 concessionaire management with a total area of 571,127 ha within the IMPLI Project’s targeted PHUs have had technical discussions on peatland ecosystem recovery plan documents with the Directorate of PEDC using the IMPLI Project’s budget with details as follows: - PT 1: 34,469 ha - PT 2: 32,661 ha - PT 3: 9,401 ha - PT 4: 46,226 ha - PT 5: 46,226 ha - PT 6: 16,358 ha - PT 7: 20,129 ha - PT 8: 5,630 ha - PT 9: 148,712 ha - PT 10: 11,963 ha - PT 11: 205,767 ha A total of 206 ha of smallholder plantations owned by 81 smallholder farmers in Riau Province have received training on ISPO/RSPO standards with details as follows. - Dayun: 96 ha of plantations from 20 smallholder HHs - Rawa Mekar Jaya: 20 ha of plantations from 20 smallholder HHs - Temiang: 55 ha of plantations from 20 smallholder HHs - Tasik Serai: 35 ha of plantations from 21 smallholder HHs |
| 2 | Core Indicator 4: Area of landscapes under improved practices 1.2 million hectares of peatland landscape sustainably managed | BRGM annual reports, MoEF annual reports, IMPLI annual reports | Dit. PKEG PMO IMPLI | All IMPLI Project's targeted PHUs have been inventoried at a 1:50,000 scale with details as follows. - Sungai Rokan-Sungai Siak Kecil PHU (832,458 ha) - IMPLI 2024 - Sungai Siak Kecil-Sungai Siak PHU (163,787 ha) - SMPEI 2022 - Sungai Siak-Sungai Kampar PHU (722,929 ha) - IMPLI 2024 - Sungai Batanghari-Sungai Air Hitam Laut PHU (189,862 ha) - BRGM 2018 - Sungai Air Hitam Laut-Sungai Buntu Kecil PHU (183,856 ha) - APBN 2020 - Sungai Merang-Sungai Ngirawan PHU (82,021 ha) - BRGM 2018 - Sungai Ngirawan-Sungai Sembilang PHU (73,475 ha) - BRGM 2018 - Sungai Sembilang-Sungai Lalan PHU (84,670 ha) - APBN 2020 - Sungai Burnai-Sungai Sibumbung PHU (86,679 ha) - APBN 2020 (SK.129/MENLHK/SETJEN/PKL.0/2/2017) The total area of IMPLI Project's targeted PHUs that have been inventoried using IMPLI Project grant is 1,555,387 ha. The total area of all IMPLI Project's targeted PHUs is 2,567,072 ha. Note: The total area of each PHU refers to the Ministerial Decree on the determination of the national peatland hydrological unit map. |
| 3 | Core Indicator 6: Greenhouse gas emissions mitigated 4.31 million metric tons of CO2e mitigated | BRGM annual reports, MoEF annual reports, IMPLI annual reports | Dit. PKEG PMO IMPLI | The Tier-2 methodology to calculate GHG emission reductions is still in the process of finalisation by MoEF and will be ready in Q2 2025, whilst the baseline data will be ready in Q3 2025. |
| 4 | Core Indicator 11: Number of direct beneficiaries disaggregated by gender 5,000 smallholder HHs directly benefit through sustainable peatland management practices and livelihoods, and 15,000 HHs indirectly benefit through improved knowledge and access to markets (total of 20,000 HHs) | BRGM annual reports, MoEF annual reports, IMPLI annual reports | PMO/PPMO/PDU IMPLI | As of October 2024 (Mid Term Review), project outreach of the IMPLI Project is 1,830 HHs which consists of 1,045 men and 785 women. Note: Calculation for project outreach needs to be detailed and thorough to prevent double counting. |

| Core Indicator 3 | Area of land restored (This indicator will be reported as an aggregate of the four Sub-indicators, to captures the hectares of new protected areas which meet the key Biodiversity Area Criteria and that result from the project’s support. For BD projects, in addition to explaining the project ‘s consistency with the biodiversity focal area, also describe which Aichi Target(s) the project will directly contribute to achieving) |  |  |  |  | (Hectares) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Hectares (3.1+3.2+3.3+3.4) |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
|  |  |  | 0 | 120,000Ha | 571,127 Ha |  |
| Indicator 3.1 | Area of degraded agricultural land restored (Indicate the hectares of agricultural land that was in a degraded state but is undergoing restoration through GEF funded interventions. Restoration here is defined as “the improvement of degraded land on al large scale that rebuilds ecological integrity and enhances people’s lives. It is suggested to provide GIS files showing extent of the degraded land that is undergoing restoration and also indicate the relative state of the areas prior to GEF activities.) |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Indicator 3.2 | Area of forest and forest land restored (Indicate the hectares of forest and forest land undergoing ecological restoration through GEF funded interventions. This Sub-indicator intends to capture the area of forest and forest land in which best practices for ecological restoration are being applied) |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Indicator 3.3 | Area of natural grass and shrublands restored (Indicate the hectares of natural grass and shrublands that are undergoing ecological restoration through GEF funded interventions. This sub-indicator intends to capture the area of natural grass and shrublands in which best practices for ecological restoration are being applied) |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Indicator 3.4 | Area of wetlands (including estuaries, mangroves) restored (Indicate the hectares of wetlands, including estuaries and mangroves, that are undergoing ecological restoration through GEF funded interventions. This sub-indicator intends to capture the area of wetlands in which best practices for ecological restoration are being applied) |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
|  |  |  | 0 |  |  |  |
| Core Indicator 4 | Area of landscapes under improved practices (hectares; excluding protected areas) (This indicator will be reported as aggregate total of four sub-indicators. Ensure that the hectares reported under each Sub-indictor do not overlap.) |  |  |  |  | (Hectares) |
|  |  |  | Hectares (4.1+4.2+4.3+4.4) |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
|  |  |  | 0 | 1,200,000Ha | 0 Ha The IMPLI project has inventoried 9 Peatland Hydrology Units (PHUs) with scale 1: 50,000, for a total area of 2.57 million ha. Moreover, the project has finalised the Peat Ecosystem Management and Protection Plans (RPPEG) in the three target provinces, and almost finalised the RPPEGs in all targeted Districts, setting in place the regulatory framework for the implementation of sustainable peatland management practices over an area of 7,981,429.50 ha of peatland. |  |
| Indicator 4.1 | Area of landscapes under improved management to benefit biodiversity (Indicate the landscape area that is being managed to benefit biodiversity, but which is not certified. Please provide qualitative description of the benefit provided to biodiversity through the change in management. It is also suggested to provide GIS files showing the extent of the land under this improved management (outside of protected areas) |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Indicator 4.2 | Area of landscapes that meet national or international third-party certification that incorporates biodiversity considerations (Indicate the landscape area that achieves certification in which biodiversity considerations are being incorporated, including details of the third-party certification. Ideally, provide GIS files showing the extent of the land under this improved management (outside of protected areas) |  |  |  |  |  |
| Third party certification(s): (please list third party certification standard that has been applied and how many hectares that have been certified under each standard applied.) |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Indicator 4.3 | Area of landscapes under sustainable land management in production systems (Indicate the landscape area that that is in production (e.g. agriculture, rangeland, forestry) and whose soil, air and water are managed in a sustainable way. Also include the details of the management practices and where possible provide GIS files showing the extent of the land under sustainable land management) |  |  |  |  |  |
|  |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
| Indicator 4.4 | Area of High Conservation Value Forest (HCVF) loss avoided (Indicate the area of High Conservation Value Forest (HCVF) that would be the lost without implementation of the GEF project. Projects first must indicate the names and areas of the HCVF that are targeted (ideally GIS files depicting these areas would be submitted), if not already recognized by the HCV network, projects should submit documentation that the targeted forests meet one or more of the HCV criteria) |  |  |  |  |  |
| Include documentation that justifies HCVF |  |  | Hectares |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |

| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment (Indicate the number of individual people who receive targeted support from a given GEF project and/or who use the specific resources that the project maintains or enhances. Direct Beneficiaries are all individuals who are receiving targeted support from a given project. Targeted support is the intentional and direct assistance of a project to individuals or groups of individuals who are aware that they are receiving that support and/or who use the specific resources.) |  |  |  |  | (Number) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Number |  |  |  |
|  |  |  | Expected |  | Achieved |  |
|  |  |  | PIF stage | Endorsement | MTR | TE |
|  |  | Female | 0 |  | 785 |  |
|  |  | Male | 0 |  | 1,045 |  |
|  |  | Total | 0 | 5,000 | 1,830 |  |

## Logframe

(as of October 2024)

| Results Hierarchy | Indicators | Units |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Mid-Term target | End Target | 2022 | 2023 | 2024 | Cumulative results |
| Goal: Peatlands managed and used sustainably to conserve biodiversity and ecosystem services and reduce greenhouse gas emissions | 1.2 million hectares of peatland landscape sustainably managed | hectares | 0.4 million | 1.2 million | 571,127 | 0 | 0 | 571,127 |
| Development Objective: To strengthen systems for the sustainable management, biodiversity conservation, reduced GHG emissions, and improved rural livelihoods in target peatlands of Indonesia | 4.31 million metric tons of CO2e mitigated | metric tons of CO2e | 2.2 million | 4.31 million | 0 | 0 | 0 | 0 |
|  | 5,000 smallholder HHs directly benefit through sustainable peatland management practices and livelihoods, and 15,000 HHs indirectly benefit through improved knowledge and access to markets (total of 20,000 HHs) | households | 2,000 (direct) | 5,000 (direct) | 0 (women-headed HHs) 0 (men-headed HHs) 0 (total direct) | 388 (women-headed HHs) 489 (men-headed HHs) 877 (total direct) | 397 (women-headed HHs) 556 (men-headed HHs) 953 (total direct) | 785 (women-headed HHs) 1.045 (men-headed HHs) 1.830 (total direct) |
|  |  |  | 7,000 (indirect) | 15,000 (indirect) | 0 (indirect) | 0 (indirect) | 0 (indirect) | 0 (indirect) |
|  | Additional 120,000 ha of peatlands under an improved management regime (disaggregated by smallholder (20,000 ha, disaggregated by men/women smallholders) and concessionaire management (100,000 ha) | hectares | 50,000 (total) | 120,000 (total) | 0 ha (smallholders) | 0 ha (smallholders) | 0 ha (smallholders) | 0 ha (smallholders) |
|  |  |  |  |  | 571,127 (concessionaire manag.t) | 0 (concessionaire manag.t) | 0 (concessionaire manag.t) | 571,127 (concessionaire manag.t) |
| Outcome 1: Institutional capacity, frameworks and partnerships for scaling-up of sustainable peatland restoration operational | Trained peatland stakeholders competently applying sustainable PHU management (gender disaggregated) | percentage of stakeholders | 50% | 80% | 0% (female) | 0% (female) | 0% (female) | 0% (female) |
|  |  |  |  |  | 0% (male) | 0% (male) | 0% (male) | 0% (male) |
| Output 1.1: Capacity building of key stakeholders in sustainable peatland management | 600 national and regional stakeholders trained in landscape scale peatland analysis and management (disaggregated at national and provincial levels) | number of stakeholders | 500 | 600 | 0 (female) | 0 (female) | 0 (female) | 0 (female) |
|  |  |  |  |  | 0 (male) | 0 (male) | 0 (male) | 0 (male) |
| Outcome 2: Integrated management of priority PHUs in Project provinces sustained | Reduced peatland and forest degradation (50%) and fires (70%) in GSK-BB peatland landscape (against rolling three-year average) | percentage | 20%-40% | 50%-70% | 2% (degradation) | 0% (degradation) | 10% (degradation) | 12% (degradation) |
|  |  |  |  |  | 0% (fires incidence) | 0% (fires incidence) | 0% (fires incidence) | 0% (fires incidence) |
| Output 2.1: Sustainable integrated management of the GSK-BB Peatland Landscape | Multiple stakeholders supporting Biosphere Reserve Management Plan implementation and regular updating | document | Plan under implementation | Updated plan 2021-2026 | 0 | 0 | 0 | 0 |
|  | Medium term strategy and PHU protection, management and financing plans for GSK-BB Peatland Landscape/PHU | document | 1 | 1 | 0 | 0 | 0 | 0 |
|  | 100,000 ha of plantation and 20,000 ha of community peatlands have medium-term SPM investment frameworks including a pipeline of investment concepts | hectares | 30,000 ha (plant.s) | 100,000 ha (plant.s) | 0 | 0 | 0 | 0 |
|  | At least 10,000 smallholders trained in ISPO/ RSPO standards using Project-prepared compliance training package | number of smallholders | 4,000 | 10,000 | 0 | 0 | 81 | 81 |
| Output 2.2: Support development of integrated Project Peatland Protection and Management Plans in Jambi and South Sumatra provinces | Land-use plans for the protection and management of 100,000 ha of PHU Landscapes in the provinces of Jambi and South Sumatra respectively | hectares | 40,000 | 100,000 | 0 | 0 | 2,996,740.76 ha (Jambi 904,422.82 ha; South Sumatra 2,092,317.94 ha) | 2,996,740.76 ha (Jambi 904,422.82 ha; South Sumatra 2,092,317.94 ha) |
| Outcome 3: Sustainable peatland management knowledge, technologies, and markets developed and expanded | MOEF coordinated National Sector Working Group for Peatland Management and its web-based knowledge platform operating sustainably |  | Yes | Yes | 0 | 0 | Yes | Yes |
|  | At least 5,000 smallholder households in 13 villages implementing sustainable peatland livelihoods (gender disaggregated) | households | 2,000 | 5,000 | 0 (men-headed HHs) | 189 (men-headed HHs) | 0 (men-headed HHs) | 189 (men- Headed HHs) |
|  |  |  |  |  | 0 (women-headed HHs) | 95 (women-headed HHs) | 0 (women-headed HHs) | 95 (women-headed HHs) |
|  |  |  |  |  | 0 (total) | 284 (total) | 0 (total) | 284 (total) |
| Output 3.1: Platform and database for effective stakeholder communication on peatland policy and management | At least 6,000 stakeholders participate in workshops (2,000), training/exchanges (1,000) and access information on Peatland management hub (4,000) (disaggregated by activity and, where possible, by gender) | number of stakeholders | 3,000 | 6,000 | 32,000 (users accessing the SIMATAG and SIPPEG peatland management hubs) | 0 | 81 (smallholders trained in RSPO/ISPO standards) | 81 (smallholders trained in RSPO/ISPO standards) 32,000 (users accessing the SIMATAG and SIPPEG peatland management hubs) |
| Output 3.2: Technology and markets for the sustainable use of already converted peatlands | At least three high-value ecologically beneficial peatland products sustainably developed and marketed | peatland products | 2 | 3 | 0 | 0 | 2 | 2 |

### Annex 1: List of PHUs inventoried by the GEF6 IMPLI Project & MOEF

| No. | Name of PHU | Code | Province | District | Area (Ha) |
| --- | --- | --- | --- | --- | --- |
| 1 | KHG Sungai Rokan-Sungai Siak Kecil | KHG.14.03-07-12.01 | Riau | Bengkalis,Kota Dumai, Rokan Hilir | 832,458 |
| 2 | KHG Sungai Siak Kecil-Sungai Siak | KHG.14.03-08.01 | Riau | Bengkalis, Siak | 163,787 |
| 3 | KHG Sungai Siak-Sungai Kampar | KHG.14.05-08.01 | Riau | Pelalawan, Siak | 722,929 |
| 4 | KHG Sungai Batanghari-Sungai Air Hitam Laut | KHG.15.05-07.01 | Jambi | Muaro Jambi, Tanjung Jabung Timur | 189,862 |
| 5 | KHG Sungai Air Hitam Laut-Sungai Buntu Kecil | KHG.15-16.01 | Jambi, Sumatera Selatan | Muaro Jambi, Tanjung Jabung Timur, Banyuasin | 183,856 |
| 6 | KHG Sungai Merang-Sungai Ngirawan | KHG.16.06-07.01 | Sumatera Selatan | Banyuasin, Musi Banyuasin | 82,021 |
| 7 | KHG Sungai Ngirawan-Sungai Sembilang | KHG.16.06-07.02 | Sumatera Selatan | Banyuasin, Musi Banyuasin | 73,475 |
| 8 | KHG Sungai Sembilang-Sungai Lalan | KHG.16.06-07.03 | Sumatera Selatan | Banyuasin, Musi Banyuasin | 84,670 |
| 9 | KHG Sungai Burnai-Sungai Sibumbung | KHG.16.02.05 | Sumatera Selatan | Ogan Komering Ilir | 86,679 |
| 10 | KHG Sungai Rokan Kiri - Sungai Mandau | KHG.14.01-03-06- 08.01 | Riau | Bengkalis | 103,968 |
| 11 |  |  |  | Kampar |  |
| 12 |  |  |  | Rokan Hulu |  |
| 13 |  |  |  | Siak |  |
| 14 | KHG Sungai Bangko - Sungai Rokan Kanan | KHG.14.07.03 | Riau | Rokan Hilir | 43,367 |
| TOTAL |  |  |  |  | 2,567,072 |

*Kawasan Hydrologi Gambut (KHG) = Peatland Hydrology Unit (PHU)

### Annex 2: List of concessions under improvement & support by GEF6 IMPLI

The following companies have signed concessionaire agreements with the MoEF, formalised by Directorate General Decrees:

| No. | Name of Company | Area (Ha) | License Status | PHU Name | Province | District |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | PT 1 | 34,469 | PBPH/IUPHHK-HT | KHG Sungai Rokan - Sungai Siak Kecil | Riau | Kota Dumai |
| 2 | PT 2 | 32,661 | PBPH/IUPHHK-HT | KHG Sungai Rokan - Sungai Siak Kecil | Riau | Bengkalis |
| 3 | PT 3 | 9,401 | PBPH/IUPHHK-HT | KHG Sungai Siak - Sungai Kampar | Riau | Pelalawan |
| 4 | PT 4 | 39,807 | PBPH/IUPHHK-HT | KHG Sungai Rokan - Sungai Siak Kecil | Riau | Kota Dumai Rokan Hilir |
| 5 | PT 5 | 46,229 | PBPH/IUPHHK-HT | KHG Sungai Rokan - Sungai Siak Kecil | Riau | Bengkalis |
| 6 | PT 6 | 16,358 | PBPH/IUPHHK-HT | KHG Sungai Siak - Sungai Kampar KHG Sungai Siak Kecil - Sungai Siak | Riau | Bengkalis Siak |
| 7 | PT 7 | 20,129 | PBPH/IUPHHK-HT | KHG Sungai Rokan - Sungai Siak Kecil | Riau | Rokan Hulu |
| 8 | PT 8 | 5,630 | PBPH/IUPHHK-HT | KHG Sungai Siak Kecil - Sungai Siak | Riau | Siak |
| 9 | PT 9 | 148,712 | PBPH/IUPHHK-HT | KHG Sungai Rokan - Sungai Siak Kecil KHG Sungai Siak - Sungai Kampar KHG Sungai Siak Kecil - Sungai Siak | Riau | Bengkalis Kota Dumai Rokan Hilir Siak |
| 10 | PT 10 | 11,963 | PBPH/IUPHHK-HT | KHG Sungai Siak - Sungai Kampar | Riau | Pelalawan |
| 11 | PT 11 | 205,767 | PBPH/IUPHHK-HT | KHG Sungai Siak - Sungai Kampar KHG Sungai Siak Kecil - Sungai Siak | Riau | Pelalawan Siak |
| TOTAL |  | 571,127 |  |  |  |  |

### Annex 3: Mission preparation and planning, TORs, schedules, people met.

Terms of Reference for Mid-Term Review

# Integrated Management of Peatland Landscape in Indonesia (IMPLI) project

| MISSION DETAILS |  |
| --- | --- |
| Country of Assignment/Location: | Republic of Indonesia |
| Mission Name: | Mid-Term Review of the Integrated Management of Peatland Landscapes in Indonesia (IMPLI) (Grant ID: 2000000957) |
| Mission Start Date: | 9 October 2024 |
| Mission End Date: | 18 October 2024 |
| Division/Department: | Asia and Pacific Division |
| Reports to (name and title): | Hani Elsadani Salem, Country Director/Hub Head Anupa Rimal Lamichhane (Lead Regional Environment and Climate Specialist for Asia Pacific) |

| MISSION COMPOSITION (Team members’ full name and specialization) |  |
| --- | --- |
| Name: | Specialization: |
| Hani Elsadani Salem | Country Director |
| Damayanti Buchori (independent consultant) | Team Leader & Project Management Specialist (TL) |
| Praise Uke (independent consultant) | Environment and Natural Resources Management Specialist (ENRMS) |
| Dudy Nugroho | Environment & Climate Specialist (ECS) |
| Muhammad Iskandar | Procurement Specialist |
| Chiara Merola | Water Management & Monitoring-Evaluation Specialist |
| Rahmi Khalida | Targeting & Gender-Social Inclusion Specialist |

MISSION BACKGROUND

The “Integrated Management of Peatland Landscapes in Indonesia (IMPLI)” is a five-year project that aims to strengthen systems for sustainable management, biodiversity conservation, GHG emission reduction, and improved rural livelihoods in target peatlands of Indonesia. The project focuses on the following activities: i) strengthening institutional capacity, frameworks and partnerships for scaling-up of sustainable peatland restoration; ii) sustaining integrated management of priority Peatland Hydrological Units (PHUs) in Project provinces; and iii) developing and expanding sustainable peatland management knowledge, technologies, and markets. The Financing Agreement for the Project was signed between the Ministry of Environment and Forestry of the Government of Indonesia (hereinafter referred to as MOEF) and the International Fund for Agricultural Development (hereinafter referred to as IFAD) on 22 July 2020. The Financing Agreement formalizes the approval and administration of the Financing from the Global Environment Facility (GEF) and the supervision of the project implementation for five years (2020-2025). In 2020, the IMPLI project proposed to relocate one of the site projects from North Sumatra to South Sumatra to integrate the landscape in Riau-Jambi and South Sumatra as the biggest Peat Hydrology Units (PHUs) which still have peat-dome. It was approved in 2021 by GEF Secretariat and got No Objection from IFAD. GEF6 IMPLI project was implemented on 22 July 2020 expected project completion on 30th September 2025 and expected financial closure date on 31st March 2026. The total project is US$ 27,267,832, with GEF allocated funds is US$ 4,895,872 and co-financing is US$ 22,371,960. The IMPLI Project's goal is to manage and sustainably use peatlands to conserve biodiversity and ecosystem services and reduce greenhouse gas emissions. Project Objective: To strengthen systems for sustainable management, biodiversity conservation, GHG emission reduction, and improved rural livelihoods in target peatlands of Indonesia. The project has 3 key performance indicators for: - Core Indicator 4: 1.2 million hectares of peatland landscape sustainably managed It will be focused on the Peatland Hydrology Units (PHUs) - In Riau Province: PHU Sungai Rokan – Sungai Siak Kecil and PHU Sungai Siak Kecil – Sungai Siak, which covers the Giam Siak – Bukit Batu (GSK-BB) biosphere reserve located in Bengkalis and Siak District - In Jambi Province, two PHUs will be covered: (i) PHU Sungai Batanghari – Sungai Air Hitam Laut and PHU Air Hitam Laut – PHU Sungai Buntu Kecil, in Muaro Jambi, and (ii) in Tanjung Jabung Timur district will cover the Berbak-Sembilang National Park - In South Sumatra Province, two PHUs will be covered for (i) PHU Air Hitam Laut – PHU Sungai Buntu Kecil dan PHU Sungai Ngirawan – Sungai Sembilang, in Banyuasin dan Musi Banyuasin District. - Core Indicator 6: 4.31 million metric tons of CO2e mitigated. - Core Indicator 11: 5,000 smallholder HHs directly benefit through sustainable peatland management practices and livelihoods, and 15,000 HHs indirectly benefit through improved knowledge and access to markets (total of 20,000 HHs). Additional 120,000 ha of peatlands under an improved management regime (disaggregated by smallholder (20,000 ha, disaggregated by men/women smallholders) and concessionaire management (100,000 ha). To achieve the objective and key performance indicators as mentioned above, IMPLI will manages the operational with 3 outcomes and 7 outputs as explained below: Outcome 1: Institutional capacity, frameworks, and partnerships for scaling-up of sustainable peatland restoration operational Output 1.1: Capacity building for key stakeholders in sustainable peatland management Detail key performance in Outcome 2: Key Performance Indicators - Trained peatland stakeholders competently applying sustainable PHU management. - 600 national and regional stakeholders trained in landscape scale peatland analysis and management. Outcome 2: Integrated management of priority PHUs in Project provinces sustained Output 2.1: Sustainable integrated management of the GSK-BB Peatland Landscape Output 2.2: Support development of integrated peatland protection, management and financing plans in Jambi and South Sumatera provinces Detail key performance in Outcome 2: Key Performance Indicators - Reduced peatland and forest degradation (50%) and fires (70%) in GSK-BB peatland landscape (against rolling three-year average). - Multiple stakeholders supporting Biosphere Reserve Management Plan implementation and regular updating. - Medium term strategy and PHU protection, management and financing plans for GSK-BB Peatland Landscape/PHU. - 100,000 ha of plantation and 20,000 ha of community peatlands have medium-term SPM investment frameworks including a pipeline of investment concepts. - At least 10,000 smallholders trained in ISPO/ RSPO standards using Project-prepared compliance training package - Land-use plans for the protection and management of 100,000 ha of PHU Landscapes in the provinces of Jambi and South Sumatera respectively Outcome 3: Sustainable peatland management knowledge, technologies, and markets developed and expanded Output 3.1: Platform and database for effective stakeholder communication on peatland policy and management Output 3.2: Technology and markets for the sustainable use of already converted peatlands Detail key performance in Outcome 3: Key Performance Indicators - MOEF coordinated National Sector Working Group for Peatland Management and its web-based knowledge platform operating sustainably. - At least 5,000 smallholder households in 12 villages implementing sustainable peatland livelihoods. - At least 6,000 stakeholders participate in workshops (2,000), training/exchanges (1,000) and access information on Peatland management hub (4,000). - At least three high-value ecologically beneficial peatland products sustainably developed and marketed. The IMPLI Project is expected to contribute significantly on global environment benefits in sectors of climate change, land degradation and sustainable forest management/ REDD-Plus. Five separate tracking tools have been developed to review progress of the Project against securing the benefits. Tracking Tools for CCM; BD-9; BD-1-2; SFM and LD). - Climate Change: The Project will contribute to significant reductions in GHG emissions from targeted peatlands, through enhanced water management unit and adoption of integrated fire management. In 2009, the Indonesian government pledged to reduce its emissions to 26 percent below the business-as-usual levels by 2020, and as much as 41 percent, if international funding support was forthcoming. The IMPLI will help the country achieve such targets by mitigating at least 4.31 million tons of CO2e through improved peatland management (described in further detail in the Project Design Report). - Land Degradation and Sustainable Forest Management: The key global environmental benefits will arise from the protection, rehabilitation, and sustainable management of key peatland areas which play a critical role in the economy and ecology by providing timber and non-timber products, regulating water supply and flood control, supporting livelihoods of community groups living in and adjacent to the peatlands. The project will contribute 1,200,000 ha of peatlands in Indonesia being under integrated sustainable management including at least 120,000 ha of peatlands under an improved management regime., and100,000 ha of plantation and 20,000 ha of community peatlands have medium-term SPM investment frameworks including a pipeline of investment concepts. - Biodiversity: The key global environmental benefits will arise from the protection, rehabilitation, and sustainable management of key peatland areas of globally significant biodiversity, such as in the GSK-BB BR. This will be leading to the formalization of the Giam Siak landscape as a Key Biodiversity Area (KBA), in preparation for GSK and BB Wildlife Reserves being designated as a protected area. In addition, activities in Jambi & South Sumatera Provinces will support the biodiversity of the Berbak-Sembilang National Park and the landscape within the target PHUs. IMPLI has structured the institutional operational and breakdown into (i) project management, and (ii) project implementation. The Project Management are the National Steering Committee (NSC), the Project Management Office (PMO), the Provincial Project Management Offices (PPMOs). Project Implementation are the PMO, PPMOs, National and provincial agencies, Project District Units (PDUs), the District Authorities, and the Sub-District/Village Heads where appropriate.

MISSION OBJECTIVES & OUTPUTS

The objectives of this MTR mission are: - Project performance in achieving project outputs and outcomes: This will include assessing the achievements against project logical framework, project target indicators and GEF Tracking Tools, assessing the achievements included in the Semi-Annual Progress Reports (SAPRs) submitted by the PMO, and Annual Work Plan and Budgets (AWPBs). This will also include data collection and assessing project impacts on the ground in the project sites. Overall impact and constraints in the implementation of project activities will also be assessed. - Overall project management and institutional arrangement: This will include assessing the performance and capacity gaps of NPMO, SPMO, key partners and service providers related issues, as well as any staffing gaps (e.g. turn-over the staff in National and sub-national levels, recruitment process, etc.). This will also include assessing the performance and timeliness in preparing the SAPRs, AWPBs, GEF Project Implementation Reports (PIRs), etc. - Financial management, procurement and compliance with legal covenants: This will include assessing the performance and timeliness of preparing the AWPBs and Procurement Plans (PPs), Withdrawal Applications (WAs), Statement of Expenditures (SOEs); performance and the financial management system; internal/external audit, disbursement and finance reporting from national and sub-national including the technical and financial arrangement, and compliance with legal covenants. It will also involve identifying areas for specific support/training to be provided from IFAD to the PMO. - Monitoring & Evaluation (M&E) and knowledge management: This will involve assessing the quality of the M&E concept and systems, KM concept, SAPRs and PIRs prepared by project, database systems. The quality of the knowledge products (KPs) developed by the project (videos, reports, etc.) will be assessed, recommendations will be made on possible opportunities to increase the project’s visibility and ways to better share lessons learned from the project and its contribution to sustainable use of peatlands. - Recommendations and implementation support for further improvements and adjustments of the project on all above aspects. The expected output from the MTR mission is an aide-memoire, agreed and signed by IFAD and MOEF that consist of a review of the whole implementation, financial management processes, a set agreed actions and recommendations to enhance and strengthen GEF6 IMPLI project implementation. (1) Highly unsatisfactory. Almost no targets/ requirements met. Consideration should be given to cancellation/suspension.

| INDIVIDUAL RESPONSIBILITIES, EXPECTED OUTPUTS AND REQUIRED COMPLETION DATES |  |  |
| --- | --- | --- |
| Full Name of mission member: | Description of Tasks (Expected Activities) | Expected Outputs/deliverables |
| Hani Elsadani Salem (Country Director) | The Country Director and the Regional Climate and Environment Specialist will provide overall technical and managerial guidance to the IFAD team, will lead the discussions with the MOEF from the IFAD side, and will ensure that the Aide Memoire and other documents to be prepared as a result of the Mid-Term review meet the expected quality standards. - Lead the team during the kick-off and wrap up MTR mission - Lead the strategic meetings with the government of Indonesia - Lead meeting with GEF OFP Indonesia | - Agreed the Aide Memoire with MOEF - Final Report to be submitted to IFAD HQ |
| Team Leader & Project Management Specialist (TL) (Damayanti Buchori - Independent consultant) | She will be responsible for the following: - Assess IMPLI project progress, performance and quality of implementation in line with the defined objectives, and legal and financial agreement; - Identify barriers and challenges during the implementation of the project, and discuss with the Project team - solutions, strategy and action plan to address the barriers and challenges; - Review the institutional arrangements at the national, provincial, district and village level; - Assess the current human capacity gap and staffing of the NPMO, PPMO, DPMU, Village Facilitator. - Identify IMPLI project implementation bottlenecks and recommend actions to speed up project implementation; - Review and suggest revisions as necessary the current IMPLI implementation plans, AWPBs and procurement plans; - Review national, province and district implementation structures and discuss the integration of the others peatland project within these structures; - Review the exit strategy of the project; - Propose project rating following IFAD Mission criteria and provide justifications; - Consolidate inputs from all team members and finalise the Aide Memoire in coordination with the other team members following IFAD’s formats and requirements; - Lead the compilation of the GEF Tracking Tools for the IMPLI project, updated at MTR; | Expected deliverables: - MTR mission findings, to be presented and discussed (in English) at mission wrap-up meeting with IFAD – 18 October 2024 - Draft Aide Memoire summarizing the findings and recommendations of the mission, which are to be discussed and agreed with the MOEF and other relevant stakeholders –22 October 2024 - Final MTR report (in English) to be submitted, including a 2-3 page executive summary, a set of limited and strategic recommendations (not to exceed 10 recommendations total), and response addressing issues raised during presentation of draft. The suggested template for the report will be provided – 30 October 2024 |
| Environment and Natural Resources Management Specialist (ENRMS) Praise Uke (Independent consultant) | He will be responsible for: - Assess IMPLI project progress, performance and quality of implementation in line with the defined objectives, and legal and financial agreement; - Identify barriers and challenges during implementation of the project, and discuss with the Project team - solutions, strategy and action plan to address the barriers and challenges; - In coordination with other team members identify IMPLI project bottlenecks and provide necessary support to speed up project implementation; - Keep track on the mission reporting timeline and follow up on the IFAD internal process; - In coordination with Country Director and TL, discuss on the next IMPLI implementation plan including review their AWPB; - Contribute in the assessment of project performance and quality of implementation with a focus on (a) peatland policy, regulations and institutional mechanisms and capacity enhanced, (b) PHU mapping, (c) development of integrated management plan (IMP) for KG & GB PHUs (c) enhancement of community livelihood from sustainable peatland management practise (under Components 1 and 3); - Contribute in the assessment of project performance and quality of implementation with a focus on (a) assessment of GHG emission reduced, identify any bottlenecks and provide recommendations, (b) assessment of progress of peatland fire prediction, monitoring and warning systems (under Component 2); - Propose project rating following IFAD Mission criteria and provide justifications especially on (a) overall project performance (b) likelihood of achieving project objectives, outputs and outcomes, (c) implementation progress related to Component 2 and beyond; - Assess and review the environment, social and climate change impacts identified in PDR/CER, and its consistency with the county systems and/or IFAD SECAP procedure in 2021 - Synergize the SECAP with National Determined Contribution (NCD) in Indonesia - Support compilation of the GEF Tracking Tools for the IMPLI project - Review the Knowledge Management & Communication Concept synchronize with the targeting of the IMPLI project - Identify potential knowledge products (KPs) from the project and support the review of produced KPs when necessary; - Propose and recommend for the knowledge management improvements for IMPLI including knowledge products (i.e. publications, videos, etc.), as well as outreach and project visibility aspects; - Review the knowledge/outreach products and define the key recommendations for the sustainability knowledge and information. - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Review and report the SECAP – 20 October 2024 - Update the GEF Tracking tool for IMPLI – 22 October 2024 - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to environment, secap and technical issues – 22 October 2024 Contribute for Final MTR report (in English) as guided by TL – 30 October 2024 |
| Water Management, Monitoring & Evaluation (Chiara Merola) | She will be responsible for: - Identify the Monitoring & Evaluation (M&E) concept and review the progress and the achievement to achieve the project outputs/outcomes; - Review the IMPLI M&E system and reporting (incl. logframe etc) in the absence of the baseline report, including tools for collecting information; M&E reporting (quality, timeliness), use of M&E for planning/AWPB and reporting (SAPR, PIR). - Identify potential knowledge products (KPs) from the project and support the review of produced KPs when necessary; - Propose and recommend for the M&E IMPLI - Review and provide inputs on IMPLI-related MOEF Management Information System (MIS) and websites. - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to M&E and Knowledge Management arrangements, process, and records – 22 October 2024 - Contribute for Final MTR report (in English) as guided by TL – 30 October 2024 |
| Targeting & Gender-Social Inclusion (Rahmi Khalida) | She will be responsible for: - Review the existing document PPG, and evaluate the conditions and relevance of the Theory of Change, Log Frame, and targeting based on the GEF key indicators and milestones - Review the targeting based on the revised document during the Inception Workshop of GEF6 IMPLI in 2022 - Identify gender and youth-targeted activities in the project and propose any recommendations for improved engagement where necessary; - Assess and review the environment, social and climate change impacts identified in PDR/CER, and its consistency with the county systems and/or IFAD SECAP procedure in 2021 - Support to review SECAP on the gender and social inclusion of the IMPLI project - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to M&E and Knowledge Management arrangements, process, and records – 22 October 2024 - Contribute for Final MTR report (in English) as guided by TL – 30 October 2024 |
| Environment & Climate Change Specialist (Dudy Nugroho) | He will be responsible for: - Coordinate communication between the project team and MOEF staff, and GEF OFP Indonesia; - In coordination with other team members identify IMPLI project bottlenecks and provide necessary guidance and support to speed up project implementation with a focus on (a) assessment of GHG emission reduced, identify any bottlenecks and provide recommendations, (b) assessment of progress of peatland fire prediction, monitoring and warning systems (under Component 2); - In coordination with Team Leader and ENRMS discuss on the next IMPLI implementation plan including a review their AWPB; - Review performance against and alignment with AWPBs; - Propose project rating following IFAD Mission criteria and provide justifications, especially on (a) likelihood of achieving project objectives, outputs and outcomes, (b) implementation progress related to Component 2 and beyond; - Support to identify and prepare knowledge product to showcase best practices and/or lessons learned on peatland management based on project implementation; - Review national and sub-national implementation structures and discuss the integration of the upcoming COPLI project within these structures; and - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Share the supporting documents to be used for the MTR mission – 20 October 2024 - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to technical issues in the log frame and GEF indicator– 22 October 2024 - Contribute for Final MTR report (in English) as guided by TL – 30 October 2024 |
| Procurement Specialist (Muhammad Iskandar) | He will be responsible for: - Review the current Procurement Plan in order to assess it has been fully updated and upgraded, ascertain its completeness, its concurrence with the AWPB, and its consistency with the country systems and/or IFAD Procurement Guidelines and Handbook; - Carry out spot checks on past procurement activities and assess the extent these adhere to Government and/or IFAD Procurement Guidelines and Handbook; in particular, verify that the goods, services and works procured correspond with the approved AWPB and Procurement Plan, in terms of quality and quantities; - Review the procurement, contracting and implementation processes and timeliness and appropriateness of procurement actions; - Assess contract administration and management procedures; - Determine whether adequate systems are in place for procurement planning, implementation and monitoring, and whether documentation are maintained as per required standards and can be relied upon; - Verify to the extent possible, whether goods, works and consulting services contracted were supplied/completed according to the required specifications and technical standards; - Review issues identified in the previous procurement review and aide-mémoire and procurement related issues identified in project audit reports; - Identify deficiencies and make recommendations for improvements and control mechanisms in the procurement procedures and processes; - Submit an assignment report (as per IFAD format), and any other relevant ancillary documents; - Any other tasks as requested by the Country Director, RCES or TL. | Expected deliverables: - Contribution to the Aide Memoire, as discussed and agreed with the team leader – related to procurement arrangements, process and records – 22 October 2024 - Contribute for Final MTR report (in English) as guided by TL – 30 October 2024 |

### Itinerary of the Mid-term Review (MTR) of the GEF6 IMPLI project in Indonesia

| Day/Date | Team-1 |  | Team-2 |  |
| --- | --- | --- | --- | --- |
|  | Agenda | Location | Agenda | Location |
| Wed, 9th | AM: MTR Kickoff; PM: travel to project locations Jakarta |  |  |  |
| Thu, 10th | - Meeting Coordination with PPMO Riau, and DPMU Siak and Bengkalis in Pekanbaru office - Internal meeting of PMO-DPMU, IFAD | Pekanbaru | - Meeting Coordination meeting with PPMO South Sumatra & DPMU Muba - site visits to Tanjung Menang Village | Palembang Canals blocking in 2023, Demo-plot 12 Ha |
| Fri, 11th | - Meeting with TK-PPEG in Tasik Serai Village - Meeting with village leaders, TK-PPEG, PPMO, DPMU, FM | Tasik Serai Village, Bengkalis District | - Meeting with head of Muara Medak - Visit & discussion with TK-PPEG Muara Medak | Musi Banyuasin District |
| Sat, 12th | - Meeting at Rawa Mekar Jaya Village - Discussions with TK-PPEG, village leaders, PPMO, DPMU, FM | Rawa Mekar Jaya, Siak District | - Field visits to Jebus Village - Field Visits to Sungai Aur Village | Muaro Jambi district |
| Sun, 13th | - Meeting with Head of village and village leaders in Village office - Discussions with TK-PPEG, village leaders, PPMO, DPMU, FMU | Dayun Village, Siak District | - Meeting with PPMO Jambi & DMPU Muara Jambi - Meeting with Private Sectors | Jambi |
| Mon, 14th | - Internal discussion IFAD and PMO - Travel back to Jakarta | Pekanbaru | - Am: team coordination (IFAD & PMO) - Travel back to Jakarta | Jambi |

### List of Documents Reviewed

- GEF6 IMPLI approved proposal documents (prodoc)

- GEF6 IMPLI Financial Agreement

- GEF6 IMPLI Letter to the recipient and Amendment Letter

- GEF6 IMPLI GEF Tracking Tools (compiled at design for LD, SFM, and CCM)

- GEF6 IMPLI Project Implementation Manual (PIM)

- GEF6 IMPLI Annual Work Plan and Budget (AWPB) and Procurement Plans (PP) 2022

- GEF6 IMPLI Annual Work Plan and Budget (AWPB) and Procurement Plans (PP) 2023

- GEF6 IMPLI Annual Work Plan and Budget (AWPB) and Procurement Plans (PP) 2024

- GEF6 IMPLI 1st Project Implementation Reports (PIRs)

- GEF6 IMPLI 2nd Project Implementation Reports (PIRs)

- GEF6 IMPLI 3rd Project Implementation Reports (PIRs)

- GEF6 IMPLI Semi-Annual Progress Reports (SAPRs)

- GEF6 IMPLI Implementation Support/Supervision Mission (2021 – 2022) Resume of Meeting (aide memoire)

- GEF6 IMPLI Inception Workshop Report

- GEF6 IMPLI Financial Reports (include the audit reports)

- GEF6 IMPLI Knowledge Product

- GEF6 IMPLI Monitoring & Evaluation System

- Rencana Kerja Masyarakat (Community Work Plan – 13 villages)

### List of Stakeholders Consulted

            - The Ministry of Environment and Forestry (MoEF)

            - Badan Restorasi Gambut & Mangrove (BRGM)

            - National Agency for Peat and Mangrove Restoration

            - Environment Agency, South Sumatra Province

            - Environment Agency, Jambi Province

            - Environment & Forestry Agency, Riau Province

            - Environment Agency, Siak District, Riau

            - Environment Agency, Bengkalis District, Riau

            - Environment Agency, Muaro Jambi, Jambi

            - Environment Agency, Musi Banyuasin, South Sumatra

            - Tasik Serai Village Group

            - Rawa Mekar Jaya Village Group

            - Tanjung menang Village Group

            - Muara Medak Village Group

            - Jebus Village Group

            - Sungai Aur Village Group

            - PT. Arara Abadi (RAPP)

            - PT. Jambi Batanghari Plantation

            - PT. Erasakti Wira Forestama

            - PT. Bukit Bintang Sawit