UNEP GEF PIR Fiscal Year 2020

Reporting from 1 July 2000 to 21 Apr 2021

Update version April 2021 – on impact and mitigation related to COVID.

| - Identification |  |  | GEF ID.: 9409 | Umoja no.: 1407 |  |
| --- | --- | --- | --- | --- | --- |
| Project Number + Project Title |  |  | Healthy Landscapes: Managing Agricultural Landscapes in Socio-ecologically Sensitive Areas to Promote Food Security, Well-being and Ecosystem Health |  |  |
| Duration months | Planned |  | 36 |  |  |
|  | Extension(s) |  | N/A |  | N/A |
| Division(s) Implementing the project |  |  | GEF - Biodiversity and Land Degradation Unit, Ecosystems Division |  |  |
| Executing Agency(ies) |  |  | UN Environment Programme |  |  |
| Names of Other Project Partners |  |  | Ministry of Mahaweli Development and Environment |  |  |
|  |  |  | Mahaweli Authority of Sri Lanka |  |  |
|  |  |  | Ministry of Agriculture, Department of Agriculture |  |  |
|  |  |  | Bioversity International |  |  |
| Project Type |  |  | Medium Size Project |  |  |
| Project Scope |  |  | National |  |  |
| Region (delete as appropriate) |  |  | Asia Pacific |  |  |
| Names of Beneficiary Countries |  |  | Sri Lanka |  |  |
| Programme of Work |  |  | Biennium 2018-2019 Subprogramme 3 - Healthy and productive ecosystems |  |  |
| GEF Focal Area(s) |  |  | Multi Focal Areas |  |  |
| UNDAF linkages |  |  | Pillar 4, Environmental Sustainability, Climate Change and Disaster Risk Reduction |  |  |
| Link to relevant SDG target(s) and SDG indicator(s) |  |  | SDG 2,3,5,6,15 |  |  |
| GEF financing amount |  |  | US$ 2,000,000 |  |  |
| Co-financing amount |  |  | US$ 9,047,865 |  |  |
| Date of CEO Endorsement |  |  | 30 April 2018 |  |  |
| Start of Implementation |  |  | 1 April 2019 |  |  |
| Date of first disbursement |  |  | 3 September 2019 |  |  |
| Total disbursement as of April 2021 |  |  | US$ 300,000 |  |  |
| Total expenditure as of April 2021 |  |  | US$ 278,171 |  |  |
| Expected Mid-Term Date |  |  | September 2021 |  |  |
| Completion Date |  | Planned | 2 Sept 2022 |  |  |
|  |  | Revised | 30 August 2023 |  |  |
| Expected Terminal Evaluation Date |  |  | February - March 2023 |  |  |
| Expected Financial Closure Date |  |  | March 2024 |  |  |

- OVERVIEW OF PROJECT STATUS

| UN Environment Subprogramme(s) Subprogramme 3 - Healthy and productive ecosystems 2020-2021 | Specify the relevant Expected Accomplishment(s) & Indicator(s) EA (a) The health and productivity of marine, freshwater and terrestrial ecosystems are institutionalized in education, monitoring and cross-sectoral and transboundary collaboration frameworks47 at the national and international levels Indicator: (i) The number of countries and transboundary collaboration frameworks that have made progress in monitoring and maintaining the health and productivity of marine and terrestrial ecosystems |
| --- | --- |
| The Project has yet to start field implementation or generating impact yet by strengthening the conservation, restoration and sustainable use of cascade landscape ecosystems and their services – specifically the cascade water systems, the sustainable management of forested areas in cascade landscapes and the restoration of degraded land and soil, the project will contribute to maintaining and restoring the health of productive landscapes. Additionally, by implementing agroecology and SLM practices, the project will reduce the need for agrochemicals triggering a reduction in water pollution from such sources. The project will also contribute to greater water-use efficiency, enhanced integrated water resources management, and restoration of water-related ecosystems, resulting in increased resilience and maintaining the health and productive ecosystems in Sri Lanka. |  |

For all GEF 6 and later projects:

| GEF Core Indicators Indicator 4. Area of landscapes under improved practices | Indicative expected Results 20,000 ha |
| --- | --- |
| The Project has yet to commence implementation of activities at the project sites. |  |

| Planned linkages with UNDAF | The project is consistent with UNDAF’s goals for Sri Lanka (2012-2017), particularly with pillar 4, Environmental Sustainability, Climate Change and Disaster Risk Reduction. Progress towards this goal is minimal at this stage as implementation has been delayed due to the COVID-19 pandemic |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | The project plans to contribute to the following SDG goals: SDG 2 - By improving access to safe and nutritious food, improving agricultural productivity, promoting sustainable agriculture and land management and the maintenance and conservation of genetic diversity of seeds, cultivated plants, farmed and domesticated animals and their related wild species, the project will specifically contribute to SDG targets 2.1., 2.3, 2.4. and 2.5 and indicators 2.1.1, 2.1.2, 2.3.2, 2.4.1, 2.5.1. SDG 5 - By empowering women in project landscapes to engage in project implementation, to access and share the benefits that accrue, the project will contribute to SDG target 5.5 and corresponding indicator 5.5.2 SDG 6 - Through the implementation of agroecology and SLM practices, the project will reduce the need for agrochemicals triggering a reduction in water pollution from such sources. The project will also contribute to greater water-use efficiency, enhanced integrated water resources management, restoration of water-related ecosystems and will support and strengthen the participation of local communities for improving water management in Village Tank Cascade Systems (VTCS). By so doing, the project will contribute to SDG targets 6.3, 6.4, 6.5, 6.6 and 6.B and corresponding indicators 6.3.2; 6.4.1; 6.5.1; 6.6.1; and 6.B.1. SDG 15 - By strengthening the conservation, restoration and sustainable use of cascade landscape ecosystems and their services, the sustainable management of forested areas in cascade landscapes and the restoration of degraded land and soil, the project will contribute to SDG targets 15.1, 15.2, 15.3, 15.5 and 15.9 and corresponding indicators 15.1.2, 15.2.1, 15.3.1, 15.5.1, 15.9.1. |
| --- | --- |

| Implementation Status | FY 2020 | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | … PIR | … PIR |

| Development Objective Rating FY | FY 2020 | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MU |  |  |  |  |
| The second half of 2019 in Sri Lanka proved to be a challenging time following the terrorist attacks in Colombo in April 2019. This caused a significant disruption to the planning of all activities especially the establishment of the contract with the lead NEA, as well as timing of the official Project Inception Workshop. Most government offices and universities closed temporarily and, for a couple of months following the attacks, travel within the country was not allowed or limited. Despite this, the Project Inception Workshop was able to go ahead in September 2019. Shortly after, national elections were called in November 2019, which further impacted the project. As with previous elections, government personnel were required to undertake election related duties and, when the outcomes of the election were announced, there were political changes of minister, secretary and other staff within the Ministry of Environment. This, combined with the political changes the country has gone through over the preceding 3-4 years, has made it complicated to begin project implementation. New political appointments and other new staff resulted in a considerable period of inertia shortly thereafter which dragged on until early 2020. Further, a new general election is scheduled to take place in August 2020. A LOA with the Ministry of Environment was developed in 2019, but it is still pending approval and signature from the Ministry’s side. Only once the LOA is approved and signed will it be possible for the Ministry to establish a Project Management Unit (PMU) and officially identify the national project manager and other support staff and disburse funds. The EA Project Manager visited Sri Lanka in January 2020 meeting with the core project team in Peradeniya to discuss the political situation since the Project Inception Workshop and to try to find a solution to move the project forward while things settle down in the Ministry. This resulted in a strategy to at least commence certain priority actions while awaiting approval of the government LOA. A follow up trip by the EA Project Manager was scheduled for March 2020, however, by that stage, indications of the pending COVID-19 pandemic had arisen and the trip was cancelled. Furthermore, Parliament was dissolved in March when new elections were scheduled for the end of April 2020. The COVID-19 pandemic started up in Sri Lanka at the same time, which resulted in the closure of all ministry offices as well as other organizations, and all staff working remotely, with travel to rural areas restricted or forbidden. This has been the situation for the remainder of the first half of 2020. It is only now, in July 2020, that all offices are reopening and staff slowly returning to offices. Despite the ongoing political challenges and those posed by the COVID-19 pandemic, a comprehensive scoping document, ToRs, workplan and timeline were developed to jumpstart the baseline assessment in the project landscapes using most of the core team who were involved in the PPG. This work also includes project site level consultations, awareness raising consultations at the community level in both project landscapes, including networking and partnership building among key partners and stakeholders. It is anticipated that this will establish a good platform for project implementation upon approval of the Ministry LOA. It is anticipated that this will also highlight how the project can contribute to the post-COVID-19 pandemic recovery. Relevant project communication materials are being developed including the project flyer, development of a logo/branding and hopefully the first strides towards a project website. However, activities and overall project implementation are expected to continue to be delayed due to the impact of COVID-19. Finally, in addition to assessing the COVID-19 impact in the project landscapes as above, some of the core project team are collaborating with a range of international organizations e.g. WFP, Johns Hopkins University, to undertake additional assessments and are ensuring the project sites are included in these. Further, the project team are already involved in discussions at a ministerial level to see how the project might support the recovery process, as outlined below. April 2021 update: As highlighted in the section below, Implementation Progress, there has been some progress since the YR20 PIR which is largely confined to Component 1 but which provides a strong platform for many planned activities especially those knowledge products identified in Components 3 and 4. The key challenges faced by the project have been the seemingly intractable political and management issues within MMDE highlighted in the PIR2020 compounded by the COVID-19 pandemic. All of which has resulted in impacts on establishing a project management unit, recruitment of a national manager, disbursement of funds and other downstream implementation of activities including mobilizing of key partners and co-financing. Like many project’s worldwide, activities and components of the project have been heavily affected by the pandemic situation during the 2020 and into early 2021. During much of 2020, the MMDE was shut down and many of its activities running at 50% which meant that decisions, planning and administration activities were very delayed. Furthermore, since the PIR2020, for a considerable period visits to project locations and local communities, especially for people from the greater Colombo area were not allowed. On many occasions the communities in project sites did not welcome the project-related team and relevant authorities outside of their territories during the pandemic. While this impacted the rate of implementation of the baseline assessment due to specific locational spikes in COVID-19 outbreaks the project was able to adapt and work around that and has now completed that baseline action, by abiding with strict regulations imposed by the government. However, ongoing concerns and restrictions regarding COVID-19 continues to delay the implementation of related follow up activities in project sites including awareness-raising. Both UNEP and Bioversity International have been proactive in trying to find ways to work around the current challenges identified in order to adapt and enhance project implementation. In the short-term this involved the development of an LOA with SACEP to undertake the baseline assessment activities of Component 1. This action is now completed and worked well despite constraints related to COVID-19 in both target locations. In response to the more intractable management issues within MMDE both UNEP and Bioversity International have communicated officially with MMDE concerns regarding project implementation and options to improve national project management and implementation. After consultations between UNEP and Bioversity International in late February these concerns about delays in project implementation were conveyed to the national GEF OFP. Specifically, these concerns referred to the protracted delay in establishing a contract between Bioversity International and the Ministry of Mahaweli Development and Environment (MMDE), including the inability in setting up a national Project Management Unit (PMU). It was suggested to the GEF OFP that choosing an alternative Service Provider that meets all parties’ approvals could offer a potential solution, with the Service Provider implementing some of the activities on behalf of the Ministry. Suggested options for identifying a suitable alternative Service Provider included a local NGO, the Alliance for Sustainable Landscape Management (ASLM), with previous favourable GEF project experience in Sri Lanka, or the South Asia Co-operative Environment Programme (SACEP), which is mentioned in Project Document as a key partner of the MMDE in the implementation for the project, though SACEP has a regional scope rather than national. At the same time Bioversity International undertook a number of consultations with ASLM to determine whether they are available and willing to act as an alternative Service Provider – on the condition of continuing and strengthening government ties towards the implementation of the GEF project – which they confirmed. Subsequent to this, Bioversity International officially communicated with the Secretary (and GEF OFP) on this same matter of an alternative local Service Provider. To date, there has been no official response on this to either UNEP or Bioversity International. |  |  |  |  |  |

| Implementation Progress Rating | FY 2020 | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | MU |  |  |  |  |
| Although the first disbursement from UNEP was received on 3 September 2019, and the Project Inception meeting also took place in 2019, overall project implementation progress has been hindered initially by political challenges and personnel changes as a result of government elections towards the end of 2019 early 2020, only to be compounded by the impacts of the COVID-19 pandemic in the first-half of 2020. Although the political instability that followed the terrorist attacks in Easter 2019 created a more difficult working environment throughout the remainder of that year, the delays with establishing a LOA with the Ministry of Environment is very worrying. Only once the LOA is approved and signed will it be possible for the Ministry to establish a PMU and officially identify the national project manager and other support staff, as a result the project has been managed remotely from Rome, Italy and by the lead Project Coordinator from BI based in Australia. The core project team has developed a scope of work document to undertake the baseline assessments in the project sites and TORs for this and are working with SACEP and a number of universities and government agencies to implement this as soon as possible. Preparation and desk reviews have commenced, and we are hoping that project staff will be able to travel to the field and communities in early July/August. As part of this effort, the project will also be assessing the impact of the current COVID-19 pandemic in both project landscapes and how the project can help the government dealing with the impact to farmers’ economic and food security. The implementation of the baseline assessment has allowed some activities to commence, but further progress will depend solely on how quickly the Ministry LOA can be approved and acted upon. In case the LoA cannot be signed by end of 2020, alternative solutions for local project management and execution will have to be considered. Progress since the FY20 PIR has been largely limited to Component 1. The major action here being the successful completion of the project baseline assessment including extensive desk reviews and baseline assessments for land degradation, vegetation cover and biodiversity, as well as the food security and human health assessment. To this end, three teams were established to undertake the baseline assessments for: Land Degradation and Ecosystem Services; Biodiversity; and, Food Security and Human Health. The teams involved have made effective use of the core experts involved in the PPG phase of the project together with additional expertise from local universities and with the support of postgraduate and undergraduate students. Methodologies, tools and workplans were developed for the desk reviews and field data collection. Due to travel restrictions caused by the COVID-19 pandemic, field assessments to gather data had to be postponed until 2021. Even then, communities in project sites were reluctant to interact with strangers coming from other areas. Despite this, the baseline assessment teams were able to establish good relationships with the communities by maintaining rigorous COVID-19 guidelines during all visits and consultations. As of March 2021, desk reviews and field data collection have been completed with interim reports submitted. Data is currently being analysed and a final report prepared by mid-April 2021. The findings from the baseline assessments will be prepared in suitable formats for a planned workshop to present back the key findings to project site communities (also part of Component 2). The key findings will also be presented in a number of ways at the forthcoming Cascade Ecology and Management Symposium in September 2021, co-organized by the University of Peradeniya, MMDE and Bioversity International and will also inform both knowledge management outputs in Component 3. There are a significant number of activities and outputs across all 3 technical Components, as well as further knowledge management products and tools in Component 4, which are now ready for immediate action and implementation, now that the baseline assessments are completed. |  |  |  |  |  |

| Risk Rating | FY 2020__ | FY 20__ | FY 20__ | FY 20__ | FY 20__ |
| --- | --- | --- | --- | --- | --- |
|  | S |  |  |  |  |
| The delays in signing of the LoA and enabling its funds flow for planned work, delays in establishment and staffing of the PMU, delays in most if not all of the actual fieldwork, affects over half or more of the project targets, outputs and deliverables; and as such the project is now at Substantial Risk. |  |  |  |  |  |

| Stakeholder engagement | The project has adopted a multi-sectoral, multi-stakeholder and interdisciplinary approach and intends to complement this with a fully participatory and community-based approach to project implementation at site level. Over 60 participants representing many of the key stakeholder institutions identified in the Project Document attended the Project Inception Workshop in September 2019. The report from this meeting was prepared and distributed. The calling for new elections in Spring 2020 first and then the COVID-19 pandemic have delayed signing of the LOA agreement with the lead national executing agency and implementation of this and complementary activities to be carried out by project partners. To fast track activities, however, a comprehensive scoping document with TORs for baseline assessment was developed and signed with SACEP. The scoping document includes a workplan and timeline for site level consultations, awareness raising consultations at the community level in both project landscapes, including networking and partnership building among key partners and stakeholders to cover the interim period until the Ministry LOA is signed. Update April 2021: During much of 2020, the MMDE was shut down due to COVID19, and many of its activities running at 50% which meant that decisions, planning and administration activities were very delayed. Furthermore, since the PIR2020, for a considerable period visits to project locations and local communities, especially for people from the greater Colombo area were not allowed. On many occasions the communities in project sites did not welcome the project-related team and relevant authorities outside of their territories during the pandemic. While this impacted the rate of implementation of the baseline assessment due to locational spikes in COVID-19 outbreaks the project was able to adapt and work around that and has now completed that baseline action, by abiding with strict regulations imposed by the government. |
| --- | --- |

| Gender mainstreaming | Given the limited implementation to date there has been little opportunity to address this. The project does have Gender Mainstreaming objectives, activities and targets and a gender equality and women’s empowerment strategy as outlined in the Project Document. This will guide implementation at all stages. Gender related actions have been included in the above highlighted scoping document for the baseline assessments and the focus on COVID-19 impacts will have a gender element. Update 2021: The just completed project baseline assessment included a focus on both gender and COVID-19 impact. During the baseline gender-disaggregated dietary intake data using detailed 24-hour recall methods, food frequency questionnaires, dietary diversity assessments, and anthropometric measurements, as well as biomarkers (for micronutrient status) where undertaken to assess food security and nutrition status. The baseline also focused on assessment of gender-related human health issues and aimed to identify gender-related constraints and issues in project landscapes, with a view to developing and implementing future training and support programs tailored to women. The baseline assessment also employed qualitative approaches to specifically explore the perception of people, including women and youth, about COVID-19 and the economic impact, and impacts on resilience, food security and nutrition and human health as well as to explore and gain an understanding of the public response and coping strategies during the pandemic. The data from the baseline assessment are currently being analyzed and the findings will be communicated in the full baseline report due in mid-April 2021. These findings will not only influence the objectives, activities and targets of the gender mainstreaming strategy which is described in detail in the project document, they will also be reflected in subsequent training, awareness and support to women in cascade landscapes outlines in the project results framework. |
| --- | --- |

| Environmental and social safeguards management | Slow progress in getting the LOA with Sri Lanka’s lead national executing agency approved, has meant a delay in project implementation with regards to this and other complementary activities to be carried out in collaboration with national project partners. The safeguard concerns raised in the ESERN are still pertinent and will receive due attention. In relation to SS1, it is anticipated that the impact of COVID-19 and government recognition of the need for holistic and sustainable and integrated landscape approaches (as highlighted in the recent Presidential Task Force recovery document) as part of the recovery may well lend support to the project’s plan for a landscape/ecological planning approach. The precautionary/safety caution approach highlighted in the ESERN for SS2 and SS3 will continue to receive attention. Finally, in relation to SS9, a socio-economic analysis has been included in the baseline assessment currently underway to address comments and recommendations provided by the ESERN Safeguards Advisor. |
| --- | --- |

| Knowledge activities and products | Despite the challenges and delays there has been some preliminary discussions around the development of the project website and knowledge products it would host. There has also been discussion on most of the activities planned in Output 3.1 including the establishment of a cascade ecology ‘community of practice’ and a planned book and guidelines on cascade ecology. Update 2021: The successful completion of the baseline assessment will have multiple benefits for the project knowledge products and outputs. The baseline assessment – both desk review and field assessments - has resulted in the collection and analysis of a considerable amount of information from the project cascade landscapes and other similar initiatives in other tank landscapes. This now presents a great opportunity for the project to use this information and push ahead with a range of the knowledge products and tools identified in the project document, but especially in Components 3 and 4. The project is at the early stage of co-organizing a Cascade Ecology and Management Symposium scheduled to take place in September 2021 where many of the findings from the project baseline will be presented. This information and knowledge will also be organized for the planned project website and key communication tools. It is anticipated that the aforementioned mentioned symposium, and the now substantial amount of information collected from cascade landscapes will stimulate and inform multiple other activities in Component 3, including establishing a cascade ecology community of practice, a state of knowledge book on cascade ecology, a database and web-based knowledge portal, awareness-raising and curricula materials on cascade ecology for schools and universities. Similarly, this will inform the publication of good practices, training manuals, technical bulletins and policy briefs, as identified in Component 4, to better inform the ongoing implementation of cascade landscape restoration and management about the importance of taking into consideration cascade ecology. |
| --- | --- |

| Stories to be shared | Limited for the current reporting period. However, the baseline assessments will consider the impact of COVID-19 on food security, livelihoods and wellbeing in project sites as well as coping strategies and ways the project can support recovery. Over the coming months the project should have a comprehensive assessment of the COVID impacts in project sites, as well as plans for the project to support the recovery including supporting decision-making, food security and livelihoods. Opportunities to share these stories will be found. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Observations/ justification on rating | Progress rating |
| --- | --- | --- | --- | --- | --- | --- |
| Objective Mainstreaming biodiversity using an integrated sustainable land management approach to ensure, development, health and environmental co-benefits |  |  |  |  |  |  |
| Component 1. Implementation of biodiversity-based options that improve sustainable land management in socio-ecological sensitive areas |  |  |  |  |  |  |
| Outcome 1: Sustainable landscape management approaches in support of improved ecosystem services and ecohealth outcomes adopted in prominent socio-ecological sensitive areas of Village Tank Cascade Systems (VTCS) | 1. # of hectares of agricultural lands under sustainable land management and % increase in crop diversity as measured by richness and evenness | SLM measures currently implemented on a less than 10% of agricultural lands Low levels of crop diversity in both landscapes | SLM measures adopted on 5,000 ha, and demonstrating an increase in crop diversity | SLM measures adopted on 10,000 ha | The terrorist attacks in Colombo in April 2019, plus COVID in 2020, caused a significant disruption to the planning of all activities and have set back the beginning of operations and the start of the field activities. A desk review exercise has started in June 2020 to begin documenting baseline information for this outcome, which will be followed up with baseline assessments at the project site level. | MU |
|  |  |  | 25% increase in crop diversity | 50% increase in crop diversity |  |  |
|  | 2. # farming households in 5 villages adopting gender-sensitive agroecological approaches | Few farming households in 5 villages adopting gender-sensitive agroecological approaches | At least 25 farming households in 5 villages adopting gender-sensitive agroecological approaches | At least 30 farming households in 5 villages adopting gender-sensitive agroecological approaches |  | MU |
|  | 3. Sustainable ecohealth village models established in project landscapes | No sustainable ecohealth village models exist in project landscapes | At least 2 sustainable ecohealth village models established in project landscapes | At least 5 sustainable ecohealth village models established in project landscapes |  | MU |
|  | 4. Gender-sensitive markets identified and developed for goods and services of VTCS in project landscapes | No such markets yet identified in project landscapes | Markets identified for at least 2 VTCS goods or products | Markets developed for at least 2 VTCS goods or products |  | MU |
| Component 2. Strengthened institutions, policies and integrated landscape planning of village tank cascade systems (VTCS) in socio-ecological sensitive areas. |  |  |  |  |  |  |
| Outcome 2: Improved enabling environment for sustainable integrated landscape planning, management and monitoring of ecohealth outcomes | 1. # of Multi-sectoral planning platforms in project landscapes | No multi-sectoral planning platforms exist in project landscapes | At least 1 multi-sectoral planning platform established in a project landscape | At least 2 multi-sectoral planning platforms established in and operational in project landscapes | Although most activities in Outcome 2 are scheduled for Year 2, the political situation since the Project inception Workshop and the COVID-19 pandemic have limited progress. There has been some progress on identification of key experts/trainers for awareness raising | MU given no progress – yet most under Comp 2 not yet due |
|  | 2. # comprehensive integrated landscape management plans and frameworks developed and implemented | No comprehensive integrated landscape management plans developed and implemented in project landscapes | Comprehensive integrated landscape management planning frameworks for 2 VTCSs drafted | Comprehensive integrated landscape management planning frameworks in 2 VTCSs developed and implemented covering approximately 20,000 ha |  | MU |
|  | 3. Guidelines and policy recommendations that support sustainable integrated landscape planning and implementation developed | No such guidelines have been developed for project landscapes | Guidelines and policy recommendations that support sustainable integrated landscape planning and implementation drafted | Guidelines and policy recommendations that support sustainable integrated landscape planning and implementation published and disseminated |  | MU |
| Component 3. Partnerships, awareness raising and capacity building for better sustainable integrated landscape management in support of improved ecosystem services and ecohealth outcomes. |  |  |  |  |  |  |
| Outcome 3: Improved enabling environment for sustainable integrated landscape planning, management and monitoring of ecohealth outcomes | 1. Enhanced capacity of extension, research and university staff, policy makers and other stakeholders | Limited target beneficiaries or stakeholders trained in cascade ecology and ecohealth approaches | At least 500 beneficiaries and stakeholders, at least 50% women, made aware and trained by the project | At least 1000 beneficiaries and stakeholders, at least 50% women, made aware and trained by the project | As for the previous Outcome, most activities in Outcome 3 are scheduled for Year 2. Some progress has been made in identifying practitioners and researchers to comprise a cascade ecology ‘community of practice’ as well as strategies to promote the concept of cascade ecology. Activities/Outputs in this component, which can be started remotely, have been identified and prioritized. | MU |
|  | 2. Integration of cascade ecology and ecohealth approaches into targeted education courses including universities and schools | No integration of cascade ecology and ecohealth approaches into targeted education courses including universities and schools at project outset | Curricula and short courses in cascade ecology and ecohealth approaches developed | Cascade ecology and ecohealth approaches integrated into university and school courses |  | MU |
|  | 3. Sri Lanka cascade research and development network established | No such network in place | Concept for Sri Lanka cascade research and development network developed and approved | Sri Lanka cascade research and development network established and functional |  | MS |
| Component 4. Knowledge, information management and monitoring and evaluation |  |  |  |  |  |  |
| Outcome 4: Improved enabling environment for sustainable integrated landscape planning, management and monitoring of ecohealth outcomes | 1. M&E system ensuring timely delivery of project outcomes and targets | No M&E system is in place | M&E system in place and operational | M&E providing systematic information on project progress | Preliminary discussions for the development of a project website and initial knowledge products have taken place. These will be developed in the second half of 2020. | U – more could be done by remote team |
|  | 2. Enhanced access to project knowledge products on cascade ecology and ecohealth approaches | Poor access to knowledge products at project outset | Project website and knowledge hub established | Knowledge products and lessons learned shared with a variety of audiences and stakeholders |  | MU |

Overall rating of project progress towards meeting project Result(s)

| FY2019 rating [previous] | FY2020 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| N/A | MU | The second half of 2019 in Sri Lanka proved to be a challenging time following the terrorist attacks in Colombo in April 2019. This caused a significant disruption to the planning of all activities especially the establishment of the contract with the lead NEA, as well as timing of the official Project Inception Workshop. Most government offices and universities closed temporarily and, for a couple of months following the attacks, travel within the country was not allowed or limited. Despite this, the Project Inception Workshop was able to go ahead in September 2019. Shortly after, national elections were called in November 2019, which further impacted the project. As with previous elections, government personnel were required to undertake election related duties around that time and when the outcomes of the election were announced there were political changes of minister, secretary and other staff within the Ministry of Environment. This, combined with the political changes the country has gone through over the preceding 3-4 years, has made it complicated to begin project implementation. New political appointments and other new staff resulted in a considerable period of inertia shortly thereafter which dragged on until early 2020. Further, a new general election is scheduled to take place in August 2020. A LOA with the Ministry of Environment was developed in 2019, but it is still pending approval and signature from the Ministry’s side. Only once the LOA is approved and signed will it be possible for the Ministry to establish a Project Management Unit (PMU) and officially identify the national project manager and other support staff and disburse funds. The EA Project Manager visited Sri Lanka in January 2020 meeting with the core project team in Peradeniya to discuss the political situation since the Project Inception Workshop and to try to find a solution to move the project forward while things settle down in the Ministry. This resulted in a strategy to at least commence certain priority actions while awaiting approval of the government LOA. A follow up trip by the EA Project Manager was scheduled for March 2020, however, by that stage, indications of the pending COVID-19 pandemic had arisen and the trip was cancelled. Furthermore, Parliament was dissolved in March when new elections were scheduled for the end of April 2020. The COVID-19 pandemic started up in Sri Lanka at the same time, which resulted in the closure of all ministry offices as well as other organizations, and all staff working remotely, with travel to rural areas restricted or forbidden. This has been the situation for the remainder of the first half of 2020. It is only now, in July 2020, that all offices are reopening and staff slowly returning to offices. Despite the ongoing political challenges and those posed by the COVID-19 pandemic, a comprehensive scoping document, ToRs, workplan and timeline were developed to jumpstart the baseline assessment in the project landscapes using most of the core team who were involved in the PPG. This work also includes project site level consultations, awareness raising consultations at the community level in both project landscapes, including networking and partnership building among key partners and stakeholders. It is anticipated that this will establish a good platform for project implementation upon approval of the Ministry LOA. It is anticipated that this will also highlight how the project can contribute to the post-COVID-19 pandemic recovery. Relevant project communication materials are being developed including the project flyer, development of a logo/branding and hopefully the first strides towards a project website. However, activities and overall project implementation are expected to continue to be delayed due to the impact of COVID-19. Finally, in addition to assessing the COVID-19 impact in the project landscapes as above, some of the core project team are collaborating with a range of international organizations e.g. WFP, Johns Hopkins University, to undertake additional assessments and are ensuring the project sites are included in these. Further, the project team are already involved in discussions at a ministerial level to see how the project might support the recovery process, as outlined below. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  Projects are free to put N/A to sections or add additional rows for other problems/risks such as those identified at CEO Endorsement.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | Agreed recommended actions |
| --- | --- | --- |
| on achieving Mid-Term and End of Project Targets as identified above | Political challenges since 2019 and the COVID-19 pandemic have seriously impacted the project’s planned timeline for the achievement of targets. | To expedite the approval of the current LOA and disburse funds so that the project is ready as soon as field visits and gatherings are permitted again; identify priority activities/outputs that can go ahead even remotely/virtually; complete the baseline assessment and identify what early action can be started soonest, as well as where best the project can support the post-COVID recovery. |
| on delivering GEF Core Indicators | Delayed for same reasons as stated above (see Annex for targeted GEF CORE Indicators). The underway baseline assessment will map and document the current level of improved practices in project sites and will help identify appropriate sustainable land management practices in cascade production areas | Expedite the current LOA and disbursement of funds and mobilise project team. |
| on stakeholder engagement | The closure of offices and restrictions on people movement as a result of the COVID-19 pandemic have made it difficult, if not impossible, to mobilize key stakeholders, institutions, partners. It has also made it difficult to engage with site level actors/stakeholders | Raise the profile of the project by firstly finalizing the project website and knowledge products therein (e.g. video, flyer etc.); strengthen internal communication to include a wider group of national partners/stakeholders; strengthen external communication to highlight the vision and aims of the project which are in line with the national recovery effort; emphasise the importance of the project’s Ecohealth aspects in this as well; strengthen virtual team meetings including introduction of more e-platforms and e-training, so they can be held more frequently, and so that the team can revert back to these if there are secondary waves of the virus. |
| on gender actions | N/A at this stage |  |
| on safeguards | N/A at this stage |  |
| on sustainability of results | N/A at this stage |  |
| others | N/A at this stage |  |

3.2 Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implementation status as of 30 June 2019 | Implementation status as of 30 June 2020) | Progress rating justification | Progress rating |
| --- | --- | --- | --- | --- | --- |
| Component 1. Implementation of biodiversity-based options that improve sustainable land management in socio-ecological sensitive areas |  |  |  |  |  |
| Output 1.1. Socio-ecological and biophysical system properties mapped and defined in two Project landscapes |  |  |  |  | MU – mainly delayed due to COVID |
| Activity 1.1.1 Undertake comprehensive baseline assessments (including gender, human health) in 2 project landscapes | Nov 2020 | 0% | 20% | In collaboration with the core project team, a scope of work document and TORs were developed to undertake the baseline assessments in the project sites. The assessment has begun with desk reviews, hoping that the teams will be able to travel to the field and communities in July/early August. As part of the survey the impact of the current COVID-19 crisis will be evaluated in both landscapes. Members of the core team are also involved in international collaborations related to this (WFP, JHU) which will also shed light on impact at project sites. | MS |
| Activity 1.1.2 Design and execute systems mapping ‘expert’ workshops | Nov 2020 | 0% | 20% | During the PPG and up until the present, discussions and planning to undertake a series of mapping workshops in project sites took place in collaboration with the University of Leuphana Germany (an EU funded project that would be co-financing) and with colleagues within Bioversity using the Indicators of Resilience in Socioecological Production Landscapes and Seascapes (SEPLS toolkit). The original plan was to carry out these workshops in the second half of 2020, which is now impacted by the pandemic. The design phase of this activity was completed and the methods and tools prepared. The execution will depend on when travel is again permissible and various stakeholders can be brought together. | MS |
| Activity 1.1.3 Undertake participatory systems mapping and planning exercises (in cascade and inter-cascade level) to determine factors and processes that interact with each other to influence food security, human wellbeing and ecosystem health (via ecosystem service identification) | June 2021 | 0% | 0% | This activity is linked to 1.1.2, therefore the above explanation/justification applies here. This activity also depends on signing of the LOA with the Ministry of Environment | Not yet due |
| Activity 1.1.4 Analysis of data and modelling of conservation and development scenarios and establish cascade model village development guidelines | June 2022 | 0% | 0% | Activities not scheduled until later | Not yet due |
| Activity 1.1.5 Produce reports, peer-reviewed papers and other knowledge products | June 2022 | 0% | 0% | Activities not scheduled until later | Not yet due (nyd) |
| Output 1.2. Community familiarization on VTCS restoration and agroecological and sustainable land management strategies and practices |  |  |  |  | MU |
| Activity 1.2.1 Production of community-level awareness raising and training materials on VTCS values and importance, and agroecology and sustainable land management practices | Dec 2020 | 0% | 20% | Collection of materials for awareness raising and training has commenced. Final preparation of and production materials depends on activities related to the signing of the Ministry LOA. | MU |
| Activity 1.2.2 Community-level awareness raising workshops/programmes held in project areas on the importance of the values, goods and services of cascade tank ecosystems and their conservation | June 2021 | 0% | 0% | Activity will be delayed and will depend on when travel to communities and large gatherings are permitted. Also depends on activities related to the signing of the Ministry LOA. There will be community level workshops held as part of Activity 1.1.1 above to present back to the community the findings of the baseline assessment. | MU, nyd |
| Activity 1.2.3 Support community-level training on VTCS restoration processes, planning and management | June 2021 | 0% | 0% | Activity will be delayed and will depend on when travel to communities and large gatherings are permitted. | MU |
| Activity 1.2.4 Support community-level training on agroecology and sustainable land management practices | June 2021 | 0% | 0% | Activity will be delayed and will depend on when travel to communities and large gatherings are permitted. | MU |
| Output 1.3. Physical and ecological components of selected VTCSs restored as pilot models |  |  |  |  | MU |
| Activity 1.3.1. Participatory planning of rehabilitation and restoration of VTCSs | Dec 2020 | 0% | 0% | Activity will be delayed, and will depend on when travel to communities and large gatherings are permitted, and approval of Ministry LOA and subsequent disbursement of funds | MU |
| Activity 1.3.2 Repair and renovation of tank headworks and partial de-silting of tanks | Dec 2020 | 0% | 0% | Activity will be delayed, and will depend on when travel to communities and large gatherings are permitted, and approval of Ministry LOA and subsequent disbursement of funds | MU |
| Activity 1.3.3 Development of downstream water management system | June 2021 | 0% | 0% | Activity not scheduled until year 2 but will likely be delayed, and will depend on when travel to communities and large gatherings are once again permitted, and approval of Ministry LOA and subsequent disbursement of funds | nyd |
| Activity 1.3.4 Promote conservation practices in immediate upstream landscapes | June 2022 | 0% | 0% | Activity not scheduled until years 1 and 2 | nyd |
| Activity 1.3.5 Collection of tree and other planting materials and establishment of community nurseries | June 2021 | 0% | 0% | Activity not scheduled until year 2 but will likely be delayed, and will depend on when travel to communities and large gatherings are once again permitted, and approval of Ministry LOA and subsequent disbursement of funds | nyd |
| Activity 1.3.6 Restoration of godawala, kiul-ela, iswetiya and yathuru wala and establishment of medicinal and underutilized plants | June 2021 | 0% | 0% | Activity not scheduled until year 2 but will likely be delayed | nyd |
| Activity 1.3.7 Tree planting programme in kattakaduwa, kiul-ela, godawala, gasgommana, homegardens and herbal gardens through shramadana campaigns | June 2021 | 0% | 0% | Activity not scheduled until year 2 but will likely be delayed | nyd |
| Activity 1.3.8 Assess cost-benefit of VTCS restoration | June 2022 | 0% | 0% | Activity not scheduled until year 3 | nyd |
| Output 1.4. Biodiversity-based agroecological and sustainable integrated land management practices promoted in the two selected VTCS pilot schemes |  |  |  |  | NYD |
| Activity 1.4.1 Support the implementation of sustainable land management practices that reduce human-animal conflict | June 2022 | 0% | 0% | Activity not scheduled until years 2 and 3 | nyd |
| Activity 1.4.2 Identify a package of agroecology and SLM practices for agriculture in project landscapes | June 2022 | 0% | 10% | The identification of current agroecological and SLM practices in project landscapes is part of the baseline assessments underway in Output 1.1 | MU |
| Activity 1.4.3 Integrate agrobiodiversity, including medicinal and underutilized species and practices, for improved nutrition, human health and livelihoods in cascade landscapes and food production systems | June 2022 | 0% | 0% | Activity not scheduled until years 2 and 3 | nyd |
| Output 1.5. Goods, services and functions of VTCS ecosystems identified and mainstreamed |  |  |  |  | MS |
| Activity 1.5.1 Identify, group and prioritize key goods, services and functions from VTCS | Dec 2020 | 0% | 20% | Currently being undertaken as part of the baseline assessment in Output 1.1 | MS |
| Activity 1.5.2 Establish gender-sensitive value chains for prioritized cottage-based industries and handicrafts based on VTCS products | June 2022 | 0% | 0% | Activity not scheduled until years 2 and 3 | nyd |
| Activity 1.5.3 Establish value chains for prioritized agricultural, food and medicinal products from VTCS | June 2022 | 0% | 0% | Activity not scheduled until years 2 and 3 | nyd |
| Activity 1.5.4 Identify options for certification and labelling for key goods and services arising from VTCS | June 2022 | 0% | 0% | Activity not scheduled until years 2 and 3 | nyd |
| Activity 1.5.5 Promote ecotourism linked to conservation and sustainable use in VTCS including cultural values e.g. traditional performing arts, local food cultures, traditional crafts and knowledge | June 2022 | 0% | 0% | Activity not scheduled until years 2 and 3 | nyd |
| Activity 1.5.6 Establish market centres for local products | June 2022 | 0% | 0% | Activity not scheduled until year 3 | nyd |
| Component 2. Strengthened institutions, policies and integrated landscape planning of village tank cascade systems (VTCS) in socio-ecological sensitive areas |  |  |  |  |  |
| Output 2.1. Awareness raising and capacity building of key partner institutions, local organizations and communities in participatory integrated landscape management planning of VTCS for improved eco-health outcomes |  |  |  |  | MS |
| Activity 2.1.1 Identify key experts and trainers and awareness raising and training materials | Dec 2020 | 0% | 10% | Preliminary steps were taken to identify trainers/experts as well as awareness raising training materials | MS |
| Activity 2.1.2 Create awareness among key stakeholders, institutions, local organizations and communities of the rationale for participatory integrated landscapes management of VTCS, and the multiple benefits in project areas | June 2021 | 0% | 0% | Activity planned for Year 2 | nyd |
| Activity 2.1.3 Training of key strategic stakeholders (including community-level champions, women and youth) in integrated landscape management | June 2021 | 0% | 0% | Activity planned for Year 2 | nyd |
| Output 2.2. Relevant national policies and legislation for enabling environment for the sustainable integrated landscape management reviewed and revisions recommended to Government |  |  |  |  | No rating |
| Activity 2.2.1 Review existing policies, legislation and institutional frameworks pertaining to integrated landscape management in cascade landscapes | June 2021 | 0% | 0% | Activity scheduled for Year 2 | nyd |
| Activity 2.2.2 Review findings and outputs from previous and ongoing projects and initiatives operating in VTCS aiming to improve sustainable integrated landscape management | June 2021 | 0% | 0% | Activity scheduled for Year 2 | nyd |
| Activity 2.2.3 Adopt or adapt relevant outputs and knowledge products for use in project areas | June 2021 | 0% | 0% | Activity scheduled for Year 2 | nyd |
| Activity 2.2.4 Recommend revision/review of key policy instruments and legislative framework | June 2022 | 0% | 0% | Activity scheduled for Year 3 | nyd |
| Output 2.3. Participatory sustainable integrated landscape management planning and coordination platforms developed at district and local level |  |  |  |  | MU |
| Activity 2.3.1 Identification and engagement of key actors and stakeholders to develop cascade system level platforms | Dec 2020 | 0% | 20% | Throughout the PPG and early stages of the MSP, the project has been keeping track of key stakeholders to engage with in developing these platforms. What is needed now, and has been delayed, is the identification and engagement of key stakeholders at local level. | MU |
| Activity 2.3.2 Establish a shared understanding of VTCS landscape management conditions, challenges and opportunities in project areas | Dec 2020 | 0% | 10% | Activity has commenced, with collection of some information and data | MU – little progress |
| Activity 2.3.3 Undertake collaborative planning to develop an agreed action plan for implementation of integrated landscape management in project areas including agreed stakeholder interventions | June 2021 | 0% | 10% | One aspect of the current baseline assessment is to consult with project site communities to present the findings from the baseline assessments and to begin to develop collaborative planning for project implementation | MU |
| Activity 2.3.4 Implement agreed action plan with attention to maintaining collaborative commitments | June 2022 | 0% | 0% | Activity scheduled for Year 2 and 3 | nyd |
| Activity 2.3.5 Platform undertakes monitoring of action plan implementation for adaptive management and effective inter institutional coordination and accountability | June 2022 | 0% | 0% | Activity scheduled for Year 2 and 3 | nyd |
| Output 2.4. Participatory sustainable integrated landscape planning/management guidelines developed for VTCS in socio-ecological sensitive areas |  |  |  |  | MU |
| Activity 2.4.1 Review previous efforts to promote and develop integrated landscape management planning guidelines | Dec 2020 | 0% | 20% | Considerable information and data have been collected regarding integrated land management in VTCS in socio-ecological sensitive areas to date. However, this still needs review and analysis. | MS |
| Activity 2.4.2 Draft comprehensive integrated landscape management planning guidelines based on project outputs and experiences for consideration of landscape planning platform and communities in project areas | June 2021 | 0% | 0% | Activity scheduled for Year 2 | MU (assume work should start in 2020) |
| Activity 2.4.3 Consultation and presentation of integrated landscape management planning guidelines to relevant actors, stakeholders and communities beyond project areas | June 2022 | 0% | 0% | Activity scheduled for Year 2 and 3 | nyd |
| Activity 2.4.4 Revise and prepare guidelines for integrated landscape management | June 2022 | 0% | 0% | Activity scheduled for Year 3 | nyd |
| Activity 2.4.5 Publish and disseminate final integrated landscape planning/management guidelines | June 2022 | 0% | 0% | Activity scheduled for Year 3 | nyd |
| Component 3. Partnerships, awareness raising and capacity building for better sustainable integrated landscape management in support of improved ecosystem services and ecohealth outcomes |  |  |  |  |  |
| Output 3.1 Concept of Cascade Ecology established through workshops, symposia and other knowledge products |  |  |  |  | MU |
| Activity 3.1.1 Establish a cascade ecology ‘community of practice’(CoP) | June 2022 | 0% | 10% | Some efforts have commenced to identify who might make up such a CoP, its structure, role and functions. | MU |
| Activity 3.1.2 Promote concept of cascade ecology among national and international partners (including national cascade ecology symposium) | June 2022 | 0% | 10% | Ongoing but requires more attention and focus | MU |
| Activity 3.1.3 Publish state of knowledge book on cascade ecology and other knowledge products | June 2022 | 0% | 10% | There has been some discussion regarding structure and contributors. A book outline and proposal will be available by end of 2020. | nyd |
| Activity 3.1.4 Develop cascade ecology database and web-based knowledge portal and resources | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Output 3.2. Knowledge mainstreamed to national extension, research institutions, including universities, and policy makers and other stakeholders on cascade ecology and landscape management, ecosystem services and ecohealth approaches |  |  |  |  | No rating |
| Activity 3.2.1 Consultative workshops held with universities and awareness programmes for schools on cascade ecology and ecohealth approaches | June 2021 | 0% | 0% | Activity scheduled for Year 2 | nyd |
| Activity 3.2.2 Development of relevant curricula materials for universities, schools and for informal sector on cascade ecology and ecohealth approaches | June 2022 | 0% | 0% | Activity scheduled for Year 3 | nyd |
| Activity 3.2.3 Support the implementation of short courses on cascade ecology and ecohealth approaches in universities | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Activity 3.2.4 Familiarization workshops for policy makers, national extension and research staff and other stakeholders on cascade ecology and ecohealth approaches | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Component 4. Knowledge, information management and monitoring and evaluation |  |  |  |  |  |
| Output 4.1 Gender sensitive project monitoring system operating and providing systematic information on progress in reaching expected outcomes and targets |  |  |  |  | MS |
| Activity 4.1.1 Finalize and disseminate project gender-sensitive Monitoring and Evaluation system | Dec 2020 | 0% | 20% | Will be completed in second half of 2020 | MU (key activity for completion) |
| Activity 4.1.2 Establish reporting plan and requirements | June 2020 | 100% | 100% | Ongoing | S |
| Activity 4.1.3 Submit project and financial reports to UNEP | 2019-2022 | 100% | 100% | Ongoing | S |
| Activity 4.1.4 Provide input to the project Mid-Term Evaluation | Sept 2021 | N/A | N/A | Activity scheduled for Year 2 | nyd |
| Activity 4.1.5 Provide input to the project Final Evaluation | Feb/Mar 2023 | N/A | N/A | Activity scheduled for Year 3 | nyd |
| Output 4.2 Project-related best practices, knowledge products and lessons learned systematized and published for a variety of audiences and stakeholder groups |  |  |  |  | MU |
| Activity 4.2.1 Collect, review, interpret, verify and establish knowledge systems | June 2021 | 0% | 20% | Ongoing, considerable information regarding VTCS knowledge systems was collected during the PPG and throughout the development of the MSP. This is continuing during the current baseline assessments. This will be consolidated, analysed and synthesized and completed in Year 2 | MU (not much progress) |
| Activity 4.2.2 Publish good practices for cascade landscape restoration and management, sustainable land management practices | June 2022 | 0% | 0% | Activity scheduled for Year 3 | nyd |
| Activity 4.2.3 Develop training manuals that support the design and implementation of cascade landscape restoration and management and sustainable land management practices | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Activity 4.2.4 Publish technical bulletins for specific elements of cascade landscape restoration and sustainable land management | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Activity 4.2.5 Develop policy briefs to promote and support cascade landscape restoration and management | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Activity 4.2.6 Project website updated to disseminate project findings and facilitate replication | June 2022 | 0% | 10% | A structure and plan for project website has been discussed | MS |
| Activity 4.2.7 Develop and implement a national public education and awareness programme | June 2022 | 0% | 0% | Activity scheduled for Years 2 and 3 | nyd |
| Component 5. Project management |  |  |  |  | MU |
| Output 5.1 Establish arrangements for overall project administration and implementation infrastructure including coordination units | June 2020 | 0% | 50% | The necessary arrangements for project administration and implementation have been developed, however the current delay in the approval of the Ministry LOA mean they have not been able to establish their project management unit nor identify national project coordinator | U |
| Output 5.2 Plan and undertake a full project inception meeting | Sept 2019 | 0% | 100% | Project Inception meeting was held in September 2019 | S |
| Output 5.3 Establish and operate project budgeting and accounting system | June 2020 | 100% | 75% |  | MS (yet to be done for PMU) |
| Output 5.4 Review and refine work plans with project coordinator and partners based on better understanding of local context | 2019--2022 | 0% | 0% | Ongoing. It is anticipated this activity will take place starting in second half of 2020 once the full report of the baseline assessment is available and the full impact of the COVID pandemic in project sites is fully understand, and how the project can best support recovery. The project will refine budgets and workplans including targeted co-finance contributions | MU |
| Output 5.5 Establish Project Steering Committees and conduct regular meetings | 2020-2022 | 0% | 10% | Ongoing. Activity waiting approval of Ministry LOA and follow up action to identify national project coordinator and establish project management unit. Once achieved the project can consider the establishment of the PSC and PSC meetings. The guidelines for the PSC and participation have been developed | U – project could have established the SC membership already based on the approved ProDoc, which indicated the lead NEA. |
| Output 5.6 Where relevant, establish additional site or technical committees | 2020-2022 | 0% | 0% | Ongoing. Activity has been delayed | MU |
| Output 5.7 Establish International Technical Advisory Committee to provide backstopping and guidance to technical components | 2020-2022 | 0% | 0% | Ongoing. It is anticipated that any TAC will comprise participants from collaborating international universities and agencies. Still to be determined | MU |

Overall project implementation progress

| FY2019 rating [previous] | FY2020 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| N/A | MU | Although the first disbursement from UNEP was received on 3 September 2019, and the Project Inception meeting also took place in 2019, overall project implementation progress has been hindered initially by political challenges and personnel changes as a result of government elections towards the end of 2019 early 2020, only to be compounded by the impacts of the COVID-19 pandemic in the first-half of 2020. Although the political instability that followed the terrorist attacks in Easter 2019 created a more difficult working environment throughout the remainder of that year, the delays with establishing a LOA with the Ministry of Environment is very worrying. Only once the LOA is approved and signed will it be possible for the Ministry to establish a PMU and officially identify the national project manager and other support staff, as a result the project has been managed remotely from Rome, Italy and by the lead Project Coordinator from BI based in Australia. The core project team has developed a scope of work document to undertake the baseline assessments in the project sites and TORs for this and are working with SACEP and a number of universities and government agencies to implement this as soon as possible. Preparation and desk reviews have commenced, and we are hoping that project staff will be able to travel to the field and communities in early July/August. As part of this effort, the project will also be assessing the impact of the current COVID-19 pandemic in both project landscapes and how the project can help the government dealing with the impact to farmers’ economic and food security. The implementation of the baseline assessment has allowed some activities to commence, but further progress will depend solely on how quickly the Ministry LOA can be approved and acted upon. In case the LoA cannot be signed by end of 2020, alternative solutions for local project management and execution will have to be considered. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks, if any (e.g. procurement delays, reputational risks etc). The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk.  This section should inform the risk rating in section 3.3.

| Problems/risks identified | Agreed recommended actions | By whom | When |
| --- | --- | --- | --- |
| Ongoing delays arising as a result of political elections and subsequent changes in senior positions (e.g. Minister, Secretary) within Ministries is presenting implementation challenges and delays to the project. This challenge was hindering project progress even before the outbreak of COVID-19 (below). | It may be necessary for Bioversity and/or UNEP to follow up with relevant focal points at a ministerial level to flag the impact that recent political changes have had on the project e.g. approval of LOA, and which risk continuing (there is a new general election scheduled for August 2020 and already all government agencies are busy for general election with postal voting scheduled during 14-17 July 2020) | Bioversity and/or UNEP | August 2020 |
| Delay in the approval of the current LOA with the Ministry of Environment is significantly impacting on the identification of national coordinator, support staff, the establishment of project management unit, and establishment of project steering committee and meetings. | It may be necessary for Bioversity and/or UNEP to follow up with relevant focal points in the Ministry to speed up the approval and signing of the LOA, in the context that the project can support recovery efforts to address food security, livelihoods and general wellbeing. If the LOA cannot be signed by end of 2020, alternative mechanisms for project implementation and local management support will have to be considered. | Bioversity | August 2020 Dec 2020 |
| COVID-19 pandemic has significantly impacted the project implementation through office closures and restrictions placed upon movements and gatherings of people and has exacerbated both above problems | The project needs to quickly build on the opportunity that the COVID-19 pandemic presents. The project is promoting an ecohealth and landscape approach which is very much in tune with current thinking in terms of ‘building back better’. There are considerable opportunities here. As a priority, the LOA must be signed, and funds disbursed immediately. The core project team must identify priority activities including those that can be continued virtually (in the event of secondary outbreaks/spikes e.g. when airport reopens in August). Furthermore, there are key areas of the Presidential Task Force’s Economic Recovery Plan which the project can help support. These areas need to be identified and supported. | Bioversity, PMU, core project team and National Partners | Beginning August 2020 |

3.3. Risk Rating

| Risk | Mitigation at CEO approval | Mitigation during implementation | Rank |
| --- | --- | --- | --- |
| Ongoing delays arising as a result of political elections and subsequent changes in senior positions (e.g. Minister, Secretary) within Ministries is presenting implementation challenges and delays to the project. | N/A | See ‘agreed recommended actions’ in matrix immediately above | CEO: N/A |
|  |  |  | TM:S |
|  |  |  | PM:M |
| Delay in the approval of the current LOA with the Ministry of Environment is significantly impacting on the identification of national coordinator, support staff, the establishment of project management unit, and establishment of project steering committee and meetings | N/A | See ‘agreed recommended actions’ in matrix immediately above | CEO: N/A |
|  |  |  | TM: S |
|  |  |  | PM: M |
| COVID-19 has significantly impacted project implementation through office closures and restrictions placed upon movements and gatherings of people. This has exacerbated both above problems. | N/A | See ‘agreed recommended actions’ in matrix immediately above | CEO: N/A |
|  |  |  | TM: S |
|  |  |  | PM: M |
| Political changes or changes in government administration in Sri Lanka may affect support for the project and reduce political will, commitment and leadership. Agencies with different mandates and focus areas will find it difficult to adopt a landscape planning approach and the project activities may not have the expected synergy | Project partners will use their reputation and good standing with the government to ensure that the interests of the project are supported to the extent that key objectives can be achieved. Under the Ministry of Mahaweli Development and Environment’s auspices, the project will maintain close coordination and communication with all partners and monitor national issues of this nature. All project partners have a credible history working with government institutions and occasional changes in pivotal and influential political staff which increases the likelihood that solutions can be found should an issue arise. The project team and participating organizations will ensure constant communication and engagement with all levels of government about shared project objectives, collaborative activities, and broader benefits for the country. | The project core team must continue to maintain good regular communication with all relevant government agencies and participating organizations. This could be supported through a brief communications strategy linked with the project website and knowledge products | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| Ecological approaches to linking environmental health and human health are relatively new in Sri Lanka and relevant government sectors, agencies and other institutions with different mandates and focus areas may find it difficult to adopt a landscape or ecological planning approach. This may limit commitment to cross-sectoral and integrated approaches thereby reducing opportunities and synergies from project activities | The project has already started to map and assess national capacities of the different stakeholders and actors involved in the project in relation to expertise and knowledge of ecohealth and disciplines of relevance. The project will ensure that this capacity and expertise is joined up, coordinated, communicated and mobilized during project implementation. The project has also identified international partners active in the field of planetary health, ecohealth, socio-ecological assessment and sustainable land management and this will also be linked to the project through a number of proposed mechanisms. Together, partners will identify capacity and knowledge gaps/needs as an element of select planned outputs (e.g. outputs 1.2, 2.1 and 3.2) and will accordingly develop a capacity building plan, which will seek to promote and target the institutionalization of cascade landscape approaches and knowledge through local-national institutions. | The outbreak and multidimensional impacts of COVID-19 has, more than ever, brought to the attention of many researchers and decision-makers the importance of One Health and EcoHealth approaches and enhanced need for integrated landscape approaches for human health and environmental health and the prevention of future zoonotic outbreaks. If anything, this presents a unique opportunity for the project to highlight these critical links and the project should explore ways to build on this through better communication, collaborations and awareness-raising and education. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| The project is not able to tackle the complexity of institutional arrangements and policy mechanisms relating to water and land management in the proposed project landscapes and which may limit intended project synergies and long-term impacts | The core team involved in the development of the project during the PPG brought very considerable experience and knowledge of the challenges presented in the project landscapes relating to integrated sustainable land management, appropriate governance and institutional mechanisms and the need for better coherence within a range of policies. The team were also very much aware of the work of past projects and initiatives in dealing with these issues – especially ineffective governance and institutional arrangements, and lack of coherent policies. As a result, they were able to reflect on barriers and constraints and identify key lessons learned and good practices, which will be adopted in the Healthy Landscapes project especially in the relevant outputs of component 2. These address strengthening institutional coordination, planning frameworks and key policy recommendations. While these approaches will be implemented at pilot-scale, the project will also endeavor to scale these up to other projects and initiatives which are also operating in similar landscapes in the dry zone and cascade systems elsewhere. | The key messages conveyed for mitigation at the CEO approval stage are still relevant now and the project team and partners need to remain cognizant of these. However, post COVID-19 a stronger case can be made for the need for stronger Ecohealth approaches based on stronger cooperation among different actors and openness for new solutions. | CEO: M |
|  |  |  | TM: M |
|  |  |  | PM: M |
| The current rate of economic development, urbanization and increasingly climate change impacts may limit the desired outcomes of an ecological approach to environmental health and human health | The project is cognizant of the broad range of strategies, initiatives and actions to address potential development impacts as well as vulnerability profiles for Sri Lanka. However, the exact magnitude of these impacts and expected geographic variations beyond national level is poorly articulated or not understood. The project has integrated environmental and social risk analysis during project design and also into its landscape interventions that will seek to address potential economic development and climate change impacts. The project will also cooperate with several ongoing national initiatives and other projects that are addressing drivers of change, assessing vulnerability and generating climate change predictions and vulnerability analysis, which will be analysed and internalised in the project. | As mentioned earlier, the outbreak and multidimensional impacts of COVID-19 more than ever presents unique opportunities for the project to highlight critical links between the drivers identified in this risk and the urgency of exploring ways of promoting ecological approaches for environmental health and human health through better communication, collaborations and awareness-raising and education. | CEO: M |
|  |  |  | TM: L |
|  |  |  | PM: L |
| Overall Risk Rating Project Manager |  |  | M |
| Overall Risk Rating Task Manager |  |  | M |

Assessment of Possible COVID-19 Impacts to the Project, GEF id: # 9409

| COVID-19 impacts | - Has the COVID-19 pandemic impacted project implementation? If so, how? Yes. Through closure of government and university offices, project partners having to work remotely and prohibitions on travel to project sites. - Is there a pattern to the kinds of project activities/outputs that have been significantly impacted by the COVID-19 impacts? Yes No If Yes, please explain: Yes, those activities/outputs reliant on project team members visiting project sites for data collection (such as Outputs 1.1, Output 1.2, Output 1.3) or which require large gatherings of community members, project staff and other project partners have been impacted. Also, efforts to coordinate with national project team members who no longer go to the office has been a challenge, but that is now being addressed with planned regular zoom meetings. - Is there a pattern to the kinds of project activities/outputs, if any, that have not been seriously impacted by COVID-19 and are somehow able to continue? Yes No If Yes, please explain: Yes, the project team have prioritized planned Year 1 activities which can continue ‘virtually or remotely’ through information gathering, analysis, production of knowledge products, awareness raising and training materials, but these also depend on the disbursement of funds and approval of the LOA with the Ministry of Environment. - Will COVID-19 impacts, as of 30 June 2020, have implications on the project’s ability to finish by the expected completion date? Yes No. If Yes, please estimate the likely additional extension required: _6_months. (we realize that, until such a time that work conditions have returned to normal, this could likely be an underestimate). Yes, at the very least an extension of 6 months would be required. - Will COVID-19 impacts have implications on the project’s budget for PMC? Yes No. If Yes, please explain: Yes, while any NCE extension would probably not have implications for field implementation/activities, there could be implications regarding the executing agency’s inputs if project extension was substantial. |
| --- | --- |

Project overall risk rating (Low, Medium, Substantial or High)

| FY2019 rating [previous] | FY2020 rating [current] | Justification of the current FY risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| N/A | S | The delays in signing of the LoA and enabling its funds to flow for planned work, delays in establishment and staffing of the PMU, delays in most if not all of the actual fieldwork, affects over half or more of the project targets, outputs and deliverables; and as such the project is now at Substantial Risk. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks. 
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Some projects are adopting/planning to adopt milestones for tracking the achievement of outcomes. Add the corresponding milestones in this column when applicable to inform the rating. Milestones are optional and may substitute for Mid-Term Target.

Use GEF Secretariat required six-point scale system(GEF/C.52/Inf.06/Rev.01): Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)

Add rows if your objective has more than 3 outcome indicators. Same applies for the number of outcomes.

Outputs as described in the project logframe or in any updated project revision.

As per latest workplan (latest project revision)

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent).  The 2020 assessment should be copied from previous PIR.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU)