UN Environment GEF PIR Fiscal Year 2019

(1 July 2018 to 30 June 2019)

| - IDENTIFICATION |  |  | GEF ID 3969 |
| --- | --- | --- | --- |
| Project Number + Project Title |  |  | Capacity Strengthening and Technical Assistance for the Implementation of Stockholm Convention National Implementation Plans (NIPs) in Least Developed Countries (LDCs) of the ECOWAS sub-Region |
| Duration months | Planned |  | 60 months |
|  | Extension(s) |  | 3 |
| Division(s) Implementing the project |  |  | UNEP GEF Chemicals and Waste |
| Executing Agency(ies) |  |  | Green Cross Switzerland (GCCH) |
| Names of Other Project Partners |  |  | -Basel and Stockholm Convention Regional Centre for Francophone Africa (BSCRC-FA) – Dakar, Executing Agency - National government entities (MoEs) of participating countries; - NGOs (PAN Africa, Green Cross Burkina Faso) - FAO - University of Cape Town (UCT) (additional activities) - United Nations University (UNU-ViE-SCYCLE) (additional activities) - Africa Office, UNEP - UCT, South Africa - University of Geneva |
| Project Type |  |  | FSP |
| Project Scope |  |  | Regional |
| Region (delete as appropriate) |  |  | West Africa |
| Names of Beneficiary Countries |  |  | Benin, Burkina Faso, Cape Verde Islands, Central African Republic (CAR), Chad, Gambia, Guinea, Guinea-Bissau, Liberia, Mali, Mauritania, Niger, São Tomé and Príncipe (STP), Senegal, Sierra Leone, Togo |
| Programme of Work |  |  | Chemicals and Health Programme |
| GEF Focal Area(s) |  |  | Persistent Organic Pollutants (POPs) |
| UNDAF Linkages |  |  | [Where appropriate, insert the UNDAF strategic objective to which achievement the project contributes.] |
| Link to Relevant SDG Target(s) and SDG Indicator(s) |  |  | Relevant SDGs: 3, 6, (11), 12, 15 |
| GEF Financing Amount |  |  | USD 4’000’000 |
| Co-financing Amount |  |  | USD 4’858’549 |
| Date of CEO Endorsement |  |  | 13 April 2011 |
| Start of Implementation |  |  | 01 August 2011 |
| Date of First Disbursement |  |  | 17 August 2011 |
| Total Disbursement as of 30 June 2019 |  |  | $ 3,943,057.59 |
| Total Expenditure as of 30 June 2019 |  |  | $ 3,943,057.59 |
| Expected Mid-Term Date |  |  | 01 March 2015 |
| Completion Date |  | Planned | 31 July 2016 |
|  |  | Revised | 31 August 2019 |
| Expected Terminal Evaluation Date |  |  | June 2018 |
| Expected Financial Closure Date |  |  | December 2019 |

- OVERVIEW OF PROJECT STATUS

To be completed by UNEP/GEF Task Manager

UN Environment Subprogramme(s) Chemicals, Waste and Air Quality Subprogramme EA (a) Policies and legal, institutional and fiscal strategies and mechanisms for sound chemicals management developed or implemented in countries within the framework of relevant multilateral environmental agreements and the Strategic Approach to International Chemicals Management (SAICM EA (b) Policies and legal and institutional and fiscal strategies and mechanisms for waste prevention and sound management developed or implemented in countries within the framework of relevant multilateral environmental agreements; Specify the relevant Expected Accomplishment(s) & Indicator(s) "a(i) Increase in the number of countries that have used UNEP analysis or guidance, and where possible are applying a multi-sectoral approach, in developing or implementing legislation, policies or action plans that promote sound chemicals management and implementation of the relevant multilateral environmental agreements and SAICM. b(i) Increase in the number of countries that have used UNEP analysis or guidance in implementing waste prevention and sound management policies and good practices, in accordance with relevant multilateral environmental agreements, SAICM and other relevant international agreement..

For all GEF 6 and later projects: (not applicable for this project)

| GEF Core Indicators Insert core indicator(s) from Core Indicator Worksheet to which the project contributes | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| --- | --- |
|  | Indicative expected Results [add figure approved at CEO endorsement/ approval] |
| Describe any progress made towards meeting the indicative expected results as per the approved project documentation. Describe any key changes since previous reporting period. |  |

To be completed by Project Manager, as relevant

| Planned linkages with UNDAF | Describe progress towards the UNDAF strategic objective to which the project contributes. Specifically, the project has executed activities (contributing to the Sustainable development goals (12)(6)(3)) to: - Develop national POPs strategies and regional POPs reduction guidelines; - Train countries in solid and hazardous waste management; - Train government staff in the development of enhanced post-NIP inventories; |
| --- | --- |

| Planned contribution to relevant SDG target(s) and SDG indicator(s) | Describe progress towards the stated SDG target(s) and SDG indicator(s) to which the project contributes The 2030 Agenda for Sustainable Development and its 17 Sustainable Development Goals (SDGs) were adopted by the General Assembly of the United Nations in September 2015. Sound management of chemicals and waste (SMCW) is a specific target under SDG 12 on Sustainable Consumption and Production. It is also referred to under SDG 3 on Good Health and Well-being and SDG 6 on Clean Water and Sanitation. However, given that chemicals and waste affect almost all aspects of development, SMCW is relevant for, and supports the implementation of, many of the SDGs, if not all. The project will strengthen and build the national capacity of participating countries to institutionalize the implementation of their Stockholm Convention NIPs in a sustainable, effective and comprehensive manner, while building upon and contributing to strengthening country foundational capacity for the sound management of chemicals. |
| --- | --- |

| Implementation Status | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 |
| --- | --- | --- | --- | --- | --- |
|  | 1st PIR | 2nd PIR | 3rd PIR | 4th PIR | 5th PIR |
|  | FY 2018 | FY 2019 |  |  |  |
|  | 6th PIR | PIR-Final |  |  |  |

[complete the fiscal year in the first line; select HS; S; MS; MU; U; HU; unknown; not rated to rate the progress towards the development objective for the fiscal year you are reporting in the second line. Add more columns if needed]

| Development Objective Rating FY | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 |
| --- | --- | --- | --- | --- | --- |
|  | MS | S | S | S | S |
|  | FY 2018 | FY 2019 |  |  |  |
|  | S/HS | MS |  |  |  |
| Describe progress made towards achieving the project results as per table 3.1. State key changes since previous reporting period. The information here must be consistent with the assessment and justification provided under 3.1. The main executing agency had several legal problems that affected the implementation of the project in the last stage. |  |  |  |  |  |

[complete the fiscal year in the first line; select among H; S; MS; MU; U; HU; unknown; not rated to rate the implementation progress in the fiscal year you are reporting in the second line. Add more columns if needed]

| Implementation Progress Rating | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 |
| --- | --- | --- | --- | --- | --- |
|  | MS | MS | S | MS | S/MS |
|  | FY 2018 | FY 2019 |  |  |  |
|  | S/MS | MS |  |  |  |
| Describe annual implementation progress, including any significant [expected and unexpected] environmental or other changes (Results) attributable to project implementation. Also, please discuss any major challenges to meet the objectives or specific project outcomes. [section will be uploaded into the GEF Portal ‘Information on Progress, challenges and outcomes on project implementation activities’ and is the primary report that viewers can see before opening the detailed PIR]. The information must be consistent with the assessment and justification provided under 3.2. The main executing agency had several legal problems that affected the implementation of the project in the last stage. |  |  |  |  |  |

[complete the fiscal year in the first line; select H; S; M; L; to rate the fiscal year you are reporting. Add more columns if needed]

| Risk Rating | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 |
| --- | --- | --- | --- | --- | --- |
|  | S | S | M | M | L |
|  | FY 2018 | FY 2019 |  |  |  |
|  | L | M |  |  |  |
| Describe key changes since previous reporting period. Projects with ESERN rating high medium/high risk must refer to the safeguards implementation plan and its implementation. [section will be uploaded into the GEF Portal and in UN Environment Open Platform] The information here must be consistent with the assessment and justification provided under 3.3 The main executing agency had several legal problems that affected the implementation of the project in the last stage. |  |  |  |  |  |

| Stakeholder engagement | Describe progress, challenges and outcomes on stakeholder engagement (based on the description of the Stakeholder engagement plan included at CEO endorsement) [section will be uploaded into the GEF Portal] Stakeholder involvement has a significant impact on the countries’ commitment. The project was highly relevant to national development priorities, complementing the countries’ NIPs, but was lacking substantial ownership by the government key institutions (mainly ministries of environment that held a key role in this project), not least because of frequent staff turnover in some countries and/or political instability. However, the success of the project is the inclusion of many additional stakeholders during implementation (e.g. University of Cape Town (UCT); and United Nations University (UNU). With the implication of new stakeholders, the project built on relevant results, thus significantly adding value to the project. |
| --- | --- |

| Gender mainstreaming | Describe progress, challenges and outcomes related to the gender-responsive measures documented at CEO Endorsement/Approval in the gender action plan or equivalent. Older projects that were designed before gender mainstreaming should proactively report any possible gender benefits, as appropriate. [section will be uploaded into the GEF Portal] During the course of project implementation sex disaggregated reporting (and with a view to the different trainings carried out) was an initial step towards gender mainstreaming. Also and in relation to component 3, all activities carried out by the NGOs in four countries (Burkina Faso, Mali, Senegal, and Togo) beneficially included mainly vulnerable groups, including particularly women. The introduction of participatory approaches by using multiplicators positively impacted the relevant target groups. |
| --- | --- |

| Knowledge activities and products | Provide a narrative of knowledge activities/products (when applicable), as outlined in knowledge management approved at CEO Endorsement/Approval [section will be uploaded into the GEF Portal] The project planned to revitalize the Chemical Information Exchange Network (CIEN) as a knowledge management system. The design envisaged that the SAICM Information Clearinghouse would provide links to the CIEN. In the case that CIEN would not be revitalized, the work plan included the Information Clearinghouse to house and link to the knowledge management component of this project. The decision to relocate and integrate the CIEN server into the BSCRC-AF website by upgrading hardware, internet access, redesigning the website (www.crcbsaf.org), and the population of pages and transfer of information was done. |
| --- | --- |

| Stories to be shared | Optional for mature projects: Provide a brief summary of any especially interesting and impactful project results that are worth sharing with a larger audience, and/or investing communications time in, if any. [section to be shared with communication division/GEF communication] N/A – mature project. |
| --- | --- |

- RATING PROJECT PERFORMANCE AND RISK

Based on inputs by the Project Manager, the UNEP Task Manager will make an overall assessment and provide ratings of:

- Progress towards achieving the project Results(s)- see section 3.1

- Implementation progress – see section 3.2

Section 3.3 on Risk should be first completed by the Project Manager. The UNEP Task Manager will subsequently enter his/her own ratings in the appropriate column.

  - 3.1	Rating of progress towards achieving the project Results(s)

| Project objective and Outcomes | Description of indicator | Baseline level | Mid-term target | End-of-project target | Level as of 30 June 2019 |  | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Objective Strengthen and/or build the capacity required in LDCs in ECOWAS Africa subregion to implement their Stockholm Convention NIPs in a sustainable, effective and comprehensive manner, while building upon and contributing to strengthening country's foundational capacities for sound management of chemicals. |  |  |  |  |  |  |  |
| Outcome 1: Model comprehensive chemicals regulatory system, including legislation, regulation, guidelines for implementation, sectoral guidelines and standard setting developed. | -Work plan - Number of drafted chemical regulations | ProDoc: No country in the ECOWAS subregion has comprehensive regulatory system in place for chemicals. (Several countries have sectoral regulations requiring revision to take account of the requirements of the Stockholm Convention. Framework legislation is also required). | ProDoc: Not defined | ProDoc: - 1. 7 countries have work plans for comprehensive regulatory framework developed. 2. 5 countries have developed and drafted chemicals regulation |  | - Signed agreements with 15 countries - 10 countries provided draft national legislation and regulation on chemicals: Burkina Faso, Chad, Gambia, Guinea, Guinea-Bissau, Niger, STP, Senegal, Sierra Leone, and Togo - 7 out of these countries have adopted or at least partly adopted chemicals regulation: Burkina Faso, Chad, Guinea, Guinea-Bissau, Niger, STP, and Senegal | S |
| Outcome 2: Guidelines for controlling BAT/BEP in the informal sector developed and adopted | Number of BAT/BEP sectoral guidelines. | Same as outcome 1 above | ProDoc: Not defined | ProDoc: - 4 countries have adopted and initiated implementation of BAT/BEP informal sector guidelines. |  | History outline: No further information from UNIDO available - Cancellation of activities as discussed at 4th SC meeting in 2015 and adopted at 5th SC meeting in 2016 | U |
| Outcome 3: Train-the-trainer for national level environment staff and provincial level environmental level inspectors, port workers and police, on the Stockholm Convention and hazardous wastes creates a cadre of trained personnel able to train others on the Stockholm convention. |  | ProDoc: Number of trained trainers. - Records of trainings. - Number and type of developed tool kits. - Number of trained officials. | ProDoc: Not defined | ProDoc: - 10 provincial level staff trained in each participating country. -Two “trainers” trained in each participating |  | - Sub-regional training workshop completed (Feb 2013 in Lomé, Togo) - 14 countries carried out at least 3 trainings | S |
| Outcome 4: Development of tool kit, and training of judiciary and Ministry of Finance staff on the Stockholm and other chemicals conventions leads to increased support for implementation and active and enforcement of the convention by these sectors | - Record of number of judges trained. -A record of MOF staff trained. - Training evaluation forms | ProDoc: No Stockholm Convention training materials, specifically targeting the judiciary, or Ministry of Finance, currently available. | ProDoc: Not defined | ProDoc: Three judges and 2 MOF staff trained per participating country. |  | History outline: - Toolkits for ECOWAS sub-region adapted, amended and translated into French - 1st sub-regional workshop for judiciary members (4-5 Aug 2016 in Dakar, Senegal) - 2nd sub-regional workshop for MoF/customs (28-29 Sep 2016 in Bamako, Mali) | S |
| Outcome 5: Training of environmental specialists in POPs inventory making and in the FAO Pesticide Stocks Management System (PSMS) enables better management of pesticide stocks | - Training records. - Number of trained officials. | ProDoc: Mali is the only country in the subregion utilizing the PSMS (will host the training). | ProDoc: Not defined | ProDoc: - Training of 2 agriculture and 1 environmental staff member, per country. | t | - FAO inception workshop (2-4 Mar 2016 in Ouagadougou, Burkina Faso) and 1st SC meeting (3 June 2016 in Abidjan, Ivory Coast) - Sub-regional inventory training (30 Jan-3 Feb 2017 in Bamako, Mali) ------- | U |
| Outcome 6: Comprehensive, accurate and accessible database and network on laboratories exists and is used by countries to identify options for sample analysis. | - Networked database laboratories. - A list of equipments and staff capability. | No comprehensive, accurate and accessible database exists on laboratories in the subregion. | ProDoc: Not defined | Network and database of subregional laboratories, including information on equipment, staff capability, and analytical capability, developed. |  | Conclusion to cancel output; adopted during 5th SC meeting (end June 2016) - Funds re-allocated to different other activities to improve the visibility of the project | U |
| Outcome 7: Platform reactivated as a knowledge management system and actively utilized by participating countries. | - An active CIEN platform. | ProDoc: CIEN platform exists but is inactive | ProDoc: Not defined | ProDoc: Revitalize the Chemical Information Exchange Network (CIEN) as a knowledge management system. |  | - Decision (based on May 2017 COP and Jun 2017 SC meetings) to relocate and integrate CIEN server into BSCRC-AF website. Hardware, internet access upgraded, website www.crcbsaf.org redesigned, population of pages and transfer of information | S |
| Outcome 8: Two pilot communities trained in each participating country. NGO’s are identified and gain experience in working on this issue. | - Number of trained people. - Materials developed. - Number of NGOs partnered with. | ProDoc: Little systematic targeting has been conducted for POPs- vulnerable communities in this region. Few NGOs are working on this issue | ProDoc: Not defined | Development of POPs education (including on 9 new POPs), and pilot community training, working with local NGOs and focusing on vulnerable communities. |  | - Community trainings in 4 countries (Burkina Faso, Mali, Senegal, Togo) | S |
| Outcome 9: Development of a POPs-focused environmental education program on POPs (including teacher training) creates awareness of POPs issues to a wide population and entrenches the issue in the education system | - - Number of trained teachers. - Training records. - Records of meetings held with the Ministry of Education. - Documented POPs focused environmental education program. | ProDoc: Absence of integration of chemicals and POPs issues into ECOWAS school curricula, no substantial relationship between POPs National Focal Point and Ministry of Education | ProDoc: Not defined | Teachers from 5 schools per participating country trained on POPs focused environmental education. POPs National Focal Point involved in building a relationship with the Ministry of Education. Targeted training/awareness raising for curriculum developers. |  | - Community awareness raising and 60 teachers from 5 schools (20 schools in total) trained in 4 countries (Burkina Faso, Mali, Senegal, Togo) | S |
| Outcome 10: ECOWAS countries make a declaration committing to implement the Stockholm Convention, and, if required, provide resources. | - Record of the number of participants in the ECOWAS forum. - Meetings and the forum’s reports. - ECOWAS declaration. | ProDoc: Absence of high-level support for implementation of the Stockholm Convention in the ECOWAS forum | ProDoc: Not defined | Bring high-level representatives to ECOWAS forum, to increase high level awareness on the Stockholm Convention. |  | History outline: - Side event carried out during AMCEN-2015, Cairo, Egypt (infos from April 2015) - Side event carried out during AMCEN-2017 in Libreville, Gabon to inform about project to a broader audience ------- - High-level side event with the ECOWAS Commission on 3rd Nov 2017 in the frame of experts and ministerial meeting (30 Oct-1st Nov 2017) in Abidjan, Côte d’Ivoire | S |

Overall rating of project progress towards meeting project Result(s) (To be provided by UNEP GEF Task Manager.)

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current FY rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | Summarize the annual progress towards meeting project results. Describe any significant [expected and unexpected] environmental or other changes (Results) negative and or positive attributable to project implementation. State any key changes since previous reporting period. Also, please discuss any major challenges to meet the objectives or specific project outcomes. Whenever possible, please provide evidence of attribution between the UNEP/GEF project’s intervention and observed changes towards the achievement of direct outcomes. In cases where several actors are collaborating to achieve common outcomes, evidence of the nature and magnitude of the UNEP/GEF project’s ‘substantive contribution’ and/or ‘credible association’ should be described. This information provides the rationale for the Development Objective Rating in Section 2. |

Risks to the delivery of results

The second column should be completed by the Project Manager and the third column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk. Projects should complete only the relevant sections and are free to add/delete problems/risks. This section should inform the risk rating in section 3.3.

| Problems/risks identified | Description of the problem/risk | (Agreed) recommended actions |
| --- | --- | --- |
| on achieving targets | The project closed on 30 April 2019. Activities were delayed but targets have been more than achieved and outcomes significantly exceeded. Due to efficient financial management, many additional activities could be implemented. | Project closed in September 2019. No Action recommended. |
| on gender actions | Gender specific actions were not part of the project design. The activities on community level, however, specifically focused on most vulnerable target groups, such as women and children. | Project closed in September 2019. No Action recommended. |
| on safeguards | Obsolete pesticides: Inventory were finalised in four countries. No follow-on is planned, therefore data might soon become obsolete, and there is a substantial risk of new accumulation of increasing pesticides over time. PCB inventory: Inventory was done, but follow-on actions needed to handle transformers coming to the end of their service life. | Project closed in September 2019. No Action recommended. |
| on sustainability of results | Potential risks: Financial, socio-economic, institutional, political, and environmental risks were well reflected in the project design but the mitigation measures have not been sufficiently followed-up, also with regard to the PIRs. Quickly changing environments, however, shall not be underestimated as they are essential characteristics of developing countries that need specific attention. Examples are the past Ebola outbreak in Guinea, Liberia, and Sierra Leone as well as the conflicts and political instability in the Central African Republic. Sustaining long-term project results. The project resulted in many important outcomes, with some of the countries not being able to finalise with implementation of planned activities as a consequence of project closure. However, this concerned the late implementers that were not part of the initial work plan. The targets have been more than achieved. While the project was able to create and strengthen the foundation for improved POPs management in the sub-region, it is important that there is a follow-up on the different levels of implementation (sub-regional, national, communal). Without external support, many countries lack the economic and political stability to develop national wastes agendas to be pushed in a consistent way. Follow-up planning after project closure by considering linkages to other existing and/or planned programmes and projects at national, sub-regional, and African-wide level would allow to building on significant results and sustaining long-term project results. | Project closed in September 2019. No Action recommended. |

3.2	Rating of progress implementation towards delivery of outputs

| Outputs | Expected delivery date | Implemen-tation status as of 30 June 2018 (%) | Implemen-tation status as of 30 June 2019 (%) | Progress rating justification (as much as possible, describe in terms of immediate gains to target groups, e.g. access to project deliverables, participation in receiving services; gains in knowledge, etc.) | Progress rating |  |
| --- | --- | --- | --- | --- | --- | --- |
| Output 1 1 Model comprehensive chemicals regulatory system, including legislation, regulation, guidelines for implementation, sectoral guidelines and standard setting developed. | 1st semester, year 1 | 60 % | 60 % | Not all countries’ regulatory systems could be impacted under this project. | U |
| Output 2: Guidelines on using BAT/BEP in the informal sector developed and made available for use by participating countries. | 1st and 2nd semester, year 1 | 100 % | 100% | Yes this was achieved | S |
| Output 3: Train-the-trainer for national level environment staff, results in certified trainers. | 2nd semester, year 1 | 100 % | 100 % | Yes this was achieved | S |
| Output 4: Trained cadre of provincial level staff and environmental inspectors, port workers and police on the Stockholm Convention. | 2nd semester, year 1 / 1st semester, year 2 | 60 % | 60 % | Not all identified groups could be trained via this project | U |
| Output 5: Development of tool kit, and training of judiciary and Ministry of Finance staff on the Stockholm and other chemicals conventions. | 1st semester, year 2 | 100 % | 100 % | Yes this was achieved | S |
| Output 6: Trained environmental and agricultural staff in inventory development and in the use of the FAO PSMS | End Jan 2017 | 50% | 50% | Not all activities could be completed | U |
| Output 7 Network and database of subregional laboratories, including information on equipment, staff capability, and analytical capability, developed. | End Jan 2017 | 0 % | 0 % | This output could not be achieved | U |
| Output 8: Revitalize the Chemical Information Exchange Network (CIEN) as a knowledge management system. | End Jul 2015 | 100 % | 100 % | Yes this was achieved | S |
| Output 9: Development of POPs education materials (including on 9 new POPs). | End Jan 2017 | 100 % | 100 % | Yes this was achieved | S |
| Output 10: Development of a POPs focused environmental education program. | Continuously implemented | 100 % | 100 % | Yes this was achieved | S |
| Output 11: Pilot teacher training undertaken. | End Jul 2016 | 100% | 100% | Yes this was achieved | S |
| Output 12: Bring high-level representatives to ECOWAS forum, to increase high level awareness on the Stockholm Convention. | End Jan 2017 | 100% | 100% | Yes this was achieved | S |

Overall project implementation progress  (To be completed by UNEP GEF Task Manager.):

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| MS | MS | The rating of progress in the delivery of outputs should be assessed in terms of both quantity and quality. The assessment must consider ownership by, and usefulness to, intended beneficiaries and the timeliness of their delivery. Use the comments column to explain the reasons behind the success or shortcomings of the project in delivering its programmed outputs and meeting expected quality standards. |

Risks in implementation

This section should be completed by the Project Manager and summarize implementation risks (e.g. procurement delays, reputational risks etc.).

The first column should be completed by the Project Manager and the second column should summarize the recommendations that the Project Manager and Task Manager have agreed upon to address the problem/risk. This section should inform the risk rating in section 3.3.

| Problems/Risks Identified | (Agreed) Recommended Actions | By Whom | When |
| --- | --- | --- | --- |
| - Long time period from project design to implementation - | → Recommendation 1: Delivery of co-finance (cash and in kind) should be a regular agenda point at each SC meeting, so that timely and appropriate action is possible when becoming necessary. → Recommendation 2: The scaling up of interventions is highly relevant. A comprehensive communication strategy could significantly support the sustainability of project results (this includes the elaboration of brochures and information material on project results and success stories), thus raising awareness at different levels (high level to community/direct beneficiary levels). → Recommendation 3: The executing agency Greencross Switzerland went through a major upheaval towards the end of the project and this was kept concealed from the IA. Eventually, the project closure was done with Greencross having to deliver on what they have been advanced. | EA to look into their design regularly IA, EA IA | The project is closed and all recommendations could only be implemented in another project. |

| FY2018 rating [previous] | FY2019 rating [current] | Justification of the current risk rating and explanation of reasons for change (positive or negative) since previous reporting periods. |
| --- | --- | --- |
| L | L | Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project to deliver the expected results and, whenever possible, the proposed measures to address these risks. Refer also to the assumptions and drivers e.g. when the assumptions are not holding and/or the drivers are not in place. Please refer to the GEF risk rating table below. |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. 
Substantial Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks. 
Modest Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.
Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

For joint projects and where applicable ratings should also be discussed with the Task Manager of co-implementing agency.

Add rows if your project has more than 3 key indicators per objective or outcome.

Depending on selected indicator, quantitative or qualitative baseline levels and targets could be used (see Glossary included as Annex 1).

Many projects did not identify Mid-term targets at the design stage therefore this column should only be filled if relevant.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU). See Annex 2 which contains GEF definitions.

Outputs and activities as described in the project log frame or in any updated project revision.

As per latest work plan (latest project revision).

Implementation may be assessed by qualitative assessments, percentage of delivery, and/or budget expenditure (planned and actually spent). The 2018 assessment should be copied from previous PIR.

To be provided by the UNEP Task Manager.

Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), Marginally Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).