PROJECT DOCUMENT

| Project title: Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola |  |  |  |
| --- | --- | --- | --- |
| Country: Republic of Angola | Implementing Partner: Ministry of Environment (MINAMB) |  | Management Arrangements: National Implementation Modality (NIM) |
| UNPAF/Country Programme Outcome: Outcome 4: By 2019, the environmental sustainability is strengthened through the improvement of management of energy, natural resources, access to green technology, climate change strategies, conservation of biodiversity, and systems and plans to reduce disasters and risks |  |  |  |
| UNDP Strategic Plan 2018-2021: Integrated Results and Resources Framework Output 1.4.1. Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains Indicator 1.4.1.b. Area of existing protected area under improved management (hectares) |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate Risk |  | UNDP Gender Marker: 2 (the project has gender equality as a significant objective) |  |
| Atlas Award ID: 00114883 |  | Atlas Output ID (formerly Project ID): 00112730 |  |
| UNDP-GEF PIMS ID number: 5993 |  | GEF ID number: 9735 |  |
| Planned start date: October 2019 |  | Planned end date: December 2025 |  |
| PAC meeting date: June 2019 |  |  |  |
| Brief project description: The project is designed to address key threats for wildlife in Angola including poaching and illegal wildlife trade, human-wildlife conflicts, and degradation of habitat. The project Objective is to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola. The Objective will be achieved through integrated implementation of four project strategies (Components): Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime; Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation; Component 3. Engaging local communities in sustainable wildlife, forest and PA management; and Component 4. Knowledge Management, M&E and Gender Mainstreaming. The project’s priority investments will be made in the two selected project areas – Maiombe National Park and Luando Strict Nature Reserve, which are important habitats for such endangered species as forest elephant, western lowland gorilla, central chimpanzee, and black giant sable antelope. While this project is not a part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species (GWP) it was designed to contribute to the GWP as much as possible and will coordinate its activities with the Program (GWP 9071). |  |  |  |

| Financing Plan |  |  |
| --- | --- | --- |
| GEF Trust Fund | USD 4,103,800 |  |
| - Total Budget administered by UNDP | USD 4,103,800 |  |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |  |  |
| Ministry of Environment | USD 5,477,000 |  |
| KfW Bankengruppe | USD 6,000,000 |  |
| Kissama Foundation | USD 245,000 |  |
| Stop Ivory | USD 346,934 |  |
| ICCF | USD 400,000 |  |
| ADPP | USD 4,032,000 |  |
| - Total co-financing | USD 16,500,934 |  |
| - Grand-Total Project Financing (1)+(2) | USD 20,604,734 |  |
| Signatures |  |  |
| Signature: print name below | Agreed by Government | Date/Month/Year: |
| Signature: print name below | Agreed by Implementing Partner | Date/Month/Year: |
| Signature: print name below | Agreed by UNDP | Date/Month/Year: |

# Table of Contents

Table of Contents	3

I.	Development Challenge	6

II.	Strategy	21

III.	Results and Partnerships	32

i.	Expected results	32

ii.	Partnerships	47

iii.	Stakeholders’ engagement	52

iv.	Mainstreaming Gender	58

v.	Project Risks and Mitigation Measures	61

vi.	South-South and Triangular Cooperation (SSTrC)	65

vii.	Sustainability and Scaling Up	65

IV.	Project Management	67

i.	Cost efficiency and effectiveness	67

ii.	Project Management	67

iii.	Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information	67

V.	Project Results Framework	69

VI.	Monitoring and Evaluation (M&E) Plan	76

VII.	Governance and Management Arrangements	81

VIII.	Financial Planning and Management	85

IX.	Total Budget and Work Plan	87

X.	Legal Context	91

XI.	Risk Management	91

XII.	Annexes	94

Annex A:  Multi-Year Work Plan	94

Annex B. Monitoring Plan	100

Annex C. Evaluation Plan	104

Annex D.  GEF Tracking Tool	105

Annex E. Terms of Reference	105

Annex F. Overview of Technical Consultancies	112

Annex G. UNDP Social and Environmental and Social Screening Template (SESP)	116

Annex G1. Terms of Reference for Environmental and Social Impact Assessment (ESIA) and Environmental and Social Management Plan (ESMP)	130

Annex H. Stakeholder Communication and Involvement Plan	145

Annex I. Gender Analysis and Mainstreaming Plan	155

Annex J.  UNDP Risk Log	166

Annex K. HACT micro assessment of the Implementing Partner (MINAMB/INBAC)	170

Annex L. Deleted	171

Annex L1. Indicative Procurement Plan for the project	171

Annex M. Project Co-Financing Letters	179

Annex N. OFP GEF Letter	185

Annex O. UNDP Project Quality Assurance Report	187

Annex P. Landscape Profile Report	187

Annex Q. Capacity Assessment Scorecard for a Wildlife Crime Law Enforcement Agency – National Institute for Biodiversity and Protected Areas (INBAC), Angola	188

Annex R. ICCWC Indicator Framework Report	197

Annex S. Brief Project Knowledge Management Strategy	197

Annex T. List of stakeholders consulted for the project development	200

List of acronyms and abbreviations

| ADPP | Ajuda de Desenvolvimento de Povo para Povo |
| --- | --- |
| ADRA | Acção para o Desenvolvimento Rural e Ambiente |
| AfDB | African Development Bank |
| CBD | Convention on Biological Diversity |
| CBNRM | Community Based Natural Resource Management |
| CBWM | Community Based Wildlife Management |
| CITES | Convention on International Trade in Endangered Species of Wild Fauna and Flora |
| CMS | Convention on Migratory Species |
| COSPE | Cooperazione per lo Sviluppo dei Paesi Emergenti |
| ECU | Environmental Crime Unit |
| EIA | Environmental Investigation Agency |
| EPI | Elephant Protection Initiative |
| ESIA | Environmental and Social Impact Assessment |
| ESMP | Environmental and Social Management Plan |
| FAS | Fundo de Apoio Social (Social Support Fund) |
| FSP | Full Sized Project |
| GEF | Global Environment Facility |
| GRM | Grievance Redress Mechanism |
| GWP | Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development |
| HEC | Human-Elephant Conflict |
| HWC | Human-Wildlife Conflict |
| ICCWC IF | International Consortium on Combating Wildlife Crime Indicator Framework |
| IDF | National Forest Development Institute (Instituto de Desenvolvimento Florestal) |
| IELP | International Environmental Law Project |
| INBAC | National Institute for Biodiversity and Protected Areas |
| IUCN | International Union for Conservation of Nature |
| IWT | Illegal Wildlife Trade |
| JEA | Juventude Ecologica Angolana |
| KAZA | Kavango–Zambezi Transfrontier Conservation Area |
| KfW | Reconstruction Credit Institute of Germany |
| LE | Law Enforcement |
| MINAMB | Ministry of Environment |
| MINAGRIF | Ministry of Agriculture and Forests |
| M&E | Monitoring & Evaluation |
| NIAP | National Ivory Action Plan |
| NEAP | National Elephant Action Plan |
| PA | Protected Area |
| PIF | Project Identification Form |
| PIR | Project Implementation Report |
| PPG | Project Preparation Grant |
| SADC | Southern African Development Community |
| SFM | Sustainable Forest Management |
| SLM | Sustainable Land Management |
| SGP | GEF Small Grants Programme |
| STAP | GEF Scientific and Technical Advisory Panel |
| UNDP | United Nations Development Programme |
| UNEP | United Nations Environment Programme |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNODC | United Nations Office on Drugs and Crime |
| USAID | United States Agency for International Development |
| WWF | World Wide Fund for Nature |

# Development Challenge

- Angola, officially the Republic of Angola, is located on the west coast of Africa between 4° 22’ and 18° 02’ south latitude and 11° 41’ and 24 ° 05’ west longitudes and has a land area of 1,246,700 km². It is the world’s 23rd largest country. The country is bordered to the north by the Democratic Republic of the Congo and the Republic of Congo, the east by Zambia, the south by Namibia, and the west by the Atlantic Ocean, with a coastline of 1,600 km. The total population of Angola is estimated to be 30,566,027 inhabitants unevenly distributed through the country with an average population density of 25 people per 1 km². 62.4% of the Angola’s population lives in rural areas. The human population growth is very high (it is the second country in terms of continental growth rate after South Sudan) and is estimated to be 3.52% annually (2017).

- Angola's economy has been driven by the oil sector (provides 50% of GDP and more than 90% of the country's exports) and diamond extraction (additional 5% to exports) with average economic growth of 17% in 2004-2008 and 1.3% in 2015-2017. Agriculture (mainly subsistence) provides the main livelihood for ~85% of the country population and contributes 10.2% of GDP (2011), but half of the country's food is still imported. Despite Angola being the Africa's second biggest oil producer, 40.5% of the population lives below the poverty line (2008) and the country’s Human Development Index is still low (0.533, ranked as 150 among countries of the world). Much of the country's infrastructure is still damaged or undeveloped from the long civil war, and land mines remain in the countryside.

- Angola has one of the highest ecosystem diversities in Africa, with humid tropical forest in the north and desert in the south, although much of the country (45%) is covered by Miombo forest, dry tropical woodland (savannah) (24%), and Miombo-savannah mosaic (20%). Of the estimated 8,000 plant species that are believed to exist in the country, 1,260 are endemic (the second highest number of endemic plants by African countries). The diversity of mammals is also one of the richest on the continent with 275 recorded species, including the famous giant sable antelope (Hippotragus niger variani), the African savanna and forest elephants (Loxodonta africana africana and Loxodonta africana cyclotis); the western gorilla (Gorilla gorilla), chimpanzee (Pan troglodytes); African manatee (Trichechus senegalensis) and various species of marine turtles. The country has more than 420 fish species, 78 amphibian species, 227 reptile species, and 915 bird species (92% of the avifauna of southern Africa). The exceptional biodiversity in Angola is due to a combination of a number of factors: the large size of the country, the inter-tropical geographical location, the climatic and altitude variation and the types of biomes. Habitats such as the humid-tropical forests in the north (including Maiombe National Park) are a depository of an enormous and rich variety of animal and plant species with significant international value such as chimpanzees, gorillas and forest elephants, while the Miombo woodlands that cover most of Angola are home to savanna elephants, giant sable antelopes and other species of conservation concern. Despite this high level of biodiversity, animal species such as the cheetah, brown hyenas, African wild dog, mountain and plain zebras, giraffe and oryx are listed as very vulnerable in parts of the Angolan territory, while rhinoceros is probably extinct in the country. Various other species are also facing decline due to pressure from anthropogenic activities – in fact, 50 of the 275 mammal species that occur in Angola are listed as facing risks. Some data on some of Angola’s flagship species is presented below.

- There has been no survey to determine the status of rhinos in Angola since independence (1975). A 1971 survey in Iona National Park (NP) estimated 30 black rhinos that were reported extinct by 2004. The only other information available on black rhinos in the southeast corner of Angola dates from 1989-1990: 5-6 animals found at the border of Angola and Namibia. It is most probable that both black and white rhinos are extinct in Angola.

- Prior to the 1970s, Angola was estimated to have 5,000-70,000 elephants. An estimated 100,000 elephants were killed during the civil war; however, it is likely that some of this number originated outside Angola. Current population of elephants in Angola is estimated at 3,396±1,562 individuals, which mainly concentrate in the south-east corner of the country. The number of forest elephants in Angola is unknown although existing fragmental data suggest that it does not exceed several hundred animals.

- Giant sable antelope, Angola’s national symbol and endemic, survives currently only in two protected areas – Cangandala National Park and Luando Special Reserve – with a total population of no more than 150-200 individuals. There were an estimated 2,000-3,000 Giant Sable in the late 1960s (Estes and Estes 1974; East 1999). Numbers have since been greatly reduced and by 2007 were estimated at 200-400 (P. vaz Pinto in litt. to ASG, 2007).

- Western lowland gorilla and chimpanzee in Angola occur only in Cabinda enclave in low numbers. There is no information on chimpanzee and gorilla populations in Angola. After 1982 and during the war, both species were considered to be probably extinct. The presence of both species in Cabinda enclave was verified and reported again only in 2000,. Population modelling estimates presume that the gorilla population in Cabinda declined from 3,086 (CI: 2,188-6,355) in 2005 to 1,652 (CI: 1,174-3,311) in 2013, and chimpanzee population does not exceed 1,705 individuals (1,027-4,801) in 2005-2013. However, there is no data to verify this model’s estimates.

- African lion population in the south-east corner of Angola decreased from about 1,000 individuals at the beginning of 2000s to only 10-30 individuals in 2016, although the presence of lions is reported from elsewhere in the country.

Direct Threats for Angola’s wildlife

- Key direct threats for wildlife in Angola are represented by poaching, human-wildlife conflicts, and degradation of habitat by deliberate and wild fires, expansion of agriculture based mostly on the unsustainable slash and burn practice, expansion of settlements, logging and mining concessions. Threats that are more localized but may be significant in specific ecosystems include unsustainable fishing practices, over-grazing, and invasive species.

- Poaching. Poaching is the most serious threat for wildlife in Angola, including illegal hunting for high value species like elephants, great apes, African grey parrots, and pangolins, involved in international illegal wildlife trade as well as intensive bushmeat hunting for wide range of species for domestic market.  Poaching for elephants and rhinos in Africa has surged dramatically since the late 2000s, mostly due to increased demand from Asia and particularly China, Thailand and Vietnam where ivory and rhino horn products are very popular among the widening middle-class. The main problem is an export of consolidated shipments and later sale in Asia, where Chinese nationals were by far the most frequently identified ivory buyers, representing most of the demand for raw and worked ivory in the region. While ivory sold for around US$200 per kilogram in China in 2003, the same quantity sold for US$2,500-$3,000 in 2013. However, recent ivory legislations in China have decreased ivory prices to about US$850 in 2017. Unfortunately, the decline in ivory prices is not linked to a parallel decrease in elephant poaching.

- Despite some recovery of the elephant population after the civil war, the last aerial survey in south-east Angola (2015) indicated a 21% elephant population decline from the 2005 estimate as well as high (30%) carcass ratio reflecting high level of mortality attributed to poaching. Another aerial survey conducted in Luengue-Luiana and Mavinga National Parks in September 2017 reported a high number of elephant carcasses (475) indicating high level of mortality due to poaching. Incidental elephant poaching was reported in other areas, e.g. Maiombe and Mupa NPs.

- Until 2016, Angola had a large and unregulated domestic ivory market, mainly in Luanda. Market survey in Luanda in 2005 found 41 retail outlets selling ivory products that collectively were estimated to weigh a total of 1,573.4 kg during this survey. About 90% of this ivory was found at the Mercado do Artesanato (Artists’ Market) at Benfica, south of Luanda. Another market survey in Luanda in 2014 discovered more than 10,000 items made from ivory and exposed for selling mainly at the Mercado do Artesanato (92% of all counted items). Both surveys indicated that only a small portion of the ivory found in Luanda originated from elephants killed in Angola, while most of the ivory was from recently killed forest elephants from Central and Western Africa mainly from the Democratic Republic of Congo and Republic of Congo (this area, especially TRIDOM, was indicated as a new epicentre of elephant poaching).  The main buyers of the worked ivory in Angola in 2014 were Chinese, while in 2005 they were Americans, Chinese, and Portuguese. Both surveys indicated the lack of legal documents for ivory possession and selling by the traders. The actual ban on ivory trading in Angola was reportedly imposed in March 2016, and the formal market was closed, although enforcement of the informal and illegal trade is still very weak, and the state of implementation remains to be assessed.

- Last ivory seizure statistics indicate Angola as an important transit country for trafficking of ivory from Western Africa to Asia. Until 2013, the Angolan Government never reported any seizures of ivory to the Elephant Trade Information System (ETIS). In 2012-2014, however, there have been official seizures of ivory from Angola in other countries: In September 2012, a bag with ivory originated from Angola was seized at the Jomo Kenyatta International Airport in Nairobi on its way to Bangkok. In 2013-2014, 105 kg of ivory intercepted from a flight from Angola in Bangkok airport; 45 kg of Angolan ivory were seized in Changi airport in Singapore; 79,5 kg of ivory from Angola were seized in Siem Reap airport in Cambodia; 790 kg of tusks from Angola seized by Hong Kong airport customs. In October 2015, 110 kg of ivory were intercepted at Heathrow Airport on the way from Angola to Hanover, Germany. In June 2016, 142 kg of ivory were seized in the Charles de Gaulle Airport, France, from a passenger travelling from Angola to Vietnam via Paris. 101 kg of ivory were confiscated in the Kuala Lumpur International Airport in March 2016 from two passengers travelling from Angola to Vietnam. It is interesting that Angola’s TAAG is one of the only two African carriers with non-stop flights to China. Angola was listed among top ten countries by number of ivory trafficking instances between January 2009 and August 2016 (total 16 instances were recorded). Despite this fact Angola had 0% Country Enforcement Index in 2016 indicating the country’s very low ability to detect and seize illicit wildlife products traversing through its airports.  However, at least six-seven seizures of wildlife products happened in Angola in 2015-2018, including two that can be classified as large seizures. Thus, in May 2015, 369 kg of ivory was seized at Luanda's 4 de Fevereiro International Airport. On June 4 2018, 82 elephant tusks were seized by the National Police at the airport again.

- Bushmeat hunting is probably the most serious threat to wildlife in Angola. About 60% of Angolans depend on bushmeat to a large extent as a major source of protein and income. Although any hunting and bushmeat trade is illegal in Angola, bushmeat is readily available in much of the country and can be bought openly along roadsides. The bushmeat hunting in Angola, as elsewhere, is not selective. It depletes most large and medium-sized mammals almost everywhere in the country, and even involves, deliberately non-deliberately, such endangered species as sea turtles, pangolins, leopards, giant sable antelopes, gorillas and chimpanzees, among others. A brief survey (about 10 days) of Bersacola et al. (2014) in Kumbira Forest, the Bimbe area and Benfica Mercado do Artesano market in Luanda in 2013 revealed bushmeat for sale in 13 locations and recorded 112 animal individuals/products of 23 species exposed for sale, including endangered pangolins, marine turtles, and leopards. 82 cases of bushmeat hunting involving 20 species of wildlife were recorded in the Luengue-Luiana and Mavinga NPs in July-October 2016. Fulton et al. (2016) believe that prey depletion due to uncontrolled bushmeat hunting is the main reason of very low numbers of lion (only 10-30 individuals) in the Luengue-Luiana and Mavinga NPs. High levels of evidence of poaching for bushmeat were found in the survey of Mupa NP in August-September 2016. Bushmeat poaching both for subsistence and commerce was indicated as one of the main threats for other PAs in Angola, including Bicuar, Cameia, Cangandala, Kissama, Maiombe NPs, and Luando Reserve. Intensive bushmeat hunting for commercial purposes was recorded in Bie, Moxico, and Cuando Cubango provinces by the National Geographic Okavango Wilderness Project (2017). The authors underlined that wide spread of shotguns and motorcycles among local communities made the bushmeat hunting and trade much more intensive with increasing number of remote wild areas available for hunting last years. During the PPG mission in June 2018, we could observe bushmeat exposed for selling along the roads and at the small markets in Cuanza Norte and Malanje Provinces. Some information sources call Angola the biggest bushmeat market in Africa where domestic consumption of the bushmeat is traditional from the time of the civil war. Bush meat market in Angola is driven by increasing demand from growing populations of Angola’s cities. Given average rate of bushmeat consumption in Africa of 0.152 kg/person/day, only Luanda with its population of 2,487,000 potentially consumes 378 tons of bushmeat daily! Bushmeat poaching is a serious threat for two selected project areas: Maiombe National Park (NP) and Luando Strict Nature Reserve (SNR) (see details in the Strategy section).

- Human-Wildlife Conflicts. Human-wildlife conflicts (HWC) are very common in Angola, including protected areas. Key types of the conflicts are: crop damage by elephants and hippos; damage of food stores by elephants; killing of livestock by crocodiles, lions, hyenas, and leopards; killing of people by elephants, crocodiles, lions, and hippos,. Thus, in the former Mucusso Coutada (hunting reserve), now part of Luiana-Luengue National Park in Kuando Kubango province, over 600 HWC incidences were recorded between 2008 and 2012 involving various wildlife. Key drivers of the conflict are increasing human population and livestock number; encroachment of settlements, agriculture and pastures in wildlife habitat; blocking access to rivers and other water points by crop field and settlements ,. In Cuanza Norte Province, elephants almost annually destroy crops around Cerca, Cambambe, and Massangano villlges driving local people to give up farming and switch to bushmeat poaching. HECs have been regularly reported in all villages inside the Maiombe NP and around it, with two main hotspots – Comboliambo and Buco-Zau areas. Main crops damaged in the NP are bananas, cassava, sweet potato, and corn, especially on small plantations located in the forest. In Luando Strict Nature Reserve hippos are the key conflict animals coming to feed on the croplands located near Kwanza River. In 2014-2018, two local people were killed and several were injured by hippos.

- Degradation of wildlife habitat. Wildlife habitat degradation in Angola is caused by unsustainable logging, deliberate and wild fires, expansion of human settlements and agriculture that is based mostly on the unsustainable slash and burn practice, unsustainable mining, and other land-uses, such as overgrazing of livestock. In 2000, the total forest cover in Angola was estimated in ~52.6 mln ha (or 42% of national territory). In 2000-2016, the country lost 2.5 mln ha (4.8%) of its tree cover. Thus, the average deforestation rate in Angola is 167,700 ha/year (or 0.32%/year) for that period. It should be noticed that the average deforestation rate in the country increased 2.6-fold in the last 15 years: from 83,700 ha/year in 2001-2005 to 221,200 ha/year in 2012-2016. Charcoal production is one of the main drivers of deforestation: more than 60% of Angola’s population rely on firewood and charcoal as a source of energy for heating and cooking needs. Annual demand for firewood and charcoal in Angola is estimated at 6 mln m³/year. Annual national charcoal production in Angola increased by 168% in 2001-2016: from 212,700 to 358,427 tons. Forests are also cleared by expanding slash and burn agricultural practices and illegal logging for timber trade. Logging for clearing area for agriculture and commerce (timber and charcoal) was recorded in many protected areas of Angola, such as Bicuar, Cameia, Cangandala, Kissama, Luengue-Luiana, Mavinga, Mupa, Maiombe, Luando NPs. Maiombe NP and Luando SNR lost 2.6% (5,224 ha) and 2.7% (25,287 ha) of the forest cover respectively in 2000-2017. In both project sites, the deforestation rate increased 3-5 fold last 17 years (Fig. 1).

| - Maiombe NP | - Luando SNR |
| --- | --- |

Figure 1. Annual loss of tree cover in Maiombe NP and Luando SNR in 2000-2017 (University of Maryland 2018. Global Forest Change 2000–2017).

- Anthropogenic fires are another serious cause of habitat degradation and deforestation in Angola. Fire is intensively used to clear forested land for agriculture, renovate grass growth for cattle, and drive animals to trap lines during bushmeat hunting,. During dry seasons fires can destroy large areas of forest, especially in the escarpment forests and Afromontane formations of western Angola. Fire is a threat for almost all protected areas in the country. Even fire-adapted miombo woodlands can be significantly degraded by annual fires set by local communities: while fire is a natural part of the ecosystem, young trees need at least a five-year period without fire disturbance to become robust and tall enough to grow into adult trees. Annual frequency of forest fires in Angola is very high with 314,000-344,000 annual fire incidents recorded by the MODIS sensor in 2012-2017. Human-induced fires are relatively rare in wet tropical forests of Maiombe NP with only 4-12 incidents recorded annually, but have a very significant impact on miombo woodland ecosystems in Luando Reserve with average annual rate of 5,100 fire incidents in 2013-2017.

- Current diamond mining practices are a serious threat to riparian forests and aquatic ecosystems in central and eastern Angola. At the industrial scale, general practice is to completely reroute rivers and then to dredge all alluvium within the riverbed and in adjacent alluvial deposits, to a depth that depends on the balance of extraction cost versus projected diamond recovery. All vegetation at the mining site is destroyed in the mining process, and vegetation surrounding the mining site is often significantly damaged as well.

- Overgrazing is a serious problem for arid areas mainly in Angola’s south, leading to desertification and severe degradation of savannahs as wildlife habitat. However, expansion of livestock pastures significantly contributes to deforestation and degradation of miombo ecosystems in other parts of the country.

- All the threats above contribute to decline of Angola’s wildlife populations. The summary of the direct threats and their drivers (immediate and root causes) are shown in the Table 1 and Fig. 2.

Table 1. Direct threats for wildlife in Angola and their drivers.

| Direct Threats | Threat Level | Drivers (causes) |
| --- | --- | --- |
| Poaching for high value species involved in international WT (elephants, great apes, African gray parrots, and pangolins) | Very High | Poaching and IWT as a response to high demand for ivory and other wildlife products mainly from China, Thailand, and Vietnam. Angola is considered as an important transit country for illegal ivory trafficking from Western Africa to the East Asia due to low level of law enforcement and direct flights to China. Until recently Angola had the largest open domestic ivory market in Africa |
| Poaching for bushmeat: commercial and subsistence | Very High | 40.5% of Angola’s population lives below poverty line and about 60% depend on bushmeat among main sources of protein and income. Consumption of bushmeat has been traditional and increased since civil war times. However, most significant bushmeat poaching is for commercial purposes for sale in the main cities, including among the financial elite. High demand for bushmeat from growing cities. Low level of law enforcement to control illegal trade of bushmeat. |
| Human-wildlife conflicts associated with potential retaliatory killing of wildlife | High | Increase of human-wildlife conflicts due to expansion of human activities in the wildlife habitat as a result of increasing human population, absence of land use planning and implementation of land use regulations associated with increasing area of agriculture, decreasing access to water sources, and increasing number of livestock in the habitat, combined with post-war increase of wildlife in some areas, such as Luengue-Luiana NP. Lack of HWC management programmes in the country. |
| Unsustainable logging, including slash and burn agriculture, unsustainable and insufficiently controlled logging concessions and illegal commercial and subsistence logging | High | Degradation of woodlands and forests in the country is caused by expansion of slash and burn agriculture, timber harvesting and increasing firewood and charcoal production. More than 60% of Angola’s population rely on firewood and charcoal as a source of energy for heating and cooking needs |
| Anthropogenic Fires | Very High | The vast majority of forest fires is human-caused through slash and burn agriculture, renovation of grass growth for livestock, and bushmeat hunting. The system of fire management is almost non-existent in the country. |
| Expansion of agriculture, settlements, unsustainable land-uses, and development works | Very High | Increasing human population, demand for agricultural products, associated with lack of land use planning and control from government agencies (especially in the southern part of the elephant range), as well as lack of integrated land-use planning with conservation mainstreaming at the provincial and national levels. |
| Overgrazing | Medium | Increasing number of livestock, driven by increasing population. Expansion of pastures into wildlife habitat associated with deforestation. |
| Unsustainable mining | Medium | High international demand for diamonds, gold, oil, and other minerals. Diamonds contribute significant part of GDP and national export. Lack of habitat restoration practices after mining. |

- Relevance of the development challenge to national development priorities. The Angolan government recognizes protection of environment, restoration of wildlife and combating illegal wildlife trade as key priorities for the national development. The government of Angola signed and ratified the Convention on Biological Diversity in 1997 and became a member of the Conference of the Parties in 1998. In 2006, the country developed the National Biodiversity Strategy and Action Plan 2007-2012 with the overall objective to incorporate measures for the conservation and sustainable use of biological diversity and the fair and equitable distribution of biological resources in favor of all Angolans into development policies and programmes. In 2010, Angola developed and adopted the National Policy on Forests, Wildlife and Conservation areas providing necessary policy framework for wildlife conservation and sustainable forest management. In 2013, Angola signed and ratified CITES and became the 179th party of the Convention. The 16th Conference of the Parties to CITES held in Bangkok in 2013 classified Angola among the countries “of importance to watch" in connection with the country’s domestic ivory market, its significant role in ivory trafficking and limited information on poaching and illegal wildlife trade inside the country. In 2015, Angola developed the National Ivory Action Plan (NIAP) 2015-2016 in response to the request of the 65th meeting of the CITES Standing Committee held in Geneva in July 2014. To support national implementation of CITES, the country developed the Executive Decree No. 469/15 prohibiting hunting activity and logging within the country of all protected species of wild fauna and flora. In the framework of the NIAP, the country closed its open domestic ivory market in 2016, adopted the Law No. 6/17 on Forest and Wildlife, drafted a new PA Law based on revision of colonial Decree No. 40.040/1955, started update of the Criminal Code to harmonize it with environmental legislation, conducted inventories of national ivory stockpiles for 1,244 kg of unworked and worked ivory, and established the Inter-ministerial Commission Against Environmental Crimes and related Wild Fauna and Flora. In 2016, Angola established the 31st of January Environmental Polytechnic Institute (Wildlife School) in Menongue (Cuando-Cubango province) to serve as a national and regional facility for ranger training on effective PA management and strategies for reducing IWT and poaching. In 2016, Angola joined the Elephant Protection Initiative (EPI) and signed a MOU with the Stop Ivory on collaboration in fight against the illegal trade of ivory. In 2015, the General Prosecutor’s Office of Angola in collaboration with the African Prosecutors Association (APA) organized the “International Conference on Poaching and its Harmful Effects for the Continent: Efficient Measures to Hold Perpetrators Accountable” in Menongue, Cuando-Cubango Province.

- The multi-agency ECU was established in 2015 under the leadership of MINAMB and with the participation of the following entities: the Ministry of Interior, Ministry of Defense, Ministry of Agriculture and Forest, Ministry of Fisheries, National Department of Customs, Ministry of Transport, Ministry of Petroleum, Ministry of Geology and Mining, and Ministry of Education. The defined objectives of the Unit are:  (a) to coordinate and lead the implementation of legislation for biodiversity conservation in Angola, in particular the legislation to combat wildlife crime; (b) to establish intelligence and data collection and analysis capacity and to develop an effective database to support and monitor wildlife crime enforcement; and (c) to coordinate the intelligence, enforcement and monitoring of wildlife crime in Angola, through multi-sectorial collaboration with all relevant entities in the country (the Armed Forces, National Police, Border Police, Customs, Immigration Services, Intelligence Services, IDF, Inspection Department of the Ministry of Fisheries, among others), with INBAC and the PAs staff, with regional homologous agencies, and with relevant international agencies. Once fully established, the Unit will serve as the main agency in Angola responsible for wildlife crime action, as a semi-autonomous agency, through multi-sectorial collaboration, including the coordination of the effective operation of the wildlife crime multi-sectorial task force. ,

Table 2. Angola’s Protected Area estate

| # | Name | Area (km2) | Year Established | Province |
| --- | --- | --- | --- | --- |
| National Parks |  |  |  |  |
| 1 | Iona | 15,196 | 1957 | Namibe |
| 2 | Cameia | 14,688 | 1957 | Moxico |
| 3 | Kissama | 9,227 | 1957 | Luanda |
| 4 | Bicuar | 6,748 | 1964 | Huíla |
| 5 | Mupa | 6,039 | 1964 | Cunene-Huila |
| 6 | Cangandala | 637 | 1970 | Malanje |
| 7 | Maiombe | 2,074 | 2011 | Cabinda |
| 8 | Lungué- Luiana | 22,720 | 2011 | Kuando-Kubango |
| 9 | Mavinga | ~40,000 | 2011 | Kuando-Kubango |
| Strict Nature Reserves |  |  |  |  |
| 10 | Luando | 9,930 | 1957 | Malanje/Bié |
| 11 | Ilhéu dos Pássaros | 1.5 | 1973 | Luanda |
| Partial Reserves |  |  |  |  |
| 12 | Namibe | 4,642 | 1963 | Namibe |
| 13 | Búfalo | 405 | 1971 | Benguela |
| Regional Nature Parks |  |  |  |  |
| 14 | Chimalavera | 102 | 1974 | Benguela |
|  | TOTAL | 132,410 |  |  |

- Since 2000-s, Angola’s governments has attempted to rehabilitate and expand the national Protected Areas (PAs) system that was destroyed by years of the civil war. Thus, three new National Parks (Maiombe, Luengué-Luiana and Mavinga) (the first since independence) were established in 2011,. Currently the national network includes 14 PAs with total area of 132,410 km² covering 11% of the country (Table 2). Rehabilitation and extension of PA estate for wildlife restoration in Angola are key objectives of the Angola’s National Environment Management Plan (NEMP 2009), National Biodiversity Strategy and Action Plan (NBSAP 2007-2012), Strategic Plan of the National Network of Conservation Areas of Angola (PLERNACA 2011), and the Angolan Strategic Plan for Protected Areas (PESAP) 2018-2028. The PESAP foresees extension of the national PA system to cover 17% of the national area and establishment of marine PAs. Management and oversight of the PA estate is the prime responsibility of MINAMB’s National Institute for Biodiversity and Protected Areas (INBAC, established in 2011) in collaboration with forestry guards deployed by the National Forest Development Institute (IDF) of the Ministry of Agriculture and Forests, which is responsible for the management of Angola’s forests. Total annual PA budget allocation of Angola increased from $1.5 mln in 2011 to $9 mln in 2016. Total staff of 8 National Parks increased from zero at the beginning of 2000 up to 350 in 2018 (90% are rangers), and provided with basic training, infrastructure, and equipment with support from the UNDP and GEF. Two national protected areas – Cangandala NP and Luando Strict Nature Reserve – have been involved in the Protection and Rehabilitation of Giant Sable Antelope (Hippotragus niger variani) project with support from the Kissama Foundation. In 2018, the Executive Committee was planning to follow up and reinforce the implementation of measures for conservation of the Giant Sable Antelope.

- Relevance of the development challenge to global environment issues. Despite the relatively small size of Angola’s savanna elephant population, it represents a part of a big transboundary elephant meta-population freely moving between Namibia, Botswana, Angola, Zambia and Zimbabwe. To promote tourism and conserve natural resources regionally, Angola, Botswana, Namibia, Zambia, and Zimbabwe have established the Kavango-Zambezi Transfrontier Conservation Area (KAZA TFCA) which link protected areas and communal lands in the five countries. This initiative is potentially important for elephants because it protects core elephant habitats and movement corridors between the countries. For elephants, southeast Angola is a cornerstone of the KAZA TFCA, providing a key linkage between Namibia and Zambia. Decline of the southeast Angola population could seriously reduce connectivity between elephant subpopulations in the western half of the KAZA TFCA. Moreover, elephant poaching in all the KAZA countries is interlinked, caused by the same drivers, and probably controlled by the same actors (international syndicates). Stricter control measures in neighboring countries may well be among the main causes for increased elephant poaching in Angola and require matching improved measures.

- Another transboundary area – Mayombe Forest TFCA (at the border of Cabinda Province, which touches Democratic Republic of Congo, Republic of Congo, and Gabon) is listed among emerging SADC TFCAs and has high importance for conservation of tropical rain forests of the Congo Basin with a total area 36,000 km² and transboundary populations of such endangered species as central chimpanzee, western lowland gorilla, and forest elephant. The MoU on the Mayombe Transboundary Conservation Initiative was signed by governments of Angola, Democratic Republic of Congo, and Republic of Congo in 2009 in the framework of the UNDP-NORAD project, and the Mayombe Transfrontier Initiative's Strategic Plan was adopted by all four countries in 2013. Later in 2013, Gabon joined the Mayombe transboundary initiative. The proposed Transboundary Protected Area will include following PAs in Mayombe National Park in Angola, the Luki National Park in the DRC and the Dimonika Biosphere Reserve, Conkouati-Douli National Park and Tchimpounga National Reserve in the Republic of Congo, and Myumba National Park in Gabon.

- Two more SADC TFCAs involving Angola are the Iona Skeleton Coast TFCA (emerging) at the border of Angola and Namibia and the Liuwa Plains-Mussuma TFCA (conceptual) between Angola and Zambia. There is a total of four large TFCAs involving Angola’s territory demonstrate the country’s regional importance for conservation of wildlife of Western and Southern Africa, as well as the political will to collaborate with the neighboring countries for biodiversity conservation.

- Angola is the only home for critically endangered Giant Sable Antelope, with probably no more than 150-200 individuals left in the wild. Thus, Angola has a global responsibility for protection and restoration of this unique species as well for many other animal populations dramatically declining due to high level of poaching and bushmeat trade in the country. As was mentioned above, Angola is considered to have the largest bushmeat market in Africa that involves illegal wildlife trafficking between Angola and adjacent countries of Western, Central and Southern Africa.

- Last but not least, the global importance of the country is underlined by Angola’s significant involvement in illegal ivory trafficking between Africa and East Asia: Angola was rated among top 10 countries on the number of incidents involving illegal ivory trafficking in 2009-2016. Thus, Angola has to play an important role to interrupt this inter-continental illegal trafficking chain.

- Relevance of the challenge to the Sustainable Development Goals (SDGs). Current UNDP assistance to Angola covers various strategic areas: building viable policies, mechanisms, processes and institutional environment for the fight against corruption (ongoing project ‘Strengthening legality in Economic Governance 2018-2020); alignment of national legal framework with international law on human rights and strengthening the capacity of justice and human rights institutions at national and local levels (ongoing project ‘Enhancement Human Rights in Angola 2018-2021’); building national electoral capacity (ongoing project ‘Technical Assistance for Angola’s Elections 2017-2019’); support for the institutionalization and functioning of elected local governments (ongoing project ‘Assistance to Local Governance 2018-2022); gender mainstreaming in policy and sectoral programming, gender statistics for sensitive planning and budgeting, and capacity building for gender institutions at national and provincial levels (ongoing project ‘Gender Mainstreaming 2018-2021); women’s political, economic and social empowerment at community level (ongoing project ‘Empowerment of Angolan Women 2015-2018); building civil society capacity on public policy and participation in democratic processes, and building bridges for government-civil society engagement (cross cutting to all projects and new incoming project ‘Civil Society, Youth and Participatory Governance 2019-2022’).

- Angola is among the more than 150 countries that at the United Nations Sustainable Development Summit on 25 September 2015, adopted the new 2030 Agenda for Sustainable Development, including the Sustainable Development Goals (SDGs). The Angolan Government has been taking the lead in acknowledging publicly the country commitment to the SDGs, starting with a public workshop in Luanda in December of 2015. At the same time, under the lead of the Ministry of Planning, a Rapid Assessment Analysis (RIA) was conducted to assess the degree in which the SDGs are mainstream into the ongoing National Plan. However, the development challenges described above (poaching, IWT, and wildlife habitat degradation, including deforestation) are significant threats towards the attainment of the country’s SDGs such as Goal 1 No Poverty and Goal 2 Zero Hunger (impeded by continuous degradation of natural resources (e.g., bushmeat species and iconic wildlife, miombo forests, etc.) and opportunities for their sustainable use by local communities); Goal 5 Gender Equality, Goal 8 Decent Work and Economic Growth, and Goal 10 Reduced Inequalities (affected by decreasing opportunities for women and youth for employment in wildlife tourism sector and sustainable wildlife and forest management as a result of wildlife and forest degradation);  Goal 13 Climate Action and Goal 15 Life on Land (via declining  iconic wildlife species and degradation of the entire biodiversity and ecosystems affecting adaptation potential of natural complexes and ecosystem services) as well as Goal 16 Peace, Justice and Strong Institutions (impacted by lack of effective governance and NRM planning as well as by widespread poaching and IWT).

- Relevance of the development challenge to local community issues. Approximately 60% of Angola’s population highly depend on natural resources for subsistence and income. Local communities traditionally use a wide set of products provided by forests and wildlife, such as bushmeat, fish, insects, medical plants, firewood, fruits, leaves, tubers, roots, nuts, mushrooms, honey, fodder for livestock, grass and fibre for construction, resins, tannins, latex, bark and cover of houses and raw material for the manufacture of articles and pieces handicrafts. Despite high involvement of local communities in illegal bushmeat and fish trade, current uncontrolled and illegal situation benefits mainly high-level IWT traders and criminal syndicates depleting wildlife habitats around communities. This unsustainable situation leads to inevitable wildlife and habitat degradation and lost opportunities for development of community-based tourism, sustainable forest, and wildlife management. Poaching and IWT contribute to the insecurity of local communities and growing gender inequality and exclusion of vulnerable groups, such as nomadic and semi-nomadic indigenous tribes. The main problem is that local communities do not have any ownership of the land, wildlife, forest and other natural resources and have low interest in their sustainable management. Therefore, it is important to advocate for a shift to a joint participatory approach to conservation and community-based natural resource management around PAs as it can potentially benefit local communities. It offers immense opportunities for empowering men and women of the most forest-dependent communities to gain equal access to and control over the use, sustainable management and ownership of common-pool of wildlife and forest resources, which ultimately can improve their well-being. Moreover, it is important to conduct a detailed analysis of the different drivers of different actor categories in poaching and IWT, in order to develop adequate strategies that address differently the different drivers and actors. For example, improved intelligence and enforcement capacity through multi-sectorial and international collaboration is a main strategy needed to combat the IWT syndicates; inclusion, in-depth understanding and mutually satisfactory addressing of issues, would be the main strategy to engage local communities in reducing poaching and other unsustainable practice.

- Barriers. Key barriers to adequately address poaching, IWT and wildlife habitat degradation in Angola revolve around the insufficient wildlife policy and IWT legal and institutional framework; low capacity and budget allocation of the Government and key agencies to implement effective law enforcement in the situation of widespread poaching and illegal bushmeat trade; and lack of community involvement in wildlife, forest and PA management in any form that can develop ownership and community rights on sustainable consumption of the natural resources, including wildlife. The barriers can be further described as the following:

- Insufficient wildlife policy and IWT legal framework. Analysis of wildlife legislation framework in Angola implemented by the Stop Ivory and Wildlife Impact as well as the ICCWC IF assessment of wildlife crime enforcement capacity in Angola in 2018 demonstrated that certain wildlife management and IWT related legislation is outdated and needs to be updated in accordance with international standards. Weak policy and regulatory frameworks relating to wildlife and IWT provide limited tools to manage wildlife sustainably with participation of local communities as well as monitor and combat IWT, including surveillance, investigation, prosecution, and conviction of wildlife criminals. Thus, the country still lacks an National Wildlife Management and Wildlife Crime Enforcement Strategy to guide participatory and sustainable wildlife management, national wildlife crime enforcement, effective management of human-wildlife conflicts, and finally to bring Angola’s wildlife policies and legislation in accordance with legislative policies of adjacent countries. The country still has low penalties for wildlife crimes: maximum 3 years of imprisonment and mainly financial penalties; thus, they do not fall within the definition of “serious crime” under the United Nations’ Office for Drugs and Crime’s Organized Crime Convention. No specific guidelines for prosecuting wildlife related crimes have been developed for the country’s prosecutors and judiciary. No legislation exists in the country to support Community-Based Wildlife and Natural Resources Management (CBWM and CBNRM) and establish Local Councils for Protection of Forest and Wildlife and Community Management Areas defined in the National Policy on Forests, Wildlife and Conservation areas. Despite the country’s participation in the Elephant Protection Initiative, Angola still has no National Elephant Management Plan (NEAP) and updated National Ivory Action Plan (NIAP). Angola has four TFCAs intersecting with the country territory, but only one KAZA TFCA has been formally established via an international treaty. No international protocol targeting transboundary wildlife crime law enforcement has been developed and signed by Angola, DRC, and the Republic of the Congo to effectively prosecute wildlife trafficking between the countries, including ivory. One of the project areas – Luando Strict Nature Reserve – does not fall in the strict reserve category any more due to presence of human communities in the protected area and urgently needs adjustment of the legal status and protective regime.

- Insufficient capacity of national wildlife agencies and PAs to address poaching, IWT, and habitat degradation issues. Angola made significant progress in strengthening its national wildlife law enforcement agencies and PAs in 2000-2017. Thus, the National Institute for Biodiversity and Protected Areas (INBAC) was established in 2011 with a mandate to implement the conservation policies under the Ministry of the Environment. INBAC has been strengthened in recent years to manage national PA system notably through the efforts of previous GEF projects; however, this has not included the capacity to effectively suppress poaching, IWT, and manage HWC. Currently INBAC has only 15 staff in Luanda, almost without equipment to target wildlife crime law enforcement. Current capacity of the INBAC to control wildlife crime in Angola was evaluated as only 41% of the maximal possible. The multi-agency Environmental Crime Unit was established at the MINAMB in 2015 to investigate and prosecute wildlife crime, including illegal ivory trade and trafficking. However, the Unit still has very limited staff (15 officers total, including 7 in Luanda and 8 in the provinces) and low investigation, surveillance, and technical capacity to combat wildlife crime. Some of the ECU staff has been trained in wildlife crime investigation, intelligence, and forensics by Stop Ivory and wildlife law enforcement schools in Botswana and Gabon, but the system of regular trainings for the ECU staff is still missing. The ECU still has very limited equipment for law enforcement, including only two vehicles, and initial network of informers that includes 21 people only. Given the plans of the ECU to increase its staff up to 45 officers in 2018 and ultimately up to 200 of staff, the Unit will badly need transportation, equipment as well as regular system of trainings for the staff. The Inter-ministerial Commission Against Environmental Crimes and related Wild Fauna and Flora was established, but the commission is still of low effectiveness and needs technical capacitating and strengthened collaboration among their defined member Ministries and agencies (e.g. the Commission has had only a few meetings after its establishment and never met after August 2017).

- In Angola, both the prosecution success rate and the nature of the penalties applied to wildlife criminals are still insufficient to adequately deter offenders, especially repeat offenders. This problem can in part be attributed to lack of awareness on the part of police prosecutors and the judiciary of the serious impact that poaching is having on wildlife populations, as well as ineffective legislative instruments applied to wildlife crime offenders. As a result, these crimes are often dismissed entirely, or only minor penalties are applied. The fact that wildlife poaching in the Angola’s PA is a relatively low risk crime represents a major vulnerability to the PA’s law enforcement efforts, and attracts regional and international syndicates to operate in Angola. The system of regular training for investigators, prosecutors, and judiciary on wildlife crime issues is completely missing in Angola.

- The number of park rangers and other environmental personnel has been steadily increasing in recent years up to 350 in 9 Protected Areas, but given large PA areas this number is still very low for effective law enforcement (less than 3 rangers per 1000 km²) and very far from optimal ratio of 20-30 rangers per 1000 km². Some PAs like Luando SPR and Cameia and Mupa NPs have no permanent ranger staff at all. The majority of the PA rangers need field equipment and training in patrolling and operations, evidence gathering and data recording to effectively enforce the law, HWC and fire management. Some of the PAs operate through some degree of cooperation with the National Police, the Army (FAA) and the IDF, as well as with the Provincial and Municipal authorities, and traditional authorities of the local communities. However, this cooperation needs to be significantly strengthened and better coordinated at a system level with clear roles and accountability. Insufficient intelligence-led law enforcement is restraining the ability of the PA rangers and law enforcement officers to better target efforts and resources. With better intelligence of the type and location of criminal activity, efforts may be targeted at specific geographical areas, with appropriate resources and support allocated based on the intelligence findings, thereby greatly increasing efficiency. While occasional training programs for PA rangers and other law enforcement staff (police and judiciary) from outside organizations have been contracted, this has been insufficient to meet the national demand. The government has responded to this situation through the construction of a ranger training school in Menongue in Cuando-Cubango province (created by Decree # 132 in 2015), but this school is not yet operational and does not have developed and comprehensive training programmes. Angola’s PAs do not have comprehensive results-based management plans (except of Iona NP) to provide a strategic basis for their development as effective conservation and wildlife management areas providing sustainable benefits to local communities. However, development of the basic management plans for Cameia NP, Maiombe NP, Cangandala NP, Bicuar NP and Kissama NP were launched in the framework of other UNDP-GEF projects (under GEF 4 and 5 support).

- Another critical problem is the lack of adequate patrol rations that can be easily and rapidly prepared in the field (e.g. military-style dry rations or other forms of ready-to-eat food). In terms of patrol-to-base communications, no adequate infrastructure has been put in place to enable effective VHF radio communications between patrol groups and PA bases with exception of Kissama, Iona, Cangandala and Bicuar NPs. Patrol outposts are another aspect of PA infrastructure, which falls short of current law enforcement needs. Many outposts are in urgent need of basic maintenance and repair, and many should be constructed in light of intensive poaching.

- Lack of community involvement in wildlife, forest and PA management. A participatory approach to conservation (involving local communities) has been a key strategy for biodiversity conservation in Africa. There is a need to recognize the significant role of community involvement in species and habitat protection in Angola. Communities living in and around PAs do not receive any significant benefits from conservation but suffer from HWCs, and almost a complete lack of social services, combined with difficult access to markets, which in turn has not fostered attitudes that are supportive of conservation practices. No Community-Based Wildlife and Natural Resources Management (CBWM and CBNRM) Strategies, Local Councils for Protection of Forest and Wildlife, and Community Management Areas defined in the National Policy on Forests, Wildlife and Conservation areas have been established in Angola. Many local people are involved in unsustainable bushmeat hunting and trade, ineffective slash and burn agriculture, and devastating logging and burning of forests for short-term needs, including increasing charcoal production.

- Environmental degradation is an issue of major concern attributed to lack of public awareness about the need for the conservation of environment as well as lack of economic benefits for sustainable use of natural resources. Combined with an ever-increasing population (nationally rate of increase is 3.52% annually) and inevitable higher demand for settlements, agriculture, infrastructure developments and increasing fuel-wood collection, wildlife loss and land degradation are accelerating and are compounded by climate change. These threats are accelerated by low technical know-how of local communities and inadequate extension services to promote sustainable forestry, wildlife use, and farming practices. In addition, as a result of poor planning and implementation, human settlements and infrastructure developments also affect traditional wildlife migratory routes and key wildlife habitat and lead to human-wildlife conflict as the wildlife destroys crops and infrastructure and kills livestock and people. Efforts to enhance livelihoods by promoting community-centered initiatives that support effective co-management of wildlife and their habitats, restoration and rehabilitation of degraded landscapes, reduction of wildlife crime, and sustainable local income generation are essential. Currently insufficient implementation of district planning results in multiple unplanned settlements within wildlife areas and PAs, which are leading to habitat fragmentation, human-wildlife conflicts, massive human-induced fires, and illegal wildlife off-take. Law enforcement officials are concerned about the increasing level of cooperation between international wildlife crime syndicates and local poachers, who are shifting from subsistence poaching to targeting commercially valuable flagship species such as elephants and bushmeat species under influence of criminal syndicates and pressure from human-wildlife conflicts. Key reasons for this trend include the increased awareness among local community members of the value of ivory and other illegally traded wildlife products on the black market, very low level of the law enforcement, the porous border with neighboring countries, and the increasing ease of cross-border telecommunications. This is a particularly dangerous mix in the context of widespread community unemployment and poverty that has been exacerbated by recent economic crises in Angola due to sharp drop of oil prices.

- The lack of appreciation of the value/real benefit of wildlife, forests and woodlands, lack of mechanisms to incentivize sustainable forest and wildlife management and lack of livelihood alternatives for forest and wildlife dependent communities represent major barriers to sustainable wildlife and forest management in Angola. Local population has very low resilience to flooding and droughts, low capacity on HWC management, and almost lack of capacity for sustainable wildlife, forest, and land management.

- In addition, the lack of awareness on devastating effect of poaching and IWT and insufficient involvement of key stakeholders (local governments, NGOs and private sector) in wildlife conservation is widespread in Angola. Wildlife in Angola is still largely managed by government agencies. Local communities, local government bodies, national and international NGOs, the private sector and civil society have almost no engagement in wildlife management.

Figure 2. Direct threats to Angola’s wildlife, habitat and communities; root causes leading to the threats; barriers for sustainable solution; and suggested UNDP/GEF strategies to address the challenges.

# Strategy

- The project Objective is to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola. To achieve this Objective, the project will implement four key strategies (components) (see Fig. 2 above):

- Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime. Under Component 1, the project will review and update key national policies and legislation (based on the Stop Ivory and Wildlife Impact recommendations) related to wildlife management, HWC, wildlife crime, PA protective regime, and community engagement in natural resources management and ownership to provide necessary foundation for effective wildlife crime law enforcement and wildlife management. The Environmental Crime Unit will be provided with necessary equipment and mentoring to improve their capacity to investigate and prosecute wildlife crime, based on effective local interventions to reduce IWT and poaching. Systematic training programmes on wildlife crime issues will be developed and provided to the National Police, Customs, prosecutors, and judiciary. National Environmental Polytechnic Institute (Wildlife School) for PA rangers in Menongue will be supported with necessary equipment and training programmes to ensure systematic capacity building for the national PA staff to fight poaching and manage wildlife and habitats. All training and mentoring programmes for law enforcement staff will incorporate strong component on human rights. This Component will address two barriers identified in the Development Challenge section: Insufficient wildlife policy and IWT legal framework and Insufficient capacity of national wildlife agencies and PAs to address poaching, IWT, and habitat degradation issues.

- Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation. Under Component 2, the project will make significant investments to increase law enforcement and managerial capacity as well as strengthen inter-agency collaboration to fight wildlife crime in two project areas – Maiombe NP and Luando SNR. The project will update and support implementation of two local wildlife crime inter-agency collaboration agreements in the form of inter-agency anti-poaching brigades, consisted from representatives of the PAs, National Police, IDF and military to organize joint law enforcement operations and effectively prosecute poachers and wildlife traffickers in the project areas. Also, the project will update the initial Management Plans for Maiombe NP and Luando SNR with clear results-based implementation plans for the nearest five-ten years developed and realized with participation of local communities living in the PAs. Necessary equipment and training will be provided to the PA staff to increase their capacity to combat wildlife crime and manage PAs. All training and mentoring programmes for law enforcement staff will incorporate strong component on human rights. This component will address Insufficient capacity of national wildlife agencies and PAs to address poaching, IWT, and habitat degradation issues barrier identified in the Development Challenge section.

- Component 3. Engaging local communities in sustainable wildlife, forest and PA management. Based on the experience of community-based and social initiatives developed by the FAS, ADPP, Gremio ABC, and FAO, and other similar initiatives in Africa the project will develop and implement sustainable livelihood pilot projects for local communities in the project areas – Maiombe NP and Luando SNR – with key focus on sustainable use of non-timber forest products, conservation agriculture and agro-forestry practice, sustainable fisheries, HWC management, participatory PA management, and potentially eco-tourism. The key objective of the Component 3 is to increase community participation in the natural resource and PA management in the project areas. In parallel with the sustainable livelihood activities, the project will reinforce on-going awareness and education campaign with targeted pilot programmes in the project areas and at national level to decrease bushmeat consumption and increase public support to wildlife conservation. This Component will target the barrier Lack of community involvement in wildlife, forest, and PA management.

- Component 4. Knowledge Management, M&E and Gender Mainstreaming. This Component will ensure effective lesson learning from implementation of Components 1-3, participatory M&E approach, and gender mainstreaming. Lessons learned from the project will be used to improve implementation of the Components 1-3 via adaptive management and also be shared with other national and international projects, including GWP, using South-South Cooperation mechanism and other approaches. Under this Component, the project will establish an effective Grievance Redress Mechanism (GRM) to inform and guide project implementation in socially acceptable and beneficial for local communities’ way. The Component will contribute to removal of all three barriers indicated in the Development Challenge section via increasing of the effectiveness of the project strategies through learning and adaptive management, and dissemination of successful practices in Angola for further implications.

- All four Components are designed as interconnected strategies to target key threats for wildlife (see Fig. 2 and 3), habitats and communities in the project areas. All project components (especially Components 1 and 2) will directly support the implementation of the Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES), arguably one of the most important global instruments for addressing illegal wildlife trade. The CITES Strategic Vision 2008-2020 emphasizes the importance of national commitment to implementation of the Convention and its principles. The project will support compliance through development of national and local capacity to effectively address wildlife crime via legislative, capacity building, and direct law enforcement initiatives. The project will directly contribute to the implementation of the resolutions of the CITES Conf. 10.10 on trade in elephant specimens (last updated at CoP17), Conf. 17.6 on preventing, detecting and countering corruption (adopted at CoP17), CoP17 Decision related to the use of ICCWC tools, and CoP17 decisions related to national laws for implementation of CITES and achievement of objectives of the CITES African Elephant Action Plan 2010 .

Alignment of the project with the Global Wildlife Program Theory of Change

- To respond to the growing wildlife crisis and international call for action, the Global Environment Facility (GEF) in June 2015 launched the Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development, often called the Global Wildlife Program (GWP). Led by the World Bank, the GWP is a US$131 million grant program designed to address wildlife crime across 19 countries in Africa and Asia. The GWP serves as a platform for international coordination, knowledge exchange, and delivering action on the ground. The GWP builds and strengthens partnerships by supporting collaboration amongst national projects, captures and disseminates lessons learned, and coordinates with implementing agencies and international donors to combat IWT globally. National projects within the GWP form an integral part of a community of practice that promotes the sharing of best practices and technical resources. While this UNDP-GEF project in Angola is not a national project under the GWP, it was designed to contribute to the GWP as much as possible. During project execution, Angola will share its lessons with GWP projects and will have access to the GWP documentation and materials produced during project implementations, virtual- and in-person meetings of relevance to the activities to be carried out in country, especially those on IWT control, PA management, CBWM, and biodiversity conservation mainstreaming in production sector. Angola is committed to engaging with GWP partners in Africa and Asia on joint efforts that will help with the project implementation, including issues related to human wildlife conflict and other technical areas.

- The project is aligned with GWP Theory of Change and will contribute significantly to the expected GWP Outcomes and Targets via implementation of its four Components (Strategies) (Table 3).

Table 3. Alignment of the project strategies with GWP Components, Outcomes, Indicators & Targets

| Project Component | Relevant GWP Components | Relevant GWP Outcome | Relevant GWP GEF Indicators and Targets |
| --- | --- | --- | --- |
| Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime | Component 2. Reduce Wildlife Trafficking | Outcome 4: Enhanced institutional capacity to fight transnational organized wildlife crime by supporting initiatives that target enforcement along the entire illegal supply chain of threatened wildlife and product | 4.1: Number of laws and regulations strengthened with better awareness, capacity and resources to ensure that prosecutions for illicit wildlife poaching and trafficking are conducted effectively (increase) 4.2: Number of dedicated law enforcement coordination mechanisms (increase) 4.3: Number of multi-disciplinary and/or multi-jurisdictional intelligence-led enforcement operations (increase) 4.4: Proportion of seizures that result in arrests, prosecutions, and convictions (increase) |
| Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation | Component 1. Reduce Poaching and Improve Community Benefits and Co-management | Outcome 1: Reduction in elephants, rhinos, and big cat poaching rates | 1.1: Reduction of poaching rates of target species at program sites 1.2: Number of poaching-related incidents (i.e. sightings, arrests, etc.) per patrol day 1.3: Number of investigations at program sites that result in poaching-related arrests (increase at first, then decrease over time) 1.4: Increase in the proportion of poaching-related arrests that result in prosecution 1.5: Protected areas (METT score) and community/ private/ state reserves management effectiveness for Programme sites (increase) |
| Component 3. Engaging local communities in sustainable wildlife, forest, and PA management | Component 1. Reduce Poaching and Improve Community Benefits and Co-management | Outcome 2: Increased community engagement to live with, manage, and benefit from wildlife Outcome 3: Increase in integrated landscape management practices and restoration plans to maintain forest ecosystem services and sustain wildlife by government, private sector and local community actors, both women and men | 2.1: Decrease in human-wildlife conflict (HWC) as measured by incident reports 2.2: Increase in benefits received by communities from sustainable (community-based) natural resource management activities and enterprises 3.2: Increase in area of forest resources restored in the landscape, stratified by forest management actors (compared to baseline levels at start of project) 3.3: Increase in community benefits generated for managing forest ecosystems and restoration plans |
| Component 4. Knowledge Management, M&E and Gender Mainstreaming. | Component 4. Knowledge, Policy Dialogue and Coordination | Outcome 6: Improved coordination among program stakeholders and other partners, including donors | 6.2: Program monitoring system successfully developed and deployed 6.3: Establishment of a knowledge exchange platform to support program stakeholders |

- The project Theory of Change is explained in Fig. 3.

Figure 3. Project Theory of Change (see Fig. 2 for the barriers addressed by the project strategies)

Justification of selected strategies and approaches

- The project design is based on the lessons learned from the initial wildlife crime actions implemented in Angola,, and on other programmes and projects supported by UNDP, GEF, FAO, FAS, ADPP, KfW, ICCF, EPI, USAID, WCS, USFWS, Wildlife Impact, Stop Ivory, other international agencies and NGOs in Angola and abroad to make sure the project strategies can bring real progress in wildlife management and wildlife crime law enforcement in the country, especially in the project areas. First of all, the project development process has been based on the lessons learned by GEF Independent Evaluation Office (IEO) on project design that are the key for the project success:

- Strong stakeholder participation in project design and/or implementation leads to ownership and a shared vision;

- Flexible project design allows to implement effective adaptive management;

- Project design should be well-aligned with existing needs, capacities, and norms;

- Capacity building integrated in the project design increases sustainability of its results.

- Based on the lessons above, the design of this project was developed in strong cooperation with national and international stakeholders (155 national and international stakeholders participated in the consultations, see Annex T. List of stakeholders consulted), who were involved in the process from the earliest stage of its formulation and integration of all available experience in the project Theory of Change, Outputs and Outcomes. Design of the project Outputs, while based on actual needs, allows considerable flexibility for the PMU to select different options and partners for their delivery based on the current situation, support lessons learning and incorporating them in the project adaptive management. Capacity building for wildlife crime law enforcement agencies, PAs and local communities takes considerable part of the project budget to ensure achievement and sustainability of the project Outcomes. To achieve higher impact and real change in wildlife conservation, the project focuses its key interventions and main investments only on two representative project areas – Maiombe NP and Luando SNR. At the same time, presence of only two project areas in the project framework and active involvement of the key partners in delivery of the project Outputs will make the project management a bit easier in Angola where the GEF project managerial capacity has been low in the past.

- By implementing Component 1, the project will develop the necessary capacity and governance environment for confronting wildlife crime and managing wildlife (including HWCC) at the national level. Development of National Wildlife Crime Enforcement Strategies, analysis of key gaps in national wildlife crime law enforcement systems, and review of wildlife legislation to recognize wildlife crime as a serious crime is one of the key priorities identified by the ICCWC Strategic Programme 2016-2020 (Activity 2.3) that the project will follow under Output 1.1. Also, under Output 1.1 the project will update the national legislation to provide more rights and benefits to local communities on wildlife and habitat management in Angola. Empowerment of local communities and direct involvement of local people in wildlife and other natural resource management proved to be an effective tool for wildlife conservation in such countries as Namibia, Kenya, Zimbabwe, Gambia, etc  . Another strategy suggested by the project – support of the National Environmental Crime Unit (Output 1.2) – has been proven to be successful by experience of such countries as Indonesia, Kenya, Tanzania, Uganda, India, Zimbabwe, and others. Capacity building for customs, police, judiciary, prosecutors, border officers and other law enforcement agencies to investigate, prosecute and penalize wildlife crime via comprehensive and systematic training programmes (Output 1.2) was highly recommended by the ICCWC Strategic Programme 2016-2020 (Activities 3.1-3.5) and was successfully implemented in Kenya, Tanzania, Zimbabwe and other countries of the world. Output 1.3, which focuses on the capacity building for the Environmental Polytechnic Institute (Wildlife School) in Menongue, was suggested based on the positive experience of similar wildlife crime law enforcement training centers in Kenya, South Africa, and Gabon. The project will promote effective exchange with these centers to benefit from lessons learned and peer experiences. The Component 1 will provide necessary foundation for effective anti-poaching and anti-trafficking in Angola.

- Component 2 will directly target poaching and wildlife trafficking of endangered wildlife (forest elephant, gorilla, chimpanzee, black giant sable) and bushmeat species as well as other key threats (deforestation and wild fires) in the two project areas – Maiombe NP and Luando SNR via classic inter-agency anti-poaching cooperation approach (Output 2.1) built on cooperation of ECU, INBAC, IDF, National Police and judiciary at the provincial level. Support of a national-level inter-agency cooperation and establishment of local inter-agency anti-poaching brigades has been recognized as one of the best-practice in tackling IWT in other countries of Africa, including successful experience of multi-agency units (MAU) in Tanzania, Uganda, Mali and Kenya. It is founded on a resolution passed by 69th session of the UN General Assembly in 2015, calling for an end to ‘illicit trafficking in wildlife’ and encouraging countries to adopt effective measures to prevent and counter the serious problem of crimes such as illicit trafficking in wildlife and wildlife products, including flora and fauna and poaching. An example of successful inter-agency cooperation can be found in the case of Uganda's inter-agency task force comprising the Police, Uganda Revenue Authority (URA), Uganda Wildlife Authority (UWA), INTERPOL, Civil Aviation Authority and the Chieftaincy of Military Intelligence, established in 2013 with the intention of enhancing prosecutions to secure better court outcomes in wildlife crime. The glaring gap in this task force is the apparent lack of representation by prosecutors or the judiciary. The task force has achieved several major milestones including (i) UWA staff becoming part of a Joint Security Team at Entebbe International Airport, (ii) URA establishing a specialized unit focusing on wildlife enforcement and (iii) Uganda participating in regional wildlife trade enforcement initiatives.

- Output 2.2 (update and realization of the Management Plans for Maiombe NP and Luando SNR) is based on the Results-Based Management approach proved to be an effective tool for conservation and sustainable development projects implemented by UNDP, UNEP, WWF, IUCN and other leading conservation organizations. The planning process is built on fully participatory approach to develop common view for the sustainable development of the target PAs and communities and organization of implementation mechanism for the management plan based on the cooperation of the PA, local communities and other stakeholders (partnerships with International NGOs and private sector). Output 2.2 will considerably strengthen the target PA management capacity via significant equipment support and repetitive training programmes for the PA staff on anti-poaching, HWC management, wildfire prevention and control, and monitoring of endangered species.

- Component 3 is built on successful experience of the FAO, FAS, and ADPP in Angola, as well as community-based conservation initiatives in other countries, to develop rural communities and provide them with sustainable income via traditional and alternative livelihood approaches (Outputs 3.1). Such tested working models as Field Farmer School, Farmers’ Club, Green Negotiated Territorial Development (GreeNTD), Sustainable Charcoal, Conservation Agriculture, and ADECOS developed by the above mentioned organizations will be adjusted for CBNRM and CBWM and other similar models adequate for the Angolan policy and legislation frameworks, for local communities living inside and at the borders of the Maiombe NP and Luando SNR.  To involve local communities in wildlife conservation and sustainable use of forest resources the project will use adjusted for Angola IUCN’s First Line of Defence against Illegal Wildlife Trade (FLoD) approach that proved to be effective for CBWM and CBNRM projects in Kenya, Namibia and South Africa.

- Component 4 is designed to connect all the project strategies together and ensure effective learning and adaptive management of the project, including gender mainstreaming. This approach has been practiced as essential for all GEF 5 and 6 projects to ensure their effective management .

Project areas

- The project has two project areas – Maiombe National Park (2,074 km²) in Cabinda Province and Luando Strict Nature Reserve (9,930 km²) located at the border of Malanje and Bie Provinces (Fig. 4). The project sites were selected and confirmed with the MINAMB during stakeholder consultations and country mission of the PPG team in June 2018. The total project sites area is 12,004 km², or 1,200,400 ha, located in the biodiversity hotspots of Angola significantly impacted by poaching and illegal wildlife trade as well as habitat degradation due to unsustainable human activities. Key criteria for selection of the project areas were the following: (a) most important habitat for highly endangered species in Angola – forest elephant, gorilla, and chimpanzee (Maiombe NP) and black giant sable (Luando SNR), and (b) extremely high level of poaching and IWT in both sites; (c) high importance of both areas for development of wildlife tourism; and (d) almost complete lack of other conservation and law enforcement investments in the selected PAs. Brief description of the project sites is placed below (see Annex P. Project Areas Profile for full details).

| b a. | Figure 4. Project areas: (a) Maiombe National Park and (b) Luando Strict Nature Reserve |
| --- | --- |

- Maiombe National Park. The National Park was established in 2011 in the Cabinda Province (an enclave of Angola between the Republic of the Congo and DRC) on a total area of 207,400 ha (Fig. 5) for conservation of wildlife, rare species, and ecosystems' integrity; eco-tourism development; research and environmental education. The area is covered mainly by secondary high dense tropical rainforest with small patches of climax rainforest with patches of lowland drier forest, forest-woodland-savannah and riverine gallery forests. The Park represents the south-west margin of tropical rainforest massive called the Mayombe Forest covering ~36,000 km² along the coastline of Gabon, Republic of the Congo, Angola, and DRC,. The Maiombe National Park is home for mammal species of outstanding global interest, such as the central chimpanzee, western lowland gorilla and forest elephant, as well as giant pangolin and tree pangolin. The African manatee was reported in the Zaire and Chiloango Rivers. Among other mammals there are forest buffalo, moustached (red-tailed) guenon, greater white-nosed guenon, Bosman’s potto, golden potto, several species of bush-babies, several small forest duiker species, water chevrotain, sitatunga, bushpig, red river hog and forest hog, leopard, two-spotted palm civet, several genet species, flying squirrels and a yet to be studied variety of fruit bats and insectivorous bats. Avifauna is particularly rich too, including such endangered species as the African gray parrot.

- Poaching for bushmeat is the main threat for wildlife in the Maiombe NP. Most of the hunting is for bushmeat consumption and commercial use. Bushmeat poached in the NP is sold in the urban centers within the Maiombe along the main road, and to several vendors from the city of Cabinda. The main species subjected to poaching, in a recent survey, are blue duikers, black-backed duikers, bushbucks, cane rats, brush-tailed porcupines, red forest hog, and civets. The majority of adult men of the communities in and around the NP engage in subsistence hunting and small-scale commercial use. Reportedly, following the efforts of the NP staff since 2013, only a minority of community members engage now in larger-scale commercial poaching that target such endangered species as forest elephant, pangolins, chimpanzee, gorilla, and grey parrot. Foreign poachers, infiltrating mainly from DRC, are reported to engage in illegal activities of commercial poaching, logging and cross-border trafficking of wildlife, live parrots, live ape infants, bushmeat and other wildlife derivatives, and timber. In 2013-2018, at least 4 elephants were killed by poachers in the park.

Figure 5. Maiombe National Park: (a) boundaries; (b) area covered by forest (>=20% of the tree cover) – green, tree cover loss in 2000-2017 – red, forest fires in 2013-2017 – red dots; (c) human population density – from 0.14 persons/ha (light pink) to 0.88 persons/ha (dark brown).

| - National Park boundaries |  |
| --- | --- |
| - Deforestation and fires | - Human population density |

- Other direct threats for wildlife in the Park include deforestation due to illegal logging and slash-and-burn agriculture, HEC, and invasive species (Chromolaena odorata). In 2000-2017, the National Park lost about 5,224 ha (2.6%) of the tree cover and the annual deforestation rate increased from 120 ha/year in 2000-2007 to 718 ha/year in 2013-2017. Human-induced fires are relatively rare in wet tropical forests of Maiombe NP with only 4-12 incidents recorded annually. HECs have been regularly reported in all villages inside the Maiombe NP and around it, with two main hotspots – Comboliambo and Buco-Zau areas. At least six reports about HEC are submitted annually to the Maiombe NP administration. Main crops damaged in the NP are bananas, cassava, sweet potato, and corn, especially on small plantations located in the forest. Around 56,000 inhabitants live in two Municipalities (Buco-Zau and Belize) in the Maiombe NP, with their livelihoods based mostly on poaching, fishing, logging, subsistence cultivation and small-scale livestock breeding (Fig. 5).

- The Maiombe NP has only 15 staff, including 12 rangers operating in two groups. The NP staff represents recruited demobilized soldiers, trained at the Catalangombe School in Kissama, and deployed in the Park since 2012. Two of the rangers were recruited among community members in the park and the others are from Cabinda city. Since 2014 they receive regular salaries and have uniforms and basic equipment. The Park has only basic infrastructure, two 4X4 vehicles and one quadbike. The Park cooperates with IDF, National Police, and Army for the law enforcement activities. In 2013-2018, 47 poachers and illegal loggers were arrested in the Park (about 30 of them are citizens of the DRC). After 2013, 7 infant chimpanzees, 3 infant gorillas, 1 infant elephant, and 26 African gray parrots were confiscated by Park rangers; the last known incidents of gorilla poaching happened in 2018  .

- Luando Strict Nature Reserve. The protected area was established in 1957 at the border of Malanje and Bie Provinces on the area of 993,000 ha with the key objective to protect remnant population of the giant black sable (1,000-2,000 individuals in 1970s) (Fig. 6). About 94% of the reserve area is covered by miombo woodland, other ecosystems are represented by seasonally inundated grasslands, riverine gallery forests, marshes, and thickets.

- Currently the reserve (mainly northern part) is a home for about 160 giant black sables. Other species reported by the local people are bushbuck, roan, duikers, reedbuck, lechwe, sitatunga, bush-pig, warthog, forest buffalo, hippopotamus in Luando and Dando Rivers, vervets, blue guenons, banded mongoose, lutra, lion, wild dog (at least 3-4 packs), leopard, gennet, spotted hyena, jackal, porcupine, aardvark, pangolin, turtoises, rich avifauna and a variety of amphibians and fish. Among other large and medium-sized mammals reported previously there were also defassa waterbuck, puku and oribi. The giant black sables and most other large mammals are found mostly in the northern part of the Reserve, around Cunga Palanca.

- Poaching for bushmeat is the most significant threat to biodiversity in Luando SNR and a main threat to the remnant population of the black giant sable. Bush-meat poaching occurs both for subsistence and for commercial use. Subsistence poaching is practiced mostly by members of the local communities, who are normally not armed and use mainly snares and traditional traps, as well as dogs, resulting with unselective and significant impact on the already rather decimated wildlife populations. Most of the commercial bushmeat poaching is driven by demand in bush-meat markets in Malanje and Bie Provinces, as well as by the illegal diamond explorers ("garimpeiros"), operating on the banks of the Dando River, and who often participate themselves in poaching activities to complement both protein and income. Commercial bush-meat poachers operate normally in well-equipped and armed groups of 3-10 poachers, often involving participation and guidance of local community members. Motorbikes, arms, equipment and bush-meat are transported by poachers mainly across the Dando River with small boats and canoes. Most of the poaching activity occurs in the area of Cunga Palanca in the north of the Reserve, with highest presence of wildlife, including the giant black sable.

- Poaching of giant black sable for bush-meat is reported, with at least one incident recorded. According to the information of the Administrators of Capunda, Kunga Palanca and Quimbango villages received in June 2017 commercial poachers mainly come to the reserve from Kissonde, Dombo, Seque, Caionde, Zimbo, Simbanda, Tunda, Singuengo, Papo Seco, Sangamba, Siminhe, Sweka, Missongue, Ngunga, and Walitcha villages located on the bank of the Kwanza River bordering the reserve. At least 3 out of 16 GPS-collared black giant sables (19%) have been presumably poached in the Luando SNR since 2016.

- Among other threats to wildlife in the reserve are deforestation and wild fires. Thus, in 2000-2017 the reserve lost about 25,300 ha (2.7%) of its tree cover mainly due to slash and burn agriculture practices and uncontrolled fires. The deforestation rate increased from 702 ha/year in 2001-2007 to 1800 ha/year in 2013-2017. Wild fires have very high frequency in the reserve with ~5,100 fire incidents recorded annually in the period of 2013-2017 (Fig. 6).

- Around 20,000 inhabitants live in 3 communes – Capunda (6,724 people), Quimbango (10,566 people), and Cunga Palanca (2,802 people) scattered in small villages mainly along the main roads – inside the Luando Reserve. The communities mainly rely on small-scale agriculture, fishing and bushmeat hunting for subsistence. The communities also use non-timber forest products such as jinguenga (Aframomum alboviolaceum), maboque (Strychnos spinosa), loengo (Anisophyllea gossweileri), various types of mushroom and honey, but find it difficult to sell them on the markets due to poor road conditions. In Luando SNR, hippos are the key conflict animals coming to feed on the croplands located near Kwanza River. In 2014-2018, two local people were killed, and several were injured by hippos.

- Currently the Luando Reserve has no formal staff. 14 giant sable "pastors" were recruited from local communities (6 - in Kunga Palanca, 7 - in Quimbango and 1 - in Capunda) through the Giant Sable Project of the Kissama Foundation, and as act "part-time" rangers. They are poorly trained, equipped or armed and do not receive salaries, but only modest subsidies. They have no means of transport. They do, however, dedicate a good part of their time to this work and realize 1-7 days foot patrols regularly. The patrols are aimed mainly at collecting information on the giant sable and other species, through direct observations and spoor, and on poaching activities, as well as at collecting snares and other traps installed by poachers. Considering that the poachers in the reserve are normally armed, equipped and use motorbikes, while none of these conditions is available to the pastors, they cannot perform law enforcement activities. In several cases, they have been threatened and attacked by armed poachers. However, they do receive help from both the Police and the army. In one incident, 2 poachers were caught, and their arms confiscated but handed to the Municipal Administration. In 2017, the pastors confiscated 16 wildlife traps from Capunda and Quimbango communities.

Figure 6. Luando Strict Nature Reserve: (a) boundaries; (b) area covered by forest (>=20% of the canopy cover) – green, tree cover loss in 2000-2017 – red; (c) forest fire incidents in 2017; (c) human population density – from 0.0 persons/ha (light pink) to  0.65 persons/ha (dark brown).

| - Nature Reserve boundaries |  |  |
| --- | --- | --- |
| - Deforestation | - Wild fires 2017 | - Human population density |

# Results and Partnerships

## Expected results

- The project is designed to achieve following Long-Term Impacts (Global Environmental Benefits) (see Fig. 3):

- Stable or increasing populations of the flagship species in the project areas:

- Forest Elephant (Maiombe NP): baseline to be established on the first year of the project; population is at least stable by the end of the project (>= baseline).

- Western lowland gorilla (Maiombe NP): baseline to be established on the first year of the project; population is at least stable by the end of the project (>= baseline).

- Chimpanzee (Maiombe NP): baseline to be established on the first year of the project; population is at least stable by the end of the project (>= baseline).

- Black Giant Sable (Luando SNR): 150 (2016); >= 200 by the end of the project

- Stable area of wildlife habitat in the project areas:

- Tropical Rain Forest (Maiombe NP): baseline - 196,275 ha (2017); no decline from the baseline by the end of the project.

- Miombo woodlands (Luando SNR): baseline – 929,191 ha (2017); no decline from the baseline by the end of the project.

- The Long-Term impacts will be achieved via attainment of the Mid-Term Impacts (direct threat reduction):

- Decreased poaching and IWT for high-value and bushmeat species:

- Number of cases of elephant poaching discovered in Maiombe NP by the Park staff and other LE agencies: at least 1 elephant is poached annually; 0 - at the end of the project.

- Number of cases of gorilla poaching discovered in Maiombe NP by the Park staff and other LE agencies: baseline – 1 (2017); 0 – by the end of the project.

- Number of cases of chimpanzee poaching discovered in Maiombe NP by the Park staff and other LE agencies: baseline – 1-2 annually; 0 – by the end of the project.

- Number of cases of black giant sable poaching discovered in Luando SNR by the Park staff and other LE agencies: baseline – at least 3 (2017); 0 – by the end of the project.

- Bushmeat is exposed for selling along the roads and at the local markets in Maiombe NP, around Luando SNR, and in Luanda: baseline – Yes (2018); No – by the end of the project.

- Decreased deforestation rate in the project areas (ha/year):

- Maiombe NP: baseline – 718 ha/year; 0 ha/year – by the end of the project;

- Luando SNR: baseline – 1,800 ha/year; 0 ha/year – by the end of the project;

- Decreased frequency of human-induced fires in Luando SNR: baseline – 5,023 incidents/year; <= 2,500 incidents/year by the end of the project.

- To ensure the Mid-Term Impacts the project will achieve the following Outcomes:

Outcome 1. Strengthened policy, legal and institutional framework to combat wildlife crime and manage wildlife, including HWC

- Capacity of the INBAC to combat wildlife crime (UNDP Capacity Scorecard): baseline – 41% (2018); >=60% - by the end of the project.

- National capacity to combat wildlife crime (ICCWC Indicator Framework Score): baseline – 28% (2018); >=45% - by the end of the project.

Outcome 2. Strengthened capacity of PAs and other law enforcement agencies in the project areas to reduce wildlife crime, manage HWC, and prevent habitat degradation

- Management effectiveness of the target PAs (METT score):

  - Maiombe NP: baseline – 35 (2018); >=55 – end of the project

  - Luando SNR: baseline – 20 (2018); >=40 – end of the project

- Annual wildlife crime law enforcement results in the project areas:

  - Maiombe NP: baseline (2017) – total number of staff available for enforcement: 12; intensity of patrolling (ranger/days/month): 216; annual number seizures of wildlife and forest products: 3-5; annual number of arrests of wildlife and forest crime offenders: 9-10. End of the project: total number of staff available for enforcement: >=30; intensity of patrolling (ranger/days/month): >=450; annual number seizures of wildlife and forest products: >=50; annual number of arrests of wildlife and forest crime offenders: >=50.

  - Luando SNR: baseline (2017) – total number of staff available for anti-poaching: 0; intensity of patrolling (ranger/days/month): 0; annual number seizures of wildlife products: 0; annual number of arrests of wildlife crime offenders: 0. End of the project: total number of staff available for anti-poaching: >=30; intensity of patrolling (ranger/days/month): >= 450; annual number seizures of wildlife products: >=50; annual number of arrests of wildlife crime offenders: >=50.

- HEC conflicts in Maiombe NP:

  - Percentage of solved/mitigated HEC: baseline – 0% (out of at least 6 cases annually); >=50% by the end of the project.

Outcome 3. Increased involvement of local communities in the project areas in wildlife, habitat, and PA management

- Total number of people (F/M) practicing SFM, SLM, CBNRM and/or participating in the PA management:

  - Maiombe NP: baseline (2018) – 0; >= 3,000 by the end of the project

  - Luando SNR: baseline (2018) – 0; >= 3,000 by the end of the project

- Total area (ha) under community-based SFM, SLM, and CBNRM:

  - Maiombe NP: baseline (2018) – 0 ha; >= 10,000 ha by the end of the project

  - Luando SNR: baseline (2018) – 0 ha; >= 10,000 ha by the end of the project

Outcome 4. Lessons learned by the project through participatory M&E and gender mainstreaming are used nationally and internationally

- Number of the lessons learned by the project that are used in other national and international projects: baseline – 0; >=5 by the end of the project.

- Percentage (%) of women participating in (and/or benefiting from) the project: baseline – 0; >=50 by the end of the project.

- To achieve these Outcomes, the following Outputs will be delivered by the project:

- ESIA should be conducted and ESMP should be developed before initiation of the activities to deliver the project Outputs.

Outcome 1. Strengthened policy, legal and institutional framework to combat IWT and poaching, and manage wildlife, including HWC

Output 1.1. National policy and regulatory framework for IWT control and wildlife management is reviewed and updated

- As it was mentioned in the Development Challenge section, weak policy and regulatory frameworks relating to wildlife and IWT provide limited tools to manage wildlife sustainably with participation of local communities as well as monitor and combat IWT, including surveillance, investigation, prosecution, and conviction of wildlife criminals. Thus, the country still lacks a National Wildlife Crime Enforcement Strategy to guide national wildlife crime enforcement, inter-agency and international cooperation to combat poaching, illegal wildlife trade and trafficking. The country still has low penalties for wildlife crimes: maximum 3 years of imprisonment and mainly financial penalties; thus, they do not fall within the definition of “serious crime” under the United Nations’ Organized Crime Convention. No specific guidelines for prosecuting wildlife related crimes developed for the country’s prosecutors and judiciary. No legislation exists in the country to support Community-Based Wildlife and Natural Resources Management (CBWM and CBNRM) and establish Local Councils for Protection of Forest and Wildlife and Community Management Areas defined in the National Policy on Forests, Wildlife and Conservation areas. The country also needs updated National Ivory Action Plan (NIAP) to guide national efforts to stop illegal ivory trafficking through Angola. Legal documents for Luando SNR (dated on 1957) and Maiombe NP need to be updated to improve management (Luando SNR) and optimize the PA boundaries (Maiombe NP).

- The project will take in account wildlife crime legislation review and recommendations developed by the IELP, Stop Ivory and Wildlife Impact projects in Angola (2018-2019) as well as the results of the brief ICCWC IF assessment in August 2018 and will initially focus on the update and promotion of the official approval of the following legislation documents:

- National Wildlife Crime Enforcement Strategy, as the key national policy document to guide improve wildlife crime law enforcement in Angola. In specific the strategy should:

  - Describe key measures to stop poaching and illegal wildlife trade, and strengthen the inter-agency and international collaboration in the Governance, Justice, Law in dealing with illegal wildlife trade;

  - Define key targets to achieve in the wildlife crime enforcement in the country;

  - Indicate key mechanisms and sources of funding for improved wildlife crime enforcement;

  - Include measures to decrease national demand for bushmeat and increase national awareness on the impact of wildlife crime on the national biodiversity and economy.

As an example of the policy document the project can use the Kenya’s National Wildlife Conservation and Management Strategy that should be finalized by the end of 2018, Zimbabwe’s National Law Enforcement and Anti-Poaching Strategy 2017-2021, and other documents. The Angolan Strategy should be developed in accordance with the SADC Regional Law Enforcement and Anti-Poaching Strategy.

- Wildlife Crime and Hunting Legislation. Based on the IELP, Stop Ivory and Wildlife Impact analysis of wildlife crime legislation in 2018-2019 the project can potentially update one or two key wildlife legislative documents to improve prosecution and increase penalties for wildlife crime in the country. The laws to be updated in the project framework will be identified during the project inception phase based on the results of on-going process of legislation improvement in the country.

- Legislation on Community-Based Wildlife and Natural Resources Management to provide a legal framework for the sustainable management and protection of wildlife and forest resources within communal lands. The laws should ideally provide ownership rights (not only user rights) to local communities to manage wildlife and forest resources as well as incentives to local communities for sustainable wildlife and forest management. The project can use the appropriate legislation and experience of Zimbabwe, Namibia, Botswana, and Zambia as examples for development of the Angolan Community Wildlife and Forest Management Legislation.

- If planned co-financing is fully available, the project will also work on the following legislation documents:

  - Ancillary Legislation, such as Mutual Legal Assistance (MLA). Based on IELP, Stop Ivory and Wildlife Impact analysis and outcomes of validation workshop in September 2018, one or two targeted priorities may be identified to specifically address gaps in related ancillary legislation helpful to combating wildlife trafficking, including customs, criminal, MLA, extradition, anti-money laundering, anti-corruption, assets forfeiture, and permanent deportation of foreigners involved in wildlife crime in Angola, etc. In many cases, increasing penalties will facilitate the ability of prosecutors to use this “ancillary” legislation. However, some targeted intervention may be necessary to improve MLA legislation and key MLA relationships, such as between demand, source, and transit countries, to increase the probability of prosecutions and cooperative law enforcement throughout the supply chain.

  - National Human-Wildlife Conflict Management Strategy through a holistic planning approach.

  - Updated National Ivory Action Plan for 2020-2025 with a goal to completely stop ivory trafficking through Angola (if not developed before the project start). The NIAP can be a section or an Annex for the NEAP that is under development in 2018.

  - Update of the legal documents for the target PAs: Luando SNR (e.g., to improve its management as a National Park given the current situation) and Maiombe NP (e.g., to include important chimpanzee and gorilla habitat adjacent to the south-west portion of the park and make appropriate zoning of the park given high human population density areas inside the PA). The project will be able to update 3-4 legislative documents total based on the priorities identified during the project inception phase from the list above. The selected legislation documents will be developed by the MINAMB and other partners with the project technical support in fully open and participatory process with involvement of all interested stakeholders under potential leadership of the Angola’s Conservation Caucus (that is currently under establishment in the National Assembly with support from the ICCF Group). The final documents will be submitted by the MINAMB to the National Assembly of Angola for official approval that can be facilitated by the Conservation Caucus. The project can also to assist MINAMB in development of NIAP Reports.

- Key partners for delivery of Output 1.1: Leading partners: MINAMB, ECU, INBAC, Interministerial Commission on Wildlife Crime, Attorney General’s Office, CITES Secretariat, MINAGRIF, IDF. Supporting partners: Stop Ivory, Wildlife Impact, EIA, ICCF Group, 51 Degrees, USFWS, IELP, national legal and thematic experts.

- Deleted

Output 1.2. National Environmental Crime Unit and other wildlife law enforcement agencies are provided with trainings, manuals, and equipment to effectively enforce, prosecute, and penalize wildlife crime.

- Angola made significant progress in strengthening it is national wildlife crime law enforcement agencies and PAs in 2000-2017. The INBAC has been strengthened in recent years to manage national PA system notably through the efforts of previous GEF projects. However, this has not included the capacity to effectively suppress poaching, IWT, and manage HWC. Thus, the current capacity of the INBAC to control wildlife crime was evaluated as 41% of maximal possible score (see Annex Q. UNDP Capacity Scorecard for INBAC). The Environmental Crime Unit was established under MINAMB leadership in 2015 to investigate and prosecute wildlife crime, including illegal ivory trade and trafficking. The Unit still has very limited staff (15 officers total, including 7 in Luanda and 8 in the provinces) and insufficient investigation, surveillance, and technical capacity to combat wildlife crime. Some of the ECU staff has been trained in the wildlife crime investigation, intelligence, and forensics by the Stop Ivory and at the wildlife law enforcement schools in Botswana and Gabon, but the system of regular trainings for the ECU staff is still missing. The ECU still has very limited equipment for law enforcement, including only two vehicles, and initial network of informers that includes 21 people only. Given the plans of the ECU to increase its staff up to 45 officers in 2018 and ultimately up to 200 of staff, the Unit will badly need transportation, equipment as well as regular system of trainings for the staff.

- Initial ICCWC Indicator Framework assessment (see Annex R) clearly demonstrated capacity gaps in adequate investigation, intelligence, enforcement, and prosecution of wildlife and forest crime in the country. Both the prosecution success rate and the nature of the penalties applied are still insufficient to adequately deter offenders. This problem can in part be attributed to lack of awareness of the police prosecutors and the judiciary of the serious impact that poaching and trafficking are having on Angola’s wildlife. As a result, these crimes are practically dismissed entirely, or only minor penalties are applied.

- Thus, the Output 1.2 has been designed to strengthen (1) National ECU and (2) other law enforcement agencies capacity (INBAC, Police, Judiciary, and Customs) to investigate, prosecute and penalize wildlife crime.

- The project will provide the ECU with one additional vehicle (Toyota Pickup) to be deployed as per the greatest need in the country considering especially the Maiombe NP and Luando SRN targeted by the project, VHF radios, field equipment for 20 officers, cameras and possibly equipment for phone analysis (e.g. CellBrite). The application of specific methodologies (e.g. canines) and innovative intelligence technology (including relevant trainings) by the ECU will be analyzed at the project inception phase in cooperation with UNODC and mentoring partner for the ECU. The unit will be provided with mentoring from an international law enforcement expert organization (e.g., Stop Ivory, Salama Fikira, ESPA, Retarius, MacKenzie Intelligence, Wildlife Justice Commissio`n, Maisha Group Ltd., or Freeland) which will cover personal and data security, interrogation, network analysis, open source investigation, surveillance, phone analysis, evidence handling, forensics, prosecution dossier development, informer handling, governance, anti-corruption, cyber approaches, species and derivatives identification, and chain of custody. The project will support experience exchange visits for the ECU officers to relevant law enforcement agencies in other countries (e.g., South Africa, Namibia, Gabon, Kenya, Tanzania, Mozambique (Portuguese-speaking) as well as their participation in the regional wildlife crime law enforcement meetings. The mentoring programme will include basics of conservation biology and will have strong component on human rights issues.

To monitor appropriate use of provided vehicle and equipment the project team and INBAC will use logbooks for all vehicles (all rides and maintenance) and equipment monitoring lists which will regularly be audited. INBAC has also started to put GPS into their vehicles to monitor their use, thus this measure will be implemented too. Quarterly auditing missions will be done by the PMU to ensure that ECU have all provided equipment in place, correctly use and maintain it.

- To eliminate wildlife crime capacity gap, the project will provide repetitive trainings to the key law enforcement organizations – INBAC, police, customs, military, border authorities, and judiciary working in the cooperation with the ECU. Following indicative list of mandatory and repetitive trainings can be developed and delivered in the project framework based on the previous experience of the Stop Ivory, Wildlife Impact, Space for Giants, Wildlife Justice Commission, Freeland, Maisha Group Ltd., and ICCF across Africa (the list of trainings can be updated by the PMU in framework of Adaptive Management to adopt to changing situation and needs in the country and project area):

  - CITES theoretical and practical course, including specimen identification and CITES permits (for INBAC, police, and Customs) (at least 5 trainings in 2019-2025 for 15-20 officers each);

  - Special Training for Investigators on wildlife and forest crimes, including scene of crime management (at least 3 trainings in 2019-2025, and at least 40 officers should be trained);

  - Special Training for Prosecutors on wildlife and forest crimes (at least 4 trainings in 2019-2025 for 15-20 prosecutors each);

  - Special Training for Judiciary on wildlife and forest crimes (judicial sensitization) (at least 3 trainings in 2019-2025 for 15-20 judges each).

- The suggested trainings will include basics of conservation biology and will have strong component on human rights issues.

- Overall, under this output the project is going to target 200-250 of LE agents, investigators, prosecutors and judiciary working in Luanda (including sea port and airport) and the project areas (Cabinda and Malanje Provinces).

- Key partners for delivery of Output 1.2: Leading partners: ECU, INBAC, Inter-ministerial Commission on Wildlife Crime, Attorney General’s Office, CITES Secretariat, National Directorate for Biodiversity, IDF, Police, Customs, Judiciary; Supporting Partners: Stop Ivory, Wildlife Impact, EIA, IELP, USFWS, Space for Giants, Maisha Group Ltd., Vulcan, ICCF, thematic experts.

- Deleted

Output 1.3. The Environmental Polytechnic Institute (Wildlife School) in Menongue has comprehensive national training programmes for PA rangers and provides necessary training for the PA staff

- To support capacity building of the national PA staff and conservation managers in Angola and entire SADC, the Government established the 31st of January Environmental Polytechnic Institute (Wildlife School) in Menongue (Cuando-Cubango Province) on June 5th 2016. The school has basic infrastructure and classrooms for 150 students (6 classrooms for 25 students each), however, accommodations are available for 50 students only. The classrooms are equipped with desks and chairs, but student dormitory has no beds. There are two office areas for instructors all equipped with desks, chairs and 3 computers and one printer. The school is powered by a diesel power generator. The school has 22 persons of permanent staff, including a principal, a secretary and security guards. The school has no instructor staff and no training equipment. The school does not have any training programmes and does not run regular trainings for PA rangers. Last (and only) training at the school was conducted in May 2017 and no other trainings are currently planned by the INBAC.

- The project is going to support the Environmental Polytechnic Institute (wildlife school) to become a fully-functional national center for PA staff capacity building with necessary equipment (e.g., furniture for classes and student rooms, computers and printers, field equipment for trainings, VHF radio equipment, GPS navigators, SMART cyber-trackers, gasoline generator, a military troop carrier, firefighting equipment). To monitor appropriate use of provided vehicles and equipment the project team and INBAC will use logbooks for all vehicles (all rides and maintenance) and equipment monitoring lists which will regularly be audited. Quarterly auditing missions will be done by the PMU to ensure that the Wildlife School has all provided equipment in place, correctly use and maintain it.

- Based on the results and recommendations of the Strengthening Angola’s Criminal Justice System for Wildlife Project of the Stop Ivory and 51 Degrees the project will develop following indicative list of the essential training programmes for PA rangers using the existing programmes of the South African Wildlife College, KWS ranger schools in Kenya, and wildlife ranger training centers in Namibia and Gabon adjusted for Angola (the list can be updated at the project inception phase):

- Advanced anti-poaching tactic and arrest training for Rapid Response Units of the PAs (20 days);

- Basic anti-poaching training course (15 days);

- Special HWC Management and Mitigation Training (5 days);

- First Aid in the field training (3 days);

- Bush fire management course (3 days);

- Human rights in the law enforcement operations

- The project will provide a training for trainers for at least 5 Environmental Polytechnic Institute instructors to run essential training programmes for rangers. Finally, the project will support mandatory trainings for at least 250-300 PA rangers with key focus to the rangers from the project areas (Maiombe NP and Luando SNR) and Mavinga and Luiana-Luengue NPs (key savanna elephant habitat and poaching hotspot in Angola). It should be mentioned that other projects, such as Stop Ivory and KAZA initiatives will also invest in the Institute with overall objective to train at least 1,500 PA rangers in Angola. Thus, the GEF project will be responsible only for clearly defined above part of the joint initiative. Additional long-term support to the Environmental Polytechnic Institute and its staff will be provided by the MINAMB and international donors.

- Key partners for delivery of Output 1.3: Leading partners: Menongue Environmental Polytechnic Institute (Wildlife School), INBAC; Supporting partners: Stop Ivory, 51 Degrees, South Africa Wildlife College, KWS Training Centers, Space for Giants, wildlife ranger training centers in Namibia, Tanzania, Mozambique and Gabon, KAZA TFCA Secretariat, Connected Conservation, thematic experts.

- Deleted

Outcome 2. Strengthened capacity of PAs and other law enforcement agencies in the project areas to reduce IWT and HWC, and prevent habitat degradation

Output 2.1. Two local inter-agency Environmental Crime Units (local sub-divisions of the national Environmental Crime Unit) are established in the project areas and provided with comprehensive anti-poaching trainings, equipment, and initial operational support

- National ECU, INBAC, IDF, National Police, and Judiciary in Angola have significantly intersected and interdependent responsibilities to combat wildlife and forest crime. To facilitate interagency cooperation the government of Angola established the Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora and National Environmental Crime Unit to implement wildlife crime control in Angola with the participation of the all law enforcement agencies in the country at national and local levels. However, interagency cooperation remains low and insufficient at national, provincial, and local levels. For example, Maiombe NP has initial agreements and irregular cooperation with IDF, National Police, and Military for anti-poaching patrolling. Given lack of rangers, inter-agency cooperation is difficult now in the Luando SNR and represents rare cases of support of pastors’ patrolling with a local staff of the National Police.

- It should be mentioned, that well-established interagency collaboration to fight wildlife and other crimes in the form of anti-poaching units, brigades, or task forces can considerably increase effectiveness of law enforcement and significantly suppress poaching and IWT. Interagency collaboration needs some additional coordination efforts but provides multiple benefits to participating agencies including leveraging resources (vehicles, equipment, staff, and operational expenses) for patrolling and joint operations; strengthening impact of special operations with more officers involved; provide joined brigades with unique opportunity to target wide spectrum of crimes (poaching, IWT, illegal logging and burning, possession of illegal arms, narcotics, etc.) and different areas (PAs and non-PAs); effective intelligence and sharing of actionable information between agencies; effective coordination of plans of different agencies; and effective prevention of bribery in the multi-agency groups. Moreover, the initial national wildlife crime action concept in Angola (establishment of the ECU and of the Interministerial Commission) was based on a multi-agency cooperation at all levels.

- Based on the positive experience of multiple countries the project is going to assist the Angolan government to establish and operationalize two local interagency Environmental Crime Units (local sub-divisions of the national Environmental Crime Unit) in the project areas based on the existing agreements and experience of inter-agency collaboration – Maiombe NP and Luando SNR – to coordinate and leverage enforcement efforts among participating agencies; provide adequate operational response to the wildlife crime activities inside and outside the PAs via joint sting operations and strengthened patrolling of the poaching hotspots; and organize effective prosecution and penalization of wildlife and forest crime offenders. Each local ECU will consist from at least 8-10 officers from the PAs, ECU, IDF, National Police, military, Border Police, and Judiciary and can be strengthened with other staff of the participating agencies for special sting operations. The ECU in Maiombe NP will work in strong cooperation with the border agencies for control of transboundary trafficking of wildlife and forest products and other illicit goods. The project will support following activities to establish and support the local ECUs:

- Development of interagency protocols on the local ECUs (as extensions of existing inter-agency agreements) with clear roles and responsibilities of each participating agency and focal areas of leadership of each agency under the protocol (will be implemented directly by the Angolan government in framework of the project co-financing);

- Development of the Standard Operating Procedures for cooperation, information exchange, and rapid response cases of the local ECUs;

- Development of the joint action plans of the local ECUs;

- Initial workshops and trainings on interagency cooperation for each local ECU;

- Quarterly meetings of the local ECUs for information exchange, planning, and reporting to the national Environmental Crime Unit on the results of joint activities in the project areas;

- Necessary law enforcement training to the participants of the local ECUs will be provided under Output 1.2 (INBAC, Police, and Judiciary), Output 1.3 and 2.2 (PA rangers), including innovative wildlife crime detection, intelligence and investigation approaches (if feasible for local units). All training programmes for law enforcement staff will incorporate strong component on human rights;

- Procurement of the equipment for the local ECUs, including field equipment, HVF radios, cameras, DeLorme messengers (for real-time monitoring of the Unit members locations during field operations and fast response in the cases of emergency);

- Support of initial operations of the local ECUs to enforce forest and wildlife crimes, including poaching, illegal logging and burning, bushmeat trafficking and trade.

- Salaries and other operational expenses of the local ECUs will be supported by the participating agencies and non-governmental donors.

- Key partners for delivery of Output 2.1: Leading partners: National ECU, INBAC, Maiombe NP and Luando SNR, National Police, FAA, Judiciary, IDF, Presidential Programme for Conservation and Restoration of the Black Giant Sable; Supporting partners: Kissama Foundation, Mayombe Transfrontier Initiative's Secretariat, 51 Degrees, Maisha, Vulcan, Wildlife Impact, USFWS, thematic experts.

- Deleted

Output 2.2. Comprehensive and participatory Management Plans for the PAs in the project areas are updated and implemented, including the PA support with trainings, equipment and infrastructure

- Management effectiveness of two project areas – Maiombe NP and Luando SNR – have been evaluated as low by the PPG team (baseline METT score for the Maiombe NP is 35, and Luando SNR – 20 only) due to limited financial resources, insufficient staff number and quality and lack of clear long-term management guidance. In 2018-2019, INBAC is planning to significantly strengthen the PAs with additional staff (currently Maiombe PA has only 15 of staff while Luando SNR has no official staff at all). Both target PAs currently have no management plans. However, a comprehensive and cutting-edge management plan for Maiombe NP is under development now, under GEF 5 support, and expected to be available before this project starts.

- Thus, the project will update (or develop if still lacking) the existing management documents to fully operational management plans for the Maiombe NP and Luando SNR using following key basic principles:

- A management plan (MP) has to be based on the Result-Based Management (RBM) concept with clear identification of the plan Goal (desired and achievable status of Conservation Targets – endangered wildlife populations and area of key ecosystems) and Objectives (aimed to reduction of direct threats for the Conservation Targets) and clear links between the plan expected results of different level: Outputs (products and services of the MP implementing team), Outcomes (increased capacity of PA management), Mid-Term Impacts (reduction of direct threats for PA’s biodiversity) and Long-Term Impacts (improvement of status of key wildlife species and ecosystems). The MP should incorporate Financial Sustainability Strategy with key sources of funding to support the PA development. Results at all levels should be measurable and need to have clear Indicators. For each MP, a clear Theory of Change should be developed and clarified with key stakeholders based on existing approaches of the IUCN First Line of Defense, or WWF’s Open Standards for Conservation Planning, or UNDP’s Management for Development Results, or other models based on the RBM;

- A MP has to be developed in fully participatory approach and involve all key stakeholders in the planning process, including local administration, palanca pastors, relevant government agencies, NGOs supporting the PA, communities inside and around the PA, logging and mining concessions/camps (if present in the area);

- A MP should be based on the ecosystem and habitat map for the entire area of the PA (can be developed based on the ready for use data of the Global Forest Watch and basic interpretation of last Landsat 7 and 8 imageries freely available on-line), maps of key threats to the PA (e.g., known poaching sites, deforestation hotspots, areas of wild fires) and topographic maps showing relief, water bodies, populated places, and roads. The maps should be used to delineate management zones for the PA (e.g., settlement and agriculture zone, sustainable forest and wildlife management zone, and strictly protected zone) and planning of key interventions under the MP;

- A MP has to be designed for no more than a 5 to 10-year period and include budgeted M&E plan to allow lessons learning and adaptive management through the implementation;

- Ideally a MP should have a Wildlife Adaptive Management section with simple population growth models for key species (e.g., forest elephant, gorilla, chimpanzee, and black giant sable) and wildlife monitoring plan with detailed survey methodology;

- A MP should include Special Operating Procedures for PA rangers to deal with wildlife and forest crimes.

- A MP must have clear Operational and Financial Plan (2-3 years) with timelines to deliver the MP’s Outputs, responsible persons, required budgets and indicated sources of the budgets;

- A MP has to be in agreement with MINAMB/INBAC plans and aligned with other relevant strategies/programmes such as the PLERNACA, Presidential Programme for the Black Giant Sable, Mayombe TFCA Strategic Plan and NEAP.

- A MP has to be officially approved by the MINAMB/INBAC with assignment of the staff to supervise the MP implementation;

- A MP has to have clear mechanism for implementation with potential involvement of supporting NGOs, donor organizations, private sector, and communities to facilitate and control the process of MP implementation (e.g., PA management committee) or other forms of management mechanism. To ensure sustainability of the PAs and steady progress to the PA goals MINAMB can consider partnerships with international NGOs (e.g., WWF, WCS, AFW, African Parks, ZSL, FZS, etc.) and private sector for the PA co-management or delegated management. Local communities can be involved in the PA management via so called PA-Community Councils that allow local people to participate in PA decision-making and management, especially in the areas of conflicts between a PA and local communities (see Output 3.1).

- The updated/produced PA management plans will be used as the key guiding documents to support target PAs on anti-poaching, habitat management, including fire control, and HWC management. While detailed needs of the PAs will be identified during management planning process, some urgent priorities indicated by the PA capacity assessment can be supported by the project before the MPs are finalized/updated.  They include the following:

- On-the-site trainings for PA managers and rangers as additional to those provided at the Environmental Polytechnic Institute (Wildlife School) in Menongue under Output 1.3 (the list of trainings can be updated by the PMU in framework of the project adaptive management):

  - Local refresher of the advanced anti-poaching tactic and arrest training for the patrol groups of the PAs and local inter-agency ECU (established under Output 1.2) (at least 12 rangers need to be trained during 3 training sessions in 2019-2025). Highly trained anti-poaching personnel should not be transferred to implement other tasks in the PAs;

  - Local refresher of the basic anti-poaching training (at least 50 rangers have to be trained during 3 training sessions in 2018-2024);

  - Off road driving training for PA rangers (at least 6 ranger-drivers have to be trained during 4 training sessions in 2019-2025);

  - Special HWC Management and Mitigation Training (at least 12 rangers have to be trained during 2 sessions in 2019-2025);

  - First Aid in the field training (at least 50 rangers have to be trained during 2 sessions in 2019-2025);

  - Species identification and wildlife monitoring training, including camera-trapping, distance sampling, and occupancy (at least 20 rangers have to be trained during 2 sessions in 2019-2025);

  - Bush Fire management course (at least 50 rangers have to be trained during 3 sessions in 2019-2025);

  - Human rights in law enforcement operations.

- Equipment critical for proper protection and management of the target PAs (indicative list, that can be updated by the PMU in framework of the project adaptive management and in accordance with the PA needs and budget at the project start):

  - Luando SNR:

    - Field equipment for 40 rangers (uniform, boots, night vision scopes, GPS, tents, camping gear, raincoats, backpacks, first aid kits, lanterns, chest webbings, binoculars, digital camera);

    - One Toyota Pick-Up for patrols including with the local ECU;

    - One John Deere tractor with accessories for bush fire management and road repair

    - One boat and trailer for river patrols;

    - VHF radio equipment, including repeaters, will provide critical communication network to support anti-poaching and management in the entire landscape;

    - Five DeLorme satellite trackers for patrol groups for real-time control and safety of rangers during patrolling;

    - Five Gasoline generators and emergency water pumps for ranger posts and fire management;

    - Four Computers and printers for the Luando SNR office;

    - Fully equipped temporary tented camp at park HQ, for 20 people at a time;

    - Border and entrance signs for the Reserve;

    - First aid equipment and material;

    - Tablets or smartphones for data collection with an Open Data Kit application (1 for every 4 rangers)

- Other equipment, such as Vulcan DAC technology, will be provided by the project partners in framework of the project co-financing

  - Maiombe NP:

    - Field equipment for 40 rangers (uniform, boots, night vision scopes, GPS, tents, camping gear, raincoats, chest webbings, digital camera, etc.);

    - One Toyota Pick-Up for patrols including with the ECU;

    - 5 motorcycles;

    - One boat and trailer for river patrols;

    - VHF radio equipment, including repeaters, will provide critical communication network to support anti-poaching and management in the entire landscape;

    - Five DeLorme satellite trackers for patrol groups for real-time control and safety of rangers during patrolling;

    - Four computers and printers for the Maiombe NP office;

    - Solar panel; generator; water pump; water treatment system; water tanks; water pipes; sewerage system; waste disposal facility, in the MNP headquarters;

    - Border and entrance signs for the NP;

    - Rehabilitation facility for confiscated parrots;

    - Two fully equipped tented mobile post (for 6 staff at any time);

    - First aid equipment and material;

    - Tablets or smartphones for data collection with an Open Data Kit application (1 for every 4 rangers)

- To monitor appropriate use of provided vehicles and equipment the project team and INBAC will use logbooks for all vehicles (all rides and maintenance) and equipment monitoring lists which will regularly be audited. INBAC has also started to put GPS into their vehicles to monitor their use, thus this measure will be implemented too. Quarterly auditing missions will be done by the PMU to ensure that PA rangers have all provided equipment in place, correctly use and maintain it.

- The project will also provide initial support to the ranger anti-poaching, HWC control, and other management activities in the Maiombe NP and Luando SNR in the form of daily ration packs and gas for vehicles and facilitate community-based production of daily ration packs for rangers under Output 3.1. Other operational expenses of the target PAs will be provided by INBAC and international donors.

- Under the Output 2.2 the project will support baseline and end of project population surveys for forest elephants, gorilla, chimpanzee, and black giant sable to qualify actual project impact on the endangered species populations.

- Key partners for delivery of Output 2.2: Leading partners: INBAC, Presidential Programme for Conservation and Restoration of the Black Giant Sable, Maiombe NP and Luando SNR; Supporting partners: Mayombe Transfrontier Initiative Secretariat, Kissama Foundation, 51 Degrees, Vulcan, Maisha, Wildlife Impact, USFWS, WCS, JGI, Local government and communities, thematic experts, palanca pastors.

- Deleted

Outcome 3. Increased involvement of local communities in the project areas in wildlife, habitat, and PA management

Output 3.1. Pilot projects on community-based conservation, HWC management, sustainable use of natural resources, and alternative sources of income for local communities are developed and implemented in the project areas

- Communities living around PAs in Angola do not receive any significant benefits from conservation, but suffer from HWCs, and almost lack of social services, and difficult access to markets, which in turn has not fostered attitudes that are supportive of conservation practices. No Community-Based Wildlife and Natural Resources Management (CBWM and CBNRM), Local Councils for Protection of Forest and Wildlife, and Community Management Areas defined in the National Policy on Forests, Wildlife and Conservation areas have been established in Angola so far. Many local people are involved in unsustainable bushmeat hunting and trade, ineffective slash and burn agriculture, illegal logging and mining, burning of woodlands for short-term needs, including increasing char-coal production. All these are true for the selected project areas – Maiombe NP and Luando SNR – with total population inside the PAs about 73-75,000 people.

- Under this Output the project will invest in the local communities’ sustainable livelihood in the Maiombe NP and Luando SNR via involving them in the PA management, SFM and SLM, and increasing local people capacity to effectively manage HWC (especially HEC in the Maiombe NP).  As the first step of the process, the project will support feasibility assessment of different forms of sustainable livelihood and community-based NRM given functional zones of the PAs defined under the Output 2.2. During the feasibility assessment the project will explore following options:

- Forms and procedures for involving local communities in the PA management process (can be done under the Output 2.2), including, establishment of community councils for the PAs, potential employment or other forms of direct engagement of community agents/eco-guards in the PA protection, community negotiators, educators, etc;

- Community-Based Forest and Wildlife Management and establishment of Community Management Areas (CMAs) in the PAs;

- Sustainable agriculture, conservation farming, agro-forestry, as alternative to unsustainable slash-and-burn practice;

- Sustainable use of fish and other freshwater resources;

- Effective techniques for HWC, especially HEC management through holistic planning approach;

- Initial community-based eco-tourism in the PAs;

- Perspective value chains and markets for community products and services;

- Potential for Integrated Conservation and Development Projects (ICDPs) and conservation partnerships with private sector and international donors to ensure sustainability of the community-based initiatives (e.g., Fair Trade, Rainforest Alliance, etc.).

- Based on the results of the feasibility assessment and experience of FAO, ADPP, FAS, Gremio ABC and other organizations in Angola and in the region, the project will develop Community Action Livelihood Plans for each project area as a part of ESMP, and will implement a set of specific vocational training programmes for selected local communities inside the PAs with focus on management of CMAs; sustainable use of non-timber forest products and fisheries; HEC prevention and management; sustainable/conservation farming and agro-forestry; bush fire safety, prevention and suppression techniques and tools; small business basics and establishment of cooperatives, including community nurseries for reforestation and small scale livestock breeding. The training programmes will be developed and implemented using approaches developed and successfully tested in Angola by the FAO, ADPP, and FAS including Field Farmer School, Farmers’ Club, Green Negotiated Territorial Development (GreeNTD), Sustainable Char-Coal, Conservation Agriculture, ADECOS, IUCN’s First Line of Defense against Illegal Wildlife Trade (FLoD) approach, and Conservation farming programmes of the TNC and Eco-exist. In total, the project is going to train 10,000-12,000 local people (50% of women) in the project areas. Experienced project partner selected for implementation of the Output 3.1 will also assist the PMU to implement ESMP, including following parts: Human Rights and Safety Action Plan, Community Livelihood Action Plan, and Gender Mainstreaming Strategy (Output 4.3).

- In parallel with capacity building activities, the project in strong cooperation with FAO, ADPP, FAS, Gremio ABC, AfDB, and other partners will develop and support following pilot projects of the local communities (the list of thematic projects can be updated and narrowed after the feasibility assessment):

- Establishment and operationalization of Community Councils at the Maiombe NP and Luando SNR based on the existing traditional leadership models;

- Establishment and running of Community Management Areas based on the PA-community agreements and in accordance with functional zoning of the PA, including sustainable collection and marketing of mushrooms, berries, fruits, honey, fish, mopane worms, grass, wood, etc. The project can develop and use attractive branding of the community products for effective marketing (e.g., Giant Black Sable or Forest Elephant Honey);

- HEC management projects based on holistic approach and land use planning, and including fencing, chilly and bee barriers, crop guarding, switching to chilly farming and growing of other crops unattractive for elephants;

- Switching from slash-and-burn agriculture in the forest and woodlands to sustainable use of fields around villages, located in the settlement and agriculture zones of the PAs. This kind of projects can significantly decrease frequency of bush fires, deforestation, and HWC. In Maiombe NP these initiatives will be conducted in strong cooperation with the Ministry of Agriculture (IDA), Provincial Government, and the AfDB Cabinda Province Agriculture Value Chains Development Project (see Partnerships section) and will provide not only environmental, but also strong social and economic benefits (potential ICDP);

- Family and local group small environment friendly business initiatives, like community gardens, medicinal plant plantations, tree nurseries, cane rat and small livestock breeding, production of daily ration packs for PA rangers, etc.;

- Village initiatives to prevent and control bush fires;

- Development of community agents/eco-guards network to assist in the PA protection;

- Establishment of community training centers on the base of local schools (these activities can help to restore destroyed schools in the PAs that can serve as a community environmental education centers at the same time).

- It is expected that as a result of the pilot projects at least 6,000 local people (50% are women) in Maiombe NP and Luando SNR will switch to CBNRM, SFM, SLM and other sustainable practices and will participate in the PA management via PA-Community Councils. Each of the supported pilot project should have simple business plans with sustainability options based on the economic profitability or continuing support from other public or private donors.

- Key partners for delivery of Output 3.1: Leading partners: Maiombe NP and Luando SNR, selected local communities, traditional leaders, IDA; Supporting partners: FAO, AfDB, ADPP, FAS, Gremio ABC, Administrations of Cabinda and Malanje Provinces and municipalities, Eco-Exist, JGI, Connected Conservation, relevant thematic experts (e.g., HEC experts).

- Deleted

Output 3.2. Public awareness campaign targeting IWT, bushmeat consumption, HWC and habitat degradation is developed and implemented in the project areas and at national level.

- The project will design and implement targeted outreach campaign for adult and children in Maiombe NP, Luando SNR, and at the national level based on the on-going MINAMB’s programmes and lessons learned from the experience of public campaigns in Angola and other countries (e.g., Kenya and Zimbabwe). The campaign will have a general plan for 5 years and detailed plans for yearly and monthly activities. Following indicative activities can be supported by the project (the list should be updated at the project start):

- Support of environmental clubs, education camps, school forestries and Climate Smart Gardens for schoolchildren living in the target PAs;

- Organization of Wildlife Festivals for target communities (e.g. Elephant or Giant Black Sable events) with active involvement of adults and kids;

- Organization of community and Parks joint sport events (e.g. football games between Park rangers and community members, shooting and specialized ranger competitions, etc.) to build trust, friendship and collaboration for conservation;

- Publication of brochures and booklets for local communities on criminal and administrative responsibilities and penalties for poaching, wildlife trafficking, illegal logging and mining;

- Stop Bush Fire campaign for local people in the Luando SNR;

- Involvement of palanca pastors, traditional leaders, and chiefs in outreach programmes for local communities on sustainable wildlife and forest use;

- Regular publication in local newspapers on the project progress and activities;

- MINAMB’s "Eu Não Como Carne de Caça" campaign on the national TV with national celebrities, radio and TV translation of interviews with environmental and conservation leaders;

- Exchange visits to successful community projects to pick up best experience;

- Targeted environmental education programme for government officials, including army and police, in the project areas;

- Focus groups for adults with clear and simple explanations of climate change, deforestation, bush fires and wildlife degradation consequences by leading experts; and

- Integrated theatre groups in communicating conservation information around local communities;

- MINAMB/INBAC's environmental education web-platforms.

- Law enforcement, government officials and private sector representatives should be involved in dialogue with local communities as much as possible to build strong trust and collaboration between different actors in conservation and sustainable development of the area.

- Key partners for delivery of Output 3.2: Leading partners: target local communities, INBAC, Maiombe NP and Luando SNR; Supporting partners: ADPP, JEA, Gremio ABC, National TV channels, Kissama Foundation, Maiombe Network, Ministry of Education, Department of Environmental education at MINAMB, Center of Information and Communication (CDI) at MINAMB, Ministry of Social Communication, National media, Wildlife Impact, JGI/Roots and Shoots, thematic experts.

- Deleted

Outcome 4. Lessons learned by the project through participatory M&E and gender mainstreaming are used nationally and internationally

Output 4.1. Participatory project monitoring, evaluation and learning framework is developed and implemented

- Participatory project monitoring and evaluation is a key part of the RBM approach practiced by UNDP and GEF for all project and programmes. Thus, the project will develop an M&E system and encourage stakeholders at all levels to participate in M&E to provide sufficient information for adaptive management decision-making.  For M&E, the project will use standard UNDP approaches and procedures and following groups of indicators:

- Output Indicators will be used to measure delivery of the project outputs (the project’s products and services) and monitor routine project progress on monthly and quarterly basis. Collection of information on the output indicators will be performed by the PMU and represented in the project Quarterly and Annual Reports;

- Outcome Indicators will be used to indicate the progress toward and achievement of the project outcomes (e.g. capacity or behavioral changes happened in result of use of the project outputs by target groups of stakeholders). Collection of information on the outcome indicators will be performed by the PMU and key partners or might require hiring of consultants. Project progress against outcome indicators will be reflected in the Annual, Mid-Term and Terminal Project Reports, GEF Core Indicator Framework, and Mid-Term and Terminal Evaluation Reports;

- Mid-Term Impact Indicators will demonstrate how the project outcomes contribute to mid-term project impacts (e.g. reduction of direct threats for Conservation and Sustainable Development Targets). Collection of information for mid-term impact indicators might require special consultants and appropriate expenses and will be performed generally at the project mid-term and completion to compare project progress in reducing key threats against baseline data. Information on mid-term impact indicators will be generally presented in the Mid-Term and Terminal Project Report and Terminal Evaluation Report;

- Long-Term Impact Indicators, or GEBs will be used to measure the level of achievement of the ultimate project impacts (status of wildlife populations, their habitats, improvements in the livelihood and benefits for target communities). Long-term project impacts can be only partially achieved during the project lifetime (6 years) and might fully materialize several years after the project is over. Particularly to measure long-term project impact, the project will support baseline and end of project population surveys for forest elephants, gorilla, chimpanzee, and black giant sable and remote sensing analysis of woodland cover in the project areas to qualify actual project impact on the wildlife population and habitat. Information for long-term impact indicators will be collected with wide involvement of the project partners and consultants and will be reflected in the included in the Mid-Term and Terminal Project Report and Terminal Evaluation Report.

- Gender and Social and Environmental Risk Indicators will be used to assess impact of the project activities on gender equality and involvement of women in sustainable wildlife and NR management. The project will conduct ESIA procedure at the Inception Phase and will develop an ESMP (budgeted under Output 3.1) with at least following parts: Human Rights and Safety Action Plan, Community Livelihood Action Plan, and Gender Mainstreaming Strategy (Output 4.3). The ongoing data collection on these ESMP indicators will be annually carried out by selected project partner for Output 3.1 that will assist PMU in implementation of the ESMP.

- Key partners for delivery of Output 4.1: Leading partner: INBAC; Supporting partners:  WCS, JGI, Kissama Foundation, all other partners, thematic experts.

- Deleted

Output 4.2. Lessons learned from the project are shared with national and international conservation programmes, including GWP

- An effective M&E system (Output 4.1) and regular analysis of M&E data will allow the project: (i) to identify the most effective project strategies; (ii) to check project assumptions (hypotheses) and risks; (iii) to prepare management response to changing political, economic, and ecological environment; (iv) to learn from successful and unsuccessful project experience; (v) to incorporate learning in the project planning and adaptive management; and (vi) share experience among GWP, GEF and other projects in Africa and the world. Lessons learned through the project cycle will be reflected in the Annual Project Reports to ensure that the project uses the most effective strategies to deliver project Outputs and achieve project Outcomes in the changing environment.

- To systemize and share its lessons and knowledge, the project will use different communication means including:

- A project page on the INBAC web-site with available project reports, publications, press-releases, datasets, draft and final legislative documents, developed management plans, etc.;

- Quarterly or 6 month project information bulletin;

- Special paper publications, including manuals, guidance, methodologies, etc.;

- Publications and presentations at the Virtual Knowledge Exchange hosted by the Global Wildlife Programme;

- Collaborative and experience exchange meetings with other GWP projects in Africa and Asia and other relevant projects;

- Exchange visits for local communities, PA and LE agencies to demonstrate the best practices;

- Publications in mass media, conservation, and scientific journals; and

- Other available communication tools and approaches.

- Key partners for delivery of Output 4.2: Leading partners: INBAC, target PAs, National media channels; Supporting partners: Environmental Crime Unit, Interministerial Commission on Wildlife Crime, other law enforcement agencies, local communities, NGOs

- Deleted

Output 4.3. Gender strategy developed and used to guide project implementation, monitoring and reporting

- The GEF project is going to build on the work of gender-oriented organizations experience to develop and implement an effective Gender Mainstreaming Strategy (as a part of ESMP) to guide the project implementation to:

- Build project partner capacity to mainstream gender and bring along with it globally tested approaches in Women Economic Empowerment strategies that empower women as agents rather than as victims of habitat degradation and climate change;

- Facilitate a multi-stakeholder analysis of the gender issues in all the different components of the programme that will inform the gender strategy and action planning with a clear set of measurable gender indicators.

- The project Gender Mainstreaming Strategy should include the following core components (also indicated in the Annex I. Gender Analysis and Mainstreaming Plan):

- Gender Analysis and Action Planning;

- Gender Mainstreaming Capacity Building in Implementing Partners, Stakeholder and the Community;

- Gender Mainstreaming Knowledge and Evidence Generation for Policy Influencing;

- Operational Monitoring, Evaluation, and Learning.

- Project partner selected for implementation of Output 3.1 will assist PMU in implementation of the Gender Mainstreaming Strategy.

- Key partners for delivery of Output 4.3: Leading Partners: INBAC, target PAs; Supporting partners: ADPP, other law enforcement agencies, local communities, NGOs

- Deleted

## Partnerships

- This GEF project is built on other baseline programmes and projects in Angola, designed to establish strong collaborations and partnerships with many of them (see the table below).

| Name of on-going and planned programme/project, years of implementation | Programme/project objectives and targets | How proposed UNDP/GEF project will collaborate with the programme/project? |
| --- | --- | --- |
| GOVERNMENT |  |  |
| Protection and Rehabilitation of Giant Sable Antelope Presidential Programme, 2017-ongoing Budget: $181,000 | Restoration and monitoring of the Giant Sable population in the Cangandala and Luando National Parks | Lessons learning and incorporation into the GEF project design and implementation; Partnerships with the Programme to deliver Outputs for Outcomes 2 and 3 in the Luando project area Representation of the Programme in the GEF Project Board Project co-financing |
| MINAMB’s Program for Biodiversity Conservation and Protected Areas, 2017-2020 Budget: $5,500,000 | Rehabilitation and development of National PA system | Lessons learning and incorporation into the GEF project design and implementation; Partnerships with the Programme to deliver Outputs for Outcomes 2 and 3 Representation of the Programme in the GEF Project Board Project co-financing |
| MINAMB’s Project to Support Parks and Reserves, 2017-2020 Budget: $3,600,000 | Rehabilitation and development of National PA system |  |
| INBAC’s National Project for the Zoning and Regulation of Parks, 2017-2020 Budget: $1,100,000 | Zoning and improvement of the PA system management |  |
| MINAMB’s Programme of the Transfrontier Conservation Initiative for the Mayombe Forest Budget: $812,00 | Contribution to the establishment of Mayombe Forest TFCA (International Treaty). Participation in the development of international conservation cooperation in the TFCA | Lessons learning and incorporation into the GEF project design and implementation; Partnerships with the Programme to deliver Outputs for the project Outcomes 1-3 in the Cabinda project area Representation of the Programme in the GEF Project Board Project co-financing |
| FAS Social Development Programme, ongoing | Promotion of sustainable economic and social development of the communities in Angola, including sustainable agriculture practices | Lessons learning and incorporation into the GEF project design and implementation; Partnerships with the Programme to deliver Outputs for the Outcome 3 Representation of the Programme in the GEF Project Board |
| BI-LATERAL AND MULTI-LATERAL AGENCIES |  |  |
| German Financial Cooperation with SADC Kavango-Zambezi Transfrontier Conservation Area (KAZA TFCA) Phase III, 2017-2020 Budget: $18,200,000, including $3,531,000 for Angola’s part | To support the development of the KAZA TFCA by establishing appropriate organizational structures at regional, national and local levels, facilitating integrated management of natural resources, improving the management of protected and wildlife dispersal areas, and uplifting the socioeconomic conditions of the targeted local populations, clearly demonstrating desired impact at both biodiversity and socio-economic levels. Including support for infrastructure of Luengue-Luiana NP, ranger training, SMART introduction, and CBNRM support on Angolan side. | Lessons learning and incorporation into the GEF project design and implementation; Project co-financing |
| DEFRA IWT Challenge Fund’s Developing investigation & Prosecution Capacity to Save Angola’s Elephants Project (implemented by the Stop Ivory/EPI), 2017-2020 Budget: $438,000 | Review of penalties and application in wildlife crime Best practice handbook on wildlife crime prosecutions for prosecutors and the judiciary Deliver skills-based training course on wildlife crime prosecutions for 30 prosecutors and 20 magistrates/judges Implement national wildlife crime recording database Desktop scoping study of Angola’s historical and current ivory trade. Scoping visit to Luanda – on-site assessment of ivory markets, interviews with traders and law enforcement officials and production of report for investigations First investigation on Angolan ivory trade including site visits and interviews. | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcome 1 Representation of the Project in the GEF Project Board; Project co-financing |
| USFWS Cooperative Agreement “Building the Capacity of the Government of Angola in Countering Wildlife Trafficking in Cabinda Province” (implemented by the Wildlife Impact), 2018-2019 Budget: $222,510 | Assessment of legislation relevant to CITES implementation and wildlife crime. Roundtable review of legislation framework recommendations; Develop permit system and enforcement database to support national CITES authorities Training on CITES/Angolan law as legal basis for enforcement and prosecutions High-level enforcement and intelligence mentoring/training workshop Community Training in Maiombe National Park and Cabinda Province Wildlife confiscation and disposition training | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcomes 1-3 in the Cabinda project area and at National level; Representation of the Project in the GEF Project Board; |
| FAO Angola Country Programme, 2013 - ongoing | Strengthening smallholder production and productivity to improve food security and nutrition, enabling farmers to apply improved production techniques through Farmer Field Schools; Strengthening sustainable management of natural resources; Increasing resilience of rural livelihoods to climatic shock and climate change, through the development and application of an integrated Disaster Risk Reduction and Management Plan | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcome 3; Participation in the GEF Project Board; |
| AfDB Cabinda Province Agriculture Value Chains Development Project, 2017-2021 Budget: $123,150,000 | Improvement of production, storage, processing and marketing infrastructure necessary for food crops, cash crops, marine and inland fisheries, small ruminants, and horticulture; Rehabilitation of water conveyance structures necessary for irrigation; Training for value chain actors in technical and managerial skills; Rehabilitation/construction of rural infrastructure in the communities and improvement of rural energy access. Establishment of a credit facility for rural communities | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcome 3; Participation in the GEF Project Board |
| World Bank led Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development, 2015- ongoing | The GWP is a $131 million grant program designed to address wildlife crime across 19 countries in Africa and Asia. The GWP serves as a platform for international coordination, knowledge exchange, and delivering action on the ground. The GWP builds and strengthens partnerships by supporting collaboration amongst national projects, captures and disseminates lessons learned, and coordinates with implementing agencies and international donors to combat IWT globally. | Lessons learning and incorporation into the GEF project design and implementation; Exchange of lessons and best practices with other GWP Child Projects. |
| EU’s FRESAN Project (Strengthening resilience and food and nutritional security in Angola), 2017-2023 Budget: $76,000,000 | Sustainable agricultural resilience and production; Improving nutrition through education and social programmes; Institutional reinforcement and multisectoral information management Project area: Cunene, Huila and Namibe Provinces | Lessons learning and incorporation into the GEF project design and implementation; Participation in the GEF Project Board. |
| INTERNATIONAL AND NATIONAL NGOs |  |  |
| GardaWorld-supported Strengthening Angola’s Criminal Justice System for Wildlife Project (implemented by Stop Ivory/IPE), 2018 Budget: $134,000 | Phase One Anti-Poaching Ranger Training Knowledge Exchange Trip for senior Angolan ministry personnel (January, 2018) Rapid Needs Assessment (RNA) for protected area management of Luengue-Luiana and Quicama and Management Action Plans (MAP) (June, 2018) Phase Two Anti-Poaching Ranger Training: Development of funded ranger training programme for induction of new recruits into INBAC over the next three years, including training trainers and on-going mentoring at the Menongue Ranger Training School (pending funding, to start 2018) | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcomes 1 and 2; Representation of the Project in the GEF Project Board; Project co-financing |
| ICCF Programme to establish Conservation Caucus and support wildlife conservation in Angola, 2017 - ongoing | Establishment of functional Conservation Caucus in Angola; Support for wildlife crime law enforcement and conservation in Angola | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcomes 1 and 2; Representation of the Project in the GEF Project Board; Project co-financing |
| ADPP Agriculture, Rural and Economic Development Programme, ongoing | Farmers’ Clubs, including Women’s Farmers’ Clubs project to provide local people with the knowledge, tools and resources necessary to sustainably improve agricultural production; Sustainable Charcoal Project | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcomes 3; Representation of the Project in the GEF Project Board; Project co-financing |
| Wild@Life Chimpanzee Rescue Project in Cabinda Angola, ongoing | Capacity building for Maiombe NP rangers to fight illegal logging and wildlife crime. Establishment of rehabilitation facility for chimpanzees confiscated from poachers in Cabinda | Lessons learning and incorporation into the GEF project design and implementation; Partnership to deliver the project Outputs 2.1, and 2.2 in the Maiombe NP |
| EU-funded Southern Africa Illegal Wildlife Trade regional training facility for KAZA TFCA Project (implemented by the Space for Giants and Tihokomela Trust), 2018-2020 Budget: $1,766,000 | A trans-frontier wildlife law enforcement training facility in Boro, Botswana Wildlife law enforcement training curriculum 250 people across KAZA will be trained and mentored (rangers/intelligence investigators/ public investigators/ community management staff) KAZA TFCA satellite communications network | Lessons learning and incorporation into the GEF project design and implementation; Potential partnership to deliver the project Outputs 1.3 |
| GEF PROJECTS |  |  |
| UNDP/GEF Iona National Park Project, 2013-2018 Budget: $8,405,000 | The project focused on the support of the government in the establishment and operationalisation of the ‘Department of Conservation Areas’ within the recently approved Instituto Nacional de Biodiversidade e Áreas de Conservação (INBAC) and rehabilitation of the largest National Park in Angola, Iona National Park (15,150 km²). | Lessons learning and incorporation into the GEF project design and implementation |
| UNDP/GEF Project “Expansion of Angola’s Protected Areas System”, 2015-2020 Budget: $6,300,000 | The project will increase the coverage of terrestrial PAs in Angola, enhance the capacity of the PA authority to deliver PA functions, including management planning, monitoring, surveillance of malpractices and law enforcement; and will address the needs of PA adjacent communities, for example by managing human-wildlife conflicts and developing activities that generate local socio-economic benefits. | Lessons learning and incorporation into the GEF project design and implementation; Representation of the Project in the GEF Project Board; Delivery of the Outputs for Outcomes 2 and 3 in the project areas. |
| UNDP/GEF OKACOM UNDP Demonstration Projects (implemented by ACADIR), 2018-2019 Budget: $164,500 | Support of local communities in the Cubango-Okavango basin (1) to empower them to increase crop yields and improve resilience against climate change, while at the same time protecting and stimulating the biological functioning of the land; and (2) develop sustainable fishery practices | Lessons learning and incorporation into the GEF project design and implementation; |

## Stakeholders’ engagement

- This project was developed using transparent, open, and fully participatory approach with the involvement of all groups of relevant stakeholders (government organizations, multilateral and bilateral agencies, NGOs, local communities, and the private sector) at national and project area levels. Individual and focus group consultations were conducted in Luanda City, Luando SNR (with representatives of Capunda, Kunga Palanca and Quimbango villages), Luquembo village, Cabinda, and Maiombe NP, Cabinda Province, where meetings and informal conversations were held in the municipalities of Belize and Buco Zau. Special consultations and meetings were conducted with MINAMB, INBAC, FAS, FAO, AfDB, ADPP, KAZA and Mayombe TFCA Secretariats, ICCF, Stop Ivory, EPI, EIA, Wildlife Impact, UNODC, and other organizations. E-mail communication and Skype calls took significant part of consultative process with national and international stakeholders. Key objectives of consultative process were the following:

- Inform all group of stakeholders on the project preparation and allow them to participate in the project development and share their concerns about the project proposed implementation;

- Evaluate current level of key threats for wildlife, key ecosystems, and communities at the national level and in the project areas and identify obvious barriers on the way of sustainable development;

- Collect information on baseline programmes and projects related to the project objective;

- Understand local, cultural and political context in the country and the project areas;

- Assess current capacity of government agencies and local communities to combat wildlife crime and manage natural resources sustainably;

- Develop relevant project Outputs based on key national and project area needs;

- Conduct Social and Environmental Screening Procedure and identify key risks for the project implementation;

- Clearly define project area for interventions and collect information on Outcome and Impact Indicators; and

- Identify potential project partnerships (see Partnerships section) and clarify stakeholder roles in the project implementation.

- A total of 155 stakeholders were consulted (25% females and 75% males). Based on our observations during the stakeholder engage exercise, we noted the need to deliberately focus on women as key stakeholders in order to amplify their voices (see Mainstreaming Gender section of the ProDoc and Annex I. Gender Mainstreaming Analysis and Plan).

- As a result of Stakeholder Analysis, the following groups of stakeholders were identified for project implementation (excluding some of stakeholders already mentioned in the Partnerships section) (see details in Annex H. Communication/Stakeholder Engagement Plan).

| Stakeholders | Functions | Role in Project | Key Engagement Strategies |
| --- | --- | --- | --- |
| Government |  |  |  |
| Ministry of Environment (MINAMB) | Responsible for conservation and sustainable management of natural resources, protection of biodiversity and endangered species, establishment and support of Protected Areas. | Implementing Partner and the Project Board Chair Direct participation in the delivery of Output 1.1 (policy and legislation) Project co-financing | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| Ministry of Interior (National Police) | The mission of the National Police Force is to: enforce law and order; execute police duties while respecting human rights and freedoms; protect private and public property; prevent, detect and investigate crime; and defend the country and ensure its security. | Key project partner to deliver the project Outputs 1.1-1.2, and 2.1. Participation in the Project Board | Inception Workshop, Project Board meetings, informing on the project progress, working meetings, M&E activities |
| Ministry of Agriculture and Forest (MINAGRIF) | Support of national agricultural development, sustainable management and protection of forest and wildlife resources outside the Protected Areas | Key project partner to deliver Outputs 1.1-1.2, 2.1.,2.2, and 3.1. Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| Ministry of Defense | Development and supervision of Angolan army, navy, and air force. | Key project partner to deliver Outputs 1.2, and 2.1 in cooperation with other law enforcement agencies. | Inception Workshop, informing on the project progress, working meetings |
| Ministry of Social Action, Family, and Women Promotion | Development and implementation of social services, family and women support programs in Angola | Project partner for Outputs 3.1, 4.1-4.3. Consulting of the project team on gender mainstreaming issues | Inception Workshop, informing on the project progress, working meetings |
| National Institute for Biodiversity and Protected Areas (INBAC) | Conservation of biodiversity and management of protected areas; Designing of programme and land planning within conservation areas; Environmental studies in order to preserve the wildlife and biodiversity; Development of protected areas system; Wildlife Crime law enforcement in the PAs | Key beneficiary of the project Direct participation in the delivery of all project Outputs; Participation in the Project Board Project Management | PMU, Inception Workshop, Project Board meetings, M&E activities |
| National Forest Development Institute (IDF) | Sustainable management, protection and restoration of forest and wildlife resources in the country | Key project partner to deliver Outputs 1.1-1.2, 2.1.,2.2, and 3.1. Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| National Environmental Crime Unit | The national multi-agency body responsible for investigation and prosecution of wildlife crime in Angola, including poaching, IWT, and wildlife trafficking | Key project partner to deliver Outputs 1.1-1.2, and 2.1 and key beneficiary of the project Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora | Ensuring compliance with environmental legislation on environmental crimes, gather information, monitor and prohibit hunting and illegal harvesting of wildlife and related products, through trade and illegal trafficking of endangered species, including export, import and transit and fulfill the obligations of Angola under the Convention's implementation on International Trade in Endangered species (CITES) and other conventions related to biodiversity conservation. Includes following members and leadership of the MINAMB: - Minister of Defence; - Minister of Interior; - Minister of Justice and Human Rights; - Minister of Finances; - Minister of Agriculture; - Minister for Fisheries; - Minister of Petroleum; - Minister of Transportation; - Minister of Communication | Key project partner to deliver Outputs 1.1-1.3, and 2.1 Participation in the Project Board Participation in the project M&E | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| General Prosecutor’s Office of Angola | Prosecution of crimes, including wildlife crime; Reformation and improvement of the administration of criminal justice. | Key project partner to deliver Outputs 1.1, 1.2, and 2.1 | Inception Workshop, working meetings and trainings, M&E activities |
| National Customs Service | Investigation, prosecution and prevention of trafficking of illegal goods, including wildlife products | Key project partner to deliver Output 1.2 | Inception Workshop, informing on the project progress, working meetings and trainings, M&E activities |
| 31st of January Environmental Polytechnic Institute (Wildlife School) in Menongue | Capacity building for PA rangers via comprehensive training programmes | Key project partner and beneficiary to deliver Output 1.3 | Inception Workshop, working meetings and trainings, M&E activities |
| Government of Cabinda Province | Sustainable economic and social development of the province, environmental protection | Project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| Government of Malanje Province | Sustainable economic and social development of the province, environmental protection | Project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| Government of Bie Province | Sustainable economic and social development of the province, environmental protection | Project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, M&E activities |
| Maiombe NP | Protection and sustainable management of the Maiombe forest, wildlife and forest crime law enforcement, development of cooperation with local communities | Key project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 and beneficiary of the project. Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, implementation of project activities, M&E activities |
| Luando SNR | Protection and sustainable management of the miombo woodlands and wildlife, wildlife and forest crime law enforcement, development of cooperation with local communities | Key project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 and beneficiary of the project. Participation in the Project Board | Inception Workshop, Project Board meetings, working meetings, implementation of project activities, M&E activities |
| UN agencies |  |  |  |
| UNDP CO | Assistance in sustainable development and achievement of SDGs in Angola | Project oversight Participation in the Project Board for Project Assurance | Inception Workshop, Project Board meetings, M&E activities |
| UNODC | Assists Member States in their struggle against illicit drugs, crime and terrorism. In the Millennium Declaration, Member States also resolved to intensify efforts to fight transnational crime in all its dimensions, to redouble the efforts to implement the commitment to counter the world drug problem and to take concerted action against international terrorism. | Assistance to the Angola Government and PPG team to conduct ICCWC IF assessment Consulting the project team on the Outputs 1.1-1.3. Participation in the monitoring of Angola’s national capacity to control wildlife crime in the project framework | Inception Workshop, consultations and working meetings, trainings for law enforcement staff, ICWCC IF workshops |
| FAO Angola | Strengthening smallholder production and productivity to improve food security and nutrition, enabling farmers to apply improved production techniques through Farmer Field Schools; Strengthening sustainable management of natural resources; Increasing resilience of rural livelihoods to climatic shock and climate change, through the development and application of an integrated Disaster Risk Reduction and Management Plan | Lessons learning and incorporation of them into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcome 3; Participation in the GEF Project Board; | Inception Workshop, Project Board meetings, working meetings and consultations, implementation of project activities, M&E activities, exchange of experience |
| International Partnerships and TFCAs |  |  |  |
| EPI | Assistance to member countries to implement IUCN African Elephant Action Plan (AEAP) and combat ivory trade. Development of NEAP in Angola | Participation in the project development Assistance to the project team to deliver Outputs 1.1-1.3 | Inception Workshop, consultations and working meetings. |
| Mayombe TFCA Secretariat | Promotion of conservation and sustainable development in Mayombe Forest Transboundary Landscape in Gabon, Congo, DRC, and Angola. | Participation in the project development Key partner to deliver Outcomes 1-4 in the Maiombe NP; Participation in the GEF Project Board; | Inception Workshop, Project Board meetings, working meetings, implementation of project activities, M&E activities |
| NGOs |  |  |  |
| Kissama Foundation | Management of the Presidential Programme for restoration and conservation of the black giant sable | Participation in the project development Key partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2. Participation in the Project Board Project co-financing | Inception Workshop, Project Board meetings, working meetings, implementation of project activities, M&E activities |
| Stop Ivory | Implementation of the Strengthening Angola’s Criminal Justice System for Wildlife Project and Developing investigation & Prosecution Capacity to Save Angola’s Elephants Projects (see Partnerships section) | Participation in the project development Key partner to deliver Outputs 1.1-1.3 Participation in the Project Board Project co-financing | Inception Workshop, Project Board meetings, working meetings, implementation of project activities, M&E activities |
| 51 Degrees Ltd. | Capacity building programmes for wildlife rangers on anti-poaching and law enforcement Participation in the implementation of the Strengthening Angola’s Criminal Justice System for Wildlife Project leaded by the Stop Ivory | Key partner to deliver Outputs 1.3 and 2.2 (training programmes for PA rangers) | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| Wildlife Impact | Implementation of the Project “Building the Capacity of the Government of Angola in Countering Wildlife Trafficking in Cabinda Province” (see Partnerships section) | Participation in the project development Key partner to deliver Outputs 1.1-1.3 at National level, and Outcome 2 in the Maiombe NP | Inception Workshop, consultations and informing. |
| Environmental Investigation Agency (EIA) | Participation in the implementation of the Developing investigation & Prosecution Capacity to Save Angola’s Elephants Project leaded by the Stop Ivory | Key partner to deliver Outputs 1.1-1.2 | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| Space for Giants | Implementation of the Southern Africa Illegal Wildlife Trade regional training facility for KAZA TFCA Project (see Partnerships section) | Potential partner to deliver Outputs 1.1-1.3 | Inception Workshop, working meetings and consultations |
| ADPP | Farmers’ Clubs, including Women’s Farmers’ Clubs project to provide local people with the knowledge, tools and resources necessary to sustainably improve agricultural production; Sustainable Charcoal Project | Lessons learning and incorporation of them into the GEF project design and implementation; Partnership to deliver Outputs for the project Outcomes 3; Participation in the Project Board; Project co-financing | Inception Workshop, Project Board meetings, working meetings, implementation of project activities, M&E activities |
| Gremio ABC | All community-related aspects of conservation in Cabinda province and in the Mayombe TFCA | Key partner to deliver Outputs 3.1 and 3.2. in Maiombe NP | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| WCS Congo | Conservation and monitoring of forest elephant, gorilla and chimpanzee in the Congo Basin, including the Republic of the Congo | Key partner to develop monitoring programme, design and manage population surveys for forest elephant, gorilla and chimpanzee in the Cabinda NP and adjacent area of Congo. Participation in the delivery of 2.2 and 4.1. | Inception Workshop working meetings, implementation of project activities, M&E activities |
| Jane Goodall Institute | Conservation and monitoring of chimpanzee populations in Congo Basin | Participation in the delivery of outputs for Outcomes 2, 3 and 4 in the Maiombe NP | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| Maiombe Environmental Network | The National Association of Environmental NGOs | Potential partner to deliver Outputs 3.1 and 3.2. | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| ADRA | National NGO, focusing on agriculture development with communities | Potential partner to deliver Output 3.1. and 3.2. | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| JEA | National environmental NGO, focusing mainly on environmental education | Potential partner to deliver Output 3.2. | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| Maisha Group | Strategic consulting based on advanced intelligence, innovative technology, and big data analysis | Potential partner to deliver Outputs 1.2, 2.1 and 2.2 | Inception Workshop, Project Board meetings, working meetings, participation in trainings, M&E activities |
| Vulcan | Advanced technology to support law enforcement | Potential partner to deliver Outputs 1.2, 2.1 and 2.2 | Inception Workshop, working and coordination meetings |
| EcoExist | Fostering co-existence between elephants and people and developing conservation farming projects with local communities, in the KAZA region (http://www.ecoexistproject.org/) | Potential partner to deliver Outputs 3.1. and 3.2. | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| Connected Conservation | Anti-poaching solutions and HWC mitigation through holistic planning | Potential partner for HWC mitigation planning, policy development and trainings for PA rangers and local people under Outcomes 1-3. | Inception Workshop, working meetings, implementation of project activities, M&E activities |
| Local communities |  |  |  |
| Local communities living inside and outside the Luando SNR: Capunda, Kunga Palanca, Quimbango, Kissonde, Dombo, Seque, Caionde, Zimbo, Simbanda, Tunda, Singuengo, Papo Seco, Sangamba, Siminhe, Sweka, Missongue, Ngunga, and Walitcha | Practicing subsistence agriculture, char-coal production, NTFP consumption, fishing and bushmeat hunting. Some community members are involved in illegal logging, commercial bushmeat trade and high-value species poaching. | Key partner to deliver project Outputs 2.2, 3.1 and 3.2 and major beneficiary of the project Participation in the Project Board | Inception Workshop, Project Board meetings, Technical Committee, regular meetings and consultations with local communities, implementation of project activities, M&E activities |
| Local communities living inside and outside the Miombe NP: to be selected at project inception phase, among communities residing in the Municipalities of Miconge, Buco Zau and Cacongo | Practicing subsistence agriculture, char-coal production, NTFP consumption, fishing and bushmeat hunting. Some community members are involved in illegal logging, commercial bushmeat trade and high-value species poaching. | Key partner to deliver project Outputs 2.2, 3.1 and 3.2 and major beneficiary of the project Participation in the Project Board | Inception Workshop, Project Board meetings, Technical Committee, regular meeting and consultations with local communities, implementation of project activities, M&E activities |

## Mainstreaming Gender

- Gender equality and women’s empowerment are matters of fundamental human rights and social justice, as well as a pre-condition for societies to thrive towards inclusive development. As unequal opportunities persist between women and men worldwide that delays any development effort, gender equality and women´s empowerment was prioritized simultaneously as a goal itself by the United Nations, the 5th of the 17 Sustainable Development Goals (SDGs), and a cross cutting issue throughout the Agenda 2030. Gender equality implies equal treatment of women and men in laws and policies, including equal access to resources and services within families, communities and society. Statements from UN Women have noted that SDGs cannot be achieved without the full participation and engagement of both women and men. Therefore, the achievement of any development goal implies a gender mainstreaming approach that consists of a comprehensive analysis of all the specific needs and interests of women and men in order to come up with effective interventions that enable both to equally participate and benefit from development efforts, including this UNDP/GEF project.

- According to Global Gender Gap Index (GGI), published by the World Economic Forum in 2017, Angola was ranked 123, out of 144 countries polled, with one of the lowest scores of 0.640, in Sub-Saharan Africa (SSA), and the rest of the world. This value has not improved much since 2006, when Angola was ranked 96 out of 115 countries.

- Despite the country’s rapid post-war economic growth based on oil production, Angolan society is still characterized by a wide disparity between women and men with regard to education, health, income, political rights, access to basic services such as energy, water and sanitation, housing, land for cultivation and credit. Although 52% of the total 25.8 million Angolan nationals are women, they are overall less literate than men. The 2014 National Census states that 66% of the population aged 15 years and older is able to read and write, including 80% of men and only 53% of women. The current index of gender inequality in access to education in Angola is 0.64, which is still far from the 0.99 value announced by the Angolan Government as a national goal under implementation of the Basic Law for the Education System of 2004 (MINFAMU, 2017: 24). Due to their lower level of literacy and technical education, women and girls account less as paid workforce than men, as they engaged mainly in informal employment. In fact, about 45% of women aged 15 or over are economically active in comparison with 61% of men of the same age group (MINFAMU, 2017: 47).

- The national employment rate was about 40%, with 34.4% in urban areas and 50% in rural areas. At the same time the employment rate for women aged between 15 and 64 years is 34% and 47% for men of the same age group. The unemployment rate in urban areas reached 31% against 14.3% in rural areas with 25% among women and 24% among men (MINFAMU, 2017: 47).

- Consequently, women in the country hardly benefit from existing legal rights such as maternity leave, social security and decent wages, which put them into severe employment vulnerability. During the country mission it was noticed that women play a crucial role in rural communities as a very significant proportion of the work force in food production and as the key players in managing and sustaining their natural resources and environment. Nevertheless, as pointed out by them, women need appropriate skills and control over land and production inputs, as well as more access to trading and credit opportunities in the local markets in order to successfully manage their livelihoods. Currently women struggle to get employed or hold the least qualified jobs in the formal labor market. As a result, the informal labor sector is the last resort for many women to sustain themselves and their families. Due to the lack of equal educational and professional opportunities, women tend to be underrepresented in decision-making forums and institutions, and experience numerous forms of gender inequality.

- Although equality between women and men is enshrined in the constitution and the objective of several recent laws and policies, the influence of traditional laws and culture often implies in a certain discrimination against women, including with regard to ownership of property, increasing the social vulnerability of women within society. To improve this situation in the context of the UNDP/GEF project, appropriate gender and social measures have been fully considered in the project design, and gender accountability is a cross-cutting issue that will be tracked as part of the project M&E system.

- This GEF project can be classified as Gender targeted (result focused on the number or equity (50/50) of women, men or marginalized populations that were targeted) with strong gender interventions incorporated in the project design. During the project development, the PPG team tried to involve as many women as possible in the consultation process. However, overall women’s participation was much lower (21% only) due to traditional male dominance in anti-poaching, wildlife and environmental management issues at the national level and in the project sites.

- To implement gender mainstreaming, the project will develop and implement an effective Gender Mainstreaming Strategy (Output 4.3) as a part of the ESMP. The strategy will guide the project implementation to build project partner capacity to mainstream gender and bring along strategies that empower women as agents rather than as victims of wildlife depletion, habitat degradation, and climate change. This strategy will also facilitate a multi-stakeholder analysis of the gender issues with a clear set of measurable gender indicators.

- The key guidelines for the strategy are outlined below:

- Gender balance will be ensured as much as possible regarding women participation in the Project Board and in the PMU. Project interventions will seek a greater and more even gender representation with the potential for gender mainstreaming-related activities at the national level and in the project areas - Maiombe NP and Luando SNR. Furthermore, relevant gender representation will be pursued in the project management. All project staff recruitment shall be specifically undertaken inviting and encouraging women applicants. The TORs for key project staff all incorporate gender mainstreaming related responsibilities.

- In response to the relatively low participation of women in the project development, the project will incorporate gender considerations in the implementation procedures in a number of different ways:

  - Empower women by involving them in policy and legislation review, management planning processes to combat wildlife crime and manage wildlife, including capacity building activities and law enforcement of wildlife crime under Components 1 and 2;

  - Strong focus on rural communities and gender within Components 3 and 4 with an emphasis on involving women in development and implementation of pilot projects on CBWM, CBNRM, HWC management; development and alternative sources of income and value-chains for local communities in the project areas that have an emphasis on female-led activities (e.g. collection of fuelwoods and/or NTF products);

  - All awareness raising activities will specifically target women and encourage them to take responsibilities including for engagement with the authorities with respect to natural resource management, illegal killing and trading of wildlife products and live animals;

  - Women’s organisations (associations and clubs) will be involved in project implementation and capacity development at national, provincial and communal levels.

- The project will adopt the following principles in the day to day management: (i) gender stereotypes will not be perpetuated; (i) women and other vulnerable groups will be actively and demonstrably included in project activities and management whenever possible, and (iii) derogatory language or behaviour will not be tolerated.

- The project will promote gender mainstreaming and capacity building within its project staff to improve understanding of gender issues, and will appoint a designated focal point for gender issues to support development, implementation, monitoring and strategy on gender mainstreaming internally and externally. This will include facilitating gender equality in capacity development and women’s empowerment and participation in the project activities. The project will also work with UNDP experts in gender issues in Luanda to utilize their expertise in gender mainstreaming. These requirements will be monitored by the UNDP Gender Focal Point during project implementation.

- The project will use gender disaggregated indicators in the PRF for regular monitoring and evaluation of the project progress and reporting, and will facilitate involvement of women in the M&E and Grievance Redress Mechanism implementation (see Table below and Annex I. Gender Analysis and Mainstreaming Plan).

Proposed gender mainstreaming activities in the project components

| Project Components | Measures relating to gender mainstreaming |
| --- | --- |
| Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime | - Active outreach to women and women’s groups to participate in the review and update of the policy and legislation documents; Ensure participation of at least 25% of women in the various law enforcement training sessions organized by the project; Promotion of potential involvement of women in the law enforcement staff of the INBAC and ECU at national and provincial levels. |
| Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation | Active involvement of women in the PA management plan development and realization process, including PA-Community Councils; Involvement of women in capacity building trainings for the Maiombe NP and Luando SNR staff; |
| Component 3. Engaging local communities in sustainable wildlife, forest, and PA management | Gender sensitive consultations on development and implementation of community NRM plans; Through 50/50 policy for training, provide women friendly training facilities to increase their capacity in CBNRM, CBWM, SFM, SLM, and HWC management and alternative income livelihoods in the project areas. Active involvement of women in the planning and implementation of pilot projects on CBWM, CBNRM, HWC, and activities that foster alternative livelihood income sources and value-chains for local communities in the project areas; Develop fair rules for distribution of the project community based initiatives benefits to women and marginalized groups in the target communities; Ensure effective participation of women in natural resource management groups and PA-Community Councils in the target PAs; Increase the focus of interventions on female-headed households as beneficiaries of the projects. |
| Component 4. Knowledge Management, M&E and Gender Mainstreaming | Apply gender specific analysis in the project M&E; Active involvement of women in the project M&E processes; Incorporate gender issues in the process of lessons learning; Involve women and women organizations in generation gender lessons; Develop and implement a project gender strategy; Consider gender related reporting in KM and Lessons Learnt reports; |
| Project Management | Ensure that both men and women are visible and inclusive in the project documents; Collect gender-sensitive data (age, ethnicity, income, education) for reporting and planning; Apply gender clause to human resource recruitment, encouraging the applications from women candidates and their hiring; At inception: gender screening of the project design and workplan; TORs of all staff to include specific responsibilities, which support mainstreaming of gender throughout project implementation. |

## Project Risks and Mitigation Measures

- During the PPG process and SESP assessment, a set of key project risks was identified (see Table below and Annex J. UNDP Risk Log). As per standard UNDP requirements, the project will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log.  Risks will be reported as critical when the impact and probability are high (i.e., when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher). Management responses to critical risks will also be reported to the GEF in the annual PIR. Please refer to Annex J UNDP Risk Log for a detailed matrix of project risks and mitigation measures.

- The Social and Environmental Screening Procedure (SESP) was followed during project preparation, as required by the SESP Guidance Note of the UNDP. Accordingly, the social and environmental sustainability of project activities is in compliance with the SESP for the project (see Annex G. UNDP Social and Environmental and Social Screening Template). The SESP identified moderate social and environmental risk for this project (see details in the Annex G) that would have potential negative impacts in the absence of safeguards in the conditions of ineffective project management. There are no any indigenous people in the project areas, therefore the project will not affect their rights and livelihood in any way. To avoid any potential risks for any likely impacts, the project will conduct ESIA and develop ESMP at the project Inception Phase, that will include at least following parts: Human Rights and Safety Action Plan, Community Livelihood Action Plan, and Gender Mainstreaming Strategy (Output 4.3).   The ESIA will be completed and ESMP developed before any project activities may start. Responsibility on implementation and monitoring of the ESMP will be assigned to an experienced project partner (organization) selected for implementation of the Output 3.1 that will work in cooperation with Technical Committees in the project areas and assist PMU in implementation of ESMP. The project staff and partners will ensure social and environmental screening of all proposed investments to determine if there are any negative impacts. If the impacts are considered significant or cannot be managed by simple and practical mitigation measures that can be implemented within the capacity of the communities and other stakeholders, these activities will be avoided. The Project Board will monitor social and environmental risk for the project activities on the annual bases (representatives of local communities in the project areas will be part of the Project Board) using information and recommendations provided by Technical Committees in the project area and project partner for implementation of the Output 3.1. Annually supervision missions of the PMU will assess the extent to which the risks have been identified and managed. Overall, the project is expected to result in positive impacts for biodiversity conservation and socio-economic benefits through the greater participation of local communities in NR management, improved PA management. However, the project will significantly strengthen law enforcement and protective regime of the Maiombe NP and Luando SNR and may have potentially negative impact on human rights of local communities, access to critical and limited natural resources. Other proposed measures for the risk mitigation are included in the Project Risks and Mitigation Matrix above and the Annex G.

- In line with UNDP standard procedures, the Project will set up and manage a grievance redress mechanism (GRM) as recommended by UNDP (2014) that would address project affected persons’ (PAP) grievances, complaints, and suggestions. The GRM will be managed and regularly monitored by the GRM Sub-Committee of the Project Board and Technical Committees in the project areas. It will comply with the following requirements:

- Uptake. The GRM will have multiple uptake locations and channels. PAPs in the project areas will be able to submit complaints or suggestions to assigned members of the Project Board (PB) (GRM Sub-Committee) in person, via mail, email, via special page of the Project web site and telephone. These channels will be locally appropriate, widely accessible and publicized in written and verbal forms on all project communication materials, and in public locations in the project areas. Since the project will be dealing with local community members, they will be facilitated to communicate their problems directly to the PMU staff, INBAC, project partners, and M&E experts. These entities will be responsible for the functioning as an interface for the grievance redress mechanism.

- Sort & process. All grievances will be registered by the GRM Sub-Committee and assigned a unique tracking number upon its submission. GRM Sub-Committee will maintain a database with full information on all submitted complaints and responses taken. These data are important to assess trends and patterns of grievances across the Project districts and for monitoring & evaluation purposes.

- Investigate & act. Strict complaint resolution procedures will be developed and observed, and a person at the GRM Sub-Committee will be assigned to handle the grievances. GRM Sub-Committee will develop clear and strict grievance redress procedures and assign responsibilities. Complaints that are beyond the Project scope will be conveyed by PMU to relevant local or regional authorities in the project areas. Difficult situations and conflicts will always be brought to the attention of the Project Board and UNDP CO. A repository of all the grievances received from the different stakeholders will be maintained at the GRM Sub-Committee for monitoring and evaluation purposes and also for learning. This aspect will be facilitated through Outcome 4 relating to communication and knowledge sharing. Further, this information will be used to assess trends and patterns of grievances across current and future PAs and for monitoring and evaluation purposes.

- Provide feedback. Feedback will be provided in response to all registered grievances. GRM Sub-Committee will provide feedback by contacting the complainant directly (if his/her identity is known), by reporting on actions taken in community consultations and/or by publishing the results of the complaints on the Project web site, local newspapers and as part of project materials. Once some decisions/actions are taken on a complain, the complainant will be informed about that.

- Enable appeals. Complainants will be notified of their right to appeal the decision taken by the GRM Sub-Committee. If complainants are not satisfied with GRM Sub-Committee response to their grievance, they will be able to appeal to GRM Sub-Committee again via mail, e-mail or the Project web site. Environmental and social grievances will be reported to the GEF in the annual PIR. The full SESP screening report is included in Annex G.

- Monitoring and evaluation: All information about the grievances and their resolution will be recorded and monitored. This data will be used to conduct in-depth analyses of complaint trends and patterns, identify potential weaknesses in the Project implementation, and consider improvements.

- Another mechanism that can be used in the project framework is the Social and Environmental Compliance Unit (SECU) and the Stakeholder Response Mechanism (SRM). The SECU investigates alleged non-compliance with UNDP’s Social and Environmental Standards and Screening Procedures from project-affected stakeholders and recommends measures to address findings of non-compliance.

- The SRM helps project-affected stakeholders, UNDP’s partners (governments, NGOs, businesses) and others jointly address grievances or disputes related to the social and/or environmental impacts of UNDP-supported projects.

- Affected people have a choice: they can ask SECU to pursue a compliance review examining UNDP’s compliance with UNDP social and environmental commitments, they can attempt to resolve complaints and disputes through the Stakeholder Response Mechanism or they can ask both for compliance review and for an effort to resolve their concerns.

## South-South and Triangular Cooperation (SSTrC)

- The GEF alternative represented by this project will contribute to the South-South and Triangular Cooperation via sharing Angola’s best experience in wildlife crime control, PA management, and development of community-based conservation and natural resource management initiatives amongst the GWP and GEF community of practice and with other interested partners like FAO, EU, KfW, WBG, USAID, UNODC and UNEP under the project Component 4. The Angola project will share knowledge and best practices with Central and South Africa states protecting African elephants, gorillas and chimpanzees that have committed to combating poaching and illegal wildlife trade in the CITES led African Elephant Action Plan and IUCN’s Regional Action Plan for Conservation of Western Lowland Gorillas and Central Chimpanzees 2015-2025. The project will be an important tool for Angola to fulfill its commitments under the International Convention on International Trade in Endangered Species of Wild Fauna and Flora to ensure that international trade in specimens of wild animals and plants does not threaten their survival. Moreover, the project will directly contribute to implementation of the MoU between Angola, the Republic of Congo, DRC, and Gabon on the Maiyombe Transboundary Conservation Initiative and the Mayombe Transfrontier Initiative's Strategic Plan. The project will ensure higher input of Angola to the Elephant Protection Initiative of 15 African countries to stop elephant poaching and illegal ivory trafficking as well as implementation of the SADC Regional Law Enforcement and Anti-Poaching Strategy. Indirectly the project will contribute to negotiations and agreements on IWT control with countries of ivory and other wildlife product demand in South-Eastern Asia (China, Thailand, and Viet Nam) via coordination and management of the GWP.

## Sustainability and Scaling Up

- The project will ensure the sustainability of the Outcomes in financial, institutional, social, and environmental aspects through a number of means integrated in the delivery of the project Outputs.

- Financial sustainability will be achieved by (i) involvement of key partners and donors with a likely long-term presence in the country and target areas in the project implementation and sustaining its results after the project is over (e.g., Stop Ivory, EPI, 51 Degrees, FAO, ADPP, AfDB, FAS, UNODC, etc); (ii) careful financial planning and budget sources analysis integrated in the management planning for the Maiombe NP and Luando SNR and community pilot projects in the project area (the MPs as well as community projects will include analysis of necessary funding for different activities, sources of the funding that are available for their implementation, and identification of effective markets and value chains for community products and services); (iii) development of collaboration mechanisms for inter-agency wildlife crime enforcement and implementation of the MPs co-management and delegated management mechanisms; (iv) development of sustainable and efficient CBNRM and alternative income models for local communities that allow long-term community investment in the NRM and ownership of endangered species and natural resources.

- Institutional sustainability will be provided via a systematic capacity building programme integrated in all project Outputs and targeting ECU, INBAC, customs, police, judiciary, border officers, PA staff in the project areas and local communities. The project will also establish a BLO in Cabinda province and local inter-agency ECUs in the Maiombe NP and Luando SNR as well as strengthen the PAs with progressive management plan and enforcement capacity. Output 1.3 will improve capacity and sustainability of the Environmental Polytechnic Institute (Wildlife School) in Menongue to provide regular and comprehensive trainings to PA rangers in Angola. The project will establish collaborative mechanisms for implementation of the management plans for the PAs and target communities and support sustainable livelihood of local communities in the long-term. To ensure institutional sustainability and ownership of the project results it is built on the partnerships of government organizations (Inter-ministerial Commission, ECU, INBAC, IDF, Customs, National Police, etc.) and international NGOs and donors (e.g., Stop Ivory, Wildlife Impact, UNODC, FAO, ADPP, AfDB, etc.). The project is built in line with on-going government programmes and agreements, like the National Policy on Forests, Wildlife and Conservation Areas; NBSAP; NIAP; MINAMB’s Program for Biodiversity Conservation and Protected Areas 2017-2020; Presidential Programme for Conservation and Restoration of the Black Giant Sable; and Mayombe Transfrontier Initiative's Strategic Plan to ensure its ownership by national and local governments.

- Social sustainability will be ensured through the development/strengthening of stakeholder participation and gender mainstreaming mechanisms at national and project area levels (see Annex H. Stakeholder Communication and Involvement Plan and Annex I. Gender Analysis and Mainstreaming Plan); the development and implementation of community NRM pilot projects; and the development of opportunities for local communities on generation of sufficient income via CBNRM and alternative livelihood.

- Environmental sustainability will be achieved through the implementation of all project Outputs that aim to improve wildlife crime law enforcement, protection for endangered wildlife and bushmeat species, PA management, and sustainable CBNRM. The achievement of the project Outcomes will lead to reduction of poaching, IWT, deforestation, and frequency of bush fires in the project areas and finally to stabilizing of the wildlife populations and area of their habitats.

- Scaling-Up: The project is designed to provide demonstration models for upscaling in Angola and other African countries. In particular, the capacity building of the project stakeholders and careful documentation of the lessons learned by the project (Component 4) will strongly support its up-scaling. Communicating and disseminating project’ results under Output 4.2 will help in generating demand for similar initiatives in the country and abroad. The involvement of multiple government partners, international agencies, NGOs, and local communities will lead to further upscaling of the project’s interventions. Following models developed by the project can be potentially upscaled nation-wide and internationally:

- Development of the National Wildlife Crime Enforcement Strategy, review of wildlife crime legislation, and development of CBNRM legislation will provide effective regulatory framework for wildlife crime enforcement and sustainable wildlife management nation-wide;

- Establishment of the multi-agency border cooperation and local ECUs can be used as models by other Central and South Africa’s countries to improve national implementation of the CITES and strengthen government response to the international wildlife crime;

- Training programmes for law enforcement agencies, PAs, and local communities can be potentially used nationally and internationally for other projects in GWP/GEF framework and beyond;

- RBM approach to development of implementable management plans for the target Pas and community pilot projects can be easily replicated by other PAs, communities, and administrative units;

- Implementation of community-based NRM and alternative livelihood models will likely be widely replicated in other districts of Angola in biodiversity and poaching hotspots.

# Project Management

## Cost efficiency and effectiveness

- To ensure the project cost efficiency and effectiveness the project was developed using fully participatory approach (more than 158 stakeholders were consulted), was built on the tested models and lessons learned by other projects and organizations (see Strategy section), and  has carefully designed Theory of Change (see Expected Results section). The project implementation is based on a set of partnerships with Government, non-Government, multilateral and local organizations and communities (about 30 organizations were defined as partners for the project) to share time, labour and finacial resources to deliver the project Outputs. Thus, the project is built on a strong financial foundation: total co-financing for the project is US$ 16,500,934 with GEF contribution of US$ 4,103,800, or 20% of the total project budget. To further increase the project efficiency, it suggests fully participatory project M&E system that will allow effective lesson learning and adaptive management to select the most effective strategies to achieve the project Outcomes (see Outputs 4.1-4.2). The project has clearly defined target areas – Maiombe NP and Luando SNR (key habitats of forest elephant, gorilla, chimpanzee, and black giant sable) – with total area 1,200,400 ha. The total GEF investments in the project areas (all outputs of Components 2 and 3, and considerable part of the Output 4.1) is US$ 2,810,000, or US$ 234/km². At the same time investments under Component 3 will target the selected local communities in the project areas on the total area of <=30,000 ha with even more significant investment level of US$ 3,733/km².

- A detailed budget has been prepared to manage all project investments and discussed with stakeholders, to ensure appropriate funding of the activities necessary to deliver each project Output. The project will use standard UNDP rules for procurement; these are specifically designed to optimise value for money. All activities will be included in the Annual Work Plan, which will be discussed and approved by the Project Board to ensure that proposed actions are relevant and necessary. When the activities are to be implemented and project Outputs monitored and evaluated, cost-effectiveness will be taken into account but will not compromise the quality of the Outputs. When hiring third party consultants or contractors, the project will follow a standard recruitment and advertising process to have at least three competitors for each contract. Selection will be based on qualifications, technical experience and financial proposal, to ensure hiring the best consultant (individual or organization) for an optimal price. Economy fares will be applied for necessary air and road travel, and appropriate lodging facilities will be provided to the project staff that ensures staff safety and cost-effectiveness. Similarly, the project will follow a tendering process for equipment purchase and any printing/publishing that accounts for more than USD 10,000, comparing at least three vendors. In case there is a single vendor only for any activity, appropriate official norms will be followed to obtain approval from UNDP and GEF.  Expenses will be accounted for according to UNDP rules and in line with the GEF policy. Finally, in order to maximise the effectiveness and sustainability of the project results, an exit plan will be developed by the end of year 5, for implementation and tracking during the final year. This will identify a key owner and sustainability mechanism for each of the project’s results that also contributes to the project effectiveness.

## Project Management

- The project will have a Project Management Unit hosted by INBAC in Luanda. The PMU will comprise a Project Coordinator, an International Technical Advisor, a Project Finance and Procurement Officer, a Project Technical and Administrative Assistant, and a driver. The PMU will directly work with indicated project partners at national and project area levels to ensure effective and timely delivery of the project Outputs. The PMU will cooperate with other projects implemented in at national level and in the project area directly and via designated partners, including during monitoring and evaluation visits and meetings of the Project Board. Other details of the project management arrangements are described in the section 7 – Governance and Management Arrangements.

## Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information

- To give proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials including publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also properly acknowledge the GEF. Information will be disclosed in accordance with relevant policies, notably the UNDP Disclosure Policy and the GEF policy on public involvement.

# Project Results Framework

| This project will contribute to the following Sustainable Development Goal (s): Goal 1 No Poverty; Goal 2 Zero Hunger; Goal 5 Gender Equality; Goal 8 Decent Work and Economic Growth; Goal 10 Reduced Inequalities; Goal 13 Climate Action; Goal 15 Life on Land; Goal 16 Peace, Justice and Strong Institutions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: Outcome 4: By 2019, the environmental sustainability is strengthened through the improvement of management of energy, natural resources, access to green technology, climate change strategies, conservation of biodiversity, and systems and plans to reduce disasters and risks |  |  |  |  |  |
| This project will be linked to the following output of the UNDP Strategic Plan 2018-2021: Output 1.4.1. Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value chains Indicator 1.4.1.b. Area of existing protected area under improved management (hectares) |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Assumptions/Data Collection Method |
| Project Objective: to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola | Mandatory Indicator 1: Total area of PAs with improved management (Maiombe NP and Luando SNR), ha: | 0 | 600,000 | 1,200,400 | Assumption 1. The PAs will be provided with additional and complementary to the project support from Angola Government and international donors Assumption 2. The PAs’ staff will use knowledge, skills, and equipment provided by the project to improve PA management and protection Data Collection method: METT assesment, GIS calculation of area under increased patrolling frequency and regular fire management |
|  | Indicator 2: Populations of the flagship species in the project areas: 1.Forest Elephant: 2.Western Lowland Gorilla: 3.Chimpanzee: 4.Black Giant Sable: | 1) TBE on the Year 1 2) TBE on the Year 1 3) TBE on the Year 1 4) 150 (2016, P. vaz Pinto, personal communication): baseline needs to be updated on the Year 1 | 1) >=baseline 2) >= baseline 3) >= baseline 4) >=170 | 1) >=baseline 2) >=baseline 3) >=baseline 4) >=200 | Assumption 2. The flagship species population will stabilize a result of decreased poaching (the key threat) and increased survival rate; Assumption 3. Other environmental factors are favorable for the elephant population restoration (no epidemics); Assumption 4. All key threats for the project conservation targets (including forests) are correctly identified Data Collection method: Dung (elephants) and nest (gorillas and chimpanzees) distance sampling survey along line transects. Camera-trapping survey for the black giant sable |
|  | Indicator 3: Area of wildlife habitat in the project areas, ha: 1.Tropical Rain Forest: 2.Miombo Woodlands: | 1) 196,275 ha (2017) 2) 929,191 ha (2017) (Calculated for the Maiombe NP as the total area covered with forest (>=20% of canopy cover) in 2000 (201,499 ha) minus area of tree cover loss in 2000-2017 (5,224 ha) based on the data of the University of Maryland. Calculated for the Luando SNR as the total area covered with forest (>=20% of canopy cover) in 2000 (954,477 ha) minus area of tree cover loss in 2000-2017 (25,287 ha) based on the data of the University of MarylandGlobal Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. Baseline needs to be updated at the project Inception phase with data for 2018) | 1) >=baseline 2) >=baseline | 1) >=baseline 2) >=baseline | Assumption 5: Any logging activities are illegal in the Maiombe NP and Luando SNR. Increased law enforcement and participation of local communities in the PA management will stop all illegal logging in the PAs Data Collection methods: GIS analysis of the Global Forest Watch data 2017 - 2026 |
|  | Indicator 4: Level of poaching in the project areas: 1.Number of elephants poached annually in Maiombe NP: 2.Bushmeat is exposed for selling in/around: a) Maiombe NP: b)Luando SNR: c)Luanda City: | 1) >=1(Maiombe NP staff, pers. comm) 2a) Yes (Observations of PPG team in June and September) 2018) 2b) Yes 2c) Yes | 1) 0 2a) No 2b) No 2c) No | 1) 0 2a) No 2b) No 2c) No | Assumption 6: Poaching and IWT will decrease to minimal level as a result of increased law enforcement Data Collection method: Elephant carcasses count during patrolling of Maiombe NP. Express-observations at the local markets and roads (bushmeat trade). |
| Outcome 1. Strengthened policy, legal and institutional framework to combat wildlife crime and manage wildlife, including HWC | Indicator 5: Capacity of INBAC to control wildlife crime (UNDP Capacity scorecard, %): | 41% | >=48% | >=60% | Assumption 1. Law enforcement officers will use new skills, and tools provided by the project to increase their effectiveness in IWT control and achieve higher results. Assumption 2. Law enforcement agencies have sufficient support from Government and other donors Assumption 3. Indicator 5 and 6 values are expected to increase due to (a) increased number of well-trained rangers and officers in the target PAs, INBAC, ECU and other law enforcement agencies; (b) strengthened technical capacity (equipment) of INBAC, ECU, and other law enforcement agencies to address wildlife crime; (c) improved inter-agency law enforcement collaboration; (d) improved policy and wildlife regulatory framework Data Collection methods: Calculation of score using UNDP Capacity Scorecard and ICCWC IF (Indicators 5 and 6); Content analysis of annual ECU and INBAC reports (Indicator 7) |
|  | Indicator 6: National capacity to combat wildlife crime (ICCWC Indicator Framework Score: see Annex R. ICCWC Indicator Framework Report Angola 2018) | 28% | >=35% | >=45% |  |
| Outcome 2. Strengthened capacity of PAs and other law enforcement agencies in the project areas to reduce wildlife crime, manage HWC, and prevent habitat degradation | Indicator 7: Annual effectiveness of anti-poaching in the project areas: 1. Maiombe NP: a) total number of staff available for anti-poaching: b) intensity of patrolling (inspector/days/month): c) annual number seizures of wildlife and forest products: d) annual number of arrests of wildlife and forest crime offenders: 2.Luando SNR: a) total number of staff available for anti-poaching: b) intensity of patrolling (ranger/days/month): c) annual number seizures of wildlife and forest products: d) annual number of arrests of wildlife and forest crime offenders: | 1a) 12(2018) 1b) 216 (Each ranger in the Maiombe NP works 21 days after 21 days of rest (~18 days/month): 12 rangers*18 days/month = 216 ranger/day/month) 1c) 3-5 (Maiombe NP staff, pers.comm 1d) 9-10 (in 2013-2018 47 offenders were arrested in the Park) 2a) 0 (2018) 2b) 0(2017) 2c) 0(2017) 2d) 0(2017) | 1a) >=20 1b) >=300 1c) >=20 1d) >=20 2a) >=14 2b) >= 180 (We assume that two groups (6 rangers each) will patrol the Luando SNR for 15 days (at least 8 hours of patrolling per day) each every month (or minimum 15 effective patrol man-days per month per ranger) (H. Jachmann, pers. comm.)) 2c) >=20 2d) >=20 | 1a) >=30 1b) >=450 1c) >=50 1d) >=50 2a) >=30 2b) >= 450 (We assume that at least 5 groups (6 rangers each) will patrol the Luando SNR for 15 days (at least 8 hours of patrolling per day) each every month (or minimum 15 effective patrol man-days per month per ranger) (H. Jachmann, pers. comm.)) 2c) >=50 2d) >=50 | Assumption 1. The PAs will be provided with additional and complementary to the project support from Angola Government and international donors Assumption 2. The PAs’ staff will use knowledge, skills, and equipment provided by the project to improve PA management and protection Assumption 3. Increased effectiveness of law enforcement will have strong deterrent effect on poachers and unsustainable NRM practices in the project areas because of threat of severe punishment and decreased income from illegal activities Assumption 4. Local people will maintain high level of tolerance to elephants and HECs; Data Collection methods: Content analysis of the PAS annual reports (Indicator 7); METT assessment of the PA management (Indicator 8); Content analysis of the PAs’ annual reports on HEC, random interviews of local people (Indicator 9) |
|  | Indicator 8: METT score (see Annex D. BD GEF TT): - Maiombe NP: - Luando SNR: | 35 20 | >=45 >=30 | >=55 >=40 |  |
|  | Indicator 9: % of mitigated/solved HEC annually (Maiombe NP): | 0% (out of at least 6 cases annually in Maiombe NP) | >= 30% | >= 50% |  |
| Outcome 3. Increased involvement of local communities in the project areas in wildlife, habitat, and PA management | Indicator 10: 1. Total number of people (F/M) practicing SFM, SLM, CBNRM and/or participating in the PA management: a) Maiombe NP: b) Luando SNR: 2. Total area (ha) under community-based SFM, SLM, and CBNRM: a)Maiombe NP: b)Luando SNR: | 1a) 0 (2018) 1b) 0 (2018) 2a) 0 (2018) 2b) 0 (2018) | 1a) >= 1,000 (50% are females) 1b) >= 1,000 (50% are females) 2a) >= 5,000 2b) >= 5,000 | 1a) >=3,000 (50% are females) (Our assumption based on the previous experience of ADPP and FAO on sustainable livelihood of local communities in Angola (at least 50-60% of 5,000-6,000 people in Maiombe NP and Luando SNR the project will train under Output 3.1)) 1b) >=3,000 (50% are females) 2a) >=10,000 2b) >= 10,000 (Our assumption (at least 5% of the Maiombe NP and 1% of Luando SNR)) | Assumption 1. Local people will use knowledge and skills on CBNRM provided by the project to practice sustainable NRM; Assumption 2. Local communities will have sustainable, safe, and sufficient income from CBNRM comparable or higher with income from poaching, unsustainable agriculture, pasture, and forest use Assumption 3. Unsustainable practices in the PAs will decrease as a result of increased law enforcement and involvement of local people in CBNRM and PA management Data Collection methods: Content analysis of the project activity reports, Interviews with local communities (Indicator 10); GIS analysis of the Global Forest Watch data 2017 - 2026 (Indicator 11) GIS analysis of the NASA (FIRMS) MODIS NRT active fire product (MCD14DL) data 2017 - 2026 (Indicator 12) |
|  | Indicator 11: Deforestation rate in the project areas, ha/ year: - Maiombe NP: - Luando SNR: | a)718 ha/year b)1,800 ha/year (Calculated as average for last 5 years (2013-2017) based on the data of the University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. Baseline needs to be updated at the project Inception phase with data for 2018) | a)<=350 ha/year b)<= 900 ha/year | a)0 ha/year b)0 ha/year (The deforestation rate is projected to decrease to zero level as a result of increased law enforcement, sustainable consumption of wood, natural reforestation, and reforestation efforts of local communities. According to the Decree No. 469/15 hunting activity and logging is prohibited within the country’s protected areas, 13 July 2015) |  |
|  | Indicator 12: Frequency of wild fires in in Luando SNR (number of incidents/year, NASA Fire Information for Resource Management System (FIRMS) 2018. MODIS NRT active fire products (MCD14DL) for Angola 2017 processed using the standard MOD14/MYD14 Fire and Thermal Anomalies product https://firms.modaps.eosdis.nasa.gov/data/download/DL_FIRE_M6_14771.zip): | 5,023 | <=3,500 | <= 2,500 |  |
| Outcome 4: Lessons learned by the project, including gender mainstreaming, through participatory M&E are used to fight poaching and IWT nationally and internationally | Indicator 13: Number of the lessons on anti-poaching and CBNRM learned by the project that used in other national and international projects | 0 | >= 2 | >= 5 | Assumption 1. Other stakeholders have interest to learn from lessons and successful practices developed by the project, including gender mainstreaming practices; Assumption 2. Other projects make references to the GEF project if they use its experience and lessons; Assumption 3. Women have high interest to the project participation to improve their livelihood and social status Data Collection methods: Content analysis of publications, project documents and reports (Indicator 13); Content analysis of the Gender Strategy implementation reports, random interviews with local women (Indicator 14); Analysis of the project participants lists in the project activity reports (Indicator 15). |
|  | Indicator 14: % of women among the project participants (relative number of women directly involved in the project activities, e.g., policy and legislation review, law enforcement trainings, CBNRM and alternative livelihood activities, and environmental education programmes) | 0 | >=30% | >=50% |  |
|  | Indicator 15: Total number of direct project beneficiaries (m/f): | 0 | >= 4,000 ((at least 40% are women) | >=10,490 (at least 40% are women) (Includes ~10,000 local people of selected communities in Maiombe NP and Luando SNR (Outputs 3.1-3.2); at least 240 law enforcement officers of ECU, Customs, Border Police, prosecutors and judiciary receiving training and equipment under Output 1.2; and at least 250 PA rangers trained and equipped under Outputs 1.3, 2.1 and 2.2.) |  |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results. With Knowledge Management and M&E, the project monitoring and evaluation plan will also facilitate learning and ensure knowledge is shared and widely disseminated to support the scaling up and replication of project results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

- Project Coordinator:  The Project Coordinator is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Coordinator will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Coordinator will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Coordinator will develop annual work plans based on the multi-year work plan included in Annex, including annual output targets to support the efficient implementation of the project. The Project Coordinator will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. ESMP, gender action plan, stakeholder engagement plan etc.) occur on a regular basis.

- Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner is responsible for providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes where possible, and is aligned with national systems so that the data used and generated by the project supports national systems.

- UNDP Country Office:  The UNDP Country Office will support the Project Coordinator as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission. The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Coordinator.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within two months after the project document has been signed by all relevant parties to, amongst others:

- Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

- Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

- Review the results framework and finalize the indicators, means of verification and monitoring plan;

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

- Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; SESP and other safeguard requirements; project grievance mechanisms; the gender strategy; the knowledge management strategy, and other relevant strategies;

- Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

- Plan and schedule Project Board meetings and finalize the first year’s annual work plan.

- The Project Coordinator will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.

- GEF Project Implementation Report (PIR):  The Project Coordinator, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Coordinator will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. In line with UNDP’s SES the project will conduct  an environmental and social impact assessment (ESIA) and develop an environmental and social management plan (ESMP) that will include at least the following: Human Rights and Safety Action Plan, Community Livelihood Action Plan, and Gender Mainstreaming Strategy. Any environmental and social risks and related management plans will be monitored regularly in accordance with the ESMP, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Board. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyze and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

- GEF Focal Area Tracking Tools:  The following GEF Tracking Tool(s) will be used to monitor global environmental benefits: GEF Global Wildlife Programme Tracking Tool. The baseline/CEO Endorsement GEF Focal Area Tracking Tool(s) – submitted as Annex B to this project document – will be updated by the Project Coordinator/Team (not the evaluation consultants hired to undertake the MTR or the TE) and shared with the mid-term review consultants and terminal evaluation consultants before the required review/evaluation missions take place. The updated GEF Tracking Tool(s) will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and approved by the Project Board.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Coordinator will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.  The TE report will be publicly available in English on the UNDP ERC.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Mandatory GEF M&E Requirements and M&E Budget

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office | USD 10,000 | None | Within two months of project document signature |
| Inception Report | Project Coordinator | None | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Risk management | Project Coordinator Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Coordinator | Total: USD 9,790 | None | Annually before PIR |
| GEF Project Implementation Report (PIR) | Project Coordinator and the UNDP-GEF team | None | None | Annually |
| Lessons learned and knowledge generation | Project Coordinator | Per year: USD 3,000 Total: USD 18,000 | None | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project partner for Output 3.1 Project Coordinator UNDP Country Office | Year 1: USD 5,000 Per year 2-6: USD 2,000 Total: USD 15,000 | None | Year 1 ESIA & ESMP inputs On-going monitoring |
| Addressing environmental and social grievances | GRM Sub-Committee of the Project Board | Per year: USD 2,000 Total: USD 12,000 | None | On-going |
| Project Board meetings | Project Board UNDP Country Office Project Coordinator | Per year: USD 5,000 Total: USD 30,000 | None | At minimum annually |
| Supervision missions | UNDP Country Office | None | None | Annually |
| Oversight missions | UNDP-GEF team | None | None | Technical advice and troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Coordinator and UNDP-GEF team | None | None | To be determined. |
| Mid-term GEF Tracking Tool | Project Coordinator | None | None | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 25,000 | None | Between 2nd and 3rd PIR. |
| Terminal GEF Tracking Tool | Project Coordinator | None | None | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 35,000 | None | At least three months before operational closure |
| Translation of MTR and TE reports into English | UNDP Country Office | None | None | As required. GEF will only accept reports in English. |
| TOTAL indicative cost Excluding project team staff time, and UNDP staff and travel expenses |  | USD 154,790 | None |  |

# Governance and Management Arrangements

Roles and responsibilities of the project’s governance mechanism

Implementing Partner

- The Implementing Partner for this project is the Ministry of Environment (MINAMB). The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

- The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

UNDP

- UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is also responsible for the Project Assurance role of the Project Board/Steering Committee.

Project Board

- The Project Board (also called Project Steering Committee) is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

- In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

- Specific responsibilities of the Project Board include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on project manager’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

- The composition of the Project Board must include the following roles:

- Project Executive: Is an individual who represents ownership of the project and chairs the Project Board. The Project Executive is normally the national counterpart for nationally implemented projects. The Project Executive will be the Secretary of State of MINAMB (or its delegate such as the Director General of INBAC).

- Beneficiary Representatives: Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. Often civil society representative(s) can fulfil this role. The Beneficiary Representatives will be appointed from amongst representatives of the Ministry of Interior, Ministry of Agriculture and Forests, National Institute for Biodiversity and Protected Areas (INBAC), Maiombe NP,  Luando SNR, Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora, Provincial Governments of Cabinda/Malanje/Bie Provinces, and representatives of local communities in the project areas (all names to be determined);

- Development Partners: Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partners will be appointed from amongst representatives of FAO Angola, the Mayombe Transfrontier Initiative Secretariat, Environmental Crime Unit, National Forest Development Institute, the Presidential Programme for the Black Giant Sable conservation, Kissama Foundation, Stop Ivory, ICCF, ADPP (all names to be determined);

- Project Assurance: UNDP performs the quality assurance role and supports the Project Board and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. UNDP provides a three – tier oversight services involving the UNDP Country Offices and UNDP at regional and headquarters levels. Project assurance is totally independent of the Project Management function.

- The Project Board will meet after the Inception Workshop and at least once each year thereafter.

Project organisation structure

Implementing Partner: INBAC with Project Management Unit:

Project Coordinator; Project Assistant; Administration and Finance Assistant; UN Volunteer; Driver

Project Board/Steering Committee

Project Executive

MINAMB Secretary of State (or its delegate	e such as the Director General of INBAC)

Beneficiary Representatives

To be appointed from amongst representatives of Ministry of Interior, Ministry of Agriculture and Forests, INBAC, Maiombe NP, Luando SNR, Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora, Provincial Governments of Cabinda/Malanje/Bie Provinces, and representatives of local communities in the project areas

Development Partners

To be appointed from amongst representatives of FAO Angola, Mayombe Transfrontier Initiative Secretariat, Environmental Crime Unit, National Forest Development Institute, Presidential Programme for the Black Giant Sable conservation, Kissama Foundation, Stop Ivory, ICCF, and ADPP

Project Assurance: UNDP

Head of Environment and Sustainable Development, UNDP Angola; RTA, UNDP-GEF Istanbul; PTA & Head of Biodiversity, UNDP NYC

Technical Committees

in Project Areas

Key Partners (Components 1-2):

ECU, Customs, Police, Judiciary, Interministerial Commission on Wildlife Crime, CITES Secretariat, Maiombe NP, Luando SNR, Stop Ivory, 51 Degrees, ICCF

Key Partners (Component 3):

Local Communities and Administrations, FAO, AfDB, ADPP, FAS, Kissama Foundation

Project Coordinator

- The Project Coordinator has the authority to run the project on a day-to-day basis on behalf of the Project Board within the constraints laid down by the Board. The Project Coordinator is responsible for day-to-day management and decision-making for the project. The Project Coordinator’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.  The Implementing Partner appoints the Project Coordinator, who should be different from the Implementing Partner’s representative in the Project Board.

- The Project Coordinator will be an ex-officio member of the PB and will serve as secretary to the Board.

- Specific responsibilities of the Project Coordinator are indicated in Annex E.

Project Management Unit

- A Project Management Unit (PMU) will be established at the INBAC, Luanda, and led by a Project Coordinator. The PMU will assume the day-to-day management of project operations, including implementation of activities and accountability for the delivery of the project’s outputs and preparation of quarterly and annual work plans and reports, in direct collaboration with project partners under the guidance of the Project Board. The PMU will also be staffed by an International Technical Advisor, a Project Finance and Procurement Officer, a Project Technical and Administrative Assistant, and a Driver. An experienced project partner (organization) selected for implementation of Output 3.1 will assist the PMU in monitoring of SESP risks and implementation of ESMP. The TORs for the Project Coordinator, International Technical Advisor, Project Finance and Procurement Officer and Project Technical and Administrative Assistant are included in Annex E.

- Mandatory HACT assessment for the MINAMB/INBAC was conducted by the UNDP CO and included in the Annex K.

Governance role for project target groups: Technical Committees

- To involve local communities in the decision-making process, direct project implementation, and ensure SESP risk monitoring and control of ESMP implementation, and M&E the project will establish Technical Committees in the project areas that will consists from representatives of the target PAs,  communities, local governments, NGOs actively present in the project area. The Technical Committees will have meetings at least once a year before the Project Board meeting to review the project progress under Components 2 and 3, extract key lessons, plan project activities, review community concerns and grievances and provide recommendations to the PB and PMU. The Technical Committees will ensure coordination among all stakeholders and their involvement in the participatory project M&E and management under PMU guidance; the Committees will ensure access of local community to GRM channels. The Technical Committees’ recommendations will be reviewed and taken into consideration by the PB at its meetings as well as by the Project Management Unit (PMU). Members of the Technical Committees will be selected at the Inception phase of the project. The locations of Technical Committees’ meetings will be determined during the project implementation in the project area.

Project extensions

- The UNDP-GEF Executive Coordinator must approve all project extension requests. Note that all extensions incur costs and the GEF project budget cannot be increased. A single extension may be granted on an exceptional basis and only if the following conditions are met: one extension only for a project for a maximum of six months; the project management costs during the extension period must remain within the originally approved amount, and any increase in PMC costs will be covered by non-GEF resources; the UNDP Country Office oversight costs during the extension period must be covered by non-GEF resources.

# Financial Planning and Management

- The total cost of the project is USD 20,548,734. This is financed through a GEF grant of USD 4,103,800 and USD 16,500,934 in parallel co-financing. UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to the UNDP bank account only.

- Parallel co-financing:  The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF. The planned parallel co-financing will be used as follows (see Annex M. Co-financing letters):

| Co-financing source | Co-financing type | Co-financing amount, USD | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Ministry of Environment | In kind | 5,477,000 | Outputs 1.1-2.2, Project Management | Moderate, actual co-financing can be less due to insufficient resources of MINAMB to manage PA and fight wildlife crime | To leverage additional funds from NGOs and other donors working in Angola |
| Kissama Foundation | Grant | 245,000 | Outputs 2.2 and 3.1 | Low, funding is secured | None |
| KfW Bankengruppe | Grant | 6,000,000 | Output 1.2-1.3, 3.1 and 3.2 | Low, funding is secured | None |
| Stop Ivory | In kind | 346,934 | Outputs 1.1-1.3 | Low, funding is secured | None |
| ICCF | In kind | 400,000 | Outputs 1.1-1.2 | Low, funding is secured | None |
| ADPP | Grant | 4,032,000 | Outputs 3.1 and 3.2 | Low, funding is secured | None |
| TOTAL: |  | 16,500,934 |  |  |  |

- Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project coordinator to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the Project Coordinator and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; or b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Any over-expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (UNDP TRAC and cash co-financing).

- Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

- Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP.  On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

- Transfer or disposal of assets: In consultation with the NIM Implementing Partner and other parties of the project, UNDP programme manager (UNDP Resident Representative) is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) The project is operationally completed or has been cancelled; b) The Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

# Total Budget and Work Plan

| Atlas Proposal or Award ID: | 114883 |
| --- | --- |
| Atlas Primary Output Project ID: | 112730 |
| Atlas Proposal or Award Title: | Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola |
| Atlas Business Unit: | AGO10 |
| Atlas Primary Output Project Title: | Combating Illegal Wildlife Trade and Human Wildlife Conflict |
| UNDP PIMS #: | 5993 |
| GEF PMIS # | 9735 |
| Implementing Partner: | Ministry of Environment (MINAMB) |

| GEF Component/Atlas Activity | Resp. Party/ Atlas Impl. Agent | Fund ID | Donor Name | Atlas Budget Acct Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Amount Year 6 (USD) | Total (USD) | See Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1. Strengthened policy, legal and institutional framework to combat wildlife crime and manage wildlife | MINAMB (INBAC) | 62000 | GEF | 71300 | Local Consultants | 14,400 | 14,400 | 14,400 | 14,400 | 14,400 | 7,200 | 79,200 | 1 |
|  |  | 62000 | GEF | 72100 | Contractual services | 80,000 | 155,000 | 55,000 | 49,800 | 40,000 | 0 | 379,800 | 2 |
|  |  | 62000 | GEF | 72200 | Equipment and Furniture | 90,000 | 100,000 | 0 | 0 | 0 | 0 | 190,000 | 3 |
|  |  | 62000 | GEF | 75700 | Training, workshop, meetings | 60,000 | 60,000 | 50,000 | 0 | 0 | 0 | 170,000 | 4 |
|  |  |  | GEF |  | Total Outcome 1 | 244,400 | 329,400 | 119,400 | 64,200 | 54,400 | 7,200 | 819,000 |  |
| COMPONENT 2. Strengthened capacity of PAs and other law enforcement agencies in the project areas to reduce wildlife crime, manage HWC, and prevent habitat degradation | MINAMB (INBAC) | 62000 | GEF | 71300 | Local Consultants | 54,400 | 44,400 | 44,400 | 44,400 | 44,400 | 20,619 | 252,619 | 5 |
|  |  | 62000 | GEF | 72100 | Contractual services | 215,000 | 55,000 | 0 | 0 | 0 | 160,000 | 430,000 | 6 |
|  |  | 62000 | GEF | 72200 | Equipment and Furniture | 100,000 | 410,000 | 0 | 0 | 0 | 0 | 510,000 | 7 |
|  |  | 62000 | GEF | 72300 | Materials and Goods | 0 | 250,000 | 0 | 0 | 0 | 0 | 250,000 | 8 |
|  |  | 62000 | GEF | 71600 | Travel | 21,967 | 21,967 | 21,967 | 21,967 | 21,967 | 21,967 | 131,800 | 9 |
|  |  | 62000 | GEF | 75700 | Training, workshop, meetings | 30,000 | 30,000 | 30,000 | 30,000 | 0 | 0 | 120,000 | 10 |
|  |  |  | GEF |  | Total Outcome 2 | 421,367 | 811,367 | 96,367 | 96,367 | 66,367 | 202,586 | 1,694,419 |  |
| COMPONENT 3. Increased involvement of local communities in the project areas in wildlife, habitat, and PA management | MINAMB (INBAC) | 62000 | GEF | 71200 | International Consultants | 65,000 | 35000 | 35000 | 35000 | 35000 | 35000 | 240,000 | 12 |
|  |  | 62000 | GEF | 71300 | Local Consultants | 11,800 | 1,800 | 1,800 | 1,800 | 1,800 | 900 | 19,900 | 13 |
|  |  | 62000 | GEF | 72100 | Contractual services | 20,000 | 20,000 | 10,000 | 10,000 | 20,000 | 20,000 | 100,000 | 14 |
|  |  | 62000 | GEF | 72600 | Grants | 50,100 | 125,000 | 125,000 | 105,000 | 105,000 | 105,000 | 615,100 | 15 |
|  |  | 62000 | GEF | 75700 | Training, workshop, meetings | 20,000 | 30,000 | 30,000 | 30,000 | 20,000 | 0 | 130,000 | 16 |
|  |  |  | GEF |  | Total Outcome 3 | 166,900 | 211,800 | 201,800 | 181,800 | 181,800 | 160,900 | 1,105,000 |  |
| COMPONENT 4: Lessons learned by the project through participatory M&E and gender mainstreaming are used nationally and internationally | MINAMB (INBAC) | 62000 | GEF | 71200 | International Consultants | 0 | 0 | 30,000 | 0 | 0 | 30,000 | 60,000 | 17 |
|  |  | 62000 | GEF | 71300 | Local Consultants | 18,000 | 2,000 | 2,000 | 2,000 | 2,000 | 12,000 | 38,000 | 18 |
|  |  | 62000 | GEF | 71600 | Travel | 12,000 | 19,581 | 22,000 | 22,000 | 22,000 | 21,381 | 118,962 | 19 |
|  |  | 62000 | GEF | 74500 | Miscellaneous | 0 | 2000 | 2000 | 3000 | 3000 | 3000 | 13,000 | 21 |
|  |  | 62000 | GEF | 75700 | Training, workshop, meetings | 15,000 | 5,000 | 10,000 | 10,000 | 10,000 | 10,000 | 60,000 | 22 |
|  |  |  | GEF |  | Total Outcome 4 | 45,000 | 28,581 | 66,000 | 37,000 | 37,000 | 76,381 | 289,962 |  |
| Project Management Cost | MINAMB (INBAC) | 62000 | GEF | 71300 | Local Consultants | 5,400 | 5,400 | 5,400 | 5,400 | 5,400 | 2,700 | 29,700 | 26 |
|  |  | 62000 | GEF | 71400 | Contractual Services - Individuals | 28,500 | 28,500 | 28,500 | 28,500 | 28,500 |  | 142,500 | 25 |
|  |  | 62000 | GEF | 72500 | Office Supplies | 2,219 | 2,000 | 1,000 | 1,000 | 1,000 | 1,000 | 8,219 | 24 |
|  |  | 62000 | GEF | 74100 | Audit | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | 15,000 | 20 |
|  |  |  | GEF |  | Total Project Management | 38,619 | 38,400 | 37,400 | 37,400 | 37,400 | 6,200 | 195,419 |  |
|  |  |  |  |  | PROJECT TOTAL (GEF) | 916,286 | 1,419,548 | 520,967 | 416,767 | 376,967 | 453,267 | 4,103,800 |  |

Summary of Funds:

|  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Amount Year 5 | Amount Year 6 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF | 916,286 | 1,419,548 | 520,967 | 416,767 | 376,967 | 453,267 | 4,103,800 |
| Ministry of Environment | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 | 477,000 | 5,477,000 |
| Kissama Foundation | 50,000 | 50,000 | 50,000 | 40,000 | 40,000 | 15,000 | 245,000 |
| KfW Bankengruppe | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 | 6,000,000 |
| Stop Ivory | 100,000 | 76,934 | 60,000 | 60,000 | 50,000 | 0 | 346,934 |
| ICCF | 80,000 | 80,000 | 60,000 | 60,000 | 60,000 | 60,000 | 400,000 |
| ADPP | 672,000 | 672,000 | 672,000 | 672,000 | 672,000 | 672,000 | 4,032,000 |
| TOTAL COFINANCE | 2,902,000 | 2,878,934 | 2,842,000 | 2,832,000 | 2,822,000 | 2,224,000 | 16,500,934 |
| TOTAL | 3,818,286 | 4,298,482 | 3,362,967 | 3,248,767 | 3,198,967 | 2,677,267 | 20,604,734 |

Budget Notes:

| # | Description |
| --- | --- |
| 1 | National Consultant (Project Coordinator): $3,000/month*60 months*40% = $72,000 (Years 1-5) and $1,500*12 months*40% = $7,200 (Year 6), Total: $79,200 (direct contribution of the Project Coordinator to delivery of Outputs 1.1 – 1.3). |
| 2 | Contract(s) with selected project partner(s) (organization) to develop a National Wildlife Crime Law Enforcement Strategy and update selected legislation on Years 1 and 2: $100,000 (Output 1.1); Contract(s) with selected project partner(s) (organization) to provide training and mentoring programme on wildlife crime investigation, intelligence, forensics, etc., to the national Environmental Crime Unit on Years 1-3: $150,000 (Output 1.2); Contract(s) with selected project partner(s) (organization) to develop mandatory training programmes for the Environmental Polytechnic Institute (Wildlife School) in Menongue, train the school instructors, and provide mandatory trainings to PA rangers on Years 1-5: $129,800 (Output 1.3); |
| 3 | Equipment and software for the national Environmental Crime Unit (Toyota Pickup: $40,000; radios, cameras, computers, software, investigation equipment: $50,000) on the Years 1-2 (Output 1.2); Training equipment for the Environmental Polytechnic Institute (Wildlife School) in Menongue on the Years 1-2: $100,000 (Output 1.3); |
| 4 | Organization of meetings with stakeholders to discuss and facilitate approval of developed National Wildlife Crime Law Enforcement Strategy, updated wildlife crime legislation and other legal documents: $20,000 on Year 1 and 2 (Output 1.1); Training for the law enforcement agencies to investigate, prosecute, and penalize wildlife crime on Years 1-3: $150,000 (Output 1.2); |
| 5 | National Consultant to develop inter-agency protocols, ToRs, and SOPs for establishment and functioning of local ECU in Maiombe NP and Luando SNR on the Year 1: $10,000 (Output 2.1). National Consultant (Project Coordinator): $3,000/month*60 months*40% = $72,000 (Years 1-5) and $1,500*12 months*40% = $7,200 (Year 6), total: $79,200 (direct contribution of the Project Coordinator to delivery of Outputs 2.1 and 2.2). National Consultant (Project Technical and Administrative Assistant): $1,500/month*60 months = $90,000 (Years 1-5) and $750*12 months = $9,000 (Year 6), total: $99,000 (direct contribution to delivery of Outputs 2.1 and 2.2). National Consultant (Project Driver): $1,000/month*60 months = $60,000 (Years 1-5) and $500*8.8 months = $4,419 (Year 6), total: $64,419 (direct contribution of the Driver to delivery of Outputs 2.1 and 2.2). |
| 6 | Contract(s) with selected project partner(s) (organization) to develop/update the RBM Management Plans for Maiombe NP and Luando SNR on the Years 1-2: $110,000 (Output 2.2); Contract(s) with selected project partner(s) (organization) to design and implement elephant, gorilla, and chimpanzee population transect surveys in the Maiombe NP on the Years 1 and 6: $200,000; to design and implement black giant sable camera-trapping surveys in the Luando SNR on the Years 1 and 6: $120,000 (Output 2.2) |
| 7 | Equipment for local ECUs in the Maiombe NP and Luando SNR on the Years 2 and 3: 2 Toyota Pick-Ups - $80,000; field equipment for the officers - $20,000 (Output 2.1); Equipment for the Maiombe NP and Luando SNR rangers on the Years 1-3, including field equipment for rangers, fire management equipment, communication equipment, etc. - $410,000 (Output 2.2) |
| 8 | Construction of base camp in Luando SNR and two ranger posts in Maiombe NP (Output 2.2) |
| 9 | Travel expenses including fuel and rations for operations of national and local ECUs and anti-poaching operations by rangers in Maiombe NP and Luando SNR (Outputs 2.1 and 2.2) |
| 10 | On-the-site trainings/refreshers for the Maiombe NP and Luando SNR management and ranger staff on the Years 1-4: $120,000 (Output 2.2); |
| 12 | International Technical Advisor to oversee and support project activities, especially under Output 3, including planning, benchmarking, capacity development, monitoring and evaluation, including ICCWC IF assessments on the Years 3 and 6. Total: $210,000 for Years 1-6 (Output 3.1). International Consultant to conduct Environmental and Social Impact Assessment and develop Environment and Social Management Plan for the project (Output 3.1): $30,000, Year 1 |
| 13 | National Consultant (Project Coordinator): $3,000/month*60 months*5% = $9,000 (Years 1-5) and $1,500*12 months*5% = $900 (Year 6), Total: $9,900. National Consultant to design national and project area levels awareness campaign on negative impact of wildlife crime and bushmeat consumption in Angola on the Year 1: $10,000 (Output 3.2) |
| 14 | Contract(s) with selected project partner(s) (organization) to conduct feasibility assessment for different forms of community-based conservation and involvement of local communities in the PA and NR management, and assist local communities to develop pilot projects on community-based conservation and sustainable NR management in the Maiombe NP and Luando SNR, and implement ESMP on the Years 1-6: $100,000 (Output 3.1) |
| 15 | Low Value Grants (via a project partner selected in the budget note 14) to selected local communities in the Maiombe NP and Luando SNR to implement pilot projects on community-based conservation and sustainable NR management on the Years 1-6: $530,100 (Output 3.1); Grants to selected NGOs to implement activities in framework of the awareness campaign (Output 3.2) on the Years 1-6: $85,000. |
| 16 | Trainings to selected local communities in the project areas on selected forms of sustainable livelihoods and CBNRM (Output 3.1) on the Years 1-5: $130,000 |
| 17 | International Consultant for the MTR in Year 3 (Output 4.1): $30,000; International Consultant for the TE in Year 6 (Output 4.1): $30,000 |
| 18 | National Consultant for the TE in Year 6 (Output 4.1): $10,000; National Consultant to develop and support the project website in Years 1-6: $18,000 (Output 4.2); National Consultant to develop the project Gender Mainstreaming Strategy in Year 1: $10,000 (Output 4.3). |
| 19 | Travel expenses for the project team to monitor PRF and SESP indicators in accordance with ESMP, stakeholder involvement, and GRM (Output 4.1): $46,962 for Years 1-6; Travel expenses for the project team and partners to participate in the national and international meetings, seminars and conferences to exchange experience (Output 4.2): $48,000 for Years 1-6; Travel expenses for the project team to monitor implementation of the gender mainstreaming strategy (Output 4.3): $24,000 for Years 1-6. |
| 20 | Annual audit of the project implementation (Output 4.1): 6 years*$3,000 = $18,000 |
| 21 | Publication of the project materials, including lessons learned (Output 4.2) |
| 22 | Organization of Inception workshop (Output 4.1): $10,000 on the Year 1; Project Board meetings once a year (Output 4.1): $5,000/year * 6 years = $30,000; Meetings, seminars, and workshops for the project team and partners to exchange experience and extract lessons learned, including ICCWC IF workshops on the Year 3 and 6 (Output 4.2): $20,000 for Years 3-6. |
| 24 | PMU office supplies, paper, cartridges and other consumables: $2,000*6 years = $12,000 |
| 25 | Project Finance and Procurement Officer to lead and support financial planning, reporting and procurement for project implementation: $28,500*5 years = $142,500. |
| 26 | National Consultant (Project Coordinator): $3,000/month*60 months*15% = $27,000 (Years 1-5) and $1,500*12 months*15% = $2,700 (Year 6), Total: $29,700. |

# Legal Context

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of the Republic of Angola and UNDP, signed on 18 February 1977.   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

- This project will be implemented by the Ministry of Environment (Implementing Partner) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

  - put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

  - assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

  - In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

  - Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment.

- In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

- The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

  - Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

  - The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

  - All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

  - The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

  - The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

  - In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

- Note: The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# Annexes

## Annex A:  Multi-Year Work Plan

| Activities | Responsible | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Project Initiation and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inception Workshop | MINAMB, UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Constituting of Project Board and Technical Committees | MINAMB, UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Constituting of the PMU, hiring management staff | MINAMB, UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Signing agreement with MINAMB a on the project implementation | MINAMB, UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establishment of Project Special Accounts and Fund Flow Arrangements | UNDP, MINAMB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Board meetings | PMU, MINAMB, UNDP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Technical Committee Meetings in the project areas | PAs, Local Communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ESIA and EMP development | International Consultant, PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1. National policy and regulatory framework for IWT control and wildlife management is reviewed and updated Indicator: Presence of updated and officially approved policy and legislative documents selected by the project for development/improvement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assessment to clarify current gaps in the legislation and select target policy and legislative documents for development/update | MINAMB, INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Drafting/updating of the selected documents | MINAMB, INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discussion of the updated/drafted documents with stakeholders | MINAMB, INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalizing of the legislation and submitting to the Government | MINAMB, INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promotion of approval of the updated policy/legislation by the National Assembly | MINAMB, INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2. National ECU and other wildlife law enforcement agencies are provided with trainings, manuals, and equipment to effectively enforce, prosecute, and penalize wildlife crime Indicator: INBAC Capacity Scorecard, ICCWC IF Score for Angola |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement of equipment for the ECU | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trainings and mentoring for ECU staff | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trainings for law enforcement officers of INBAC, Police, Customs, Prosecutors and Judiciary | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development and publication of manuals on wildlife and forest crime for LE officers | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3. The Wildlife School in Menongue has comprehensive national training programmes for PA rangers and provides necessary training for the PA staff Indicator: at least 250-300 PA rangers trained at the school |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement of training equipment for the school | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of the training programmes and trainings for trainers | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regular trainings for PA rangers | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1. Two local inter-agency Environmental Crime Units are established in the project areas and provided with comprehensive anti-poaching trainings, equipment, and initial operational support Indicator: two officially established and functional ECUs in the Luando SNR and Maiombe NP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development and facilitation of official endorsement of interagency agreements to establish the ECUs, SOPs and cooperation plans | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial workshops and trainings on interagency cooperation for each ECU | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly meetings of the ECUs for information exchange, planning, and reporting | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Necessary law enforcement training to the participants of the ECUs | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement of the equipment for the ECUs | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial support of the ECUs operations | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2. Comprehensive and participatory Management Plans for the PAs in the project areas are developed/updated and implemented Indicator: officially approved and agreed with local communities RBM Management Plan for the Maiombe NP and Luando SNR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of land cover map for the project areas based on the satellite imageries | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development/update of the MPs for the PAs | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discussions of the MP with stakeholders and its approval | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regular trainings for the PA staff | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement of the equipment for the PA staff | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support for the PA management | INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1. Community natural resource management plans in the elephant habitat are developed and implemented Indicator: at least 10,000-12,000 people are trained in the sustainable NRM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Feasibility assessment of different forms of sustainable livelihood and community-based NRM | Project Partner for Output 3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Providing trainings to the local communities on CBNRM and other forms of sustainable livelihood | Project Partner for Output 3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development and support of the community based pilot CBNRM initiatives in the target communities | Project Partner for Output 3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of ESMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2. Public awareness campaign targeting IWT, bushmeat consumption, HWC and habitat degradation is developed and implemented in the project areas. Indicator: at least 100,000 people are involved in the campaign |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development and support of the public awareness campaign projects | MINAMB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.1. Participatory project monitoring, evaluation and learning framework is developed and implemented Indicator: Number of stakeholders participating in the M&E activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Audit | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Update of the GEF TT | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MTR | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TE | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Transect surveys of forest elephant, gorilla, and chimpanzee in Maiombe NP | PMU, INBAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Population surveys for Black Giant Sable in the Luando SNR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring of Stakeholder Engagement Plan | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring of Social and Environmental Risks in accordance with ESMP | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring of GRM and response to the grievances | GRM Sub-Committee of the PB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring of Output delivery | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring of Outcome achievements | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2. Lessons learned from the project are shared with national and international conservation programmes, including GWP Indicator: Number of lessons documented and shared by the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of the project web-site | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publication of the project bulletin | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collaborative experience exchange meetings and conferences | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project publications | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.3. Gender strategy developed and used to guide project implementation, monitoring and reporting Indicator: Presence of the Gender Strategy, annual reports on the Strategy implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of the Gender Strategy | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation and monitoring of the Strategy | PMU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex B. Monitoring Plan

| Objective/ Outcome | Indicators/ Description | Data source/Collection Methods | Frequency | Responsible for data collection | Means of verification | Assumptions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective: to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola | Mandatory Indicator 1: Total area of PAs with improved management (Maiombe NP and Luando SNR), ha: | PA patrolling and fire management data METT assessment | Annually | INBAC | METT assessment, GIS calculation of area under increased patrolling frequency and regular fire management | Assumption 1. The PAs will be provided with additional and complementary to the project support from Angola Government and international donors Assumption 2. The PAs’ staff will use knowledge, skills, and equipment provided by the project to improve PA management and protection Risk: insufficient Government support to the target PAs |
|  | Indicator 2: Populations of the flagship species in the project areas: 1.Forest Elephant: 2.Western Lowland Gorilla: 3.Chimpanzee: 4.Black Giant Sable: | Transect (distance sampling) survey in Maiombe NP; Transect and camera-trapping survey in Luando SNR | Year 1 and Year 6 | INBAC | Statistical analysis of the surveys’ data | Assumption 1. The flagship species population will stabilize a result of decreased poaching (the key threat) and increased survival rate; Assumption 2. Other environmental factors are favorable for the elephant population restoration (no epidemics); Assumption 3. All key threats for the project conservation targets (including forests) are correctly identified Risk: Populations may continue to decline due to low population numbers, extremely low population growth rate, and epidemics |
|  | Indicator 3: Area of wildlife habitat in the project areas, ha: 1.Tropical Rain Forest: 2.Miombo Woodlands: | Global Forest Watch data 2017-2025, Landsat 8 imageries | Annually | INBAC | Remote sensing and GIS analysis | Assumption: Area of forest and woodlands will remain stable under increased law enforcement and participation of local communities in conservation Risk: Incentives provided by the project to local communities may be insufficient to stop destructive and illegal practices |
|  | Indicator 4: Level of poaching in the project areas: 1.PIKE (Maiombe NP): 2.Bushmeat is exposed for selling in/around: a) Maiombe NP: b)Luando SNR: c)Luanda City: | Elephant carcasses count during patrolling of Maiombe NP. Express-observations at the local markets and roads (bushmeat trade). | Annually | INBAC | Analysis of patrolling reports and observation reports on the bushmeat trade | Assumption 1: Poaching and IWT will decrease to minimal level as a result of increased law enforcement Risk: support from the Government to LE agencies may be insufficient for effective wildlife crime enforcement |
| Outcome 1. Strengthened policy, legal and institutional framework to combat wildlife crime and manage wildlife | Indicator 5: Capacity of National Enforcement Agencies to control IWT (UNDP Capacity scorecard, %): INBAC | UNDP Capacity Scorecard | Year 3 and Year 6 | PMU, INBAC | Calculation of score using UNDP Capacity Scorecard | Assumption: INBAC officers, ECU, police, judiciary and prosecutors will use knowledge and tools provided by the project to achieve better results in LE of wildlife crimes; Government and other donors provide adequate support to LE agencies to fight wildlife crime Risk: support from the Government to LE agencies may be insufficient for effective wildlife crime enforcement |
|  | Indicator 6: National capacity to combat wildlife crime (ICCWC Indicator Framework Score) | ICCWC IF Express-Assessment | Year 3 and Year 6 | PMU, INBAC | ICCWC IF express-assessment report |  |
| Outcome 2. Improved capacity of PAs and other law enforcement agencies in the project areas to reduce wildlife crime, manage HWC, and prevent habitat degradation | Indicator 7: Annual effectiveness of anti-poaching in the project areas: a)total number of staff available for anti-poaching: b)intensity of patrolling (inspector/days/month): c)annual number seizures of wildlife and forest products: d)annual number of arrests of wildlife and forest crime offenders: | Maiombe NP and Luando SNR annual reports | Annually | INBAC | Content analysis of the PA reports | Assumption 1 . LE staff in the PAS will use knowledge, tools and equipment provided by the project to improve wildlife protection and the PA management and achieve higher results in LE. Risks: Number of the PA inspectors can be insufficient for effective law enforcement |
|  | Indicator 8: METT score (see Annex D. BD GEF TT): 1. Maiombe NP: 2. Luando SNR: | METT score | Year 3 and Year 6 | PMU, INBAC | METT assessment |  |
|  | Indicator 9: a) total annual number of HEC in Maiombe NP: b) % mitigated/solved HEC annually: | Collecting data on HEC by the NP staff | Annually | INBAC | Content analysis of the PAs’ annual reports on HEC. Random interviews of local people | Assumption 1. Local people will maintain high level of tolerance to elephants and HECs; Risk: uncontrolled use of natural resources and chaotic expansion of agriculture may increase number of HECs |
| Outcome 3. Increased involvement of local communities in the project areas in wildlife, habitat, and PA management | Indicator 10: 1. Total number of people (F/M) practicing SFM, SLM, CBNRM and/or participating in the PA management: 2. Total area (ha) under community-based SFM, SLM, and CBNRM: | Reports on pilot project results under Output 3.1 | Annually | Project Partner for Output 3.1 | Content analysis of the reports Interviews with local communities | Assumption 1. Local communities can see economic and social benefits and have interest to develop and implement CBNRM practices in the project area; Assumption 2. Local people will use knowledge and skills on CBNRM provided by the project to practice sustainable NRM; Risk: uncontrolled use of natural resources and chaotic expansion of agriculture may increase number of HECs and anthropogenic pressure on the natural resources. |
|  | Indicator 11: a. Deforestation rate in the project area, ha /year | Global Forest Watch data 2018-2025 | Annually | INBAC | Field verification Remote sensing and GIS analysis |  |
|  | Indicator 12: Frequency of wild fires in in Luando SNR (number of incidents/year): | GIS analysis of the NASA (FIRMS) MODIS NRT active fire product (MCD14DL) data 2017 - 2026 | Annually | INBAC | GIS analysis |  |
| Outcome 4: Lessons learned by the project through participatory M&E and gender mainstreaming are used nationally and internationally | Indicator 13 Number of the lessons on IWT control and CBNRM learned by the project that used in other national and international projects | Official letters from other projects about used experience References to the project in other project documents, reports and publications | Annually | PMU | Content analysis of publications, project documents and reports | Assumptions: GWP projects and other projects in Africa are interested to use lessons learned by this GEF project; Other projects make reference to the GEF project if they use its experience and lessons; Women have high interest to the project participation to improve their livelihood and social status Risks: other organizations may not provide references to the project |
|  | Indicator 14 % of women among the project participants directly benefiting from the project activities | Gender Strategy implementation reports Other reports on the project activities MTR and TE Reports | Annually | PMU, MEP | Content analysis Random interviews with local women |  |
|  | Indicator 15 Total number of direct project beneficiaries (m/f) | Project activity reports | Annually | PMU, MEP | Content analysis of the project activity reports |  |
| Mid-term GEF Tracking Tool | N/A | Standard GWP GEF Tracking Tool available at www.thegef.org Baseline GEF Tracking Tool included in Annex. | After 2nd PIR submitted to GEF | PMU, National Consultants | Completed GEF Tracking Tool |  |
| Terminal GEF Tracking Tool | N/A | Standard GWP GEF Tracking Tool available at www.thegef.org Baseline GEF Tracking Tool included in Annex. | After final PIR submitted to GEF | PMU, National Consultants | Completed GEF Tracking Tool |  |
| Mid-term Review | N/A | To be outlined in MTR inception report | Submitted to GEF same year as 3rd PIR | Independent evaluator | Completed MTR |  |
| Environmental and Social risks and management plans, as relevant. | In accordance with ESMP | As outlined by ESMP | Annually | Project Coordinator Project partner for Output 3.1. UNDP CO | Updated SESP an implemented ESMP |  |

## Annex C. Evaluation Plan

| Evaluation Title | Planned start date Month/year | Planned end date Month/year | Included in the Country Office Evaluation Plan | Budget for consultants | Other budget (i.e. travel, site visits etc…) | Budget for translation |
| --- | --- | --- | --- | --- | --- | --- |
| Mid-Term Review | May 2022 | August 2022 | No | USD 25,000 | 0 | 0 |
| Terminal Evaluation | October 2024 | December 2024 | Yes | USD 35,000 | 0 | 0 |
| Total evaluation budget |  |  |  | USD 60,000 |  |  |

## Annex D.  GEF Tracking Tool

- See file PIMS 5993 Angola GEF6 ANNEX D. GEF-6 BD TT Luando SNR and Maiombe NP Jan 20.xlsx1

## Annex E. Terms of Reference

Technical Committees in the project areas

Technical Committee in the project area will consist from representatives of local government, target communities, NGOs actively present in the project areas, and private sector. The Technical Committees will have meetings at least once a year before the Project Board meeting to review the project progress under Components 2 and 3, extract key lessons, plan project activities, review community concerns and grievances and provide recommendations to the PB, and PMU. The Technical Committee will ensure coordination among all stakeholders and their involvement in the participatory project M&E and management under PMU guidance. The Technical Committee recommendations will be reviewed and taken into consideration by the PB at its meetings as well as by the Project Management Unit (PMU). Members of the Technical Committee will be selected at the Inception phase of the project. The locations of Technical Committee meetings will be determined during the project implementation in the project area. Technical experts may be invited in to discuss specific issues. Indicative Terms of Reference are as follows. These will be reviewed by the Project Board during project inception and may be extended as necessary.

- Provide direction and guidance to project PMU;

- Review planned activities suggested by PMU and ensure that they are technically sound and that, wherever possible, there is integration and synergy between the various project components during planning and implementation in the project area;

- Review project progress, involvement of local communities and other stakeholders;

- Liaise with the Project Board to assure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Responsible for project administration;

- Plan the activities of the project and monitor progress against the project results framework and the approved annual workplan;

- Mobilize personnel, goods and services, training and grants to initiative activities, including drafting terms of reference and work specifications, and overseeing all contractors’ work;

- Monitor events as determined in the project monitoring schedule plan/timetable, and update the plan as required;

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments or reimbursement using the fund authorization and certificate of expenditures;

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports;

- Be responsible for preparing and submitting financial reports to UNDP on a quarterly basis;

- Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Participate in project M&E, monitoring of social and environmental risks, implementation of Stakeholder Communication and Engagement Plan, and the Project Gender Strategy;

- Promote technical coordination between institutions in the project area, where such coordination is necessary and where opportunities for synergy and sharing of lessons exist;

- Provide technical advice and guidance on specific issues related to the project to the Project Board;

- Share information on project progress and lessons learned with related stakeholders at the local level;

- The Technical Commttee or a subset of its members may be requested to undertake specific project-related tasks, such as preparing or reviewing analytical reports, strategies and action plans, etc.;

- Capture lessons learned during project implementation;

- Prepare the annual workplan for the following year; and update the Atlas Project Management module if external access is made available.

- Prepare the GEF PIR and relevant GWP reports and submit the final report to the Project Board;

- Based on the GEF PIR and the Project Board review, prepare the AWP for the following year.

- Ensure the mid-term review process is undertaken as per the UNDP guidance, and submit the final MTR report to the Project Board.

- Identify follow-on actions and submit them for consideration to the Project Board; and

- Ensure the terminal evaluation process is undertaken as per the UNDP guidance, and submit the final TE report to the Project Board

Key Project Staff

National Project Director

The National Project Director is appointed by the Implementing Partner. The National Project Director (NPD) is responsible for ensuring the smooth implementation of the project in line with planned project objective and outcomes. The NPD should ideally be a senior officer within the IP and will be a member of the Project Board (PB). The NPD will provide strategic support as needed to the project and with assistance from the Project Coordinator will also be responsible for ensuring cooperation, collaboration and efficient implementation of the project by project partners and reporting on project progress to the PB and for coordinating the flow of results and information from the project to the Project Board. The function of the NPD is not funded through the project.

Duties and Responsibilities

- Serve as a Chair of the Project Board;

- Supervise compliance with objectives, activities, results, and all fundamental aspects of project execution as specified in the project document;

- Supervise compliance of project implementation with national policies, procedures and ensure consistency with national plans and strategies;

- Facilitate coordination with other organizations and institutions and coordinate the project partnerships;

- Participate in project evaluation and monitoring missions;

- Coordinate with national governmental representatives on legal and financial aspects of project activities;

- Coordinate and supervise government staff inputs to project implementation;

- Coordinate, oversee and report on government cofinancing inputs to project implementation.

Project Coordinator

Background

The UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola” was designed to address key threats for wildlife in Angola including poaching and illegal wildlife trade, human-wildlife conflicts, and degradation of habitat. The project Objective is to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC). The Objective will be achieved through integrated implementation of four project strategies (Components): Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime; Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation; Component 3. Engaging local communities in sustainable wildlife, forest and PA management; and Component 4. Knowledge Management, M&E and Gender Mainstreaming. The project’s priority investments will be made in the two selected project areas – Maiombe National Park and Luando Strict Nature Reserve, which are important habitats for such endangered species as forest elephant, western lowland gorilla, central chimpanzee, and giant sable antelope. While this project is not a part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species (GWP) it was designed to contribute to the GWP as much as possible and will coordinate its activities with the Program (GWP 9071).

The Ministry of Environment / National Institute for Biodiversity and Protected Areas of Angola (MINAMB/INBAC) is looking for a Project Coordinator to manage the UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola”.

Duties and Responsibilities

The Project Coordinator (PC) will be locally recruited following Government procedures. The position will be appointed by the project Implementing Partner and funded entirely from the Project. The PC will be responsible for the management of the Project, including the mobilisation of all project inputs, supervision over project staff, consultants and sub-contractors, and will provide technical inputs and oversight across the Components. The PC will report to the NPD on all of the Project’s substantive and administrative issues, in close consultation with the assigned UNDP Programme Manager providing project oversight.

From the strategic point of view of the Project, the PC will report on a periodic basis to the Project Board, based on the NPD’s instruction. Generally, the PC will support the NPD who will be responsible for meeting government obligations under the Project, under the national implementation modality. The PC will perform a liaison role with the government, UNDP and other UN agencies, CSOs and project partners, and maintain close collaboration with other donor agencies providing co-financing.

Management and administrative M&E

- Manage the overall conduct of the project.

- Provide direction and guidance to project team(s)/ responsible party (ies); supervise and coordinate the work of all project staff, consultants and sub-contractors ensuring timing and quality of outputs.

- Execute activities by managing personnel, goods and services, training and low-value grants, including drafting terms of reference and work specifications, and overseeing all contractors’ work.

- Coordinate all project inputs and ensure that they are adhere to UNDP procedures for nationally executed projects.

- Coordinate the recruitment and selection of project personnel, consultants and sub-contracts, including drafting terms of reference and work specifications and overseeing all contractors’ work.

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments, or reimbursement using the UNDP provided format.

- Prepare, revise and submit multi-year, annual and quarterly workplans, as required by Project Board and UNDP.

- Monitor financial resources and accounting to ensure accuracy and reliability of financial reports, submitted on a quarterly basis.

- Liaise with UNDP, Project Board, relevant government agencies, and all project partners, including donor organisations and CSOs for effective coordination of all project activities.

- Monitor progress, watch for plan deviations, and make course corrections when needed within project board-agreed tolerances to achieve results.

- Facilitate administrative support to subcontractors and training activities supported by the Project.

- Provide support for completion of assessments required by UNDP, spot checks and audits.

- Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form.

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports.

- Prepare and submit financial reports to UNDP on a quarterly basis.

- Assess major and minor amendments to the project within the parameters set by UNDP-GEF.

- Assists and advises the Project Implementation Units responsible for activity implementation in the target sites.

- Carry regular, announced and unannounced inspections of all sites and the activities of the Project Implementation Units.

Technical leadership, inputs and technical M&E

- Supervise, coordinate and contribute to the achievement of project outcomes and production of project outputs across all technical components, as per the project document, in a timely and high-quality fashion.

- Prepare and ensure timely submission of Inception Report (no later than one month after the inception workshop), annual GEF Project Implementation Reports, Technical reports, quarterly financial reports, and other reports as may be required by UNDP, GEF and other oversight agencies.

- Monitor events as determined in the project monitoring plan and update the plan as required.

- Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR.

- Monitor and track progress against the GEF Core indicators.

- Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the Project Board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log.

- Perform regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities.

- Support and inform the Mid-term review and Terminal Evaluation process.

- Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans.

- Disseminate project reports and respond to queries from concerned stakeholders.

- Report progress of project to the steering committees and ensure the fulfilment of PSC directives.

- Capture lessons learned during project implementation and oversee the exchange and sharing of experiences and lessons learned with relevant community based integrated conservation and development projects nationally and internationally.

- Assist community groups, municipalities, CSOs, staff, students and others with development of essential skills through training workshops and on-the-job training thereby increasing their institutional capabilities.

- Encourage staff, partners and consultants such that strategic, intentional and demonstrable efforts are made to actively include women in the project, including activity design and planning, budgeting, staff and consultant hiring, subcontracting, purchasing, formal community governance and advocacy, outreach to social organizations, training, participation in meetings; and access to program benefits.

Required skills and expertise

- A university degree (MSc) in a subject related to natural resource management or environmental sciences.

- At least 5 years of experience in natural resource management (preferably in the context of wildlife conservation and law enforcement).

- At least 5 years of demonstrable project/programme management experience.

- At least 5 years of experience working with ministries, national or provincial institutions that are concerned with natural resource and/or environmental management.

Competencies

- Strong leadership, managerial and coordination skills, with a demonstrated ability to effectively coordinate the implementation of large multi-stakeholder projects, including financial and technical aspects.

- Ability to effectively manage technical and administrative teams, work with a wide range of stakeholders across various sectors and at all levels, to develop durable partnerships with collaborating agencies.

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project.

- Ability to coordinate and supervise multiple project implementation units in their implementation of technical activities in partnership with a variety of subnational stakeholder groups, including community and government.

- Strong drafting, presentation and reporting skills.

- Strong communication skills, especially in timely and accurate responses to emails.

- Excellent command of Portuguese, working knowledge of English is required.

International Technical Advisor

The International Technical Advisor will lead the technical project work to be carried out under all Outcomes.  The ITA will take a very active role in the creation and delivery of project outputs. This person will be directly responsible for making certain deliverables are promoting the achievement of desired GEB’s, including conservation of globally significant biodiversity.  This will include oversight of technical experts, assistance with recruitment, completion of ToRs and other quality assurances.  The ITA will support the Government with the design and implementation of policy and recommendations in mainstreaming of conservation objectives across institutional platforms. This person should be fully qualified to provide professional, international level expertise and capacity building support to the project.  This includes verifiable experience with the implementation of complex, multi-dimensional programming of Combating Illegal Wildlife Trade and HWC. The ideal ITA will have a strong background in community engagement in natural resources management, protected areas management and policy.

Duties and Responsibilities

Technical supervision, advice and quality assurance:

- Provide strategic analyses on issues relating to natural resources management with a view to identifying appropriate ‘entry points’ and recommending appropriate strategic responses through the best possible project support;

- Lead and provide technical supervision, guidance and support to the project management unit so it can carry out efforts outlined in the project document.

- Provide the necessary technical support to develop technical briefs and terms of reference for technical experts and consultants engaged for work envisaged.

- Capture lessons learned during project implementation and oversee the exchange and sharing of experiences and lessons learned with relevant community based integrated conservation and development projects nationally and internationally.

Support to the PC with project planning, M&E and reporting:

- Provide leadership for any necessary update and revision of indicators, baselines, targets, and means of verification,

- Prepare and ensure timely submission of Inception Report (no later than one month after the inception workshop), annual GEF Project Implementation Reports, Technical reports, quarterly financial reports, and other reports as may be required by UNDP, GEF and other oversight agencies.

- Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR.

- Monitor events as determined in the project monitoring plan and update the plan as required.

- Monitor and track progress against the GEF Core indicators.

- Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans.

Capacity building of the implementing partners and knowledge transfer:

- Lead in the development and provision of oversight in capacity building, including mentoring of local counterparts by consultants at community level, and identify appropriate training opportunities;

- Mainstream lessons and best practices learned elsewhere into capacity building activities for the project teams;

- Transfer and apply technical knowledge and experience from his/her academic background and professional experience to enhance technical knowledge of relevant staff of the Project.

Partnerships, advocacy and resource mobilization:

- Develop and maintain strategic networks and partnerships with relevant donors and development partners working on activities of interest with a view to facilitate projects implementation and long-term impacts

- Search and analyse information and activities relating to wildlife conservation, identify possible aspects/themes of cooperation, advise on strategically linking the project with other national, regional and global initiatives by other development partners, the private sector, and communities;

- Identify opportunities for advocacy, policy dialogues, and technical discussions with the Government, development partners and all relevant stakeholders;

- Encourage staff, partners and consultants such that strategic, intentional and demonstrable efforts are made to actively include women in the project, including activity design and planning, budgeting, staff and consultant hiring, subcontracting, purchasing, formal community governance and advocacy, outreach to social organizations, training, participation in meetings; and access to program benefits.

Required Skills and Experience

- Advanced university degree (Master’s Degree);

- At least 7 years of international project experience in wildlife conservation with emphasis upon issues of community-based resources management and conservation areas;

- Proven leadership experience with technical teams;

- A track record of engagement with senior levels of government, United Nations and donors;

- Experience working within a UN agency.

- Ability to work equally successfully with community members at grassroots level and corporations and other private sector exponents;

- Fluency in English, including excellent writing skills, is required.

- Fluent in Portuguese required; Working knowledge of English required.

Project Finance and Procurement Officer

Background

The UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola” is designed to address key threats for wildlife in Angola including poaching and illegal wildlife trade, human-wildlife conflicts, and degradation of habitat. The project Objective is to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola. The Objective will be achieved through integrated implementation of four project strategies (Components): Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime; Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation; Component 3. Engaging local communities in sustainable wildlife, forest and PA management; and Component 4. Knowledge Management, M&E and Gender Mainstreaming. The project’s priority investments will be made in the two selected project areas – Maiombe National Park and Luando Strict Nature Reserve, which are important habitats for such endangered species as forest elephant, western lowland gorilla, central chimpanzee, and black giant sable antelope. While this project is not a part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species (GWP) it was designed to contribute to the GWP as much as possible and will coordinate its activities with the Program (GWP 9071).

The Ministry of Environment / National Institute for Biodiversity and Protected Areas of Angola (MINAMB/INBAC) is looking for a Project Finance and Procurement Officer to support the management of the UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola”.

Duties and Responsibilities

Under the guidance and supervision of the Project Coordinator, the Project Finance and Procurement Officer provides leadership and support in the fields of financial management and procurement, ensuring high quality of work as well as accurate, timely, and properly recorded/documented service delivery. The Project Finance and Procurement Officer ensures effective delivery of project by entering and managing data and supporting project implementation consistent with UNDP rules and regulations. The Project Finance and Procurement Officer works in close collaboration with implementing CO and various consultants. The position requires a high level of initiative and learning motivation.

The Project Finance and Procurement Officer will carry out the following tasks:

- Setting-up the project and the annual work plans (AWP) in ATLAS (ERP system);

- Enhanced project management and pipeline module;

- Track and monitor the use of budget allocations, track approval of budget revisions and their uploading;

- Create e-requisitions, check budget for accuracy, and do receipts for payments;

- Generate financial reports and prepare monthly delivery monitoring tables for the assigned project, check for correctness, identify issues, contribute to development of solutions;

- Support project management in performing budget cycle: planning, preparation, revisions, and budget execution;

- Comply and verify budget and accounting data by researching files, calculating costs, and estimating anticipated expenditures;

- Process all types of payment requests for settlement;

- Monitor budget expenditures, ensuring that no expenditure is incurred before it has been authorized and maintain a proper record of commitments and planned expenditures;

- Prepare and submit expenditure and project budget status reports;

- Prepare periodic accounting records by recording receipts, disbursements (ledgers, cashbooks, vouchers, etc.) and reconciling data for recurring or financial reports and assist in preparation of annual procurement plans;

- Lead and support procurement and contracting processes (Individual Consultants, services and goods);

- Document Contract Assets Procurement (CAP) meetings and Regional Asset Contract Procurement submission;

- Undertake project financial closure formalities including submission of terminal reports, transfer and disposal of equipment, processing of semi-final revisions, and support professional staff in preparing the terminal assessment reports;

- Ensure that contractual processes follow the stipulated UNDP and GEF procedures;

- Compile financial reports as required and support project audits;

- Ensure proper filing of all project related documents.

Required skills and expertise

- Secondary Education with preferably specialized certification in Administration and/or Accounting and Finance; OR Bachelor’s degree in business administration, financial management, public administration or related field;

- Additional academic qualifications in business, economics, accountancy, international development, biodiversity conservation, international law, governance, peacebuilding, knowledge management, innovation, law enforcement, wildlife, is an asset;

- 6 years of professional experience in fields relevant to the specific duties of the job such as in project administration and/or financial management is a requirement, preferably in an international organization (applicable for applicants having secondary education); OR 3 years of professional experience in fields relevant to the specific duties of the job such as in project administration and/or financial management is a requirement, preferably in an international organization (applicable for applicants having bachelor’s degree);

- Demonstrated track record in procurement and in the preparation of technical and financial reports, and accounts management of international projects is an asset for this position;

- Prior experience with UNDP and/or UNDP-GEF processes, project management or oversight would be an asset.

Competencies

- Innovation: ability to make new and useful ideas work;

- Leadership: ability to persuade others to follow;

- People Management: ability to improve performance and satisfaction

- Communication: ability to listen, adapt, persuade and transform

- Delivery: ability to get things done.

Project Technical and Administrative Assistant

Background

The UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola” is designed to address key threats for wildlife in Angola including poaching and illegal wildlife trade, human-wildlife conflicts, and degradation of habitat. The project Objective is to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola. The Objective will be achieved through integrated implementation of four project strategies (Components): Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime; Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation; Component 3. Engaging local communities in sustainable wildlife, forest and PA management; and Component 4. Knowledge Management, M&E and Gender Mainstreaming. The project’s priority investments will be made in the two selected project areas – Maiombe National Park and Luando Strict Nature Reserve, which are important habitats for such endangered species as forest elephant, western lowland gorilla, central chimpanzee, and black giant sable antelope. While this project is not a part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species (GWP) it was designed to contribute to the GWP as much as possible and will coordinate its activities with the Program (GWP 9071).

The Ministry of Environment / National Institute for Biodiversity and Protected Areas of Angola (MINAMB/INBAC) is looking for a Project Technical and Administrative Assistant to support the management of the UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola”.

Duties and Responsibilities

Under the guidance and supervision of the Project Coordinator, the Project Technical and Administrative Assistant provides technical as well as administrative and management support, ensuring high quality of work as well as accurate, timely, and properly recorded/documented service delivery. The PA ensures effective delivery of project by entering and managing data and supporting project implementation consistent with UNDP rules and regulations. The PA works in close collaboration with implementing CO and various consultants. The position requires a high level of initiative and learning motivation.

The Project Technical and Administrative Assistant will carry out the following tasks:

- Assist the Project Coordinator in day-to-day management and oversight of project activities;

- Assist the Project Coordinator in matters related to M&E and knowledge resources management;

- Assist in the preparation of progress reports;

- Ensure all project documentation (progress reports, consulting and other technical reports, minutes of meetings, etc.) are properly maintained in hard and electronic copies in an efficient and readily accessible filing system, for when required by PB, TAC, UNDP, project consultants and other PMU staff;

- Provide PMU-related administrative and logistical assistance;

- Assist in preparation of necessary documents to select sub-contractors;

- Collect, register and maintain all information on project activities;

- Maintain project correspondence and communication;

- Support the preparations of project work-plans and operational and financial planning processes;

- Receive, screen and distribute correspondence and attach necessary background information;

- Prepare routine correspondence and memoranda for Project Managers signature;

- Assist in logistical organization of meetings, training and workshops;

- Prepare agendas and arrange field visits, appointments and meetings both internal and external related to the project activities and write minutes from the meetings;

- Maintain project filing system;

- Maintain records over project equipment inventory; and

- Perform other duties as required.

Required skills and expertise

- A Bachelor’s degree or an equivalent qualification;

- At least three years of work experience preferably in a project involving biodiversity conservation, natural resource management and/or sustainable livelihoods, monitoring and evaluation. Previous experience with GEF project will be a definite asset;

- At least 5 years of technical and/or administrative management experience;

- Demonstrable ability to prepare project budgets;

- Very good inter-personal skills;

- Proficiency in the use of computer software applications especially MS Word and MS Excel.

- Excellent language skills in Portuguese and English.

Competencies

- Innovation: ability to make new and useful ideas work;

- Leadership: ability to persuade others to follow;

- People Management: ability to improve performance and satisfaction

- Communication: ability to listen, adapt, persuade and transform

- Delivery: ability to get things done.

## Annex F. Overview of Technical Consultancies

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management / Monitoring & Evaluation |  |  |
| National Consultants |  |  |
| Project Coordinator Rate: $3,000/month | 72 months | The Project Coordinator will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. See the full TOR above for details (Annex E). |
| Project Finance and Procurement Officer Rate: $2,375/month | 72 months | Under the guidance and supervision of the Project Coordinator, the Project Finance and Procurement Officer provides leadership and support in the fields of financial management and procurement. See the full TOR above for details (Annex E). |
| Project Technical and Administrative Assistant Rate: $1,500/m full-time, $750/m half-time | 60 months full time, 12 months half time | Under the guidance and supervision of the Project Coordinator, the Project Technical and Administrative Assistant will assist the PMU in technical project planning, implementation and reporting as well as in administrative matters. See the full TOR above for details (Annex E). |
| Project Driver: Rate: $1,000/m | 72 months | Transportation support to the project team and vehicle maintanance. |
| International Consultant |  |  |
| Technical Advisor: Rate: $2,900/m | 72 months | Support PMU on technical planning and benchmarking, deliverables, capacity development, monitoring and evaluation. Support of the project lesson learning, experience exchange, and ICCWC IF assessment on the Years 3 and 6. |
| For Technical Assistance |  |  |
| Outcome 1 |  |  |
| Contractual Services |  |  |
| Contractual Services with organization to develop a National Wildlife Crime Law Enforcement Strategy and update selected legislation Total: $100,000 | 24 months | The Contractor will be responsible for the following: - Drafting of a National Wildlife Crime Law Enforcement Strategy in Angola; - Discussion of the Strategy draft with government and non-government stakeholders, completion of the document based on stakeholder comments; - Submitting the Strategy to MINAMB for official approval; - Based on previous legislation analysis and current legislative progress in Angola to perform express analysis of gaps in wildlife crime and wildlife management legislation (see details in Output 1.1); - To develop drafts of selected legislative documents and discuss them with government and non-government stakeholders, completion of the documents based on stakeholder comments; - Assisting MINAMB in submitting of the updated legislation to the National Assembly for official approval |
| Contractual Services with organization to provide training and mentoring programme on wildlife crime investigation, intelligence, forensics, etc., to the national Environmental Crime Unit Total: $150,000 | 36 months | The Contractor will be responsible for the following: - Assessment of the current ECU capacity and key needs of the Unit; - Development of a capacity building plan for the Unit; - Providing the Unit with mentoring and special trainings according to the developed plan above. |
| Contractual Services with organization to provide training to the law enforcement agencies to investigate, prosecute, and penalize wildlife crime Total: $150,000 | 36 months | The Contractor will be responsible for the following: - Assessment of the current capacity of the law enforcement agencies in Luanda and project areas to investigate, prosecute, and penalize wildlife crime, including reviewing of results of ICCWC IF Report for Angola 2018 and other relevant assessments; - Development of the relevant set of training programmes and implementation plan (see Output 1.2) for investigators, prosecutors, judiciary and Customs in Luanda and project areas; - Implementation of repetitive training programmes for the law enforcement staff according to the implementation plan; |
| Contractual Services with organization to develop mandatory training programmes for the Wildlife School in Menongue, train the school instructors, and provide mandatory trainings to PA rangers Total: $120,000 | 60 months | The Contractor will be responsible for the following: - Development of essential training programmes for PA ranges at the Wildlife School in Menongue (see Output 1.3); - Train at least 8 instructors for continuing trainings at the Wildlife School in Menongue; - Assist the instructors in training of at least at least 250-300 PA rangers with key focus to the rangers from the project areas (Maiombe NP and Luando SNR) and Mavinga and Luiana-Luengue NPs |
| Outcome 2 |  |  |
| National Consultants: |  |  |
| National Consultant to develop inter-agency collaboration protocol and SOP for the local inter-agency ECUs Rate: $400/day | 25 days/over Year 1 | The Consultant will be responsible for the following: - Development of the ToRs and inter-agency protocol for the local inter-agency ECUs, discussion of the ToRs and agreement with involved agencies; - Development of the Standard Operational Procedures for both Units; - Providing recommendations to the involved agencies on the Units’ staffing, functioning, equipment and training; |
| Contractual Services |  |  |
| Contractual Services with organization to develop/update the RBM Management Plans for Maiombe NP and Luando SNR Total: $110,00 | 24 months | The Contractor will be responsible for the following: - Development of the RBM Management Plans for Maiombe NP and Luando SNR in fully participatory process, following requirements of the Output 2.2; - Discussion and editing the plan with the PA staff, government agencies, local government, local communities and other stakeholders, updating the MPs based on their suggestions and comments; - Organization of the process of acceptance/approval of the MPs by local stakeholders; - Assisting the PAs in submitting of the MPs to MINAMB for official approval. |
| Contractual Services with organization to provide on-the-site trainings/refreshers for the Maiombe NP and Luando SNR management and ranger staff Total: $120,000 | 36 months | The Contractor will be responsible for the following: - Assessment of capacity of the PA staff of Maiombe NP and Luando SNR to detect and intercept wildlife crime and mange PA; - Development of the relevant set of training programmes and implementation plan (see Output 2.2) based on assessment; - Implementation of repetitive training programmes for the PA rangers and other staff according to the implementation plan |
| Contractual Services with organization to design and implement elephant, gorilla, and chimpanzee population transect surveys in the Maiombe NP on the Years 1 and 6 Total: $200,000 | 12 months | The Contractor will be responsible for the following: - Design of the transect distance sampling survey for elephant, gorilla, and chimpanzee in Maiombe NP: 40 2 km-long transects following recommendations of the Chapter 6 of the IUCN Ape Survey & Monitoring Book 2007; - Train Maiombe PA staff and national biologists on the survey methodology; - Conduct the survey in full accordance to developed design and methodology; - Develop a population survey report for all three target species in the Maiombe NP. |
| Contractual Services with organization to design and implement black giant sable camera-trapping surveys in the Luando SNR on the Years 1 and 6 Total: $120,000 | 10 months | The Contractor will be responsible for the following: - Design of the camera-trapping survey for giant black sable in the northern portion of Luando SNR; - Train Luando SNR staff and national biologists on the survey methodology; - Conduct the survey in full accordance to developed design and methodology; - Develop a population survey report for giant black sable in the Luando SNR. |
| Outcome 3 |  |  |
| National Consultants |  |  |
| National consultant to design awareness campaign on the wildlife crime impact and bushmeat demand issues Rate: $400/day | 12 days over Year 1 | The Consultant is responsible for development of the implementation plan for the awareness campaign and identification of key tools, audience, partners, and budgets at national level and in the project areas. |
| Contractual Services |  |  |
| Contractual Services with organization to conduct feasibility assessment for different forms of community-based conservation and involvement of local communities in the PA and NR management, provide trainings to selected local communities on selected forms of sustainable livelihoods, assist local communities to develop pilot projects on community-based conservation and sustainable NR management in the Maiombe NP and Luando SNR on the Years 1-6 Total: $230,000 | 60 months | The Contractor will be responsible for the following: - Conduct feasibility assessment of different options for sustainable community livelihood and CBNRM (see Output 3.1) and select the most feasible of them for the Maiombe NP and Luando SNR; - Implement and update ESMP for the project; - Based on the selected options develop capacity building programmes for targeted local communities on the approaches for sustainable community livelihood and CBNRM; - Provide relevant capacity building programmes for selected communities; - Provide assistance to the selected local communities to develop and implement pilot projects for sustainable community livelihood and CBNRM in the project areas; - Organize monitoring and evaluation of the community pilot projects; - Develop final report on the project results and recommendations. |
| Outcome 4 |  |  |
| International Consultants |  |  |
| International Consultant to conduct ESIA and develop ESMP (Output 4.1) Rate: $750/day | 40 days/Year 1 | - A participatory in-depth analysis of potential social and environmental impacts, as well as identification / validation of mitigation measures according to project SESP and development of ESIA report; - Visit of project areas and additional consultation with stakeholders on SESP risk; - Assessment of risks and potential impacts with support of external consultants and participation of project team and stakeholders, and management actions identified and incorporated into project implementation strategies. - Development of the ESMP and discussion it with PMU and Project Board |
| International Consultant for MTR (Output 4.1) Rate: $700/day Rate: $700/day | 35 days/ Year 3 | - Mid-Term Review of the project according UNDP/GEF requirements (UNDP 2014) according following criteria: Project Design, Progress towards Results, Implementation and Adaptive Management, and Risks to Sustainability; - Development of specific recommendations for the project implementation |
| International Consultant for TE (Output 4.1) Rate: $700/day | 35 days/ Year 6 | - Terminal Evaluation of the project according UNDP/GEF requirements (UNDP 2014) according following criteria: Relevance, Efficiency, Effectiveness, Impact, and Sustainability; - Extraction of lessons learned by the project and recommendations for other UNDP/GEF projects in the country |
| National Consultants |  |  |
| National Consultant to develop and support the project website Rate: $1,000/month | 15 months/ over 6 years of the project | - Develop and support the project web-site; - Technical assistance to the PMU on the web-site administration and update |
| National Consultant to develop a Gender Mainstreaming Strategy (Output 4.3) Rate: $400/day | 12 days/ over Year 1 | - Develop and discuss with stakeholders the project Gender Mainstreaming Strategy; |

## Annex G. UNDP Social and Environmental and Social Screening Template (SESP)

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola |
| - Project Number | PIMS 5993 |
| - Location (Global/Region/Country) | Angola, Africa |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

The project concept was developed in accordance with internationally proclaimed human rights, in conformity with the UN guidelines, by empowering people to know and claim their rights and increasing the ability and accountability of individuals and institutions that are responsible for respecting, protecting and fulfilling the rights. Specifically, during development stage, the project promoted inclusive participation of multiple stakeholders among government, multilateral agencies, NGOs, and community-based organizations to ensure that their opinions are taken in account and included in the project, and that no right or laws are infringed by any proposed activities. At site level, the project engaged with local communities and civil society, to jointly plan on meaningful strategies to improve biodiversity conservation, and to prevent illegal wildlife trade (IWT), poaching and reduce human-wildlife conflict (HWC). This project has a primary focus on development of strong policy and legislation framework, and sufficient institutional and technical capacity of government agencies to fight IWT, as well as involvement of local communities in sustainable wildlife and other natural resources management. Establishment of Community Management Areas and introduction of CBWM and CBNRM practices will allow local people to play key and active role in the sustainable development and management of the PAs. As the human rights based approach is not only about empowering people to know and claim their rights, it also increases accountability of individuals and institutions – namely through enforcement of laws and community rules on sustainable use of natural resources. Furthermore, it supports capacity building and abilities, including improvement of livelihoods and income-generating activities at local level by supporting people to achieve their potentials. In other words, the project will help local people to attain their potentials and be free from poverty. By reviewing, developing and strengthening regulations on wildlife and natural resources management, and by strengthening the capacity of relevant law enforcement agencies to enhance enforcement of these regulations and standards, the project also upholds principles of accountability and rule of law. As detailed in the Communication and Stakeholder Engagement Plan (Annex H), equality principles have also been applied during the concept and design project phases, which will strongly be pursed in project implementation. This includes extensive cross sectoral stakeholder engagement with government agencies, NGOs, local communities, and development partners over a period of over one year, while the full project is being developed. During project implementation, the final design of specific initiatives will be shared to key stakeholders to ensure their inputs are considered in decision-making, and jointly validated. Consultations with local communities are of great importance to learn about their socioeconomic state of affairs and how best to shape the formulation of national and locally adapted strategies for addressing and preventing illegal wildlife trade (IWT), poaching and reduce human-wildlife conflict (HWC). Local representatives of both project sites in Maiombe NP and Luando SNR will communicate directly with UNDP’s PMU, project partners, and evaluation consultants in order to increase transparency and accountability of the project activities. Their role is to strengthen accountability and transparency during project implementation. In addition, the project will establish a mechanism for communities and project stakeholders to report their grievance anonymously – a project-level Grievance Redress Mechanism (see Project Risks and Mitigation Measures sub-section of the prodoc), to receive and address any concerns about potential or actual impacts of the project. The project will institute specific procedures for grievance redress and publicly make these procedures available through the communication strategy as another tool to promote and defend human rights. Another principle of human rights approach is related to inclusiveness and equitable distribution of development opportunities and benefits to women, ethnic and marginalized groups in order to strengthen environmental and social sustainability of the project during and after its completion. The project interventions will ensure that women-headed households, lower income and marginalized groups are given prioritized access to support the project demonstration activities in local communities heavily dependent on bushmeat hunting. Example of such includes the promotion of the CBNRM and alternative livelihood opportunities, such as sustainable land management, sustainable use of forest, bushmeat and fish resources, potential promotion of tourism, production of added-value craft products, decreasing HWC, and improved management of protected areas and the numerous ecosystem services they provide. In this way it will improve the economic and social rights of the local communities and will also take care of cultural values of the local communities. The project has also assessed the capacities of duty bearers (government agencies, and PA staff) in order to ensure that they can deliver on their mandate and it proposes to strengthen these capacities to enhance service delivery to local people and avoid violation of human rights (human rights subject will be fully integrated in all training and mentoring programmes for law enforcement staff). Another principle of human rights approach is that of shared responsibility where the state is obligated to realize the human rights of communities or people living in the project areas (the project will avoid any forms of discrimination of different minorities and ethnicities in NR use in the area). The principles of equality and non-discrimination between men and women are also developed and emphasized in the gender mainstreaming plan (Annex I).

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

Gender equality implies equal treatment of women and men in laws and policies, including equal access to resources and services within families, communities and society. Therefore, the achievement of any development goal implies a gender mainstreaming approach that consists of a comprehensive analysis of all the specific needs and interests of women and men in order to come up with effective interventions that enable both to equally participate and benefit from development efforts. Angolan society is still characterized by a wide disparity between women and men with regard to education, health, income, political rights, access to basic services such as energy, water and sanitation, housing, land for cultivation and credit. Rural communities of the projects sites consist of sedentary ethnic groups traditionally characterized by a strong social hierarchy in which women, as mothers and wives, face difficulties in accessing productive resources, decision-making, and economic and social opportunities. To improve this situation in the context of the implementation of the project, appropriate gender and social measures will be fully considered in the project, and gender accountability is a cross-cutting issue that will be tracked as part of the M&E system. This GEF project can be classified as Gender targeted (result focused on the number or equity (50/50) of women, men or marginalized populations that were targeted) with strong gender interventions incorporated in the project design. During the project development the PPG team tried to involve as many women as possible in the consultation process. However, overall women’s participation was much lower due to traditional male dominance in anti-poaching, wildlife and environmental management issues in the project sites. To implement gender mainstreaming, the project will develop and implement an effective Gender Mainstreaming Strategy of the project implementation (Output 4.3). The strategy will guide the project implementation to Build project partner capacity to mainstream gender and bring along strategies that empower women as agents rather than as victims of habitat degradation and climate change. This strategy will also facilitate a multi-stakeholder analysis of the gender issues in all the different components of the programme that will inform the gender strategy and action planning with a clear set of measurable gender indicators. The key guidelines for the strategy are outlined below: - Gender balance will be ensured as much as possible regarding women participation in the Project Board and in the PMU. Project interventions will seek a greater and more even gender representation with the potential for gender mainstreaming-related activities in Maiombe NP and Luando SNR. Furthermore, relevant gender representation on various levels of project governance will be pursued. All project staff recruitment shall be specifically undertaken inviting and encouraging women applicants. The TORs for key project staff all incorporate gender mainstreaming related responsibilities. - In response to the relatively low participation of women in the project development, the project will incorporate gender considerations in the implementation procedures in a number of different ways: - Empower women by involving them in policy and legislation review, management planning processes to combat wildlife crime and manage wildlife, including capacity building activities and law enforcement of wildlife crime under Components 1 and 2; - Strong focus on rural communities and gender within Components 3 and 4 with an emphasis on involving women in development and implementation of Pilot projects on CBWM, CBNRM, HWC plans and development and alternative sources of income and value-chains for local communities in the project areas that have an emphasis on female-led activities (e.g. collection of fuelwoods and/or NTF products); active involvement of women woodland restoration, grazing, and water management activities; - All awareness raising activities will specifically target women and encourage them to take responsibilities including for engagement with the authorities with respect to natural resource management, illegal killing and trading of wildlife products and live animals; - Women’s organisations (associations) will be involved in project implementation and capacity development at national, provincial and communal levels. - The project will adopt the following principles in the day to day management: (i) gender stereotypes will not be perpetuated; (i) women and other vulnerable groups will be actively and demonstrably included in project activities and management whenever possible, and (iii) derogatory language or behaviour will not be tolerated. - The project will promote gender mainstreaming and capacity building within its project staff to improve understanding of gender issues, and will appoint a designated focal point for gender issues to support development, implementation, monitoring and strategy on gender mainstreaming internally and externally. This will include facilitating gender equality in capacity development and women’s empowerment and participation in the project activities. The project will also work with UNDP experts in gender issues in Luanda-Angola to utilize their expertise in developing and implementing GEF projects. These requirements will be monitored by the UNDP Gender Focal Point during project implementation. - The project will use gender disaggregated indicators in the PRF for regular monitoring and evaluation of the project progress and reporting, and will facilitate involvement of women in the M&E and Grievance Redress Mechanism implementation (see Table below and Annex I. Gender Analysis and Mainstreaming Plan).

Briefly describe in the space below how the Project mainstreams environmental sustainability

The whole project is geared towards mainstreaming of environmental sustainability in Angola. The project seeks to prevent the extinction of endangered species and ensure sustainability of bushmeat species populations by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola through capacity building of key law enforcement agencies at national and local levels, effective management of the two project areas- Maiombe NP and Luando SNR, and involving local communities in CBNRM and conservation. Through its four components the project is aimed to decrease key threats for wildlife and habitat such as poaching, illegal wildlife trade on high value and bushmeat species (including elephants, gorillas, chimpanzees, and black giant sables), deforestation rate in rain forest and miombo landscapes, and frequency of wild fires. The project is built in full accordance with national and international policy for biodiversity conservation and sustainable use. Thus, the project will contribute directly to the achievement of obligations of Angola under a number of international conventions, including those supported through the GEF mechanisms (CBD, CMS) and CITES. The overall environmental impact of the project is expected to be positive and critical for the endangered species survival as well as an important contribution to sustainable development and community livelihoods in the country.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). If no risks have been identified in Attachment 1 then note “No Risks Identified” and skip to Question 4 and Select “Low Risk”. Questions 5 and 6 not required for Low Risk Projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |  |
| Risk 1. The project could lead to violation of human rights of local communities via increased law enforcement without appropriate training, inappropriate management planning for target PAs, and limited ability of local communities to file grievances. Principles 1: Human Rights 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? Principle 2: Gender Equality and Women’s Empowerment 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? | I = 3 P = 4 | Moderate | The project can potentially lead to violation of human rights of local people in the project area in some ways. E.g., the project will support National Environmental Crime Unit (ECU) and will establish local ECUs in the project areas to investigate and prosecute wildlife crime. However, insufficient technical capacities of these Units may impose potential danger and violation of human rights to local people involved in poaching (about 60% of Angolans depend on bushmeat to a large extent as a major source of protein and income). Same is true for ranger staff of the target PAs those are expected to increase their law enforcement activities in the project areas. The law enforcement staff may impose potential danger to local people involved in poaching via higher risk of collateral damage and potential injury of poachers during operations. Inappropriate and exclusive management planning for the target PAS and community NRM planning can potentially restrict access to water and other critical natural resources for some communities. |  | To mitigate the risk of human right violation in the landscape area, the project will include the human rights subject into all training and mentoring programmes for law enforcement staff, including ECUs, INBAC, National Police, and PA rangers to (Outputs 1.2, 2.1, and 2.2). An environmental and social impact assessment (ESIA) will be carried out at project inception to assess human rights subject and all other environmental and social risks, followed by a subsequent environmental and social management plan (ESMP). The key project strategy to mitigate the potential negative impact of exclusion and restriction of some local groups from critical NRM is to involve poorest and marginalized people in participatory development and implementation of the Management Plans for the PAs in Maiombe NP and Luando SNR (Output 2.2). Strong and independent from the project management Grievance Redress Mechanism will be established in the project areas to mitigate potential adverse impact of increased law enforcement and inappropriate planning on marginalized local people as a risk group. Access to GRM channels for local communities will be ensured by Technical Committees established in the project areas. The project will invest in capacity building of communities on inclusive CBNRM via training programmes provided under Output 3.1 to avoid marginalization of some communities on sustainable livelihood and community-based NRM use. The Output 3.1 is designed to establish pilot projects on CBWM, CBNRM, HWC and alternative sources of income for local communities in the project areas to avoid potential tensions over NR use and exclusions. To control appropriate support of the human rights and the inclusion of key local stakeholders during the project implementation all monitoring and evaluation mission for the project will be designed using fully participatory approach (Output 4.1) with opportunity for all local groups to ensure their voices are heard and taken in account in the project management. |  |
| Risk 2. The project could lead to women discrimination via support of traditionally male-dominated activities such as law enforcement and natural resource management. Principle 2: Gender Equality and Women’s Empowerment 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? Principles 1: Human Rights 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | I = 3 P = 3 | Moderate | Management activities to control poaching, IWT, HWC, and habitat degradation that will be supported by the project are traditional male domain in Angola. Thus, the project can potentially give some advantages in this field to males and potentially discriminate females from participation in the project management, review of anti-poaching strategies, trainings, development and implementation of the community pilot projects. The project will significantly strengthen law enforcement along the entire illegal supply chain of threatened wildlife and product at the national level and in the project areas and suppress poaching and habitat degradation by different offenders potentially including women involved in illegal bushmeat trade, gathering of firewood and other resources in PAs for their livelihood. Inappropriate and exclusive development of the PA Management Plans and community NRM projects may potentially limit women participation in planning and management of NR worsening their social position and access to critical resources like water, wood, and bushmeat in some communities. |  | The Gender Analysis clearly indicated that women in Angola are greatly involved in natural resource management due to their day-to-day tasks in subsistence agriculture, collection of firewood and NTFP as well as bushmeat trade. However, the influence of traditional laws and culture still implies a certain discrimination against women with regard to ownership, use and access to resources. To avoid this potential disequilibrium in the project implementation Gender Mainstreaming Plan designed to ensure women inclusion in delivery of all project Outputs was carefully developed (Annex I). The ESIA will also look at gender angles, including how gender intersects with the multiple risks in this SESP. The gender mainstreaming plan will be updated as required after the completion of the ESIA. Moreover, the project will build a comprehensive Gender Mainstreaming Strategy (Output 4.3) to ensure gender equality and equal benefits to women from the project implementation that will also be incorporated into the ESMP as required. The key project strategy to mitigate the potential negative impact is to involve women as well as poorest and marginalized people of the project areas in in PA management and CBNRM through the participatory approach to the PA management planning and implementation of pilot projects on CBWM, CBNRM, HWC and alternative sources of income under Outputs 2.2 and 3.1 Additionally during trainings for law enforcement staff the project will promote women inclusion in all appropriate training programmes including the Wildlife School in Menongue (Outputs 1.2-1.3, 2.1 and 2.2). Strong Grievance Redress Mechanism will be established in the project area to mitigate potential adverse impact of increased law enforcement on marginalized local people as a risk group, including women. Access to GRM channels for local communities will be ensured by Technical Committees established in the project areas. To control appropriate support of the women rights and gender equality during the project implementation all monitoring and evaluation mission for the project will be designed using fully participatory approach (Output 4.1) with opportunity for women to ensure their voices are heard and taken in account in the project management. |  |
| Risk 3. Project activities will occur within environmentally sensitive areas, posing insignificant potential risk to sensitive habitats and species if not designed and undertaken appropriately. Principle 3: Environmental Sustainability Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management 1.2. Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | I = 3 P =1 | Low | Both project areas, Maiombe NP and Luando SNR, are key targets for the project interventions to develop effective law enforcement on anti-poaching, habitat management, including fire control, and HWC management. These areas are critical also for sustainability of local communities, as people do not receive any significant benefits from conservation. Given the project investment in local communities’ sustainable livelihood in Maiombe NP and Luando SNR by involving them in the PA management, SFM and SLM, and increasing local people capacity to effectively manage HWC, especially HEC, only positive impact is envisioned for wildlife in Angola, its habitat, and communities. |  | No special risk management measures are required. There are no any indigenous people in the project areas. Moreover, under Output 1.1 the project will promote development of Legislation on Community-Based Wildlife and Natural Resources Management that will benefit in general to all indigenous communities in Angola. Therefore the project will not affect indigenous communities in Angola in any negative way. |  |
| Risk 4. Climate change consequences could potentially affect population of endangered species in the project areas (forest elephant, gorilla, chimpanzee, and black giant sable) via increasing frequency of wildlife epidemics and forest fires, and changing rain patterns. Principle 2: Climate Change Mitigation and Adaptation 2.2. Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | I=2 P=2 | Low | The key project objective is to restore endangered wildlife populations and protect their key habitat. However, both populations and habitat can be affected by the climate change consequences (e.g, potential increase of wildlife epidemic frequency in the rain forest and increase of fire frequency in the miombo landscapes). Climate change trends have been documented for the project area and have the potential to impact habitats and species populations in the long term, and therefore may affect the intended outcome of achieving increased or stable populations of indicator species - well after the project has been completed. |  | No special risk management measures are required or can be implemented. |  |
| Risk 5. The project could impose a potential risk to health and safety of individuals involved in poaching and illegal wildlife trade in the project areas via increased level of law enforcement by poorly trained law enforcement staff Principle 3: Environmental Sustainability Standard 3: Community Health, Safety and Working Conditions 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? Principles 1: Human Rights 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | I = 4 P = 2 | Moderate | Outputs 1.2-2.2 are designed to increase law enforcement capacity of government agencies and PA rangers at national level and in both projects areas: Maiombe NP and Luando SNR. However, due to lack of technical skills on anti-poaching training and human rights issues, alongside with lack of equipment and operational support, the law enforcement staff may impose significant risk for health and life of local people involved in poaching directly or indirectly (e.g., risk of collateral damage and potential injuries of poachers). |  | In some cases poorly trained law enforcement staff potentially can impose significant risk to health and safety of some local individuals involved in poaching and illegal consumption of wildlife or accidentally present in the area of the Unit operations. An environmental and social impact assessment (ESIA) will be carried out at project inception to assess health and safety and human rights subject and all other environmental and social risks, followed by a subsequent environmental and social management plan (ESMP). To avoid the risk, the project will invest considerable resources to train and mentor the law enforcement personal in accordance with the highest standards for security and personal safety, including treating arrested or suspected offenders, during patrolling and special operations (Outputs 1.2- 2.2). To mitigate the risk of human right violation in the project areas, the project will include the human rights subject into all training and mentoring programmes for law enforcement staff, including ECUs, INBAC, National Police, and PA rangers to (Outputs 1.2-1.3, 2.1, and 2.2). Strong and independent from the project management Grievance Redress Mechanism will be established in the project areas to mitigate potential adverse impact of increased law enforcement. Access to GRM channels for local communities will be ensured by Technical Committees established in the project areas. |  |
| Risk 6. The project can potentially lead to economic displacement of local communities in the project areas via increased law enforcement and limited agricultural activities as well as potential restrictions on natural resource consumption in Miombo NP and Luando SNR. Principle 3: Environmental Sustainability Standard 5: Displacement and Resettlement 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? Principles 1: Human Rights 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? Principle 2: Gender Equality and Women’s Empowerment 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? | I= 4 P=2 | Moderate | Inside the Luando SNR, around 20,000 inhabitants live in the 3 communes of Capunda, Quimbango and Cunga Palanca relying on small-scale agriculture, fishing, non-timber forest products and bushmeat hunting for subsistence. About 60% of Angolans depend on bushmeat to a large extent as a major source of protein and income. Communities resided in the reserve area before its designation in 1938, and consisted of mixed ethnic groups due to the large number of internally displaced people during and after the war. As for Maiombe NP, about 56,000 inhabitants live in two Municipalities of Buco-Zau and Belize, living mostly on bushmeat hunting, fishing, logging, subsistence cultivation and small-scale agriculture. The project will strengthen law enforcement (Output 2.1-2.2) and potentially can limit agricultural activities of some local communities in the PAs. Outputs 2.2 (participatory management planning for the PAs in the project areas associated with law enforcement) and 3.1 (pilot projects on CBWM, CBNRM, HWC and alternative sources of income) if not conducted properly may result in economic displacement of some local communities and groups from limited and critically important resources, such bushmeat, forest products, and subsistence farming products. |  | To avoid potential adverse impact on the local people who use the PAs resources illegally and unsustainably due to current unregulated situation the project will organize management planning of the reserve in fully participatory mode to ensure that regime of proposed PAs core zones is well known to communities (Output 2.2 and 3.1). Additionally during trainings for the Reserve’s staff the project will include human rights subject in all appropriate training programmes. As noted above, the ESIA process will further addresses the possible socioeconomic impacts, including those related to use of natural resources in the PAs, and management measures integrated into the project interventions, to ensure that local communities are duly informed and participate in key decisions. The ESIA process will also include additional consultations with local communities regarding the planned project interventions, and management measures (via ESMP that will include Livelihood Action Plan) will be integrated into project implementation to ensure socioeconomic impacts are positive and to prevent adverse impacts. Livelihood Action Plan will be developed as a part of ESMP under the Output 3.1 to ensure that communities have sufficient and balanced options to use natural resources sustainably and generate income from other biodiversity-friendly sources. Experienced project partner (community development organization) selected for implementation of Output 3.1 will be responsible for development of the Livelihood Action Plan as a part of ESMP and will assist PMU to implement ESMP in cooperation with Technical Committees established in the project areas. Strong Grievance Redress Mechanism will be established in the project areas to mitigate potential adverse impact of increased law enforcement on marginalized local people as a risk group. Access to GRM channels for local communities will be ensured by Technical Committees established in the project areas. No any resettlement activities will be supported or encouraged during the project implementation. There are no any indigenous people in the project areas, therefore the project will not affect indigenous communities in Angola in any way. Angolan indigenous peoples - the San and the Himba - live in Cunene, Cuando Cubango and Moxico provinces in south-east and south-west areas of the country, and do not inhabit Luando SNR and Maiombe NP as well as Cabinda, Malaje and Bie Provincies where the project areas are located. Moreover, under Output 1.1 the project will promote development of Legislation on Community-Based Wildlife and Natural Resources Management that will benefit in general to all indigenous communities in Angola. Therefore the project will not affect indigenous communities in Angola in any negative way”. |  |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  |  | Comments |
|  | Low Risk |  |  |  |  |  |
|  | Moderate Risk |  |  | X |  | The project has overall Moderate Risk rating given its potential negative impact on human rights, community safety as well as on gender imbalance and economic displacement of local community areas from limited and critically important natural resources on both projects sites - Maiombe NP and Luando SNR. In line with UNDP’s SES the project will conduct an environmental and social impact assessment (ESIA) and develop an environmental and social management plan (ESMP) that will include at least the following: • Human Rights and Safety Action Plan; • Community Livelihood Action Plan; • Gender Mainstreaming Strategy. Experienced project partner (community development organization) selected for implementation of Output 3.1 will assist PMU to implement ESMP in cooperation with Technical Committees established in the project areas. Implementation of an independent grievance and accountability mechanism will allow local communities and other stakeholders to raise concerns and grievances, and facilitate follow-up corrective action responses. Standard M&E and adaptive management procedures will be applied during project implementation. And, the independent Mid-term Review and Terminal Evaluation will assess whether appropriate risk mitigation measures have been taken, and how the ESMP has been implemented. |
|  | High Risk |  |  |  |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
|  | Check all that apply |  |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  | X |  | ESIA will be conducted at the Inception Phase and ESMP will be developed with Human Rights and Safety Action Plan as a part of the document. To mitigate the risk of human right violation in the landscape area, the project will include the human rights subject into all training and mentoring programmes for law enforcement staff to enhance service deliver to local people and avoid violation of human rights (Outputs 1.2-2.2). To control appropriate support of the human rights and the inclusion of key local stakeholders during the project implementation all monitoring and evaluation mission for the project will be designed using fully participatory approach (Output 4.1) with opportunity for all local communities to ensure their voices are heard and taken in account in the project management. Strong and independent from the project management Grievance Redress Mechanism will be established in the project area to mitigate potential adverse impact of increased law enforcement and inappropriate planning on local people. |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | X |  | To avoid this potential disequilibrium in the project implementation Gender Mainstreaming Plan designed to ensure women inclusion in delivery of all project Outputs was carefully developed (Annex I). Moreover, the project will build a comprehensive Gender Mainstreaming Strategy (Output 4.3) to ensure gender equality and equal benefits to women from the project implementation. The Strategy will be integrated in the ESMP |
|  | Principle 3: Environmental Sustainability Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |  |  |  |  |
|  | Principle 2: Climate Change Mitigation and Adaptation |  |  |  |  |  |
|  | Principle 3: Environmental Sustainability Standard 3: Community Health, Safety and Working Conditions |  |  | X |  | ESIA will be conducted at the Inception Phase and ESMP will be developed with Human Rights and Safety Action Plan as a part of the document. To avoid the risk the project will invest considerable resources to train and mentor the law enforcement personnel in accordance with the highest standards for security and personal safety, including treating arrested or suspected offenders, during patrolling and special operations (Outputs 1.2-2.2). Strong and independent from the project management Grievance Redress Mechanism will be established in the project area to mitigate potential adverse impact of increased law enforcement on local people |
|  | 4. Cultural Heritage |  |  |  |  |  |
|  | Principle 3: Environmental Sustainability Standard 5: Displacement and Resettlement |  |  | X |  | ESIA will be conducted at the Inception Phase and ESMP will be developed with Community Livelihood Action Plan as a part of the document. To avoid potential adverse impact on the local people who use the reserve resources illegally and unsustainably due to current unregulated situation the project will organize management planning of the reserve in fully participatory mode to ensure that regime of proposed reserve’s core zones is well known to communities (Output 2.2 and 3.1). Additionally during trainings for the reserve’s staff the project will include human right subject in all appropriate training programmes. Strong Grievance Redress Mechanism will be established in the project area to mitigate potential adverse impact of increased law enforcement on local people. A Livelihood Action Plan will be developed under Output 3.1 as a part of ESMP to support sufficient livelihood options for local communities in the project areas. Experienced project partner (community development organization) selected for implementation of Output 3.1 will be responsible for development of the Livelihood Plan and will assist PMU to implement ESMP in cooperation with Technical Committees established in the project areas. |
|  | 6. Indigenous Peoples |  |  |  |  | There are no any indigenous people in the project areas. Therefore the project will not affect indigenous communities in Angola. Moreover, under Output 1.1 the project will promote development of Legislation on Community-Based Wildlife and Natural Resources Management that will benefit to indigenous communities in Angola. |
|  | 7. Pollution Prevention and Resource Efficiency |  |  |  |  |  |

SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | Yes |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | Yes |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | Yes |
| 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | Yes |
| 6. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 7. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 8. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | Yes |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | Yes |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | Yes |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | Yes |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | Yes |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | Yes |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | Yes |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? Given UNDP sufficient experience with indigenous people groups in Angola, we are certain that the Angolan indigenous peoples like the San and the Himba, live in Cunene, Cuando Cubango and Moxico provinces in south-east and south-west areas of the country, and do not inhabit Luando SNR and Maiombe NP as well as Cabinda, Malaje and Bie Provincies where the project areas are located | No |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas)? | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.4 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.5 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.6 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.7 Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | No |
| 6.8 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

## Annex G1. Terms of Reference for Environmental and Social Impact Assessment (ESIA) and Environmental and Social Management Plan (ESMP)

| Location: | Home-based with mission travel to Angola (10-12 days) |
| --- | --- |
| Application Deadline: | XXX |
| Type of Contract: | Individual Contract |
| Post Level: | International Consultant |
| Languages required: | English and Portuguese |
| Duration of Initial Contract : | XX September 2019 – 25 December 2019 |
| Expected duration of the assignment: | 40 days, including 10-12 days on mission to Angola and the project areas. |

Background

UNDP/GEF project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola” is designed to address key threats for wildlife in Angola including poaching and illegal wildlife trade, human-wildlife conflicts, and degradation of habitat. The project Objective is to prevent the extinction of terrestrial species by combating illegal wildlife trade (IWT) and reducing human-wildlife conflict (HWC) in Angola. The Objective will be achieved through integrated implementation of four project strategies (Components): Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime; Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation; Component 3. Engaging local communities in sustainable wildlife, forest and PA management; and Component 4. Knowledge Management, M&E and Gender Mainstreaming. The project’s priority investments will be made in the two selected project areas – Maiombe National Park and Luando Strict Nature Reserve, which are important habitats for such endangered species as forest elephant, western lowland gorilla, central chimpanzee, and black giant sable antelope. While this project is not a part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species (GWP) it was designed to contribute to the GWP as much as possible and will coordinate its activities with the Program (GWP 9071).

The UNDP Social and Environmental Screening Procedure (SESP) was followed during project preparation, as required by the SESP Guidance Note of the UNDP. Accordingly, the social and environmental sustainability of project activities is in compliance with the SESP for the project. The SESP identified moderate social and environmental risk for this project that would have potential negative impacts in the absence of safeguards in the conditions of ineffective project management. To avoid any potential risks for any likely impacts, the project will conduct Environmental and Social Impact Assessment (ESIA) and develop Environmental and Social Management Plan (ESMP) at the project Inception Phase, that will include at least following parts: Human Rights and Safety Action Plan, Community Livelihood Action Plan, and Gender Mainstreaming Strategy (Output 4.3).   The ESIA will be completed and ESMP developed before any project activities may start. Responsibility on implementation and monitoring of the ESMP will be assigned to an experienced project partner (organization) selected for implementation of the Output 3.1 that will work in cooperation with Technical Committees in the project areas and assist PMU in implementation of ESMP.

The United Nations Development Programme Country Office in Angola would like to deploy an international consultant to conduct full ESIA and develop ESMP for the UNDP/GEF project.

Duties and Responsibilities

The International Consultant should conduct the project ESIA and develop ESMP using following steps and procedures:

- Conduct Social and Environmental Screening to identify potential risks and their significance, identify relevant requirements of UNDP’s SES, and determine risk category of project and nature of further assessment that may be required;

- Determine the social and environmental issues to be addressed, spatial and temporal focus, data and information needed and level of analysis required to assess the impacts;

- Determine data availability for the assessment;

- Conduct comprehensive consultations with stakeholders, partners, and project-affected communities and update of stakeholder engagement plan;

- Develop baseline environmental and social information for the ESIA;

- Review policy, legal/regulatory and institutional framework of Angola applicable for the ESIA;

- Analyze and evaluate impacts of the project on environment, communities and other stakeholders

- Examine project alternatives and revise project design based on the assessment findings;

- Prepare ESIA Report based on the structure suggested in the Attachment 2;

- Define social and environmental impact mitigation actions/measures per the mitigation hierarchy that should be implemented in the project framework;

- Detail social and environmental monitoring to be conducted during project implementation;

- Develop an ESMP to assess and build capacity to implement the environmental and social management plan and other project environmental and social components based on the structure suggested in the Attachment 3. The ESMP should contain at least following parts: Human Rights and Safety Action Plan; Community Livelihood Action Plan, and Gender Mainstreaming Strategy;

- Disclose draft ESIA and ESMP and develop a plan to communicate progress with implementation and effectiveness of the environmental and social management plan.

Deliverables and Timeframe:

The following deliverables and indicative schedule are expected from the consultancy contract. The final schedule will be agreed upon in the beginning of consultancy assignment.

| Deliverable | Timeframe |
| --- | --- |
| Deliverable 1. Assignment work schedule and mission plan agreed with UNDP CO | 10 days after signing of the contract |
| Deliverable 2. ESIA Report approved by UNDP CO and INBAC | 2 months after signing of the contract |
| Deliverable 3. ESMP approved by UNDP CO and INBAC | 3 months after signing of the contract |

Payment Conditions

This is a lump sum contract that should include costs of consultancy and international travel costs (in-country air ticket costs will be covered by the project).

Payment will be released in 3 (three) installments below upon timely submission of respective deliverables and their acceptance by the Supervisor and UNDP CO.

| Deliverable | Amount |
| --- | --- |
| Deliverable 1. Assignment work schedule and mission plan agreed with UNDP CO | 20% of the total contract amount |
| Deliverable 2. ESIA Report approved by UNDP CO and INBAC | 40% of the total contract amount |
| Deliverable 3. ESMP approved by UNDP CO and INBAC | 40% of the total contract amount |

Competencies

- Demonstrates integrity by modelling the UN’s values and ethical standards;

- Promotes the vision, mission and strategic goals of UN/UNDP;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability;

- Ability to lead strategic planning, results-based management and reporting;

- Builds strong relationships with clients, focuses on impact and result for the client and responds positively to feedback;

- Consistently approaches work with energy and a positive, constructive attitude;

- Demonstrates good oral and written communication skills;

- Demonstrates ability to manage complexities and work under pressure, as well as conflict resolution skills.

Required Skills and Experience

Education: Advanced university degree (Masters or equivalent) in social studies, public affairs, environmental and sustainable development studies, international relations, or another related field,

Experience:

- Minimum of 5 years of professional experience in conducting SESP, ESIA and development of ESMPs;

- Knowledge and experience in the area of conservation, environmental management and policy, community livelihood and social issues;

- Experience in liaising with governments, UN agencies, communities, NGOs, donors and other stakeholders;

- Experience with GEF project is desirable;

- Previous experience of work in Angola with local communities and other stakeholders is highly desirable;

- Language: Fluency in oral and written English and Portuguese is required.

Application procedures

Qualified candidates are requested to apply online via this website. The application should contain:

• Cover letter explaining why you are the most suitable candidate for the advertised position. Please paste the letter into the "Resume and Motivation" section of the electronic application.

• Technical proposal with details of the assignment completion.

• Filled P11 form including past experience in similar projects and contact details of referees (blank form can be downloaded from http://www.eurasia.undp.org/content/dam/rbec/docs/P11_modified_for_SCs_and_ICs.doc;

please upload the P11 instead of your CV.

• Financial Proposal* - specifying all-inclusive daily fee in USD.

• Incomplete applications will not be considered. Please make sure you have provided all requested materials

*Please note that the financial proposal is all-inclusive and shall take into account various expenses incurred by the consultant/contractor during the contract period (e.g. fee, health insurance, vaccination, personal security needs and any other relevant expenses related to the performance of services...).

Payments will be made only upon confirmation of UNDP on delivering on the contract obligations in a satisfactory manner. Individual Consultants are responsible for ensuring they have vaccinations/inoculations when travelling to certain countries, as designated by the UN Medical Director. Consultants are also required to comply with the UN security directives set forth underdss.un.org.

General Terms and conditions as well as other related documents can be found under: http://on.undp.org/t7fJs.

Qualified women and members of minorities are encouraged to apply.

Due to large number of applications we receive, we are able to inform only the successful candidates about the outcome or status of the selection process.

Attachment 1. Detailed description of ESIA and ESMP development

Key Stages of the ESIA Process

The key stages of an ESIA process are summarized in Table A2.1 and elaborated further below.

Table A2.1: Summary of the ESIA Process

| Stages | Steps/main tasks within each stage |
| --- | --- |
| Stage 1: Screening Key components: Complete UNDP Social and Environmental Screening Procedure (SESP) | Conduct Social and Environmental Screening to identify potential risks and their significance, identify relevant requirements of UNDP’s SES, and determine risk category of project and nature of further assessment that may be required |
| Stage 2: Scoping (for Moderate or High Risk Projects) Key components: Where initial studies and analysis have not been conducted, it is important to undertake a scoping exercise early in the assessment process (i) to identify and focus the social and environmental assessment on key issues, and (ii) to establish a logical roadmap for the assessment process. | Determine the social and environmental issues to be addressed, spatial and temporal focus, data and information needed and level of analysis required to assess the impacts |
|  | Determine data availability |
|  | Consultations with stakeholders, partners, and project-affected communities and development of stakeholder engagement plan |
| Stage 3: Conducting an ESIA Key components: Based on a clearer definition of the project to be implemented, collect necessary data/information and assess full range of impacts and examine project alternatives. Report the results of the assessment and make a draft available publically for consultation. | Further detail and define the proposed project |
|  | Develop baseline environmental and social information |
|  | Review policy, legal/regulatory and institutional framework |
|  | Examine project alternatives and revise project design |
|  | Analyze and evaluate impacts |
|  | Prepare ESIA Report |
| Stage 4: Preparing an environmental and social management plan Key components: Based on relevant findings of the assessment and the results of consultations with the project stakeholders, define measures that will be needed to, inter alia: avoid, and if avoidance is not possible, minimize, mitigate and manage expected adverse impacts of the project (per the mitigation hierarchy); monitor impacts and mitigation options/measures; build capacities, and communicate results of the environmental and social management plan (ESMP). | Define social and environmental impact mitigation actions/measures per the mitigation hierarchy |
|  | Detail social and environmental monitoring to be conducted during project implementation |
|  | Develop a plan to assess and build capacity to implement the environmental and social management plan and other project environmental and social components |
|  | Disclose draft ESIA and ESMP and develop a plan to communicate progress with implementation and effectiveness of the environmental and social management plan |
| Stages | Steps/main tasks within each stage |
| Stage 5: Appraising an ESIA/ESMP and Integrating Management Measures in Project and Budget Key components: Appraisal should ensure that the ESIA/ESMP provides information required for decision-making and that proposed actions are designed to meet national/local regulations and requirements of UNDP SES. Recommendations of ESIA/ESMP need to be adequately incorporated into project design, work plans and budget. | ESIA meets its terms of reference, both procedurally and substantively |
|  | Provides an accurate and complete evaluation of the proposed project |
|  | Describes specific mitigation, monitoring and capacity development measures that comply with applicable law, regulations, and UNDP SES |
|  | Assesses capacity of institutions responsible for implementing social/environmental management |
|  | Developed through a consultative process with strong stakeholder engagement |
|  | Assesses the adequacy of costs and financing arrangements for social and environmental management implementation |

Stage 1: Screening

UNDP requires that proposed projects undergo UNDP’s Social and Environmental Screening Procedure (SESP), with a few exceptions. The objectives of the SESP are to:

- integrate the SES Overarching Principles (i.e. human rights, gender equality and women’s empowerment, environmental sustainability) to strengthen social and environmental sustainability

- identify potential social and environmental risks and their significance

- determine a project’s risk category (Low, Moderate, High), and

- determine the level of social and environmental assessment and management required to address potential risks and impacts.

See UNDP’s SES Toolkit for SESP guidance and templates.

UNDP’s screening process assists in determining the applicability of specific SES Overarching Principles and/or Project-level Standards. Where applicable, the requirements of the relevant Principle/Standard must be addressed during the assessment and management process.

Stage 2: Scoping for an ESIA

During planning ESIA  process a number of considerations are required. These include:

- Scoping parameters of ESIA. Where initial studies and analysis have not been conducted, it is important to undertake a scoping exercise early in the assessment process (i) to identify and focus the social and environmental assessment on key issues, and (ii) to establish a logical roadmap for the assessment process. The scoping exercise will vary depending on the range and complexity of potential social and environmental impacts. Scoping typically builds on the results of the screening and involves the following tasks/components:

  - An initial identification of significant social and environmental issues and potential adverse risks and impacts to be assessed.

  - Identification of data availability and gaps for conducting the assessment

  - Identification of national/local project planning requirements as well as relevant UNDP SES requirements that must be addressed

  - Identification of feasible project alternatives that will be considered in the assessment

  - Scoping meetings with stakeholders to establish focus areas and potential issues of concern

  - A summary scoping report

Scope of Work: following details should be taken in account during scoping exercise:

    - Define project in detail and develop baseline

    - Review Policy, Legal/Regulatory and Institutional Framework

    - Examine Project Alternatives and Propose revisions to Project Design

    - Analyze and Evaluate Potential Social and Environmental Risks and Impacts

    - Prepare ESIA Report and ESMP (both draft and final following consultation)

    - Record of feedback received during consultation and how it was addressed

    - Schedule of Outputs: A schedule for conducting the assessment. (Note: schedule must be adequate for preparing the assessment, including data collection and analysis, report preparation, and implementation of the associated public disclosure and stakeholder consultation requirements).

    - Annexes

Consultations. Consulting project-affected communities on the draft terms of reference for the ESIA should be conducted to assist in identifying potential issue areas or concerns that require further attention in the conduct of the ESIA.

STAGE 3: Conducting an ESIA Study

Step 1: Further Detail and Define the Proposed Project.

The assessment must be based on the project document. Based on the project document, the project should be further detailed to include, where relevant:

- The geographic, ecological, social and temporal context of the proposed project, including any offsite investments (i.e. associated facilities) that may be required (e.g. dedicated pipelines, access roads, power plants, water supply, housing, and raw material and product storage facilities);

- Project location, site, and design (e.g. technology/process, facilities design, construction, operation and maintenance, and decommissioning or closure); and

- Map showing the project site, project’s area of influence (as determined during the scoping phase) and sensitive environmental and social features.

Step 2: Develop Baseline Information.

The current and projected environmental and social, and physical/cultural baseline data must be presented for the project’s area of influence. This should include:

- Descriptions of the relevant existing physical, biological, gender, and socio-economic conditions;

- Evaluation of any changes anticipated in these conditions before the project commences, as well as any trends in or projections of data over time after the project commences that are anticipated independently of the project, including current and proposed development activities located in the project area but not directly connected to the project; and,

- Estimation of the reliability of the information sources used and the quality of the information available, including its accuracy, precision, completeness, representativeness, etc.

The baseline data should reflect the objectives and indicators identified in the ‘scoping report.’ For spatial plans, the baseline can usefully include the stock of natural assets including sensitive areas, critical habitats, and valued ecosystem components. For sector plans, the baseline will depend on the main type of environmental and social impacts anticipated, and appropriate indicators can be selected (e.g. emissions-based air quality indicators for energy and transport strategies).

Step 3: Review Policy, Legal/Regulatory and Institutional Framework

Review the legal and permitting requirements as well as applicable social and environmental standards from:

- Applicable laws and regulations of the local and national jurisdictions in which the proposed project will operate.

- Applicable international obligations and agreements (e.g. Multilateral Environmental Agreements) that must be complied with.

- UNDP Social and Environmental Standards

- Social and environmental safeguard policies and procedures of other donors and project partners.

Assess the adequacy of the identified applicable policy, legal/regulatory and institutional framework relative to implementing and sustaining the proposed project, especially the proposed mitigation, monitoring and institutional responsibilities. Where standards differ, UNDP requires adherence to the higher standard.

This discussion provides the legal and regulatory context for the project and helps to ensure that all relevant planning approvals are identified. It must be noted that per the SES (para. 9), UNDP will not support activities that do not comply with national law and obligations under international law, whichever is higher (“Applicable Law”).

Step 4: Examine Project Alternatives and Revise Project Design.

Systematically review and compare feasible project alternatives identified during scoping and initial public consultation and select the preferred or most socially and environmentally sound and benign option(s) for achieving the objectives of the proposed project. Potential type and scale of likely social and environmental impacts associated with different alternatives should be considered. Consider all types of alternatives related to overall approach and project design, including the “no action” alternative. Factors to consider include:

| - Project site locations - Timing - Scales | - Facilities designs - Construction - Operation and maintenance |
| --- | --- |

- Partners 	                                                 • Organizational and management

- Intensities 	                                                           setups

- Technologies/processes 	                     •Ways of dealing with impacts

Based on the alternatives analysis conducted above, determine what, if any, modifications will be made to the project design to improve the social and environmental sustainability of the proposed project.

Step 5: Analyze and Evaluate Risks and Impacts.

Review and refine the list of potential risks and impacts identified during the scoping process.

This step of the assessment should consider the type, location, sensitivity and scale of the proposed project, analyze all of the likely and relevant social, environmental and related effects, including where relevant potential impacts on the following features:

- Physical: surface and ground water, air, soil, land use, landform/topography, noise, vibration, geology, seismicity and other natural hazards, resource use, waste, greenhouse gases, etc.

- Biological: terrestrial and aquatic flora and fauna, habitat and ecosystems, endangered species, protected areas, etc.

- Social and socioeconomic: impacts on socioeconomic conditions, human rights, livelihoods, indigenous peoples, vulnerable or marginalized groups, gender dimensions, risks of physical and/or economic displacement, occupational health and safety, cultural heritage, community health and safety. Examine if individuals or groups may be differentially or disproportionately affected because of their disadvantaged or marginalized status, and if so, ensure adverse impacts do not affect them disproportionately.

This step should also review and refine the project’s spatial and temporal area of influence established during the scoping phase. Impacts and risks must be analyzed in the context of the area of influence.

Impacts must also be analyzed for the key phases of a proposed project’s lifecycle.

Use the following parameters to further characterize and quantify the potential social and environmental impacts: positive and negative, direct and indirect (primary and secondary), cumulative and synergistic, and reversible and irreversible.

Determine whether the proposed project will meet applicable social and environmental requirements (e.g. national laws and regulations, international obligations, UNDP SES) and determine what reasonable period of time will be needed. For impacts that cannot be fully mitigated, determine the relative importance and acceptability of the residual impact (e.g., additional resources needed).

The purpose is to identify ‘win-win’ solutions where multiple, mutually reinforcing gains can strengthen the economic base, provide equitable conditions for all, and protect and enhance social and environmental sustainability.

Step 6: Prepare an ESIA Report

An ESIA Report will be prepared to provide an adequate, accurate and impartial evaluation and presentation of the issues and conclusions of the assessment. This report, which is usually technical, must be presented in an understandable format and in an appropriate language(s). Draft assessments and reports, including any draft management plans, should be disclosed before project appraisal; however if the assessment is conducted as part of project implementation, then draft assessments need to be disclosed and consulted on prior to initiation of any activities that may lead to adverse social and environmental impacts. Short summaries and graphic presentations will often be required to facilitate reading and understanding. Moreover, a non-technical summary – that can be understood by different stakeholders – should be included to facilitate and encourage comments. Where appropriate, independent expertise should be used to assist in the preparation of ESIA reports. Attachment 1 provides and outline of the content of an ESIA Report. Final reports are disclosed upon completion.

STAGE 4: Preparing an Environmental and Social Management Plan

Taking into account the relevant findings of the ESIA and the results of consultation with the project stakeholders, an Environmental and Social Management Plan (ESMP) needs to be prepared. The ESMP will be integrated into the overall project design, including the Project Monitoring Framework and Monitoring Schedule Plan.  Indicative structure of ESMP is included in the Attachment 2.

The ESMP consists of a set of mitigation, monitoring and institutional measures, including policies, procedures and practices – as well as the actions needed to implement these measures – to achieve the desired social and environmental sustainability outcomes.

An ESMP may apply broadly across UNDP and Implementing Partner organizations for project implementation, or it may apply to specific sites, facilities, or activities relating to the proposed project. The ESMP may range from a brief description of routine mitigation and monitoring measures (e.g. for Moderate Risk projects with limited, readily identifiable potential impacts) to a series of specific plans as required by UNDP’s Social and Environmental Standards (refer to specific requirements of applicable standards), including, for example, Resettlement Action Plans/Livelihood Action Plans, Indigenous Peoples Plans, Biodiversity Action Plans, Cultural Heritage Management Plans, Emergency Preparedness and

Response Plans. The level of detail and complexity of an ESMP and priority of the identified measures and actions will be commensurate with the proposed project’s risks and impacts. All plans will contain specific monitoring measures.

The ESMP will define desired social and environmental management outcomes and specify social and environmental indicators, targets, or acceptance (threshold) criteria to track ESMP implementation and effectiveness. It will also provide estimates of the human and financial resources required for implementation and identify organizational structure and processes for implementation.

Recognizing the dynamic nature of the project development and implementation process, the implementation of an ESMP will be responsive to changes in project circumstances, unforeseen events, and the results of monitoring.

An ESMP will consist of separate sections on:

- Social and environmental impact mitigation;

- Social and environmental sustainability monitoring;

- Capacity development;

- Stakeholder engagement;

- Implementation action plan.

In case of UNDP/GEF Project in Angola the ESMP should include at least following parts:

- Human Rights and Safety Action Plan;

- Community Livelihood Action Plan

- and Gender Mainstreaming Strategy

- Social and environmental impact mitigation. The ESMP will include environmental and social impact mitigation actions, in accordance with the following, listed in descending order of preference (i.e. the mitigation hierarchy):

  - Avoid, prevent or eliminate environmental and social risks and adverse impacts, wherever technically and financially feasible; for proposed projects involving existing facilities, remediation may need to be undertaken instead of, or in addition to, mitigation;

  - Where it is not technically or financially feasible to avoid, prevent or eliminate risks and impacts, identify measures and actions to minimize and mitigate impacts so that the project operates in compliance with applicable international, national and local environmental and social laws and regulations and UNDP requirements, or achieves acceptable levels of impacts otherwise defined and agreed;

  - Where it is not technically or financially feasible to minimize and mitigate risks and impacts, identify measures to offset them by enhancing the proposed project’s positive environmental and social impacts;

  - Where avoidance, mitigation and offset measures are not technically or financially feasible, identify compensatory measures to balance the residual adverse impacts.

The ESMP will describe each mitigation measure, including the type of impact and social and environmental parameter(s) to which it relates, the location and frequency, timing or conditions under which the measure is required (e.g., continuously or in the event of contingencies), and provide technical details on the mitigation technology, process, equipment, design and operating procedures, as appropriate. Potential social and environmental impacts of these measures will be estimated. Linkages with other mitigation plans (e.g., for displacement, indigenous peoples, or cultural heritage) required for the proposed project will be identified.

- Social and environmental sustainability monitoring and reporting. The ESMP will detail the social and environmental monitoring to be conducted during project implementation to:

  - Provide information about actual versus predicted social and environmental impacts;

  - Measure the effectiveness and evaluate the success of mitigation, remediation and enhancement measures;

  - Evaluate compliance with applicable international, national, and local policies laws, regulations, UNDP SES, other relevant performance standards, policies and procedures;

  - Allow corrective action to be taken when needed.

Specifically, the ESMP will detail the:

  - Mitigation measure being monitored;

  - Parameters to be measured;

  - Sampling and analytical or other monitoring methods to be used, including staff, procedures and detection limits (where appropriate);

  - Sampling or monitoring locations;

  - Frequency or timing of measurements;

  - Definition of thresholds that will signal the need for corrective actions.

In addition to recording information to track performance and establishing relevant operational controls, the monitoring plan will require the use of dynamic mechanisms, such as inspections and audits, where relevant, to verify compliance and progress toward the desired outcomes.

Monitoring activities should involve direct participation of affected stakeholders, where possible.

Stakeholder complaints or grievances are to be tracked and monitored.

Monitoring and reporting should include data disaggregated by categories of potential beneficiary and/or affected groups, and include specific gender indicators.

The monitoring plan should require the retaining of qualified and experienced external experts to verify monitoring information.

Evaluation, reporting and management of monitoring measures will also be specified in the ESMP. This will include required documentation and reporting of monitoring results and provisions for adjusting and amending the ESMP (e.g. incorporating corrective actions) in accordance with monitoring experience and feedback (see also stakeholder engagement section below).

Periodic reports are to be provided to the affected communities that describe progress with implementation of the ESMP and related action plans and on issues that the consultation process or grievance process has identified as a concern. Any material changes or additions to the mitigation measures or actions plans will be communicated to affected communities. Reports will be provided at a frequency proportionate to the concerns of affected communities but not less than annually; quarterly reporting is recommended.

- Capacity development. The ESMP will assess and detail a plan to develop implementation capacity, where needed. This will involve determining if there is sufficient capacity within the responsible organizations or institutions for implementing the ESMP. If not, a determination should be made as to whether it will be possible to develop the appropriate capacity and, if so, at what cost and in what timeframe.

The capacity development section of the ESMP will:

  - Recommend management arrangements for the project, including structure, roles, responsibilities, and authorities;

  - Designate specific personnel, including management representative(s), with well-defined and clearly communicated lines of responsibility and authority;

  - Require sufficient oversight and human and financial resources be provided on an ongoing basis to achieve effective and continuous environmental and social management throughout the life of the proposed project.

If needed, the capacity development section of the ESMP will outline a plan for strengthening capacities of UNDP staff, Implementing Partner staff, and contractors with direct responsibility for activities relevant to the social and environmental sustainability of the proposed project so that they have the knowledge and skills necessary to perform their work, including current knowledge of the host country’s regulatory requirements and the applicable requirements of UNDP environmental and social policies and procedures. Capacity development will also address the methods required to perform the specific actions and measures of the ESMP in a competent and efficient manner. The capacity development plan will have the following components:

  - Identification of capacity needs;

  - Development of a capacity development plan to address defined needs;

  - Monitoring and Evaluation of capacity development plan.

- Stakeholder Engagement. The ESMP will be developed in close consultation with project stakeholders and disclosed in draft and final form. The ESMP is to include a section that outlines a stakeholder engagement plan to promote meaningful, effective consultations during project implementation, including identification of milestones for consultations, information disclosure, and periodic reporting on progress on project implementation and issues of concern to project stakeholders. The plan should also include a description of effective processes for receiving and addressing stakeholder concerns and grievances regarding the project’s social and environmental performance.

If ESMP review and evaluation result in material changes in, or additions to, the mitigation, monitoring or capacity development measures or actions described in the ESMP on issues of concern to the stakeholders, the updated measures or actions will also be developed in close consultation with stakeholders and disclosed.

Periodic reports will be provided to potentially affected communities describing progress with implementation of the ESMP and on issues that the consultation process or grievance mechanism has identified as a concern. The frequency of these reports will be proportional to the concerns of the stakeholders but not less than annually. For projects designated as highly complex and sensitive, quarterly reporting should be required.

- Implementation action plan (schedule and cost estimates). For above aspects (mitigation, monitoring, capacity development, and stakeholder engagement), the ESMP provides (a) an implementation schedule for measures that must be carried out as part of the project, showing phasing and coordination with overall project implementation plans; and (b) the capital and recurrent cost estimates and sources of funds for implementing the ESMP. These figures are also integrated into the total project cost tables.

- Consultations on draft ESIA and ESMP. Meaningful, effective and informed consultations with projectaffected stakeholders should be undertaken on the draft ESIA and ESMP to ensure that they adequately respond to potential issues and concerns. The draft ESIA and ESMP are to be disclosed. At a minimum the draft ESIA report, which includes a summary of the draft ESMP, should be translated into local languages and made accessible with appropriate lead-time before consultation meetings. A summary of the consultation should be produced and disclosed and the draft ESIA and draft ESMP should revised as appropriate per input from project-affected stakeholders.

STAGE 5: Appraising the ESIA

As has been mentioned earlier, one of the main purposes of this guidance note is to provide information that will enable UNDP staff to ensure quality of the ESIA process (usually undertaken by external specialists), and appraise ESIA documentation completed by national governments or donor partners.

Appraisal should ensure that the ESIA/ESMP work:

  - Meets its terms of reference, both procedurally and substantively;

  - Provides an accurate and complete evaluation of the proposed project;

  - Contains the information required for decision-making;

  - Describes specific mitigation, monitoring and capacity development measures that comply with applicable law, regulations, and UNDP Social and Environmental Standards;

  - Assesses capacity of institutions responsible for implementing social/environmental management;

  - Was developed through a consultative process with strong iterative stakeholder engagement;

  - Assesses the adequacy of the capacities, cost of and financing arrangements for environmental and social management implementation.

Where existing assessments are found to contain inconsistencies with the requirements of UNDP’s SES, then additional assessment and, where necessary, stakeholder consultations should be undertaken.

Attachment 2. Indicative Outline of Environmental and Social Impact Assessment (ESIA) Report

UNDP Social and Environmental Standards:

ESIA Report – Indicative Outline

Please refer to the UNDP SES Guidance Note on Assessment and Management for additional information.

An ESIA report should include the following major elements (not necessarily in the following order):

(1) Executive summary: Concisely discusses significant findings and recommended actions.

(2) Legal and institutional framework: Summarizes the analysis of the legal and institutional framework for the project, within which the social and environmental assessment is carried out, including (a) the country's applicable policy framework, national laws and regulations, and institutional capabilities (including implementation) relating to social and environmental issues; obligations of the country directly applicable to the project under relevant international treaties and agreements; (b) applicable requirements under UNDP’s SES; and (c) and other relevant social and environmental standards and/or requirements, including those of any other donors and development partners. Compares the existing social and environmental framework and applicable requirements of UNDP’s SES (and those of other donors/development partners) and identifies any potential gaps that will need to be addressed.

(3) Project description: Concisely describes the proposed project and its geographic, social, environmental, and temporal context, including any offsite activities that may be required (e.g., dedicated pipelines, access roads, power supply, water supply, housing, and raw material and product storage facilities), as well as the project’s primary supply chain. Includes a map of sufficient detail, showing the project site and the area that may be affected by the project’s direct, indirect, and cumulative impacts. (i.e. area of influence).

(4) Baseline data: Summarizes the baseline data that is relevant to decisions about project location, design, operation, or mitigation measures; identifies and estimates the extent and quality of available data, key data gaps, and uncertainties associated with predictions; assesses the scope of the area to be studied and describes relevant physical, biological, and socioeconomic conditions, including any changes anticipated before the project commences; and takes into account current and proposed development activities within the project area but not directly connected to the project.

(5) Social and environmental risks and impacts: Predicts and takes into account all relevant social and environmental risks and impacts of the project, including those related to UNDP’s SES (Overarching Policy and Principles and Project-level Standards). These will include, but are not limited to, the following:

(a) Environmental risks and impacts, including: any material threat to the protection, conservation, maintenance and rehabilitation of natural habitats, biodiversity, and ecosystems; those related to climate change and other transboundary or global impacts; those related to community health and safety; those related to pollution and discharges of waste; those related to the use of living natural resources, such as fisheries and forests; and those related to other applicable standards.

(b) Social risks and impacts, including: any project-related threats to human rights of affected communities and individuals; threats to human security through the escalation of personal, communal or inter-state conflict, crime or violence; risks of gender discrimination; risks that adverse project impacts fall disproportionately on disadvantaged or marginalized groups; any prejudice or discrimination toward individuals or groups in providing access to development resources and project benefits, particularly in the case of disadvantaged or marginalized groups; negative economic and social impacts relating to physical displacement (i.e. relocation or loss of shelter) or economic displacement (i.e. loss of assets or access to assets that leads to loss of income sources or means of livelihood) as a result of project-related land or resource acquisition or restrictions on land use or access to resources; impacts on the health, safety and well-being of workers and project-affected communities; and risks to cultural heritage.

(6) Analysis of alternatives: systematically compares feasible alternatives to the proposed project site, technology, design, and operation – including the "without project" situation – in terms of their potential social and environmental impacts; assesses the alternatives’ feasibility of mitigating the adverse social and environmental impacts; the capital and recurrent costs of alternative mitigation measures, and their suitability under local conditions; the institutional, training, and monitoring requirements for the alternative mitigation measures; for each of the alternatives, quantifies the social and environmental impacts to the extent possible, and attaches economic values where feasible. Sets out the basis for selecting the particular project design.

(7) Mitigation Measures: Inclusion or summary of (with attachment of full) Environmental and Social Management Plan (ESMP) (see indicative outline of ESMP below.) The ESMP identifies mitigation measures required to address identified social and environmental risks and impacts, as well as measures related to monitoring, capacity development, stakeholder engagement, and implementation action plan.

(8) Conclusions and Recommendations: Succinctly describes conclusion drawn from the assessment and provides recommendations.

(9) Appendices:  (i) List of the individuals or organisations that prepared or contributed to the social and environmental assessment; (ii) References – setting out the written materials both published and unpublished, that have been used; (iii) Record of meetings, consultations and surveys with stakeholders, including those with affected people and local NGOs. The record specifies the means of such stakeholder engagement that were used to obtain the views of affected groups and local NGOs, summarizes key concerns and how these concerns addressed in project design and mitigation measures; (iv) Tables presenting the relevant data referred to or summarized in the main text; (v) Attachment of any other mitigation plans; (vi) List of associated reports or plans.

Attachment 3. Indicative outline of Environmental and Social Management Plan (ESMP)

UNDP Social and Environmental Standards:

ESMP – Indicative Outline

Please refer to the UNDP SES Guidance Note on Assessment and Management for additional information.

An ESMP may be prepared as part of the Environmental and Social Impact Assessment (ESIA) or as a stand-alone document. The content of the ESMP should address the following sections:

(1) Mitigation: Identifies measures and actions in accordance with the mitigation hierarchy that avoid, or if avoidance not possible, reduce potentially significant adverse social and environmental impacts to acceptable levels. Specifically, the ESMP: (a) identifies and summarizes all anticipated significant adverse social and environmental impacts; (b) describes – with technical details – each mitigation measure, including the type of impact to which it relates and the conditions under which it is required (e.g., continuously or in the event of contingencies), together with designs, equipment descriptions, and operating procedures, as appropriate; (c) estimates any potential social and environmental impacts of these measures and any residual impacts following mitigation; and (d) takes into account, and is consistent with, other required mitigation plans (e.g. for displacement, indigenous peoples).

(2) Monitoring: Identifies monitoring objectives and specifies the type of monitoring, with linkages to the impacts assessed in the environmental and social assessment and the mitigation measures described in the ESMP. Specifically, the monitoring section of the ESMP provides (a) a specific description, and technical details, of monitoring measures, including the parameters to be measured, methods to be used, sampling locations, frequency of measurements, detection limits (where appropriate), and definition of thresholds that will signal the need for corrective actions; and (b) monitoring and reporting procedures to (i) ensure early detection of conditions that necessitate particular mitigation measures, and (ii) furnish information on the progress and results of mitigation.

(3) Capacity development and training: To support timely and effective implementation of social and environmental project components and mitigation measures, the ESMP draws on the environmental and social assessment of the existence, role, and capability of responsible parties on site or at the agency and ministry level. Specifically, the ESMP provides a description of institutional arrangements, identifying which party is responsible for carrying out the mitigation and monitoring measures (e.g. for operation, supervision, enforcement, monitoring of implementation, remedial action, financing, reporting, and staff training). Where support for strengthening social and environmental management capability is identified, ESMP recommends the establishment or expansion of the parties responsible, the training of staff and any additional measures that may be necessary to support implementation of mitigation measures and any other recommendations of the environmental and social assessment.

(4) Stakeholder Engagement: Outlines plan to engage in meaningful, effective and informed consultations with affected stakeholders. Includes information on (a) means used to inform and involve affected people in the assessment process; (b) summary of stakeholder engagement plan for meaningful, effective consultations during project implementation, including identification of milestones for consultations, information disclosure, and periodic reporting on progress on project implementation; and (c) description of effective processes for receiving and addressing stakeholder concerns and grievances regarding the project’s social and environmental performance.

(5) Implementation action plan (schedule and cost estimates): For all four above aspects (mitigation, monitoring, capacity development, and stakeholder engagement), ESMP provides (a) an implementation schedule for measures that must be carried out as part of the project, showing phasing and coordination with overall project implementation plans; and (b) the capital and recurrent cost estimates and sources of funds for implementing the ESMP. These figures are also integrated into the total project cost tables. Each of the measures and actions to be implemented will be clearly specified and the costs of so doing will be integrated into the project's overall planning, design, budget, and implementation.

## Annex H. Stakeholder Communication and Involvement Plan

1. Information dissemination, consultation, and similar activities that took place during the PPG

This project was developed using transparent, open, and fully participatory approach with the involvement of all groups of relevant stakeholders (government organizations, multilateral and bilateral agencies, NGOs, local communities, and the private sector) at national and project area levels. Individual and focus group consultations were conducted in Luanda City, Luando SNR (with representatives of Capunda, Kunga Palanca and Quimbango villages), and Maiombe NP, Cabinda, where meetings and informal conversations were held in the Municipalities of Belize and Buco Zau. E-mail communication and Skype calls took significant part of consultative process with national and international stakeholders. Key objectives of consultative process were the following:

- Inform all group of stakeholders on the project preparation and allow them to participate in the project development and share their concerns about the project proposed implementation;

- Evaluate current level of key threats for wildlife, key ecosystems, and communities at the national level and in the project areas and identify obvious barriers on the way of sustainable development;

- Collect information on baseline programmes and projects related to the project objective;

- Understand local, cultural and political context in the country and the project areas;

- Assess current capacity of government agencies and local communities to combat wildlife crime and manage natural resources sustainably;

- Develop relevant project Outputs based on key national and project area needs;

- Conduct Social and Environmental Screening Procedure and identify key risks for the project implementation;

- Clearly define project area for interventions and collect information on Outcome and Impact Indicators; and

- Identify potential project partnerships (see Partnerships section) and clarify stakeholder roles in the project implementation.

A total of 155 stakeholders were consulted (25% females and 75% males) during the ProDoc development. Based on our observations during the stakeholder engage exercise, we noted the need to deliberately focus on women as key stakeholders in order to amplify their voices (see Mainstreaming Gender section of the ProDoc and Annex I. Gender Mainstreaming Analysis and Plan).

Consultations in the project area of Luando SNR included meetings with Administrators of Lukembo municipality and the Capunda commune in the Province of Malanje. In Luando SNR, the team conducted a site visit to Capunda where had the opportunity to have meetings with the municipal authorities of Luquembo and Kunga Palanca communes, pastors, village heads, traditional leaders, youth representatives, and women. The meetings in Capunda were attended mostly by men as management activities to control poaching, IWT, HWC, and habitat degradation supported by the project are traditional male domain in Angola.

The field mission in Cabinda included meetings with the Provincial Government, the administration of the Maiombe National Park, Communal Administrators, Traditional Authorities, including members of National Police, Border Police and the Army. The Informal conversations with residents of Buco-Zau and Belize were held to gather baseline information in terms of livelihoods and gender situation within the Park.

In addition, during our stakeholder engage exercise, we noted that the influence of traditional laws and culture still implies a certain discrimination against women with regard to ownership, use and access to resources which explains the low participation of women in the meetings. Hence, we note the need to deliberately focus on women as key stakeholders in order to amplify their voices and equal benefits from the project implementation (see Mainstreaming Gender section of the prodoc and Annex I. Gender Mainstreaming Analysis and Plan).

A validation workshop is tentatively planned for October 2018 to present the detailed project outputs, activities, budgets and implementation arrangements to all stakeholders, including all key government agencies and institutions was conducted before the project submission to UNDP HQ. Iterative circulation of the project documentation for stakeholders’ review and comments has been conducted during entire PPG process.

As a result of Stakeholder Analysis the following groups of partners and stakeholders were identified for the project implementation (see Table 1 and 2):

Table 1. Key project partnerships

| Name of on-going and planned programme/project, years of implementation | Programme/project objectives and targets | How proposed UNDP/GEF project will collaborate with the programme/project? |
| --- | --- | --- |
| GOVERNMENT |  |  |
| Protection and Rehabilitation of Giant Sable Antelope Presidential Programme, 2017-ongoing Budget: $181,000 | Restoration and monitoring of the Giant Sable population in the Cangandala and Luando National Parks | Lessons learning and incorporation of them into the GEF project design and implementation Partnerships with the Programme to deliver Outputs for Outcomes 2 and 3 in the Luando project area Representation of the Programme in the GEF Project Board Project co-financing |
| MINAMB’s Program for Biodiversity Conservation and Protected Areas, 2017-2020 Budget: $5,500,000 | Rehabilitation and development of National PA system | Lessons learning and incorporation of them into the GEF project design and implementation Partnerships with the Programme to deliver Outputs for Outcomes 2 and 3 Representation of the Programme in the GEF Project Board Project co-financing |
| MINAMB’s Project to Support Parks and Reserves, 2017-2020 Budget: $3,600,000 | Rehabilitation and development of National PA system |  |
| INBAC’s National Project for the Zoning and Regulation of Parks, 2017-2020 Budget: $1,100,000 | Zoning and improvement of the PA system management |  |
| MINAMB’s Programme of the Transfrontier Conservation Initiative for the Mayombe Forest Budget: $812,00 | Contribution to the establishment of Mayombe Forest TFCA (International Treaty). Participation in the development of international conservation cooperation in the TFCA | Lessons learning and incorporation of them into the GEF project design and implementation Representation of the Programme in the GEF Project Board Project co-financing |
| FAS Social Development Programme, ongoing | Promotion of sustainable economic and social development of the communities in Angola, including sustainable agriculture practices | Lessons learning and incorporation of them into the GEF project design and implementation Partnerships with the Programme to deliver Outputs for the Outcome 3 Representation of the Programme in the GEF Project Board |
| BI-LATERAL AND MULTI-LATERAL AGENCIES |  |  |
| German Financial Cooperation with SADC Kavango-Zambezi Transfrontier Conservation Area (KAZA TFCA) Phase III, 2017-2020 Budget: $18,200,000, including $3,531,000 for Angola’s part | To support the development of the KAZA TFCA by establishing appropriate organizational structures at regional, national and local levels, facilitating integrated management of natural resources, improving the management of protected and wildlife dispersal areas, and uplifting the socioeconomic conditions of the targeted local populations, clearly demonstrating desired impact at both biodiversity and socio-economic levels. Including support for infrastructure of Luengue-Luiana NP, ranger training, SMART introduction, and CBNRM support on Angolan side. | Lessons learning and incorporation of them into the GEF project design and implementation |
| DEFRA IWT Challenge Fund’s Developing investigation & Prosecution Capacity to Save Angola’s Elephants Project (implemented by the Stop Ivory/EPI), 2017-2020 Budget: $438,000 | Review of penalties and application in wildlife crime Best practice handbook on wildlife crime prosecutions for prosecutors and the judiciary Deliver skills based training course on wildlife crime prosecutions for 30 prosecutors and 20 magistrates/judges Implement national wildlife crime recording database Desktop scoping study of Angola’s historical and current ivory trade. Scoping visit to Luanda – on-site assessment of ivory markets, interviews with traders and law enforcement officials and production of report for investigations First investigation on Angolan ivory trade including site visits and interviews. | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcome 1 Representation of the Project in the GEF Project Board; Project co-financing |
| FAO Angola Country Programme, 2013 - ongoing | Strengthening smallholder production and productivity to improve food security and nutrition, enabling farmers to apply improved production techniques through Farmer Field Schools; Strengthening sustainable management of natural resources; Increasing resilience of rural livelihoods to climatic shock and climate change, through the development and application of an integrated Disaster Risk Reduction and Management Plan | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcome 3 Participation in the GEF Project Board Project co-financing |
| AfDB Cabinda Province Agriculture Value Chains Development Project, 2017-2021 Budget: $123,150,000 | Improvement of production, storage, processing and marketing infrastructure necessary for food crops, cash crops, marine and inland fisheries, small ruminants, and horticulture; Rehabilitation of water conveyance structures necessary for irrigation; Training for value chain actors in technical and managerial skills; Rehabilitation/construction of rural infrastructure in the communities and improvement of rural energy access. Establishment of a credit facility for rural communities | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcome 3 Participation in the GEF Project Board Project co-financing |
| World Bank led Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development, 2015- ongoing | The GWP is a $131 million grant program designed to address wildlife crime across 19 countries in Africa and Asia. The GWP serves as a platform for international coordination, knowledge exchange, and delivering action on the ground. The GWP builds and strengthens partnerships by supporting collaboration amongst national projects, captures and disseminates lessons learned, and coordinates with implementing agencies and international donors to combat IWT globally. | Lessons learning and incorporation of them into the GEF project design and implementation Exchange of lessons and best practices with other GWP Child Projects |
| EU’s FRESAN Project (Strengthening resilience and food and nutritional security in Angola), 2017-2023 Budget: $76,000,000 | Sustainable agricultural resilience and production; Improving nutrition through education and social programmes; Institutional reinforcement and multisectoral information management Project area: Cunene, Huila and Namibe Provinces | Lessons learning and incorporation of them into the GEF project design and implementation Participation in the GEF Project Board |
| INTERNATIONAL AND NATIONAL NGOs |  |  |
| GardaWorld-supported Strengthening Angola’s Criminal Justice System for Wildlife Project (implemented by Stop Ivory/IPE), 2018 Budget: $134,000 | Phase One Anti-Poaching Ranger Training Knowledge Exchange Trip for senior Angolan ministry personnel (January, 2018) Rapid Needs Assessment (RNA) for protected area management of Luengue-Luiana and Quicama and Management Action Plans (MAP) (June, 2018) Phase Two Anti-Poaching Ranger Training: Development of funded ranger training programme for induction of new recruits into INBAC over the next three years, including training trainers and on-going mentoring at the Menongue Ranger Training School (pending funding, to start 2018) | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcomes 1 and 2 Representation of the Project in the GEF Project Board Project co-financing |
| USFWS-funded Project “Building the Capacity of the Government of Angola in Countering Wildlife Trafficking in Cabinda Province” (implemented by the Wildlife Impact), 2018-2019 Budget: $222,510 | Assessment of legislation relevant to CITES implementation and wildlife crime. Roundtable review of legislation framework recommendations; Develop permit system and enforcement database to support national CITES authorities Training on CITES/Angolan law as legal basis for enforcement and prosecutions High-level enforcement and intelligence mentoring/training workshop Community Training in Maiombe National Park and Cabinda Province Wildlife confiscation and disposition training | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcomes 1-3 in the Cabinda project area Representation of the Project in the GEF Project Board Project co-financing |
| ICCF Programme to establish Conservation Caucus and support wildlife conservation in Angola, 2017 - ongoing | Establishment of functional Conservation Caucus in Angola; Support for wildlife crime law enforcement and conservation in Angola | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcomes 1 and 2 Representation of the Project in the GEF Project Board Project co-financing |
| ADPP Agriculture, Rural and Economic Development Programme, ongoing | Farmers’ Clubs, including Women’s Farmers’ Clubs project to provide local people with the knowledge, tools and resources necessary to sustainably improve agricultural production; Sustainable Charcoal Project | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver Outputs for the project Outcomes 3 Representation of the Project in the GEF Project Board Project co-financing |
| Wild@Life Chimpanzee Rescue Project in Cabinda Angola, ongoing | Capacity building for Maiombe NP rangers to fight illegal logging and wildlife crime. Establishment of rehabilitation facility for chimpanzees confiscated from poachers in Cabinda | Lessons learning and incorporation of them into the GEF project design and implementation Partnership to deliver the project Outputs 2.1, and 2.2 in the Maiombe NP |
| EU-funded Southern Africa Illegal Wildlife Trade regional training facility for KAZA TFCA Project (implemented by the Space for Giants and Tihokomela Trust), 2018-2020 Budget: $1,766,000 | A trans-frontier wildlife law enforcement training facility in Boro, Botswana Wildlife law enforcement training curriculum 250 people across KAZA will be trained and mentored (rangers/intelligence investigators/ public investigators/ community management staff) KAZA TFCA satellite communications network | Lessons learning and incorporation of them into the GEF project design and implementation |
| GEF PROJECTS |  |  |
| UNDP/GEF Iona National Park Project, 2013-2018 Budget: $8,405,000 | The project focused on the support of the government in the establishment and operationalisation of the ‘Department of Conservation Areas’ within the recently approved Instituto Nacional de Biodiversidade e Áreas de Conservação (INBAC) and rehabilitation of the largest National Park in Angola, Iona National Park (15,150 km²). | Lessons learning and incorporation of them into the GEF project design and implementation |
| UNDP/GEF Project “Expansion of Angola’s Protected Areas System”, 2015-2020 Budget: $6,300,000 | The project will increase the coverage of terrestrial PAs in Angola, enhance the capacity of the PA authority to deliver PA functions, including management planning, monitoring, surveillance of malpractices and law enforcement; and will address the needs of PA adjacent communities, for example by managing human-wildlife conflicts and developing activities that generate local socio-economic benefits. | Lessons learning and incorporation of them into the GEF project design and implementation Representation of the Project in the GEF Project Board Delivery of the Outputs for Outcomes 2 and 3 in the project areas |
| UNDP/GEF OKACOM UNDP Demonstration Projects (implemented by ACADIR), 2018-2019 Budget: $164,500 | Support of local communities in the Cubango-Okavango basin (1) to empower them to increase crop yields and improve resilience against climate change, while at the same time protecting and stimulating the biological functioning of the land; and (2) develop sustainable fishery practices | Lessons learning and incorporation of them into the GEF project design and implementation |

Table 2. Key stakeholders of the project

| Stakeholders | Functions | Role in Project |
| --- | --- | --- |
| Government |  |  |
| Ministry of Environment (MINAMB) | Responsible for conservation and sustainable management of natural resources, protection of biodiversity and endangered species, establishment and support of Protected Areas. | Implementing Partner and the Project Board Chair Direct participation in the delivery of Output 1.1 (policy and legislation) Project co-financing |
| Ministry of Interior (National Police) | The mission of the National Police Force is to: enforce law and order; execute police duties while respecting human rights and freedoms; protect private and public property; prevent, detect and investigate crime; and defend the country and ensure its security. | Key project partner to deliver the project Outputs 1.1-1.2, and 2.1. Project co-financing |
| Ministry of Agriculture and Forest (MINAGRIF) | Support of national agricultural development, sustainable management and protection of forest and wildlife resources outside the Protected Areas | Key project partner to deliver Outputs 1.1-1.2, 2.1.,2.2, and 3.1. Participation in the Project Board Participation in the project M&E |
| Ministry of Defense | Development and supervision of Angolan army, navy, and air force. | Key project partner to deliver Outputs 1.2, , and 2.1 in cooperation with other law enforcement agencies |
| National Institute for Biodiversity and Protected Areas (INBAC) | Conservation of biodiversity and management of protected areas; Designing of programme and land planning within conservation areas; Environmental studies in order to preserve the wildlife and biodiversity; Development of protected areas system; Wildlife Crime law enforcement in the PAs | Key beneficiary of the project Direct participation in the delivery of all project Outputs Project Management, M&E |
| National Forest Development Institute (IDF) | Sustainable management, protection and restoration of forest and wildlife resources in the country | Key project partner to deliver Outputs 1.1-1.2, 2.1.,2.2, and 3.1. Participation in the Project Board Participation in the project M&E |
| Environmental Crime Unit | The national multi-agency body responsible for investigation and prosecution of wildlife crime in Angola, including poaching, IWT, and wildlife trafficking | Key project partner to deliver Outputs 1.1-1.2, and 2.1 and key beneficiary of the project Participation in the Project Board Participation in the project M&E |
| Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora | Ensuring compliance with environmental legislation on environmental crimes, gather information, monitor and prohibit hunting and illegal harvesting of wildlife and related products, through trade and illegal trafficking of endangered species, including export, import and transit and fulfill the obligations of Angola under the Convention's implementation on International Trade in Endangered species (CITES) and other conventions related to biodiversity conservation. Includes following members and leadership of the MINAMB: - Minister of Defense; - Minister of Interior; - Minister of Justice and Human Rights; - Minister of Finances; - Minister of Agriculture; - Minister for Fisheries; - Minister of Petroleum; - Minister of Transportation; - Minister of Communication | Key project partner to deliver Outputs 1.1-1.3, and 2.1 Participation in the Project Board Participation in the project M&E |
| General Prosecutor’s Office of Angola | Prosecution of crimes, including wildlife crime; Reformation and improvement of the administration of criminal justice. | Key project partner to deliver Outputs 1.1, 1.2, and 2.1 Participation in the project M&E |
| National Customs Service | Investigation, prosecution and prevention of trafficking of illegal goods, including wildlife products | Key project partner to deliver Output 1.2 and 1.3 Participation in the project M&E |
| 31st of January Wildlife School in Menongue | Capacity building for PA rangers via comprehensive training programmes | Key project partner and beneficiary to deliver Output 1.3 Participation in the project M&E |
| Government of Cabinda Province | Sustainable economic and social development of the province, environmental protection | Project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 Participation in the Project Board Participation in the project M&E |
| Government of Malanje Province | Sustainable economic and social development of the province, environmental protection | Project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 Participation in the Project Board Participation in the project M&E |
| Government of Bie Province | Sustainable economic and social development of the province, environmental protection | Project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 Participation in the Project Board Participation in the project M&E |
| Maiombe NP | Protection and sustainable management of the Maiombe forest, wildlife and forest crime law enforcement, development of cooperation with local communities | Key project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 and beneficiary of the project. Participation in the Project Board Participation in the project M&E |
| Luando SNR | Protection and sustainable management of the miombo woodlands and wildlife, wildlife and forest crime law enforcement, development of cooperation with local communities | Key project partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2 and beneficiary of the project. Participation in the Project Board Participation in the project M&E |
| UN agencies |  |  |
| UNDP CO | Assistance in sustainable development and achievement of SDGs in Angola | Development of the project and support of its implementation Project assurance and in that role participation in the Project Board Project co-financing |
| UNODC | Assists Member States in their struggle against illicit drugs, crime and terrorism. In the Millennium Declaration, Member States also resolved to intensify efforts to fight transnational crime in all its dimensions, to redouble the efforts to implement the commitment to counter the world drug problem and to take concerted action against international terrorism. | Assistance to the Angola Government and PPG team to conduct ICCWC IF assessment Consulting the project team on the Outputs 1.1-1.3. Participation in the monitoring of Angola’s national capacity to control wildlife crime in the project framework |
| International Partnerships and TFCAs |  |  |
| EPI | Assistance to member countries to implement IUCN African Elephant Action Plan (AEAP) and combat ivory trade. Development of NEAP in Angola | Participation in the project development Assistance to the project team to deliver Outputs 1.1-1.3 |
| Mayombe TFCA Secretariat | Promotion of conservation and sustainable development in Mayombe Forest Transboundary Landscape in Gabon, Congo, DRC, and Angola. | Participation in the project development Participation in the project M&E |
| NGOs |  |  |
| Kissama Foundation | Management of the Presidential Programme for restoration and conservation of the black giant sable | Participation in the project development Key partner to deliver Outputs 2.1, 2.2, 3.1 and 3.2. Participation in the Project Board Participation in the project M&E |
| Stop Ivory | Implementation of the Strengthening Angola’s Criminal Justice System for Wildlife Project and Developing investigation & Prosecution Capacity to Save Angola’s Elephants Projects (see Partnerships section) | Participation in the project development Key partner to deliver Outputs 1.1-1.3 Participation in the Project Board Participation in the project M&E Project co-financing |
| 51 Degrees Ltd. | Capacity building programmes for wildlife rangers on anti-poaching and law enforcement Participation in the implementation of the Strengthening Angola’s Criminal Justice System for Wildlife Project leaded by the Stop Ivory | Key partner to deliver Outputs 1.3 and 2.2 (training programmes for PA rangers) Participation in project M&E |
| Wildlife Impact | Implementation of the Project “Building the Capacity of the Government of Angola in Countering Wildlife Trafficking in Cabinda Province” (see Partnerships section) | Participation in the project development Key partner to deliver Outputs 1.1-1.3 Participation in the project M&E Project co-financing |
| Environmental Investigation Agency (EIA) | Participation in the implementation of the Developing investigation & Prosecution Capacity to Save Angola’s Elephants Project leaded by the Stop Ivory | Key partner to deliver Outputs 1.1-1.2 Participation in the project M&E |
| Space for Giants | Implementation of the Southern Africa Illegal Wildlife Trade regional training facility for KAZA TFCA Project (see Partnerships section) | Potential partner to deliver Outputs 1.1-1.3 |
| Gremio ABC | Realization of sustainable development and education initiatives with local communities of Cabinda Province | Key partner to deliver Outputs 3.1 and 3.2. in Maiombe NP Participation in the project M&E |
| WCS Congo | Conservation and monitoring of forest elephant, gorilla and chimpanzee in the Congo Basin, including the Republic of the Congo | Key partner to develop monitoring programme, design and manage population surveys for forest elephant, gorilla and chimpanzee in the Cabinda NP and adjacent area of Congo. |
| WWF Congo | Conservation of endangered species and ecosystems in the Congo Basin | Participation in the delivery of Output 2.2 (wildlife surveys in Maiombe NP) |
| Jane Goodall Institute | Conservation and monitoring of chimpanzee populations in Congo Basin | Participation in the delivery of Output 2.2 (wildlife surveys in Maiombe NP) |
| Maiombe Environmental Network | The National Association of Environmental NGOs | Potential partner to deliver Outputs 3.1 and 3.2. Participation in the project M&E |
| ADRA | National NGO, focusing on agriculture development with communities | Potential partner to deliver Output 3.1. and 3.2. Participation in the project M&E |
| JEA | National environmental NGO, focusing mainly on environmental education | Potential partner to deliver Output 3.2. Participation in the project M&E |
| Local communities |  |  |
| Local communities living inside and outside the Luando SNR: Capunda, Kunga Palanca, Quimbango, Kissonde, Dombo, Seque, Caionde, Zimbo, Simbanda, Tunda, Singuengo, Papo Seco, Sangamba, Siminhe, Sweka, Missongue, Ngunga, and Walitcha | Practicing subsistence agriculture, char-coal production, NTFP consumption, fishing and bushmeat hunting. Some community members are involved in illegal logging, commercial bushmeat trade and high-value species poaching. | Key partner to deliver project Outputs 2.2, 3.1 and 3.2 and major beneficiary of the project Participation in the Project Board Participation in the project M&E |
| Local communities living inside and outside the Miombe NP: Buco-Zau, Belize, Inhuca, Miconje, Sassa-Zau, Intataba, Sanga Mongo, and Dinge Velho | Practicing subsistence agriculture, char-coal production, NTFP consumption, fishing and bushmeat hunting. Some community members are involved in illegal logging, commercial bushmeat trade and high-value species poaching. | Key partner to deliver project Outputs 2.2, 3.1 and 3.2 and major beneficiary of the project Participation in the Project Board Participation in the project M&E |

2. Approach to stakeholder participation

The project approach to stakeholder involvement and participation during project implementation is premised on the principles outlined in the table below.

| Principle | Stakeholder participation will: |
| --- | --- |
| Value Adding | be an essential means of adding value to the project |
| Inclusivity | include all relevant stakeholders |
| Accessibility and Access | be accessible and promote access to the process |
| Transparency | be based on transparency and fair access to information; main provisions of the project’s plans and results will be published in local mass-media |
| Fairness | ensure that all stakeholders are treated in a fair and unbiased way |
| Accountability | be based on a commitment to accountability by all stakeholders |
| Constructive | Seek to manage conflict and promote the public interest |
| Redressing | Seek to redress inequity and injustice |
| Capacitating | Seek to develop the capacity of all stakeholders |
| Needs Based | be based on the needs of all stakeholders |
| Flexible | be flexibly designed and implemented |
| Rational and Coordinated | be rationally planned and coordinated, and not be ad hoc |
| Excellence | be subject to ongoing reflection and improvement |
| Meaning | Provide meaningful information and language that is readily understandable |
| Timely | Provide information of consultation in advance of decision-making |
| Respectful | Of the traditional languages, timeframes, and decision-making processes |
| Inclusive | Representative of the views including women and vulnerable and minority groups |
| Grievances | Provide mechanism for [people to air their concerns |
| Feedback | Provide mechanisms for responding to people’s concerns |

3. Stakeholder involvement plan

The project’s design incorporates several features to ensure ongoing and effective stakeholder participation in the project’s implementation. The mechanisms to facilitate involvement and active participation of different stakeholders in project implementation will comprise include project inception workshop, establishing a steering committee, establishing a Project Management Unit, developing a project communication strategy and capacity building of all stakeholders.

- Project inception workshop to enable stakeholder awareness of the start of project implementation

The project will be launched through a multi-stakeholder workshop. The workshop will provide all stakeholders updated information on the project aims, objectives, project work plan, and budget. It will also serves as a basis for further consultation as the project implementation commences.

The inception workshop will address a number of key issues including: assist all partners to fully understand and take ownership of the project; detail the roles, support services and complementary responsibilities of key stakeholders. In addition it will acquaint the stakeholders with the regulatory framework of the project, the timetable, and the roles and responsibilities of each stakeholder. The inception report will also specify the grievance redress mechanisms, reporting to stakeholders, management functions, stakeholder involvement in project monitoring, and negotiation and partnerships.

- Constitution of Project Board to ensure representation of stakeholder interests in project

A Project Board will be constituted to ensure broad representation of all key interests throughout the project’s implementation. The representation, and broad terms of reference, of the SC are further described in Section I, Part III (Management Arrangements) of the Project Document. These will be drawn from the key implementing partners.

- Establishment of a Project Management Unit to oversee stakeholder engagement processes during project

The Project Management Unit (PMU) leaded by the Project Coordinator will take direct operational and administrative responsibility for facilitating stakeholder involvement at daily bases and ensuring increased local ownership of the project and its results.

- Project communications to facilitate ongoing awareness of project

Under Component 4 the project will develop, implement and maintain a communications strategy to ensure that all stakeholders are informed on an ongoing basis about: the project objectives; the project activities; overall project progress; and the opportunities for involvement in various aspects of the project’s implementation. This strategy will ensure the use of communication techniques and approaches that appropriate to the local contexts such as appropriate languages and other skills that enhance communication effectiveness. The project will develop and maintain a web-based platform for sharing and disseminating information on CBWM, CBNRM and HWC practices among international, national, and local stakeholders. In project areas, the Provincial Government and target local communities will provide a platform for sharing and reporting ongoing project activities including the so-important coordination of interventions.

The project communication strategy will ensure that all stakeholders, including communities have direct access to the information about the project activities and results.  The community liaison person will be selected based on their understanding of the local language and community dynamics.  The information will be shared via newspapers, posters, radio and television developed in non-technical manner and shared at existing information centres. The youth friendly corners established through the provincial government and INBAC notice boards will be used to share project related information.

To share project information, its lessons and knowledge the project will use different communication means:

- A project web-site with available project reports, publications, press-releases, datasets, draft and final legislative documents, developed management plans, etc.;

- Quarterly or 6 month project information bulletin;

- Special paper publications, including manuals, guidance, methodologies, etc.;

- Publications and presentations at the Virtual Knowledge Exchange hosted by the Global Wildlife Programme;

- Collaborative and experience exchange meetings with other GWP projects in Africa and Asia and other relevant projects;

- Exchange visits for local communities, PA and LE agencies to demonstrate the best practices;

- Publications in mass media, conservation, and scientific journals; and

- Other available communication tools and approaches.

- Stakeholder consultation and participation in project implementation

A comprehensive stakeholder consultation and participation process will be developed and implemented for each all project outputs/activities. This will include among other interviewing stakeholder representatives during the project implementation, conducting public meetings, workshops and focus group discussions with specific groups affected or benefitting from the project. The engagement with project stakeholders will be participatory and will seek the promotion of joint decision-making or strengthen partnerships with local communities.

A participatory approach will be adopted to facilitate the continued involvement of local stakeholders including the vulnerable and marginalized members of the community (including women) in Pilot projects on CBWM, CBNRM, HWC and alternative sources of income in the project areas under outputs related to outcome 3, in particular.

Wherever possible, the project will invest in the local communities’ sustainable livelihood in the Maiombe NP and Luando SNR via involving local residents from the targeted villages in the PA management, SFM and SLM, and increasing local people capacity to effectively manage HWC, especially HEC. In addition, the project will actively recruit women to take up job opportunities and attend appropriate trainings programmes to promote women inclusion in all project-related activities. Local traditional leaders will also participate in the implementation of the project as they will also supervise community-based initiatives.

- Formal structures to facilitate stakeholder involvement in project activities

The project will work within formalized structures to in order to avoid creating parallel project structures. The formal project implementation structures are elaborated in the introduction. The process of formalizing project activities in will include a formal application by the PMU to establish project activities in the respective municipalities. The established Community-Based Forest and Wildlife Management and the Community Management Areas (CMAs) in the PAs will serve as institutional mechanism for implementing the sustainable livelihood and community-based NRM. These committees will be chaired by the elected councilors.

- Capacity building

All project activities are strategically focused on building the capacity - at the systemic, institutional and individual level - in order to ensure sustainability of initial project investments. The project will focus on systematic and repetitive trainings of Environmental Crime Units officials, prosecutors, judiciary, investigators, PA managers and rangers, INBAC and government officials including traditional authorities will attend regular training sessions as one of the most effective ways to communicate with the project stakeholders and directly involve them in the project activities.

- Monitoring and Evaluation

Participatory project monitoring and evaluation is a key part of the RBM approach practiced by UNDP and GEF for all project and programmes. Thus, the project will develop M&E system and encourage stakeholders at all levels to participate in the M&E to provide sufficient information for adaptive management decision making. For M&E the project will use standard UNDP approaches and procedures (see Monitoring and Evaluation Plan section for details).

4. Coordination with other related initiatives

The project Steering Committee will ensure that there is coordinated knowledge management and cross-fertilisation of other projects with the UNDP/GEF project (see Results and Partnerships section for details).

## Annex I. Gender Analysis and Mainstreaming Plan

1. Methods

In order to develop a gender strategy for combating illegal wildlife trade and human wildlife conflict in Angola, a gender analysis was carried out by an experienced female consultant (Ms. Veronica Pais) during a fieldtrip to the two project areas: Maiombe National Park (NP) in Cabinda Province and Luando Strict Nature Reserve (SNR) located in Malanje province as well as stakeholder consultations and meetings in Luanda. The information presented in this report is based on a thorough desk study and literature review of projects undertaken in the region, collection of gender disaggregated data through official sources, interviews with key informants and stakeholders in the form of meetings and observatory participation to ensure a greater inclusivity of gender and vulnerable groups into the project.

2. Introduction

Gender equality and women’s empowerment are matters of fundamental human rights and social justice, as well as a pre-condition for societies to thrive towards inclusive development.

According to the Africa Human Development Report 2016, gender inequality costs sub-Saharan Africa $US95 billion a year, threatening the continent’s efforts for inclusive human development and economic growth (https://bit.ly/2byzEPe). In fact, African women achieve only 87% of the human development outcomes of men. Moreover, African women hold 66% of all jobs in the informal sector and only make 70 cents for each dollar made by men (Idem).

As unequal opportunities persist between women and men worldwide that delays any development effort, gender equality and women´s empowerment was prioritized simultaneously as a goal itself by the United Nations, the 5th of the 17 Sustainable Development Goals (SDGs), and a cross cutting issue throughout the Agenda 2030.

Gender equality implies equal treatment of women and men in laws and policies, including equal access to resources and services within families, communities and society. Statements from UN Women, have noted that SDGs cannot be achieved without the full participation and engagement of both women and men.

Therefore, the achievement of any development goal implies a gender mainstreaming approach that consists of a comprehensive analysis of all the specific needs and interests of women and men in order to devise effective interventions that enable both to equally participate and benefit from development efforts.

Women play a crucial role in rural communities as a very significant proportion of the work force in food production and as key players in managing and sustaining their natural resources and environment (FAO, 2011). Nevertheless, women need appropriate skills and control over land and production inputs as well as trading opportunities in the local markets in order to successfully manage their lives.

3. Context and gender situation in Angola

Despite the middle-income status, poverty in Angola is still a major challenge, mainly in rural areas, resulting in high dependence on natural resources including wildlife products. According with the 2018 African Economic Outlook (AEO), Angola has significantly reduced its poverty rate from 54% in 2000 to the current 37% (https://bit.ly/2Itcsrd).

Thanks to better performance in agriculture, fisheries, and energy sectors, Angolan economic growth recovered to an estimated 2.1% in 2017, in comparison to 0.1% in 2016. Nevertheless, economic prospects for 2018 and 2019 are still quite humble with figures between 2.4% and 2.8%, respectively, due to low oil prices. As Angolan economy continues to be strongly dependent on oil, there is a growing interest in economic diversification that’s includes tourism as a measure to tackle the overall economic slowdown (Idem).

The 2016 UNDP Human Development Report ranked Angola as low human development country positioned as 150th out of 188 countries, with Cabo Verde Islands raking 122nd, while Mozambique is in 181st position (https://bit.ly/2mNTSLv). This report also informs that Angola has a Human Development Index (HDI) of 0.533, an index adjusted to the inequality of 37.0, which measures the country's overall achievement on health, level of education attainment and standard of living. Ranging from 0 to 1, a country scores higher HDI when the lifespan, the education level and the GDP per capita are high.

As for the per capita income, the report estimates that Angolan citizens receive an annual average of $US 6,219 ($US 1 is about 232 Angolan Kwanza, https://bit.ly/1RH9CHk); much lower than Norway, with an average higher than $US 40,000 (https://bit.ly/2mNTSLv).

According with the 2014 National Census (INE, 2016), the Angolan population was 25 million, with men representing 48% of that total and women 52%. The age group between 0-14 years and 15-24 years corresponds to about 65% of the total population, which represents an extremely young population. Only 2% of the population is 65 years or older.

The country's life expectancy is at 60.2 years, 57.5 for men and 63 years for women, respectively. The average age of the Angolan population is 20.6 years. The adult literacy rate stands at 71.1%, while the average level of schooling is five years only, against the 11 expected years of schooling. Only 13% of the population between 18 and 24 years completed the secondary education while only 2.5% of the population aged 24 or over hold higher education (Idem).

Around 40% of the population of 15 or more years is engaged in labor market, with primary sector activities accounting for 44.2%, the secondary sector for 6.1%, and the tertiary for 26.2%of the national economy. About 44% of the households have access to appropriate drinking water while 31.9% have access to electricity whereas 50.9% are found in urban areas and 2.2% in rural locations. Flashlights and candles are the most used alternative to electricity (Idem).

Regarding the gender-based situation in social norms, practices and laws in Angola, the Social Institutions and Gender Index 2014 (SIGI) informs that the country has medium levels of discrimination against women in social institutions, which includes unequal inheritance rights, early marriage, violence against women, and uneven land and property rights. Angola also shows currently low discrimination based on a person´s gender and high prejudice in restricted access to resources and assets (https://bit.ly/2rVl2DM ).

In terms of political participation, the UNDP African Human Development Report on Gender 2016 acknowledged that Angola is the 8th country in the region concerning women representation in National Parliament with 36.7% of its seats occupied by women. In fact, out of the total 162 local administrators elected 50 are women and 35 women are deputy municipal administrators, 2 other women are provincial governors and 10 are vice-provincial governors (https://bit.ly/2byzEPe).

Angola is gradually making progress on promoting equal access between men and women through laws, policies and action plans (MINFAMU, Relatório Analítico de Género de Angola, 2017). At the regional and international levels, Angola has adhered to main instruments promoting human rights and women's development complemented with national initiatives promoted by the Ministry of Family and Promotion of Women. The Ministry was created in 1997 succeeding to the former Secretary of State established in 1991. MINFAMU is responsible for designing and implementing the national policy for the defense and guarantee of women´s rights including their empowerment within social, political, economic and cultural affairs (Idem).

Along with a Constitution that ensures general human rights and equal rights for women and men, Angola has signed and ratified in 1984 the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) and the Convention on the Political Rights of Women in 1985 (https://bit.ly/2L6J0oF).

Continuous efforts to achieve gender equality and the empowerment of women in Angola were made through the country´s participation in the Fourth Global Conference on Women in Beijing in 1995, where a platform of action and set of commitments was established to achieve goals of Equality, Development and Peace for all women and girls in the interest of Humanity (Idem). After 22 years, the Beijing Declaration and Platform for Action, continues very relevant with all member-states deciding that gender equality, empowerment and the rights of women and girls must be included as a goal on the 17 Global Goals that make up the 2030 Agenda for Sustainable Development (Idem).

At a national level, Angola has been taking decisive steps towards the promotion of gender equality through the contemplation of political documents. One political milestone is the National Development Plan 2013-2017 (PND) that establishes as priority, the formulation of policies that promote equal opportunities, rights and responsibilities in all areas of life for men and women. It also underlines the need to battle poverty through actions to promote women's entrepreneurship, support for women's associations and the promotion of studies on the role of women in the economic sector (Relatório Analítico de Género de Angola, MINFAMU, 2017: 11).

Alongside with the PND, the National Policy for Gender Equity and Equity Policy unanimously approved by the Council of Ministers indicates actions aimed at consolidating the process of building a society based on equality and justice, which values human and women's rights, in particular, respects and encourages positive cultural values, promotes solidarity, and the effective participation of men and women in political, economic, social, sporting and cultural life (https://bit.ly/2GujUws).

This political diploma distinguishes the follow essential areas: 1) Access to basic social services; 2) Access to economic resources and opportunities for formal employment, assurance of social protection for women in informal economy; 3) Increased participation and representation of women in local and national governmental institutions; 4) Reinforcement of legal and juridical mechanisms to protect women against domestic violence, and intervention on cultural practices that are contrary to the rights of women; 5) Family and community education to mitigate imbalances of opportunities and benefits between women and men, between girls and boys(Idem).

Despite the country’s rapid post-war economic growth based on oil production, Angolan society is still characterized by a wide disparity between women and men with regard to education, health, income, political rights, access to basic services such as energy, water and sanitation, housing, land for cultivation and credit.

Although 52% of the total 25.8 million Angolan nationals are women, they are overall less literate than men. This is informed by the 2014 National Census where is stated that 66% of the population aged 15 years and older is able to read and write. Of those, 80% are men and only 53% are women. Data shows therefore an index of gender inequality in access to education of 0.64, which is still far from the 0.99 value that Angolan Government established as a goal with the implementation of the Basic Law for the Education System as of 2004 (MINFAMU, 2017: 24).

Due to their lower level of literacy and technical education, women and girls account less as paid workforce than men, as they engaged mainly in informal employment. In fact, about 45% of women aged 15 or over where economically active, against 61% of men same age group (MINFAMU, 2017: 47).

The national employment rate is about 40%, including 34.4% in urban areas and 50% in rural areas. When considering gender, then figures change slightly as employment rate for women aged between 15 and 64 years was of 34.1% and 46.6% for men. In the same period, the unemployment rate in urban areas reached 30.8% against 14.3% in rural areas, with 24.9% among women and 23.6% among men (Idem). Consequently, women hardly benefit from existing legal rights such as maternity leave, social security and decent wages which put them into severe employment vulnerability.

During fieldwork it was noticed that women play a crucial role in rural communities as a very significant proportion of the work force in food production and as the key players in managing and sustaining their natural resources and environment. Nevertheless, as pointed out by them, women need appropriate skills and control over land and production inputs, as well as trading and credit opportunities in the local markets in order to successfully manage their lives. The consequences of such are evident in the formal labor market, where women struggle to get employed or hold the least qualified jobs. As a result, the informal sector is the last resort for them to sustain themselves and their respective families. Due to the lack of equal educational and professional opportunities, women tend to be underrepresented in decision-making forums and institutions, and experience numerous forms of gender inequality.

To improve this situation in the context of the implementation of the project, appropriate gender and social measures will be fully considered in the project, and gender accountability is a cross-cutting issue that will be tracked as part of the M&E system.

This GEF project can be classified as Gender targeted (result focused on the number or equity (50/50) of women, men or marginalized populations that were targeted) with strong gender interventions incorporated in the project design. During the project development the PPG team tried to involve as many women as possible in the consultation process. However, overall women’s participation was much lower due to traditional male dominance in anti-poaching, wildlife and environmental management issues in the project sites.

To implement gender mainstreaming, the project will develop and implement an effective Gender Mainstreaming Strategy (Output 4.3). The strategy will guide the project implementation to Build project partner capacity to mainstream gender and bring along strategies that empower women as agents rather than as victims of habitat degradation and climate change. This strategy will also facilitate a multi-stakeholder analysis of the gender issues in all the different components of the programme that will inform the gender strategy and action planning with a clear set of measurable gender indicators.

4. Analysis of Gender issues in the two project sites

4.1. Role and participation of men and women in biodiversity conservation

In both project areas of Luando Strict Nature Reserve and Maiombe NP, it was observed that men and women undertake different but complementary roles, responsibilities and tasks in the natural resource management, livelihoods and use of biodiversity resources. The knowledge and perceptions of their natural environment and the biodiversity around them is the result of gender differences in functions, responsibilities, needs, social relations, behaviors, resource accessibility, ownership, and awareness, which are location-specific and socially constructed and can be changed.

Considering the way women and men experience environmental and socioeconomic changes alongside with their roles and responsibilities, is extremely important to improve the livelihoods of resource dependent social groups taking gender issues in the account. Both project areas are biodiversity hotspots of Angola significantly impacted by poaching and illegal wildlife trade, as well as habitat degradation due to unsustainable human activities.

In addition, it was noticed that women play a critical role in maintaining and sustaining household based activities, child care, fuel, fodder and water management, animal care and also agriculture related works such as applying manure, weeding, watering, harvesting, and processing the products for consumption. When agricultural products are in surplus, women sell them to obtain some cash or products lacking in their homes. Despite their zero representation in the local village committees and decision-making, women and girls are more involved in natural resource management than men, due to their day-to-day tasks on the fields and collection of wild plants and firewood. Girls accompany their mothers, while boys go to school or stay at home playing.  The low and discrete participation of women in the meetings reveals the fact that their participation in livelihood activities and natural resource management must be increased throughout the project.

4.2. Workload related to household management and livelihood activities in the project sites

4.2.1. Maiombe National Park, Cabinda Province

During the field mission for the PPG study, the consultant visited communities of Buco-Zau and Belize in the area of Maiombe NP, located in the oil-rich enclave of Cabinda Province, which is the northernmost province of the Republic of Angola.

The province of Cabinda is bounded on the north by the Republic of Congo, east and south - by the Democratic Republic of Congo, and west - by the Atlantic Ocean. The capital of the province is the city of Cabinda. The province has total area of 7,283 km² and about 716,076 inhabitants; of those 360,310 are women. Agriculture, logging and oil extraction are the most important economic sectors of the province.

Maiombe National Park includes both Buco-Zau and Belize municipalities with a total of 56,000 inhabitants approximately. The number of women is slightly higher than men according to key informants, but the exact numbers of men and women are unknown. Buco-Zau is a town with ~40,000 inhabitants, while Belize is a village with ~18,000 inhabitants only. The population of Buco-Zau and Belize belong almost entirely to the Bantu people, to a group formerly called Fiote whose language consist of the most spoken language in the province, after the Portuguese language according with the 2014 Census (INE, 2016).

Communities in Maiombe NP rely mostly on poaching, fishing, logging and subsistence agriculture that requires periodic clearing of forest to plant new fields as productivity declines at old sites. Wood removed is used for firewood or sometimes turned to charcoal for cooking and heating needs. Charcoal is often sold along roadsides representing a major source of income for many families within this area.

Men have the responsibility of cleaning up the fields to be then cultivated by their spouses. Some couples have joint plots while others have separated lavras. Widows and single women pay to men in the village to clean up their fields. Cassava, sweet potatoes, peanut, corn, beans and vegetables are the main cultivated crops that simultaneously feed the household and generate income. Gathering of edible plants and plant products such as fruits, leaves, tubers, roots, nuts, mushrooms, and medicinal plants are of great importance as well and often done by women and girls.

Both women and girls in Maiombe NP are engaged from early morning till night in household based activities, child care, fuel and water management, animal care and also family crops and trade. Men are mainly engaged in hunting, fishing, and construction of infrastructures, and other related-services.

Trade is mainly done by women along the main road to minimize costs associated with transportation; nevertheless some women travel to Macabi market located at the border with Congo to sell their products. Alongside with agriculture, some women produce basketry items for house-consumption and trade. This seems to have great commercial potential as the movement of people and goods between Maiombe NP and Cabinda, and to the Congolese border is daily intensive.

Decisions about income distribution are not that linear: some men keep the greatest proportion of it; while others do the opposite allowing their spouses to decide on what is important to buy for the family and how much to spend on education and health of their children. Families have 7 to 8 members in average.

The representative of the ADPP in Cabinda, Mr. José Lelo, informed that women are generally discriminated in their own family and community. Women´s opinion in important matters are often not heard or consulted. Leadership is still male dominant despite the matriarchal marriage custom that is traditionally practiced by the Fiote ethnic group. In matrilineal society, land and land-related resources belong to the woman because the husband follows the wife and settles on the wife´s clan or village. However, in some cases women are replaced by their brothers in key matters. In terms of inheritance, the maternal uncle often inherits the children of his sisters to the detriment of his own children, which have been causing some queries within families.

Families in Maiombe NP greatly depend on forest products like bushmeat and fish as their principal source of protein and income as well. Poverty and unemployment are said to be the main explanation for poaching. The main species hunted for bush-meat are: duikers, bush pig, buffalos, pangolins, guenons, cane rats, snakes, and freshwater fish, among many others species, can be bought along roadsides all the way from Cabinda to Belize. Some locals inform that overtime the number of wild animals has reduced which is lowering the ability of men generating cash to fulfill their family needs.

Many families in Maiombe NP raise goats and sheep which were delivered some years ago by several non-governmental initiatives with the aim of reducing hunting, in particular of endangered species. By doing so, these initiatives tried to give the population alternative sources of income and other sources of animal protein. The national NGO ADPP, for example, under the program “Mulheres em Acção” distributed pigs, ducks, goats and sheep to families in the Municipality of Buco-Zau including support to construct fenced areas for the livestock delivered. Raising ducks mainly have great economic potential due to their fast reproduction, and high market value. Nevertheless, ducks are easily taken by youngsters who can easily sell them for 5.000 AOA each.

Traditional honey collection in Maiombe NP is mainly a subsistence activity and only carried out on a local basis by men. A litre of honey can cost 2500 AOA, which may be a major source of income if sustainable apiculture techniques are employed. According with ADPP, most of the local honey production is still quite destructive and usually involves the cutting or burning of trees and the destruction of the hive. As a result of such, a few years ago, ADPP developed a training program in honey production and processing in Maiombe NP.

Communities acknowledge the enormous potential of the Park for ecotourism, which can generate employment for the residents if well planed. However, the realization of this potential is still limited by the poor infrastructures within Maiombe NP incluindg the lack of skills and abilities of the residents to undertake tourist-related activities.  As a result, the project should include training for tour guides, catering and hospitality mainly for women and youth. Currently, the main road between Cabinda and Belize is in very bad shape, which makes the trip longer and tiring, and places for accommodation and food are still nonexistent.

Informal conversations with residents in Buco-Zau inform that, alongside with the lack of employment, wildlife damages to agriculture mainly caused by elephants and buffalo is the major cause for wildlife hunting. To mitigate the seriou human-wildlife conflict, ADPP in 2015 in partnership with MINAMB invited a human-elephant expert mission from Gabon to Cabinda, to provide training for technicians, and work with selected communities in the forest on HEC mitigation.

4.2.2. Luando Strict Nature Reserve, Luquembo municipality, Malange province

During the PPG field mission, the Commune of Capunda inside the Luando SNR was visited and key stakeholders were interviewed. Around 20,000 inhabitants live in three communes of the Reserve scattered in small villages mainly along the main roads, as follows: Capunda (6,724 people), Quimbango (10,566 people), and Cunga Palanca (2,802 people). The reserve is part of Lukembo municipality, which is a town in the province of Malanje.

Malanje has an area of 98,302 km² and a population of about 986,363; with the majority of those being women (506,575) (INE, 2016). It is essentially an agricultural province, with the following main crops: cassava, rice, cotton, corn, sweet potatoes, peanut, sunflower, beans, soybeans and vegetables. The province is known mainly for having the Black Giant Sable, the Angola's national symbol, in the National Park of Cangandala and Luando SNR.

In the absence of gender disaggregated data, the Administrative authorities inform that women are in higher number than men, which follows the national census picture. This is explained by the long years of war that killed many men. Nowadays, due to the lack of employment, many single and married men migrate to Malange, the capital of the province, and Luanda, looking for a paid work, leaving their wives and children alone for long periods of time.

Capunda commune stays 84 kms away from Quimbango, and 52 kms away from Kunga Palanga, where the biggest remnant Black Giant Sable population can be found. Due to the bad roads and bridges and flooding of the banks of the river, o the communes of Quimbango and Kunga Palanga are accessible only in July-September. Heavy rains occur from September 15 to mid April and make access to the villages inaccessible.

The communities rely on small-scale slash and burn practice agriculture, fishing, non-timber forest products and bushmeat hunting for subsistence. Communities resided in the reserve area before its designation in 1938; however the population has increased following the war with a large number of internally displaced people. Hence, the population is consisted from mixed ethnic groups such as Kimbundu and Songo, according with the Administrators of Capunda, Kunga Palanca and Quimbango villages.

The communities use non-timber forest products such as the locally designated jinguenga (Aframomum alboviolaceum), maboque (Strychnos spinosa), loengo (Anisophyllea gossweileri), and various types of mushroom (tertulhos). Some men in the reserve, especially in the region of Capunda keep honeybees in trees and collect honey for own consumption and for selling. They also sell or barter the surplus of bombó (fermented cassava flour). Nevertheless, selling these products on the markets is quite difficult due to poor road conditions, which become impassible during wet season.

Poaching for bush-meat is by far the most significant threat to biodiversity in Luando SNR to complement both protein and income of the local communities. Subsistence poaching is practiced mostly by male members of the local communities, who are normally not armed and use mainly traditional traps, as well as dogs. Most of the commercial bush-meat poaching is driven by demand in bush-meat markets in Malange and Bie Provinces, as well as by hunters operating on the banks of the Dando River. Families mainly eat cassava, fish, wild boar, and deer that hunters sometimes sell in the commune. This meat and other animals like duck and goats are bought with the money they get from selling cassava.

Schools and health clinics are poorly equipped and suffer from lack of staff. For instances, the commune of Capunda has only 6 teachers, the Commune of Quimbango 10 teachers, while the Commune of Kunga Palanca has 4 teachers. Primary classes are often given under a mango tree to a small number of boys and girls that generally drop out the classes, according to their mothers. Secondary schooling is only available in the Municipality of Luquembo, 102 Kms away, being affordable for a few families only. This explains the high number of people in the communities unable to read and write. Traditional healers (Kimbadeiro) and midwives (Parteiras), use wild medicinal herbs, to heal the community members in the absence of appropriate equipped and staffed health clinics.

Field study for PPG revealed that women in Capunda commune have a heavy workload from early morning (5.00 am) till night (8.00 pm), taking care of household based activities, child care, fuel and water management, animal care and also family crops mainly cassava, rice and sweet potato. During dry season, women practice fishing in the closest river to the village, the Luando River that is about 4 kms from Capunda. Daily water collection and fuel is done primarily by women, but can also be done by men. While women cut the fodder and collect fuel, men take up the work of transporting it home. Men also help women to grow crops. Most men are engaged in hunting, fishing, construction of infrastructures i.e. houses, health post, schools. They sell the surplus fish to traders that come from outside the community.

Analysis of the workload reveals that there are cultural reasons affecting the gender inequality in terms of sharing the household, related workload by men and women. Despite the fact that most of men do not share livelihood activities with women, others do help their wives. This can be explained by the cultural background in Capunda where the dominant ethnic groups i.e. Kimbundos and Songos, follow the patrilineal marriage custom with extended families. In the patrilineal system, the husband and his family (i.e. parents and siblings) have authority and influence regarding family affairs including control over property and resources. The practice of dowry generally results in the loss of many rights for women, as they are expected to be under control of the husbands and follow the rules set for them. Meetings with women in Capunda inform that the sharing of a workload between men and women occurs but still is very uncommon.

Decisions on land-use and related-resources can be jointly made, depending largely on the couple´s religion. Most of married women, whose husbands married others, are left alone to decide upon a household management and livelihood activities, and carry all the workload by themselves. For instance, Mrs. Antónia is the sixth wife of her husband who is a teacher in another province and has 4 children. Her husband comes home once or twice a year to visit his wives and 15 children. She says she is the one who affords everything for her children. Divorce is often avoided and families are brought to the traditional leaders to advice on the best way to move forward. The traditional leaders (Soba) often take a role of counselors to troubled couples.

Under the patrilineal descent system, inheritance of land is traced through father and their blood relatives. As a consequence, men are the owners of the land because it is passed on from generation to generation through male children. In Capunda, women access land and related-resources through their husbands. When women are divorced, they are expected to return to their parents’ home thereby losing rights to the land. When women are widowed, they can be allowed to maintain the ownership of the land together with their children.

The various activities and role of men and women in Luando and Maiombe project areas are summarized as following:

| Activities/ Tasks | Present status | Suggested project interventions |
| --- | --- | --- |
| Firewood management | Firewood collection in rural areas of both project areas is time and energy high consuming. Rural households depend on fuel wood for cooking, lighting and heating purposes. | The project can promote distribution of solar cookers and solar lamps to reduce the dependency on forest for fuel and the workload of women. Their time can then be used in studying and income-generating activities. |
| Water for drinking and Irrigation | In Capunda, women do collect drinking water from the two only available sources. However, these sources are not enough to fulfil their needs. The closest water pipe requires women to wake up at 3 am and stay in the line for hours. Otherwise they have to walk long-distance to other water source. In addition, water arrangements for irrigation such as sprinklers that avoid the need and wastage of water are not very appropriate. In Belize and Buco-Zau municipality, there are appropriate water drinking sources available. However, water arrangements for irrigation should be improved. | The project can provide tanks for water storage (LPDE) and solar water pumps in both project areas. |
| Food Preparation | In both project areas, women and girls take the responsibility of food preparation. Only on social gatherings men can be seen preparing barbeque. As for the diet, cassava is the main ingredient of local food. Share of green vegetables in the local diet is insufficient. Women and girls collect wild mushrooms and wild fruits from forest. | Ecotourism related activities, through home stay or restaurant, is the key activity of the household, and can be promoted through the project where feasible. Men can start sharing with women the workload related to food preparation. The project can introduce new cooking recipes to ensure more nutritious and healthier meals. The project can also introduce techniques for the production of home-made jams from wild fruits i.e. loengo, múcua, including papaya and mango and peanut (butter) which are available seasonally in large amount. The project can also promote sustainable use of medicinal herbs. More active involvement of men in traditional women activities can reduce women’s workload. |
| Non-farm – Fishing and Honey production | Both men and women of Capunda commune in Luando area practice fishing in the surroundings rivers. Women fish in dry season only as it´s safer than in wet season. Fishing, besides providing an important protein source for the household, can generate income. In Luando and Maiombe, honey production is done exclusively by men as it is considered a dangerous activity. Women help to sell the honey, which can have a significant economic potential. | The project can introduce advanced techniques for extracting and producing honey including its commercialization that involves participation of women. It also can promote use of sustainable fishing techniques and fish farms. In addition, the project can introduce effective processing and marketing techniques for fish production and trade. The project can support chicken, duck and pig farming in project communities as an additional source of protein alternative to bushmeat. |
| Work in farm land and post harvesting activities | In both project areas, women and men both equally share the responsibility of field work on the farm land; however tasks are of different nature. Women undertake field development, sowing, and harvesting activities while men do the work of ploughing and taking care of the transport. Selling of the farm products is mainly done by women. In Maiombe NP, women produce basketry for domestic-consumption and trade. | Project can introduce small machineries such as small tractors to reduce the manual work of women and men. It also can promote increase of current agricultural production through eco-friendly techniques to improve soil and crops while introducing new seeds such as onions, garlic, peppers, carrots, lettuce and green vegetables including cereals like beans and lentils for more diversified and nutritious diet. Surplus can be sold at the local markets. Lastly, the project can provide training to women on techniques for extraction, drying and commercialization of mushrooms, and wild fruits including its use in family cooking practice. |

5. Gender Mainstreaming Plan

Although equality between women and men is enshrined in the constitution and the objective of several recent laws and policies, the influence of traditional laws and culture often implies in a certain discrimination against women, including with regard to ownership of property, increasing the social vulnerability of women within society. To improve this situation in the context of the UNDP/GEF project, appropriate gender and social measures have been fully considered in the project design, and gender accountability is a cross-cutting issue that will be tracked as part of the project M&E system.

This GEF project can therefore be classified as Gender targeted (result focused on the number or equity (50/50) of women, men or marginalized populations that were targeted) with strong gender interventions incorporated in the project design. During the project development the PPG team tried to involve as many women as possible in the consultation process. However, overall women’s participation was much lower due to traditional male dominance in anti-poaching, wildlife and environmental management issues at the national level in the project sites. Overall, from the 155 stakeholders consulted during the project development from those  25% were women.

To implement gender mainstreaming, the project will develop and implement an effective Gender Mainstreaming Strategy (Output 4.3). The strategy will guide the project implementation to build project partner capacity to mainstream gender and bring along strategies that empower women as agents rather than as victims of wildlife depletion, habitat degradation, and climate change. This strategy will also facilitate a multi-stakeholder analysis of the gender issues with a clear set of measurable gender indicators.

The key guidelines for the strategy are outlined below:

- Gender balance will be ensured as much as possible regarding women participation in the Project Board and in the PMU. Project interventions will seek a greater and more even gender representation with the potential for gender mainstreaming-related activities at the national level and in the project areas - Maiombe NP and Luando SNR. Furthermore, relevant gender representation will be pursued in the project mangement. All project staff recruitment shall be specifically undertaken inviting and encouraging women applicants. The TORs for key project staff all incorporate gender mainstreaming related responsibilities.

- In response to the relatively low participation of women in the project development, the project will incorporate gender considerations in the implementation procedures in a number of different ways:

  - Empower women by involving them in policy and legislation review, management planning processes to combat wildlife crime and manage wildlife, including capacity building activities and law enforcement of wildlife crime under Components 1 and 2;

  - Strong focus on rural communities and gender within Components 3 and 4 with an emphasis on involving women in development and implementation of pilot projects on CBWM, CBNRM, HWC management; development and alternative sources of income and value-chains for local communities in the project areas that have an emphasis on female-led activities (e.g. collection of fuelwoods and/or NTF products);

  - All awareness raising activities will specifically target women and encourage them to take responsibilities including for engagement with the authorities with respect to natural resource management, illegal killing and trading of wildlife products and live animals;

  - Women’s organisations (associations and clubs) will be involved in project implementation and capacity development at national, provincial and communal levels.

- The project will adopt the following principles in the day to day management: (i) gender stereotypes will not be perpetuated; (i) women and other vulnerable groups will be actively and demonstrably included in project activities and management whenever possible, and (iii) derogatory language or behaviour will not be tolerated.

- The project will promote gender mainstreaming and capacity building within its project staff to improve understanding of gender issues, and will appoint a designated focal point for gender issues to support development, implementation, monitoring and strategy on gender mainstreaming internally and externally. This will include facilitating gender equality in capacity development and women’s empowerment and participation in the project activities. The project will also work with UNDP experts in gender issues in Luanda to utilize their expertise in gender mainstreaming. These requirements will be monitored by the UNDP Gender Focal Point during project implementation.

- The project will use gender-disaggregated indicators in the PRF for regular monitoring and evaluation of the project progress and reporting, and will facilitate involvement of women in the M&E and Grievance Redress Mechanism implementation.

The project gender mainstreaming approach includes the following key steps with gender consideration reflected in the whole project cycle:

Activity 1: Gender Analysis and Action Planning: (Encompasses Project Identification and design and planning). This entails developing an Action Plan for Mainstreaming Gender so as to engage different stakeholders and implementing partners identify the impact of gendered impact of climate change and adaptation strategies. In addition this will also help to identify the gendered impacts of all planned project activities. This also includes reviewing policy issues and assessing if there is a budget line that supports the participation of women.

Activity 2: Gender Mainstreaming Capacity Building in Implementing Partners, Stakeholder and the Community: Strengthen institutional capacity for mainstreaming gender in all implementing partners, key stakeholders and the beneficiary communities using gender GEF/UNDP mainstreaming frameworks and tools. This will include putting the project plan into action and making sure that the resources and benefits are not controlled by men, assessing the recruitment and staffing levels and overall coordination of the various project components.

Activity 3: Evaluation and Monitoring: This will include developing tools for measuring impact and using the evidence to generate policy relevant information, decide on what indicators can be used to measure progress in achieving the project goals, providing feedback to communities in a timely manner, develop impact stories and training manuals.

Proposed project specific gender mainstreaming activities are summarized in the Table below:

Table: Proposed gender mainstreaming actions for project implementation

| Project Outputs | Responsible organizations | Gender Mainstreaming Actions |
| --- | --- | --- |
| Component 1. Strengthening the policy, legal and institutional framework and national capacity to manage wildlife, including HWC, and address wildlife crime |  |  |
| Output 1.1. National policy and regulatory framework for IWT control and wildlife management is reviewed and updated | MINAMB, ECU, INBAC, Interministerial Commission on Wildlife Crime, Attorney General’s Office, CITES Secretariat, MINAGRIF, IDF, Stop Ivory, Wildlife Impact, ICCF Group, 51 Degrees, and IELP. | - Active outreach to women and women’s groups to participate in the review and update of the policy and legislation documents; Promotion of potential involvement of women in the law enforcement staff of the INBAC and ECU at national and provincial levels. |
| Output 1.2. National ECU and other wildlife law enforcement agencies are provided with trainings, manuals, and equipment to effectively enforce, prosecute, and penalize wildlife crime. | ECU, INBAC, Inter-ministerial Commission on Wildlife Crime, Attorney General’s Office, CITES Secretariat, National Directorate for Biodiversity, IDF, Police, Customs, Judiciary, Stop Ivory, Wildlife Impact, Space for Giants, ICCF. | Ensure participation of at least 25% of women in the various law enforcement training sessions organized by the project; Promotion of potential involvement of women in the law enforcement staff of the INBAC and ECU at national and provincial levels; Target 50/50 training recruitment policy to all types of trainings for LE agencies, prosecutors, and judiciary. |
| Output 1.3. The Environmental Polytechnic Institute (Wildlife School) in Menongue has comprehensive national training programmes for PA rangers and provides necessary training for the PA staff. | MEWC Menongue Wildlife School, INBAC, Stop Ivory, 51 Degrees, South Africa Wildlife College, KWS Training Centers, wildlife ranger training centers in Namibia and Gabon, ZPWMA. | Ensure participation of 50% of women in the various training programmes for PA rangers and PA Staff. |
| Component 2. Strengthening capacity of selected PAs and law enforcement agencies in the target areas to control poaching, IWT, HWC, and habitat degradation |  |  |
| Output 2.1. Two inter-agency Environmental Crime Units are established in the project areas and provided with comprehensive anti-poaching trainings, equipment, and initial operational support | National ECU, INBAC, Maiombe NP and Luando SNR, National Police, IDF, Presidential Programme for Conservation and Restoration of the Black Giant Sable, Kissama Foundation, 51 Degrees. | Active involvement of women in the PA management plan development and realization process, including PA-Community Councils; Target 50/50 participation of women in capacity building trainings for the Maiombe NP and Luando SNR staff. Trainings and awareness of gender-sensitivities and monitored to ensure appropriate behavior/professional conduct towards women (as well as other community members) |
| Output 2.2. Comprehensive and participatory Management Plans for the PAs in the project areas are developed/updated and implemented | INBAC, Presidential Programme for Conservation and Restoration of the Black Giant Sable, Maiombe NP and Luando SNR, Kissama Foundation, 51 Degrees, Local government and communities. | Ensure Gender sensitive resource management committees of target communities; Include women in the management planning for Maiombe MP and Luando SNR; Establish 50/50 participation of women on-the-site trainings for PA managers and rangers as additional to those provided at the Wildlife School in Menongue (under Output 1.3); Develop fair rules for distribution of benefits to women and vulnerable groups in both project areas. |
| Component 3. Engaging local communities in sustainable wildlife, forest and PA management |  |  |
| Output 3.1. Pilot projects on CBWM, CBNRM, HWC and alternative sources of income for local communities in the project areas are developed and implemented | Maiombe NP and Luando SNR, selected local communities, IDA, FAO, AfDB, ADPP, FAS, Gremio ABC, Administrations of Cabinda and Malanje Provinces. | Ensure effective participation of women in natural resource management groups and PA-Community Councils in the target PAs; Through 50/50 policy for training, provide women friendly training facilities to increase their capacity in CBNRM, CBWM, SFM, SLM, and HWC management and alternative income livelihoods in the project areas; Active involvement of women in the planning and implementation of pilot projects on CBWM, CBNRM, HWC, and activities that foster alternative livelihood income sources and value-chains for local communities in the project areas; Develop fair rules for distribution of the project community based initiatives benefits to women and marginalized groups in the target communities; Increase the focus of interventions on female-headed households as beneficiaries of the projects. |
| Output 3.2. Public awareness campaign targeting IWT, bushmeat consumption, HWC and habitat degradation is developed and implemented in the project areas. | Target local communities, INBAC, Maiombe NP and Luando SNR, ADPP, JEA, Gremio ABC, National TV channels, Kissama Foundation. | Target active involvement of women in design and implementation of pilot projects. Increase the focus of interventions on femaleNatheaded households as beneficiaries of projects. Promote fare distribution of benefits from CBWM, SFM and SLM with significant share to women. |
| Component 4. Knowledge Management, M&E and Gender Mainstreaming |  |  |
| Output 4.1. Participatory project monitoring, evaluation and learning framework is developed and implemented | INBAC, WCS, Kissama Foundation, all other partners. | Apply gender specific analysis in the project M&E; Active involvement of women in the project M&E processes. |
| Output 4.2. Lessons learned from the project are shared with national and international conservation programmes, including GWP | INBAC, target PAs, National media channels, Environmental Crime Unit, Interministerial Commission on Wildlife Crime, other law enforcement agencies, local communities, NGOs. | Incorporate gender issues in the process of lessons learning; Involve women and women organizations in generation gender lessons. |
| Output 4.3. Gender strategy developed and used to guide project implementation, monitoring and reporting | INBAC, target PAs, other law enforcement agencies, local communities, NGOs. | Develop and implement project gender strategy; Adopt measures that ensure gender sensitive planning and budgeting; Track gender disaggregated data for M&E; Consider gender related reporting in KM and Lessons Learnt reports. |
| Project Management | PMU | Ensure that both men and women are visible and inclusive in the project documents; Collect gender-sensitive data (age, ethnicity, income, education) for reporting and planning; Apply gender clause to human resource recruitment, encouraging the applications from women candidates and their hiring; At inception: gender screening of the project design and workplan; TORs of all staff to include specific responsibilities that support mainstreaming of gender throughout project implementation. |

## Annex J.  UNDP Risk Log

| # | Description | Date Identified | Type | Impact & Probability | Counter-measures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Low capacity for effective project management may result in implementation delays and incomplete achievement of project Outcomes | June 23 2018 | Operational | I= 4 P=5 HIGH | The risk is only partly under project control. Implementation of the GEF project portfolio in Angola suffers chronically from ineffective management: almost all of the projects have significant delays and often do not achieve all planned outcomes. To mitigate this risk the project will support Results-Based Management training for the PMU and Implementing Partner (MINAMB/ INBAC) at the project inception phase and an international technical advisor will be hired to assist the PMU on technical benchmarking and deliverables. The project will in addition involve experienced project partners and international consultants to support effective delivery of the selected project outputs. For example, SESP risks and gender mainstreaming in the project areas will be regularly monitored by selected project partner (organization) for Output 3.1 (community livelihood initiatives) based on ESMP developed at the project Inception Phase. | PMU, INBAC | PPG Team and UNDP CO | October 20 2018 | Currently the risk is high, but can decrease after the project start |
| 2 | Insufficient national and local capacity for effective and complete delivery of project Outputs | June 23 2018 | Operational | I= 4 P=4 HIGH | The risk is only partly under project control. Despite high political commitment of the Angolan government to fight wildlife crime, capacity of the key law enforcement agencies (e.g., ECU and INBAC) remains low (agencies are understaffed, level of skills and knowledge is insufficient, necessary equipment is lacking), and inter-institutional cooperation is rudimentary. At the same time local communities in the project areas have low capacity for sustainable natural resource management and almost full lack of relevant experience. However, under all three key project components (1-3) the project will invest considerable resources in capacity building of the law enforcement agencies, PAs, and local communities to plan, manage and monitor wildlife crime, and implement sustainable NRM. The project will involve a wide range of experienced international partners and consultants in the project implementation that have significant capacity to ensure delivery of the project outputs in time and with high quality. | PMU, INBAC | PPG Team and UNDP CO | October 20 2018 | Currently the risk is high, but can decrease after the project start |
| 3 | Insufficient sustainability of the project Outcomes due to lack of ownership and continuing financial support after project completion | June 23 2018 | Operational, Financial | I= 4 P=3 HIGH | The risk is only partly under project control. The Outputs suggested by the project need high level of ownership from the relevant stakeholders and financial support to ensure their sustainability and effectiveness in the nearest 5-10 years after the project is over. Current government support to the PAs and law enforcement agencies remains low, which puts the project Outcomes at risk of loss. To increase the sustainability of the project results, considerable funds will be invested in the development of the inter-agency cooperation and co-financing mechanisms (Output 2.1), identification and leveraging of additional sources of funding from the government and international partners (Output 1.1, 2.1 and 2.2), establishment of partnerships with international donors and private sector (Outputs 1.2, 1.3, 2.2 and 3.1), and identification of effective markets for the community-based products and services (Output 3.1). | PMU, MINAMB | PPG Team and UNDP CO | October 20 2018 | Currently the risk is high, but can decrease after the project start |
| 4 | Mal-governance and associated corruption at national and regional levels including in the wildlife crime enforcement | June 23 2018 | Operational | I=3 P=4 MODERATE | The risk is only partly under project control. Addressing corruption requires considerable high-level political support and commitment. Reducing its impact requires action against corruptors, but can also be addressed through tighter regulatory structures and effective project monitoring and evaluation that highlight when inappropriate action is being taken. Overall project design is made to address corruption and other forms of mal-practice and mal-governance in wildlife crime control. For example, strengthening the regulatory framework and government capacity to fight IWT will enhance oversight and limit opportunities for such a malpractice. However, strict M&E and project oversight will be essential for the use of the project funds and equipment, including vehicles. Presence of other internationally funded high-profile projects will further stimulate the government’s efforts to fight corruption and malpractice in the project implementation | Project Board, UNDP CO | PPG Team and UNDP CO | October 20 2018 | Currently risk level is stable. |
| 5 | Unwillingness of the government agencies to cooperate can lead to ineffective implementation of the wildlife crime enforcement | June 23 2018 | Political | I=3 P=3 MODERATE | The risk is only partly under project control. Considerable intersection of responsibilities often results in the inter-agency conflicts in Angola that impede the organizations’ ability to cooperate in law enforcement. The project is designed to increase the level of interagency cooperation in the country via mutually beneficial partnerships of different agencies (Outputs 2.1 and 2.2). These measures will decrease the probability of the risk. | PMU, Project Board | PPG Team and UNDP CO | October 20 2018 | Currently risk level is stable, but may decrease during the project implementation. |
| 6 | Combined effect of the low population growth rate and vulnerability to diseases may lead to decline of the gorilla and chimpanzee population in the Maiombe NP despite conservation efforts of the project | June 23 2018 | Environmental | I= 5 P=3 MODERATE | The risk is not under project control. However, the project can increase ape survival rates via decrease of poaching and habitat degradation rates in the Maiombe NP through capacity building and support of the law enforcement staff, support of anti-poaching activities, and improved management of the PA (Outputs 2.1, and 2.2). Component 3 is fully designed to increase capacity of local communities to co-exist with apes and forest elephants on sustainable basis and share of common natural resources, which will also contribute to higher survival rate of the species. | PMU, MINAMB | PPG Team and UNDP CO | October 20 2018 | Currently the risk is moderate but can slightly decrease after the start of the project |
| 7 | Benefits provided by the project to local communities may be insufficient to draw them from poaching, illegal wildlife trade and other illegal activities | June 23 2018 | Social | I=4 P=3 HIGH | The risk is only partly under project control due to limited funding. Currently a significant number of local populations in the project areas are involved in illegal bushmeat hunting and trade, illegal logging, burning of the woodlands and other unsustainable activities (see also Annex G. UNDP Social and Environmental and Social Screening Template (SESP)). The project can decrease the risk partly via implementation of the Outputs 2.2, 3.1 and 3.2 (sustainable livelihood of the local communities and community participation in the PA management) and partly via increased level of law enforcement (under Outputs 2.1 and 2.2) that will allow much less opportunities for illegal practices. At the same time, the project will identify economically and socially feasible ways to involve local communities in conservation and CBNRM as well as effective markets for community-based products, and will build effective partnerships with international donors and private sector in the project areas to ensure higher sustainability and local ownership of the Output 3.1. To mitigate the risk the project investment in the local communities is quite high ($1,075,000, or 26% of the GEF grant), however, the total area of the investment is limited to 20,000 ha only ($54/ha of the most important poaching hotspots in the project areas) to achieve high impact. The project will develop a Local Livelihood Plans in framework of the Output 3.1 to guide the project actions to mitigate the risks associated with increased law enforcement activities in two project areas – Luando SNR and Maiombe NP. However, there are no indigenous people in the project areas, therefore the project will not affect their rights and livelihood in any way | PMU, INBAC | PPG Team and UNDP CO | October 20 2018 | Currently the risk is high but can slightly decrease after the start of the project |

## Annex K. HACT micro assessment of the Implementing Partner (MINAMB/INBAC)

See file PIMS 5993 Angola GEF6 ANNEX K - HACT micro assessment of the IP.pdf

## Annex L. Deleted

## Annex L1. Indicative Procurement Plan for the project

This needs to be updated at project inception

The National Implementing Agency shall update the procurement plan throughout the duration of the project at least annually by including contracts previously awarded. All procurement plans, their updates or modifications shall be published on the website of the National Implementation Agency.

General Information

| Project Name: Combating illegal wildlife trade and human wildlife conflict in Angola |  |
| --- | --- |
| Country: Angola | Implementing Partner: Ministry of Environment of the Republic of Angola |
| Date of First Procurement: 3rd Quarter 2019 | Date of this Procurement Plan: November 2018 |

Process Thresholds, Review and Procurement Plan

1. Project Procurement Thresholds

The following UNDP procurement thresholds shall apply to procurement of goods and works:

2. Prior or Post Review

The following UNDP prior or post review requirements apply to the various procurement and consultant recruitment methods used for the project.

|  |  | Level 1 (Country Level): Contracts, Assets and Procurement Committee | Level 2 (Regional): Regional Advisory Committee on Procurement (country offices only) | Level 3 (HQ): Advisory Committee on Procurement |
| --- | --- | --- | --- | --- |
| Competitive procurement process |  |  |  |  |
| Any contract or series of contracts including amendments to be awarded to a vendor in a calendar year that in aggregate has a cumulative value: |  | Above US $50,000 (above US $100,000 for Individual Contracts) and up to the standard delegated procurement authority – Direct Review by CAP Chairperson Above the standard delegated procurement authority and up to any increased delegated procurement authority – by CAP Committee | Above the delegated procurement authority and up to US $2 million (applies per year for Long-Term Agreements) | Country offices: above US $2 million (applies per year for Long-Term Agreements) |
| Direct contracting |  |  |  |  |
| Any contract or series of contracts, including amendments to be awarded to a vendor in a calendar year that in aggregate has a cumulative value: |  | Above US $50,000 and up to 50 percent of the standard delegated procurement authority – Direct Review by CAP Chairperson Above 50 percent of the standard delegated procurement authority and up to 50 percent of any increased delegated procurement authority – by CAP Committee | Above 50 percent of the delegated procurement authority and up to US $2 million (applies per year for long-term agreements) | Headquarters units: above 50 percent of the delegated procurement authority Country offices: above US $2 million (applies per year for long-term agreements) |
| Amendment of all contracts |  |  |  |  |
| Any amendment or series of amendments to a contract which, in aggregate, increases the contract value by 20 percent or the delegated procurement authority, whichever is less: |  | Above US $50,000 and up to the standard delegated procurement authority – Direct Review by CAP Chairperson. Above the standard delegated procurement authority and up to the increased delegated procurement authority - by CAP Committee | Above the delegated procurement authority and up to US $2 million (applies per year for long-term agreements) | Country offices: above US $2 million (applies per year for long-term agreements) |
| Ex ante review |  |  |  |  |
| Ex ante review refers to the review of the procurement strategy roadmap prior to commencement of the procurement process for complex procurement actions with a value: |  | N/A | Above US $1 million and up to US $2 million (applies per year for long-term agreements) | Above US $2 million (applies per year for long- term agreements) |
| Notes: | - The procurement support unit shall participate when requested in the committee review of ex ante submissions. - An ex ante review is not required if: - The business unit has had a previous successful experience in the procurement of similar goods/services/works that was already subject to an ex ante review; or - There is sufficient specific corporate guidance and templates on the procurement of the said goods/services. - Irrespective of the above, the procurement authority may submit the cases for ex ante review if significant risks are perceived. |  |  |  |

Table 1: Expected Goods and Non-Consulting Services under the GEF project “Combating illegal wildlife trade and human wildlife conflict in Angola”

| No | General Description | Contract Value USD (cumulative) | Procurement Method | Procurement By | No of Contracts | Advertisement Date (quarter/year) | Implementation Start date (quarter/year) | Prior or Post review |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 3 Toyota Pickups for the national Environmental Crime Unit (1) and Maiombe NP (1) and Luando SNR (1) | 120,000 | Request for Quotation | UNDP | 1 | Q1/2020 | Q2/2020 | Post |
| 2 | Radios, cameras, computers, software, investigation equipment for the national Environmental Crime Unit | 15,000 | Request for Quotation | UNDP | 2 | Q1/2020 | Q2/2020 | Post |
| 3 | Training equipment for the Wildlife School in Menongue on the Years 1-2 | 80,000 | Request for Quotation | MINAMB | 2 | Q1/2020 | Q2/2020 | Post |
| 4 | Special equipment for the inter-agency cooperation of border agencies in Cabinda Province on Year 2 | 10,000 | Request for Quotation | MINAMB | 1 | Q3/2020 | Q4/2020 | Post |
| 5 | Deleted |  |  |  |  |  |  |  |
| 6 | Field equipment for the officers of local ECUs in the Maiombe NP and Luando SNR | 20,000 | Request for Quotation | MINAMB | 1 | Q2/2021 | Q3/2021 | Post |
| 7 | Deleted |  |  |  |  |  |  |  |
| 8 | Field equipment for rangers, fire management equipment, communication equipment | 350,000 | Invitation to bid advertised in national media | MINAMB | 3 | Q4/2020 | Q1/2021 | Post |
| 9 | Publication of the project materials, including lessons learned | 13,000 | Request for Quotation | MINAMB | 2 | Q3/2022 | Q4/2022 | Post |
| 10 | PMU office supplies, paper, cartridges and other consumables | 12,000 | Request for Quotation | MINAMB | 1 | Q4/2019 | Q1/2020 | Post |

Table 2: Expected Works Contracts under the GEF project “Combating illegal wildlife trade and human wildlife conflict in Angola”

| No | General Description | Contract Value USD (cumulative) | Procurement Method | Procurement By | No of Contracts | Advertisement Date (quarter/year) | Implementation Start date (quarter/year) | Comments | Prior or Post review |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Contract to develop a National Wildlife Crime Law Enforcement Strategy and update selected legislation on Years 1 and 2 | 100,000 | Direct contracting | MINAMB | 1 | Q1/2020 | Q2/2020 | International | Post |
| 2 | Contract to provide training and mentoring programme on wildlife crime investigation, intelligence, forensics, etc., to the national Environmental Crime Unit on Years 1-3 | 150,000 | Direct contracting | MINAMB | 1 | Q1/2020 | Q2/2020 | International | Post |
| 3 | Contract to provide training to the law enforcement agencies to investigate, prosecute, and penalize wildlife crime on Years 1-3 | 150,000 | Direct contracting | MINAMB | 1 | Q1/2020 | Q2/2020 | International | Post |
| 4 | Contract to develop mandatory training programmes for the Wildlife School in Menongue, train the school instructors, and provide mandatory trainings to PA rangers on Years 1-5 | 10,000 | Direct contracting | MINAMB | 1 | Q1/2020 | Q2/2020 | International | Post |
| 5 | Contract to provide training and mentoring to the border agencies staff in Cabinda province on Years 1-5 | 130,000 | Direct contracting | MINAMB | 1 | Q1/2020 | Q2/2020 | International | Post |
| 6 | Organization of meetings with stakeholders to discuss and facilitate approval of developed National Wildlife Crime Law Enforcement Strategy, updated wildlife crime legislation and other legal documents | 20,000 | Request for quotation | MINAMB | 3 | Q2/2020 | Q3/2020 | National | Post |
| 7 | Organization of working meetings for Angola and Congo Governments to develop a protocol on the wildlife crime law enforcement cooperation and establishment of the BLO on the Years 1 and 2 | 20,000 | Request for quotation | MINAMB | 3 | Q2/2020 | Q3/2020 | National | Post |
| 8 | Contract(s) with selected project partner(s) (organization) to develop/update the RBM Management Plans for Maiombe NP and Luando SNR on the Years 1-2 | 110,000 | Invitation to bid Advertised in national media | MINAMB | 2 | Q2/2020 | Q3/2020 | International | Post |
| 9 | Contract(s) with selected project partner(s) (organization) to provide on-the-site trainings/refreshers for the Maiombe NP and Luando SNR management and ranger staff on the Years 1-4 | 120,000 | Direct contracting | MINAMB | 1 | Q2/2020 | Q3/2020 | International | Post |
| 10 | Contract(s) with selected project partner(s) (organization) to design and implement elephant, gorilla, and chimpanzee population transect surveys in the Maiombe NP and to design and implement black giant sable camera-trapping surveys in the Luando SNR | 320,000 | Invitation to bid Advertised in national media | MINAMB | 4 | Q4/2019 | Q1/2020 | International | Post |
| 11 | Construction of base camp in Luando SNR and two ranger posts in Maiombe NP | 150,000 | Invitation to bid Advertised in national media | MINAMB | 1 | Q1/2021 | Q2/2021 | National | Post |
| 12 | Travel expenses including fuel and rations for initial operations of the local ECUs in in the Maiombe NP and Luando SNR on the Years 2-4 | 30,000 | Request for quotation | MINAMB | 2 | Q1/2021 | Q2/2021 | National | Post |
| 13 | Travel expenses including fuel and rations for initial anti-poaching operations of the Maiombe NP and Luando SNR rangers on the Years 1-5 | 82,000 | Request for quotation | MINAMB | 2 | Q2/2020 | Q3/2020 | National | Post |
| 14 | Contract(s) with selected project partner(s) (organization) to conduct feasibility assessment for different forms of community-based conservation and involvement of local communities in the PA and NR management, provide trainings to selected local communities on selected forms of sustainable livelihoods, assist local communities to develop pilot projects on community-based conservation and sustainable NR management in the Maiombe NP and Luando SNR on the Years 1-6 | 230,000 | Invitation to bid Advertised in national media | MINAMB | 2 | Q2/2020 | Q3/2020 | National | Post |
| 15 | Travel expenses for the project team to monitor PRF and SESP indicators, stakeholder involvement, and GRM (Output 4.1) | 46,962 | Request for quotation | UNDP | 1 | Q3/2019 | Q4/2019 | National | Post |
| 16 | Travel expenses for the project team and partners to participate in the national and international meetings, seminars and conferences to exchange experience (Output 4.2) | 48,000 | Request for quotation | UNDP | 1 | Q3/2019 | Q4/2019 | National | Post |
| 17 | Travel expenses for the project team to monitor implementation of the gender mainstreaming strategy (Output 4.3) | 24,000 | Request for quotation | UNDP | 1 | Q3/2019 | Q4/2019 | National | Post |
| 18 | Annual audit of the project implementation (Output 4.1) | 18,000 | Request for quotation | UNDP | 1 | Q3/2020 | Q4/2020 | International | Post |
| 19 | Organization of the Inception workshop (Output 4.1) | 10,000 | Request for quotation | UNDP | 6 | Q3/2019 | Q4/2019 | National | Post |
| 20 | Project Board meetings once a year (Output 4.1): | 30,000 | Request for quotation | UNDP | 6 | Q1/2020 | Q2/2020 | National | Post |
| 21 | Meetings, seminars, and workshops for the project team and partners to exchange experience and extract lessons learned, including ICCWC IF workshops on the Year 3 and 6 (Output 4.2) | 20,000 | Request for quotation | UNDP | 10 | Q2/2020 | Q3/2020 | National | Post |
| 22 | Additional travel expenses for the PMU for Years 1-6 | 12,419 | Micro-purchasing | MINAMB | 1 | Q1/2020 | Q2/2020 | National | Post |

Table 3: Expected Consultancy Services under the GEF project “Combating illegal wildlife trade and human-wildlife conflict in Angola”

| No | General Description | Contract Value USD (cumulative) | Procurement Method | Procurement By | No of Contracts | Advertisement Date (quarter/year) | Implementation Start date (quarter/year) | Comments | Prior or Post review |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | National Consultant to develop inter-agency protocols, ToRs, and SOPs for establishment and functioning of local ECU in Maiombe NP and Luando SNR on the Year 1 | 10,000 | Advertisement in national media | MINAMB | 1 | Q4/2019 | Q1/2020 | National | Post |
| 2 | International Consultant (Technical Advisor) to support PMU on technical planning and benchmarking, deliverables, capacity development, monitoring and evaluation, including ICCWC IF assessments on the Years 3 and 6 | 210,000 | Advertisement in international media | MINAMB | 1 | Q2/2021 | Q3/2021 | International | Post |
| 3 | National Consultant to design national and project area levels awareness campaign on negative impact of wildlife crime and bushmeat consumption in Angola on the Year 1 | 10,000 | Advertisement in national media | MINAMB | 1 | Q3/2019 | Q4/2019 | National | Post |
| 4 | International Consultant for the MTR on Year 3 (Output 4.1) | 25,000 | Advertisement in international media | UNDP | 1 | Q3/2021 | Q4/2021 | International | Post |
| 5 | International Consultant for the TE on Year 6 (Output 4.1) | 25,000 | Advertisement in international media | UNDP | 1 | Q3/2024 | Q4/2024 | International | Post |
| 6 | National Consultant (Project Coordinator) | 198,000 | Advertisement in national media | MINAMB | 1 | Q3/2019 | Q4/2019 | National | Post |
| 6b | National Consultant (Project Finance and Procurement Officer) | 171,000 | Advertisement in national media | MINAMB | 1 | Q3/2019 | Q4/2019 | National | Post |
| 7 | National Consultant (Project Technical and Administrative Assistant) | 99,000 | Advertisement in national media | MINAMB | 1 | Q3/2019 | Q4/2019 | National | Post |
| 8 | National Consultant (Project Driver) | 64,419 | Advertisement in national media | MINAMB | 1 | Q3/2019 | Q4/2019 | National | Post |
| 9 | Local consultant costs for development of best practice notes | 15,000 | Advertisement in national media | MINAMB | 1 | Q1/2022 | Q2/2022 | National | Post |
| 10 | National Consultant for the TE on the Year 6 (Output 4.1) | 10,000 | Advertisement in national media | MINAMB | 1 | Q3/2024 | Q4/2024 | National | Post |
| 11 | National Consultant to develop and support the project web-site on the Years 1-6 | 15,000 | Advertisement in national media | UNDP | 1 | Q1/2020 | Q2/2020 | National | Post |
| 12 | National Consultant to develop the project Gender Mainstreaming Strategy on the Year 1 | 5,000 | Advertisement in national media | UNDP | 1 | Q1/2020 | Q2/2020 | National | Post |

## Annex M. Project Co-Financing Letters

## Annex N. OFP GEF Letter

## Annex O. UNDP Project Quality Assurance Report

See file PIMS 5993 Angola GEF6 ANNEX O - Quality Assurance Report.pdf

## Annex P. Landscape Profile Report

See file PIMS 5993 Angola GEF6 ANNEX P - Landscape Profile Report.pdf

## Annex Q. Capacity Assessment Scorecard for a Wildlife Crime Law Enforcement Agency – National Institute for Biodiversity and Protected Areas (INBAC), Angola

Project/Programme Name: UNDP/GEF Project “Combating Illegal Wildlife Trade and Human Wildlife Conflict in Angola”

Project/Programme Cycle Phase: PPG. Date of assessment: July 2018.

Participants of the assessment: Aristofanes Pontes, Director General; Vanessa Falkowsky, UNDP CO; Mikhail Paltsyn, Team Leader and Wildlife Crime Expert

Table 1. UNDP Capacity Assessment Scorecard Summary

| Strategic Areas of Support | Systemic |  |  | Institutional |  |  | Individual |  |  | Average % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Project Scores | Total possible score | % achieved | Project Scores | Total possible score | % achieved | Project Scores | Total possible score | % achieved |  |
| (1) Capacity to conceptualize and formulate policies, legislations, strategies and programs | 3 | 6 | 50% | 0 | 3 | 0% | n/a | n/a | n/a | 25% |
| (2) Capacity to implement policies, legislation, strategies and programs | 3 | 6 | 50% | 7 | 18 | 39% | 2 | 6 | 33% | 41% |
| (3) Capacity to engage and build consensus among all stakeholders | 2 | 6 | 33% | 3 | 6 | 50% | 2 | 3 | 67% | 50% |
| (4) Capacity to mobilize information and knowledge | 1 | 3 | 33% | n/a | n/a | n/a | 2 | 3 | 67% | 50% |
| (5) Capacity to monitor, evaluate, report and learn | 2 | 6 | 33% | 2 | 6 | 33% | 1 | 3 | 33% | 33% |
| TOTAL Score and average for %'s | 11 | 27 | 41% | 12 | 33 | 36% | 7 | 15 | 47% | 41% |

Table 2. Detailed Results from the Capacity Assessment Scorecard

| Strategic Area of Capacity | Outcomes | Outcome Indicators (Scorecard) | Initial Evaluation | Evaluative Comments |
| --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, legislations, strategies and programs |  |  |  |  |
| Systemic | The national agenda to combat poaching and IWT is being effectively championed / driven forward. | 0 -- There is essentially no agenda on combating poaching and IWT; 1 -- There are some persons or institutions actively pursuing anti-poaching agenda but they have little effect or influence; 2 -- There are a number of persons and institutions that drive the anti-poaching agenda, but more is needed; 3 -- There are an adequate number of able "champions" and "leaders" effectively driving forwards anti-poaching and IWT agenda | 2 | Angola has high government commitments and political agenda to combat wildlife crime. In 2013 Angola signed and ratified CITES and became the 179th party of the Convention. In 2015 Angola developed the National Ivory Action Plan (NIAP) 2015-2016 in response to the request of the 65th meeting of the CITES Standing Committee held in Geneva in July 2014. To support national implementation of CITES the country developed the Executive Decree No. 469/15 prohibiting hunting activity and logging within the country’s Protected Areas. In the framework of the NIAP the country closed its open domestic ivory market in 2016, adopted the Law No. 6/17 on Forest and Wildlife , drafted a new PA Law based on revision of colonial Decree No. 40.040/1955, started update of the Criminal Code to harmonize it with environmental legislation, conducted inventories of national ivory stockpiles for 1,244,000 kg of unworked and worked ivory, and established the Environmental Crime Unit and Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora. The National Institution for Biodiversity and Conservation Areas (INBAC) has been established in 2011 as the key government agency under the Ministry of Environment responsible for management of protected areas and conservation of endangered species. Other actors in Angola involved in wildlife crime law enforcement are Environmental Crime Unit, IDF, National Police, Customs and Military. The agencies need stronger collaboration and joint efforts to combat wildlife crime effectively. |
| Systemic | There is a strong and clear legal mandate for combating poaching and IWT. | 0 -- There is no legal framework to support efforts aimed at combating poaching and IWT; 1 -- There is a partial legal framework supporting efforts aimed at combating poaching and IWT, but it has many inadequacies; 2 – There is a reasonable legal framework supporting efforts aimed at combating poaching and IWT but it has a few weaknesses and gaps; 3 -- There is a strong and clear legal mandate supporting efforts aimed at combating poaching and IWT; | 1 | Current mandate of the INBAC to combat wildlife crime involves biodiversity conservation and Protected Areas management. Given that current punishment for wildlife crime in the country does not exceed 3 years in prison and that the penalties are mainly financial in nature, the wildlife crime does not fall within the definition of “serious crime” under the United Nations’ Office for Drugs and Crime, Organized Crime Convention. No specific guidelines for prosecuting wildlife related crimes developed for the country’s prosecutors and judiciary. |
| Institutional | Institutions responsible for combating poaching and IWT are able to strategize and plan. | 0 -- Institutions responsible for combating poaching and IWT have no plans or strategies; 1 -- Institutions responsible for combating poaching have strategies and plans, but these are old and no longer up to date or were prepared in a totally top-down fashion; 2 -- Institutions responsible for combating poaching and IWT have some sort of mechanism to update their strategies and plans, but this is irregular or is done in a largely top-down fashion without proper consultation; 3 – Institutions responsible for combating poaching and IWT have strategies and plans which are relevant, prepared in a participatory manner and regularly updated | 0 | Currently INBAC does not have any strategy or institutional plans to combat wildlife crime. |
| 2. Capacity to implement policies, legislation, strategies and programs |  |  |  |  |
| Systemic | There are adequate skills for combating poaching and IWT. | 0 -- There is a general lack of skills for combating poaching and IWT; 1-- Some skills exist but in largely insufficient quantities to guarantee effective anti-poaching and prevention of IWT; 2 -- Necessary skills for effective anti-poaching and prevention of IWT do exist but are stretched and not easily available; 3 -- Adequate quantities of the full range of skills necessary for effective anti-poaching and prevention of IWT are easily available | 1 | Currently INBAC has 15 inspectors responsible for combating wildlife crime based in Luanda and 350 rangers in the country’s Protected Areas. This number is very far from enough (less than 20% of number inspectors needed) staff required to fight wildlife crime in the Protected Areas. 150 of inspectors and rangers have been trained at the Kissama NP and have basic level of skills required to fight wildlife crime. However, regular system of repetitive trainings for the INBAC staff and rangers is needed. The INBAC has a Wildlife School in Menongue for capacity building of the wildlife crime law enforcement staff, but the school is not functional yet. All other wildlife crime agencies (ECU, National Police, IDF, Customs) in the country are understaffed and have insufficient capacity to fight illegal wildlife trade. |
| Systemic | There is a fully transparent oversight authority for the institutions responsible for combating poaching and IWT. | 0 -- There is no oversight at all of institutions responsible for combating poaching and IWT; 1 -- There is some oversight, but only indirectly and in a non-transparent manner; 2 -- There is a reasonable oversight mechanism in place providing for regular review but lacks in transparency (e.g. is not independent, or is internalized) ; 3 -- There is a fully transparent oversight authority responsible for combating poaching and IWT | 2 | The INBAC is oversight by the Ministry of Environment. The Department for Human Resources of the INBAC and Ministry of Environment are responsible for the agency performance, but INBAC does not currently have any regular audit or risk committee. INBAC issues an annual report, that is not officially published, but available upon request. |
| Institutional | Institutions responsible for combating poaching and IWT are effectively led. | 0 – Institutions responsible for combating poaching and IWT have a total lack of leadership; 1 -- Institutions responsible for combating poaching and IWT exist but leadership is weak and provides little guidance; 2 -- Institutions responsible for combating poaching and IWT have reasonably strong leadership but there is still need for improvement; 3 -- Institutions responsible for combating poaching and IWT are effectively led | 2 | INBAC follows the General Labor Law of Angola and the Internal Rules of Conduct. INBAC has an annual performance evaluation and provides opportunities for professional growth of its staff, such as vacancy for students and projects for the staff capacity building. |
| Institutional | Institutions responsible for combating poaching and IWT have regularly updated, participatorily prepared, comprehensive management plans. | 0 -- Institutions responsible for combating poaching and IWT have no management plans; 1 -- Some institutions responsible for combating poaching and IWT have up-to-date management plans but they are typically not comprehensive and were not participatorily prepared; 2 -- Most institutions responsible for combating poaching and IWT have management plans though some are old, not participatorily prepared or are less than comprehensive; 3 – All institutions responsible for combating poaching and IWT have a regularly updated, participatorily prepared, comprehensive management plans | 0 | INBAC does not have a management plan for institutional development and combating of wildlife crime. |
| Institutional | Human resources are well qualified and motivated. | 0 -- Human resources are poorly qualified and unmotivated; 1 -- Human resources qualification is spotty, with some well qualified, but many only poorly and in general unmotivated; 2 -- HR in general reasonably qualified, but many lack in motivation, or those that are motivated are not sufficiently qualified; 3 -- Human resources are well qualified and motivated. | 2 | Currently INBAC has 15 inspectors responsible for combating wildlife crime based in Luanda and 350 rangers in the country’s Protected Areas. 150 of inspectors and rangers have been trained at the Kissama NP and have basic level of skills required to fight wildlife crime. The motivation of INBAC staff, including rangers, is generally high enough. The average staff salary in the institution is approximately 400 USD, other benefits include social security, paid leave, Christmas bonus. INBAC motivates its staff to achieve higher results by offering subsidies, travels to congresses and conferences, etc. |
| Institutional | Management plans for IWT control and wildlife management are implemented in a timely manner effectively achieving their objectives. | 0 -- There is very little implementation of management plans; 1 -- Management plans are poorly implemented and their objectives are rarely met; 2 -- Management plans are usually implemented in a timely manner, though delays typically occur and some objectives are not met; 3 -- Management plans are implemented in a timely manner effectively achieving their objectives | 1 | INBAC has regular delays in the implementation of Protected Areas Management Plans due to budget limitation, policies and regulations of the Government/MINAMB and the Project Partners. |
| Institutional | Institutions for combating poaching and IWT are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate. | 0 -- Institutions responsible for combating poaching and IWT typically are severely underfunded and have no capacity to mobilize sufficient resources; 1 -- Institutions responsible for combating poaching and IWT have some funding and are able to mobilize some human and material resources but not enough to effectively implement their mandate; 2 -- Institutions responsible for combating poaching and IWT have reasonable capacity to mobilize funding or other resources but not always in sufficient quantities for fully effective implementation of their mandate; 3 -- Institutions responsible for combating poaching and IWT are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 1 | The INBAC as well as Protected Areas and other wildlife crime law enforcement agencies are chronically underfunded and understaffed in Angola. There is no info about the current budget for wildlife crime law enforcement and wildlife management at the INBAC. INBAC is trying to mobilize additional resources for wildlife protection and management via partnerships with UNDP, Stop Ivory, Wildlife Impact, Panthera, KfW, and private sector. INBAC plans to have no less than 1,500 rangers in the National PAs by 2020. Mobilizing sufficient funds for conservation in Angola is still challenging due to limited presence of international donors in the country. |
| Institutional | Anti-poaching and IWT prevention are effectively carried out | 0 -- No enforcement of regulations is taking place; 1 -- Some enforcement of regulations but largely ineffective and external threats remain active; 2 -- Regulations are regularly enforced but are not fully effective and external threats are reduced but not eliminated; 3 -- Regulations are highly effectively enforced and all external threats are negated | 1 | Given INBAC and PA staff is severely underfunded and understaffed, wildlife law enforcement in the PAs represents a great challenge. PA rangers lacks important skills, equipment and infrastructure for effective anti-poaching. In 2017 INBAC’s rangers arrested 57 poachers and confiscated 11 rifles. |
| Individual | Individuals are able to advance and develop professionally | 0 -- No career tracks are developed and no training opportunities are provided; 1 -- Career tracks are weak and training possibilities are few and not managed transparently; 2 -- Clear career tracks developed and training available; HR management however has inadequate performance measurement system; 3 -- Individuals are able to advance and develop professionally | 1 | The INBAC has a Wildlife School in Menongue for capacity building of the wildlife crime law enforcement staff, but the school is not functional yet. There are no training programmes for INBAC’s staff and rangers. The training activities carried out for INBAC’s personnel are developed using support of externally funded projects. |
| Individual | Individuals are appropriately skilled for their jobs | 0 -- Skills of individuals do not match job requirements; 1 -- Individuals have some or poor skills for their jobs; 2 -- Individuals are reasonably skilled but could further improve for optimum match with job requirement; 3 -- Individuals are appropriately skilled for their jobs | 1 | Only 150 of 350 PA rangers have been trained at the Kissama NP and have basic level of skills required to fight wildlife crime. A system of regular trainings for INBAC staff and other wildlife crime enforcement agencies is needed. |
| 3. Capacity to engage and build consensus among all stakeholders |  |  |  |  |
| Systemic | Institutions for combating poaching and IWT have the political commitment they require | 0 -- There is no political will at all, or worse, the prevailing political will runs counter to the interests of institutions; 1 -- Some political will exists, but it is not strong enough to make a difference; 2 -- Reasonable political will exists, but is not always strong enough to fully support institutions; 3 -- There are very high levels of political will to support institutions | 1 | As was stated above, Angola has high government commitments and political agenda to combat wildlife crime, however, the country faces many challenges to actually realize these commitment due to lack of appropriate legislation, sufficient funding, staff, equipment and infrastructure. All of these is true for INBAC struggling to implement its mandate in conditions of very limited resources and capacity. Much more targeted investments are needed to support appropriate wildlife crime enforcement in and outside of the PAs in the country. |
| Systemic | Institutions for combating poaching and IWT have the public support they require | 0 -- The public has little interest in institutions responsible for combating poaching and IWT and there is no significant lobby for these institutions; 1 -- There is limited support for institutions responsible for combating poaching and IWT; 2 -- There is general public support for institutions responsible for combating poaching and IWT and there are various lobby groups such as environmental NGO's strongly pushing them; 3 -- There is tremendous public support in the country for institutions responsible for combating poaching and IWT | 1 | There is a very limited public support for wildlife crime law enforcement institutions, including INBAC, in Angola. National NGOs have almost no involvement in the wildlife crime issues and very limited number of International NGOS are actually involved (e.g., Stop Ivory, Wildlife Impact, Panthera, ICCF). Communities living around PAs do not receive any significant benefits from conservation but suffer from HWCs, which in turn has not fostered attitudes that are supportive of conservation practices. No Community-Based Wildlife and Natural Resources Management (CBWM and CBNRM), Local Councils for Protection of Forest and Wildlife, and Community Management Areas defined in the National Policy on Forests, Wildlife and Conservation areas have been established in Angola. Many local people are involved in unsustainable bushmeat hunting and trade, ineffective slash and burn agriculture, devastating logging and burning of forests for short-term needs. |
| Institutional | Institutions responsible for combating poaching and IWT are mission oriented | 0 -- Institutional mission not defined; 1 -- Institutional mission poorly defined and generally not known and internalized at all levels; 2 -- Institutional mission well defined and internalized but not fully embraced; 3 – Institutional missions are fully internalized and embraced | 1 | INBAC’s mission statement is to ensure the implementation of the biodiversity conservation policy, determining the conservation status of species, vulnerable ecosystems and ways for their recovery, as well as diversifying the categories of conservation areas in Angola. However, it is not clearly present in the organizational communication to public. |
| Institutional | institutions responsible for combating poaching and IWT can establish the partnerships needed to achieve their objectives | 0 -- Institutions responsible for combating poaching and IWT operate in isolation; 1 -- Some partnerships in place but significant gaps and existing partnerships achieve little; 2 -- Many partnerships in place with a wide range of agencies, NGOs etc, but there are some gaps, partnerships are not always effective and do not always enable efficient achievement of objectives; 3 -- Institutions responsible for combating poaching and IWT establish effective partnerships with other agencies and institutions, including national and local governments, NGO's and the private sector to enable achievement of objectives in an efficient and effective manner | 2 | INBAC is quite able to build partnerships with other donors and organizations, including UNDP, Stop Ivory, ICCF, Panthera, Wildlife Impact, etc. Also INBAC participate in the Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora, Technical Committee to Combat Wildlife Crime, and Presidential Programme to restore Black Giant Sable populations. However, much more effective collaboration and higher level of INBAC involvement is needed to achieve positive change in wildlife conservation and management through the collaborative efforts. Currently INBAC and PAs have very limited collaboration with local communities inside and outside the PAs. |
| Individual | Individuals carry appropriate values, integrity and attitudes | 0 -- Individuals carry negative attitude; 1 -- Some individuals have notion of appropriate attitudes and display integrity, but most don't; 2 -- Many individuals carry appropriate values and integrity, but not all; 3 -- Individuals carry appropriate values, integrity and attitudes | 2 | There are no stated core values of the INBAC’s staff. However, many of the staff trying to implement the tasks well despite limited capacity. |
| 4. Capacity to mobilize information and knowledge |  |  |  |  |
| Systemic | Institutions responsible for combating poaching and IWT have the information they need to develop and monitor strategies and action plans for the management of the protected area system and plan everyday activities | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 -- Much information is easily available and mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 -- Institutions responsible for combating poaching and IWT have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 1 | INBAC does not have expertise in GIS, poaching analysis, wildlife trade, deforestation and forest fires. Information available at INBAC is scattered. There are no regular wildlife counts in the PAs. The reports available are usually produced through pilot projects. |
| Individual | Individuals working with institutions responsible for combating poaching and IWT work effectively together as a team | 0 -- Individuals work in isolation and don't interact; 1 -- Individuals interact in limited way and sometimes in teams but this is rarely effective and functional; 2 -- Individuals interact regularly and form teams, but this is not always fully effective or functional; 3 -- Individuals interact effectively and form functional teams | 2 | INBAC’s staff work in interaction, but hierarchy plays a strong role in the organization, which can sometimes affect direct communication of the staff. |
| 5. Capacity to monitor, evaluate, report and learn |  |  |  |  |
| Systemic | Policies for institutions responsible for combating poaching and IWT are continually reviewed and updated | 0 -- There is no policy or it is old and not reviewed regularly; 1 -- Policy is only reviewed at irregular intervals; 2 -- Policy is reviewed regularly but not annually; 3 -- Institutional policy for combating poaching and IWT is reviewed annually | 1 | INBAC was created in 2010 and its institutional policy was enacted in the same law. INBAC’s institutional policy is being reviewed this year (2018) for the first time after establishment. INBAC has participated in the revision of MINAMB’s institutional policy, which happened at the beginning of 2018. |
| Systemic | Society monitors the state of institutions responsible for combating poaching and IWT | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the institutions responsible for combating poaching and IWT | 1 | National and International NGOs, general public and local communities have very little involvement in the monitoring of the INBAC performance in relations to wildlife crime enforcement and wildlife management. Open dialog with public is needed to involve it in the implementation and support of the INBAC’s functions. |
| Institutional | Institutions are highly adaptive, responding effectively and immediately to change | 0 -- Institutions resist change; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change | 1 | Timely INBAC’s responses to national challenges including wildlife crime issues and wildlife management are complicated by insufficient staff, capacity and funding. Thus, immediate actions in response to the challenge is not possible in majority of cases. However, INBAC is progressing on wildlife crime enforcement and wildlife management issues via cooperation with UNDP, Stop Ivory, ICCF, Panthera and other international actors. |
| Institutional | Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 1 | The Department for Human Resources of INBAC and Ministry of Environment are responsible for the agency performance, but INBAC does not have any regular audit or risk committee. INBAC issues an annual report that it is available upon request. |
| Individual | Individuals are adaptive and continue to learn | 0 -- There is no measurement of performance or adaptive feedback; 1 -- Performance is irregularly and poorly measured and there is little use of feedback; 2 -- There is significant measurement of performance and some feedback but this is not as thorough or comprehensive as it might be; 3 -- Performance is effectively measured and adaptive feedback utilized | 1 | The INBAC has an annual performance evaluation and provides some limited opportunities for professional growth of its staff, such as vacancy for students and projects for capacity building. However, the system to measure individual performance of the institutional staff is not sufficient as well as the system to improve this performance |

## Annex R. ICCWC Indicator Framework Report

See file PIMS 5993 Angola GEF6 ANNEX R - ICCWC Indicator Framework Report.pdf

## Annex S. Brief Project Knowledge Management Strategy

To respond to the growing wildlife crisis and international call for action, the Global Environment Facility (GEF) in June 2015 launched the Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development, often called the Global Wildlife Program (GWP). Led by the World Bank, the GWP is a $131 million grant program designed to address wildlife crime across 19 countries in Africa and Asia. The GWP serves as a platform for international coordination, knowledge exchange, and delivering action on the ground. The GWP builds and strengthens partnerships by supporting collaboration amongst national projects, captures and disseminates lessons learned, and coordinates with implementing agencies and international donors to combat IWT globally.  National projects within the GWP form an integral part of a community of practice that promotes the sharing of best practices and technical resources. While this UNDP-GEF project in Angola is not a national project under the GWP, it was designed to contribute to the GWP as much as possible. During project execution, Angola will share its lessons with GWP projects and will have access to the GWP documentation and materials produced during project implementations, virtual- and in-person meetings of relevance to the activities to be carried out in country, especially those on IWT control, PA management, CBWM, and biodiversity conservation mainstreaming in production sector. Angola is committed to engaging with GWP partners in Africa and Asia on joint efforts that will help with the project implementation, including issues related to human wildlife conflict and other technical areas.

The brief Knowledge Management (KM) Strategy refers to the process of capturing, storing and sharing knowledge so that we can learn lessons from the past and apply them in the future. It is designed to promote awareness towards the project from local to national and global level, for flow of information and exchange of ideas between stakeholders for knowledge management and implementation.

It will also help build visibility and interest towards the environmental sustainability in Angola conservation needs by connecting communities, policy makers, media, research and academic institutes, private sector, NGOs and general public, through a comprehensive program that goes from consultative meetings, to outreach and awareness campaigns, events and talks at local level.

The core intent of the communication strategy is to inform the stakeholders and build among them an ownership to the goals of the project i.e. the combat of illegal wildlife trade (IWT) and reduction of human-wildlife conflict (HWC) through capacity building of key law enforcement agencies at national and local levels, effective management of the two project areas- Maiombe NP and Luando SNR, and involvement of local communities in CBNRM for effective and efficient conservation purposes. The main idea is to put systems in place that facilitate and generate a common vision for the project to ensure its sustainability in the future from its People.

The following are key principles that guide the UNDPs Knowledge management practices in the project framework:

- It is people centered and rather than document centered and processes and technology are used to provide a supporting function;

- Knowledge transfer is effective when transmitted within a specific context;

- Knowledge is most effectively disseminated when there is an audience;

- Knowledge management is not for the organization only but ultimately targets the public;

- KM should be seen as the core value proposition for the organization and not a standalone activity.

KM strategy will prioritize the six focus areas as outlined in the UNDP’s Knowledge Management Guidelines:

- Organizational Leaning and Knowledge capture include developing a database that captures the lessons learned and conduct under “Lessons Learned campaigns”.

- Knowledge networking consists in online knowledge sharing using social networks and project website.

- Openness and public engagement consists of developing blogs to report on project activities, and debates in public forums such as the ones convened by the Mass Public Opinion Institute.

- South-South Cooperation and External Client-Services (See extended discussion on South-South Cooperation in Expected Results section).

- Measurement and Incentives, and

- Talent management.

UNDP will integrate the KM into its management processes to ensure that the knowledge products are translated into the deliverables within the work plans. KM thus will be integrated in the following processes:

- Human Resources;

- Project management;

- Finance;

- Communication and Advocacy; and

- Technology development.

To systemize and share its lessons and knowledge the project will use different communication means, as follows:

- A project web-site with available project reports, publications, press-releases, datasets, draft and final legislative documents, developed management plans, etc.;

- Quarterly or 6 month project information bulletin;

- Special paper publications, including manuals, guidance, methodologies, etc.;

- Publications in mass media, conservation, and scientific journals; and

- Public awareness campaign targeting IWT, bushmeat consumption, HWC and habitat degradation in the project areas;

- Support of environmental clubs, education camps, school forestries and Climate Smart Gardens for schoolchildren living in the target PAs;

- Organization of Wildlife Festivals for target communities (e.g. Elephant or Giant Black Sable events) with active involvement of adults and kids;

- Organization of community and Parks joint sport events (e.g. football games between Park rangers and community members, shooting and specialized ranger competitions, etc.) to build trust, friendship and collaboration for conservation;

- Publication of brochures and booklets for local communities on criminal and administrative responsibilities and penalties for poaching, wildlife trafficking, illegal logging and mining;

- Stop Bush Fire campaign for local people in the Luando SNR;

- Involvement of palanca pastors, traditional leaders, and chiefs in outreach programmes for local communities on sustainable wildlife and forest use;

- Regular publication in local newspapers on the project progress and activities;

- Nao Como Carne de Casa campaign on the national TV with national celebrities, radio and TV translation of interviews with environmental and conservation leaders;

- Exchange visits to successful community projects to pick up best experience;

- Targeted environmental education programme for government officials, including army and police, in the project areas;

- Focus groups for adults with clear and simple explanations of climate change, deforestation, bush fires and wildlife degradation consequences by leading experts; and

- Integrated theatre groups in communicating conservation information around local communities.

## Annex T. List of stakeholders consulted for the project development

| Name | Gender | Organization | Contact info |
| --- | --- | --- | --- |
| Susan Lylis | F | ICCF | susanlylis@iccfoundation.us |
| Daniel Tanner | M | ICCF | dtanner@internationalconservation.org |
| Goetz Schroth | M | UNDP Angola | goetz.schroth@undp.org |
| Vanessa Falkowsky | F | UNDP Angola | vanessa.falkowski@undp.org |
| Javier Montano | M | UNODC Kenya | javier.montano@unodc.org |
| Manuela Matzinger | F | UNODC Kenya | manuela.matzinger@un.org |
| Nils Meyer | M | KfW | Nils.Meyer@kfw.de |
| Alexander Rhodes | M | Stop Ivory | Alexander.Rhodes@Mishcon.com |
| Keith Roberts | M | EIA | kroberts@conservation.org |
| Shruti Suresh | F | EIA | ShrutiSuresh@eia-international.org |
| Mary Rice | F | EIA | MaryRice@eia-international.org |
| Andrew Parker | M | African Parks | andrewp@africanparks.org |
| Shamini Jayanathan | F | Space for Giants | shamini@spaceforgiants.org |
| Steve Boyes | M | Okawango Wilderness Project | steve@wildbirdtrust.com |
| Jimmiel Mandima | M | AWF | jmandima@awf.org |
| Chris Weaver | M | WWF-Namibia | cweaver@wwf.na |
| Holly Dublin | F | IUCN | holly.dublin@gmail.com |
| Lilian Pintea | M | Jane Goodall Institute | lpintea@janegoodall.org |
| Hugo Jachmann | M | EPI | hjachmann@elephantprotectioninitiative.org |
| Chris Thouless | M | Save the Elephants | thouless@savetheelephants.org |
| Sophie Ledger | F | Stop Ivory | sophie.ledger@stopivory.org |
| Danilo Barbero | M | Delegation of the EU in Angola | danilo.barbero@eeas.europa.eu |
| Fiona Maisels | F | WCS-Congo | fmaisels@wcs.org |
| Ashley Vosper | M | Independent consultant on wildlife surveys | ashley.vosper@gmail.com |
| Samantha Strindberg | F | WCS | sstrindberg@wcs.org |
| Emma Stokes | F | WCS Africa Programme | estokes@wcs.org |
| Erica Liman | F | IELP | erica.j.lyman@gmail.com |
| Lumiere Jean-Felix Issang | M | UNDP-Congo | jean-felix.issang@undp.org |
| Jessie Mee | F | UNDP RBM Specialist | jessie.mee@undp.org |
| Julie Sherman | F | Wildlife Impact | julie@wildlifeimpact.org |
| Vladimir Russo | M | Kissama Foundation | vladyrusso@gmail.com |
| Pedro vaz Pinto | M | Presidential Programme for Black Giant Sable | pedrovazpinto@gmail.com |
| Ed Humphrey | M | KAZA TFCA Secretariat | ed.humphrey@kavangozambezi.org |
| Martin Ewi | M | ENACT | mewi@issafrica.org |
| Agnes Ebo'o | F | ENACT | aeboo@issafrica.org |
| Deo Gumba | M | ENACT | dgumba@issafrica.org |
| Peter Newland | M | 51 Degrees | pete@51degreesltd.com |
| Andrew Batian Craig | M | 51 Degrees | batian@51degreesltd.com |
| Barry Cork | M | 51 Degrees | barry@51degreesltd.com |
| Pedro Simone | M | AfDB | p.simone@afdb.org |
| Clare Ward | F | ADPP | clare.ward@adpp-angola.org |
| Anke Voorhoeve | F | ADPP | anke.voorhoeve@adpp-angola.org |
| Mustaque Ahmed | M | ADPP | mustaque.ahmed@adpp-angola.org |
| Anastacio Goncalves | M | FAO | anastacio.goncalves@fao.org |
| Txaran Basterrechea | M | FAO | txaran.basterrechea@fao.org |
| Afonso Zola | M | FAO | Afonso.Zola@fao.org |
| Gerson Hurtado Bergeth | M | UNODC, Border Management Programme | gerson.bergeth@un.org |
| Maria Lôa | F | Ministry of Environment /INBAC | Marialoa2004@yahoo.com.br |
| Marta Alexandre Zumbo | F | Ministry of Environment /INBAC | mnsambalex@gmail.com |
| Mikhail Paltsyn | M | Consultant/ UNDP Angola | paltsyn@mail.ru |
| Henrik Fredborg Larsen | M | UNDP Angola | Henrik.larsen@undp.org |
| Daniel Tanner | M | International Conservation Caucus Foundation | dtanner@internationalconservation.org |
| Evaristo Jorge Tavares | M | AJUDECA | ajudecanacional@yahoo.com.br |
| Mbo João Domingos | M | MBAKITA | Mbojoao2@hotmail.com |
| Verónica Pais | F | Consultant/ UNDP Angola | veronikapais@gmail.com |
| Avelina Lopes | F | UNDP Angola | Avelina.lopes@undp.org |
| Edna Azevedo | F | Fundação Kissama | Ednaazevedo06@gmail.com |
| Célsia Isabel da Gama Africano | F | Ministry of Environment/ INBAC | celsiagama@hotmail.com |
| Hilária Valério | F | Ministry of Environment/ INBAC | hilamachado@hotmail.com |
| Victor Paca | M | Ministry of Environment/ INBAC | victorpacasvictor@gmail.com |
| José Novais Felix | M | UNDP Angola | Jose.felix@undp.org |
| Tamar Ron | F | Consultant/ UNDP Angola | tamarron@bezeqint.net |
| Pascoal Baptistiny | M | MBAKITA | mbakitaangola@hotmail.com |
| Nascimento Antonio | M | Ministry of Environment/ National Direction of Biodiversity | Kidima.nascimento@yahoo.co.uk |
| Zacarias Castro Selalo | M | Attorney General of the Republic | zacariasselalo@gmail.com |
| José Antonio Dianguesso | M | Ministry of Environment/ INBAC | Jose.dianguesso@hotmail.com |
| Filomena Pereira Mateus | F | University Agostinho Neto - Faculty of Biology | mavuapereira@yahoo.com.br |
| Albertina Nzuzi | F | Ministry of Environment/ CITES Focal Point | wetekakalando@gmail.com |
| Angelo Bernardo António | M | Ministry of Environment/ INBAC | angebernant@gmail.com |
| António José | M | Environment Crimes Unit | 923086551 |
| Waldemar José dos Santos Van Dúnem | M | Angolan Institute for Roads | - |
| Flávia Silva | F | Ministry of Industry | mhamhi@hotmail.com |
| José Rodrigues | M | Environment Crimes Unit | Ambiente128@gmail.com |
| Sango de Sá | M | Ministry of Environment/ INBAC | Bigsango11@gmail.com |
| Maria da C. Pascoal | F | Ministry of Environment | Mariakissdua2018@hotmail.com |
| Paulo Miteculo | M | Environment Crimes Unit | 924137878 |
| Domingos Ndjundo | M | Ministry of Environment/ INBAC | vascoinbac@gmail.com |
| Júlio Sebastião Matias | M | Civil society | juliosebastiaosabadomatias@gmail.com |
| José Silva | M | Angolan Ecological Youth (JEA) | zsambiente@gmail.com |
| Donana João da S. Filho | F | Communal Administration of Cerca | 923020421 |
| Afonso Manuel Domingos | M | Communal Administration of Cerca | 943035101/ afonso.domingos.1980@gmail.com |
| António Zacarias Manuel | M | Communal Administration of Cerca | 928796672 |
| Nicolau Rodrigues de Oliveira | M | Communal Administration of Cerca | 928827597 |
| Salvador Bartolomeu Jerónimo | M | Communal Administration of Cerca | 926757309 |
| Antonio Magalhães | M | Municipal Administration of Luquembo | 921317122 |
| Albano Babanga | M | Municipal Administration of Luquembo | 927445673 |
| Ernesto Cufele Chapuco | M | Municipal Administration of Luquembo | 925665557 |
| Tiago Tomás | M | Communal Administration of Kunga Palanca | 943529520 |
| Garcia Antonio | M | National Police | 931174483 |
| Abreu Manuel Mussumba | M | Communal administration of Quimbango | 947522019 |
| Pedro Afonso | M | Communal Administration of Capunda | 931821471/ 921645335/ 222697786 |
| Baião António Baião | M | Communal Administration of Capunda | 929866932/ 222697787 |
| Feliciano da Piedade | M | Communal Administration of Capunda | 930251014 |
| Rufino Franco Capopo | M | Communal Administration of Capunda | 930698763 |
| Antónia Pedro | F | Commune of Capunda | - |
| Anita Sociano Gazamba | F | Commune of Capunda | - |
| Walter da Glória P. Demba | M | Provincial Direction of Agriculture – Cuanza Norte | walterdemba@yahoo.com.br |
| José Mateus Augusto | M | Provincial Direction of Agriculture – Cuanza Norte | Josemmateus2016@gmail.com |
| Wasewa Ndolumingu | M | Provincial Direction of Agriculture – Cuanza Norte | wasewa@yahoo.fr |
| Armando Sousa | M | Provincial Direction of Agriculture – Cuanza Norte | 923716106 |
| Ndomba Meyi Antonio | M | Provincial Direction of Agriculture – Cuanza Norte | 941260330 |
| Armindo Manuel João Domingos | M | Forest Development Institute – Cuanza Norte | 930699949 |
| Santinho Figueira | M | FAS | figueirasantinho@gmail.com |
| Daniel Miji Mujinga | M | FAS | dmiji@fas.co.ao |
| Anastacio Gonçalves | M | FAO | Anastacio.goncalves@fao.org |
| Afonso Zola | M | FAO | Afonso.zola@fao.org |
| Txaran Basterrechea | M | FAO | Txaran.basterrechea@fao.org |
| Mustaque Ahmed | M | ADPP | Mustaque.ahmed@adpp.angola.org |
| Clare Ward | F | ADPP | Clare.ward@adpp.angola.org |
| Anke Voorhoeve | F | ADPP | Anke.voohoeve@adpp.angola.org |
| Aristófales Pontes | M | INBAC | Arisebac40@hotmail.com |
| Albertina Nzuzi | F | Ministry of Environment/ CITES Focal Point | wetekakalando@gmail.com |
| Sango de Sá | M | Ministry of Environment/ INBAC | Bigsango11@gmail.com |
| Hilária Valério | F | INBAC/MINAMB | hilamachado@hotmail.com |
| Célsia Africano | F | INBAC/MINAMB | celsiagoma@hotmail.com |
| Olívio Panda | M | Maiombe/MINAMB | op_panda82@hotmail.com |
| Pedro Simone | M | African Development Bank | P.SIMONE@afdb.org |
| Juliano Capita | M | Provincial Secretary for Territory, Urban Planning and Environment | Jcapita2015@gmail.com |
| Hernani Geovany de Oliveira | M | National Direction for Biodiversity | Hern.any23@hotmail.com |
| Daniel Tati Luemba | M | Provincial Secretary for Territory, Urban Planning and Environment | dtatiluemba@gmail.com |
| José Maria Bizi | M | Maiombe National Park /INBAC | bizijose@yahoo.com.br |
| Zacarias Cubola Gomes | M | Maiombe National Park/ INBAC | 924005923 |
| Chiquinho Bernardo Guimbi | M | Maiombe National Park/ INBAC | 921326917 |
| Serafim Sema | M | Municipal Administration of Belize | 92232379 |
| Adão Domingos Neto | M | Border Police | 922992892 |
| Casimiro Novais | M | National Police | 946787277 |
| Júlio Ducosto | M | Army | 929425291 |
| Paulo Matiala | M | Regedoria Bulo | 996989813 |
| Celestino Macaia | M | Communal Administration of Miconje | 935777506 |
| Abel Ndungui Gomes | M | Regedoria Bulo | 946355757 |
| Joaquim Victor Toco | M | Regedoria Tsango Bata | 949817993 |
| Enoqui Zom | M | Regedoria Tsango Bata | 936749075 |
| Fernando Milando | M | Regedoria Tsango Bata | 946456486 |
| Manuel Agostinho | M | Regodoria Tsango Bata |  |
| Pedro Garcia | M | Bata Maba |  |
| Mateus Cipriano Guimbi | M | Regedoria Zala de Baixo | 926009801 |
| Pedro Zom | M | National Police | 934118828 |
| Edmundo Bilendo Somo | M | National Police | 930251169 |
| Angelino Afonso | M | National Police |  |
| Oscar Vinquissa | M | National Police | 937639428 |
| Alberto Quibinda | M | National Police | 939735805 |
| Alexandre Zelo | M | Buco Zau Municipal Administration | 948210886 |
| Estanislau Kianga João | M | National Police | 943872599 |
| José Macaia Capita Muanda | M | National Police | 929299540 |
| Simão Mavungo Filo | M | National Police | 946735619 |
| Fernando Antonio Guiba Cuicu | M | National Police | 924391408 |
| Donatien Quimbi Damba | M | National Police | 946789539 |
| João António Bumba | M | National Police | 921761134 |
| Lourenço Vicente Bueia Mboca | M | National Police | 244786829 |
| José Luemba Bungo | M | National Police | 940621595 |
| Alfredo Rosário Chimbuca | M | National Police | 924331279 |
| José Maria Cabinda | M | National Police | 924331279 |
| Mateus Kuanga Muvungo | M | National Police | 934122684 |
| José Luís B. Guimbi | M | National Police | 948807978 |
| Afonso Muanda Macaia | M | National Police | 944943069 |
| Dario Lembe | M | National Police | 944079464 |
| Marcos Massunga | M | National Police | 939733643 |
| Beto João | M | Army | 932466747 |
| João Amadeu | M | Army | 947704010 |
| Lucas Joaquim Brasileiro | M | Army | 940560222 |
| João Baptista Nungo Barros | M | Maiombe National Park/ INBAC | 943619021 |
| Joana Malanda Quibinda | F | Maiombe National Park/ INBAC | Joanaquibinda35@hotmail.com |
| João Buino Sambulo | M | Maiombe National Park/ INBAC | 934902377 |
| Alberto Paca Zuzi Macosso | M | Vice Governor of Cabinda Province for the Political and Social Sector | albertopaca@yahoo.com |
| José Lelo | M | ADPP | joseleloluaka@hotmail.com |

https://en.wikipedia.org/wiki/Geography_of_Angola

http://www.worldometers.info/world-population/angola-population/

ibid

https://www.cia.gov/library/publications/resources/the-world-factbook/rankorder/2002rank.html#ao

https://www.cia.gov/library/publications/resources/the-world-factbook/geos/ao.html

https://www.cia.gov/library/publications/resources/the-world-factbook/geos/ao.html

https://www.cia.gov/library/publications/resources/the-world-factbook/geos/ao.html

http://hdr.undp.org/en/countries/profiles/AGO

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

Institute for Forestry Development 2004. Angola – Recursos florestais e suas potencialidades. Brochure. Instituto de Desenvolvimento Florestal, Luanda, Angola.

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

IUCN 1992. Angola: Environment status quo assessment report. Regional Office for Southern Africa, World Conservation Union, Harare, Zimbabwe.

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

Angola’s National Biodiversity Strategy and Action Plan 2007-2012.

Brett, R. Angola. Rhino Resource Center. http://www.rhinoresourcecenter.com/pdf_files/119/1197200580.pdf

Anstey S. Angola: elephants, people and conservation, a preliminary assessment of the status and conservationof elephants in Angola. Harare, Zimbabwe: IUCN Regional Office for Southern Africa; 1993.

Kumleben ME. Commission of inquiry into the alleged smuggling of and illegal trade in ivory and rhinoceros horn in South Africa. Durban, South Africa: Report to the State President of the Republic of SouthAfrica; 1996.

C.R. Thouless, H.T. Dublin, J.J. Blanc, D.P. Skinner, T.E. Daniel, R.D. Taylor, F. Maisels, H. L. Frederick and P. Bouché (2016). African Elephant Status Report 2016: an update from the African Elephant Database. Occasional Paper Series of the IUCN Species Survival Commission, No. 60 IUCN / SSC Africa Elephant Specialist Group. IUCN, Gland, Switzerland. vi + 309pp

Ibid

P. vaz Pinto, personal communication

IUCN SSC Antelope Specialist Group. 2017. Hippotragus niger ssp. variani. The IUCN Red List of Threatened Species 2017: e.T10169A50188611. http://dx.doi.org/10.2305/IUCN.UK.2017-2.RLTS.T10169A50188611.en. Downloaded on 02 May 2018.

Maisels, F., Bergl, R.A. & Williamson, E.A. 2016. Gorilla gorilla (errata version published in 2016). The IUCN Red List of Threatened Species 2016: e.T9404A102330408. http://dx.doi.org/10.2305/IUCN.UK.2016-2.RLTS.T9404A17963949.en. Downloaded on 02 May 2018.

Ron, T. 2005. The Maiombe Forest in Cabinda: conservation efforts, 2000-2004. Gorilla Journal (Journal of Berggorilla and Regenwald Direkthilfe, published in English, French and German) 30: 18-21, (http://www.berggorilla.de/fileadmin/gorilla-journal/gorilla-journal-30-english.pdf ).

Ron, T. 2001. Gorillas and chimpanzees in the Maiombe Forest, Cabinda Enclave, Angola. Abstract, presented paper and poster. Evolutionary Neighbors, The 4th International SAGA Symposium, November 2001, Okayama, Japan (http://www.saga-jp.org/sympo/SAGA4/4abst/4_oral.pdf). The Ministry of Fisheries and Environment of Angola and UNDP

Strindberg et al. 2018. Guns, germs, and trees determine density and distribution of gorillas and chimpanzees in the Western Equatorial Africa. Sci. Adv. 4. http://advances.sciencemag.org/content/4/4/eaar2964

Fulton et al. 2016. The Distribution and Status of Lions and Other Large Carnivores in Luengue-Luiana and Mavinga National Parks. Survey Report. Panthera, MINAMB, KAZA

Miller, J., Vira, V., and Utermohlen, M. 2015. Species of Crime. Typologies & Risk Metrics for Wildlife Trafficking.  C4ADS

‘Status of elephant populations, levels of illegal killing and the trade in ivory: A report to the CITES Standing Committee’ just prepared for 69th meeting of the CITES Standing Committee https://cites.org/sites/default/files/eng/com/sc/69/E-SC69-51-01-A.pdf

Schlossberg S, Chase MJ, Griffin CR (2018). Poaching and human encroachment reverse recovery of African savannah elephants in south-east Angola despite 14 years of peace. PLoS ONE 13(3): e0193469. https://doi.org/10.1371/journal.pone.0193469

Bushskies Aerial Photography 2017. An aerial photographic wildlife survey of Luengue-Luiana and Mavinga National Parks, Angola, September 2017. Survey Report

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

Milliken, T., Pole, A., and Huongo, A. (2006). No Peace for Elephants: Unregulated Domestic Ivory Markets in Angola and Mozambique. TRAFFIC International, Cambridge, UK.

Martin E. and Vigne L. 2014. Luanda—the largest illegal ivory market in southern Africa. Survey Report.

Miller, J., Vira, V., and Utermohlen, M. 2015. Species of Crime. Typologies & Risk Metrics for Wildlife Trafficking.  C4ADS

Hungerford, E. (2016). Government bans trade of ivory in Angola. The Independent, London, United Kingdom.

http://www.independent.co.uk/voices/campaigns/GiantsClub/government-bans-trade-of-ivory-in-angolaa6944486.html

Martin E. and Vigne L. 2014. Luanda—the largest illegal ivory market in southern Africa. Survey Report.

https://www.standardmedia.co.ke/article/2000066828/police-unearth-illegal-ivory-from-angola

Martin E. and Vigne L. 2014. Luanda—the largest illegal ivory market in southern Africa. Survey Report.

https://www.ifaw.org/united-kingdom/news/significant-seizure-elephant-ivory-heathrow-airport

Mary Utermohlen & Patrick Baine. 2017. Flying Under the Radar: Wildlife Trafficking in the Air Transport Sector. C4ADS, USAID.

https://www.thestar.com.my/news/nation/2016/03/03/elephant-tusks-seized-at-klia-three-vietnamese-men-on-transit-nabbed-at-arrival-hall/

Miller, J., Vira, V., and Utermohlen, M. 2015. Species of Crime. Typologies & Risk Metrics for Wildlife Trafficking.  C4ADS

Mary Utermohlen & Patrick Baine. 2017. Flying Under the Radar: Wildlife Trafficking in the Air Transport Sector. C4ADS, USAID.

Mary Utermohlen & Patrick Baine. 2017. Flying Under the Radar: Wildlife Trafficking in the Air Transport Sector. C4ADS, USAID.

http://www.redeangola.info/policia-apreende-370-kg-de-marfim-no-aeroporto-de-luanda/

http://allafrica.com/stories/201806220097.html

National Policy on Forests, Wildlife and Conservation areas in Angola, dated on January 14, 2010

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment and PPG team observations in June 2018.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

Bersacola et al. 2014. Hunted in Angola: Surveying the bushmeat trade. January 2014.

Fabiano et al. 2017. Wildlife Inventory of Two National Parks in Southeastern Angola, July-October 2016.

Fulton et al. 2016. The Distribution and Status of Lions and Other Large Carnivores in Luengue-Luiana and Mavinga National Parks. Survey Report. Panthera, MINAMB, KAZA

Overton et al. 2016. A Large Mammal Survey of Bicuar and Mupa National Parks, Angola. Panthera and MINAMB.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

National Geographic Okavango Wilderness Project. 2017. Initial Findings from Exploration of the Upper Catchments of the Cuito, Cuanavale, and Cuando Rivers, May 2015 to December 2016

http://www.bbc.com/news/world-africa-36457637

Fa et al. 2002. Bushmeat Exploitation in Tropical Forests: an Intercontinental Comparison. Conservation Biology, Pages 232–237. Volume 16, No. 1, February 2002

Karidozo, M, La Grange, M & Osborn, F.V. (2016) Assessment of the human wildlife conflict mitigation measures being implemented by the Kavango-Zambezi Transfrontier Conservation Area (KAZA TFCA) partner countries. Report to the KAZA TFCA Secretariat (BMZ No.: 2009 66 788 and BMZ No.: 2006 65 646), Kasane, Botswana.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF

Karidozo, M, La Grange, M & Osborn, F.V. (2016) Assessment of the human wildlife conflict mitigation measures being implemented by the Kavango-Zambezi Transfrontier Conservation Area (KAZA TFCA) partner countries. Report to the KAZA TFCA Secretariat (BMZ No.: 2009 66 788 and BMZ No.: 2006 65 646), Kasane, Botswana.

Karidozo, M, La Grange, M & Osborn, F.V. (2016) Assessment of the human wildlife conflict mitigation measures being implemented by the Kavango-Zambezi Transfrontier Conservation Area (KAZA TFCA) partner countries. Report to the KAZA TFCA Secretariat (BMZ No.: 2009 66 788 and BMZ No.: 2006 65 646), Kasane, Botswana.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF

Walter Demba, Head of the Provincial Direction for Agriculture in Cuanza Norte, personal communication

Joe Heffernan. 2005. Elephants of Cabinda. Mission Report, Angola, April 2005. UNDP and FFI.

Ron, T. 2018. Report of the preliminary wildlife survey in the Maiombe National Park. National Biodiversity Project. Ministry of Environment (MINAMB), UNDP, GEF, EU.

Joe Heffernan. 2005. Elephants of Cabinda. Mission Report, Angola, April 2005. UNDP and FFI.

Joe Heffernan. 2005. Elephants of Cabinda. Mission Report, Angola, April 2005. UNDP and FFI.

Administrators of Capunda, Kunga Palanca and Quimbango villages, personal communication

Global Forest Watch : Angola (all forested areas with canopy cover >= 20% are classified as forested) https://www.globalforestwatch.org/country/AGO?treeCover=eyJ0aHJlc2hvbGQiOjIwfQ%3D%3D&treeLoss=eyJ0aHJlc2hvbGQiOjIwfQ%3D%3D

Global Forest Watch: Angola (all forested areas with canopy cover >= 20% are classified as forested) https://www.globalforestwatch.org/country/AGO?treeCover=eyJ0aHJlc2hvbGQiOjIwfQ%3D%3D&treeLoss=eyJ0aHJlc2hvbGQiOjIwfQ%3D%3D

National Policy on Forests, Wildlife and Conservation areas in Angola, dated on January 14, 2010

National Policy on Forests, Wildlife and Conservation areas in Angola, dated on January 14, 2010

http://www.factfish.com/statistic-country/angola/wood+charcoal,+production+weight

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

National Geographic Okavango Wilderness Project. 2017. Initial Findings from Exploration of the Upper Catchments of the Cuito, Cuanavale, and Cuando Rivers, May 2015 to December 2016

Global Forest Watch Fires: Angola http://fires.globalforestwatch.org/report/index.html#aoitype=GLOBAL&reporttype=globalcountryreport&country=Angola

NASA Fire Information for Resource Management System (FIRMS) 2018. MODIS NRT active fire products (MCD14DL) for Angola 2013-2018 processed using the standard MOD14/MYD14 Fire and Thermal Anomalies product https://firms.modaps.eosdis.nasa.gov/data/download/DL_FIRE_M6_14771.zip

USAID 2013. Angola Biodiversity and Tropical Forests:118/119 Assessment

UNDP/GEF Project “SLM Capacity Building in Angola” (PIMS 3379)

NBSAP Angola 2007-2012

NBSAP Angola 2007-2012

Resolution No. 1/10 approving the National Policy on Forests, Wildlife and Conservation areas dated on January 14 2010

https://www.cites.org/eng/news/party/20131009_angola.php

NIAP Angola 2015-2016

NIAP Angola 2015-2016

Dated on January 24 2017

Presidential Decision No. 81/15 creating the Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora, 29 September 2015

Decree 112/15; MINAMB request to UNDP Angola to provide support for the 31st of January Wildlife School (Environmental Polytechnic Institute) in Menongue, May 31 2016

http://www.elephantprotectioninitiative.org/epi_in_action/angola-announces-its-membership-to-the-elephant-protection-initiative-as-it-gears-up-for-world-environment-day/

Decree 133/15, April 21 2015

Ron, T. 2012. Policia Verde Para a Fiscalização da Legislação para Conservação da Biodiversidade em Angola: Estatuto Orgânico Proposto Preliminar. MINAMB.

Ron, T. 2012 (updated, 2014). Policia Verde - Unidade Nacional de fiscalização do crime em vida selvagem. MINAMB

Luis Verissimo 2018. Map “ÁREAS DE CONSERVAÇÃO DA NATUREZA EM ANGOLA”. PROJECÇÃO POLICÓNICA

MINAMB data

Decreto Lei nº 38/11 de 29 de Dezembro que cria os Parques Nacionais de Luengue-Luiana, de Mavinga e do Maiombe

http://www.angop.ao/angola/en_us/noticias/ambiente/2018/1/8/Strategic-Plan-foresees-creation-new-conservation-zones,a490b9da-1396-4b7e-a8b6-da07a5121c3d.html

PIR UNDP/GEF PA Rehabilitation and Expansion Project 2017

PIR UNDP/GEF PA Rehabilitation and Expansion Project 2017; PIR UNDP/GEF Angola Iona Conservation Project 2017; Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

https://angolafieldgroup.com/palanca-negra/

Presidential Decision No. 2/18 creating the Executive Committee to follow up and reinforce the implementation of measures for Protection and Conservation of the Giant sable antelope, dated on April 4 2018.

Schlossberg S, Chase MJ, Griffin CR (2018). Poaching and human encroachment reverse recovery of African savannah elephants in south-east Angola despite 14 years of peace. PLoS ONE 13(3): e0193469. https://doi.org/10.1371/journal.pone.0193469

Schlossberg S, Chase MJ, Griffin CR (2018). Poaching and human encroachment reverse recovery of African savannah elephants in south-east Angola despite 14 years of peace. PLoS ONE 13(3): e0193469. https://doi.org/10.1371/journal.pone.0193469

Emerging TFCAs (Category B): These are TFCAs established on the basis of a Memorandum of Understanding (MOU). The MOUs serve as instruments that facilitate negotiations of Treaties to formally establish the respective TFCAs for eventual formalization to Category A (established TFCAs)

Ron, T. (2011): Potential for designating Protected Areas for conservation and for identifying conservation corridors as part of the planning process of the Mayombe forest TPA. Prepared for the Governments of Angola, Congo and DRC, UNEP and IUCN

Ron, T. 2011. Towards a transboundary protected area complex in the Mayombe forest ecosystems.  Strategic Plan (5 years). With inputs from Angola, Congo, DRC, UNEP and IUCN. Adopted by the Mayombe Transfrontier Initiative's governments on March 2013.

https://tfcaportal.org/node/438

Conceptual TFCAs (Category C): These are TFCAs without an official mandate from the participating countries but have been proposed by SADC Member States as potential TFCAs

https://tfcaportal.org/sadc-tfcas

IUCN SSC Antelope Specialist Group (2017). "Hippotragus niger variani". IUCN Red List of Threatened Species. Version 2017.

Mary Utermohlen & Patrick Baine. 2017. Flying Under the Radar: Wildlife Trafficking in the Air Transport Sector. C4ADS, USAID.

UNDP in Angola http://www.ao.undp.org/content/angola/en/home/ourwork/sustainable-development-goals-in-angola-.html

UNDP in Angola http://www.ao.undp.org/content/angola/en/home/ourwork/sustainable-development-goals-in-angola-.html

National Policy on Forests, Wildlife and Conservation areas dated on January 14 2010

National Geographic Okavango Wilderness Project. 2017. Initial Findings from Exploration of the Upper Catchments of the Cuito, Cuanavale, and Cuando Rivers, May 2015 to December 2016.

Law nº 3/14 about the criminalization of the infractions related to Money laundry, dated on February 10 2014

National Policy on Forests, Wildlife and Conservation areas dated on January 14 2010

NEAP-Angola is currently under development by the EPI

Established TFCAs (Category A): These are TFCAs established through a Treaty or any other form of legal agreement between the participating countries

Optimum staffing densities for a maximum of 0.2% illegal off take of an elephant population (acceptable) is between one ranger/32 km2 and 1 ranger/49 km2 (Jachmann, 1998. Monitoring Illegal Wildlife Use and Law Enforcement in African Savannah Rangelands.  Wildlife Resource Monitoring Unit, ECZ, Lusaka, Zambia.  Creda Communications, Johannesburg RSA. 124 pp.)

African Elephant Action Plan (AEAP) approved as a consensus document by all 37 African elephant range states in the margins of the 15th meeting of the Conference of the Parties to CITES (Doha, Qatar 13-25 March 2010)

https://www.thegef.org/sites/default/files/project_documents/ID9439__Global_Wildlife_Program_PFD_March_28_Final_V2_0.pdf

MINAMB data

Ron, T. 2012 (updated, 2014). Policia Verde - Unidade Nacional de fiscalização do crime em vida selvagem. MINAMB

http://www.gefieo.org/ops/ops-5

Redpath, S., S. Bhatia, and J. Young. 2015. “Tilting at Wildlife: Reconsidering Human-Wildlife Conflict.” Oryx 49 (2): 222–25. doi:10.1017/S0030605314000799. Reeb, D. 1999. “Sustainable Forestry in Gambia: How Policy and Legislation Can Make Community Forest Ownership a Reality.” Entwicklung& Ländlicher Raum 33 (5). Roe, D., ed. 2015. Conservation, crime and communities: case studies of efforts to engage local communities in tackling illegal wildlife trade. London: IIED. Roe, D., R. Cooney, H. Dublin, et al. 2017. “First Line of Defence: Engaging Communities in Tackling Wildlife Crime.” Unasylva 68 (249): 33–38.

http://www.fao.org/agriculture/ippm/programme/ffs-approach/en/

http://www.adpp-angola.org/en/projects/agriculture-rural-and-economic-development/farmers-clubs

FAO 2107. Toolkit for the application of  Green Negotiated Territorial Development  (GreeNTD). https://www.researchgate.net/publication/316740200_Toolkit_for_the_application_of_Green_Negotiated_Territorial_Development_GreeNTD

ADPP 2017. Annual Report  http://www.adpp-angola.org/images/PDF/annual-report-en/ADPP-Angola-Annual-Report-2017-Eng-web.pdf

http://fas.co.ao/?s=ADECOS&lang=pt-pt

https://www.iucn.org/regions/eastern-and-southern-africa/our-work/conservation-areas-and-species/local-communities-first-line-defence-against-illegal-wildlife-trade-flod

http://www.gefieo.org/ops/ops-5

Areas of the target Pas are different from gazetted and are based on the last assessment of the PA areas by Luis Verissimo 2018. Map “ÁREAS DE CONSERVAÇÃO DA NATUREZA EM ANGOLA”. PROJECÇÃO POLICÓNICA

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

Ibid

Ron, T. (2011): Potential for designating Protected Areas for conservation and for identifying conservation corridors as part of the planning process of the Mayombe forest TPA. Prepared for the Governments of Angola, Congo and DRC, UNEP and IUCN

Mayombe Forest Transfrontier Protected Area https://tfcaportal.org/node/438

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

Ron, T. 2018. Report of the preliminary wildlife survey in the Maiombe National Park. National Biodiversity Project. Ministry of Environment (MINAMB), UNDP, GEF, EU.

Personal communication of the PPG team with the Maiombe NP staff

University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html

Joe Heffernan. 2005. Elephants of Cabinda. Mission Report, Angola, April 2005. UNDP and FFI.

Ron, T. 2018. Report of the preliminary wildlife survey in the Maiombe National Park. National Biodiversity Project. Ministry of Environment (MINAMB), UNDP, GEF, EU.

Joe Heffernan. 2005. Elephants of Cabinda. Mission Report, Angola, April 2005. UNDP and FFI.

Personal communication of the PPG team with Miombe NP staff

Joe Heffernan. 2005. Elephants of Cabinda. Mission Report, Angola, April 2005. UNDP and FFI.

AfriPop (www.afripop.org) dataset for Angola. Alpha version 2015 estimates of numbers of people per grid square, with national totals adjusted to match UN population division estimates

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

Personal communication of the PPG team with the Maiombe NP staff

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF; Ron, T. 2018. Report of the preliminary wildlife survey in the Maiombe National Park. National Biodiversity Project. Ministry of Environment (MINAMB), UNDP, GEF, EU.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. All areas with >20% of the canopy cover was classified as forest and woodlands.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

P. vaz Pinto, personal communication

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF.

P. vaz Pinto, personal communication

University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html

NASA Fire Information for Resource Management System (FIRMS) 2018. MODIS NRT active fire products (MCD14DL) for Angola 2013-2018 processed using the standard MOD14/MYD14 Fire and Thermal Anomalies product https://firms.modaps.eosdis.nasa.gov/data/download/DL_FIRE_M6_14771.zip

Administrators of Capunda, Kunga Palanca and Quimbango villages, personal communication; Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF; AfriPop (www.afripop.org) dataset for Angola. Alpha version 2015 estimates of numbers of people per grid square, with national totals adjusted to match UN population division estimates

Administrators of Capunda, Kunga Palanca and Quimbango villages, personal communication

Administrators of Capunda, Kunga Palanca and Quimbango villages, personal communication

Administrators of Capunda, Kunga Palanca and Quimbango villages, personal communication

The forest elephant annual population growth rate for the project area was assumed to be very low (1.2% max) given the last study of Turkalo et al. 2017.  Slow intrinsic growth rate in forest elephants indicates recovery from poaching will require decades. Journal of Applied Ecology 54 (1): 153-159. Thus, we do not expect any significant growth in the elephant population in the Maiombe NP during the project life-time (6 years) and we consider stability of the elephant population as a considerable result of the project.

The population estimates of the gorilla for the entire Cabinda province in 2013 is 1,652 (CI: 1,174-3,311) based on the population modelling (Strindberg et al. 2018. Guns, germs, and trees determine density and distribution of gorillas and chimpanzees in the Western Equatorial Africa. Sci. Adv. 4). However, no actual population survey has been done in the area.

The western lowland gorilla potential annual population growth rate in the project area (at the zero rate and stable habitat) was assumed to be as low as 0.4-0.5% given the data received for gorilla populations in Congo and Gabon by King et al. 2014. Assessing reintroduction success in long-lived primates through population viability analysis: western lowland gorillas Gorilla gorilla gorilla in Central Africa. Oryx, 48(2), 294–303. Thus, we do not realistically expect population growth of the gorilla population in the project timeframe (6 years), give the species population in Cabinda could decline by 47% in 2005-2013 (or 5.9% annually) (Strindberg et al. 2018). Thus, even stopping the population decline will be a great result for the project!

The population estimates of the chimpanzee for the entire Cabinda province was 1,705 (CI: 1,027-4,801) in 2005-2013 based on Strindberg et al. 2018. Guns, germs, and trees determine density and distribution of gorillas and chimpanzees in the Western Equatorial Africa. Sci. Adv. 4. However, no actual population survey has been done in the area.

We do not realistically expect population growth of the chimpanzee population in the project time-frame (6 years), for the same reason as in the case with the western lowland gorilla above (Strindberg et al. 2018). Thus, even stopping the chimpanzee population decline in the project area will be a great result for the project!

P. vaz Pinto, personal communication. Baseline needs to be updated on the first year of the project.

We are likely to expect some population growth for the Black Giant Sable in the project life-time if poaching is effectively suppressed

Calculated as the total area covered with forest (>=20% of canopy cover) in 2000 (201,499 ha) minus area of tree cover loss in 2000-2017 (5,224 ha) based on the data of the University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. Baseline needs to be updated at the project Inception phase with data for 2018

Calculated as the total area covered with forest (>=20% of canopy cover) in 2000 (954,477 ha) minus area of tree cover loss in 2000-2017 (25,287 ha) based on the data of the University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. Baseline needs to be updated at the project Inception phase with data for 2018

Personal communication of the PPG team with the Maiombe NP staff: at least 4 elephants were poached in the park in 2013-2018.

Personal communication of the PPG team with the Maiombe NP staff and Ron 2018: at least 7-8 infant chimpanzees were confiscated from poachers in 2013-2018.

Last case of gorilla poaching in the Maiombe NP was recorded in 2018 according to Tamar Ron.

P. vaz Pinto, personal communication

Calculated as average for last 5 years (2013-2017) based on the data of the University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. Baseline needs to be updated at the project Inception phase with data for 2018

All logging is illegal in the target Pas and can be stopped with increased law enforcement efforts.

Calculated as average for last 5 years (2013-2017) based on the data of the University of Maryland. Global Forest Change 2000–2017 http://earthenginepartners.appspot.com/science-2013-global-forest/download_v1.5.html. Baseline needs to be updated at the project Inception phase with data for 2018

NASA Fire Information for Resource Management System (FIRMS) 2018. MODIS NRT active fire products (MCD14DL) for Angola 2017 processed using the standard MOD14/MYD14 Fire and Thermal Anomalies product https://firms.modaps.eosdis.nasa.gov/data/download/DL_FIRE_M6_14771.zip

See Annex R. ICCWC Indicator Framework Report Angola 2018

Each ranger in the Maiombe NP works 21 days after 21 days of rest (~18 days/month): 12 rangers*18 days/month = 216 ranger/day/month

Ron, T. 2015. Preliminary Assessment of eight National Parks and one Strict Nature Reserve for planning further Project and Government Interventions. Ministry of Environment, UNDP, EU, GEF; Ron, T. 2018. Report of the preliminary wildlife survey in the Maiombe National Park. National Biodiversity Project. Ministry of Environment (MINAMB), UNDP, GEF, EU.

In 2013-2018 47 individuals were arrested for illegal activities inside the park. 30 of them were from the Democratic Republic of Congo.

INBAC is going to increase the PA staff until 2020

We assume that at least 5 groups (6 rangers each) will patrol the Maiombe NP for 15 days (at least 8 hours of patrolling per day) each every month (or minimum 15 effective patrol man-days per month per ranger) (H. Jachmann, pers. comm.)

INBAC plans to have 120 rangers at the Luando SNR, however, it may not happen during the project timeline. Thus, we keep the end of the project number of rangers as 30 only that is more realistic.

We assume that at least 5 groups (6 rangers each) will patrol the Luando SNR for 15 days (at least 8 hours of patrolling per day) each every month (or minimum 15 effective patrol man-days per month per ranger) (H. Jachmann, pers. comm.)

Personal communication of the PPG team with the Maiombe NP staff in September 2018.

Our assumption based on the previous experience of ADPP and FAO on sustainable livelihood of local communities in Angola (at least 50-60% of 5,000-6,000 people in Maiombe NP the project will train under Output 3.1)

Our assumption based on the previous experience of ADPP and FAO on sustainable livelihood of local communities in Angola (at least 50-60% of 5,000-6,000 people in Luando SNR the project will train under Output 3.1)

Our assumption (at least 5% of the Maiombe NP)

Our assumption (at least 1% of Luando SNR)

Our assumption based on the previous experience of ADPP and FAO on sustainable livelihood of local communities in Angola

Law nº 3/14 about the criminalization of the infractions related to Money laundry, dated on February 10 2014

National Policy on Forests, Wildlife and Conservation areas dated on January 14 2010

The list will be updated at the project Inception Phase given the actual progress in the legislation improvement in the country.

The list needs to be updated at the project inception phase based on the situation

Presidential Decision No. 81/15 creating the Interministerial Commission Against Environmental Crimes and related Wild Fauna and Flora, 29 September 2015

Ron, T. 2012. Policia Verde Para a Fiscalização da Legislação para Conservação da Biodiversidade em Angola: Estatuto Orgânico Proposto Preliminar. MINAMB;  Ron, T. 2012 (updated, 2014). Policia Verde - Unidade Nacional de fiscalização do crime em vida selvagem. MINAMB

INBAC is going to increase the SNR staff up to 117

Distance sampling survey for three species – forest elephant, gorilla and chimpanzee – in the Maiombe NP can be designed by the WCS and /or JGI (e.g., Ms. Fiona Maisels fmaisels@wcs.org and Ms. Samantha Strindberg sstrindberg@wcs.org  of WCS or Lilian Pintea of JGI, LPintea@janegoodall.org;). It will require 40 2 km-long transects and appropriate training of the NP staff and national biologists as recommended by the Chapter 6 of the IUCN Ape Survey & Monitoring Book 2007. The training can be potentially provided by Mr. Ashley Vosper, ashley.vosper@gmail.com, JGI team, or other experienced wildlife biologist with strong experience of the distance sampling surveys in the Congo Basin.

Camera-trapping or occupancy survey in the northern portion of the Luando SNR can be potentially organized by Pedro vaz Pinto or other experienced wildlife biologists with involvement of the SNR rangers.

http://www.fao.org/agriculture/ippm/programme/ffs-approach/en/

http://www.adpp-angola.org/en/projects/agriculture-rural-and-economic-development/farmers-clubs

FAO 2107. Toolkit for the application of  Green Negotiated Territorial Development  (GreeNTD). https://www.researchgate.net/publication/316740200_Toolkit_for_the_application_of_Green_Negotiated_Territorial_Development_GreeNTD

ADPP 2017. Annual Report  http://www.adpp-angola.org/images/PDF/annual-report-en/ADPP-Angola-Annual-Report-2017-Eng-web.pdf

http://fas.co.ao/?s=ADECOS&lang=pt-pt

https://www.iucn.org/regions/eastern-and-southern-africa/our-work/conservation-areas-and-species/local-communities-first-line-defence-against-illegal-wildlife-trade-flod

Our assumption based on experience of ADPP, FAO, and FAS on sustainable livelihood development in Angola

Our assumption based on the previous experience of ADPP and FAO on sustainable livelihood of local communities in Angola (at least 50-60% of 10,000-12,000 people in Maiombe NP and Luando SNR the project will train under Output 3.1)

E.g., Loki Osborn, Connected Conservation (loki.osborn@gmail.com)

Distance sampling survey for three species – forest elephant, gorilla and chimpanzee – in the Maiombe NP can be designed by the WCS and /or JGI (e.g., Ms. Fiona Maisels fmaisels@wcs.org and Ms. Samantha Strindberg sstrindberg@wcs.org  of WCS or Lilian Pintea of JGI, LPintea@janegoodall.org;). It will require 40 2 km-long transects and appropriate training of the NP staff and national biologists as recommended by the Chapter 6 of the IUCN Ape Survey & Monitoring Book 2007. The training can be potentially provided by Mr. Ashley Vosper, ashley.vosper@gmail.com, or JGI team, or other experienced wildlife biologist with strong experience of the distance sampling surveys in the Congo Basin.

Camera-trapping or occupancy survey in the northern portion of the Luando SNR can be potentially organized by Pedro vaz Pinto or other experienced wildlife biologists with involvement of the SNR rangers.

Can be done using Global Forest Watch data 2018-2025 https://www.globalforestwatch.org/

UNDP 2016. Environmental and Social Screening Procedure

Ron, T. 2011. Towards a transboundary protected area complex in the Mayombe forest ecosystems.  Strategic Plan (5 years). With inputs from Angola, Congo, DRC, UNEP and IUCN. Adopted by the Mayombe Transfrontier Initiative's governments on March 2013.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.

National Policy on Forests, Wildlife and Conservation areas in Angola, dated on January 14, 2010

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

Screening is not required for projects (a) where UNDP serves only as the Administrative Agent, or (b) projects with outputs comprised solely of the following activities: report preparation, coordination of events/trainings/ workshops/meetings/conferences, or development of communication materials and dissemination of results (e.g. publications, media). See SESP, para. 7.

Determining feasibility of alternatives has several dimensions. Technical feasibility means the proposed measures and actions can be implemented with commercially viable skills, equipment and materials, taking into consideration prevailing local factors such as climate, geography, demography, infrastructure, security, governance, capacity and operational reliability. Financial feasibility means the ability to apply sufficient financial resources to install the measures and maintain them in operation in the long term.

Whenever feasible, preference should be given to projects, or project components, that are sited on lands already converted (e.g. not on natural habitats).

Disadvantaged or marginalized status may be due to such factors as race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority.

Refer to UNDP SES Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management, para. 12 regarding conditions and limitations on use of biodiversity offsets.

For example, the Environmental, Health, and Safety Guidelines (EHSGs), which are technical reference documents with general and industry-specific statements of Good International Industry Practice. The EHSGs contain information on industry- specific risks and impacts and the performance levels and measures that are generally considered to be achievable in new facilities by existing technology at reasonable cost. Available at www.ifc.org/ehsguidelines.

This may be particularly relevant where contractors are being engaged to carry out the project, or parts thereof, and the ESMP sets out the requirements to be followed by contractors. In this case the ESMP should be incorporated as part of the contract with the contractor, together with appropriate monitoring and enforcement provisions.