## Annex A:  Multi Year Work Plan

* Note that the indicators are tentative steps and should be reviewed and adjusted at Inception

| Output | Indicators * | Responsible Party | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Outcome 1: An enabling environment to mainstream integrated approaches into natural resource management in production sectors and landscapes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Draft ministerial directives and subsidiary agreements for special working arrangements between government agencies and administrations in the three Trial Landscapes | All technical papers describing and supporting project approach written | PMU MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Necessary directives prepared, signed by, endorsed and promulgated by Government | PMU, UNDP, MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2. Integrated Landscape Management and Mainstreaming Modules for institutions offering in-service and pre-service training of state employees | Review of lessons from landscape management and integrated planning from GEF 05 ESA and GCF projects |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training needs assessments done | UNDP PMU MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | In-service and pre-service training modules prepared by other projects evaluated and refined/upgraded and tailored for nine selected institutions | UNDP PMU MMDE |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |
|  | All selected institutions using the training modules | UNDP PMU MMDE |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |
| Output 1.3. Routine coordination established between the wide range of relevant development projects, programmes, and public and private sector initiatives operating in the same geographical area | Establishment of routine system of meetings with projects, programmes and public and private sector initiatives sharing the project landscape | UNDP PMU MMDE |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Establishment of routine coordination mechanism at district and divisional levels involving exchange of progress reports and work plans. | UNDP PMU MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Output 1.4. Recommendations and proposals for changes in policy, institutions or practice that will be required for replication of the landscape conservation design approach to mainstreaming nationally. | Gradual development of policy recommendations to facilitate scaling up of Project-led approaches nationally, based on demonstrations related to agriculture, fisheries, forestry and tourism in the field | UNDP PMU MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Guidelines on mainstreaming developed, initially using the experience of GEF 05 ESA Project and field tested under Output 2.4/ 3.4 to be developed into recommendations | UNDP PMU MMDE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Recommendations covering range of relationships between biodiversity and NRM, including for example, the trade-offs between "land sharing" and "land sparing" (see Prodoc Sections 1.4 and 4.2) for biodiversity conservation and livelihoods in the context of the Project. | UNDP PMU MMDE |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |
|  | Preparing policy prescriptions and tools to support land-use zoning approach and SEA (strategic environmental assessments) tested in the ESA Project to be improved for adoption in 2.2 and 2.3 | UNDP PMU MMDE | X | X | X | X |  |  |  |  |  |  | X | X | X | X |  |  |
|  | Specific policy recommendations regarding how to address biodiversity concerns related to international transboundary issues, climate change mitigation at landscape scale, and assessment of biodiversity impacts of irrigation projects | UNDP PMU MMDE |  |  |  |  |  |  |  |  | X | X | X | X | X | X |  |  |
| Outcome 2: Natural resource management, tourism and land use are guided by a strategic design for biodiversity conservation and sustainable livelihoods across multiple jurisdictions in three Trial Landscapes in the Northern and North Central Provinces |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1. Public information and involvement programme designed and implemented across all Districts and Divisional Secretariats represented in the Trial Landscapes | Design of the public information and involvement programme that will facilitate the preparation and implementation of the landscape strategies for the three TLs | UNDP PMU MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Public meetings and presentations held in districts, divisions and focal village clusters | PMU, UNDP, MMDE |  | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |
|  | Links to the programme under Focal Village Clusters (Output 3.1) which will begin after the TL programme | PMU, UNDP, MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Preparation of publicity materials - print and film | PMU, UNDP, MMDE |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Competitions and other forms of engagement | PMU |  | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |
|  | Guided visits to protected areas | PMU, MMDE |  |  | X | X | X | X | X | X | X | X | X | X |  |  |  |  |
|  | Mobile Education Unittouring the three TLs and District centres with films, presentations, and theatre targeted at the landscape level planning | PMU, UNDP, MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Development of Mannar Project office as a centre of excellence for information on Biodiversity (including Climate Change) | PMU, UNDP, MMDE |  |  | X | X | X | X | X | X | X | X | X | X |  |  |  |  |
| Output 2.2 Mechanisms for trans-jurisdictional and multi-sectoral consultations in the landscape conservation design process | Establishment of working arrangements with local government following up on Directives under Output 1.1 | PMU MMDE |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Finalize the trans-jurisdictional and multi-sectoral government interlocutors for the landscape | PMU MMDE |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Hold pilot meetings to test exactly how the Project will work with communities and government together | PMU MMDE |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Determine capacity needs in terms of GIS for example | UNDP PMU MMDE |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 Strategic conservation designs for each Trial Landscape for incorporation into government decision making and local development plans | Determination of the scope of each strategic design and preparation of full outlines | PMU MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Decisions on core planning teams for each TL - and the links between the teams for TL2 and TL3 and engagement with other donor funded projects operating in the TLs | PMU MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Agreement on the process for development of each TL strategic design, and assignments allocated, with the people responsible, and time table | PMU MMDE |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Formal agreements with District and lower level governments negotiated, for adoption of the final strategic designs in local Development Plans and decision making processes | UNDP PMU MMDE |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Data needs determined (See Section 4.2) | PMU,MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Necessary research and analysis done | PMU,MMDE |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | User-friendly GIS maps with advanced tools to facilitate landscape scale planning, and paper maps for easy use in remote villages | PMU, UNDP, MMDE |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Current and potential threats and constraints agreed upon by consensus | PMU, UNDP, MMDE |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Analysis of consequences of current policies and their implementation and recommendations for changes (alternatives) that could be implemented locally | PMU, UNDP, MMDE |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Definition of management actions required by responsible agencies and groups to implement recommended alternatives | PMU, UNDP, MMDE |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Identification of resource requirements: e.g. funds and funding sources, skilled personnel, equipment and facilities, training, public participation in management, information | PMU, UNDP, MMDE |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | Development of mechanisms and timetable for provision of resources | PMU, UNDP, MMDE |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | Preparation of a "living document" subject to periodic revisions, | PMU, UNDP, MMDE |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Review period, before joint agreement / ratification | PMU, UNDP, MMDE |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 Guidelines for mainstreaming biodiversity conservation into natural resource management, tourism and land use planning. | Review of existing governmental and community procedures (at both national and local levels) that regulate impacts on biodiversity, of tourism, agriculture, fisheries and forest management | PMU, UNDP, MMDE |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | Review of Technical Guidelines developed by GEF 05 ESA Project and improved/updated based on status quo and the TL strategic designs, for incorporation into local, and eventually national, regulations and normal practice: a) land use planning, b) tourism, c) infrastructure development, d) agriculture and fisheries e) forestry, f) protected area management | PMU, UNDP, MMDE |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | Consultation and production of guidance on certification of sustainablity in tourism, agriculture, fisheries and forestry. | PMU, UNDP, MMDE |  |  | X |  | X | X |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 Technical and material support for immediate actions required under the agreed strategic designs | Identification of, and consensus on, the actions to be supported under the Project and those to be the pursued by other organizatons | PMU, UNDP, MMDE |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | Integration of strategic design (Output 2.3) and mainstreaming guidelines (Output 2.4) into District (and lower level) development plans, routine decision making, local regulations, and proposed actions under donor-supported development projects and programmes. | PMU, UNDP, MMDE |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
|  | Interventions required under the strategies on land allocation for conservation, such as elephant corridors, and Environmentally Sensitive Areas | PMU, UNDP, MMDE |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |
|  | Achievement of reforestation targets whether through natural regeneration or planting | PMU, UNDP, MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Monitoring and regulation of tourist operations and tourist development proposals | PMU, UNDP, MMDE |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |
|  | Tourism green certification system tested | PMU, UNDP, MMDE |  |  |  |  |  | X | X | X | X | X | X | X |  |  |  |  |
|  | Monitoring and regulation of current and proposed practices (such as described in proposals for new developments) in fisheries, water management and agriculture | PMU, UNDP, MMDE |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X |
|  | Direct support to other donor-funded projects in the Project landscape to incorporate the agreed mainstreaming guidelines into those projects' work plans and modi operandi. | PMU, UNDP, MMDE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 3: Biodiversity conservation priorities shape sustainable livelihoods in natural resource management and tourism in six Focal Village Clusters in three Trial Landscapes in the Northern and North Central Provinces |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1. Public information and involvement programme designed and implemented in the focal village clusters | Focal village clusters identified through public involvement in 1.3 and 2.1 | PMU MMDE |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design of the public information and involvement programme focused on facilitation of the preparation and implementation of the six Focal Village Cluster Plans | PMU MMDE |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Close links with the wider Trial Landscape programmes under Output 2.1 through Public meetings and presentations held | PMU |  |  |  | X | X | X | X | X | X | X | X | X | X | X |  |  |
|  | School based activities that aim to (a) involve and inspire young people and (b) influence parents through their children | PMU |  |  |  | X | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Ecology clubs, nature watching clubs (both inside and outside school settings), guided visits to protected areas. (See Prodoc para 73) | PMU |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Competitions and other forms of engagement | PMU |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Mobile Education Unit (see above under Output 2.1) visits to the six Focal Village Clusters with films, presentations, photographs etc improving the effectiveness of inter community lessons sharing for community level planning (in collaboration with other similar projects operating in the area) | PMU, UNDP, MMDE |  |  |  |  | X | X | X | X | X | X | X | X | X | X |  |  |
| Output 3.2. Participatory mechanisms to bring together community and government stakeholders in a landscape conservation design approach to local land use planning | Wide consultation on best practice, followed by adoption of a plan and schedule for working arrangements ithat include the participation of Grama Niladharis and other local government officials, livelihood focused CBOs, women's groups, and youth organizations, and individual citizens and other interest groups both local and visiting. | PMU, MMDE |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Mapping of vulnerabilities and risks to inform the design, including poverty rates, female headed households and nutrition standards and disaster exposure | PMU, MMDE | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Formal meetings and workshops held to test the mechanisms for application under Output 3.4 | PMU, MMDE |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
|  | Informal, long term relationships to build up confidence, understanding and ownership of Project aims. | PMU, MMDE |  |  |  |  |  | X | X | X | X | X | X | X | X | X |  |  |
|  | Scoping of private sector and other development actors in the focal villages and TLs that have longer term stake in the area | PMU, MMDE | X | X |  |  | X | X |  |  | X | X |  |  |  |  |  |  |
| Output 3.3. Biophysical and socio-economic information required for analysis and reference before and during community-centred land-use planning | Collation and assessment of existing information and assessment of gaps | PMU, UNDP, MMDE | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparation of multidisciplinary research and monitoring plan covering biophysical and socio-economic data requirements | PMU, UNDP, MMDE | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Engagement with partners including international research organizations | PMU, UNDP, MMDE |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Implementation of the research and monitoring plans | PMU, UNDP, MMDE |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Output 3.4. Six village cluster land-use plans that provide opportunities for novel or modified livelihoods linked with biodiversity conservation | Determination of the scope of each Focal Village Cluster Plan and preparation of full outlines | PMU, UNDP, MMDE |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Decisions on core planning teams for each FVC, including links with the respective TL teams preparing the overarching Landscape strategic designs, and engagement with other donor funded projects operating in the FVCs | PMU, UNDP, MMDE |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Agreement on the process for development of each FVC land-use plan, and assignments allocated, with the people responsible, and time table | PMU MMDE |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Formal agreements with GND, DSD and local Land Use Planning Department Units negotiated, for adoption and/or acceptance of the completed plans in local government plans and and routine decision making | PMU, UNDP, MMDE |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | User-friendly GIS maps with advanced tools to facilitate landscape scale planning, and paper maps for easy use | PMU, MMDE |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make use of community based three dimensional mapping techniques for visualization of land use options and ecological flow and impacts | PMU, MMDE |  |  | X | X | X | X | X | X |  |  |  |  |  |  |  |  |
|  | Current and potential threats and constraints agreed upon by consensus | PMU, MMDE |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Analysis of consequences of current land use practice and the drivers of them, with reference to Project ThOCh analyses (Annex K) | PMU, MMDE |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Recommendations for alternative land use that could be implemented locally, and definition of actions required by individuals, community groups, and responsible agencies in order to implement recommended alternatives | PMU, MMDE |  |  |  |  | X | X |  |  | X | X |  |  | X | XX |  |  |
|  | Preparation of a "living document" subject to periodic revisions, | PMU, MMDE |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
|  | Review period, before joint agreement / ratification | PMU, MMDE |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
|  | Identification of resource requirements: e.g. funds and funding sources, skilled personnel, equipment and facilities, training, public participation in management, information for livelihood-focused interventions | PMU, UNDP, MMDE |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
|  | Development of mechanisms, engagement of partners, and a timetable for provision of resources, implementation of the plans, and establishment of working arrangements with potential investors in livelihood-focused interventions | PMU, UNDP, MMDE |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Output 3.5. Technical and material support for livelihood changes under the land-use plans in the fields of tourism and natural resource management | Technical and material support for novel or modified livelihoods in tourism, agriculture, fisheries, forestry and wildlife conservation (not yet defined in detail because that would pre-empt the planning process and its participatory and inclusive nature - see Prodoc 4.1 para 79). | PMU, MMDE |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Facilitation of links with private sector investors, provision of market advice | PMU, UNDP, MMDE |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Financial and technical support in selected interventions in areas such as: + Payments for Ecosystem Services + Ecological certification for agricultural produce, harvests of wild plants, fisheries, and tourism operations + Premium pricing for traditional varieties of rice + Conservation agreements, grants and co-management arrangements + Contributions towards the capital costs of well-planned mechanisms to avoid crop damage and livestock losses from wild animals (to replace compensation eventually). | PMU, UNDP, MMDE |  |  |  |  |  | X | X | X | X | X | X | X | X | X |  |  |
|  | Environmental and socio-economic impact assessments for all proposed interventions before approval followed by monitoring during implementation | PMU, UNDP, MMDE |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Vocational training carried out under the Project in support of specific livelihood-focused interventions. | PMU, UNDP, MMDE |  |  |  |  |  | X | X | X | X | X | X | X |  |  |  |  |
|  | Institutionalization of training locally (see Prodoc para 79) | PMU, MMDE |  |  |  |  |  |  |  |  | X | X | X | X | X | X | X |  |
| Outcome 4 Monitoring and evaluation, and dissemination of project methods and results contributes to wider application of landscape approach to mainstreaming of biodiversity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.1 Monitoring protocols and necessary institutional agreements to assess the impacts of the landscape conservation design and livelihood-focused interventions both during and after the end of the project | Finalization of the Project Results Framework and measurement of the indicator baselines that are still outstanding (Approval at Inception Workshop) | PMU, UNDP, MMDE | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Development of a monitoring plan based on PRF, and allocation of responsiblities through external contracts where necessary | PMU, UNDP, MMDE | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implementation of the monitoring plan | PMU, UNDP, MMDE |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Development of post-project monitoring protocols, necessary training, and agreements from institutions that will execute them | PMU, UNDP, MMDE |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X |
| Output 4.2 Periodic reviews and evaluations of monitoring data collected during the project | Annual reviews against the PRF, including for PIR when due | PMU, UNDP, MMDE |  |  |  | X |  | X |  |  |  | X |  |  |  | X |  |  |
|  | Biannual Technical Advisory Committee/Steering Committee meetings (in Colombo and in Project landscape) with intervening field visits by subgroups of the TAC/SC | PMU, UNDP, MMDE | X |  | X |  | X |  | X |  | X |  | X |  | X |  | X | X |
| Output 4.3 Publications, films, exhibitions, databases that publicize the methods used and the results of the project interventions | Development of master plan for the dissemination of Project messages and results, engagement in dialogue with stakeholders, and facilitation of replication in other landscapes | PMU, UNDP, MMDE | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Formation of links with similar projects in other countries followed by exchange of news and experience. For example, a Picture Story and video will be prepared in partnership with UNDP Ecosystems and Biodiversity. | PMU, UNDP, MMDE | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Project website, Project Twitter feeds and Project Facebook pages updated daily | PMU, UNDP, MMDE | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Databases that are made openly available on the Project website | PMU, UNDP, MMDE |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | A quarterly Project Newsletter reporting on activities, and addressing, through editorials and specialist articles, substantive related conservation issues each month. | PMU, UNDP, MMDE |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Publicity materials, for general public, for teachers and undergraduates, NGOs, press releases. | PMU, UNDP, MMDE |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Coordination of the use of Project products such as the guidelines to mainstreaming of biodiversity into natural resource management and tourism produced under Output 2.4 to pursue policy changes and policy implementation changes under Output 1.4. | PMU, UNDP, MMDE |  |  |  |  |  |  | X | X | X | X | X | X | X | X | X | X |
| Output 4.4 Organized visits by the public and by national and regional government officials to project sites to demonstrate and explain project activities and achievements | Overall plan prepared for visits | PMU, UNDP, MMDE | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Plan developed to fund visits from certain categories of people through grants. These might include journalists, writers, film-makers students | PMU, UNDP, MMDE | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Visits arranged for print and media journalists, specialist NGOs, writers, film-makers, students | PMU, UNDP, MMDE |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Visits arranged for: + National and regional government officials who will meet officials from other sectors and jurisdictions + Conservation NGOs, rural development NGOs, bilateral and multilateral aid organizations + Private sector companies and consortia | PMU, UNDP, MMDE |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |
|  | Exchange visits for Project beneficiaries with people in other areas of the Project landscape | PMU, UNDP, MMDE |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |
| Output 4.5 Talks and presentations by project staff in Colombo and in District and Provincial centres to explain project methods and results | An overall plan to cover all relevant forums | PMU, UNDP, MMDE | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Informal "training" for journalists, amateur or novice film-makers and teachers in the basics of mainstreaming, and biodiversity conservation outside protected areas, and biodiversity professionals in how to reach the public better. | PMU, UNDP, MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X |  |  |
|  | Regular conservation “salons” where talks by guest speakers will be followed by discussion sessions in conjunction with: + Media groups, + Private sector organizations such as Biodiversity Sri Lanka and the various Chambers of Commerce + Individual companies and business organizations + Government officials | PMU, UNDP, MMDE |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X |  |
|  | The Mobile Education Unit established with private-sector support and public collaboration that will tour the Project landscape will be tasked at intervals to travel to Colombo and other selected cities to set up a Project exhibition and to host Project speakers, in key sites, including University campuses and public parks. | PMU, UNDP, MMDE |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  |

http://pubs.iied.org/pdfs/9312IIED.pdf#page=72   (Chapter 11)

http://wwf.panda.org/homepage.cfm?10641/conservation-goes-3d