# Annex C:  Overview of Technical Consultancies

| Consultant | Time Input | Tasks, Inputs and Outputs |
| --- | --- | --- |
| For Project Management / Overall Technical Direction / Monitoring & Evaluation |  |  |
| Local / National contracting |  |  |
| Project Manager (PM) Duty Station: Project Landscape, with frequent travel to Colombo, Anuradhapura and all three Trial Landscapes Rate: US$ 2,250 per month | 48 months | The Project Manager (PM), together with the STA will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. |
| Senior Technical Adviser (STA) Duty Station: Project Landscape, with frequent travel to Colombo, Anuradhapura and all three Trial Landscapes Rate: US$2,250 per month | 48 months | The Senior Technical Adviser (STA) will be responsible for providing overall technical advice and management support to the entire Project. Will organize and participate in all aspects of the project, including the high level policy directives follow up in Outcome 1; oversee the development of landscape conservation designs, and guidelines for mainstreaming of biodiversity into natural resource management and economic development (Outputs 2.1, 2.2, 2.3, 2.4, 2.5) commissioning of biophysical and socio-economic research under Outputs 2.3 and 3.3. |
| Safeguards and Monitoring Officer- Part time Duty Station: Colombo Rate: US$ 1,500 per month (Cost to the project 750 USD per month) | 48 months (Part time. Cost shared with other projects) | Providing technical guidance on monitoring of project activities and safeguards to the project activities; support the annual reporting (PIR) processes and complete the tracking tools, especially carbon sequestration details. |
| Project Assistant Duty Station: Project Landscape Rate: US$ 500 per month | 48 months | Self-explanatory at this level - See Annex D for details |
| Finance and Procurement Officer Duty Station: Colombo with frequent travel to Project Landscape Rate: US$1,500 per month (only 750 USD per month will be charged to the project | 48 months (Part time. Cost shared with other projects) | Support the project implementation with financial accounting; maintaining all the financial records; Support annual auditing process; Lead procurement activities as per the guidelines accepted by the government, UNDP and the implementing partner; Prepare financial reports including quarterly financial progress reports for the project. |
| For Specific Technical Assistance |  |  |
| Across all Outcomes |  |  |
| Local / National contracting |  |  |
| Learning and Communication Officer Duty Station: Project Landscape, with frequent travel to Colombo, Anuradhapura and all three Trial Landscapes Rate: US$900 per month | 48 months | The Learning and Communication Officer (LCO) will be responsible for all information and involvement programmes under the Project, in particular the design and delivery of Outputs 2.1, 3.1, 4.3, 4.4 and 4.5, and will liase with all project officers and consultants, and with partners (projects and programmes) to deliver Output 1.3 Will maintain the Stakeholder Engagement Framework and draw up and implement the Project Knowledge Management and Communication Strategy |
| For Specific Technical Assistance |  |  |
| Outcome 1 |  |  |
| International / Regional and global contracting |  |  |
| Data and Modelling Expert Duty Station: Project Landscape, with travel to all three Trial Landscapes Rate: US$10,000 per month | 3 months. 6 weeks in Year 1 (outcome 1) and 6 weeks in Year 4 (outcome 4) | Identify key features of the landscape that can be quantified and used for developing models that will enable the decision makers to compare different possible scenarios with different project approaches and input levels; develop user friendly model usage instructions; Support the project to develop monitoring mechanisms of different model inputs; Support the Senior Technical Advisor to develop landscape models and approaches. |
| Local / National contracting |  |  |
| Training Needs Assessor Duty Station: Colombo, with travel as necessary Rate: US$ 750 per month | 6 months (Year 1) | Under close supervision of Senior Technical Adviser (STA) and Project Manager (PM) carry out training needs assessment for mainstreaming of biodiversity and compare, using Gap Analysis, with training currently available in government in-service and pre-service training institutions and in universities (Output 1.1). |
| Curriculum Developer Duty Station: Colombo, with travel as necessary Rate US$750 per month | 12 months (Years 1,2) | Under close supervision of Senior Technical Adviser (STA) and Project Manager (PM) and in collaboration with the Training Needs Assessor, develop modules and mechanisms to fill the gaps demonstrated in the Training Gap Analysis and train teachers in their use (Output 1.2) |
| Additional consultancies required for delivering the training programmes | 1-2 months each for consultancies as required | Technical and training experts who would deliver the training programmes required for the project |
| Outcome 2 |  |  |
| Local / National contracting |  |  |
| International / Regional and global contracting |  |  |
| International Landscape Conservation Advisor (ILCA) Duty Station: Project Landscape, with travel to all three Trial Landscapes Rate: US$ 10,000 per month | 2 months over 4 years | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA) and respective Community-based Conservation Experts (ILCA, will provide international perspective, strategic guidance and technical inputs to the implementation of activities under Outputs 2.1, 2.2, 2.3, 2.4, 2.5. |
| International Ecotourism & Biodiversity Business Development Advisor Duty Station: Project Landscape, with travel to all three Trial Landscapes Rate: US$ 10,000 per month | 2 months in Year 2 (0.5 months from outcome 2 annd 1.5 months from outcome 3) | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA) the Community-based Conservation Experts (CCE), and the Learning and Communications Officer (LCO), and the three Community-based Conservation Experts (CCE) will provide international perspective, strategic guidance and technical inputs to the implementation of activities under Outputs 2.3,3.1, 3.2, 3.3, 3.4 and 3.5. |
| Eight to ten short term consultants: including specialists in tourism; agriculture; fisheries; biodiversity; analysing socio-economic development of the landscape; gender integration; Sustainable Forest Management; Innovative finance mechanisms for conservation finance; Livelihoods development and others Duty Stations: TBD according to needs Rate: US$100 - 200 per day depending on duration of contract | As required: estimated one to two months per year for between one and four years | Specific tasks as required |
| Outcome 3 |  |  |
| Local / National contracting |  |  |
| Upper Malwathu Community-based conservation expert (UMCCE) Duty Station: Ritigala Rate: US$1,400 per month | 48 months | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA) and the Learning and Communications Officer (LCO), will oversee, in Trial Landscape 1, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5) |
| Lower Malwathu Community-based conservation expert (LMCCE) Duty Station: Madhu Rate: US$1,400 per month | 48 Months | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA and the Learning and Communications Officer (LCO), will oversee, in Trial Landscape 2, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5) |
| Malwathu Estuary Community-based conservation expert (MECCE) Duty Station: Arippu Rate: US$1,400 per month | 48 months | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA) and the Learning and Communications Officer (LCO), will oversee, in Trial Landscape 3, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5) |
| Three short term consultancies on Land use mapping including bio cultural and heritage sites / spatial features, Eco system carrying capacity assessment, Value and market chain identification and development | As required: estimated one to two months per year for between one and four years | Specific tasks as required |
| International / Regional and global contracting |  |  |
| Eco Tourism and Biodiversity Business development Adviser Duty Station: Project Landscape, with travel to all three Trial Landscapes Rate: US$10,000 per month | 2 months in Year 2 (0.5 months from outcome 2 and 1.5 months from outcome 3) | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA) the Community-based Conservation Experts (CCE), and the Learning and Communications Officer (LCO), and the three Community-based Conservation Experts (CCE) will provide international perspective, strategic guidance and technical inputs to the implementation of activities under Outputs 2.3,3.1, 3.2, 3.3, 3.4 and 3.5. |
| Outcome 4 |  |  |
| Local / National contracting |  |  |
| Senior Technical Adviser | [48 months ] | See above at top, under Project Management/Monitoring and Evaluation |
| Impact monitoring specialist Duty Station: Project Landscape, with travel to all three Trial Landscapes Rate: US$1,000 per month | 12 months over four years | Review project documents and in close coordination with the Project Manager (PM) and the Senior Technical Adviser (STA) prepare project impact monitoring framework in line with GEF requirement. Advice on improving the output level indicators for better capture project delivery. Provide social and environmental impact monitoring of field level activities and advice the project manager in reporting the same (Outputs 4.1 and 4,2) |
| Communications Strategy and product development Duty Station: Colombo with travel to all three Trial Landscapes Rate: US$ 1,500 per month | 12 months | The project is piloting an innovative approach and its success as well as the impact will depend on the ability to communicate its objectives, achievements and impacts clearly to the targeted stakeholders. This position will play a pivotal role in identifying different target audiences, develop communication strategies for different key stakeholders, develop communication plans ensuring the efficient resource utilization; identify different information, communication and education products required to different target audiences and support the project to develop the relevant products in a timely manner; Support the project to disseminate the messages using different media including social and mass media available in the country. |
| Expert for Mid Term Evaluation (Local) Duty Station: Colombo with travel to all three Trial Landscapes Rate: US$ 10,000 per month | 1 month | Work in collaboration with the International Expert to review the project outcomes against the project document and advice the project board on best possible ways to ensure the achievement of project objectives; Assess the opportunities, threats, weaknesses and strengths of the project after two years of implementation and recommend revisions to the project approach if necessary. |
| Expert for Terminal Evaluation (Local) Duty Station: Colombo with travel to all three Trial Landscapes Rate: US$ 7,500 per month | 2 months | Work in collaboration with the International Expert to assess the level of achievement related to project objectives; assess the comparative strengths and weaknesses of the project; Review the project outputs and assess the efficiency, effectiveness, relevance and sustainability of the project approaches. |
| International / Regional and global contracting |  |  |
| Data and Modelling Expert Duty Station: Project Landscape, with travel to all three Trial Landscapes Rate: US$10,000 per month | 3 months. 6 weeks in Year 1 and 6 weeks in Year 4 | Identify key features of the landscape that can be quantified and used for developing models that will enable the decision makers to compare different possible scenarios with different project approaches and input levels; develop user friendly model usage instructions; Support the project to develop monitoring mechanisms of different model inputs; Support the Senior Technical Advisor to develop landscape models and approaches. |
| Expert for Mid Term Evaluation Duty Station: Colombo with travel to all three Trial Landscapes Rate: US$ 10,000 per month | 1 month | Review the project outcomes against the project document and advice the project board on best possible ways to ensure the achievement of project objectives; Assess the opportunities, threats, weaknesses and strengths of the project after two years of implementation and recommend revisions to the project approach if necessary. |
| Expert for Terminal Evaluation Duty Station: Colombo with travel to all three Trial Landscapes Rate: US$ 10,000 per month | 2 months | Assess the level of achievement related to project objectives; assess the comparative strengths and weaknesses of the project; Review the project outputs and assess the efficiency, effectiveness, relevance and sustainability of the project approaches. |