# Annex C:  Overview of Technical Consultancies

| Consultant | Time Input |  | Tasks, Inputs and Outputs |
| --- | --- | --- | --- |
| For Project Management and Overall Technical Direction |  |  |  |
| Local / National contracting |  |  |  |
| Project Manager (PM) Duty Station: Mannar, with frequent travel to Colombo, Anuradhapura and all three Trial Landscapes Rate: US$2,250 per month | 48 months |  | The Project Manager (PM), together with the Senior Technical Adviser (STA) will be responsible for the overall management of the project, including the mobilization of all project inputs, supervision over project staff, consultants and sub-contractors. |
| Senior Technical Advisor (STA) Duty Station: Mannar, with frequent travel to Colombo, Anuradhapura and all three Trial Landscapes Rate: US$2,250 per month | 48 months (nominally 4 months under Project Management, and 44 months under the individual Outcomes - see below) |  | The Senior Technical Adviser (STA) will be responsible for providing overall technical advice and management support to the entire Project. Will take the lead in particular on the Landscape Conservation Design (Outcome 2), but will organize and participate in all aspects of the project, including the commissioning and oversight of biophysical and socio-economic research under Outputs 2.3 and 3.3, and the oversight of the work of other Project staff engaged primarily under Outcomes 1, 3 and 4. |
| Project Officer (PO) Rate US$1,500 per month | 48 months part time; |  | The Project Officer will assist with project assurance and project management at the Colombo base, Support the Project Manager and Senior Technical Advisor in monitoring of the project activities; providing technical guidance on incorporation of gender and social inclusiveness aspects and overall safeguards to the project activities |
| Project Assistant (PA) Rate: US$1,200 per month | 48 months |  | The Project Assistant and Interpreter will assist in the PMO and at the field sites in administrative, practical tasks as well as with a reasonable amount of translation and interpretation when required. |
| Finance and Procurement Officer (FPO) Rate: US$1,500 per month. (Cost sharing basis- only 750 US$ per month will be charged to the project). | 48 months |  | The FPO will support project implementation with financial accounting; maintaining all the financial records; supporting the annual audit; implementing procurement in collaboration with the Project Manager according to the applicable guidelines; preparing financial reports |
| For Specific Technical Assistance |  |  |  |
| Across all Outcomes |  |  |  |
| Local / National contracting |  |  |  |
| Learning and Communications Officer (LCO) Duty Station: Mannar, with frequent travel to Colombo, Anuradhapura and all three Trial Landscapes Rate: US$1200 per month | 48 months |  | The Learning and Communications Officer (LCO) will be responsible for all information and involvement programmes under the Project, in particular the design and delivery of Outputs 2.1, 3.1, 4.3, 4.4 and 4.5, and will liaise with all project officers and consultants, and with partners (projects and programmes) to deliver Output 1.3 Will maintain the Stakeholder Engagement Framework and draw up and implement the Project Knowledge Management and Communication Strategy |
| Eight to ten short term consultants Duty Stations: TBD according to needs Rate: US$1500 to US3000 per month pro rata depending on qualifications and duration of contract | As required: estimated one to two months per year for between one and four years |  | Specific tasks as required. Will include specialists in tourism, agriculture, forestry, fisheries, birds, elephants, sociology, gender, meeting facilitation and others |
| For Specific Technical Assistance |  |  |  |
| Outcome 1 |  |  |  |
| Local / National contracting |  |  |  |
| Training Needs Assessor (TNA) Duty Station: Colombo, with travel to Mannar and Arunadhapura as necessary Rate: US$ 1,600 per month | 6 months (Year 1) |  | Under supervision of Senior Technical Advisor (STA) and Project Manager (PM) carry out training needs assessment for mainstreaming of biodiversity and compare, using Gap Analaysis, with the training currently available in government in-service and pre-service training institutions and in universities (Output 1.1). |
| Curriculum Developer (CD) Duty Station: Colombo, with travel to Mannar and Arunadhapura as necessary Rate US$1,600 per month | 12 months (Six months per year in Years 1,2) |  | Under supervision of Senior Technical Advisor (STA) and Project Manager (PM) and in collaboration with the Training Needs Assessor (TNA), develop modules and mechanisms to fill the gaps demonstrated in the Training Gap Analysis and train teachers in their use (Output 1.2) |
| Outcome 2 |  |  |  |
| Local / National contracting |  |  |  |
| International / Regional and global contracting |  |  |  |
| International Landscape Conservation Advisor (ILCA) Duty Station: Mannar District, with travel to all three Trial Landscapes Rate: US$ 10,000 per month (inclusive) | 2 months (2 months Year 2) |  | In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA) and the Landscape Conservation Planner (LCP), will provide international perspective, strategic guidance and technical inputs to the implementation of activities under Outputs 2.1, 2.2, 2.3, 2.4, 2.5. |
| Outcome 3 |  |  |  |
| Local / National contracting |  |  |  |
| Upper Malwathu Community-based conservation expert (UMCCE) Duty Station: Ritigala Rate: US$1,400 per month | 48 months |  | In close coordination with the Project Manager (PM), the SeniorTechnical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA), the Landscape Conservation Planner (LCP) and the Learning and Communications Officer (LCO), will oversee, in Trial Landscape 1, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5) |
| Lower Malwathu Community-based conservation expert (LMCCE) Duty Station: Madhu Rate: US$1,400 per month | 48 months |  | In close coordination with the Project Manager (PM), the SeniorTechnical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA), the Landscape Conservation Planner (LCP) and the Learning and Communications Officer (LCO), will oversee, in Trial Landscape 2, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5) |
| Malwathu Estuary Community-based conservation expert (MECCE) Duty Station: Arippu Rate: US$1,400 per month | 48 months |  | In close coordination with the Project Manager (PM), the SeniorTechnical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA), the Landscape Conservation Planner (LCP) and the Learning and Communications Officer (LCO), will oversee, in Trial Landscape 3, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5) |
| International / Regional and global contracting |  |  |  |
| Outcome 4 |  |  |  |
| Local / National contracting |  |  |  |
| Mid-term Review Consultant Duty Station: Home based with one trip to Colombo, Mannar, Arundhapura and selected field sites Rate: US$10,000 inclusive | ca 1 month | Review the Project results against the project document and advise the project board on best possible ways to ensure the achievement of the project objective; Assess the opportunities, threats, weaknesses and strengths of the project after two years of implementation and recommend revisions to the project approach if necessary. |  |
| Terminal Evaluation Consultant Duty Station: Home based with one trip to Colombo, Mannar, Arundhapura and selected field sites Rate: US$15,000 inclusive | ca 1 month | Assess the level of achievement against project objective and outcomes; Assess the comparative strengths and weaknesses of the project and make recommendations for future interventions |  |
| International / Regional and global contracting |  |  |  |
| Mid-term Review Team Leader Duty Station: Home based with one trip to Colombo, Mannar, Arundhapura and selected field sites Rate: US$20,000 inclusive | ca 1 month | Review the Project results against the project document and advise the project board on best possible ways to ensure the achievement of the project objective; Assess the opportunities, threats, weaknesses and strengths of the project after two years of implementation and recommend revisions to the project approach if necessary. |  |
| Terminal Evaluation Consultant Duty Station: Home based with one trip to Colombo, Mannar, Arundhapura and selected field sites Rate: US$30,000 inclusive | ca 1 month | Assess the level of achievement against project objective and outcomes; Assess the comparative strengths and weaknesses of the project and make recommendations for future interventions |  |