## Annex D: Terms of Reference for long term (20 months or over)  positions

(Terms of Reference for short term consultants (see Annex C) to be developed by Senior Technical Advisor and Project Manager as required during Project implementation)

Terms of Reference for the Project Board

The Project Board (PB) will serve as the project’s decision-making body.  It will be chaired by the Secretary, Ministry of Mahaweli Development and Environment (MMDE) and will meet at least twice each year (usually in Colombo, but when the opportunity arises, in Mannar or Arunadhapura) to review Project progress, sign off on  Project annual work plans, and endorse major project Outputs. The PB is responsible for providing  strategic guidance and oversight during Project implementation, ensuring that progress is made towards the Project Objective and Outcomes, and approving any adaptive management measures that become necessary.

The PB’s responsibilities include:

- Provide strategic guidance to project implementation;

- Ensure coordination between various donor funded and government funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Approve annual project work plans and budgets proposed by the Project Manager;

- Approve any major changes in project plans or programmes;

- Oversee monitoring, evaluation and reporting in line with GEF requirements;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Negotiate solutions between the project and any parties beyond the scope of the project;

- Ensure that UNDP Social and Environmental Safeguards Policy is applied throughout project implementation; and, address related grievances as necessary.

These terms of reference will be finalized during the Project Inception Workshop.

Terms of Reference for the Technical Advisory Committee (TAC)

The TAC will provide technical advice and inputs related to project implementation and will be chaired by the Project Director (PD).   Meetings will be called as required, but at least three times per year, and will be held, more or less alternately, in Colombo and in the Project landscape.  The members of the TAC will consist of Government Ministers or their representatives, and representatives of UNDP, other relevant government agencies, research and educational organizations, NGOs, technical experts and other stakeholders to be coopted with the agreement of the Project Board. Technical experts may be invited in to discuss specific issues.

Indicative Terms of Reference are as follows. These will be reviewed by the Project Board during project inception and may be extended as necessary.

- Review planned activities and ensure that they are technically sound and that, wherever possible, there is integration and synergy between the various project components during planning and implementation;

- Promote technical coordination between institutions, where such coordination is necessary and where opportunities for synergy and sharing of lessons exist;

- Provide technical advice and guidance on specific issues concerning agriculture, tourism, fisheries, protected area systems and forestry;

- Share information on project progress and lessons learned with relevant stakeholders at national and subnational levels;

- The TAC or a subset of its members may be requested to undertake specific project-related tasks, such as preparing or reviewing analytical reports, strategies and action plans, etc. and such tasks may involve work in the field;

- Other tasks as indicated by the Project Board

Terms of Reference for Key Project Staff

Project Director (PD)

Appointment Duration: 48 months, full time

Duty Station: Colombo, with visits to Project Office in Mannar and the three Trial Landscapes as required

Background

The Project Director (PD) is a nominee of the Ministry of Mahaweli Development and Environment (MMDE), who will be accountable to the MMDE and to UNDP for the achievement of the Objective and Outcomes of the Project.  The PD will serve as a member of the Project Board and will chair the Technical Advisory Committee.  The PD will be financed through national government funds (co-financing), and will be appointed by the Secretary, MMDE, in consultation with UNDP CO.

Duties and Responsibilities

- Serve as a member of the Project Board.

- Keep track of progress towards the Project Objective and Outcomes

- Maintain overall responsibility for Project expenditures in such a way that funds are disbursed efficiently according to the agreed Project financial and implementation arrangements

- Ensure compliance of Project implementation with the signed Project Document and any subsequent modifications agreed by the Board.

- Facilitate coordination with other projects, organizations and institutions that will conduct related activities (see under Partnerships in Prodoc Section 4.2)

- Participate in Project review, evaluation, fact-finding and monitoring missions.

- Ensure that the necessary government directives for working arrangements between local government, local residents and the Project are in place by the time of Project Inception

- Coordinate with national governmental representatives on legal and financial aspects of Project activities.

- Coordinate, facilitate and supervise planned government staff inputs to Project implementation.

- Stimulate and initiate additional inputs from government agencies to Project implementation if and when they are relevant to achievement of the Objective and Outputs.

- Coordinate, oversee and report quarterly on government cofinancing inputs to Project implementation, and take action to follow up on shortfalls in or delays to promised co-finance.

## Project Manager (PM)

Appointment Duration:  48 months, full time

## Duty Station: Project Office in Mannar, with travel to Colombo, Arunadhapura, and Trial Landscapes as required

Background

The Project Manager (PM), will be locally recruited, with input to the selection process from the Project partners, and will be funded entirely from Project funds. The PM will be responsible for the overall management of the Project, including the mobilisation of all project inputs, and the supervision of project staff, consultants and sub-contractors.  The PM, in consultation with the Senior Technical Advisor and the assigned UNDP Country Office Project Officer, will report to the PD on all substantive and administrative issues related to the Project.  These reports will be both at and between meetings of the Project Board.  Generally, the PM will provide support to the PD who takes overall responsibility for meeting government obligations under the Project.    The PM, with the support of the Senior Technical Advisor and the Learning and Communications Officer (LCO), will liaise with government, UNDP and other UN agencies, NGOs, and project partners, and maintain close collaboration with all agencies providing co-finance.   He or she will make an overarching written and verbal report at each meeting of the PB and the TAC,  incorporating technical contributions and assessments from Project staff and consultants.

The Project Manager will remain on contract until the Terminal Evaluation report and the corresponding management response have been finalized and the required tasks for operational closure and transfer of assets are fully completed

Duties and Responsibilities

- Coordinate and take part in Project planning with the other Project staff, consultants, and stakeholders

- Coordinate and oversee the provision of Project inputs. Active support will be provided to the PM by the STA, the LCO, the three CCEs, the Project Assistant and Interpreter (PAI), and the assigned Country Office Project Officer (COPO) for the following specific tasks:

  - a) recruitment and selection of Project staff and consultants and the issuing of sub-contracts, including drafting terms of reference and work specifications

  - b) monitoring the performace of all project staff, consultants and sub-contractors through on-the-job visits, reporting and informal and formal meetings

  - c) ordering and supply of equipment, printed matter and audio-visual resources

  - d) provision of necessary administrative and logistical support to consultants, sub-contractors, Project staff, Project visitors and TAC members

  - e) oversight of travel arrangements for all project activities, ensuring adherence to safety procedures without exception

- Manage requests for the provision of financial resources under NIM, through advance of funds via MMDE, direct payments from UNDP, or reimbursement according to the established procedures.  This will involve setting up and operating a system for quarterly reporting (Finance and Technical) and quarterly advance requests (Financial), and work plans (Technical) that works smoothly on a decentralized project far from the capital yet meets the requirements of UNDP NIM, and it will require the active support of the PD, the CO Project Officer  and all Project field staff.

- Coordinate and oversee the production of project Outputs, and keep track of progress against the approved work plans

- Ensure that all required Project reports (including, but not limited to, Inception Report, Annual (from Year 2) Project Implementation Reports, Monthly Reports, Mid-Term and Terminal Reports)  are produced on time with all required input from the persons responsible (e.g. STA), and submitted or disseminated as planned, again by the persons responsible (e.g. LCO).

- Keep track of financial resources through oversight of the work of the Project Finance and Procurement Officer.

- In collaboration with the STA, the PD and the LCO, liaise as appropriate with UNDP, government agencies, the Project Board, donor agencies, NGOs and research and educational institutions.

- Respond to queries from stakeholders and the general public, and, if necessary, refer people on to the STA, the LCO, the CO Project Officer or others as appropriate

- Oversee the exchange and sharing of experiences and lessons learned with relevant community based integrated conservation and development projects nationally and internationally.

- Organize and hold half-yearly Project learning workshops that rotate between Project sites and Colombo and facilitate intra-project exchanges of ideas and experience

Qualifications, skills and experience

- A postgraduate degree (MSc or PhD).  If in a subject relevant to natural resource management or biodiversity conservation, it would be an advantage.

- At least 8 years of project management experience.  If in project(s) relevant to natural resource management or biodiversity conservation, it would be an advantage.

- At least 3 years of experience working with Sri Lankan Government Ministries and/or national or provincial institutions that are concerned with natural resources, environmental management and issues affecting biodiversity conservation

- Strong leadership, managerial and coordination skills, with a demonstrated ability to effectively coordinate the implementation of large multi-stakeholder projects, including financial and technical aspects.

- Ability to effectively manage technical and administrative teams, work with a wide range of stakeholders across various sectors and at all levels, to develop durable partnerships with collaborating agencies.

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project.

- Ability to coordinate and supervise a Project operating with field staff in several different locations in their implementation of technical activities in partnership with a variety of stakeholder groups, including community and government.

- Strong drafting, presentation and reporting skills.

- Strong communication skills, especially in timely and accurate responses to emails.

- Strong computer skills, in particular mastery of all applications of the MS Office package and internet search.

- Excellent command of both spoken and written English and Sinhala and, preferably at least a working knowledge of Tamil.

## Senior Technical Adviser (48 months, full time)

## Duty Station: Project Office in Mannar, with travel to Colombo, Arunadhapura, and Trial Landscapes as required

Background

The Senior Technical Adviser (STA) will be responsible for providing overall technical advice to the entire Project, and will also provide specific technical and management support to the PM during planning, recruitment, sub-contracting, procurement, performance monitoring and reporting.   The STA will, through coordination with the PM, the three CCEs, assigned CO Project Officer and the LCO, variously organize, oversee, and participate in, diverse aspects of the project, including landscape conservation design (see more on this below), commissioning of biophysical and socio-economic research, community-based conservation, livelihood-focused interventions for biodiversity conservation, monitoring of Project impacts, and dissemination of knowledge.  The Project Assistant and Interpreter will provide substantial support to the STA.

Duties and Responsibilities

- Provide technical advice related to all Outputs and Outcomes of the Project and support other Project staff in establishing a commonly held vision for the Project's landscape conservation design and mainstreaming approach

- Prepare a guide to the rationale, scope and targets of the landscape conservation design and how it should be implemented under the Project, and present it at initial workshops on landscape design and community based conservation planned under the Project in Colombo, Anuradhapura and Mannar

- Work with the Project Manager, the Project Director, the LCO, the three CCEs and UNDP CO to develop an effective strategy for ensuring (a) appropriate public involvement and (b) that the eventual landscape conservation design is accepted and followed by all relevant government agencies, non-governmental organizations and members of the public.

- With the support of, the Project Manager, the International Landscape Conservation Design Adviser (ILCA), the Learning and Communications Officer (LCO), the Landscape Conservation Planner (LCP),  and the three Community Conservation Experts (CCE), take the lead on guiding the landscape design process (Outputs 2.1 to 2.3) including necessary data collection and analysis, oversee the development of mainstreaming guidelines (Output 2.4),  facilitate acceptance of the resultant design and incorporation of design and guidelines into the institutional and routine decision making of government (under Output 2.3), and oversee partial implementation of the design through project and other interventions (Output 2.5).

- Provide technical support and guidance to the three Community Conservation Experts on Focal Village Cluster planning (Outcome 3) and, together with the Project Manager, the LCP and the LCO to coordinate the synergies between Outcomes 2 and 3

- Take a lead role, together with the PM, the PD and the UNDP CO Project Officer, in coordination of Project activities with parallel activities of the wide range of relevant development projects, programmes, and public and private sector initiatives operating in the same geographical area (Output 1.3)

- Contribute directly in areas of expertise to training courses, workshops, on-the-job training, technical meetings and internal UNDP CO and MMDE and other relevant agencies' capacity development and coordination briefings

- Oversee and participate in the project and project staff work planning processes at all levels.  Support the Project Manager with technical advice and assessments in preparation and submission of (a) quarterly and annual (including PIR) progress reports, (b) quarterly advance requests and work plans

- Take a lead role with the Project Manager in decisions on procurement, including the preparation of Terms of Reference, the selection and recruitment of project consultants, the awarding of sub-contracts, and the development of Memoranda of Understanding where required to coordinate the contributions of NGOs

- Provide technical support to the PM in the supervision of project staff, consultants and subcontractors, in review and quality assurance of all Project technical reports, analyses, proposed training programmes, public information and advocacy material, stakeholder engagement plans, SRF and Core Indicator monitoring reports, and other documents prepared by Project staff, consultants and research teams.

- Establish contacts and links with relevant organizations, research and educational institutions, networks and individuals outside the project and encourage project staff to follow up where appropriate.  In particular, with the support of the ILCA, build links with sources of relevant knowledge and experience regarding biodiversity conservation practices, through global and regional networks.

- Participate in and report at Project Technical Advisory Committee meetings and Project Board meetings in Colombo and in the Trial Landscapes

- Prepare and deliver presentations and reports on the Project at donor coordination and regional meetings and workshops in coordination with the Project Board, the PM and the PD

Qualifications, Skills and Experience

- Master's degree in a field relevant to environmental or natural resources management;

- At least fifteen years of work experience related to biodiversity conservation and rural development, preferably in a project management setting involving a multi-lateral/ international funding agency. Previous experience with UN project will be a definite asset;

- Significant experience in collating, analyzing and writing up results for reporting purposes;

- Very good knowledge of results-based management and project cycle management, particularly with regards to M&E approach and methods.

- Knowledge of and experience in developing and implementing environmental and social safeguard strategies for organizations or projects

- Understanding of biodiversity conservation, law enforcement and sustainable livelihoods

- Very good inter-personal skills and initiative

- Able to work in uncomfortable rural, and remote conditions

- Proficiency in computer application and information technology.

- Excellent language skills in English and Sinhala (writing, speaking and reading) and knowledge of Tamil an advantage.

- Demonstrated understanding of the links between sustainable development, social and gender issues;

- Excellent analytical, writing, advocacy, presentation, and communications skills.

Country Office Project Officer

Appointment Duration:  48 months, one third of the time spent on this project i.e. 4 months per year for four years and full time for the last quarter- In total 17 months)

## Duty Station: UNDP Country Office with frequent travel to the PMO

Background

In order to ensure high quality project assurance by UNDP CO, this position will be based in Colombo and provide a liaison role between the PMU, project implementation responsible partners and the government. In addition s/he will facilitate advocacy activities at the highest levels of government, and with other donors and agencies.

1.   Project Assurance

- Rigorous technical review of quarterly advance requests and quarterly reports

- Ensuring that environmental and social risks are identified, avoided, mitigated and managed throughout project implementation, through rigorous environmental and social assessments of all proposed Project interventions before approval under the workplan;

- With the support of the STA and the MEO, ensure the implementation of the project’s M&E plan, including periodic appraisal of the Project’s Theory of Change, and Results Framework, with reference to actual and potential project progress and results;

- Encourage staff, partners and consultants such that strategic, intentional and demonstrable efforts are made to actively include women, people with disabilities and other socially marginalized groups in the project, including activity design and planning, budgeting, staff and consultant hiring, subcontracting, purchasing, formal community governance and advocacy, outreach to social organizations, training, participation in meetings; and access to program benefits.

- Ensure that reporting, monitoring and evaluation fully address the gender and safeguard issues of the project;

- Monitor progress in implementation of the project Gender Action Plan ensuring that targets are fully met and the reporting requirements are fulfilled;

- Oversee/develop/coordinate implementation of all safeguard-related plans;

- Monitor and update the status of the all project risks in the Risk Log (Annex H)

- Submit new risks, if they arise, to the Project Board for consideration and decision on any actions required

- Review the Social and Environmental Screening Procedure and Action Plan annually, update and revise the corresponding Risk Log (see immediately above), and propose to the PB and TAC mitigation and management plans as necessary;

- Monitor progress in implementation of the project ESMP ensuring that UNDPs SES policy is fully met and the reporting requirements are fulfilled;

- Ensure social and environmental grievances are managed effectively and transparently;

- Ensure full disclosure with concerned stakeholders;

- Carry out announced and unannounced inspections of all sites and the activities of the Project

2.  Project Management

- Assist the PM with recruitment as required

- Manage requests for the provision of financial resources by the Implementing Partner, through advance of funds, direct payments, or reimbursement

- Facilitate smooth links between PMU, MMDE, IUCN and UNDP Regional Office in Bangkok

- Support the Project Director in maintaining close coordination between project’s  external partners such asthe SLTDA, GIZ, ESCAMP and private sector

- Take part in networks of UNDP-GEF personnel and project staff in other countries, in particular to exchange information, ideas, experiences, lessons learned and information

- Support the LCO in facilitating proper communication and coordination between project initiatives in different places and between project staff, consultants and subcontractors where appropriate

- Participate, where appropriate, in meetings and working groups relevant to the project's objectives

- Disseminate project reports and respond to queries, with the support of Project staff, from concerned stakeholders.

- Follow up on recommendations made at PB meetings

- Take the lead on arrangements and logistics for the Mid-term Review and the Terminal Evaluation of the Project;

- With the support of the MEO, the PM and the PD ensure that the Project's monitoring protocols will be continued with sustained funding post-project so that the impacts of the Landscape Conservation Design approach can be tracked over a useful time period

## Upper Malwathu Community-based conservation expert (UMCCE  )

Duty Station:  Ritigala  FVC  48 pm

In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA), the Landscape Conservation Planner (LCP) and the Learning and Communications Officer (LCO), the UMCCE will oversee, in Trial Landscape 1, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5)

- Organize and implement with the LCO a public information and involvement programme in the selected Focal Village Clusters of TL1 so that the general public and community based organizations understand and embrace the aims of the Project (Output 3.1)

- Slowly get to know the local community and its environs and carry out a public consultation to inform people about the landscape design and the FVC land-use plans and answer questions that people have

- Collect opinions regarding people's understanding of the impacts that

a) they themselves and b) others

have on biodiversity and ecological services and what impacts they might have in the future both locally and further afield (through pollution or overuse of water for example), including on vegetation, on wild species of plants and animals

- Design, with local stakeholders, Project staff and consultants, and with the input of relevant organizations a process to engage slowly and patiently over the whole project period as a resident, with individuals and organizations in the community and local government officials (Output 3.2)

- Coordinate and oversee the collection of data required for local land-use plans and the development of livelihood-focused interventions (Output 2.3)

- Support the LCP and the ILCA during the landscape design process with particular reference to providing socio-economic and biophysical data for the FVCs

- Carry out a slow and steady consultative land-use planning process, building community confidence, engaging traditionally sidelined groups (such as women and the disabled).  For possible approaches see papers such as: Felix G. Bello, Neil Carr & Brent Lovelock (2016) Community participation framework for protected area-based tourism planning, Tourism Planning & Development, 13:4, 469-485

- Make contact with, and develop links through the PM with, public and private sector partners who are interested in collaborating on livelihood-focused interventions under Output 3.5

- Arrange periodic exchange meetings so that CCEs and members of the FVC teams from different Trial Landscapes can compare progress and conditions

Qualifications and Experience required

- Master’s Degree in a relevant  field

- At least 10 years work experience in the field of biodiversity conservation, consensus building with communities and community organizations regarding natural resource management.

- A demonstrated ability to take the initiative in difficult situations

- Excellent communication and facilitation skills

- Able to live and work in remote areas

## Lower Malwathu Community-based conservation expert (LMCCE  )

Duty Station:  Madhu/  FVC  48 pm

In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA), the Landscape Conservation Planner (LCP) and the Learning and Communications Officer (LCO), the UMCCE will oversee, in Trial Landscape 2, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5)

- Organize and implement with the LCO a public information and involvement programme in the selected Focal Village Clusters of TL2 so that the general public and community based organizations understand and embrace the aims of the Project (Output 3.1)

- Slowly get to know the local community and its environs and carry out a public consultation to inform people about the landscape design and the FVC land-use plans and answer questions that people have

- Collect opinions regarding people's understanding of the impacts that

a) they themselves and b) others

have on biodiversity and ecological services and what impacts they might have in the future both locally and further afield (through pollution or overuse of water for example), including on vegetation, on wild species of plants and animals

- Design, with local stakeholders, Project staff and consultants, and with the input of relevant organizations a process to engage slowly and patiently over the whole project period as a resident, with individuals and organizations in the community and local government officials (Output 3.2)

- Coordinate and oversee the collection of data required for local land-use plans and the development of livelihood-focused interventions (Output 2.3)

- Support the LCP and the ILCA during the landscape design process with particular reference to providing socio-economic and biophysical data for the FVCs

- Carry out a slow and steady consultative land-use planning process, building community confidence, engaging traditionally sidelined groups (such as women and the disabled).  For possible approaches see papers such as: Felix G. Bello, Neil Carr & Brent Lovelock (2016) Community participation framework for protected area-based tourism planning, Tourism Planning & Development, 13:4, 469-485

- Make contact with, and develop links through Project Management with, public and private sector partners who are interested in collaborating on livelihood-focused interventions under Output 3.5

- Arrange periodic exchange meetings so that CCEs and members of the FVC teams from different Trial Landscapes can compare progress and conditions

Qualifications and Experience required

- Master’s Degree in a relevant field

- At least 10 years work experience in the field of biodiversity conservation, consensus building with communities and community organizations regarding natural resource management.

- A demonstrated ability to take the initiative in difficult situations

- Excellent communication and facilitation skills

- Able to live and work in remote areas

## Malwathu Estuary Community-based conservation expert (MECCE  )

Duty Station:  Arippu  FVC  48 pm

In close coordination with the Project Manager (PM), the Senior Technical Adviser (STA), the International Landscape Conservation Design Adviser (ILCA), the Landscape Conservation Planner (LCP) and the Learning and Communications Officer (LCO), the UMCCE will oversee, in Trial Landscape 3, the development and implementation of participatory consultation within communities and between communities and local government, the development of village-cluster level land-use plans and technical and material support for livelihood-focused project interventions in natural resource management (Outputs 3.1, 3.2, 3.3, 3.4, 3.5)

- Organize and implement with the LCO a public information and involvement programme in the selected Focal Village Clusters of TL3 so that the general public and community based organizations understand and embrace the aims of the Project (Output 3.1)

- Slowly get to know the local community and its environs and carry out a public consultation to inform people about the landscape design and the FVC land-use plans and answer questions that people have

- Collect opinions regarding people's understanding of the impacts that

a) they themselves and b) others

have on biodiversity and ecological services and what impacts they might have in the future both locally and further afield (through pollution or overuse of water for example), including on vegetation, on wild species of plants and animals

- Design, with local stakeholders, Project staff and consultants, and with the input of relevant organizations a process to engage slowly and patiently over the whole project period as a resident, with individuals and organizations in the community and local government officials (Output 3.2)

- Coordinate and oversee the collection of data required for local land-use plans and the development of livelihood-focused interventions (Output 2.3)

- Support the LCP and the ILCA during the landscape design process with particular reference to providing socioeonomic and biophysical data for the FVCs

- Carry out a slow and steady consultative land-use planning process, building community confidence, engaging traditionally sidelined groups (such as women and the disabled).  For possible approaches see papers such as: Felix G. Bello, Neil Carr & Brent Lovelock (2016) Community participation framework for protected area-based tourism planning, Tourism Planning & Development, 13:4, 469-485

- Make contact with, and develop links through Project Management with, public and private sector partners who are interested in collaborating on livelihood-focused interventions under Output 3.5

- Arrange periodic exchange meetings so that CCEs and members of the FVC teams from different Trial Landscapes can compare progress and conditions

Qualifications and Experience required

- Master’s Degree in a relevant  field

- At least 10 years work experience in the field of biodiversity conservation, consensus building with communities and community organizations regarding natural resource management.

- A demonstrated ability to take the initiative in difficult situations

- Excellent communication and facilitation skills

- Able to live and work in remote areas

## Learning and Communications Officer (48pm)

## Duty Station: Project Office in Mannar, with travel to Colombo, Arunadhapura, and Trial Landscapes as required

Background

The Learning and Communications Officer (LCO) will be responsible for all information and involvement programmes under the Project, in particular the design and delivery of Outputs 2.1, 3.1, 4.3, 4.4 and 4.5, and will liase with all Project staff and consultants, and with partners (projects and programmes) to deliver Output 1.3

Duties and responsibilities

- Develop a project communications strategy and involvement plan coordinated across all four Outcomes, incorporate it with the annual work plans and update it annually in consultation with project stakeholders; coordinate its implementation

- Liaise with the Implementing partner, the Project Board, relevant government agencies, all other project partners, including donor organisations and NGOs for effective coordination of project information dissemination, streamlining resources and identifying potential synergies.

- Coordinate the implementation of knowledge management outputs of the project;

- Coordinate and oversee the implementation of public information and involvement activities across all project components

- Take the lead in designing and initiating Project interventions to involve and engage youth and other social sub-groups in Project activities and stimulate them to spread important messages themselves

- Facilitate the design and maintenance of the project website/webpages and ensure it is up-to-date and dynamic;

- Facilitate learning and sharing of knowledge and experiences relevant to the project;

Qualifications and Experience

- A Bachelor's degree, preferably in the field of community development or natural resource / environmental management;

- A communications qualification

- At least three years of work experience in developing and implementing communications strategies for organizations or projects, ideally involving international donors

- Strong professional working capacity to use information and communications technology, specifically including website design and desk-top publishing software

- Understanding of biodiversity conservation, sustainable livelihoods and associated issues

- Very good inter-personal skills

- Excellent language skills (writing, speaking and reading) in English and Sinhala, and at least a working knowledge of Tamil  would be a great asset

## Project Assistant (48 pm)

## Duty Station: Project Office in Mannar, with travel to Colombo, Arunadhapura, and Trial Landscapes as required

Duties and Responsibilities

Under the guidance and supervision of the Project Manager, the Project Assistant will carry out the following tasks:

- Assist the Project Manager in day-to-day management and oversight of project activities;

- Assist the Senior Technical Adviser in matters related to M&E and knowledge resources management;

- Assist in the preparation of progress reports;

- Translate and interpret between English, Tamil and Sinhala where required for documents and at formal and informal meetings (note that it may be necessary to engage additional interpreters for some large meetings when visitors come from Colombo)

- Ensure all project documentation (progress reports, consulting and other technical reports, minutes of meetings, etc.) are properly maintained in hard and electronic copies in an efficient and readily accessible filing system, for when required by PB, TAC, UNDP, project consultants and other PMU staff;

- Assist the LCP to track down and engage with people and institutions relevant for the preparation of the landscape designs

- Communicate with and coordinate inputs from partners and team members by email, mail and telephone and in person

- Arrange meetings for the team members with agencies and individuals

- Attend meetings and maintain full and accurate records of the planning process, including correspondence, research materials, meeting minutes and drafts of the three landscape designs

- Find out specific information and track down required documents and data

- Translate research materials where necessary for the ILCA

- Follow up with team members on their contributions in order to keep to deadlines

Qualifications and Experience

- A Bachelors degree or an equivalent qualification;

- At least three years of work experience preferably in a project involving biodiversity conservation, natural resource management and/or sustainable livelihoods. Previous experience with UN project will be a definite asset;

- Very good inter-personal skills;

- Proficiency in the use of computer software applications especially MS Word and MS Excel.

- Excellent language skills (writing, speaking and reading)  in English, Tamil and Sinhala

- A demonstrated ability to take adequate initiative in difficult situations

## Finance and Procurement Officer (48pm)

## Duty Station: Project Office in Mannar, with travel to Colombo, Arunadhapura, and Trial Landscapes as required

Duties and Responsibilities

Under the guidance and supervision of the Project Manager, the Project Finance and Procurement Officer will have the following specific responsibilities:

- Keep records of project funds and expenditures, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Manager;

- Implement procurement in collaboration with the Project Manager according to the applicable guidelines

- Monitor financial resources to ensure accuracy and reliability of financial reports submitted quarterly.

- Review project expenditures and ensure that project funds are used in compliance with the Project Document and GOSL financial rules and procedures;

- Validate and certify FACE forms before submission to UNDP;

- Provide necessary financial information as and when required for project management decisions;

- Provide necessary financial information during project audit(s);

- Review annual budgets and project expenditure reports, and notify the Project Manager if there are any discrepancies or issues;

- Consolidate financial progress reports submitted by the responsible parties for implementation of project activities;

- Liaise and follow up with the responsible parties for implementation of project activities in matters related to project funds and financial progress reports.

Qualifications, Skills and Experience

- A Bachelor's degree or an advanced diploma in accounting/ financial management;

- At least five years of relevant work experience preferably in a project management setting involving multi-lateral/ international funding agency. Previous experience with UN project will be a great asset

- Proficiency in the use of computer software applications particularly MS Excel;

- Excellent language skills in English and Sinhala (writing, speaking and reading) and a working knowledge of Tamil would be an advantage

- DOI: 10.1080/21568316.2015.1136838

- DOI: 10.1080/21568316.2015.1136838

- DOI: 10.1080/21568316.2015.1136838