## Annex H:   UNDP Risk Log

Note: Red = High Risk, Yellow = Medium Risk, Green = Low Risk

| Risk No. | Description | Date Identified | Type | Impact & Probability | Mitigation measures (see Annex E SESP for more details) | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Institutional inertia and administrative inflexibility hinders a) cross-sectoral and trans jurisdictional collaboration b) enhanced implementation of existing legislation to provide necessary back-up for project interventions at village and landscape level c) adoption of policy recommendations and pre-service and in-service training modules d) establishment and financing of post-project monitoring protocol | 20 December 2018 | Political, Regulatory, Financial | P:2 I:4 | Action on enabling central government directives (Output 1.1) will be monitored, and reinforced where necessary. The project's approach will be slow and patient, with the Project Management Office and full time Project staff based in the project landscape. If progress is insufficient UNDP CO is ready to step in with high level representations and project funding could be suspended according to UNDP-GEF procedures (PIR, MTR). Districts will facilitate this. |  |  |  |  |
| 2 | The other programmes, projects and private-sector enterprises with which the Project has agreed close collaboration under Output 1.3 do not invest sufficient time and other resources in consultations, coordination, communication and cooperation | 20 December 2018 | Operational | P:2 I:4 | UNDP will increase communication and involvement with the concerned organizations well before Project Inception so that by the time of Inception there is full understanding of the need for collaboration. The Project will ensure that momentum is maintained, taking the lead whenever necessary to keep links active, interesting and productive. Project Office and project staff based full time in the project Districts will facilitate this. |  |  |  |  |
| 3 | Public information and involvement programmes are not sustained after the end of the project | 20 December 2018 | Operational | P:3 I:3 | Printed and audio-visual (videos, for example) materials for learning and communciation are insufficient to ensure continuation of public information and involvement programmes, so the Project will emphasize training in the skills required to develop and deliver them and will work with MMDE to ensure that such capacity is available post-project. BIOFIN is an important partner in this respect. |  |  |  |  |
| 4 | Technological constraints at local level limits use of GIS for the strategic design | 20 December 2018 | Operational | P:3 I:2 | The project will use traditional mapping, including 3D modelling alongside GIS |  |  |  |  |
| 5 | Local residents do not feel sufficiently involved and valued, are sceptical as a result of being exposed other projects that led to unrealistic expectations, and find that the Project's livelihood-focused interventions produce results too slowly to persuade people to continue with changed behaviour beyond the end of the project | 20 December 2018 | Social, Operational | P:2 I:3 | The Project will monitor feelings of involvement, strengthen public information and involvement programmes as appropriate (e.g. arrange visits between focal and non-focal Village Clusters), and modify the participatory methods if indicated. The full time resident staff in each of the three Trial Landscapes will communicate constantly, and will demonstrate an environmentally friendly, sometimes self-sacrificing, approach by establishing a low carbon footprint - low use of plastics, sensible use of fuel and electricity, attention to sewage and solid waste disposal in project operations. |  |  |  |  |
| RISKS IDENTIFIED BY THE SOCIAL AND ENVIRONMENTAL SCREENING PROCEDURE (ANNEX E) |  |  |  |  |  |  |  |  |  |
| Risk 6 SER1 * | Livelihood-focused interventions might have deleterious impacts on wild species or habitats in protected areas or areas proposed for protection or recognized as environmentally sensitive or critical | 20 December 2018 | Social, Environmental | P:2 I:4 | Project design includes mitigation of this risk through environmental and social assessment of each and every project intervention (see ThOCh: M8). All project interventions will be developed through long and careful participatory processes with local government, village communities and with partner projects and programmes (see lll Strategy). Care will be taken to avoid inadvertent impacts on key habitats and species through encouraging influx of people to the sites of livelihood-focused interventions. |  |  |  |  |
| Risk 7 SER2 * | Reforestation interventions, whether through natural regeneration or planting, are poorly planned and implemented | 20 December 2018 | Social, Environmental | P:2 I:2 | Project design includes mitigation of this risk through environmental and social assessment of each and every project intervention (see ThOCh: M8). Expert consultation with foresters on the relative merits of natural regeneration and various possible planting regimes considering water availability and the use to which the forest will be put (eg wildlife habitat). |  |  |  |  |
| Risk 8 SER3 * | Livelihood-focused interventions in fisheries or aquaculture lead to damage to species or habitats | 20 December 2018 | Social, Environmental | P:2 I:4 | Project design includes mitigation of this risk through environmental and social assessment of each and every project intervention (see ThOCh: M8). All project interventions will be developed through long and careful participatory processes with local government, village communities and with partner projects and programmes (see lll Strategy). |  |  |  |  |
| Risk 9 SER4 * | Livelihood-focused interventions in non-timber forest products, in-situ or ex-situ, lead to damage to species or habitats | 20 December 2018 | Social and Environmental | P:3 I:3 | See management measures under Risk 3 |  |  |  |  |
| Risk 10 SER5 * | Cultural values may be adversely affected by introduction of tourism | 20 December 2018 | Social and Environmental | P:2 I:3 | On the one hand there will be long and careful discussions with the local people before the project invests in any new tourism development. On the other hand, the project will be very circumspect in its engagement with private enterprise partners to ensure that such partners are genuinely committed to developing enterprises that will provide benefits in the long term through stabilizing impacts of local livelihoods on species and habitats. |  |  |  |  |
| Risk 11 SER6 * | Risk 11: In order to implement the Project's landscape conservation strategic designs, government decides on involuntary resettlement of people from proposed elephant corridors and other forest areas and as a result the Project becomes associated with any consequent negative impacts. | 20 December 2018 | Social and Environmental | P:3 I:4 | It is impossible to predict a) whether resettlements will be required, and b) where and how many people might be involved but a clear course of action is laid down in case resettlements become the preferred course of action (see Annex E). The Project will first make every effort to find solutions that provide for elephant conservation at the same time as ensuring the well-being of local residents and, in particular, avoid involuntary, or indeed voluntary, resettlement. If and when it is decided to pursue resettlement, or endorse it by association, a full ESIA will be carried out (see end of Annex E) according to standards established in The Sri Lankan National Involuntary Resettlement Policy (NIRP) 2001 OP 4.12, UNDP Social and Environmental Standards (SES), and the updated GEF policy on environmental and social safeguards. |  |  |  |  |
| Overall Risk 12 SER7 * | Participation in community-based planning and implementation is dominated by people from traditionally empowered groups and under-represents women and other marginalized people, including those facing uncertain futures as a result, for example, of poverty, the recent three year drought, and land-tenure disputes | 20 December 2018 | Social | P:1 I: 3 | Project staff will be well trained in community-centred participatory processes and will live on site full time in the communities they are working with, thus building up understanding of social pressures and how to address them in the context of the project. Participatory mechanisms will be slow in pace and will focus on ensuring that there is no "elite capture" of community benefits, and that traditionally less-empowered groups of society are engaged. |  |  |  |  |

*   SER = Social and Environmental Risk and the number refers to the Risks given in the SESP (Annex E)

http://www.treasury.gov.lk/documents/10181/272149/RPF-NAPPP+-+For+disclosure.pdf/aa720af8-413f-4394-9ec7-1693ff487bc3

http://www.undp.org/content/undp/en/home/librarypage/operations1/undp-social-and-environmental-standards.html

http://www.thegef.org/sites/default/files/documents/Policy%20on%20Environmental%20and%20Social%20Safeguards%2C%20DRAFT%20for%20Consultation%2C%202018-08-31.pdf