WWF GEF Agency

PROJECT IMPLEMENTATION REPORT

FY2023

Securing the Future of Peru’s Natural Protected Areas

(Amazon Sustainable Landscapes Program)

GEF PMIS Number: 9374 (Child Project ID); 9272 (Program ID)

Project Report information:

| Report Author(s) | Claudia Yep, Lucía Chuquillanqui, Isabel Filiberto |
| --- | --- |
| Report Completion Date | 08/18/23 |

| 1. GENERAL INFORMATION | PIR Submission Date |  |
| --- | --- | --- |
|  | Agency Approval Date | 3/30/2018 |
|  | Fiscal Year | 2023 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 5th PIR |
| 2. CURRENT YEAR RATINGS | Overall DO rating | Moderately Satisfactory |
|  | Overall IP rating | Satisfactory |
|  | Overall Risk rating | Moderate |
| 3. KEY DATES | CEO Endorsement Date | 10/3/17 |
|  | Actual Implementation Start Date | 3/30/2018 |
|  | First Disbursement Date | 4/18/2018 |
|  | Expected Mid-Term Review Date | 4/4/2022 |
|  | Expected Completion Date | 06/30/2024 |
|  | Expected Financial Closure | 12/31/2024 |
|  | Actual Completion Date |  |
| 4. BUDGET | GEF Project Budget | $ 9,007,528 |
|  | Total GEF disbursement through June 30 of the FY (USD) for project that has been in implementation for at least 1 FY | $ 7,918,339 Co-finance $29,862,813.30 (until Dec 2022) |

WWF GEF Support Contacts:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Supervision Project Manager | Isabel Filiberto | Isabel.Filiberto@wwfus.org |
| Sustainable Finance Specialist | Claudia Yep | Claudia.yep@wwfperu.org |
| Safeguards Specialist | Soledad Altrudi | Soledad.altrudi@wwfus.org |
| Gender Specialist | Nathalie Simoneau | Nathalie.Simoneau@wwfus.org |
| RBM Specialist | Amelia Kissick | Amelia.kissick@wwfus.org |
| Financial Manager | Joyce Miguel | Joyce.miguel@wwfperu.org |

PMU Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Director | Rossina Manche | rmanche@sernanp.gob.pe |
| Project Manager | Lorenzo Beck | lbeckgef6-pdp@sernanp.gob.pe |
| NPA Management Specialist | Zara Sánchez | zsanchezgef6-pdp@sernanp.gob.pe |
| Safeguards Specialist | Liz Clemente | lclementegef6-pdp@sernanp.gob.pe |
| M&E Specialist | Milagros Silva | msilvagef6-pdp@sernanp.gob.pe |
| Administrative assistant | Leyla Arévalo | larevalo@profonanpe.org.pe |
| Marketing specialist | Laura Morales | lmoralesgef6-pdp@sernanp.gob.pe |
| Administration and Finance Director Profonanpe | Christian Bueno | cbueno@profonanpe.org.pe |
| Director de la Dirección de Desarrollo y Supervisión de PROFONANPE | Omar Corilloclla | ocorilloclla@profonanpe.org.pe |

### Ratings

Fill in all ratings based on the Rating Scale provided in Annex I.

|  | Year 1 (2019) | Year 2 (2020) | Year 3 (2021) | Year 4 (2022) | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Development Objective (DO) | MS | MS | MU | MS |  |
| Implementation Progress | HS | MS | MS | S |  |
| Risk | L | M | M | M |  |

Justification for Current Year Ratings:

The project’s Development Objective Rating is Moderately Satisfactory, with 72.22% of overall year results targets met in Y4 (Jan – Dec 2022), reported on by the PMU in March 2023. Y4 was still affected by the consequences of the COVID 19 Pandemic, the political instability and some contract delays. However, the efforts made by SERNANP generally allowed the GEF6-PdP project to be again on track to achieve the expected targets of the project Results Framework. The Implementation Progress Rating is Satisfactory, with 80.60% of the Y4 Annual Work Plan activities having been implemented. Activities not implemented were mainly due to the cancelation of a consultancy (all financial sources planning module) due to the Non-Compliance of the contract by the hired company. SINANPE´s Master Plan, considered to be the official high-level strategic document that will incorporate into the PdP Initiative, has not yet been approved due to the effects of the pandemic and political instability. This pre-approved document is expected by the end of 2023 or early 2024. The implementation of protocols and performance monitoring systems is approximately 75% complete due to operational delays at the beginning of the consultancy. The Risk Rating is Modest. The economic crisis that the Pandemic left in the country negatively affected the SERNANP (National Service of State Natural Protected Areas) public budget in 2020, 2021 and 2022, but in 2023 it has been recovering. However, this general economic crisis could continue impacting SERNANP’s ability to increase revenues through the proposed financial mechanisms in the coming years. Finally, in Y4 there was high political instability, including episodes of social unrest in the country, due to a change of president. SERNANP change its management team and that brought some delays in the implementation of the project.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

PROGRESS The project objective is to promote long-term financial sustainability for the effective management of the Amazon Protected Areas of the National System of Natural Protected Areas of Peru (SINANPE), for the protection of globally important biodiversity and ecosystem services in the Amazon Biome. A description of key project advances towards the achievement of the expected project results in Y4 is presented below. The project results indicators are measured annually at the end of the calendar year. In this report, we are presenting targets measured in December 2022 for Y4 and estimations through June 2023. PDO Ind 01 - Achieve single close to cover the financial gap for management of the Amazon natural protected areas (NPAs). The result was achieved in 2019, with the PdP single close agreement. PDO Ind 02 – Number of hectares of NPAs where METT score has been improved (≥ 70%) due to the intervention of the GEF6-PdP Project. The indicator didn´t have targets for 2022. The project is on track to meet the 2023 target (530,327.47 ha). 2018 METT baseline score is presented below: NPA; Area (ha); Baseline. Machiguenga; 218,905.6; (42.4%). Rio Abiseo; 274,520; (63.6%). Tabaconas-Namballe; 32,124.87; (62.5%). Tingo María; 4,777; (60.4%). As of December 2022, 498,202.60 hectares had improved METT score: Río Abiseo National Park (hereinafter Río Abiseo NP), Tingo María National Park (hereinafter Tingo María NP) and Machiguenga Communal Reserve (hereinafter Machiguenga CR) (with METT scores of 88.89%, 88.54% and 78.89%, respectively). Tabaconas Namballe National Sanctuary (hereinafter SN Tabaconas Namballe) had a METT score of 66.67%. PDO Ind 03 - Number of NPAs that maintain or improve their conservation status. The indicator didn´t have targets for 2022. Following the trend from previous years, out of the 4 project NPAs, 3 of them maintained or improved it and Machiguenga CR reduced its conservation status (99.04% in 2018, 98.72% in 2021, 97,27% in 2022). PDO Ind 04 - Number of NPAs that maintain or reduce negative environmental impacts rate. Indicator in 2022 met 50% of the target. 2 of the 4 project NPAs increased their rate of negative environmental impacts: NP Rio Abiseo reduced this (2.62%), SN Tabaconas Namballe maintained it (1.19%) and PN Tingo Maria and RC Machiguenga increased this (1.65% and 0.71%, respectively), with regards to the 2018 baseline (2.68%, 1.19%, 1.61% and 0.39%, respectively). In the case of PN Tingo Maria, this was related to the reduced monitoring and control activities done during the COVID 19 pandemic and the associated field work restrictions and this negative trend is expected to be reversed in the coming months. In the case of the Machiguenga CR, the reduced conservation status and increased negative environmental impacts are due to agricultural activities done by Indigenous Communities in the area and the establishment of clandestine airstrips related to illegal drug trade activities. While the first issue is being approached by the NPA Management directly with the involved communities, through an open dialogue to find a consented solution, the second issue is more complex, and involves other competent authorities in Peru beyond SERNANP. Results of Project Implementation Component 1 Development of a multi-partner, public-private initiative for long-term financial sustainability of the NPAs in the Peruvian Amazon. The expected C1 result is to develop a public-private initiative between multiple partners to achieve long-term financial sustainability of the NPAs in the Peruvian Amazon (PdP Initiative). This component has 3 indicators, and its progress is as follows: Ind.R1.1. Number of conditions developed to generate commitment between government and donor. End of project target was achieved in 2019 (project year 1). Ind.R1.2. Number of conditions developed to operationalize the single close agreement effectively and efficiently. Two of the 04 closing conditions for the PdP Memorandum of Understanding (institutional arrangements and systems and methodologies that allow transparent financial management of the trust fund - EMMA System), were achieved in Y1. The other 2 were planned for 2021 (Y3), but were not achieved in 2021 or 2022. The two remaining closing conditions are the development of the SISPOFFI and and the Environmental Monitoring System (SMA, for its acronym in spanish), the status of which in June 2023 is: - SERNANP´s System for Financial Planning and Reporting by all Sources (SISPOFFI): In 2022 SERNANP cancelled the contract with the company hired to develop this system, due to breach of contract, and decided to hire 7 individual consultants to work under the leadership of SERNANP´s Information and Communication Technologies department. As of June 2023, the consultants have presented the contractual products established, and the SISPOFFI has an advance of 30% of expected deliverables. The module is expected to be completed by the end of 2023 fourth quarter with potential adjustments during the first half of 2024. - The Protocols and Performance Monitoring Systems (PPMS) (Sernanp´s environmental planning and monitoring system): SERNANP decided to develop this system with SERNANP/KfW co-financing funds. In 2022 SERNANP and Profonanpe hired a consulting company (BARTECH SAC) to prepare it. The consultancy advanced well but with delays. As of June 2023 the SMA has an advance of approximately 75% (based on contract deliverables status), and the two pending products are expected to be finalized in the fourth quarter of 2023. Ind.R 1.3a. # of official high-level strategic documents that incorporate the PdP-Amazon Initiative. The target for this indicator was to have the SINANPE Master Plan approved in 2021. However, as of June 2023, this target still hasn’t been met because the process suffered delays, first due to COVID-related meeting restrictions, and more recently due to the turnover of government focal points. In 2022 the process was affected by the political crisis and change of authorities in SERNANP. During the first semester of 2023 a preliminary SINANPE Master Plan draft was produced, and published in SERNANP’s webpage, as part of the public consultation process. SERNANP plans to submit the final SINANPE Master Plan to MINAM for approval at the end of 2023. Ind.R1.3b. # of master plans that incorporate planning in accordance with the EI-Amazonía. Non-cumulative annual targets for this indicator are 9 plans in 2021, 6 plans in 2022, and 4 plans in 2023. The process for updating NPA Master Plans advanced satisfactorily in 2022 and updates to the master plans of the Tingo María NP, Yanachaga Chemillen NP, SN Tabaconas Namballe , SN Megantoni, SN Pampa Hermosa, RN Allpahuayo Mishana, RN Matsés , BP San Matías San Carlos, RC Airo Pai and RC Machiguenga were completed and approved. During the first semester of 2023, the updates to the master plans of the Sierra del Divisor NP, BP Alto Mayo and RC Huimeki were also approved. As of June 2023, there are 14 updated master plans that incorporate the goals of the PdP-Amazon Initiative and the project is advancing well towards achieving the final project target (19 Master Plans). Component 2 Diversification of sources to increase NPA financing. Component 2 will provide technical and financial assistance to explore, identify and analyze the feasibility of a set of innovative PA revenue generating mechanisms, both at national and local level, in order to diversify SERNANP's portfolio and help fulfill its commitments under the PdP Initiative. Component 2 has three Outcome-level indicators: Ind.R2.1. Number of official events to raise awareness of the importance of financial sustainability in NPAs. Target in 2022 was 2 events and the target was surpassed. Some of the events organized included: - An online Dialogue Table titled "What are NPAs and how can they drive conservation?" was organized using the virtual platform of El Comercio group, a leading formal written and digital media with extensive reach in Peru. The objective of the event was to raise awareness about the importance of NPAs and of promoting their financial sustainability. Although the number of people reached online did not meet initial expectations (reach: 402,562, interactions: 7,166, views: 128,914, maximum live viewers: 427), the event allowed the PMU to reconsider the awareness raising strategy, that from that moment onwards transitioned from a mass and generalized communication approach to a more personalized strategy targeting specific interest groups, particularly those connected to the financial mechanisms driven within the framework of the GEF6-PdP project. - ExpoAmazonica: This event is an annual international fair held in the Peruvian Amazon regions, aimed at promoting rainforest products. The project participated in this fair to raise awareness among participants about the importance of NPAs and their financial sustainability and to present and position one of the project financial mechanisms that consisted on a virtual fundraising platform ("Perú por Naturaleza") PERU POR NATURALEZA(https://perupornaturaleza.com/) with QR codes to collect donations to NPAs. - +Amazonía: In coordination with PROFONANPE’s Innova Project, and PdP Coordination Unit, the PMU organized the event +AMAZONIA in Lima, November 2022 aimed to raise awareness and increase access to new financial resources through virtual fundraising targeting both national and international citizens. The +AMAZONIA event offered an experience full of art, gastronomy, music, talks, where a greater commitment, awareness, and action for the benefit of natural protected areas for current citizens and future generations was promoted. The event received a great response with over 2,500 attendees. - In 2022 bilateral meetings with selected private companies to raise their awareness about the value of the NPA and to do a call for action for this companies to support the NPAs. Meetings were held with Adidas, Calidda, JcDecaux, Merrell, Latam, AJE and Larcomar and all of the private companies showed interest in collaborating with SERNANP. During the first semester of 2023 an alliance was established with JCDecaux, a leading outdoor advertising company in Peru. The purpose of this alliance was to provide free advertising space for SERNANP (National Service of Natural Protected Areas) to emphasize the importance of ANPs (Protected Natural Areas). This advertising will be displayed in airports nationwide, where the said company advertises. Furthermore, a partnership has been forged between SERNANP, Profonanpe, and Latam Airlines under the "SOSelva" program launched by the airline. More details about this alliance will be elaborated in Indicator R2.2, mechanisms involving the private sector – partnerships with private companies. Ind.R 2.2a. % of increase in the public budget that SERNANP contributes to the PdP-Amazon Initiative. 2024 target is a 10% increase over the 2017 baseline, an equivalent to USD 323,874USD. In 2022 the financial mechanisms identified are not yet contributing to a significant budget increase. However, projections of financial mechanisms implemented by the project show that the target of this indicator will be achieved in the first semester of 2024. Ind.R2.2b. # of financial mechanisms at the national level with technical and/or legal proposals prepared (targets were established for 2021 (1 mechanism), 2022 (1 mechanism) and 2023 (1 mechanism). These targets have already been surpassed. To date, technical and/or financial proposals have been prepared for 4 financial mechanisms, out of which one started implementation in 2022 and the rest will start implementation in the second half of 2023 and first quarter of 2024. Four additional financial mechanisms are being developed at the national level. The status of the 8 financial mechanisms is presented below: - Coercive authority to collect fines, infractions, and civil reparations in NPAs (Law proposal elaborated and approved): In 2021, under the leadership of SERNANP's Legal Advisory Office (OAJ), the PMU developed a proposal of Law Amendment to modify the legislative decree No. 1013, which established SERNANP. The objective was to grant SERNANP the authority for coercive enforcement to effectively collect fines and penalties for infractions committed within NPAs. The Law proposal was presented and approved by the Council of Ministers and forwarded for consideration by the Congress of the Republic; in 2022, the Decentralization, Regionalization, Local Governments, and Modernization of State Management Committee of the Congress unanimously recommended the approval of the Bill and the Spokespersons' Board of the Congress agreed to debate it in the plenary session. The amended Law was finally approved on June 13th, 2023, and SERNANP will start implementing this new legal mandate in the second semester of 2023. - Digital fundraising (technical proposal elaborated, approved and under implementation). In 2021, a partnership agreement was signed between SERNANP and Profonanpe to develop and implement a virtual platform. This platform hosts products and services intended to attract monetary and non-monetary resources from individuals and legal entities towards NPAs. The platform "Perú por Naturaleza" was implemented in 2022, and offered services such as: i) sponsoring the management of a NPA in the jungle, ii) adopting an endangered species or an Amazonian tree, iii) supporting community development initiatives, and iv) launching personal conservation initiatives. The campaign, "A Coffee to Conserve" was piloted in 2022. This campaign took place in the Alto Mayo Protection Forest and intended to support the local coffee-producing community, which contributes to the conservation of the NPA. The campaign generated a revenue of S/. 16,116.99 (4,340USD, approximately). - Entrance fee updates (technical and legal proposal developed and approved): The update of NPAs entrance fees required technical proposal with favourable input from the Ministry of Foreign Trade and Tourism (MINCETUR). The proposal was developed under the leadership of the Tourism Office (UOF-T) and submitted to MINCETUR in December of 2022. On January 12th, 2023, MINCETUR issued a favourable opinion and on January 24th, 2023, SERNANP approved a Presidential Resolution approving the new fees. These new fees will take effect in January, 2024, and will increase SERNANP´s collection by 100% in the next 5 year. - Environmental compensation (legal proposal/SERNANP resolution and technical proposal, under preparation): The activity aims to develop and implement an improved methodology and protocol to enhance the estimation of environmental compensation actions in NPAs by large-scale projects. In 2022, a consultant was hired to support the development of the methodology and protocol. The preliminary methodological proposal was developed and is being negotiated with MINAM, who has to provide no objection before SERNANP can approve. This is expected to happen before the end of 2023. - Allocation of resources from the National Water Authority (ANA) (technical and legal proposal under preparation): In 2021, a study to assess alternatives to be able to redistribute resources from ANA towards the conservation of the ANP was developed. Due to the political instability and change of authorities in SERNANP this process didn’t advance significatively in 2022. In the first semester of 2023, the possibility of developing an alliance with ANA to collaborate on the conservation of water ecosystem services in the hydroelectric sector was assessed. The assessment determined the technical and regulatory feasibility and the roadmap for various alternatives, of which priority was given to the following: - Agreement with ANA to consider economic contribution from water users and irrigation users of major and minor hydraulic infrastructure, for the conservation and preservation of water sources in NPAs. - Promote that hydroelectric plants implement MERESE agreements (Volunteer Payment for Ecosystem Services) for those plants to contribute to the conservation of the water ecosystem services offered by the NPAs. - Private Sector In 2022, two strategies with the private sector were explored to increase sustainable finance alternatives for NPAs: - Certificate of collaboration with NPAs for private companies: A quick assessment with a sample of private companies determined that companies contributing to the conservation of NPAs would be interested in having a brand, or certificate in order to be recognized by their clients as a company that supports conservation and sustainable development issues in the country. Following this assessment, a proposed certificate was prepared and in 2023 a SERNANP directive will be developed to establish the criteria and processes to be able to grant the certificate to companies that contribute to the financial sustainability of NPAs. - Alliances with private companies: Agreements have been developed with the following companies: - Latam Airlines: An agreement has been drawn up between SERNANP, Profonanpe and Latam , for July-December 2023, to develop joint actions that contribute to the promotion and positioning of ANPs. - Matilda Art: The company in question specializes in creating 3D polygon puzzles out of cardboard with animal concepts. A proposal for an agreement is being prepared between SERNANP and the Art Matilda company so that part of the sales of the puzzles go to the ANP and the company can use the aforementioned certificate. Ind.R2.2c. # of financial mechanisms at the NPA level implemented in the 4 pre-selected NPAs of the GEF6-PdP Project (target for 2021 was 1 mechanism, for 2022 was 1 mechanism, and for 2023 is 1 mechanism. The term "implemented financial mechanism" is understood when the mechanism generates or captures financial resources, which could not be achieved during the year 2022 due to delays in the design of financial mechanisms caused by quarantine measures established by the Peruvian government in 2020 and 2021. These measures hindered fieldwork and the delay in finding and hiring specialized consultants in the subject. In 2022 and first semester of 2023, updates on financial mechanisms being developed for a total of 10 Amazonian ANPs, are as follows: - Hydrological Ecosystem Services Remuneration Mechanism (MERESE-hydro): The objective is to implement this mechanism in a NPA. While it does not require a regulation, it requires a technical proposal and an agreement between SERNANP and the service provider company. Under the leadership of UOF-GP, in coordination with OPP, UOF-SF, UOF-GA, and UGP, a consultancy was completed in 2022, with the purpose of identifying NPAs with the greatest potential to develop a MERESE-hydro based on their water supply contributions and potential actors willing to establish this mechanism. Based on this assessment, it was decided to implement this mechanism in the Allpahuayo Mishana NR, leading to discussions with the water and sanitation service company SEDALORETO, the National Superintendence of Sanitation Services (SUNASS), and the NPA governance committee. A proposal for a Hydrological Ecosystem Services Remuneration Mechanism was prepared and the tariff study was approved by SEDALORETO. The plan is currently under implementation. - Management Contracts: The aim is to implement this mechanism in five NPAs. Management contracts or NPA Management Agreements are a participatory management tool where a nonprofit legal entity, known as the Executor, is entrusted by the State to carry out required management and administrative actions to achieve specific results prioritized in the NPA master plan. It also has financial implications, as the Executor needs financial resources for the assigned results and can commercialize rights generated by conservation projects within the NPA. Efforts are being made to award management contracts to different NPAs through various procedures, including at the initiative of external organizations and SERNANP. - Improvement of tourist services in the Tingo María National Park (technical and regulatory proposal - prepared). In 2022 the NPA tourist site plan was approved, which outlines the various tourist services that the NPA will provide. After the approval of the document and during the first semester of 2023, SERNANP has continued to prepare the technical file for the public investment project that will improve tourist services in the NPAs in the central zone of the country, which includes the Tingo María NPA. - Virtual Fundraising via QR codes: This mechanism aims to be implemented in four NPAs and in collaboration with private companies. It involves placing physical collaboration modules in high-traffic tourist areas within ANPs, as well as virtual collaboration through a platform. Partnerships are also sought with private companies to promote collaboration through donations and product commercialization. Component 3 Implementation of PdP Action Plan Measures to consolidate and improve the effective management of Amazon NPAs. At the beginning of 2020, the work plan for financing the enabling conditions of the basic and structural management levels of the 4 beneficiary NPAs was approved, and USD 5M were transferred from the project to the transition fund of the PdP Initiative. Ind.R 3.1a. # of NPAs that achieve the basic management level (2023 cumulative target was 4 NPAs). As of June, 2023, Tingo María NP, Tabaconas Namballe SN , and Machiguenga RC had achieved all the goals of the basic management level. It is expected that SERNANP will approve, in the second semester of 2023, the master plan of the Río Abiseo NP, and with that the 4 NPA of the project will have achieved the basic management level in 2023. Ind.R3.1b. # of NPAs that reach the structural management level measured by (i) Effective monitoring and control system that has achieved ≥80% of the necessary financial resources, and (ii) Biological Monitoring System has ≥80% of the necessary financial resources). As of June 2023, the advance towards this target is as follows: Effective monitoring and control system (has ≥80% of the necessary resources). As of June, 2023, PN Tingo María, PN Río Abiseo, and RC Machiguenga achieved 102.20%, 93,80% and 90.42%, respectively, of the financial resources needed to implement their monitoring and control system, planned for the 2020-2023 period, as established in the 2018 baseline of the project Results Framework. SN Tabaconas Namballe achieved 75.96% of the required financial resources. NPA biological monitoring system implemented (has ≥80% of the necessary resources). As of June, 2023, the 4 project NPAs had secured 100% of the budget required to have an effective biological monitoring system, financed entirely with PdP Transition Fund. Implementation of the biological monitoring system has started in the 4 project NPAs and is advancing adequately. Ind.R3.1c. # of NPAs from the Amazon selected for the project that are receiving financing from the PdP-Amazon Initiative, through the funds of the GEF6-PdP Project and co-financing (2022 target was 4 NPA) As of June 30, 2023, the 4 NPAs have been receiving financing from the transition fund of the PdP-Amazon Initiative source GEF6 and co-financing from SERNANP for the enabling conditions of the basic and structural management levels. Challenges - In December of 2022, the president of the Republic was impeached by the Congress of the Republic, and the vice president of Peru assumed the office, as established in the Political Constitution of Peru. This led to a change in the entire council of ministers and changes in government officials, resulting in a shift in national policy. SERNANP was not exempt from these changes, as a new institutional head was appointed. The political situation of the country in 2022 did not allow sustained political support from MINAM to the activities of the project, that was required to move forward activities with a strong public component, such as the financial mechanisms, and establishing coordination with other sectors to implement the financial mechanisms dependent on them. In 2023, this challenge could continue due several sectors of the Peruvian population want the elections to be brought forward, as they have a high degree of disapproval of the current President of the Republic and the Congress. - The implementation of the work plan in the 4 beneficiary Protected Natural Areas continues to present challenges due to the low spending capacity and the time-consuming administrative processes required by SERNANP (National Service of Natural Protected Areas) and Profonanpe (Peruvian Trust Fund for National Parks and Protected Areas). Additionally, social unrest at the end of 2022 hindered and prevented the development of several field activities. In 2023, this will be the main challenge due to the budget that needs to be executed to achieve the enabling conditions of the level of structural management and the potential for political and social conflict. - Integrating the Executor of the Machiguenga Communal Reserve Management Contract (hereinafter ECA-MAENI) as a new executor of the transition fund of the GEF6 PdP Initiative was a challenge, as it required due diligence on the part of Profonanpe, which took approximately 6 months. It was also necessary to train and support ECA-MAENI for the proper execution of the transferred budget. - In the first half of September 2022, Profonanpe changed its financial management system, which led to the suspension of funds until mid-October, approximately. This brought the challenge of not halting the activities of the 4 ANPs or reconsidering their execution for the following months while rapidly learning to use the new system, in order to achieve the set goals for that year. Strengths - The political and technical support, and time dedication from key SERNANP departments is essential to achieve the expected goals of the GEF6-PdP Project. - The total openness and willingness of the personnel of the 4 beneficiary NPAs and the UOFs of SERNANP to accept technical assistance and allow the PMU to assume the role of liaison between both instances has allowed the PMU to achieve expected goals of the project and recover from delays created by the COVID 19 field work restrictions and political instability situation. - The full confidence and support that the PdP Coordination Unit has been giving to the PMU to adapt the technical and budgetary planning and to expedite the processing of the budgetary requirements that are needed in the 4 beneficiary NPAs to achieve the goals of the enabling conditions and the plan of work 2020-2023 of these. - The technical and administrative capacity and the knowledge of the PMU staff of the SERNANP and Profonanpe processes, and their ability to integrate them, allows them to provide practical solutions that contribute to the implementation of the 2023 annual workplan of the 4 beneficiary NPAs. Safeguards Social risks Given the aforementioned increase of the unique and special rates for entry (for tourism purposes) to all nationally protected areas (NPAs), the GEF PdP Safeguards staff has provided technical assistance to SERNANP Tourism Unit to elaborate a mitigation plan for the specific social risks this change might create. As a result, the UOF of Tourism will soon: 1) develop TORs for a consultant whose objective will be to produce a complementary guide to operationalize Presidential Resolution No. 026-2023-SERNANP; 2) produce a Totem or digital screen to display information and/or other communications materials. Following the framework provided by that mitigation plan, the chiefs of PN Tingo Maria and the safeguards staff have jointly developed a mitigation plan specific to this area because Tingo Maria has been categorized as “medium” in terms of potential conflict vis a vis the increased entry rates.* This plan includes the development of communication materials as well as socialization meetings to raise awareness of the new measure, what it entails and how beneficial it can be to the financial health of the Park. Thus far, 3 banners have been printed with information on the Grievance Redress Mechanism (MAQS, for its name in Spanish); 1 workshop has been conducted to provide technical assistance on how the MAQS applies to tourism related matters and on implementation of the new entry rates; and 1 socialization meeting with local tourism operators and representatives of DIRCETOUR and the municipal Tourism Secretary of Tingo Maria, among others. Between the months of January and June 2023, 159 people (69 women, 98 men) have received training on the project’s Grievance Redress Mechanism, MAQS (from its Spanish name) and safeguards. Among the participants were UOF of Tourism; chiefs of PN Tingo Maria, RCM and ECA MAENI; tourism interested parties; and newly incorporated volunteer park rangers. Out of those 159 people, 29 (13 women and 16 men) received training on the Grievance Redress Mechanism specifically as part of the strategy devised to prevent conflicts that might erupt in response to the increase in entrance fees in the near future. *: Please note that this assessment was done on the basis of a screening tool, developed as one of the mitigation plan actions to both establish a baseline for each of the nationally protected areas in terms of their strengths and weaknesses, and help inform future communication strategies and actions. Environmental risks The form each of the 4 NPAs have to keep track of hazardous waste has been updated. Furthermore, each NPA continues to have special waste bins to collect used batteries, which were acquired as part of the environmental safeguards kit the GEF6 PdP SERNANP project acquired. In relation to the construction of a new administrative headquarters in PN Tingo Maria, safeguards were incorporated in the contract signed by the chosen construction company. In April, a WWF GEF support mission was carried out to oversee the adherence to those measures during the construction phase, and the results were satisfactory. Grievances In the period between July and December, 2022, two grievances were recorded through the project’s GRM, the MAQS, and both pertained to PROFONANPE’s inadequate management of funds. For example, in the grievance filed in September of 2022, a SERNANP employee complained about PROFONANPE’s lack of payment to catering vendors in due time, which resulted in the personnel hosting a workshop having to pool their own money to purchase food and beverages the day of the meeting. This grievance and the one logged in December (also about unfulfilled payment to a food provider by PROFONANPE) have both since been resolved. No grievances were recorded during the Jan-July 2023 period.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

### Based on the Stakeholder Participation objectives of the Prodoc the following table summarizes the progress, challenges, and results of the stakeholder participation during the FY:

| ### Partners | ### Challenges | ### Progress/Results |
| --- | --- | --- |
| ### MINAM | ### Political instability and changes in key MINAM focal points for the Project | ### Several meetings have been held to obtain political and technical support for the financial mechanisms, including the political support for the Congress of the Republic to approve the new power of coercive executor for SERNANP. ### MINAM focal points participate in ASL meetings and workshops and Annual Conferences ### MINAM chairs the Steering Committee of the PdP-Amazon initiative / GEF Project. |
| ### SERNANP (Headquarters) | ### In 2022, the main challenge for effective representation from SERNANP and technical participation in the project was the political instability and the change of SERNANP leadership. | ### Participated in the Steering Committee of the PdP-Amazon initiative / GEF Project. ### SERNANP leads the project implementation. Almost all SERNANP departments have focal points that lead/monitor implementation of project work plan. The project ownership by SERNANP technical staff is high, despite challenges in the last project year. |
| ### Profonanpe | ### Some challenges have been related to delays in procurement of goods and services, within the framework of the transition fund of the Amazon PdP. | ### Participated in the Steering Committee of the PdP-Amazon initiative / GEF Project. ### There have been regular coordination meetings between PROFONANPE, the PMU and PdP Coordination Unit to see the progress in the acquisition of goods and consultancies of the Amazon PdP Initiative and the GEF6-PdP Project. ### Several meetings have been held to strengthen the processes for the acquisition of goods and equipment and the selection and hiring of consultants. ### PROFONANPE participated in supervision meetings and in the annual supervision mission, led by WWF GEF and held in November 2022. |

### Project Partners

### National Stakeholders

| ### National Stakeholders | ### Challenges | ### Progress/Results |
| --- | --- | --- |
| ### Ministry of Agriculture and Irrigation – National Water Authority | ### Political instability caused delays in ANA´s engagement in the project. | ### Meetings between leadership of SERNANP and the National Water Authority have been held to coordinate development of the financial mechanism to redistribute resources for the conservation of the basins within the NPA. |
| ### Ministry of Foreign Trade and Tourism |  | ### Ministry participated in the development of the new NPAs entrance fee and approved the new tariffs. |
| ### WWF - Peru |  | ### Provided technical support to the PMU, through regular meetings. |
| ### Moore Foundation |  | ### Member of the board of directors of the PdP-Amazon Initiative and cofinancier of PdP. |
| ### Private sector and society in general | ### To get interest from private sector that can have impact on the sustainable finance of the NPAs was a challenge. A couple of activities didn´t offer good results and the team learnt that a market scoping exercise was needed to target project activities to specific project audience. | ### Engaged through communication events, bilateral meetings, and call to actions for the various strategies of the private financial mechanisms the project is implementing (as described in the Section B above). |

| ### Local Stakeholders: Local stakeholders are engaged, following SERNANP's participatory processes, through NPAs Management Committees. |  |  |
| --- | --- | --- |
| ### Local Actor | ### Challenges | ### Progress/Results |
| ### SERNANP (headquarters of the 4 beneficiary ANPs) | ### Capacities of NPA Management teams are limited. The PMU is working to provide technical and administrative support so that the activities of the Project advance at the necessary pace to achieve the enabling conditions of the management levels and the financial mechanisms in the 4 beneficiary PNAs. | ### NPA Management teams are leading the implementation of project activities in each of the 4 project NPAs, coordinate closely with the PMU, including the implementation of safeguards and gender requirements. The heads of the 4 NPAs and their personnel (professionals, park rangers and administrative assistants) have led and dedicated a great effort to improving the enabling conditions of the basic and structural management levels, without neglecting all other activities of the NPA. The management committees and regional governments of the beneficiary NPAs have actively participated in developing the NPA Master Plans. |
| ### Management committees of the 4 beneficiary ANPs (hereinafter CG) | ### Limited capacities of management committees are a challenge in some NPAs. To overcome this challenge, the PMU has provided technical support to SERNANP and the CGs through its executive board, and specially to promote and contribute to increasing the number of women participating in the management committees, as established in the gender action plan of the project. | ### The Management Committees are recognized and in force in the 4 beneficiary NPAs. They meet regularly and members of the CG participate in the management of the 4 beneficiary NPA s, and are represented by their executive board. ### The management committees of the Yanachaga Chemillen NP, Sierra del Divisor NP, Bahuaja Sonene NP, San Matías San Carlos BP and Pui Pui BP, the regional governments of Pasco, Junín, Ucayali and Puno and the Ministry of Culture have participated in Ad Hoc commissions created by the project to conduct the process of selecting administrators and signing NPA administration contracts. |
| ### Executor of the Administration Contract of the Machiguenga Communal Reserve | ### The initial lack of management capacities of the ECA MAENI (Administrative Contract Executor of the Machiguenga CR) has been a challenge to advance on the ground activities of the project. | ### The members of the NPA executive board participate in the co-management of the Machiguenga CR. ### The ECA MAENI, administrative contract executor, representative of Indigenous Communities, have received a microcapital from the Project to implement activities on the ground in the Machiguenga CR (master plan update, physical demarcation, operation of the Management Committee). They have had working sessions, and periodic meetings with the PMU, who have imparted trainings and TA. The ECA-MAENI has become a new executor of the transition fund of the PdP Initiative, which has strengthened the co-management model of the Machiguenga RC, by reinforcing management, technical and operational capacities of the ECA on behalf of its 14 indigenous communities and one rural settlement. ECA-MAENI has demonstrated a greater involvement and institutional commitment with the goals of the basic and structural management levels in the NPA. |
| ### Local Government Institutions |  | ### Represented and participating in project activities through the management committees of the beneficiary NPAs and the Ad Hoc Committees that are selecting NPA Administration Contracts. |

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

The project has contributed to the social inclusion process that the Peruvian Government and SERNANP implement. In this sense, the incorporation of transversal approaches (gender, intercultural and intergenerational) and social, environmental and gender safeguards have been developed in the different management documents, processes and activities that are implemented; In parallel, capacity building has been developed for the actors with whom the GEF6-PdP Project is linked, in order to provide an induction or training on cross-cutting policies and social and environmental safeguards, this being a permanent action that is sustained in a multidisciplinary work coordinated by the PMU and SERNANP team (Annex 16. Social Safeguards and Gender): - There are 8 checklists to determine the gender dimensions in financial mechanisms. - The master plans of the 4 beneficiary NPAs incorporate the gender approach. - An induction has been carried out for 5 volunteer park rangers from the RC Machiguenga, who have just joined SERNANP. - Contribution has been made to training and providing technical assistance to the management committees of the Tingo María NP, Tabaconas Namballe SN and Machiguenga RC to incorporate the gender approach GENDER ACTION PLAN (Completed December 2020) The gender action plan was satisfactorily implemented in 2022 with the most important activities: - Within the framework of workshops for the socialization and gathering of contributions from indigenous communities in the process of updating the master plan of the Machiguenga Communal Reserves, under the leadership of the ANP (Protected Natural Area) management and ECA-MAENI (Executor of the Machiguenga Communal Reserve Management Contract), a participation methodology was developed that included spaces for the care of indigenous children under the supervision of local caregivers in the communities. This allowed for greater participation of women in the workshops, with women's participation accounting for 48%, compared to 52% participation by men. Additionally, local women and men interpreters were hired during the workshops. - Under the leadership of SERNANP UOF-GP (General Planning Office), in coordination with the PMU, a proposal for gender-affirmative measures was designed for the normative document of NPA management committees at the national level. This proposal was approved through Presidential Resolution No. 075-2022-SERNANP. Executives of the management committees in 3 NPAs were also trained in these measures. A matrix for updating information collection for monitoring the aforementioned measures was designed and piloted in the 4 beneficiary NPAs. Furthermore, representatives of the NPA management committees were trained in gender sensitivity. - The gender perspective was incorporated into meetings with private companies to establish partnerships under the financial crowdsourcing mechanism in tourist NPAs areas. - All consultants hired under the GEF6-PdP project, as well as activities carried out using resources from the GEF6 PdP Initiative, have been trained in using a gender-sensitive approach. - The gender perspective has been incorporated into the approved master plans of the 3 beneficiary ANPs. Additionally, personnel from the 4 beneficiary ANPs and communal guards have been trained in gender sensitivity. - The relevance of incorporating the gender perspective into the financial mechanisms known as collaboration and environmental compensation modules was assessed. For the first mechanism, it was determined that the approach must be integrated into its design, which has been done, as indicated in the third paragraph of this section. For the second mechanism, it was determined that the gender perspective is not applicable, since the project is promoting a new compensation calculation methodology. However, the compensation itself could incorporate the gender perspective depending on the actions and stakeholders involved in compensation, which will need to be evaluated during the compensation plan development processes.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

- The key knowledge management products developed in the year are: - A Guide for the Implementation of Retribution Mechanisms for Hydrological Ecosystem Services in NPAs was prepared. The PMU prepared and disseminated this guide to allow the NPA heads to identify enabling conditions and have a roadmap to implement water resources payment for ecosystem services in NPAs. (https://worldwildlifefund-my.sharepoint.com/personal/lucia_chuquillanqui_wwfus_org/_layouts/15/guestaccess.aspx?share=EZxYgp9u8yFFgWbrrfvjoLcBcdp5Fj4Zwiv_TsTyuxjs3Q&e=nmSndZ) - A guide to identify, select, design and implement sustainable finance mechanisms in NPAs (https://worldwildlifefund-my.sharepoint.com/personal/lucia_chuquillanqui_wwfus_org/_layouts/15/guestaccess.aspx?share=Eacueeti1gxPgShfu6ju08wBvnmYyWkRD95jF005JGtt2g&e=qeknwt)

### Adaptive Management

During the project year, the PMU has proposed adaptation in the Work plan, as explained below:

Please check all applicable modifications made to the project during this reporting period noting a description of the change, justification for the change and the date of No-Objection given by the WWF GEF Agency. If not applicable, please leave blank. Please see guidance on definitions and procedures for Major and Minor Amendments. Note: it is recommended that all changes be discussed in advance with the GEF Program Manager. Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☐ Results framework. ☐ Components and cost. ☐Institutional and implementation arrangements. ☐Financial management. X ☐Implementation schedule; The PMU is proposing some changes to activities, under certain project outputs. Those have been discussed during periodic meetings between PMU and the GEF Agency, who provide No Objection to them.; This are small adaptations of the original plan that don´t change components, Outcomes, Outputs, or budget across Components. See justification below for each activity change.; Changes were proposed in the June 2023 supervision meeting and the GEF AGency provided no objection to them.. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☐ Safeguards. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. X ☐ Other: <fill in>; The PMU is proposing some changes to activities, under certain project outputs. Those have been discussed during periodic meetings between PMU and the GEF Agency, who provide No Objection to them.; This are small adaptations of the original plan that don´t change components, Outcomes, Outputs, or budget across Components. See justification below for each activity change.; Changes were proposed in the June 2023 supervision meeting and the GEF AGency provided no objection to them.. - Activity 1.2.3 #1. Preparation of the planning module for all sources of financing: The budget wais increased by an additional USD 104,480 for the payment of the contracted consultants, according to the contract. - Product 2.2.1 #1 Preparation of the SERNANP financial plan: Initially, it was planned to prepare the financial strategy for the 38 NPAs in Amazonia. However, the new SERNANP leadership considers that the project should develop the financial plan of SERNANP. Likewise, the budget has been reduced by USD 29,780, due to the fact that the plan will be develop in house. - Product 2.2.4 #1. Technical assistance and monitoring of the implementation of improvements to tourist services in the Tingo María NP: The budget wais increased by an additional USD 10,000 to cover the cost of extra activities that need to be carried out in the field. - Product 2.2.4 #3. Technical assistance to grant an administration contract for Sierra del Divisor NP, Yanachaga Chemillen NP, San Matías San Carlos BP, Pui Pui BP and Bahuaja Sonene NP – Puno Sector: The budget wais increased by an additional USD 9,000 to cover field work. . - Product 2.2.5 #1. Provide technical assistance to SERNANP to prepare the methodology for calculating the environmental compensation for restoration and conservation: The budget wais increased by an additional USD 5,000 for paying the contracted consultant, according to the final contract issued. - Product 2.2.5 #2. Provide technical assistance to SERNANP to review and improve the procedures for granting management contracts: The budget was reduced by USD 7,000. - Product 2.2.5 #3. Provide technical assistance to SERNANP to develop a model for the sale of carbon credits in advance: The task is eliminated, since SERNANP has made the decision not to address this issue yet. However, the task is replaced to develop and implement the social safeguards for the implementation of the new entrance fees to the 7 NPAs of Amazonia, and a provisional budget of USD 10,000 is maintained. - Product 2.2.5 #4. Generate alliances with the private sector for the dissemination and incorporation of points of collaboration: The budget is reduced by USD 12,195 and the goal of 6 alliances is reduced to 3 alliances due to projections made to generate these. - Product 2.2.5 #5. Installation and monitoring of the collaboration modules in 4 NPAs of the Amazon biome: The activity is separated from activity 2.2.5 #4, in order to be able to visualize its budget and goal. - Product 2.2.5 #6. Develop a proposal for a directive on the commercialization of the rights generated by conservation projects in NPA executed directly by SERNANP: The activity and budget (USD 6,000) developed in the first semester are increased. - Product 2.2.5 #7. Redirection of financial resources from ANA: A budget of USD 15,000 is incorporated, for the study developed in the first semester of the year and because there is already a decision and roadmap by SERNANP to design the financial mechanism. - Product 2.2.6 #1. Prepare and disseminate a working document that allows SERNANP and the NPA headquarters to identify the enabling conditions to implement economic mechanisms at the national and NPA level: The budget is reduced by USD 5,000, because the activity is finished. - Product 3.1.3 #1. Monitoring and technical assistance to SERNANP, UC-PdP and the headquarters of the 4 NPAs for the planning and implementation of the goals of the PdP-Amazon Initiative source GEF6: An additional USD 10,900 is incorporated in order to be able to provide adequate technical assistance to the NPA headquarters to implement the approved work plan. - Payment of PMU personnel: The budget has been reduced by USD 6,626, due to the fact that the contract for the PMU financial sustainability specialist ended. - Profonanpe technical assistance: The budget was increased by USD 6,749, so that Profonanpe can collect the same, according to the 2023 semi-annual execution. For any proposed or anticipated changes to the project this coming year, please describe below what those changes would be (e.g., in the workplan or results framework) and provide justification. Note: It may be helpful to reference project lessons, challenges, strengths and/or the project theory of change.

### Geolocation Information

Please provide a location name, latitude and longitude (04 decimal points) or, as applicable, a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide as a reference. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Tingo María National Park (PNTM); -9.36985; -76.00287; PA Management. Río Abiseo National Park (PNRA); -7.72609; -77.22932; Pa Management. Tabaconas Namballe National Sanctuary (SNTN); -5.157; -79.26817; Pa Management. Machiguenga Communal Reserve (RNM); -11.845847; -73.399269; Pa Management.

The annexes can be downloaded from the following link:

https://drive.google.com/drive/folders/1aA0x4DpCQJ6uWeLCeroB0RIcBLtx0DhB?usp=share_link

Results Framework:

WWF GEF 9374 G0010 PdP GEF 6 Result Framework 2021 ENGLISH.xlsb.xlsx

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

The methodology of the effects generated by anthropic activities, approved by SERNANP through Presidential Resolution No. 238-2013-SERNANP. The state of conservation of a NPA (100%-P) is expressed as a percentage and results from the calculation of the difference between the degree of affectation with respect to 100%. The results are expressed in probability of non-occurrence of effects that cause loss of biological diversity at the SINANPE level; and it is related to the sample units that do not present effects.

The methodology of the effects generated by anthropic activities, approved by SERNANP through Presidential Resolution No. 238-2013-SERNANP. One of the ways to express the results of this methodology is through the index of effects by activities, which is a measure of the intensity of affectation of a NPA. The affectation index has a value between 0 and 1 and can be expressed as a percentage. The index formula is as follows: Iexa=(∑Ei)/(NX 4) x 100 Ei: number of effects in the i-th sample unit ( 0,1,2,3,4) of the NPA. N: total number of sample units of the NPA.