WWF GEF Agency

PROJECT IMPLEMENTATION REPORT

FY 2024

Securing the Future of Peru’s Natural Protected Areas

(Amazon Sustainable Landscapes Program)

GEF Child Project ID: 9272

Project Report information:

| Report Author(s) | Isabel Filiberto |
| --- | --- |
| Report Completion Date | 9/11/2024 |

| 1. GENERAL INFORMATION | PIR Submission Date |  |
| --- | --- | --- |
|  | Agency Approval Date | 3/30/2018 |
|  | Fiscal Year | 2024 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | Final PIR (6th) |
| 2. CURRENT YEAR RATINGS | Overall DO rating | S |
|  | Overall IP rating | S |
|  | Overall Risk rating | M |
| 3. KEY DATES | CEO Endorsement Date | 10/3/17 |
|  | Actual Implementation Start Date | 3/30/2018 |
|  | First Disbursement Date | 4/18/2018 |
|  | Expected Mid-Term Review Date | 4/4/2022 |
|  | Expected Completion Date | 06/30/2024 |
|  | Expected Financial Closure | 12/31/2024 |
|  | Actual Completion Date | 9/12/2024 |
| 4. BUDGET | GEF Project Budget | 9,007,528 USD |
|  | Total GEF disbursement through June 30 of the FY (USD) for project that has been in implementation for at least 1 FY | 8,743,175 USD |
|  | Materialized Co-finance | 52,617,279 USD (Sernanp: 38,020,587 Profonanpe: 296,692, y Fundación Moore: 9,300,000 y WWF: 5,000,000) |

PMU Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Director | Danny Daniel Morales Dueñas | dmorales@sernanp.gob.pe |
| Project Manager | Lorenzo Beck | lbeckgef6-pdp@sernanp.gob.pe |
| NPA Management Specialist | Zara Sánchez | zsanchezgef6-pdp@sernanp.gob.pe |
| Safeguards Specialist | Liz Clemente | lclementegef6-pdp@sernanp.gob.pe |
| M&E Specialist | Milagros Silva | msilvagef6-pdp@sernanp.gob.pe |
| Administrative assistant | Leyla Arévalo | larevalo@profonanpe.org.pe |
| Administration and Finance Director Profonanpe | Christian Bueno | cbueno@profonanpe.org.pe |
| Director de la Dirección de Desarrollo y Supervisión de PROFONANPE | Omar Corilloclla | ocorilloclla@profonanpe.org.pe |

WWF GEF Support Contacts:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Manager | Isabel Filiberto | Isabel.Filiberto@wwfus.org |
| Sustainable Finance Specialist | Claudia Yep | Claudia.yep@wwfperu.org |
| Safeguards Specialist | Soledad Altrudi | Soledad.altrudi@wwfus.org |
| Gender Specialist | Nathalie Simoneau | Nathalie.Simoneau@wwfus.org |
| RBM Specialist | Amelia Kissick | Amelia.kissick@wwfus.org |
| Financial Manager | Joyce Miguel | Joyce.miguel@wwfperu.org |

### Ratings

Fill in all ratings based on the Rating Scale provided in Annex I.

|  | Year 1 July 2018 through December 2019 | Year 2 2020 | Year 3 2021 | Year 4 2022 | Year 5 & 6 January 2023 through June 2024 |
| --- | --- | --- | --- | --- | --- |
| Development Objective (DO) | MS | MS | MU | MS | S |
| Implementation Progress | HS | MS | MS | S | S |
| Risk | L | M | M | M | M |

Justification for Current Year Ratings:

The project activities were completed June 30, 2024. The project close out period is anticipated to be July 1st to December 31st where final technical and financial reports, Terminal Evaluation and formal project close out activity will occur. This PIR reports advances in activities between January 1st, 2023 and June 30th, 2024 (project follows the calendar year but this report includes also activities in the first half of 2024) . The project’s Development Objective Rating for the report period is Satisfactory, with 85.28% of annual results targets met from January 2023 until June 2024. The overall Development Objective Rating for the entire project is 90.28%. Despite the consequences of the COVID 19 Pandemic, the political instability that still affects the country, and some contract delays, the efforts made by SERNANP and PROFONANPE allowed the GEF6-PdP project to achieve most of the targets of its project Results Framework. The Implementation Progress Rating is Satisfactory, with 85.70% of 2023 and 2024 Annual Work Plan activities having been successfully implemented. Activities not implemented in 2023, mainly related to delays in the development of SERNANP’s financial planning module, were achieved in early 2024. Activities not entirely completed by June 30, 2024, include some sustainable finance mechanisms and SINANPE´s Master Plan (designed but not officially approved yet) are expected to be finalized in the second half of 2024, during project closeout. The Risk Rating is Modest. The economic crisis caused by the Pandemic negatively affected SERNANP’s public budget in 2020, 2021 and 2022, but in 2023 it started to recover. Political high instability affected the project in its entire life, and in the reporting period brought new challenges on the development and approval of SINANPE’s Master Plan and in getting high level political support to some of the project proposed sustainable finance mechanisms. However, as of June 30, 2024, the results achieved by the project in terms of PA effective management increase, SERNANP installed capacities for conservation finance, and projected revenues increase by the project sustainable financial mechanisms are solid.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

Project Progress A summary of project advances towards the achievement of the proposed project results is presented below, with more detailed presented for Y5 and Y6 results targets. Project Objective Indicators PDO IND 01 –Achieve single close to cover the financial gap for management of the Amazon natural protected areas (NPAs). Project target 100% achieved in 2019. PDO IND 02 – Number of hectares with METT score improved (≥ 70%) due to the intervention of the GEF6-PdP Project. Project target 100% achieved in 2023 (530,327.47 ha). NPA; METT Baseline; METT (June 2024). Machiguenga; 42.4%; 83.33%. Rio Abiseo; 63.6%; 91.11%. Tabaconas-Namballe; 62.5%; 75.27%. Tingo María; 60.4%; 88.54%. The 4 project NPAs have significatively raised their METT during the lifetime of the project, as presented in the table below. Furthermore, the project has indirectly facilitated the METT increase in 14,132,718 ha in 27 additional Peruvian amazon NPAs, through the operationalization and technical support to the PdP Initiative. PDO IND 03 - Number of NPAs that maintain or improve their conservation status. Project target was 50% achieved as of June 30, 2024. As of June 30, 2024, 2 of the 4 project NPAs had reduced its conservation status rating (a national rating system used by SERNANP to assess the conservation status -in terms of effects by anthropic activities- of a PA) with respect to the indicator baseline. The reduction in Machiguenga was due to narcotraffic activities, and the aperture of clandestine airstrips linked to illegal drug trade. Tackling this threat involves a coordinated action with other government authorities. Regarding Tingo Maria, the reduction in the conservation status rating was caused by: (i) the review and improvement of the methodology for calculating this indicator in this PA, and (ii) an increase of unplanned agriculture and NNRR extraction activities in the PA. The management of this PAS reports that this threat to the conservation status is not a concern, that problematic activities have been identified and mitigation measures are being implemented as of June, 30, 2024. PDO IND 04 - Number of NPAs that maintain or reduce negative environmental impacts rate. Project target 50% achieved as of June 30, 2024. 2 of the 4 project NPAs increased their rate of negative environmental impacts (PN Tingo Maria and RC Machiguenga), as described in the above paragraph. Component 1 Development of a multi-partner, public-private initiative for long-term financial sustainability of the NPAs in the Peruvian Amazon. IND.R1.1. Number of conditions developed to generate commitment between government and donor. Project target 100% achieved in 2019. IND.R1.2. Number of conditions developed to operationalize the single close agreement effectively and efficiently. Project target 75% achieved as of June 30, 2024. During the reporting period, SERNANP´s System for Financial Planning and Reporting by all Sources, that had had delays due to contractual problems since project early stages, was finally completed. The system allows SERNANP to control the allocation of government counterpart funds from all sources to the PdP Amazon Initiative. The remaining single close condition, the Environmental Monitoring System financed by KFW, as of June 30th, 2024, was completed at 85% and was expected to be completed in the second half of 2024. IND.R 1.3a. # of official high-level strategic documents that incorporate the PdP-Amazon Initiative. Project target 75% achieved as of June 30, 2024. The target for this indicator was the SINANPE Master Plan approved in 2021. However, as of June 2024, this target still wasn’t met. The process suffered continuous delays from the beginning of the project, first due to COVID-related meeting restrictions, and afterwards due to the turnover of government focal points. In 2023 the SINANPE Master Plan process and document was concluded and published in SERNANP’s webpage. Its approval by MINAM is expected to be achieved in the second half of 2024. IND.R1.3b. # of master plans that incorporate planning in accordance with the EI-Amazonía. Project target 100% achieved as of June 30, 2024. The project supported the participatory update of 22 Amazon NPA master plans, surpassing the project target of 19 plans. During the process, the project supported the improvement of templates and strategic planning methodologies, with a better inclusion of safeguards, stakeholder participation and gender considerations. Component 2 Diversification of sources to increase NPA financing. IND.R2.1. Number of official events to raise awareness of the importance of financial sustainability in NPAs. Project target 100% achieved in 2022. The project continued to support and participate in events to raise awareness of the importance of NPA financial sustainability until project close out, such as “Salón de Café y Chocolate, 2023”, “Perú: Líder mundial de diversidad de aves, 2023”, “Hinchas por la Conservación, in the Jockey Plaza”, “SOS Selva, with LATAM company”, “Expo-Amazonia, 2023”, or the participation in the XXV Congress of the Latam network of Environmental Trust Funds, 2023”. IND.R2.2a. % of increase in the public budget that SERNANP contributes to the PdP-Amazon Initiative. Project target (a 10% increase over the 2017 baseline, an equivalent to USD 323,874USD) was 100% achieved in 2024. This target was highly challenged by the economic crisis the country had as a consequence of the pandemic, that delayed project activities and the possibility of achieving higher impact during the lifetime of the project. However, as of June 2024, financial mechanisms implemented by the project had generated a 15.73% increase of SERNANP public budget contribution to the PdP Amazon Initiative (509,600USD) and SFMs developed by the project in NPAs (see description in sections below) had a revenue projection of 20,223,221 USD for the 2024 – 2028 period. IND.R2.2b. # of financial mechanisms at the national level with technical and/or legal proposals prepared. Project target (3 financial mechanisms prepared) was 100% achieved and surpassed in 2023. As of June 30, 2024, the status of the national sustainable finance mechanisms developed by the project is as follows: - Coercive authority to collect fines, infractions, and civil reparations in NPAs: In 2021, the project developed a proposal of Law Amendment to modify the legislative decree No. 1013, which established SERNANP, to grant SERNANP the authority for coercive enforcement to effectively collect fines and penalties for infractions committed within NPAs. The Law was approved by the Congress of the Republic on June 13th, 2023, and SERNANP started implementing this new legal mandate in the second semester of 2023. - NPA Co-management Contracts: Co-management Contracts are a participatory management tool where a nonprofit legal entity, known as the Executor, is entrusted by SERNANP to manage a NPA to achieve its NPA master plan objectives. The Executor can then commercialize rights generated by conservation actions within the NPA (such as carbon credits), that can become important factors for the NPA financial sustainability. The project supported and created capacities in SERNANP that resulted in a prioritization of Amazon NPAs that could adopt this management tool, and in better internal procedures to streamline and expedite the selection of Executors, the negotiation and processing of co-management contracts, and their supervision. This is the SFM supported by the project with the highest revenue potential in the coming years (a projection of 20MUSD or 99% of the projected project SFM revenue in the 2024 – 2028 period), mostly because it has enabled the possibility for carbon credits trade in the NPAs (SERNANP is not allowed to trade credit carbons by law). The project also developed a proposal to allow SERNANP to directly trade rights generated by conservation projects in NPAs. However, this proposal got paused by MINAM and would not advance until MINAM finished the legal framework of REDD+, the national registry of mitigation measures, and the REDD+ safeguards system, under development as of June 30th, 2024. - Digital fundraising: In 2021, a partnership agreement was signed between SERNANP and PROFONANPE to develop and implement a virtual platform for digital fundraising. This platform designed products and services (+Amazonia, a green product with a local financial institution, and the “Peru por Naturaleza” virtual fundraising platform) intended to attract monetary and non-monetary resources from individuals and legal entities towards NPAs. The campaigns and products offered by the platform didn’t generate the expected revenues during the project lifetime and this mechanism is being reassessed by SERNANP and PROFONANPE. - Entrance fee updates: A proposal for updated NPA entrance fees was developed under the leadership of SERNANPs Tourism Office (UOF-T), received a favorable opinion from MINCETUR and was approved by SERNANP on January 24th, 2023. These new fees would have taken effect in January, 2024, and would have increased SERNANP´s fees collection by 100% in the following 5 year. The New SERNANP’s management decided, in 2023, to derogate the proposal and to develop a different and somehow less ambitious, according to the socioeconomic reality of the country, that is expected to take effect in January 2026. - Environmental compensation: The project developed an improved methodology and legal protocol to enhance the estimation and facilitate and manage environmental compensation actions of large – scale projects in NPAs. The technical proposal is under final review by MINAM, who must provide no objection before SERNANP can approve it. - “Certificate of SERNANP Ally” for private companies: In 2023 the project developed an internal directive in SERNANP to establish the criteria and processes to grant a certificate to private companies that contribute to the financial sustainability of NPAs. The proposal was completed and as of June, 30th, 2024, it was under review for approval by SERNANPs management. - Allocation of resources from the National Water Authority (ANA): In 2021, a study to assess alternatives to be able to redistribute resources from ANA towards the conservation of the ANP was developed. Due to the political instability and change of authorities in SERNANP this process didn’t advance significantly in 2022. In the first semester of 2023, the possibility of developing an alliance with ANA to collaborate on the conservation of water ecosystem services in the hydroelectric sector was reassessed but didn’t take traction amongst the new decision makers in SERNANP and ANA. - Software module for granting tourism and NNRR use permits: The software will allow SERNANP to gain efficiencies in the permits management, in the promotion and optimization of the touristic offer. The design of the module was advanced as of June 30th, 2024, and expected to start operations at the end of the same year. IND.R2.2c. # of financial mechanisms at the NPA level implemented. Project target (3 NPA financial mechanisms) was 100% achieved. The status of the SFMs, as of June 30, 2024, is the following: - Co-Management Contracts: The project provided technical assistance and facilitated the development of co-management contracts in 3 Amazon NPAs: - Sierra del Divisor National Park. On November 9, 2023, a co-management contract was signed between SERNANP and the Center for Conservation, Research, and Management of Natural Areas – Cordillera Azul (hereinafter CIMA) for a period of 20 years. CIMA will implement the contract in partnership with the Center for the Development of Indigenous Amazonians – CEDIA and The Shared Wood Company S.A.S. – sWc. The financial proposal for the first five-year period by CIMA is USD 6,904,381. CIMA's financial sustainability strategy is primarily based on the development of a payment for ecosystem services mechanism (REDD+ Initiative) in partnership with sWc, which will be complemented by actions leveraging public, private, and international cooperation financing, and catalyzing technical resources through strategic alliances and other nature-based solutions mechanisms. - Yanachaga Chemillén National Park (PNYCH) and San Matías San Carlos Reserved Zone (BPSMSC). On November 9, 2023, a co-management contract was signed between SERNANP and the Kowen Antani Consortium, formed by the NGO Sustainable Rural Development – DRIS, the Asháninka Communities Association of the Pichis Valley – ANAP, and the Association for the Conservation and Management of the Yanesha Reserved Zone – AMARCY, for a period of 20 years. This is the first co-management contract signed by SERNANP with an IP Association. The financial proposal for the first five-year period by Kowen Antani Consortium is 8,072,825 USD. Their financial sustainability strategy is based primarily on the development of a payment for ecosystem services mechanism (REDD+ Initiative) and an Indigenous Amazon REDD+ Initiative (RIA) in the Yanesha Reserved Zone and associated indigenous communities, in partnership with Mercuria Energy Trading S.A. This will be complemented by actions leveraging funding through a PES associated with water regulation, amongst other financing mechanisms. - Bahuaja Sonene National Park. On September 20, 2023, the co-management contract was signed between SERNANP and the Association for Research and Comprehensive Development (AIDER) for a period of 20 years. The financial proposal for the first five-year period by AIDER is USD 6,940,381.00. Additionally, AIDER's strategy for the sustainability of the contract is primarily based on the development of a payment for ecosystem services mechanism (REDD+ Initiative), in partnership with TOTAL Nature Based Solutions, complemented by actions leveraging funding through interinstitutional collaboration via strategic alliances, international cooperation financing, public and private sector funding, and AIDER’s own resources. - Tourism in Tingo María National Park: This mechanism strengthened tourism services and strategies to attract more tourists, with the aim of maximizing NPA revenue, improving infrastructure and tourist services, and increasing the touristic appeal of the protected area. The project developed the NPA Tourist Plan to promote, diversify and regulate NPA tourism services, improved its tourism Infrastructure, reducing its maintenance costs, and developed new tourist experiences. Thanks to project support, in 2021, 2022, 2023, and 2024, the park was recognized in the Top 100 global Green Destinations, an important recognition that increases the NPA global visibility and will attract more visitors. Through this mechanism, Tingo María National Park is projected to achieve financial self-sustainability by 2027. - Hydrological Payment for Ecosystem Services Mechanism (MERESE-hydro): The project identified the potential NPA and developed the technical proposal with the key stakeholders for this PES in the Allpahuayo Mishana NR. On November 30, 2023, an agreement was signed between SERNANP the National Superintendency of Sanitation Services (SUNASS), the Loreto Municipal Potable Water and Sewage Sanitation Service Provider Company (EPS SedaLoreto), and Profonanpe, to protect, conserve, and restore the water ecosystem services provided by the Nanay River basin, located in this NPA. The funding for this initiative amounts to S/. 248,890 (approximately 67,200USD) for a period of three years. Component 3 Implementation of PdP Action Plan Measures to consolidate and improve the effective management of Amazon NPAs. IND.R 3.1a. # of NPAs that achieve the basic management level. Project target (4 NPA achieve goals for basic management level) 100% was achieved in 2023. IND.R3.1b. # of NPAs that reach the structural management level measured by (i) Effective monitoring and control system that has achieved ≥80% of the necessary financial resources, and (ii) Biological Monitoring System has ≥80% of the necessary financial resources. As of June 2024, the project target was 75% achieved. Tingo Maria, Machiguenga and Tabaconas Namballe reached the structural level. Rio Abiseo NPA met the rest of the conditions but only achieved 77%, and not the established 80%, of necessary resources for an effective monitoring and control system. IND.R3.1c. # of project NPAs that are receiving financing from the PdP-Amazon Initiative, through the funds of the GEF6-PdP Project and co-financing. Project target was 100% achieved. As of June 30, 2024, the 4 NPAs were receiving financing from the transition fund of the PdP-Amazon Initiative. It is important to highlight that activities in the PAs to strengthen effective management were in most cases implemented by NPA management teams, but in the case of the Machiguenga Communal Reserve, an Indigenous Reserve, the work plan was co-implemented with the ECA Maeni, an Indigenous Organization that acts as the Executor of the Co- Management Contract with SERNANP in that PA. This was the first Indigenous Organization receiving funding from the PdP Initiative. The project paid special attention and resources to assess and strengthen required capacities in ECA Maeni’s team for technical and financial planning and management, administration, monitoring and reporting, etc. The experience was successful and left an important precedent in SERNANP and in the PdP Initiative, for channeling funds to Indigenous Executing Organizations. Challenges - High political instability and turnover affected the entire project implementation. The project has seen 5 Republic presidents, 9 Ministries of Environment, 3 SERNANP’S Directors, 3 SERNANP’S General Managers, 2 PROFONANPE Managers and 2 PdP Coordinators, since its inception, which meant different visions and priorities on conservation finance. This has constituted a major challenge, since the advancement of the most impactful or innovative sustainable finance mechanism proposed required a continued high level political support that was not always obtained and limited the project impact. - Capacities within PROFONANPE, SERNANP, NPA management teams, management committees and co-management executors (ECA Maeni) to implement an ambitious work plan, through pandemic and post pandemic times, and with a general “hiring freeze period” in the public sector for most of the project life affected project implementation. The work plan in the 4 beneficiary Protected Natural Areas, that saw their budget significatively increased with the PdP Initiative, but remained with serious staff gaps, had big bottle necks related to low spending capacity, further affected by time-consuming administrative processes required by SERNANP (National Service of Natural Protected Areas) and PROFONANPE (Peruvian Trust Fund for National Parks and Protected Areas). Finally, integrating the Executor of the Machiguenga Communal Reserve Management Contract (ECA-MAENI) as a new executor of the transition fund of the GEF6 PdP Initiative brought additional set of challenges. - The limited market for conservation finance experts and for IT companies that were able to develop the financial management and environmental monitoring software systems in SERNANP created significative delays in project implementation. - The Steering Committee of the project was chaired by the Vice Minister of MINAM, but the project would have benefited from stronger engagement from relevant MINAM Departments, from the Ministry of Economy and Finance, or the Ministry of Tourism, that were relevant for some project themes. Strengths - SERNANP management and its departments maintained a strong ownership of the project, in part due to the PMU strategy of strengthening SERNANP capacities across all project components, and facilitate SERNANP’S leadership, to ensure the institutional sustainability of the project actions. - The political and technical support, and time dedication from key SERNANP departments, the PMU and the 4 beneficiary NPAs has been essential to achieve the outcomes of the GEF6-PdP Project. The total openness and willingness of the personnel of the 4 beneficiary NPAs and SERNANP departments to accept technical assistance and allow the PMU to assume the role of liaison between both instances was key for the PMU to achieve the expected project goals, despite the challenges described. The PMU had good adaptive management capacity, that allow to overcome many of the challenges presented above. - The PMU had a very strong safeguard capacity, applied to the reality of SERNANP and the NPAs teams. This allowed the project to implement strong safeguards actions and to influence the PdP Initiative and SERNANP’S PA system as a whole. For example, the project grievance mechanism was adopted by SERNANP at the system level and the project was able to influence the NPA Management Committees Regulation, introducing gender parity considerations, at the system level (which during the lifetime of the project, increased dramatically the participation of women in several NPA Management Committees). The NPA management teams valued the safeguards work very positively and recognized that it helped avoiding conflicts with the communities. Safeguards - Since the last report, the decision to increase the fees for access to protected areas, which came as a result of an executive resolution, was postponed due to the economic recession Peru was experiencing and it is now expected to come into effect in 2025. In the meantime, no promotional fees (example: children enter for free on Sundays) will be applied. - In SN Tabaconas Namballe, the conditions were met in order to proceed with the demarcation as the conflict that had manifested in 2022 has now been resolved and the company hired to implement the activity was already versed in safeguards (they had received two previous training by project staff). - There was a slight delay in the printing of the colloquial version of the master plan for the RC Machiguenga, though said version was approved in 4 indigenous languages and distributed to native communities in the reserve’s buffer zone. - Lastly, there was a small landslide in PN Tingo Maria, affecting one of the stairs of the Cueva de las Lechuzas. In order to mitigate the negative effect on livelihoods this could cause (due to decreased visitation and, therefore, less sales of artisanal goods), special events were organized and funded. The closure and events were socialized through audiovisual materials. - The last couple of months of the project were mainly characterized by the elaboration of a final report that would systematically capture the work done on safeguards and stakeholder engagement, as well as lessons learned and challenges faced. - No grievances were recorded during the Jan 2023 – June 2024 period.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

A summary of stakeholder engagement activities in the report period is presented below: - SERNANP continued to play a leadership role in all GEF6-PdP project activities. This entailed the involvement of SERNANP’s management team, directors of the DGANP and the Strategic Development Directorate, heads of OPP, OA, and OAJ, personnel from UOF-GP, UOF-GA, UOF-T, UOF Natural Resource Management, UOF-PyP, UOF-GI, UOF-PMG, UOF-PICTNI, UOF-TIC, UOF-IICS, UPF-GDA, UOF Investment Execution, and UOF-SF. - PROFONANPE was the Financial Manager of the Project. Participated in the Steering Committee of the PdP-Amazon initiative / GEF Project. There have been regular coordination meetings between PROFONANPE, the PMU and PdP Coordination Unit to see the progress in the acquisition of goods and consultancies of the Amazon PdP Initiative and the GEF6-PdP Project. - MINAM chaired the Steering Committee of the PdP-Amazon initiative. Several meetings were held to obtain political and technical support for the financial mechanisms. MINAM focal points participated in ASL meetings and workshops and the ASL Annual Conference. - The project engaged with the private sector specially in Component 2, and events and calls to action have been organized for private sector and general public regarding various strategies of the financial mechanisms. - NPA Management teams continued to lead the implementation of project activities in each of the 4 project NPAs, and coordinated closely with the PMU, including the implementation of safeguards and gender requirements. The heads of the 4 NPAs and their personnel (professionals, park rangers and administrative assistants) dedicated a great effort to improving the enabling conditions of the basic and structural management levels, without neglecting all other activities of the NPA. Capacities of NPA Management teams are limited. The PMU worked to provide technical and administrative support so that the activities of the Project advanced at the necessary pace to achieve the enabling conditions of the management levels and the financial mechanisms in the 4 beneficiary PNAs. - The NPA management committees and regional governments of the beneficiary NPAs actively participated in developing the NPA Master Plans. The Management Committees were recognized and in force in the 4 beneficiary NPAs. They met regularly and members of the CG participated in the management of the 4 beneficiary NPA s, and are represented by their executive board. The management committees of the Yanachaga Chemillen NP, Sierra del Divisor NP, Bahuaja Sonene NP, San Matías San Carlos BP and Pui Pui BP, the regional governments of Pasco, Junín, Ucayali and Puno and the Ministry of Culture participated in Ad Hoc commissions created by the project to conduct the process of selecting administrators and signing NPA co-management agreements. Limited capacities of management committees are a challenge in some NPAs. To overcome this challenge, the PMU provided technical support to SERNANP and the CGs through its executive board, and specially promoted and contributed to increasing the number of women participating in the management committees, as established in the gender action plan of the project. - The ECA MAENI, the administrative contract executor of the Machiguenga Communal Reserve, and representative of the Indigenous Communities in the Reserve, was a key actor in the co-management of the Machiguenga NPA and was strongly involved as a project executing partner. They received a micro capital from the Project to implement activities on the ground in the PA (master plan update, physical demarcation, operation of the Management Committee). The initial lack of management capacities of the ECA MAENI was a challenge that slowed the advance of the on the ground project activities. This was mitigated with working sessions, and periodic meetings with the PMU, who provided trainings and TA to the ECA. The project strengthened the ECA's technical and administrative capacities, and this will enable this ECA to manage resources in the future and implement projects more quickly on site. The ECA-MAENI became the first IP organization subgrantee of PdP transition fund, which strengthened the co-management model of the Machiguenga RC, on behalf of its 14 indigenous communities and one rural settlement. Through this experience, ECA-MAENI has also developed a greater involvement and institutional commitment with the goals of the basic and structural management levels in the NPA.

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

In the reporting period, the project Gender Action Plan was successfully implemented, including the following: - Fifteen people (park rangers and volunteers) were trained across the 4 beneficiary NPAs to implement environmental and social safeguards and gender approach in monitoring and control actions. - Meetings were held with ECAMAENI and the leadership of RC Machiguenga to strengthen capacities for implementing environmental and social safeguards and gender approach in the baseline development process for monitoring protocols of sachavaca (a type of wild animal) and birds. - Meetings were held with ECAMAENI and the leadership of RC Machiguenga to assess the implementation of the risk mitigation plan for microcapital, which was fully implemented. - Two events were organized, one with the PMU team and the other with the 4 beneficiary ANPs, both aimed at reviewing and sharing the systematization and lessons learned from the GEF6-PdP Project regarding environmental and social safeguards and gender approach, as well as the implementation - Technical support was provided to RC Machiguenga for printing the master plan in four local indigenous languages (Yine Yami, Asháninca, Machiguenga, and Caquinte). - Training and monitoring meetings were conducted on the implementation of environmental and social safeguards and gender approach in the demarcation process of the SN Tabaconas Namballe. - The environmental and social risk mitigation plan for the maintenance of the owl cave in PN Tingo María was implemented, with the following activities developed: i) 12 environmental education events (painting and drawings for children, gardening, and local product fair), ii) 4 socialization meetings with local stakeholders regarding the maintenance of the owl cave, iii) 7 communication products (videos and radio spots) and 3 communication events (radio spots, screenshots of Facebook and Instagram posts, and video interviews) to disseminate the work, iv) 2 inductions on environmental and social safeguards and gender approach to company staff, and v) 1 field visit for monitoring and assessing compliance with environmental and social safeguards and gender approach. - The implementation of the Gender Action Plan of the GEF6-PdP Project was evaluated.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

The project participated in several ASL KM activities, including the Program Annual Conference in Lima, and in the exchange of experiences in monitoring the long-term impacts of conservation agreements between Brazil, Colombia, and Peru. The key knowledge management products developed in the reporting period are: - A Guide for the Implementation of Retribution Mechanisms for Hydrological Ecosystem Services in NPAs was prepared. The PMU prepared and disseminated this guide to allow the NPA heads to identify enabling conditions and have a roadmap to implement water resources payment for ecosystem services in NPAs. (https://worldwildlifefund-my.sharepoint.com/personal/lucia_chuquillanqui_wwfus_org/_layouts/15/guestaccess.aspx?share=EZxYgp9u8yFFgWbrrfvjoLcBcdp5Fj4Zwiv_TsTyuxjs3Q&e=nmSndZ) (See annex) - A guide to identify, select, design and implement sustainable finance mechanisms in NPAs (https://worldwildlifefund-my.sharepoint.com/personal/lucia_chuquillanqui_wwfus_org/_layouts/15/guestaccess.aspx?share=Eacueeti1gxPgShfu6ju08wBvnmYyWkRD95jF005JGtt2g&e=qeknwt) (See annex) - In 2024, the PMU conducted a systematization of the project implementation experience, for which a participatory 360-degree exercise was carried out, gathering lessons learned and impressions from 46 key stakeholders from PROFONANPE, SERNANP, WWF, the PMU, and key personnel and stakeholders from the management committees of the four project NPAs: Tingo María National Park, Río Abiseo National Park, Tabaconas Namballe National Sanctuary, and Machiguenga Communal Reserve.

### Adaptive Management

Please check all applicable modifications made to the project during this reporting period noting a description of the change, justification for the change and the date of No-Objection given by the WWF GEF Agency. If not applicable, please leave blank. Please see guidance on definitions and procedures for Major and Minor Amendments. Note: it is recommended that all changes be discussed in advance with the GEF Program Manager. Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☐ Results framework. ☐ Components and cost. ☐Institutional and implementation arrangements. ☐Financial management. ☐Implementation schedule. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☐ Safeguards. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other: <fill in>. For any proposed or anticipated changes to the project this coming year, please describe below what those changes would be (e.g., in the workplan or results framework) and provide justification. Note: It may be helpful to reference project lessons, challenges, strengths and/or the project theory of change.

### Geolocation Information

Please provide a location name, latitude and longitude (04 decimal points) or, as applicable, a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide as a reference. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Tingo María National Park (PNTM); -9.36985; -76.00287; PA Management. Río Abiseo National Park (PNRA); -7.72609; -77.22932; PA Management. Tabaconas Namballe National Sanctuary (SNTN); -5.157; -79.26817; PA Management. Machiguenga Communal Reserve (RNM); -11.845847; -73.399269; PA Management.

ANNEXES:

- Final Project Results Framework (English) with 2023 and 2024 AWPB tracking tools (Spanish)

- GEF 6 ASL PdP Peru systematization of project implementation experience (in Spanish)

- Guide for Implementation of Retribution Mechanisms for Hydrological Ecosystem Services in NPAs (Spanish)

- Guide for Sustainable Finance Mechanisms in Peruvian NPAs (Spanish)

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

The methodology of the effects generated by anthropic activities, approved by SERNANP through Presidential Resolution No. 238-2013-SERNANP. One of the ways to express the results of this methodology is through the index of effects by activities, which is a measure of the intensity of affectation of a NPA. The affectation index has a value between 0 and 1 and can be expressed as a percentage. The index formula is as follows: Iexa=(∑Ei)/(NX 4) x 100 Ei: number of effects in the i-th sample unit ( 0,1,2,3,4) of the NPA. N: total number of sample units of the NPA.