WWF GEF Agency

Project Implementation Report

Securing the Future of Peru’s Natural Protected Areas

(Amazon Sustainable Landscapes Program)

GEF PMIS Number: 9374 (Child Project ID); 9272 (Program ID)

Project Report information:

| Report Author(s) | Claudia Yep, Lucía Chuquillanqui, Isabel Filiberto |
| --- | --- |
| Report Completion Date | 08/26/2022 |

| 1. General Information | PIR Submission Date | 9/14/22 |
| --- | --- | --- |
|  | Agency Approval Date | 3/30/2018 3/30/2018 |
|  | Fiscal Year | 2022 |
|  | Implementation Status (1st PIR, 2nd PIR, Final PIR) | 4TH PIR |
| 2. Current Year Ratings | Overall DO rating | Moderately Unsatisfactory |
|  | Overall IP rating | Moderately Satisfactory |
|  | Overall Risk rating | Moderate |
| 3. Key dates | Actual Implementation Start Date | 3/30/2018 |
|  | First Disbursement Date | 4/18/2018 |
|  | Expected Mid-Term Review Date | 4/4/2022 |
|  | Expected Completion Date | 1/7/2024 |
|  | Expected Financial Closure | 9/30/2024 |
|  | Actual Completion Date |  |
| 4. BUDGET | Total GEF disbursement through June 30 of the FY (USD) for project that has been in implementation for at least 1 FY | USD 7,140,010.15 |
|  | Total Project budget | Total project budget: USD 64,278,986 Total GEF budget: USD 9,007,528.00 |
|  | Total co-finance executed through June 30 | USD 22,700,478.80 (SERNANP: USD 8,197,428.43, Profonanpe: USD 203,050.41, Moore Foundation: USD 9,300,000.00 and WWF: USD 5,000,000.00) |

Project Contact information:

| Project Position | Name | E-mail |
| --- | --- | --- |
| Project Director | Rodolfo Valcárcel | rvalcarcel@sernanp.gob.pe |
| Project Manager | Lorenzo Beck | pdp@sernanp.gob.pe |
| NPA Management Specialist | Zara Sánchez | zsanchezgef6-pdp@sernanp.gob.pe |
| Sustainable Finance Specialist | Alberto Cuba | acubagef6-pdp@sernanpe.gob.pe |
| Safeguards Specialist | Liz Clemente | lclementegef6-pdp@sernanpe.gob.pe |
| M&E Specialist | Milagros Silva | msilvagef6-pdp@sernanp.gob.pe |
| Administrative assistant | Leyla Arevalo | larevalo@profonanpe.org.pe |
| Administration and Finance Director Profonanpe | Christian Bueno | cbueno@profonanpe.org.pe |
| Financial Manager | Omar Corilloclla | ocorilloclla@profonanpe.org.pe |

### Ratings

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year X |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development Objective | MS | MS | MU |  |  |  |  |
| Implementation Progress | HS | MS | MS |  |  |  |  |
| Risk | L | M | M |  |  |  |  |

Justification for Current Year Ratings:

The project’s Development Objective Rating is Moderately Unsatisfactory, with 53.28% of overall Y3 results targets having been met in Y3 (Jan – Dec 2021, reported on by the PMU in March 2022). In general, the project is still on track to achieve its objective. However, Y3 was still affected by the consequences of the COVID 19 Pandemic and the change of Government. The Moderately Unsatisfactory DO rating was due to delays in contracts, the face to face and field work restrictions associated with the pandemic and the government leadership turnover after the presidential elections. The Implementation Progress Rating is Moderately Satisfactory, with 74.40% of the Y3 Annual Plan activities having been implemented. This Annual Work Plan had been updated along the year, to decrease the scope of some activities, especially field work activities, to adapt to COVID-19 field work restrictions, as the quarantine restrictions were extended during the year. The pandemic and the political instability affected the implementation of all project components, with most important delays caused by the need to stop on the ground consultative and participatory processes. The Risk Rating is Modest. As explained, the COVID-19 pandemic brought an important set of challenges to the project from the beginning of 2020. The economic crisis that the Pandemic left in the country is having consequences in SERNANP (National Service of State Natural Protected Areas) public budget, that suffered a reduction in 2020 and 2021. Additionally, the general economic crisis could continue impacting SERNANP’s ability to increase revenues through the proposed financial mechanisms in the coming years. Finally, in 2021 Peru had presidential elections, and the change of government brought political instability and high turnover of high-ranking public officials, which meant that for several months there was unclear political support to PdP, the proposed project financial mechanisms and other policy processes.

### Progress, Challenges, and Outcomes on Project Implementation

(Based on Outcomes, Challenges, and Safeguards sections of the Progress Report)

Challenges In the context of the implementation of the 2022 PdP operative plan: The NPAs management teams have limited administrative and procurement capacities, and this created bottle necks in the execution of the PdP Transition Fund. There have been additional challenges associated to aligning PROFONANPE (Peruvian Trust Fund for National Parks and Protected Areas) and SERNANP procurement procedures. The identified challenges are being tackled by the project but create delays to project implementation. The economic crisis that the Pandemic left in the country has had consequences in SERNANP´s public budget, that suffered reductions in 2020 and 2021. Additionally, the general economic crisis will impact SERNANP’s ability to increase revenues through the proposed financial mechanisms, in the short and medium term. In that regard, the PMU is strengthening efforts to identify, during the lifetime of the project, complementary high impact public and private financial mechanisms that can be implemented to bring additional resources to PdP. Design and implementation of financial mechanisms: It is a permanent challenge to obtain specialized consultants that meet the TORs requirements or that deliver their outputs within the established contractual times. With regards to the coercive executor power for SERNANP, it is a challenge to achieve political influence so that the proposed Law 788/2021-PE is put on the agenda and debated in the Congress of the Republic. With regards to the SERNANP system for financial planning and reporting by all sources (SISPOFFI), the consultant contract that was supposed to design this system was cancelled due to their inability to deliver. In some NPAs (National Protected Areas) (RC Machiguenga and PN Tingo Maria), the pandemic has led to an increase in illegal activities such as illegal mining or drug trade resulting in increased negative environmental impacts (mostly forest clearance). As discussed in this report, this could be related to the economic crisis left by the pandemic and the decreased NPA management control activities due to the Pandemic field work restrictions. The government elections in 2021 brought political shifts and staff turnover that affected project implementation, especially considering that the success of PdP and of the financial mechanisms requires strong government back up and leadership. The political instability in the country continued during the first semester of 2022. Strengths The PdP Coordination Unit adaptive management capacity to accommodate to the different realities and requirements of the NPAs has been crucial in the process of updating the PdP NPA work plans, to achieve their 2020-2023 goals. The technical and administrative capacity of the PMU staff about SERNANP and Profonanpe processes facilitate the integration of project outputs in the government systems. This has allowed SERNANP to improve institutional processes. The 4 beneficiary NPAs and the SERNANP´s departments are open and willing to allow the PMU to serve as liaison and provide technical assistance. Outcomes The project objective is to promote long-term financial sustainability for the effective management of the Amazon Protected Areas of the National System of Natural Protected Areas of Peru (SINANPE), for the protection of globally important biodiversity and ecosystem services in the Amazon Biome. A description of key project advances towards the achievement of the expected project results in Y3 is presented below: PDO IND 01 - Achieve single close to cover the financial gap for management of the Amazon natural protected areas (NPAs). The result was achieved in 2019, with the PdP single close agreement. PDO IND 02 - Number of hectares with improved METT score. The indicator didn´t have targets in 2021 or 2022. The project is advancing well towards achieving the project close targets for this indicator in the next years. PDO IND 03 - Number of NPAs that maintain or improve their conservation status. For PDO IND 03, the project achieved 75% of its Y3 target . From the 4 project NPA, the Machiguenga Communal Reserve didn´t maintain or improve its conservation status. The Machiguenga CR suffered a reduction of its conservation status (from 99.04% in 2018 to 97.27% in 2021) due to loss of natural habitat as a consequence of IPs agricultural activities and establishment of clandestine airstrips related to illegal drug trade activities. PDO IND 04 - Number of NPAs that maintain or reduce negative environmental impacts rate. Indicator in Y3 only met 50% of the target. 2 of the 4 project NPA saw their rate of negative environmental impacts increased. In the case of the RC Machiguenga, this was related to the reasons explained above. In the case of PN Tingo Maria, this was related to the reduced monitoring and control activities done during the COVID 19 pandemic due to associated field work restrictions. Component 1 The expected C1 result is to develop a public-private initiative between multiple partners to achieve long-term financial sustainability of the NPAs in the Peruvian Amazon (PdP Initiative). This component has 3 indicators, and its progress is as follows: 1. Ind.R1.1. Number of conditions developed to generate commitment between government and donor. The goals of this indicator are related to the achievement of 5 closing conditions of the single agreement, which were achieved in 2019 (project year 1). 2. Ind.R1.2. Number of conditions developed to operationalize the single close agreement effectively and efficiently. Two of the 4 closing conditions for the PdP Memorandum of Understanding (institutional arrangements and systems and methodologies that allow transparent financial management of the trust fund - EMMA System), were achieved in Y1. The other 2 were planned for Y3, and they were not achieved: - SERNANP´s system for financial planning and reporting by all sources (SISPOFFI): During 2021, the company Background Consultores S.A.C., presented its first product which was approved by SERNANP. The company should have presented its second product on March 4, 2022 and its third product on June 10, 2022, which did not happened. SERNANP and Profonanpe tried to reconcile with the company, but did not achieved the expected results. In order to achieve the established goal, SERNANP cancelled the contract and is evaluating alternatives solutions. At the moment SERNANP is discussing its options, but no decisions have been made regarding the mechanism to design and implement the financial planning and reporting system. - With regards to the Protocols and Performance Monitoring Systems (Sernanp´s environmental planning and monitoring system): SERNANP decided that this system would be developed with SERNANP/KfW co-financing funds. During 2021, SERNANP and Profonanpe hired a consulting company (BARTECH SAC) to prepare it. To date, the company has presented three products out of six and it is expected that the consulting company will complete its service in November 2022. Ind.R1.3a. Number of official strategic documents that incorporate PdP. The Y3 target for this indicator was to have the SINANPE Master Plan approved. The target was not met because the process, suffered, for the third consecutive year, delays related to COVID-related meeting restrictions, and due to the turnover of government focal points. The SINANPE Master Plan update goes beyond the responsibility of this project. The project is supporting the process through technical assistance and by financing the sustainable finance working group coordinator. As the project advances and the chances to have this Master Plan approved by the end of the year decrease, the PMU and SERNANP are discussing alternative activities the project could be supporting to still achieve the original project outcome. Ind.R1.3b Number of NPA management plans that incorporate financial planning according to the approved EI-Amazonia (Implementation Strategy of the PdP for its acronym in Spanish). The GEF6-PdP Project has as a goal of updating by 2023 19 master plans, incorporating the objectives of the EI-Amazon. To date, there are 6 updated master plans that incorporate the goals of the PdP-Amazon Initiative. This activity is delayed with respect to the original timeline, because during the pandemic, all field work activities had to be cancelled. Even if the original outcome targets are not being met as originally expected, the activities are advancing positively, and the PMU is confident the project targets will be met. To overcome potential challenges related to the legitimacy of the participatory processes and to ensure an inclusive methodology adapted to the challenges of the semi remote participatory work, the PMU prepared a roadmap that was adopted officially by SERNANP, with a methodology to implement a semi-virtual participatory process for the development of the NPA Master Plan. Component 2. Diversification of sources to increase NPA financing. Component 2 has three Outcome-level indicators: IND.R2.1 Number of official events to raise awareness of the importance of financial sustainability in NPAs. Y3 target was 2 and the target was only met partially. Only 1 event was organized in 2021. At the end of 2021, a virtual meeting was organized by the project to generate awareness and dialogue about the value of nature and the NPAs. The feedback from the event was not positive, therefore, the next events will be done face-to-face to reach better the key actors related to the financial mechanisms promoted by SERNANP within the framework of the GEF6-PdP Project. Ind.R2.2a. % increase in the public Budget that SERNANP contributes to PdP for the management of the NPAs. In the first half of 2022, a crowdfunding donation site, called Digital Collection, under the leadership of the Innova Project, was able to raise S/. 12,896.00 (USD 3,306.66), which corresponds to an increase of 0.09% with respect to the RdR (resources directly collected) of SERNANP, which is 1/10th of the end of project target. There are several mechanisms under preparation and the PMU is confident the project end target can still be achieved, but there are several challenges to solve, as discussed in this report. Ind.R2.2b. Number of financial mechanisms at national level with technical and / or legal proposals developed. The target for this indicator in 2021 was 1 (target was met) and for 2022 is also 1. The target was met in 2021 and is on its way to being met for 2022.To date, the advances on the technical and legal proposals for the national financial mechanisms are described below: - Coercive power to collect fines, infractions, and civil reparations in NPAs. (Regulatory proposal prepared - in the process of promulgation): In 2021, the technical support and proposal for a draft law was prepared to amend paragraph d, numeral 2, of the second final complementary disposition of Legislative Decree No. 1013, on the creation of SERNANP (hereinafter Draft Law 788/2021-PE), so that this institution may have the power of coercive executor, and enforce the collection of fines and infractions committed in the NPA. In this regard, i) on November 17, 2021, the proposed Law was supported by SERNANP and approved by the Council of Ministers; ii) on November 18, 2021, the President of the Republic and the President of the Council of Ministers sent Law Project 788/2021-PE to be submitted to the consideration of the Congress of the Republic; iii) on January 9, 2022, the Commission of Decentralization, Regionalization, Local Governments and Modernization of State Management of the Congress of the Republic unanimously recommends, the approval of Law Project 788/2021-PE; and iv) on June 15, 2022, the Board of Spokespersons of the Congress of the Republic agreed to pass Law Project 788/2021-PE to the plenary for debate. To date, the corresponding debate is pending. - Innova Project: In 2021 an inter-institutional alliance agreement was signed between SERNANP and Profonanpe to develop and implement products and services to attract monetary and non-monetary gifts from people and legal entitities. Under the framework of that agreement and under the leadership of the Innova Project, which is in charge of Profonanpe's Innovation and Strategic Management Area, and in coordination with the UOF of Financial Sustainability, the UOF of Investment Projects, and National and International Technical Cooperation of the SERNANP Office, the Coordination Unit of the PdP-Amazon Initiative (UC-PdP) and the Management Unit of the GEF6-PdP Project, during 2021 and the first semester of 2022, designed and implemented the "Peru by Nature" online platform which hosts the following donation mechanisms: - Crowdfunding campaigns: It is in the design and testing phase. A mechanism that through periodic campaigns and small contributions finances a specific project or initiatives. During the first semester of 2022, a study was developed i) to systematize the best practices and lessons learned from the experience of managing a crowdfunding model, ii) to develop qualitative and exploratory research to validate the initiatives in a methodological way with the private sector and other stakeholders and iii) to generate an exponential business model and massive impact, based on crowdfunding. In addition, i) a first crowdfunding campaign was carried out as a test and as part of an opportunity called "Recover my Sea", which raised S/. 1,690,587.00 (USD437,000), which shows that the mechanism has potential, if it takes advantage of the various media events related to environmental issues and ii) a second crowdfunding campaign called "A coffee to conserve", which aimed to raise S/. 300,000.00 (USD 77,533) for the BP Alto Mayo, however, it had a collection of S/. 12,901.00 (USD 3,334), which shows that before launching a campaign it is necessary to analyse in detail the target audience with which you want to connect, the objective of collection, the current opportunities, and the positioning of the platform, among other variables. The success and failure of the aforementioned campaigns will be assessed by the GEF project and serve as experience for the launching of future campaigns. b. Collaboration points (like donation collection points): In the design phase. As part of the “Peru by Nature” campaign, 17 physical modules have been placed in the most visited tourist circuits with internet connection in the 4 NPAs (Tingo Maria NP, Machu Picchu Historic Sanctuary, Tambopata National Reserve and Pacaya Samiria National Reserve). QR codes on the signs direct the donor to the digital platform, which contains in detail the purpose of the donation on the landing page and the ways to donate (Yape, Paypal, Niubiz, bank transfers, visa, among others). In a second stage, the product will consist of generating alliances with private companies (hotels, restaurants, airports, malls, etc.), so those companies can host collaboration points. In this regard, during the first semester of 2022, in coordination with the managers of the 4 NPA, the Tourism and the Financial Sustainability Departments of SERNANP, PdP coordination unit and the Innova Project, a technical proposal has been prepared to assess and define the target audience (international tourists) of the financial mechanisms in the 4 selected NPAs. Likewise, the history and purpose of the collaboration to be requested for each of the 4 NPAs was defined, and a call has been launched for the design, construction and installation of the informational signs in the aforementioned NPA, which will be fully operational during the third quarter of this year. Also, a technical proposal has been prepared that assess the potential companies outside the NPAs, at a national level, to expand the physical or virtual collaboration points (hotels, restaurants, airport, malls, etc.) and the potential synergies that could be sought between companies to achieve greater collaboration. - Environmental Compensation: Requires a directorial resolution from SERNANP. The purpose of the financial mechanism is to develop a methodological proposal to improve the estimation of environmental compensation actions for restoration and conservation to be carried out by large-scale projects within the scope of influence of these NPAs. Likewise, it consists of motivating large-scale projects that are developed outside the NPAs to want to compensate within the NPAs. In this regard, during the first half of 2022, a consultant has been hired to i) validate and approve the protocol and methodological proposal for restoration and conservation in NPAs and ii) provide follow-up and support environmental compensation negotiations in NPAs. - New entry fees (technical proposal – under evaluation): Requires a presidential resolution from SERNANP. During the first half of 2022, technical assistance was provided to improve the technical support report to be submitted to the Ministry of Foreign Trade and Tourism for review and approval. This report is in the final review process by SERNANP, and it is expected that by the second half of 2022 the new entrance fees to the NPAs will be approved, which would take effect in 2024, in accordance with the applicable regulations. - Redirection of resources from the National Water Authority (ANA) (technical proposal – in design): It requires a technical proposal and may require a regulatory proposal, depending on the type of chosen alternative. During 2021, a consultancy was developed to define the best alternative for redirecting ANA resources to the conservation of the upper watersheds within the NPAs, with the following possibilities: i) request a transfer of resources from ANA to SERNANP; ii) increase the economic retribution charged by ANA, to be transferred to SERNANP directly or through a fund; iii) create a trust fund with resources from ANA and other sources, and iv) develop a collaboration agreement between ANA and SERNANP. During the first half of 2022, a decision has not been made regarding the aforementioned alternatives, and coordination with MINAM, the Ministry of Agrarian Development and Irrigation and ANA is expected to begin during the second half of 2022. - Green banking (technical proposal - in design): Requires a technical proposal and an alliance (agreement) between a financial entity and Profonanpe: Under the leadership of the Innova Project and with the technical assistance of the UOF of Financial Sustainability of SERNANP and the UGP, during the first semester of 2022, meetings were held with the Caja Municipal de Ica, in order to identify the target public to offer them banking products or benefits. During the second half of 2022, it is expected that the products to be offered will be defined and an agreement between the Caja Municipal de Ica and Profonanpe will be signed. Ind.R2.2c Number of NPA mechanisms that have been implemented in the 4 project NPAs. 2021 target in the results framework: 1 financial mechanism implemented. “Financial mechanism implemented” is when the mechanism generates or attracts financial resources, which has not been possible to date, due to the lockdown measures established by the Peruvian government in 2020 and 2021 and the delay in obtaining/hiring specialized consultants for the studies. - Remuneration Mechanism for Ecosystem Services (MERESE). It does not require a Law, but it does require a technical proposal and an agreement between SERNANP and the service provider. During the first half of 2022, the consultancy was completed with the purpose, among others, of identifying the NPAs with the greatest potential to develop a MERESE, based on their water contribution in their different areas of influence (supply characteristics) and the potential stakeholders willing to establish this mechanism in NPAs and identify the most viable strategic stakeholders for the implementation of a MERESE Hídrico and choose a NPA with the most relevant experience to start with the implementation of this. In this regard, the Allpahuayo Mishana National Reserve was chosen as the Amazonian NPA with the greatest potential to develop a water compensation mechanism. Conversations began with the Loreto Drinking Water and Sanitation Company (Empresa Prestadora de Servicios de Saneamiento de Agua Potable y Alcantarillado de Loreto S. A. -hereinafter SEDALORETO), the National Superintendence of Sanitation Services (hereinafter SUNASS) and the governance table, so that the Allpahuayo Mishana is part of the MERESE under development. In this sense, the Intervention Plan for the water compensation mechanism f was sent to SEDALORETO. On July 6, 2022, SEDALORETO published in El Peruano, the Resolution of the Board of Directors N 052-2022-SUNASS-CD, which approved the draft resolution that would establish the tariff formula, tariff structure, management goals and maximum costs of the units to determine the prices of collateral services of sanitation services, which would be applicable by SEDALORETO during the regulatory period 2022-2027, which is part of the necessary steps to implement the water MERESE. . In this regard, MERESE is expected to be implemented in Allpahuayo Mishana National Reserve during the second half of 2022 or first half of 2023. - Administration Contract (under evaluation): It requires a process at the request of a party or a merit-based competition at the initiative of SERNANP, selection of a non-profit organization, and the signing of a management contract; it does not require a Law. In this regard, during the first half of 2022, a consulting firm was hired to develop a study to i) identify financial mechanisms associated with ecosystem services or others in the framework of management contracts and ii) identify and prioritize NPA with the potential to be granted in management contracts. Component 3. Implementation of PdP Action Plan Measures to consolidate and improve the effective management of Amazon NPAs. At the beginning of Y2, the work plan for financing the enabling conditions of the basic and structural management levels of the 4 beneficiary NPAs was approved, and the USD 5M were transferred from the project to the transition fund of the PdP Initiative. The execution of those funds was, in 2020, largely impacted by the field work restrictions associated with the COVID-19 pandemic, and the Y2 activities in each of the 4 beneficiary NPAs were not executed as initially planned. The work plan for the 4 NPAs were updated during the year Y3, to take into account the different scenarios that could arise in the face of the temporal pandemic uncertainty. IND.R3.1a - Number of NPAs that achieve all benchmarks under the ¨basic¨ management level. The indicator does not have targets for Y3 but for Y4 is it expected that 4 NPA, as anticipated, will reach this basic management level. During the first semester of 2022, the update of the Tingo María NP master plan was approved, with which the NPA maintains the basic management level. Analysis of each enabling condition of the basic management level for each of the 4 beneficiary NPAs. - Chief of NPA designated by a Presidential Resolution. 4 NPA meet this condition. - % of the demarcated perimeter of the NPA (target 2023 in the results framework: ≥ 80% of the demarcated perimeter of the NPA). This condition is met by Abiselo River NP and Tingo Maria NP. • SN Tabaconas Namballe: On December 2021, the Chief of the NPA reported a demarcated perimeter of 65.42%, which implies an increase in the demarcated perimeter reported in the 2018 baseline (65.00%). Likewise, in 2021, 17 points were located in the field to install demarcation signs, equivalent to 35km or 34.58% of the perimeter to be demarcated. In the first half of 2022, 11 points have been certified, which is equivalent to 36.78 km or 34.21%. This means it is expected to meet the target before the end of the year, with an expected 83.15% demarcated perimeter. • RC Machiguenga: In 2020, the Chief of the NPA reported a demarcated perimeter of 62.00%, which implies an increase in the demarcated perimeter in relation to that reported in the 2018 baseline (20.00%). During 2021, the Chief of the NPA identified the location in the field of 10 points to install demarcation signs, equivalent to 116.50Km or 23.16% of the perimeter to demarcate, which have been certified in the first half of 2022 and which are expected to be installed. This would mean having a 85.16% of the perimeter demarcated before the end of the year. It is worth mentioning that it will not be possible to demarcate 100% of the NPA perimeter, because there is a risk for the staff in some areas that have a high incidence of activities related to drug trafficking. - NPA registered in the SUNARP NPA registry By 2020, the 4 beneficiary NPAs are registered in the SUNARP (National Superintendency of Public Registries) NPA registry. - Updated master plan • Río Abiseo PN and Tabaconas Namballe SN: During 2021, consultants were hired to provide technical assistance to have preliminary master plans, local actors were identified, and a roadmap was prepared for the participatory process and to ensure safeguard measures. • Tingo María National Park: The master plan was approved on January 20, 2022, through Presidential Resolution No. 027-2022-SERNANP. • RC Machiguenga: The NPA master plan was approved for the 2017-2021 period. During 2021, a consultant was hired to provide assistance to update its master plan and have a preliminary document, which was achieved. - Recognized management committee and executive committee of the current management committee. As of the first semester of 2022, the management committees of the 4 beneficiary NPAs and the executive commission of the PN Rio Abiseo and PN Tingo Maria are recognized. During the first semester of 2022, the executive commissions of the SN Tabaconas Namballe and the RC Machiguenga were updated. Ind.R3.1b. Number of NPAs that achieve all the benchmarks under ¨structural¨ management level. - Effective monitoring and control system (has ≥80% of required resources). - PN Rio Abiseo: The NPA requires a budget of USD 1,747,789.27 to have an effective monitoring and control system for the 2020-2023 period, of which the SERNANP treasury budget would finance USD 635,747.94, the GEF 6 PdP Project would finance USD 1,003,755.40, and there would be a budget gap of USD 108,285.93. Therefore, between SERNANP's treasury budget and the GEF 6 PdP Project, the NPA would have a budget of USD 1,639,503.34, which would represent 93.80% of the required budget for that period, which would reach the goal to consider that the NPA has an effective monitoring and control system. - PN Tingo María: The NPA requires a budget for an effective monitoring and control system for the 2020-2023 period of USD 1,038,165.57, of which the SERNANP treasury budget would finance USD 248,566.02, the GEF 6 PdP Project would finance USD 713,435.15, and there would be a budget gap of USD 76,164.38. Therefore, between SERNANP's treasury budget and the GEF 6 PdP Project, the NPA would have a budget of USD 962,001.09, which would represent 92.66% of the required budget for that period, which would reach the goal to consider that the NPA has an effective monitoring and control system. - SN Tabaconas Namballe: The NPA requires a budget to have an effective monitoring and control system, for the period 2020-2023, of USD 1,403,116.71, of which the SERNANP public treasury budget would finance USD 417,807.94, the transition fund of the GEF 6 PdP Project would finance USD 648,001.37, and there would be a budget gap of USD 337,307.39. Therefore, between SERNANP's treasury budget and the PdP-Amazon Initiative transition fund from GEF6, the NPA would have a budget of USD 1,065,809.32, which would be 75.96% of the required budget for that period, which would not reach the goal to consider that the NPA has an effective monitoring and control system. - RC Machiguenga: The NPA requires a budget to have an effective monitoring and control system, for the period 2020-2023, of USD 1,405,570.10, of which with the SERNANP public treasury budget would finance USD 135,013.69, the transition fund of the GEF 6 PdP Project would finance USD 1,147,907.09, and there would be a budget gap of USD 122,649.31. Therefore, between SERNANP's treasury budget and the GEF 6 PdP Project, the NPA would have a budget of USD 962,001.09, which would represent 91.27% of the required budget for that period, which would reach the goal established to consider that the NPA has an effective monitoring and control system. While three of the four NPAs have achieved the objective of having the necessary budget for effective monitoring and control system, the execution of the budget of PN Rio Abiseo has been 34.12%, PN Tingo Maria has been 32.95% and SN Tabaconas Namballe has been 23.29% (execution from 2020 to first semester of 2002), which should be evaluated as to what factors in addition to the restrictions that occurred due to the pandemic hinder the capacity for execution. RC Machiguenga, has had a budget execution of 69.80%. - NPA biological monitoring system implemented (has ≥80% of the necessary resources). In 2021, the chiefs of the 4 NPAs and the Monitoring, Surveillance and Control Department of SERNANP prioritized the species and ecosystems to be monitored. It was also established that the GEF 6 PdP project would finance the protocols and baselines for the species and that the ecosystems did not require financing to develop their protocols and baselines since they would be developed by SERNANP staff. However, during the first quarter of 2022, it was established that a budget would be required to prepare the protocols and baselines for the ecosystems to be monitored due to the heavy workload of the chiefs of the NPAs and the Monitoring, Surveillance and Control UOF. Likewise, they have taken the decision not to monitor some species agreed upon during 2021 and to include some others. It is worth mentioning that the aforementioned modifications will not imply major changes with respect to the budget planned for the 4 PNAs to implement the monitoring system in them. - PN Rio Abiseo: The NPA has prioritized the spectacled bear (Tremarctos ornatus) as the species to be monitored. Likewise, the NPA has its monitoring protocol for palm leaves approved, so its baseline will be funded during 2023. The need to monitor the taruka (Hippocamelus antisensis) and yellow-tailed choro monkey (Oreonax flavicauda) has been dismissed because the former is not found within the NPA and the latter is not threatened and will be incorporated into the master plan as research priorities. In the case of ecosystems, the development of protocols and baselines for vegetation cover and pastures for 2023 is incorporated. In this sense, a budget of USD 220,547.94 is required to have an effective monitoring system for the period 2021-2023, which will be fully financed with the transition fund of the GEF 6 PdP project, which would imply 100% of the budget required for that period, which would meet the goal established to consider that the PNA has an effective monitoring system. - NP Tingo María: The NPA has prioritized the guácharo (Steatornis caripensis), butterflies and native bees as the species to be monitored. The protocols for monitoring the aforementioned species were developed and approved in the first half of 2021. In addition, the protocol and baseline for vegetation cover will be prepared. A budget of USD 98,232.87 is required to have an effective monitoring system for the period 2021-2023, which will be fully financed with the transition fund of the GEF 6 PdP project, which would imply 100% of the budget required for that period, which would meet the goal established to consider that the NPA has an effective monitoring system. - SN Tabaconas Namballe: The NPA has prioritized as the species to monitor the Andean tapir (Tapirus pinchaque) approved the first semester of 2022, the spectacled bear (Tremarctos ornatus) and the romerillo (Podocarpus sprucei). It also incorporates the development of the protocol and baselines for vegetation cover and pastures, which will be developed in 2023. In this regard, a budget of USD 155,780.82 is required to have an effective monitoring system for the period 2021-2023, which will be financed entirely with the transition fund of the GEF 6 PdP project, which would imply 100% of the budget required for that period, which would meet the goal established to consider that the NPA has an effective monitoring system. - RC Machiguenga: The NPA has prioritized as the species to monitor the sachavaca (Tapirus terrestris), which will be approved in the second semester of 2022, and the protocol for wild species has been specified for wild pavas. The protocol and baseline for vegetation cover has also been incorporated and will be developed in 2023. In this regard, a budget of USD 161,369.86 is required to have an effective monitoring system for the period 2021-2023, which will be financed in its entirety with the transition fund of the GEF 6 PdP Project, which would imply 100% of the budget required for that period, which would meet the goal established to consider that the NPA has an effective monitoring system. Ind.R3.1c Number of NPAs that receive financing from the PdP Initiative, through the Project funds and its co-financing. As of June 30, 2022, the 4 PNAs are receiving funding from the GEF 6 PdP Project and co-financing from SERNANP for the enabling conditions of the basic and structural management levels.

Progress on safeguards The main activities that had safeguards implications in Y3 were boundary demarcation, creation of the master plans and the grievance redress mechanism (MAQS). Physical Demarcation: Two protocols/guidelines were developed, one on methodological guidelines for social and environmental analysis and the other on environmental guidelines for physical demarcation. In SNTN and RCM, trainings were given on the guidelines for physical demarcation / technical equipment. In SNTN, one Study of Social and Environmental Analysis of the physical demarcation was conducted. Social and environmental safeguards, including considerations on the management of solid, combustible, and hazardous waste were mainstreamed in TORs for the physical demarcation work. One check list was created to apply the monitoring or evaluation of the implementation in RCM. Support to the development of NPA Master Plans: SERNANP has clear established processes for Safeguards, but due to COVID-19 they have been delayed. Roadmaps have been created to ensure their implementation. Safeguards support for Master Plans ensured that proper participatory processes and stakeholder engagement is incorporated into the Master Plan process. The following was achieved: - 4 TORs for updating master plans incorporate safeguards considerations, including participatory processes. - 4 trainings on Social Policies and Safeguards to consultants in charge of developing master plans. - 4 technical assistance tracking matrices for stakeholder participation. - 4 face-to-face meetings with the Executive Boards of the CG of the four NPAs. - 4 roadmaps on the participatory process PM validated by the CG executive board. - 2 communication products/videos new guidelines of the participatory process of the FP. Grievance Mechanism (MAQS for its acronym in Spanish): The Government of Peru already had a grievance mechanism (the book of claim attention to citizenship), since Supreme Decree 042-2011, but it has only received one complaint thus far. The grievance mechanism, which complies with WWF and GEF’s requirements by being more accessible to stakeholders, was approved by Presidential Resolution. Claims, complaints, and queries can not only be made on the web, but there is also a physical notebook in each area, where complaints can be made in the native language of the population of the area. The MAQS is now operationalized, and training for the management and use of MAQS has started. So far it was noted that 3 consultations and 1 complaint have been made and appropriately handled. It is planned to develop a video tutorial, which can be shared on WhatsApp, Facebook, etc., to reach many more people. In addition, it is planned to develop an evaluation process after the system is propagated and implemented in all areas. Next Steps and Recommendations Project Y3 was instrumental for setting up the processes and guidelines for safeguards to inform and be incorporated into project activities. During 2022 the implementation of the guidelines, roadmaps and processes started. Physical demarcation activities will commence using the established roadmap for social and environmental analysis. Roadmaps have been developed for stakeholder participation in the updating of the master plans, and these will proceed according to those processes. Further training and dissemination of the MAQS will lead to greater institutionalization and to its operationalization. All of these efforts will lead to greater stakeholder participation and the implementation of safeguards measures to minimize any negative environmental or social impacts.

### Progress, Challenges, and Outcomes of Stakeholder Engagement

### (Based on Stakeholder Engagement Plan (SEP) or equivalent included in the ProDoc)

This item is based on section 4 Stakeholder Participation of the Prodoc, being the progress, challenges and results of the participation of stakeholders during the first semester of 2022, the following: - Partners of the GEF6-PdP Project Partners; Challenges; Progress/Results. MINAM; - Have the political and technical support of the government for the implementation of financial mechanisms and the PdP-Amazon Initiative.; - Various meetings have been held to obtain political and technical support for the financial mechanisms. - Participation in GEF and ASL meetings - Chairs the board of directors of the PdP-Amazon initiative.. SERNANP (Headquarters); - Strengthen the appropriation and incorporation of the activities of the GEF6-PdP Project in the institutional processes of SERNANP. - Reconcile with the corresponding SERNANP instances the incorporation of the targets of the Amazon PdP Implementation Strategy in the updating of the master plan and the master plans of the NPA. - Reconcile with the different instances of SERNANP so that the activities of the GEF6-PdP Project advance at the necessary pace to achieve the enabling conditions of the management levels in the 4 beneficiary NPAs and the financial mechanisms.; - Participation in the meetings of the board of directors of the Amazon PdP Initiative. - Appropriation and conciliation of the activities of the GEF6-PdP Project by the SERNANP UOF and incorporation of these in the institutional processes. Profonanpe; - Quarterly budget reports submitted in a timely manner to the WWF agency. - Strengthen the process of procurement of goods and services, within the framework of the transition fund of the Amazon PdP, to have these in a timely manner.; - Participation in the meetings of the board of directors of the Amazon PdP Initiative - Monthly coordination with the PMU and UC-PdP to see the progress in the acquisition of goods and consultancies of the Amazon PdP Initiative and the GEF6-PdP Project, as appropriate. - Several meetings have been held to strengthen the processes for the acquisition of goods and equipment and the selection and hiring of consultants.. WWF Agency; - Participation in the meetings of the board of directors of the Amazon PdP Initiative - Periodic meetings with the PMU to monitor the progress of the GEF6-PdP Project and provide technical assistance to the PMU.. Source: Self-made - ASL Program Partners ASL Partners; Challenges; Progress/Results. ASL projects (Brazil and Colombia). Productive Sustainable Landscapes Project in the Peruvian Amazon; - Strengthen the exchange of experiences between both ASL projects in country, related to financial sustainability.; - Good participation in Knowledge Management activities organized by the ASL, as explained in the Knowledge Management section of this report. The ASL representatives participated in the Annual Supervision Mission of the GEF 6 PdP project.. Source: Self-made National Actors National Actors; Challenges; Progress/Results. Ministry of Economy and Finance; - The GEF6-PdP Project does not have a financial mechanism that implies the involvement of the sector at the design or development level.. Ministry of Agriculture and Irrigation – National Water Authority; - Coordinate and involve the sector in the development of the financial mechanism to redistribute resources for the conservation of the basins within the NPA.. Ministry of Foreign Trade and Tourism; - Have the agreement of the sector for the new entry fee proposal.; - Informal consultations have been held to find out the opinion of the sector regarding the proposal for new entrance fees.. Congress of the republic; - Involve the legislative power in the Bill 788/21-PE.; - The Commission for Decentralization, Regionalization, Local Governments, and modernization of State Management of the Congress of the Republic recommended the approval of the bill. - Through a meeting of spokespersons of the Congress of the Republic, it was agreed to submit the proposed Law for discussion of the plan.. WWF - Peru; - Technical support to the PMU, through regular meetings. Moore Foundation; - Participation in the meetings of the board of directors of the PdP-Amazon Initiative - It has been complying with the commitments assumed regarding the counterpart contributions to the transition fund, as established in the operations manual of the PdP-Amazon Initiative - Crowdfunding campaign was launched. Private sector and society in general; - Raise awareness and involve in the financial sustainability of the PNAs; - The virtual dialogue table was held. The financial mechanism called collaboration points was developed.. Source: Self-made - Local Actors: Local actors participate in the GEF6-PdP Project within the framework of SERNANP's participatory processes for the enabling conditions of the basic and structural management levels, as appropriate. In the case of financial mechanisms at the site level, they will participate according to the particularity of each mechanism to be promoted. Local Actor; Challenges; Progress/Results. SERNANP (headquarters of the 4 beneficiary ANPs); - Strengthen the appropriation and incorporation of the activities of the GEF6-PdP Project in the management of the NPA Reconcile with the incorporation of the goals of the EI-Amazon in the update of the master plans of the PNAs of the Amazon biome - Provide technical and administrative support so that the activities of the GEF6-PdP Project advance at the necessary pace to achieve the enabling conditions of the management levels in the 4 beneficiary PNAs and the financial mechanisms.; - Appropriation of the activities of the GEF6-PdP Project - Reconciliation with the heads of the NPA of the inputs required to have an effective surveillance and control system, and the prioritized environmental elements of the monitoring system. Management committees of the 4 beneficiary ANPs (hereinafter CG); - Provide technical and logistical support to SERNANP, to generate the necessary conditions that contribute to promoting and ensuring the participation of the actors that comprise it, considering the safeguards, biosecurity measures and restrictions against COVID-19, according to determine by the Peruvian State - Provide technical support to SERNANP and the CGs through its executive board, to promote and contribute to increasing the number of women participating in the management committees, as established in the gender action plan of the project; - The CGs are recognized and in force in the 4 beneficiary NPAs - Members participate in the management of the 4 beneficiary NPAs, represented by their executive board Currently, participation has had to be permanently adapted to the measures and restrictions due to the COVID-19 pandemic. Executor of the Administration Contract of the Machiguenga Communal Reserve; - Provide technical and logistical support to SERNANP, to generate conditions that contribute to promoting and ensuring the participation of the actors that make up the ECA-MAENI, considering the safeguards, biosecurity measures and restrictions against COVID-19, according to determine by the Peruvian State - Strengthen the technical and financial capacities, which were not considered in the conception of the GEF6-PdP Project, but which are necessary for the effective management and financial sustainability of the NPA - Implement a micro capital for the ECA-MEANI for the process of updating the master plan, physical demarcation, and CG.; - The members of the executive board participate in the co-management of the RC Machiguenga - Profonanpe has been making a Due Diligence to grant micro capital to ECA-MAENI.. Local Government Institutions; - Site-level financial mechanisms involving them have not yet been identified or started to develop - They participate in the framework of the management committees of the 4 beneficiary NPA s. Source: Self-made In relation to guaranteeing social inclusion, the GEF6-PdP Project is aligned with the inclusion processes implemented by the Peruvian State, therefore SERNANP. In this sense, the incorporation of transversal approaches (gender, intercultural and intergenerational) and social and environmental safeguards have been developed in the various management documents, processes and activities implemented by the GEF6-PdP Project. [1] Amazon Sustainable Landscape Program (ASL).

### Information on Progress on Gender-Responsive Measures

### (As documented in the ProDoc, Results Framework, the Gender Action Plan or Equivalent)

During the last reporting period, the newly developed and adopted Gender Action Plan (GAP) - January 2021- was used to launch implementation of gender mainstreaming activities. Several activities were accomplished from project Components 2, 3 and 4, as per the GAP. These activities ensured the integration of gender dimensions into management processes, financial mechanisms, and gender disaggregated data collection for proper recording of both women and men’s participation in project consultations, events, trainings, workshops, etc. For example, in component 2, one of the major accomplishments included the incorporation of gender dimensions into the financial mechanisms of two NPAs. To analyze progress on gender (and other criteria) within these mechanisms, a check list has been prepared that measures participation, information management, conflicts, rights, indigenous populations, etc. Another example of an accomplishment from Component 3 includes the training of 30 people on the monitoring system to gather data and record progress on safeguards and gender mainstreaming, among other things. The project expects to be able to increase women’s participation in project activities and protected area management processes and committees by 5% every year until the end of the project. Another achievement was that during 2022, with technical assistance from the GEF6-PdP Project, SERNANP approved the Presidential Resolution No. 075-2022-SERNANP, which includes the requirement and methodology for including gender considerations in management committees’ operation at the national level. There is growing enthusiasm and interest in applying the GAP and using a gender lens among project actors and stakeholders. The evidence of this is in the results obtained during this reporting period on the gender mainstreaming results. The following table presents the accumulated progress to the first semester of 2022 of the GAP logical framework: Component/ Result; Indicator /Unit; End of project target; Baseline; Year 2021; Year 2022; Advance in the first semester 2022. RPAG GEF6.2.1. Differentiated information of women and men that shows values and benefits of the NPA, contributes to sensitize decision-makers in the public and private spheres Related product in POA 2.1.2 #3; IND PAGE GEF6 2.1. Number of events show differentiated information on the value and benefits of the NPA, incorporate the gender approach; 2; LB: 0; 1; 0/1; Planned for the second semester. RPAG. GEF6. 2.2. Financial mechanisms incorporate a gender analysis. Related product in POA 2.2.5 #5; IND PAGE GEF6 2.2. Number of financial mechanisms with gender analysis, determines the relevance or not of incorporating the approach in it.; 6; LB: 0; 2; 1/2; The relevance of incorporating the gender approach in the financial mechanism called collaboration points was determined. In the second semester, the gender approach will be incorporated into the same. RPAG.GEF6 3.1. The participation of women is strengthened with the implementation of protocols for the process of demarcation of the limits of the NPA Related product in POA 3.1.2 #3; IND PAGE GEF6 3.1. Number of protocols implemented by the headquarters of the 2 NPA s (SNTN, RCM) that incorporate the gender approach in the demarcation processes; 2; LB: 0; 2; Although the goal was met during 2021, during 2022 the same will be implemented in the SN Tabaconas Namballe and the RC Machiguenga. In this sense, during the first semester of 2022, the person of the 2 NPA has been trained for the demarcation process within the framework of the 2 protocols mentioned above, and the roadmaps for the demarcation processes in said NPA have been prepared.. RPAG.GEF6 3.2. Master Plan as a management tool for the NPA incorporates the gender approach, contributing to participatory management Related product in POA 3.1.2 #2; IND PAGE GEF6 3.2. Number of master plans that incorporate the gender approach; 4; LB:0; 1; 0/3; Three monitoring matrices have been prepared for the mainstreaming of the gender approach in the master plans. Likewise, technical assistance has been provided to the 3 PNAs to incorporate the gender approach in the process of updating the master plans.. RPAG. GEF6 3.3. Management committees with strengthened capacities, promote the participation of women Related product in POA 3.1.2 #6; IND PAGE GEF6 3.3. Number of female representatives participating in the management committee; 15%; LB: 33 women participate in the CG of 4 NPA (2020) PNA; TOTAL; M; H. SNTN; 36; 5; 31. PNTM; 64; 15; 49. PNRA; 26; 9; 17. RCM*; 30; 4; 26. Total; 156; 33; 123.; 0; 0/5%; Planned for the second semester During 2022, with technical assistance from the GEF6-PdP Project, SERNANP approved Presidential Resolution No. 075-2022-SERNANP, which includes a gender approach in management committees at the national level.. RPAG GEF6 3.4. The surveillance and control plans incorporate and implement the gender approach for the activities that are financed with the project Related product in POA 3.1.2 #6; IND PAGE GEF6 3.4. Number of women and men who are part of surveillance and control actions participate in awareness raising and training on social and gender safeguards; 90; LB: 16 people W:8 H:8 (Year 2020) PNA; TOTAL; M; H. CV; 62; 15; 47. GO; 43; 9; 3. 4. GV; 56; 29; 27. Total; 161; 53; 108. CV; Surveillance Committee GO: Official park rangers GV: Volunteer park ranger; 30; 0/30; Planned for the second semester. RPAG GE6 4.1. Good practices and lessons learned from the participation of women and/or mixed groups contribute to effective management of the PNAs Related product in POA 3.1.2 #6; IND PAGE GEF6 4.1. Number of events in which good practices and/or lessons learned from women and/or mixed groups that contribute to effective management of the PNAs are socialized; 3; LB: 0; 1; 0/1; Planned for the second semester.

### Knowledge Activities / Products

### (When Applicable, as Outlined in Knowledge Management Approach in the ProDoc)

- SERNANP proposed the ASL to develop an exchange between ASL countries in NPA conservation agreements. The event was held in the second quarter of the year. This exchange of experiences strengthened Sernanp's tool of conservation agreements. - SERNANP´s Monitoring and Control Department, together with the manager of the Tabaconas Namballe NPA and members of the PMU participated in meetings of the ASL activity "Strengthening the capacity of governments and ASL communities to analyze wildlife data obtained from camera traps and Wildlife Insights", where the Tabaconas Namballe NPA is part of one of the project pilot NPAs for Peru, for monitoring the Andean tapir (Tapirus pinchaque) and the spectacled bear (Tremarctos ornatus). - SERNANP´S Environmental Management department and the PMU participated in meetings of the ASL activity "Strengthening regional collaboration to address the impacts of mercury pollution in the Amazon" which strengthened SERNANP´s capacities and knowledge about how other amazon countries are facing the impacts generated by mercury pollution in the Amazon. - SERNANP staff (headquarters and NPA) participated in the "Community Tourism Course", within the framework of the ASL. - The event "Exchange of Experiences on Gender mainstreaming in the Management of NPAs" was developed virtually with the participation of the 4 project NPAs, including their managers, their management committees, SERNANP staff and ECA MAENI. In the event participated 41 people (28 women and 16 men). - Two online events were organized by the PMU, via the online platform of ¨El Comercio¨, one of the most popular newspapers in Perú. The first virtual event was organized at the end of 2021 with the objective of creating awareness on the value of NPAs. The second event was organized at the beginning of 2022 with the objective of creating awareness on how the general public can collaborate in the conservation of the NPAs.

### Adaptive Management

Category of change; Description of the change; Justification; Date of No-Objection by WWF GEF. Major Amendments. ☐Project Scope. ☐ Project Objective. ☐>5% Increase in financing. Minor Amendments. ☐ Results framework. ☐ Components and cost. ☐Institutional and implementation arrangements. ☐Financial management. ☒Implementation schedule; Some activities have a delay, with respect to the original PRODOC timeline, especially those related to field work and consultations, and also to procurement of specialized services, which has been difficult to secure in Perú.; - Field restrictions due to the COVID pandemic. - Political instability due to turnover of high level. - Cancellation of consultancies due to underperformance of companies or consultants and the need to find alternative solutions. - Lack of expression of interest submitted to consultancies call for proposals.; Every year, in the supervision mission, and when we approve the annual work plan and budget. And halfway through the project year, when we do the 6 month Project Progress Report review.. ☐ Executing Entity. ☐Executing Entity Category. ☐Minor project objective change. ☐ Safeguards. ☐ Risk analysis. ☐ Increase of GEF project financing up to 5%. ☐ Co-financing. ☐ Location of project activity. ☐ Other: <fill in>. In general terms, the total budget for 2022 has not been modified. However, there have been budget adjustments between outputs.

### Geolocation Information

Please provide a location name, latitude and longitude (04 decimal points) or, as applicable, a GEOname ID for locations of GEF-financed activities under this project. Location and activity description is optional. Maps or shapefiles are recommended, but optional. Please use this Guide as a reference. Location Name; Latitude; Longitude; Geo Name ID; Location & Activity Description (Optional). Tingo María National Park (PNTM); -9.36985; -76.00287; PA Management. Río Abiseo National Park (PNRA); -7.72609; -77.22932; Pa Management. Tabaconas Namballe National Sanctuary (SNTN); -5.157; -79.26817; Pa Management. Machiguenga Communal Reserve (RNM); -11.845847; -73.399269; Pa Management.

Annex I: Rating Scales and Guidance

### Development Objective Rating

The project Development Objective (DO) rating is quantified by analyzing progress against the Results Framework according to the rating scale below. Note that the average is not taken across component averages, but rather across all indicators in the Results Framework. No percent achieved should surpass 100% even if the target is exceeded.

DO Rating scale

| Rating | % Achievement of Results Framework targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100% |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate DO Rating from Results Framework

| Objective/Component/ Outcome | Indicator | Unit | Target Y1 | Achieved Y1 | Percent achieved Y1 |
| --- | --- | --- | --- | --- | --- |
| Project Objective | Indicator 1 | # policies | 5 | 4 | 80 |
|  | Indicator 2 | # ha | 1,000,000 | 900,354 | 90 |
| Component 1 |  |  |  |  |  |
| Outcome 1.1 | Indicator 3 | # beneficiaries | 500 | 410 | 82 |
| Outcome 1.2 | Indicator 4 | # sites | 10 | 12 | 100 |
| Component 2 |  |  |  |  |  |
| Outcome 2.1 | Indicator 5 | % score | 80% | 75% | 93.75 |
| Average of total |  |  |  |  | 89.15 |

### Implementation Progress Rating

The project Implementation Progress (IP) rating is based on progress against the annual workplan, based on the rating scale provided below.  Note that the average is not taken of the component averages, but rather across all indicators in the workplan. No percent achieved should surpass 100% even if the target is exceeded.

IP Rating scale

| Rating | % Achievement of annual workplan targets (average) |
| --- | --- |
| Highly Satisfactory (HS) | 100 |
| Satisfactory (S) | 80 – 99 |
| Moderately Satisfactory (MS) | 60 – 79 |
| Moderately Unsatisfactory (MU) | 40 – 59 |
| Unsatisfactory (U) | 20 – 39 |
| Highly Unsatisfactory (HU) | Below 20% |

Guiding Example: How to calculate IP Rating from AWP&B

| Project Activities Y1 | Unit | Target | Achieved | Percent Achieved |
| --- | --- | --- | --- | --- |
| Component 1 |  |  |  |  |
| Activity 1.1.1 | Sites | 5 | 4 | 80 |
| Activity 1.1.2 | Households | 120 | 122 | 100 |
| Average Component 1 |  |  |  | 90 |
| Component 2 |  |  |  |  |
| Activity 2.1.1 | Plans | 6 | 5 | 83 |
| Activity 2.1.2 | Reports | 2 | 2 | 100 |
| Activity 2.1.3 | Proposals | 10 | 7 | 70 |
| Average Component 2 |  |  |  | 84.3 |
| Component 3 |  |  |  |  |
| Activity 3.1.1 | Trips | 2 | 0 | 0 |
| Activity 3.1.2 | Trainings | 4 | 3 | 75 |
| Average Component 3 |  |  |  | 37.5 |
| Average achievement of all activities in workplan |  |  |  | 72.57 |

### Risks

Examine whether the project faces substantial risks in terms of the sustainability of project results. Please rate individually identified project risks (reference ProDoc, previous reports, Safeguards documents, etc) according to the rating scale and use all assessed risks to determine an overall or average risk.

Risk Rating Scale

| Rating |  |
| --- | --- |
| High Risk (H) | There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks. |
| Substantial Risk (S) | There is a probability of between 51% and 75% that assumptions may fail to hold, and/or the project may face substantial risks. |
| Modest Risk (M) | There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |
| Low Risk (L) | There is a probability of up to 25% that assumptions may fail to hold or materialize, and/ or the project may face only modest risks. |

Guiding example: How to determine Risk Rating from Risk Analysis in PPR

| Risk Description | Risk Rating | Notes |
| --- | --- | --- |
| Elections – change of leadership lead to not holding up to commitments | Substantial | If there is a party change, the MOU protected area designation may be thrown out. From our research, the party change is highly likely. See mitigation plan. |
| The newly established coordination mechanism does not meet regularly, and coordination fails | Modest | There is a history of newly established mechanisms not having the intended effects – which is partially due to limited resources and partially due to lack of buy-in. See mitigation plan. |
| The new equipment given to rangers will fail at some point and there will be no expert or replacement parts available to fix. | Substantial | Focal person of the lead ministry is engaged in multiple work. So has given very least priority to the project, wanted to take the position as PCC coordinator, however, has least concern in project implementation. |

After assessing each individual risk according to the risk rating scale, the overall risk is identified as Substantial given that two of the three risks are Substantial, and one is Moderate. This rating is qualitative in nature and considered the best estimate for the average risk the project is facing.

Start date is grant agreement signature or soft start.

As specified in the CEO Approval/ Endorsement or subsequent revision.

Should be no more than 12 Months after the expected closing date. Please keep current.

Date of Submission of Final PIR (when operations are complete).

This 3rd PIR covers the third year of the project (2021) and includes updates from the first semester of 2022.

SERNANP assess the conservation status of a particular NPA through an official methodology that measures the probability of occurrence of negative environmental impacts by human activities. The conservation status percentage for a given NPA is a proxy for the percentage of the NPA that doesn´t present negative impacts by human activities.