| Table 1. PROJECT RESULTS FRAMEWORK |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT / OUTCOME | INDICATOR / UNIT | MEASUREMENT AND DESCRIPTION | METHOD / SOURCE | BASELINE | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 |
| Objective Indicators |  |  |  |  |  |  |  |  |  |  |
| Project Objective: To promote long-term financial sustainability for the effective management of the National System of Natural Protected Areas of Peru (SINANPE) for the protection of globally important biodiversity and ecosystem services in the Amazon Biome. |  |  |  |  |  |  |  |  |  |  |
| Sustainable Financing | IND. 01- Achieve single close to cover the financial gap (estimated between $60-70M) for the management of the Amazon natural protected areas (NPAs). Target: Single Agreement achieved ($70 million) and closing conditions agreed to. | Non Cumulative Single close agreement is defined in prodoc. | Single close agreement signed. Legal Terms sheet and Memorandum of Understanding signed by the partners of the Initiative as part of the Single Agreement. | In June 2018, signature of MdE have not happen and $40M have been currently committed towards single close. | Single close signed for 70M |  |  |  |  |  |
| Effective management | IND.O2- # of hectares with improved METT score due to Project intervention Target: 530.327,47 hectares corresponding to selected NPAs with improved METT score due to Project intervention | Cumulative METT calculated annually and assessed at the end of the project. Los puntajes del METT de las 4 ANP se reflejarán en la línea de base, en consulta con cada Jefe del ANP. | Standard METT score assessed by Project team The number of hectares will be determined based on the areas of the NPAs that improve their score.. The number of hectares will be determined based on the areas of the NPAs that improve their score. | NPA; Área (ha); Baseline. Machiguenga; 218.905,6; 55/90 (61.1%). Rio Abiseo; 274.520; 63/96 (65.6%). Tabaconas-Namballe; 32.124,87; 50/96 (52.1%). Tingo María; 4.777; 64/96 (66.7%). |  |  |  |  |  | 530.327,47 |
|  | IND.O3- Number of selected NPAs that maintain or improve their conservation status (%). Target: 4 NPAs selected by project maintain or improve their conservation status. | Cumulative Improvement or maintenance of conservation status determined by standard scorecard. To be measured annually and at baseline.(Degree of area impacted) . | This is a standard scorecard used by SERNANP to test for anthropogenic activities/drivers for affecting biodiversity - no CC- i) overuse of resources, ii) pollution, iii) displacement of native species, iv) habitat loss. Link is available at: http://www.sernanp.gob.pe/documents/10181/12318/11+Doc+Trbajo+SISTEMA+DE+MOITOREO+DEL+ESTADO+DE+CONSERVACION-GRILLAS.pdf/49265472-1895-4b19-bf38-718aeab25bfe | 0 NPA |  |  | 4 NPA |  |  | 4 NPA |
| Outcome Indicators |  |  |  |  |  |  |  |  |  |  |
| Component 1: Development of a multi-partner, public-private initiative for long-term financial sustainability of the NPAs in the Peruvian Amazon |  |  |  |  |  |  |  |  |  |  |
| 1.1 Government and donor commitment secured for a long-term financial sustainability initiative for effective management of Peru’s Amazon NPAs | IND.R1.1- Number of closing conditions developed to generate commitment between government and donors Target: 5 of the 9 MoU conditions developed (see details of conditions and measurement of indicator achievement in the Indicators description Annex) | Non Cumulative The conditions considered for this indicators are those directly related to the generation of commitments amongst the partners of the MoU | Minutes of the PdP Initiative Steering Committee, informing on approval of conditions Each condition has a methodology to determine its achievement | 0 conditions achieved in June, 2018 | 5 |  |  |  |  |  |
| 1.2 PdP Initiative for the financial sustainability of Amazon NPAs operationalised | IND.R1.2- Number of conditions developed to operationalise the MoU in an efficient and effective way Target: 5 of the 9 MoU conditions developed (see details of conditions and measurement of indicator achievement in the Indicators description Annex | Non Cumulative The conditions considered for this indicators are those directly related to facilitate the operationalisation of the PdP Initiative | Minutes of the PdP Initiative Steering Committee, informing on approval of conditions Each condition has a methodology to determine its achievement | 0 conditions achieved in June, 2018 | 2 |  | 2 |  |  |  |
| 1.3 PdP mainstreamed in SERNANP and sectors related to management and financing of Amazon NPAs | IND.R1.3a- Number of high level official strategic documents that incorporate PdP Target PdP Initiative incorporated in the new Master Plan of SINANPE | Non Cumulative | SINANPE´s Master Plan The conditions to consider when PdP Initiative has been incorporated in SINANPE’S Master Plan are defined in the Indicators sheet annex. | 0 |  |  | 1 |  |  |  |
|  | IND.R1.3b- Number of NPAs Master Plans that incorporate financial planning according to PdP Implementation Strategy Targets will be established according to SERNANP’s plans for year 2 and 5 | Cumulative Financial planning of master plans means that the plans include structural and optimal level measures, according to the PdP financial model. | NPA Master Plans The indicator sheet annex specifies the conditions to consider that financial planning according to PdP IA has been incorporated in the NPAs Master Plans. | 0 (NPA Master Plans, in June 2018, include certain financial planning aspects around costs and have targets related to the PdP Implementing Strategy. However, they don't include measures for all the PdP IS targets and that is why the baseline is 0) |  |  | 9 | 6 | 4 |  |
| Componente 2: Diversificación de fuentes para incrementar el financiamiento del ANP |  |  |  |  |  |  |  |  |  |  |
| 2.1 Demostración de valores y beneficios de ANP para aumentar el apoyo público y privado al PdP y los nuevos mecanismos de financiamiento | IND.R2.1-Número de eventos que generan concientización sobre la importancia de la sostenibilidad financiera para una gestión efectiva en las ANP Meta: 4 eventos que generan concientización elaborados | Acumulativa | En la ficha del indicador se especifican las condiciones para considerar que un evento permite generar conciencia. | 0 |  |  | 2 | 4 |  |  |
| 2.2. Mayores opciones de financiamiento sostenible de las ANP | IND.R2.2a- Porcentaje de aumento en el presupuesto público que el SERNANP contribuye a la Iniciativa PdP-Amazonía . Metas: 10% al final del proyecto. | No acumulativa El presupuesto que contribuye a la Iniciativa PdP-Amazonía sería recolectado de los servicios que las ANP brindan a nivel de sitio o a nivel de sistema (recursos autogenerados o RDR, o DyT), a través de mecanismos financieros nacionales y de ANP. Los fondos solo serán contabilizados cuando sean razonablemente determinados para ser un resultado de la intervención del proyecto (según los criterios establecidos en la ficha del indicador). | Aumento del presupuesto público mediante recursos autogenerados (recursos directamente recaudados o RDR). POA e informes trimestrales y anuales de la gestión de las ANP. Portal de Transparencia Económica del MEF: https://www.mef.gob.pe/es/seguimiento-de-la-ejecucion-presupuestal-consulta-amigable Plan Operativo Institucional del SERNANP (POI) | RdR año base 2017 es de aproximadamente US$ 3 millones para las 38 ANP de la Amazonía, y las DyT es 0 |  |  |  |  |  | 10% |
|  | IND.R2.2b - Número de mecanismos financieros a nivel nacional con propuestas técnicas y/o legales elaboradas Meta: 3 mecanismos nacionales que cuentan con propuestas legales y técnicas elaboradas, al final del proyecto. | Acumulativa Los mecanismos financieros a nivel nacional se definen como aquellos que: - Pueden o no requerir cambios normativos o requerir una decisión política sectorial específica. - Los recursos financieros generados pueden ser destinados a cualquiera de las 70 ANP del sistema. | Documentos de propuesta legal y/o técnica | 0 mecanismos nacionales |  |  | 1 | 2 | 3 |  |
|  | IND.R2.2c- Número de mecanismos a nivel de ANP que han sido implementados en las ANP pre-seleccionadas del Proyecto Meta: 3 mecanismos a nivel de ANP | Acumulativa Mecanismo “implementado” es aquel que genera ingresos adicionales (RdR y DyT) a los existentes en el año 2017 en aquellas ANP que se implementen los mismos. Se considerará la implementación del mecanismo, si es razonablemente atribuible al proyecto. | Documentos oficiales Registro de recaudación de los mecanismos Se considerará a un mecanismo razonablemente atribuible al proyecto si cumple con los criterios establecidos en la ficha del indicador | 0 mecanismos a nivel de ANP |  |  | 1 | 2 | 3 |  |
| Componente 3: Implementación de las Medidas del Plan de Acción del PdP para consolidar y mejorar la gestión efectiva de las ANP de la Amazonía |  |  |  |  |  |  |  |  |  |  |
| 3.1 Mejoras en los niveles de gestión efectiva contribuyen a la conservación de la biodiversidad, manejo sostenible de los bosques y de los recursos naturales, y mantenimiento de los servicios ecosistémicos en 2 a 4 ANP de la Amazonía. | IND.R3.1a - Número de ANP que alcanzan el nivel de gestión básico Meta: La meta final es que 4 ANP directamente apoyadas por el financiamiento del Proyecto GEF6-PdP a través del Fondo de Transición (PN del Río Abiseo, PN Tingo María, SN Tabaconas Namballe y RC Machiguenga) alcancen el nivel «básicos» de gestión, considerando para ello el cumplimiento de todas las condiciones habilitantes planteadas en la EI-Amazonía para dicho nivel de gestión. | No acumulativa Las ANP se seleccionarán entre las 6 seleccionadas en la fase preparatoria y recibirán financiamiento del Proyecto GEF6-PdP a través del Fondo de Transición. El nivel básico de gestión se basa en criterios establecidos por el SERNANP, detallados en la ficha del indicador. | Informe de avance anual de la EI-Amazonía Informes de implementación de los planes maestros Estrategia de implementación del del Programa Patrimonio Natural del Perú en el Bioma Amazónico El equipo revisará el avance de cada criterio en la gestión «básica» en función de los reportes arriba mencionados. | 1 PN Tingo María. |  |  |  |  |  | 4 ANP |
|  | IND3.1b - Número de ANP que alcanzan el nivel de gestión estructural Meta: La meta final es que 4 ANP directamente apoyadas por el financiamiento del Proyecto GEF6-PdP a través del Fondo de Transición (PN del Río Abiseo, PN Tingo María, SN Tabaconas Namballe y RC Machiguenga) alcancen el nivel «estructural» de gestión, considerando para ello un 100% de cumplimiento de condiciones habilitantes. | No acumulativa El nivel estructural de gestión se basa en criterios establecidos por el SERNANP, detallado en la ficha del indicador. | Informe de avance anual de la EI-Amazonía Informes de implementación de los planes maestros Estrategia de implementación del del Programa Patrimonio Natural del Perú en el Bioma Amazónico El equipo revisará el avance de cada criterio en la gestión «estructural» en función de los reportes arriba mencionados, en contraste con las metas planteadas en la EI-Amazonía | 0 |  |  |  |  |  | 4 ANP |
|  | IND3.1c - Número de ANP de la Amazonía que están recibiendo financiamiento de la Iniciativa PdP-Amazonía, a través de los fondos del Proyecto GEF6-PdP y la cofinanciación Meta: 4 ANP, se evalúa al año 3 (2) y al año 6 (4). (PN del Río Abiseo, PN Tingo María, SN Tabaconas Namballe y RC Machiguenga) | Acumulativa Las ANP se seleccionan en la fase preparatoria y recibirán financiamiento del Proyecto GEF6-PdP a través del Fondo de Transición; y de la cofinanciación puede ser a través de recursos estatales (RDR y DyT) | Informes de implementación de los planes maestros Estrategia de implementación del del Programa Patrimonio Natural del Perú en el Bioma Amazónico El equipo revisará el avance del flujo de financiamiento y de la implementación de las mejoras de los niveles de gestión en función del reporte de implementación de la EI-Amazonía y el Reporte del anual de los recursos financieros disponibles para la gestión básica y estructural, del Sistema a toda fuente de las ANP (SPE), o POA a toda fuente unificado, | 0 |  | 2 ANP | 4 ANP |  |  |  |
| Componente 4: Coordinación y M y E del Proyecto |  |  |  |  |  |  |  |  |  |  |
| 4.1 Plan de M&E finalizó con la medición, la observación y el reporte oportuno para ayudar en la toma de decisiones por resultados y la gestión adaptativa. | IND.R4.1a- Validación/modificación formal de la teoría de cambio durante el ejercicio de reflexión Meta: Un ejercicio de reflexión/reunión por año | Teoría del cambio (TdC) es la lógica de cómo las estrategias del proyecto conducirán a los resultados esperados. El TdC se ilustra mediante el diagrama de cadenas de resultados en el ProDoc. | La validación/modificación de la TdC se basará en un ejercicio formal que reúna a la UGP con otros actores interesados relevantes para revisar los datos de M&E, y los informes de campo/retroalimentación de los actores interesados (según corresponda) proporcionados a la UGP. Esta información será considerada al revisar las cadenas de resultados del proyecto (teoría del cambio). El equipo determinará si la teoría del cambio sigue siendo válida y si son necesarias modificaciones o estrategias para la Teoría del Cambio o para el proyecto. Estos cambios serán propuestos en el próximo plan de trabajo anual y las reflexiones serán reportadas en el Informe de Avance del Proyecto (PPR). | La Teoría del Cambio (cadenas de resultados) en el Prodoc sirve como línea de base. | 1 | 1 | 1 | 1 | 1 | 1 |
| 4.2 Los datos de seguimiento y evaluación de proyectos y lecciones aprendidas son transparentes, participativas y se comparten con los actores interesados para contribuir a la coordinación, la gestión del conocimiento y el logro de los resultados del programa. | IND.R4.1b- Las mejores prácticas en temas prioritarios relacionados con el mecanismo financiero para las ANP y la eficacia de la gestión en la Amazonía se documentaron de manera transparente y ampliamente difundida con los actores interesados relevantes. Meta: Anualmente se analizan las mejores prácticas; las lecciones aprendidas son compartidas y subidas al sitio web del programa una vez al año y son promocionadas ampliamente con los actores relevantes. | Los actores interesados incluirán a los miembros de otros subproyectos en el programa más grande. | Las mejores prácticas se desarrollan desde el taller de reflexión 4.1 y un consultor contratado recopiló las mejores prácticas y lecciones aprendidas. Estos se suben al sitio web dedicado al Programa Regional. |  | 1 | 1 | 1 | 1 | 1 | 1 |

Tracking Project Progress in Results Framework for Y1

| COMPONENT/RESULT | INDICATOR/UNIT | SOURCE | TARGET Y1 | ACHIEVED Y1 | % ACHIEVEMENT |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicadores del objetivo |  |  |  |  |  |  |
| Sustainable Financing | IND. 01- Achieve single close to cover the financial gap (estimated between $60-70M) for management of the Amazon natural protected areas (NPAs). Target: Single Agreement achieved ($70 million) and closing conditions agreed to. | Memorandum of Understanding signed (Single Agreement) signed | 01 Single Agreement signed for US$ 70M | Single Agreement signed | 100% |  |
| Effective Management | IND.O2- # of hectares with improved METT score due to Project intervention Target: 530.327,47 hectares corresponding to selected NPAs with improved METT score due to Project intervention | # of hectares | N/A | N/A | - |  |
|  | IND.O3- # of selected NPAs that maintain or improve their conservation status (%). Meta: 4 ANP seleccionadas del proyecto que mantiene o mejora su estado de conservación. | # of NPAs | N/A | N/A | - |  |
| Outcome Indicators |  |  |  |  |  |  |
| Component 1: Development of a multi-partner, public-private initiative for long-term financial sustainability of the NPAs in the Peruvian Amazon |  |  |  |  |  |  |
| 1.1 Government and donor commitment secured for a long-term financial sustainability initiative for effective management of Peru’s Amazon NPAs | IND.R1.1- # of closing conditions developed to generate commitment between government and donors Target: 5 of the 9 MoU conditions developed (see details of conditions and measurement of indicator achievement in the Indicators description Annex) | # of conditions | 5 | 5 | 100% |  |
| 1.2 PdP Initiative for the financial sustainability of Amazon NPAs operationalised | IND.R1.2- # of conditions developed to operationalise the MoU in an efficient and effective way Target: 5 of the 9 MoU conditions developed (see details of conditions and measurement of indicator achievement in the Indicators description Annex | # of conditions | 2 | 2 | 100% | The conditions met were: - Institutional arrangements including the documentation and the governance structures implemented (Milestones: 1. Steering Committee established, 2. Manual of Operations approved, 3. SERNANP - PROFONANPE Cooperation Agreement signed) - Systems and methodologies that allow the transparent management of PdP Transition Fund (Milestones: 1. Financial software updated and installed in PROFONANPE, and 2. PROFONANPE´s investment policy approved by PdP Steering Committee) |
| 1.3 PdP mainstreamed in SERNANP and sectors related to management and financing of Amazon NPAs | IND.R1.3a- # of high level official strategic documents that incorporate PdP Target PdP Initiative incorporated in the new Master Plan of SINANPE | SINANPE´s Master Plan | N/A | N/A | - | The project PMU is participating in the coordination meetings at SINANPE´s Coordination Council and at the level of the Strategic Development Department in SERNANP (in charge of the elaboration of SINANPE´s Master Plan) |
|  | IND.R1.3b- #of NPAs Master Plans that incorporate financial planning according to PdP Implementation Strategy Targets will be established according to SERNANP’s plans for year 2 and 5 | # of NPAs Master Plans | N/A | N/A | - | In Y1 the PMU has organized, in collaboration with SERNANPs Strategic Development Department, workshops to initiate the process for adequation and update of NPAs Master Plans: Workshops have happened in PN Tingo María, RN Allpahuayo Mishana, RC Machiguenga. |
| Component 2: Diversification of sources to increase NPA financing |  |  |  |  |  |  |
| 2.1 NPA values and benefits showcased to increase public and private support for PdP and new financing mechanism | IND.R2.1-# of events that generate awareness about the importance of sustainable financing for effective management of NPAs Target: 4 events completed that raise awareness | # of meetings or events | N/A | N/A | - |  |
| 2.2. Increased options for the sustainable financing of NPAs | IND.R2.2a- % increase of public budget that SERNANP contributes to the PdP-Amazon initiative for managing Amazon NPAs. Target: 10% at end of project. | % increase in public budget | N/A | N/A | - |  |
|  | IND.R2.2b - # of national financial mechanisms with technical and legal proposals developed for implementation Target: 3national mechanisms with legal and technical proposals for implementation by the end of the project. | # of national mechanism proposal documents | N/A | N/A | - |  |
|  | IND.R2.2c- # of NPA level mechanisms that have been implemented in the NPAs selected by the project. Target: 3 national NPA-level mechanisms | # Mechanisms implemented | N/A | N/A | - |  |
| Component 3: Implementation of PdP Action Plan Measures to consolidate and improve the effective management of Amazon NPAs |  |  |  |  |  |  |
| 3.1 Improvements in effective management levels contribute to the conservation of biodiversity, sustainable forest and natural resources management, and maintenance of ecosystem services in 2 to 4 Amazon NPAs . | IND.R3.1a - # of NPAs that achieve all the benchmarks under “basic” management Target: the final target is that the 4 PAs financed by GEF (NP Río Abiseo, NP Tingo María, NS Tabaconas Namballe and CR Machiguenga) achieve the basic management level, achieving 100% of the benchmark criteria. | # of NPAs | N/A | N/A | - | The baseline showed that NP Tingo Maria reached the basic level. |
|  | IND3.1b - # of NPAs that achieve all the benchmarks under “structural” management Target: the final target is that the 4 NPAs directly supported by GEF financing (NP Río Abiseo, NP Tingo María, NS Tabaconas Namballe and CR Machiguenga) achieve the structural level of management, achieving 100% of the benchmark criteria. | # of NPAs | N/A | N/A | - |  |
|  | IND3.1c - # of NPAs in Amazon receiving financing from PDP-Amazon initiative as a result of GEF6-PdP funds and cofinancing. Target: Y3 target is 2, Y6 target is 4.(NP Río Abiseo, NP Tingo María, NS Tabaconas Namballe and CR Machiguenga) | # of NPAs | N/A | N/A | - |  |
| Component 4: Coordination, Monitoring and Evaluation of Project |  |  |  |  |  |  |
| 4.1 M&E plan finalized with measurement, reflection and reporting on time to aid in results-based decision making and adaptive management | IND.R4.1a- Validation/Modification of the theory of change during reflection exercise. Target: 1 reflection exercise per year. | # reflection exercises on ToC per year | 1 | 1 | 100% |  |
| 4.2 Monitoring and evaluation data and lessons learned are transparent, participatory and shared with relevant stakeholders to contribute to coordination, knowledge management and achieving program results | IND.R4.1b-Best practices in priority topics related to financial mechanism for PA and management effectiveness in the Amazon documented transparently and disseminated widely with relevant stakeholders. Target: Annually analyzed best practices and lessons learned are shared and uploaded to program website once /year and widely promoted to relevant partners. | # reflection exercises on lessons learned per year | 1 | 1 | 100% |  |
| Average yearly progress |  |  |  |  | 100% | Rating: Highly Satisfactory (HS) |