## _Calc (hidden)
Rating text | Score
Highly Unsatisfactory (HU) | 1
Unsatisfactory (U) | 2
Moderately Unsatisfactory (MU) | 3
Moderately Satisfactory (MS) | 4
Satisfactory (S) | 5
Highly Satisfactory (HS) | 6
Unknown | 0
Not Rated | 0
for DevScore
|  | Person | PM/Coord | Budget Holder | LTO | GEF OFP | GTO
|  | Weight % | 20 | 25 | 25 | 0 | 30
For ImpScore
|  | Person | PM/Coord | LTO | GEF OFP | GTO
|  | Weight % | 25 | 35 | 0 | 40
Once you've filled in 2. Progress towards outcomes & 3. Implementation Progress
Please double click and press enter on Cells D20 and D21 |  | #VALUE!
#VALUE!

## Table of Contents
FAO-GEF Project Implementation Report
2025 – Revised Template
Period covered: 1 July 2024 to 30 June 2025
Table of Contents
1. BASIC PROJECT DATA
2. PROGRESS TOWARDS ACHIEVING PROJECT OBJECTIVE(S) (DEVELOPMENT OBJECTIVE) | Progress towards Achieving Project Objective(s) (Development Objective)
3. IMPLEMENTATION PROGRESS (IP) | Implementation Progress (IP)
4. SUMMARY ON PROGRESS AND CHALLENGES | Summary on progress, challenges, and outcomes
5.ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS):RISKS FROM THE PROJECT
6. RISKS TO THE PROJECT
7. FOLLOW-UP ON MID-TERM REVIEW OR SUPERVISION MISSION
8. MINOR PROJECT AMENDMENTS
9. STAKEHOLDERS' ENGAGEMENT
10. GENDER MAINSTREAMING
11. KNOWLEDGE MANAGEMENT ACTIVITIES
12. INDIGENOUS PEOPLES AND LOCAL COMMUNITIES INVOLVEMENT
13. CO-FINANCING TABLE
14. GEO LOCATION INFORMATION
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
IMPORTANT DISCLAIMER:
The final version of this PIR will be submitted to the GEF Secretariat.
The report will then be publicly available on the GEF website (click here).
Sensitive information should be submitted in Annex to be uploaded separately.
In such cases, please contact faogef-pir-support@fao.org for guidance.

## 1. Basic project data
1. Basic Project Data
General Information
Region: | Asia and the Pacific (RAP)
Country(ies): | VANUATU
Project Title: | Strengthening capacity in the Energy, Agriculture, Forestry, and other Land-use Sectors for Enhanced Transparency in the Implementation and Monitoring of Vanuatu’s Nationally Determined Contribution
FAO Project Symbol: | GCP/VAN/005/GFF
GEF ID: | 10761
Type of Trust Fund(s): | GFF
GEF Focal Area(s): | Climate Change
Project Executing Partners: | Ministry of Climate Change (MOCC) & Department of Environment protection and conservation (DEPC) , Department of Climate Change
Initial project duration (years): | 3 Years
Project Dates
GEF CEO Endorsement Date: | 2022-07-12
Actual Agency Approval Date | 2022-03-18
Project Implementation Start Date/EOD: | 2022-12-01
First Disbursement Date | 2024-01-31
Planned Project End Date/NTE1: | 30/11/2025
Revised project implementation End date (if approved)2: | 30/06/2026
Actual Completion Date: | n/a
Expected Financial Closure Date: | 2027-06-30
Funding
GEF Grant Amount (USD): | 1137215
Total GEF grant delivery (as of June 30, 2025 (USD): | 525356.65
Total Co-financing amount (USD)3: | 2994500
Total estimated co-financing materialized as of June 30, 2025: | 1100000
M & E Milestones
Date of Last Project Steering Committee (PSC) Meeting: | 29/04/2025
Expected Mid-term Review date5: | n/a
Actual Mid-term review date (if already completed): | n/a
Expected Terminal Evaluation Date6: | 2026-01-30
Overall ratings
Overall rating of progress towards achieving objectives/outcomes (cumulative): | Satisfactory
Overall implementation progess rating: | Satisfactory
Overall risk rating: | Substantial
Status
Implementation Status (1st PIR, 2nd PIR, etc. Final PIR): | 1st PIR
1 Date that was originally foreseen at the project’s operationalization and indicated in FPMIS. 2 If NTE extension has been requested and approved by the FAO-GEF Coordination Unit. 3 This is the total amount of co-financing as included in the CEO Document/Project Document. 4 Please refer to the Section 13 of this report where updated co-financing estimates are requested and indicate the total co-financing amount materialized. 5 The Mid-Term Review (MTR) should take place after the 2nd PIR, around half-point between EOD and NTE. The MTR report in English should be submitted to the GEF Secretariat within 4 years of the CEO Endorsement date. 6 The Terminal Evaluation date should be discussed with OED 6 months before the project’s NTE date.
Project Contacts
Contact | Name, Title, Division/Institution |  | E-mail
Project Coordinator (PC) | Stephanie Stephens |  | stephens.stephanie@fao.org
Budget Holder (BH) | Guangzhou Qu |  | Guangzhou.Qu@fao.org
GEF Operational Focal Point (GEF OFP) | Rolenas Tavue Baeraleo |  | rbaereleo@vanuatu.gov.vu
Lead Technical Officer (LTO) | Raushan Kumar |  | Raushan.Kumar@fao.org
GEF Technical Officer (GTO) | MdArfan Uzzaman |  | Md.Uzzaman@fao.org
Key Project Management Unit Personnel
Please indicate the composition of the PMU as per the Terms of Reference in the ProDoc. If any new position was establised during the project implementation, please insert it accordingly.
Position planned (as per ProDoc) | Position filled (Yes/No) | Start date, Name, Contact |  | Comments
National Project Coordinator | Yes | February 2023, Stephanie STEPHENS, stephens.stephanie@fao.org, tel: (+678) 7363198
Knowledge and data management Expert | Yes | September 2024, Jason Harry Obed, Jason.Harry@fao.org, tel: (+678) 524 2158
National GHG Inventory Reporting and MRV Expert | Yes | September 2024, Riddick Cevuard, Riddick.Cevuard@fao.org, tel: (+678) 761 6272
GHG inventory and MRV expert (part-time) (international) | No
Finance/Admin/Operations Associates | No

## Countries (hidden)
Select Country
Afghanistan
Åland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua and Barbuda
Argentina
Armenia
Aruba
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia (Plurinational State of)
Bonaire, Sint Eustatius and Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean Territory
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Cayman Islands
Central African Republic
Chad
Chile
China
China, Hong Kong Special Administrative Region
China, Macao Special Administrative Region
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Côte d’Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czechia
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Falkland Islands (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Territories
Gabon
Gambia
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey
Guinea
Guinea-Bissau
Guyana
Haiti
Heard Island and McDonald Islands
Holy See
Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Isle of Man
Israel
Italy
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Martinique
Mauritania
Mauritius
Mayotte
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands (Kingdom of the)
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North Macedonia
Northern Mariana Islands
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Réunion
Romania
Russian Federation
Rwanda
Saint Barthélemy
Saint Helena
Saint Kitts and Nevis
Saint Lucia
Saint Martin (French Part)
Saint Pierre and Miquelon
Saint Vincent and the Grenadines
Sint Eustatius and Saba
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Sint Maarten (Dutch part)
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Georgia and the South Sandwich Islands
South Sudan
Spain
Sri Lanka
State of Palestine
Sudan
Suriname
Svalbard and Jan Mayen Islands
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Turks and Caicos Islands
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States Minor Outlying Islands
United States of America
United States Virgin Islands
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Wallis and Futuna Islands
Western Sahara
Yemen
Zambia
Zimbabwe

## TypeofTrustFund (hidden)
Type of Trust Fund
Capacity-building Initiative for Transparency (CBIT)
Global Biodiversity Framework Fund (GBFF)
Global Environment Facility Trust Fund (GFF)
Least Developed Countries Fund (LDCF)
Special Climate Change Fund (SCCF)
Small Grants Program (SGP)

## FocalArea (hidden)
Focal Area
Multi Focal Area
Biodiversity
Chemicals and Waste
Chemicals/PoPs
Climate Change
Climate Change Adaptation
Climate Change Mitigation
International Waters
Land Degradation

## 2. Progress towards outcomes
2. Progress towards Achieving Project Objective(s) (Development objective)
(All inputs in this section should be cumulative from project start, not annual)
Please indicate the project’s main progress towards achieving its objective(s) and the cumulative level of achievement of each outcome since the start of project implementation.
Project or Development Objective | Outcomes | Outcome indicators | Baseline | Mid-term Target | End-of-project Target | Cumulative progress level at 30 June 2025 | % of cumulative progress | Progress rating
To develop Vanuatu's institutional and huma capacities for complying with Enhanced Transparency Framework (ETF) reporting requirements of the paris agreement and implementation and monitoring of vanuatu's Nationally Determined Contribution focussing on Energy, Agriculture, Forestry, and other land use sectors | Outcome 1
| 1.1.1 Institutional arrangements strengthened | (i)Qualitative gaps assessment report focusing on institutional, regulatory, human, technology, finance, and capacity building support needed, and stakeholder to meet the transparency framework of enhanced NDC actions. | 0 | At least 5 national agency/ministry related to ETF reporting as identified in the stakeholder section should be reviewed, and documented. | At least 10 national agency/ministry related to ETF reporting as identified in the stakeholder section should be reviewed and documented. | Currently the project has engaged and involved 12 government and non government agency to sign a MOA on data sharing also related to the ETF technical working group which has a draft TOR in place for review and endorsement by the MOCC. Under the LoA, the project has identified areas requiring support by developing sectoral planning and budgeting through consultations | 85% | Highly Satisfactory (HS)
|  | (ii)A national term of reference of working groups stating roles and responsibilities of stakeholders with specific guideline for participation of women (32 percent women) for data collection, sharing, and processing focusing on mitigation, adaptation, and addressing loss and damage (L&D) for observed and potential climate change impacts (e.g. extreme weather events and slow onset events). | Designated institutional working responsibilities exist for some ministry, but not sufficient for ETF. | Inter-ministerial agencies and other institutions identified for national MRV legal and regulatory framework | Formalized and published national MRV institutional terms of reference stating roles and responsibilities of stakeholders related to national MRV legal and regulatory framework | The TOR of the technical working group has been developed and finalised .Awaiting MOCC endorsement and to circulate the TOR to respective assign Project stakeholders | 75% | Highly Satisfactory (HS)
|  | (iii) An operational National ETF body. | 0 | Inter-ministerial agencies and other institutions identified for national MRV legal and regulatory framework |  | The ETF Working Group ToR is currently in draft form and was shared with the Technical Working Group members in August 2025. It has not yet been finalised. The project plans to organise a review workshop for both the ETF ToR and the Sectoral Data Working Group ToR with relevant project stakeholders. | 55% | Moderately Satisfactory (MS)
|  | (iv) Qualitative Assessment of Institutional | 0 | The National ETF roadmap is prepared and Adopted. | Established and operational National ETF body under the Climate Change Division of MECDM involving relevant ministries and entities for national ETF reporting. | Relevant project stakeholders that signed the data sharing agreement are looking into historical archive data and reporting template and available data governance related to the ETF reporting priorities. working closely with project team.There are few gaps especially with data collection methodology and tremplate which the project has consider to incorporate relevant ETF targets by sector into a standardize reporting template | 80% | Highly Satisfactory (HS)
|  | Scale -1 No designated transparency institution to support and coordinate the planning and implementation of transparency activities under article 13 of the paris agreement exists | 0 | Scale 2 Designated transparency institution exists, but with limited staff and capacity to support and coordinate implementation of transparency activities under Article 13 of Paris Agreement. Institution lacks authority or mandate to coordinate transparency activities under Article 13. | Scale 3. Designated transparency institution has an organizational unit with standing staff with some capacity to coordinate and implement transparency activities under Article 13 of the Paris Agreement. Institution has authority or mandate to coordinate transparency activities under Article 13. Activities are not integrated into national planning or budgeting activities | Government and non government agency identify as project stakeholders, has involve directly in few in country capacity building related to ETF and NDC specifically.(i) Workshop and training on ETF has been conducted, (ii) training on NDC review and sectorial data gaps has been conducted (iii) workshop /training on Climate Finance data reporting and activity reporting was also conducted to address the sectorial staff capacity building.The next training will focus on fomal education developement on MRV system which will be carried by the Nationa University of Vanuatu (NUV) | 90% | Highly Satisfactory (HS)
| 1.1.2 Sectoral transparency guidelines and protocols are established for enchanced NDC climcate change mitigation , adapatation and addressing L&D for observed and potential climcate change impacts (e.g extreme weather events and slow onset events) | (i) Number of regulatory frameworks reviewed and formulated guidelines and action plan | 0 | Based on the regulatory frameworks reviewed inter-ministerial agencies and other institutions identified for national guideline and action plan. | Published national guideline and action plan. | The project has contribute to support sectors and also as per the project framework planning, has achieved numerous reviewed and standard plans focus on the NDC and ETF. (i) the reviewed of the Data collection standard template, (ii) the review of the GHG calculation manual guideline (iii) the review of the Vanuatu NDC target 3 .With the current extension of the project LOA under DOCC, project has prioritise the review and development of GEDSI action plan which has already been developed by the sector but require a surface review to link to existing policies and sectorial NDC targets in specifics | 50% | Moderately Satisfactory (MS)
|  | (ii) Number of metrics and indicators for monitoring enhanched NDC actions focusing on climate change mitigation, adapation, and addressing L&D | 0 | Climate change mitigation (at least 4), adaptation (at least 4), and addressing L&D (at least 4). | Climate change mitigation (at least 6), adaptation (at least 6), and addressing L&D (at least 6). | This is well achieved with prioject funding through the review of the country's NDC 3 by DOCC and GGGI which outline the specific sectorial targets on specific thematic areas of mitigation, adaptation and Loss and damage .Further to that, reviewed has also identify gaps and constraits that each project stakeholder experience in terms of Climcate change reporting. | 100% | Highly Satisfactory (HS)
|  | (iii) Number of metrics and indicators for linking enhanched NDC with national Sustainable Development plan (NSDP) and their reporting | 0 | At least 4 | At least 6 | This was completed also during the NDC 3.0 review conducted by DOCC and GGGI.It outlines clearly the policy linkages from sectorial NDC targets to the national sustinable development plan of the government.The number of NDC indicators has increased by few sectors while remain the same for most sectors. At this phase, 6 metrics and indicators have been identified but still in draft. Below are the 6 metrics: 1. Climate Mitigation Targets: These targets focus on reducing greenhouse gas emissions across various sectors, including energy, transport, and waste management. 2. Climate Adaptation Actions: Indicators in this category measure the implementation of adaptation strategies, such as the development of climate-resilient infrastructure and the enhancement of community-based adaptation programs. 3. Green Employment & Youth Engagement: Metrics track the creation of green jobs and the involvement of youth in climate-related initiatives, promoting sustainable livelihoods. 4. Gender-Responsive Measures: Indicators assess the integration of gender considerations in climate policies and programs, ensuring equal participation and benefits for all genders. 5. Awareness and Capacity Building: Metrics evaluate the effectiveness of public awareness campaigns and capacity-building activities aimed at enhancing climate change knowledge among communities. 6. Reporting and Data Systems: Indicators monitor the establishment and maintenance of robust data systems for tracking climate-related progress and informing decision-making processes. | 95% | Highly Satisfactory (HS)
| 1.1.3 Established operational quality control and assurance mechanism | (i) Number of sectoral handbooks/protocols adopted (data collection, archiving, and data sharing) | 0 | Developed for at least 4 sectors. | Developed for at least 7 sectors (Forestry, Agriculture, Livestock, Energy, Transport, Industry, Waste) | This is under development especially guidline on data collection and data sharing but with standardization of data template and data historical archive activity within sector is in ongoing | 60% | Satisfactory (S)
|  | (ii) Number of sectoral data collection templates and guidelines | 0 | Developed for at least 4 sectors. | Developed for at least 7 sectors (Forestry, Agriculture, Livestock, Energy, Transport, Industry, Waste) | So far , project as agreed with project stakeholders to use a standard data collection template to avoid confusion and workload by each sector. Therefore, all data related to BTR will be incorporated and use in one template only also will be input into an open software, kobo collect toolbox app ,to make it much easier for data collection at each sector level.Currently the 8 sectors are targeted and involve directly in this project. The standard data collection template is yet to be socialised and trial-run (planned in september 2025) to the sectors and it will be utilized to collect data, starting October 2025 | 90% | Highly Satisfactory (HS)
|  | (iii) Number of MOU signed between the stakeholders for collection generation, archiving and dessimination of data focusing on enhanched NDC climate change mitigation, adaptation and addressing L&D for observed and potential climcate change impacts (e.g. Extreme weather events and slow onset events) | 0 | At least 5 MOU signed between national agency/ministry related to ETF reporting. | At least 10 MOU signed between national agency/ministry related to ETF reporting. | MOA that was drafted has been reviewed, approved and signed off by relevant sectors specify by project and DOCC.the stakeholder agency is 12 in total. | 100% | Highly Satisfactory (HS)
| Outcome 1.2 |  | 0
| Outcome 1.2.1 Strengthened guidelines on monitoring and reporting of climcate financing focusing on domestic and international sources, and both public and private sector | (i) A qualitative gap assessment report on needs, constraits and stakeholders on tracking climate finance enhanched NDC actions | 0 | At least 5 national agency/ministry related to climate finance identified and documented. | At least 10 national agency/ministry related to climate finance identified and documented. | This has been carried out by DOCC through GGGI, and also presented during the NDC 3.0 review .All sectors responsible has presented gaps and constraints related to NDC targets and reporting.This information is well documented.The current number of sector targeted is 8 including the Department of Agriculture and Rural Development, the Department of Forestry, the Department of Livestock, the Department of environmental Protection and Conservation, the Department of Energy, Vanuatu Bureau of Statistic, the Department of Climate Change and the Department of Finance | 95% | Highly Satisfactory (HS)
|  | (ii) Published and adopted sectoral methodologies, guidelines and protocols to collect, archive and dessiminate climate finance data, and training conducted on them | 0 | Developed for at least 4 sectors, and at least 2 training. | Developed for at least 7 sectors (Forestry, Agriculture, Livestock, Energy, Transport, Industry, Waste), and at least 4 training. | The DOCC LOA extended till 2026 will capture this component .But most importantly, the stakeholders agreed in using a standard data collection template .Data archiveing and data sharing is well detail in the signed MOA | 50% | Moderately Satisfactory (MS)
|  | (iii) Operational national climate finance reporting and monitoring (NCFRM) | 0 | Draft ToR and Involved national agencies are identified for national ETF body for national ETF reporting. | Operational national ETF body through govt resolution for national ETF reporting. | The workshops on climate finance tracking in Vanuatu were conducted on 28th and 30th May 2025. The ETF reporting is well presented in the MOA, and the ETF Terms of Reference have been developed. While stakeholder understanding of climate finance has improved, the ETF has not yet been operationalized. | 70% | Satisfactory (S)
| 1.2.2 Strengthened capacity of national climcate changes stakeholders to track the enhanched NDC adaptation actions | (i) Number of knowledge products/best practice documents prepared and dessiminated on monitoring and reporting of enhcnahed NDC adaptation actions. | 0 | At least 2 | At least 4 (of which at least one gender case study) | As mention above, the GENDSI component will be addressed in this LOA.Focuses mainly in developing a GEDSI action plan to be develop by GGGI funded by the CBIT project. Vanuatu BTR has been reviewed also and currently project is facilitating the country's fourth National Commuication report.Stakeholder on GEDSI action plan has happen | 60% | Satisfactory (S)
Outcome 2.1
| 2.1.1 Upgraded information Technology (IT) system for a robust MRV system hosted by MOCC based on the existing system | (i) Operational and enhanched online - based integrated MRV system | MRV system exists, but it is not updated to meet the ETF. | Hardware and software procured for enhanced MRV system. | MRV system for the relevant sector is fully operational. | Currently, project stakeholders have reported having database but not functioning , therefore the project has reach out to present sectorial historical archive data in excel spreadsheet for short term data tracking and monitoring.In terms of MRV, Department of Environment , Forestry has well function MRV system.The centralised MRV system with the DOCC is not functioning.A suppplier has been identified (Subarao) to supply hardware and software including the installation .this will will be carried out in the coming month. | 60% | Satisfactory (S)
|  | (ii) Number of activity data collected, developed and archived for estimation of emmissions sources and sinks | Activity data and emissions factors of the previous national communication are not properly archived in centralized storage system. | Developed at least 4 sectors | Developed for at least 7 sectors (Forestry, Agriculture, Livestock, Energy, Transport, Industry, Waste) | Archiving of historical data from six sectors has been on track , especially the NDC targets related and GHG data and calculation.ICAT project with CBIT project are working together to collect GHG data in each sector for calculation and to complete report | 90% | Highly Satisfactory (HS)
|  | (iii) Number of country specific emission factors collected, developed and archieved for estimation of emissions sources and sinks | Activity data and emissions factors of the previous national communication are not properly archived in centralized storage system. | Developed for at least 4 sectors. | Developed for at least 7 sectors (Forestry, Agriculture, Livestock, Energy, Transport, Industry, Waste) | Currently DOCC has conducted a review and workshop of the current emissions factors and the report is well documented .It reports on emission data collected and calculated for six sectors and these are , Petrolium company, Municipal waste, Livestock animal herd manure, Agriculture commercial farming practices, and Civil aviation for international flights record only. | 80% | Highly Satisfactory (HS)
|  | (iv) Operational centralized database with sectoral linkages | 0 | Hardware and software procured. | Centralized database are fully operational. | The procurement process to hire the international consultant- Subarao Company (sole source) for the supply and installation of hardware and software is currently ongoing. At present, only the Forestry and Department of Environment have fully functional MRV databases. | 50% | Moderately Satisfactory (MS)
|  | (v) Operational integrated MRV system with online visualization and dissemination platform | 0 | Hardware and software procured. | Integrated MRV system are fully operational | The procurement process to hire the international consultant- Subarao Company (sole source) for the supply and installation of hardware and software is currently ongoing. At present, only the Forestry and Department of Environment have fully functional MRV databases. these databases are set up but have not yet been online. | 50% | Satisfactory (S)
|  | (vi) Quality NMRV system |  | Hardware and Software procured to upgrade the existing system. | 0 | The procurement process to hire the international consultant- Subarao Company (sole source) for the supply and installation of hardware and software is currently ongoing. At present, only the Forestry and Department of Environment have fully functional MRV databases. | 50% | Satisfactory (S)
|  | Scale -3 Measurement systems are in place for a few activities improved data quality and methodologies, but not cost or time efficient, wider access to reporting is still limited and information is partial verification is rudimentary /n on-standardized | An existing MRV system framework. | Scale 5: Measurement systems are strong for a limited set of activities and periodically report on key GHG related indicators i.e. mainstreamed into the activity implementation: reporting is improved through few pathways but limited audience and formats; verification limited audience and formats verification limited | Scale 8. Strong standardized measurements processes established for key indicators and mainstreamed into institutional policy implementation: reporting is widely available in multiple formats: verification is done for a larger set of information | The MRV system needs an upgrade to centralize data under the DoCC. The existing MRV is no longer functioning, but the project will hire a consulting company in New Zealand (Subarao) to install hardware and software and develop a robust standard measurement process for relevant sectoral indicators. Meanwhile, a standard data collection template (in Kobo) has been developed for sectors to use while waiting for the international consultant to be hired. | 50% | Moderately Satisfactory (MS)
| 2.1.2. Strengthened human capacity on GHG emissions and removal tools and climcate ulnerability assessment through training and peer to peer learning | (i) Number of training organised (32 percent women participants) | Limited systematic knowledge of GHG emissions and removals and reporting. | At least 5 | At least 11 | So far , there is one training conducted on GHG , and was conducted by DOCC through the ICAT project with GHG institute.All relevant stakeholders are invited .A participant list is available as means of verification and also dissagregated by gender in specific. | 30% | Not Rated
|  | (ii) Number of training knowledge materials including training proceedings and recorded video and hosted on the online MRV system | Limited systematic knowledge of GHG emissions and removals and reporting. | At least 5 knowledge materials. | At least 11 knowledge materials. | The MRV system needs more work to be done and from there, the GHG data including other NDC targets data can be capture and report on.So far the CBIT project with DOCC through ICAT project are developing a data collection guide and template for project stakeholders to use. At this point of time, there are 4 GHG Manuals ( Agriculture, Energy, Waste and IPPU) developed by ICAT and utilise to capacity build sectors. | 60% | Satisfactory (S)
|  | (iii) Number of national agencies exchanging the lessons learned at the national , regional and global levels | 0 | Organization representing at least 4 sectors. | Organization representing at least 7 sectors (Forestry, Agriculture, Livestock, Energy, Transport, Industry, Waste). | National agencies exchanging of lessons learn is always happening.From formal workshops organised with project stakeholders to informal sector by sector detail discussions about the project .Most importantly as it happens every Tuesday of the week, update on project progress with DOCC director and also provide constraits and way forwards on how to address. So far ongoing lessons learn and project update with the 8 project stakeholders (Department of Agriculture and Rural Development, the Department of Forestry, the Department of Livestock, the Department of environmental Protection and Conservation, the Department of Energy, Vanuatu Bureau of Statistic, the Department of Climate Change and the National University of Vanuatu) has happen and its ongoing. The project also participate at regional meetings such as NDC Hub Focal Point Meetings, and the CBIT-GSP regional lessons learned shared meeting. | 80% | Highly Satisfactory (HS)
Average Cumulative progress toward outcomes (%) | Time elapsed since project start/EOD vs Planned Project End Date | % of delivery
76.94% | 92.6% | 46.2%
Development Objective (DO) Ratings, and Overall Assessment
Please note that the overall DO ratings should be substantiated by evidence and progress reported above. The ratings and comments should reflect the overall progress of results since project start
| FY2025 Development Objective rating¹ | Project Manager/ Coordinator | Budget Holder | Lead Technical Officer13 | GEF Operational Focal Point | GEF Technical Officer (GTO)
|  | Satisfactory (S) |  | Satisfactory (S) |  | Satisfactory (S)
| Comments/reasons¹² justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | Overall, the project continues to make satisfactory progress toward its development objective, with steady improvements in institutional capacity, stakeholder engagement, and development of technical tools. The ratings reflect significant achievements since the last reporting period, as well as areas where operationalization and systems integration are still in progress. Below are some positive Changes: - Greater Stakeholder Engagement: The signing of 12 MOAs for data sharing and ETF participation (exceeding the end-of-project target of 10) demonstrates strong institutional collaboration. - Standardized Templates and Tools: The development of a single standardized data collection template for all sectors (to be piloted in September 2025) has reduced duplication and improved reporting efficiency. - Increased Capacity: National agencies have actively exchanged lessons learned through regional platforms (e.g., NDC Hub, CBIT-GSP) and routine coordination meetings, significantly improving capacity for ETF reporting. - Strong Alignment with National Priorities: Revised NDC 3.0 targets and indicators have been clearly linked to the National Sustainable Development Plan (NSDP), ensuring reporting supports wider policy goals. Areas of Moderate Progress 1. Operationalization of ETF & MRV Systems: While TORs for the ETF Technical Working Group are finalized, formal endorsement by MOCC and establishment of a centralized MRV system are pending. Procurement of hardware/software is underway, with implementation expected in the next reporting cycle. 2. Climate Finance Tracking: Although sectoral gaps and constraints have been identified, guidelines for climate finance reporting are still under development, and the national climate finance monitoring system has not been fully operationalized. 3.Training Coverage: Only one formal GHG training has been conducted, limiting progress on capacity-building targets (currently at 30%). Since the prvious reporting period, ratings for MRV System Operationalization (2.1.1) remain Moderately Satisfactory (MS) due to pending procurement and installation; no change since last period. And capacity-building indicators under Outcome 2.1.2 remain Not Rated or Satisfactory, as more training sessions and online MRV functionalities are needed to meet targets. | The project remains on track, with strong progress in institutional coordination, standardized tools, and policy alignment. Key milestones—12 MOAs and a harmonized data template—have advanced ETF readiness. Next steps focus on operationalizing ETF/MRV systems, climate finance tracking, and expanding training coverage to sustain momentum. | The project demonstrates satisfactory progress toward achieving its development objectives, underpinned by notable advancements in institutional coordination, standardization of technical tools, and strengthened alignment with national policy frameworks. The formalization of 12 MOAs for data sharing and the development of a harmonized data collection template represent key milestones that enhance readiness for ETF implementation. Furthermore, capacity-building initiatives through regional knowledge platforms have contributed to incremental improvements in technical competencies. The full operationalization of the ETF and MRV systems, establishment of climate finance tracking mechanisms, and expansion of training coverage remain priority areas for the forthcoming reporting period. | Though the project has made significant progress, more effort is needed to prepare the country for the ETF, which is where the project should focus more. | The project has achieved significant progress over the reporting period. Stakeholder participation and capacity building are critical for regular data collection and the operationalization of the MRV system, which the project will prioritize in the coming days.
Measures to address MS, MU, U and HU ratings on Section 2 above
Outcome |  | Action(s) to be taken |  | By whom? |  | By When?
7 Some indicators may not identify mid-term targets at the design stage (refer to approved results framework) therefore this column should only be filled when relevant. 8 Use GEF Secretariat required six-point scale system: Highly Satisfactory (HS), Satisfactory (S), Moderately Satisfactory (MS), Moderately Unsatisfactory (MU), Unsatisfactory (U), and Highly Unsatisfactory (HU).

## 3. Implementation Progress
3. Implementation Progress (IP)
(Please indicate progress achieved during this FY as per the Implementation Plan/Annual Workplan)
Outcomes and outputs | Indicators (as per the logical framework) | Main achievements in the last 12 months (please DO NOT repeat results reported in previous year PIR) |  |  | Describe any variance 9 in delivering outputs
Outcome 1.1 NDC transparency system in place following the UNFCCC modalities, procedures, and guidelines
Output 1.1.1 Institutional arrangements strengthened | (i) Qualitative gaps assessment report focusing on institutional, regulatory, human, technology, finance, and capacity building support needed, and stakeholder to meet the transparency framework of enhanced NDC actions. (ii) A national term of reference of working groups stating roles and responsibilities of stakeholders with specific guideline for participation of women (32 percent women) for data collection, sharing, and processing focusing on mitigation, adaptation, and addressing loss and damage (L&D) for observed and potential climate change impacts (e.g. extreme weather events and slow onset events). (iii) An operational National ETF body. (iv) Qualitative Assessment of Institutional Capacity for Transparency. Scale - 1 No designated transparency institution to support and coordinate the planning and implementation of transparency activities under Article 13 of the Paris Agreement exists. | The qualitative gap assessment on sectoral constraints in implementing and reporting NDC actions has been developed by the Department of Climate Change (DOCC) through the Global Green Growth Institute (GGGI). As of the latest updates, the gap assessment report is still in progress. GGGI has been actively conducting sector-specific workshops and consultations to validate vulnerabilities and risks across key sectors such as agriculture, water, infrastructure, and tourism. These engagements are essential for identifying existing gaps in climate resilience and adaptation planning. The finalization of the report is anticipated once all sectoral inputs and stakeholder consultations are fully integrated. The current assessment comprehensively addresses multiple critical areas, including: - Regulatory Frameworks: Evaluating existing policies and regulations to identify gaps and opportunities for strengthening climate resilience. - Institutional Capacity: Assessing the effectiveness and coordination of institutions responsible for climate adaptation and resilience. - Human Resources: Identifying the skills and capacities required within sectors to effectively respond to climate risks. - Technology Needs: Determining the technological tools and infrastructure necessary to support climate adaptation efforts. The Terms of Reference (TOR) for the Data Working Group has been finalized and socialized. Similarly, the TOR for the Enhanced Transparency Framework (ETF) is currently in draft form and socialized on August 2025 and is awaiting feedback from stakeholders. Progress has been made in evaluating institutional capacity for transparency through stakeholder consultations and workshops. The assessment has highlighted strengths and gaps in institutional coordination, data management, and reporting processes. These insights will inform recommendations for strengthening transparency and accountability in climate adaptation initiatives at both national and sectoral levels. |  |  | No variance made to project output
Output 1.2 Sectoral transparency guidelines and protocols are established for enhanced NDC climate change. mitigation, adaptation, and addressing L&D for observed and potential climate change impacts (e.g. extreme weather events and slow onset events). | (i) Number of regulatory frameworks reviewed and formulated guidelines and action plan. (ii) Number of metrics and indicators for monitoring enhanced NDC actions focusing on climate change mitigation, adaptation, and addressing L&D. (iii) Number of metrics and indicators for linking enhanced NDC with National Sustainable Development Plan (NSDP) and their reporting. | The sectoral NDC review has been carried out and completed by the Department of Climate Change (DOCC) through the Global Green Growth Institute (GGGI). All metrics and indicators were reviewed by sector across key areas such as mitigation, adaptation, and loss and damage. Further discussions were also held with stakeholders to align NDC priorities with the government’s National Sustainable Development Plan. All reviews and proposed changes have been documented and await goverment endoserment. At this phase, 6 metrics and indicators have been identified but still in draft. Below are the 6 metrics: 1. Climate Mitigation Targets: These targets focus on reducing greenhouse gas emissions across various sectors, including energy, transport, and waste management. 2. Climate Adaptation Actions: Indicators in this category measure the implementation of adaptation strategies, such as the development of climate-resilient infrastructure and the enhancement of community-based adaptation programs. 3. Green Employment & Youth Engagement: Metrics track the creation of green jobs and the involvement of youth in climate-related initiatives, promoting sustainable livelihoods. 4. Gender-Responsive Measures: Indicators assess the integration of gender considerations in climate policies and programs, ensuring equal participation and benefits for all genders. 5. Awareness and Capacity Building: Metrics evaluate the effectiveness of public awareness campaigns and capacity-building activities aimed at enhancing climate change knowledge among communities. 6. Reporting and Data Systems: Indicators monitor the establishment and maintenance of robust data systems for tracking climate-related progress and informing decision-making processes. |  |  | No variance made to project output
Output 1.1.3 Established operational quality control and assurance mechanism. | (i) Number of sectoral handbooks / protocols adopted (data collection, archiving, and data sharing). (ii) Number of sectoral data collection templates and guidelines. (iii) Number of MOUs signed between the stakeholders for collection, generation, archiving, and dissemination of data focusing on enhanced NDC climate change mitigation, adaptation, and addressing L&D for observed and potential climate change impacts (e.g. extreme weather events and slow onset Events). | The sectorial Handbook, the project has not yet starting to develop the handbook, but we have the same work that was carry out by the ICAT project- which they develop 4 GHG Calculation Manual (Agriculture, Energy, Waste and IPPU) The data-sharing Memorandum of Agreement (MOA) has been drafted, approved, and signed by the relevant CBIT stakeholders. The MOA outlines guidelines for how each sector is responsible for collecting, sharing, and reporting NDC data to the DOCC's centralized MRV system. So far, a total of eight sectors have signed off on the MOA. A standard data collection template has also been drafted and is currently awaiting stakeholder discussions and feedback. This template integrates all sector-specific NDC targets and includes components related to greenhouse gas (GHG) data. |  |  | No variance made to project output
Outcome 1.2 Key Ministries, Agencies, Departments, and other stakeholder’s capacity strengthened to track the NDC actions
Output 1.2.1 Strengthened guidelines on monitoring and reporting of climate financing focusing on domestic and international sources, and both public and private sector. | (i) A qualitative gap assessment report on needs, constraints, and stakeholders on tracking climate finance on enhanced NDC actions. (ii) Published and adopted sectoral methodologies, guidelines, and protocols to collect, archive, and disseminate climate finance data, and training conducted on them. (iii) Operational National Climate Finance Reporting and Monitoring (NCFRM) cell. | A gap assessment was conducted and completed by the Department of Climate Change (DOCC) through the Global Green Growth Institute (GGGI) during the NDC 3 review. Each sector presented ongoing challenges and constraints—or barriers—that hinder the timely collection, reporting, and sharing of quality data. Through the CBIT Letter of Agreement (LOA), the DOCC also carried out climate finance reporting and monitoring activities in collaboration with government agencies, non-governmental organizations, and relevant private sector institutions. This initiative aimed to map out climate finance resources, data collection methodologies, and the reporting of climate-related activities and financing. The purpose of the workshop is to develop a standardized guideline for climate change data collection and reporting across institutions. This will help avoid duplication of funding priorities and ensure better coordination of climate finance resources. The workshop has been carried out in May 2025, it is a capacity building session but also address the significant barriers to strategic planning, accountability, and alignment with national priorities such as the Nationally Determined Contributions (NDCs) and the Climate Change and Disaster Risk Reduction Policy. |  |  | No variance made to project output
Output 1.2.2 Strengthened capacity of national climate changes stakeholders to track the enhanced NDC adaptation actions. | (i) Number of knowledge products / best practice documents prepared and disseminated on monitoring and reporting of enhanced NDC adaptation actions. (ii) Number of training conducted and training module developed | The CBIT Project LOA with the Department of Climate Change (DOCC) has identified and developed guidelines to assist project stakeholders in monitoring and reporting enhanced NDC adaptation actions. This work involves reviewing and upgrading the existing methodology. Training will be delivered, in November 2025 to January 2026, through the NUV LOA, which supports the capacity development of relevant stakeholders involved in MRV and NDC tracking |  |  | No variance made to project output
Outcome 2.1 Operational digital data integration and sharing system for a robust MRV system hosted by DEPC
Output 2.1.1 Upgraded Information Technology (IT) system for a robust MRV system hosted by MOCC based on the existing system | (i)Operational and enhanced online-based integrated MRV system. (ii)Number of activity data collected, developed and archived for estimation of emissions sources and sinks. (iii)Number of country-specific emission factors collected, developed and archived for estimation of emissions sources and sinks. (iv) Operational centralized database with sectoral linkages. (v) Operational integrated MRV system with online visualization and dissemination platform. (vi) Quality of MRV systems. Scale 3 Measurement systems are in place for a few activities, improved data quality and methodologies, but not cost or time efficient; wider access to reporting is still limited and information is partial; verification is rudimentary/non-standardized | The MOA signed with project stakeholders facilitates collaboration, and so far, sectors have identified existing databases and highlighted constraints related to data collection and reporting. The GHG data collection methodology also requires improvement, particularly in helping sectors understand how to accurately report GHG data |  |  | No variance made to project output
Output 2.1.2 Strengthened human capacity on GHG emissions and removal tools, and climate vulnerability assessment through training and peer to peer learning. | (i)Number of training organized (32 percent women participants). (ii) Number of training knowledge materials including training proceedings and recorded video, and hosted on the online MRV system. (iii) Number of national agencies exchanging the lessons learned at the national, regional, and global levels. | A GHG training was conducted by the Department of Climate Change (DOCC) with support from the ICAT and CBIT projects, and all relevant stakeholders were invited. There are 4 GHG Calculation Manuals produces to support the capacity builiding of sectors on how to calculate their GG emissions (Agriculture, Waste, energy and IPPU). Another training session is planned for later this year, 10 and 11 september 2025, focusing on GHG calculation methodologies and the use of a standardized template. Notably, women represented 50% of the participants in the previous training. Currently, the DOCC MRV system is not functioning, which means online visual access to data is not available for stakeholders. to address this concern, the project has developped a standard data collection template for sectors to use while waiting for the hire of the international consultant. |  |  | No variance made to project output
Output 2.2
Output 2.3
Output 2.4
Output 2.5
Output 2.6
Outcome 3.
Output 3.1
Output 3.2
Output 3.3
Output 3.4
Output 3.5
Output 3.6
Implementation Progress (IP) , and Overall Assessment
Please note that the overall IP ratings should be substantiated by evidence and progress reported above. The ratings and comments shoud reflect the overall progress of results during the fiscal year (July 1 2024, to June 30, 2025)
| Project Manager/ Coordinator | Lead Technical Officer | Budget Holder | GEF Operational Focal Point (OFP) | GEF Technical Officer (GTO)
FY2025 Implementation Objective rating10 | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S) | Satisfactory (S)
Comments/reasons justifying the ratings for FY2025 and any changes (positive or negative) in the ratings since the previous reporting period | The FY2025 ratings reflect steady progress, which is satisfactory, across all outputs, with key institutional, technical, and capacity-building activities either completed or on track. No significant variance in deliverables has occurred. Positive changes since the previous reporting period include enhanced institutional arrangements, improved stakeholder capacity, and strengthened alignment of NDC actions with national priorities. The main limitations relate to pending final approvals, full operationalization of the MRV system, and completion of some documentation, which are expected to be addressed in the next reporting period. | FY2025 ratings indicate satisfactory progress across all outputs, with institutional, technical, and capacity-building activities largely on track. Key improvements include strengthened institutional arrangements, enhanced stakeholder capacity, and closer alignment of NDC actions with national priorities. Remaining gaps relate to final approvals, full MRV system operationalization, and completion of documentation, which are expected to advance in the next reporting period. | Last year progress remains satisfactory, with institutional, technical, and capacity-building activities on track. Key gains include stronger institutional arrangements and improved alignment with national priorities. Outstanding actions—final approvals, MRV system operationalization, and documentation—are expected to advance next period.ments | The is assisting Vanuatu to make the country ETF ready and building the institutional capacity. The office of the OFP will provide necessury support to make the project succesfull. | While the project has achieved notable progress, the next priority should be to focus on stakeholder engagement and capacity building. These are critical steps for ensuring regular data collection and fully operationalizing the MRV system.
9 Variance refers to the difference between the expected and actual progress at the time of reporting. 10 Implementation Progress Rating – A rating of the extent to which the implementation of a project’s components and activities is in compliance with the projects approved implementation plan.

## 4. Summary_Progress & Challenge
4. Summary on progress and challenges
Please provide a summary paragraph on project implementation progress consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
The project has made steady progress toward strengthening Vanuatu’s institutional and technical capacity to meet its Enhanced Transparency Framework (ETF) and NDC reporting obligations. As of June 2025, the project has engaged over a dozen government and non-government agencies through Memoranda of Agreement (MOAs) on data sharing, alongside the establishment of technical working groups. A draft Terms of Reference (ToR) for the ETF Working Group has been prepared and circulated, with endorsement pending from the Ministry of Climate Change (MOCC). The project has advanced sectoral planning and budgeting processes, with consultations identifying capacity and data gaps, particularly in methodology and reporting templates. Progress has also been achieved in developing guidelines and protocols to strengthen monitoring, reporting, and verification (MRV) systems across priority sectors, with several handbooks and sectoral frameworks under development or near completion. Stakeholders have been actively engaged in training workshops on ETF and NDC reporting, enhancing institutional knowledge and fostering inter-agency coordination. While some activities, such as the finalization of handbooks and operationalization of sectoral data protocols, remain ongoing, the project has successfully contributed to building awareness, enhancing collaboration, and establishing a strong foundation for a functional national transparency system. Overall, the implementation progress is rated between satisfactory and highly satisfactory across most outcomes, reflecting tangible achievements in institutional arrangements, data governance, and capacity building despite minor delays in the finalization of key outputs.
Please provide a summary paragraph on challenges of project implementation consistent with the information reported in section 2 and 3 of the PIR (Max 400 words) (This section will be uploaded to the GEF portal)
While the project has achieved important progress, several challenges have affected the pace of implementation. A key constraint has been the delayed endorsement and operationalization of the ETF Working Group and related Terms of Reference, which has slowed coordination and decision-making across sectors. Although agencies have signed data-sharing agreements, the harmonization of methodologies and standardized reporting templates remains incomplete, with gaps in data quality, historical records, and sectoral consistency presenting persistent obstacles. Limited technical expertise and institutional capacity at the sectoral level have further constrained progress, requiring extensive training and ongoing support. The development of sectoral handbooks and MRV protocols has also experienced delays, reflecting both the complexity of aligning sectoral systems with national ETF requirements and the time required to achieve consensus among stakeholders. Additionally, the process of collecting, reviewing, and validating sectoral data has proven resource-intensive, with varying levels of commitment and readiness across ministries and agencies. These challenges have led to some outputs being behind schedule, though mitigation measures such as targeted consultations, capacity-building workshops, and the gradual piloting of draft tools have helped maintain momentum. Overall, the challenges highlight the need for stronger institutional buy-in, enhanced technical support, and timely stakeholder engagement to fully operationalize the transparency system.
Implementation of Exit Strategy
Has the project developed an Exit Strategy? If yes, please describe the progress to implement it. | The exit strategy will be developed during the last year of the project and validated by the relevant stakeholders.
How is the project enhancing institutional capacities to foster country ownership for more durable / sustained results? | The project is enhancing institutional capacities and fostering national ownership by embedding climate transparency processes into national systems and strengthening coordination among government agencies, non-government actors, and development partners. An important forthcoming contribution will be the project’s support to the Measurement, Reporting and Verification (MRV) program course being established by the University of the South Pacific. Once operational, this program will provide Vanuatu’s technical officers and government staff with accredited, regionally recognized training, equipping them with advanced MRV skills and ensuring that institutional capacity is strengthened in a sustainable and durable manner. The project has also facilitated multi-stakeholder consultations and collaboration platforms, including the establishment of the ETF Technical Working Group and the signing of Memoranda of Agreement on data sharing, which institutionalize inter-agency cooperation and promote shared ownership of transparency responsibilities. These initiatives not only build technical expertise but also create a strong enabling environment for sustained collaboration across sectors.

## 5. ESS Risk
5. Environmental and Social Safeguards (ESS): risks from the project
Initial ESS Risk Classification (at CEO Endorsement/Approval Stage) | Low Risk
New environmental and social risks. | None
Progress made towards implementing the Enivronmental and Social Management Plan (ESMP) (only for Moderate and High Risk Projects) | None
Grievance Redress Mechanism (GRM) | None

## 6. Risks to the Project
6. Risks to the Project
The following table summarizes risks identified in the Project Document and reflects also any new risks identified during the project implementation.
| Type of risk |  | Risk rating11 | Identified in the ProDoc Y/N | Description of Risk | Mitigation measure implemented
1 | Partnership & Coordination |  | Moderate | Yes | There is limited coordination and partnership in the implementation of LOA activities, as well as in information sharing among project stakeholders. Additionally, there is a lack of understanding of the specific LOA activities and how they positively impact government sectors. | The Data Sharing MOA has been signed by stakeholders, along with the Terms of Reference (TOR) for both the Data Technical Working Group and the ETF Working Group. The establishment of these groups will enhance coordination and partnership among stakeholders. All information will be centralized and managed by the Department of Climate Change (DOCC).
2 | Institutional |  | Moderate | Yes | There is limited human resource capacity within sectors to implement LOA activities and to report on progress required for the release of LOA tranches. Additionally, there is concern about the government's ability to fund ETF-related activities after the project cycle ends. | The project staff work closely with government sectors to implement LOA activities. They provide technical support to ensure that project activities align with sectoral plans and priorities, while also helping to secure ongoing government funding. The project has established strong partnerships with the ICAT project, the former national consultant for the NDC development, and the National Advisory Board (NAB) on CCDRR to make the best use of resources and achieve greater impact for stakeholders and sectors.
3 | Environmental |  | High | Yes | Natural Hazard has caused huge barrier and delay in project activity implementation at sector level | The CBIT project has faced significant challenges in implementing LOA activities; however, it has remained flexible by supporting and engaging with the government during disaster response and recovery efforts, aligning this support with relevant project activities.
4
5
6
7
8
Project overall risk rating (Low, Moderate, Substantial or High):
FY2024 rating | FY2025 rating | Comments/reason for the rating for FY2025 and any changes (positive or negative) in the rating since the previous reporting period
Moderate | Substantial | The project has achieved steady progress in implementing capacity-building programs and conducting training workshops across multiple sectors, including energy, agriculture, forestry, and other land-use sectors. These initiatives aim to strengthen technical skills, enhance data collection and management, and improve institutional capacity for climate action. In addition, the project actively participates in the review and updating of Vanuatu’s NDC 3.0, ensuring alignment with national priorities and international climate commitments. The project is actively fostering partnerships with existing initiatives, such as the ICAT project and GGGI-supported programs, which are leading the review of the NDC and the development of the National Adaptation Plan. These collaborations help to leverage expertise, avoid duplication of efforts, and enhance the overall impact of climate actions at the national level.
11 Risk ratings means a rating of the overall risk of factors internal or external to the project which may affect implementation or prospects for achieving project objectives. Risk of projects should be rated on the following scale: Low, Moderate, Substantial or High.

## 7. Follow-up on Mid-term review
7. Follow-up on Mid-term review or supervision mission
If the project had an MTR or a supervision mission in 2024, please report on how the recommendations were implemented during this fiscal year as indicated in the Management Response or in the supervision mission report.
MTR or supervision mission recommendations | Measures implemented during this Fiscal Year
Recommendation 1:
Recommendation 2:
Recommendation 3:
Recommendation …
Recommendation…

## 8. Minor project amendments
8. Minor project amendments
Minor amendments are changes to the design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the GEF Project and Program Cycle Policy Guidelines 12. Please describe any minor changes that the project has made under the relevant category or categories and provide supporting documents as an annex to this report if available. (This section will be uploaded to the GEF Portal)
Category of change | Provide a description of the change | Indicate the timing of the change | Approved by
Results framework | NA | NA
Components and cost | NA | NA
Institutional and implementation arrangements | NA | NA
Financial management | NA | NA
Implementation schedule | NA | NA
Executing Entity | NA | NA
Executing Entity Category | NA | NA
Minor project objective change | NA | NA
Safeguards | NA | NA
Risk analysis | NA | NA
Increase of GEF project financing up to 5% | NA | NA
Co-financing | NA | NA
Location of project activity | NA | NA
Other minor project amendment (define) | NA | NA
12 GEF Council meeting documents, guidelines, project and program cycle policy 2020 update

## 9. Stakeholders' Engagement
9. Stakeholders' Engagement
Please report on progress, challeges, and outcomes on stakeholder engagement (based on the description of the Stakeholder Engagement Plan) included at CEO Endorsement/Approval during this reporting period. (This section will be uploaded to the GEF Portal)
Profile | Stakeholder name | Type of partnership | Progress, results & Challenges on Stakeholder's Engagement
Government Institutions | Department of Climate Change | Implementing patner and Chairman of the Steering Committee | Limited human resource staff focus on LOA activity implementation
Government Institutions | Department of Environmental Protection and Conservation | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Government Institutions | Vanuatu Bureau of statistic | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Government Institutions | Department of Forestry | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Government Institutions | Department of Livestock | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Government Institutions | Department of Agriculture and Rural development | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Government Institutions | Department of Energy | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Government Institutions | Department of Meteo | Stakeholders | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Private Sector entities | UNELCO | Stakeholders | No progress collaboration yet for this entities
Private Sector entities | Paradise Petrolium | Stakeholders | No progress collaboration yet for this entities
Private Sector entities | Vanuatu Civil Aviation Authority | Member of the Steering Committee | So far, project has contribute to established a well coordinated process in terms of Data sharing and lessons learn among stakeholders.Data storage at the moment is low and needs upgrade
Others | National University of Vanuatu | Implementing patner and member of the Steering Committee | Limited human resource and capacity resources for LOA activity implementaion
NGOs | ActionAid | Stakeholders | No progress collaboration yet for this entities
NGOs | Live & Learn | Stakeholders | No progress collaboration yet for this entities

## 10. Gender Mainstreaming
10. Gender Mainstreaming
Information on Progress on Gender-responsive measures as documented at CEO Endorsement/Approval in the gender action plan or equivalent (when applicable) during this reporting period. (This section will be uploaded to the GEF Portal)
Category | Yes/No | Briefly describe progress and results achieved during this reporting period.
a. Closing gender gaps in access to and control overal natural resources | Yes | The work is still ongoing. Since the project has no field sites and focuses on national policies, institutional arrangements, and capacity building, it addresses gender gaps in data collection and access to GHG data.
b. Improving women's participation and decision making | Yes | Ongoing progress shows that the project is improving women’s participation by aligning with the government’s Gender Plan, with support from ActionAid and local gender specialists. Yes women have taken Data officer positions, for example, the focal point of Forestry, Livestock and National University of Vanuatu are female and the Mitigation Officer at the Department of Climate Change is a female. The are the ones that seats at the table to infomed the decision making in terms of Nationally dertermined Contribution Revision (called NDC 3.0) and also participate in training such as climate financing to enhance their capacity.
c. generating socio-economic benefits or services for women | No | Not applicable
Any other good practices on gender | Yes | A good practice to highlight is that, in some sectors, such as the Department of Forestry, the data officer is a woman who manages day-to-day data and is very approachable and easy to contact.

## 11. Knowledge Management
11. Knowledge and Learning Activities
Knowledge activities/products (when applicable), as outlined in Knowledge Management (and Learning) Approach approved at CEO Endorsement/Approval, during this reporting period. (This section will be uploaded to the GEF Portal)
Knowledge management and Learning (KML): Does the project have a KML strategy? | Yes
If YES, what is the implementation progress? In your answer, please describe how the project is fostering knowledge sharing and learning among stakeholders at national and sub-national level. | The PMU is following the KML while carrying out the activities.
If NO, how does the project identify, collect and document good practices?
Please list good practices, including key-technical and/or institutional innovations, from the project thus far.
Communication strategy: Does the project have a communication strategy? | Yes
Please provide a brief overview of the communications successes and challenges this fiscal year. | The project will communicate with all relevant stakeholders using the MRV system. The key task now is to make the MRV system operational through necessary upgrades and involvement of stakeholders.
Human-interest story: Please share a human-interest story from your project, focusing on how the project has helped to improve people's livelihoods while contributing to achieving the expected Global Environmental Benefits. Please indicate any Socio-economic Co-benefits that were generated by the project. Include at least one beneficiary quote and perspective, and please also include related photos and photo credits.
Please provide links to related website, social media account | The link to the national MRV system will be available after the upgradation.
Please provide a list of publications, leaflets, video materials, newsletters, or other communications assets publised on the web, if any. | All the knowledge materials will be posted in the MRV system after necessary upgradation.
Please indicate the Communication and/or knowledge management focal point's name and contact detais. | Stephanie STEPHENS, stephens.stephanie@fao.org, tel: (+678) 7363198

## 12. Indigenous & Local Involve.
12. Indigenous Peoples and Local Communites Involvement
Are Indigenous Peoples and local communities involved in the project (as per the approved Project Document)? If yes, please briefly explain.
If applicable, please describe the process and current status of on-going/completed, legitimate consultations to obtain Free, Prior and Informed Consent (FPIC) with the indigenous communities. This is not applicable to project, because the project focus on institutional arrangements and capacity building at the natinal and regional level. Do indigenous peoples and/or local communities have an active partcipation in the project activities? If yes, briefly describe how. This is not applicable, this project does not deal directly with the indigenous community.

## 13. Co-Financing Table
13. Co-Financing Table
Sources of Co-financing | Name of Co-financer | Type of Co-financing | Amount Confirmed at CEO endorsement/approval (in USD) | Actual Amount Materialized at 30 June 2025 (in USD)
Recipient Country Government | MOCC | In kind | 2699500 | 900000
Recipient Country Government | MALFB | In Kind | 295000 | 200000
Total |  | Total | 2994500 | 1100000
Please explain any significant changes in project co-financing since CEO Endorsement/Approval, or differences between the pledged and materialized co-financing amounts.
GEF CoFinancing Guidelines 2018

## 14. GEO Location
14. Geo Location Information
This section should be completed ONLY by projects with 1st PIR and in case the geographic coverage of project activities has changed since last reporting period. This information is required by GEF Secretariat in GEF Portal
Are there any changes in the geographic coverage of the project activities since the last PIR report? |  |  |  | No |  | 1st PIR
Location Name | Latitude | Longitude | Geo Name ID |  | Location & Activity Description*
Ministry of Climate Change and Meteorology | -17.7495 | 168.3145133993333 |  |  | Ministry of Climate Change and Meteorology – The Vanuatu Government Office. Under the ministry there is the Department of Climate Change (DoCC) where the Chairman of Project steering Committee (PSC) seats and which the MRV system is located to be upgraded. In the same area we also have the Office of the Government Chief Information Officer (OGCIO) that will directly work with the DoCC to move the MRV system to the Government Server.

## Annex
Annex. Monitoring Area-based GEF Core Indicator Commitments and Progress with FERM
The Framework for Ecosystem Restoration Monitoring (FERM), developed by FAO, is the official monitoring platform for tracking global progress and disseminating good practices for the UN Decade of Ecosystem Restoration. The FERM can serve as an integrated GIS-based platform, providing GEF staff and all relevant stakeholders the chance to display the progress of committed versus achieved land under restoration or under improved management for conservation and sustainable use, along with clear results such as the percentage of project achievement. Having a common tracking and monitoring platform allows users to comprehensively assess and report on project progress. A user-friendly dashboard showcasing project results gives stakeholders a clear understanding of the extent to which project targets have been achieved. Projects with area-based GEF Core Indicators (GEF Core Indicators 1-5 and LDCF Core Indicator 2) are encouraged to register in the FERM platform.
Useful links:
• FERM website
• FERM User Guide (PDF)
• FERM YouTube channel
• Email Carmen Morales
26 It also supports countries in reporting areas under restoration for the Kunming-Montreal GBF Target 2 (areas under restoration) for which FAO is the custodian agency.