GEF - PROJECT IMPLEMENTATION REPORT (PIR)

Document Generated by: CCA TM

At: 2024-08-05 05:48:03

# Table of contents

1 PROJECT IDENTIFICATION	3

1.1 Project Details	3

1.2 Project Description	4

1.3 Project Contacts	4

2 Overview of Project Status	6

2.1 UNEP PoW & UN	6

2.2. GEF Core and Sub Indicators	6

2.3. Implementation Status and Risks	7

2.4 Co Finance	9

2.5. Stakeholder	9

2.6. Gender	12

2.7. ESSM	12

2.8. KM/Learning	13

2.9. Stories	14

3 Performance	15

3.1 Rating of progress towards achieving the project outcomes	15

3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)	25

4 Risks	30

4.1 Table A. Project management Risk	30

4.2 Table B. Risk-log	30

4.3 Table C. Outstanding Moderate, Significant, and High risks	33

5 Amendment - GeoSpatial	34

5.1 Table A: Listing of all Minor Amendment (TM)	34

5.2 Table B: History of project revisions and/or extensions (TM)	34

UNEP GEF PIR Fiscal Year 2025

Reporting from 1 July 2024 to 30 June 2025

# 1 PROJECT IDENTIFICATION

## 1.1 Project Details

| GEF ID: 5456 | Umoja WBS:SB-007724 |
| --- | --- |
| SMA IPMR ID:34181 | Grant ID:S1-32LDL-000045 |
| Project Short Title: Bangladesh EBA |  |
| Project Title: Ecosystem-based Approaches to Adaptation (EbA) in the Drought-prone Barind Tract and Haor "Wetland" Area |  |
| Duration months planned: | 60 |
| Duration months age: | December 31, 2025 |
| Project Type: | Full Sized Project (FSP) |
| Parent Programme if child project: |  |
| Project Scope: | National |
| Region: | Asia Pacific |
| Countries: | Bangladesh |
| GEF Focal Area(s): | Climate Change Adaptation |
| GEF financing amount: | 5,200,000.00 |
| Co-financing amount: | 4,239,805.00 |
| Date of CEO Endorsement/Approval: | 2016-12-19 |
| UNEP Project Approval Date: | 2021-12-02 |
| Start of Implementation (PCA entering into force): | 2020-08-31 |
| Date of Inception Workshop, if available: | 2022-08-31 |
| Date of First Disbursement: | 2018-05-07 |
| Total disbursement as of 30 June 2025: | $ 3,124086 |
| Total expenditure as of 30 June 2025: | $ 2,791,970 |
| Midterm undertaken?: | No |
| Actual Mid-Term Date, if taken: | NA |
| Expected Mid-Term Date, if not taken: | 2025-09-01 |
| Completion Date Planned - Original PCA: | 2025-12-31 |
| Completion Date Revised - Current PCA: | 2026-12-31 |
| Expected Terminal Evaluation Date: | 2026-12-31 |
| Expected Financial Closure Date: | 2027-06-30 |

## 1.2 Project Description

The Least Developed Countries Fund (LDCF) has approved the full-time project entitled “Ecosystem-based Approaches to Adaptation (EbA) in the Drought-Prone Barind Tract and Haor Wetland Area Project (EbA Project)" in Bangladesh. Bangladesh is a land of diverse ecosystems which contain 25 Bio-Ecological Zones (BEZ). The Barind Tract and the Haor basin are two BEZ with unique biodiversity, topographies and special land use patterns. Barind Tract and Haor wetland areas of Bangladesh contain high productive ecosystems that provides valuable goods and services to the local communities. The country is also the most vulnerable to the negative impacts of climate change including erratic rainfall, temperature rise, and flash floods affecting crop production and ecosystems degradation.

The objectives of the project are to increase the capacity of the Government and local communities living in the Barind Tract and Haor area and to reduce the negative effects of climate change using Ecosystem-based approaches to Adaptation (EbA).  The project has three outcomes:

Outcome 1:  Strengthened technical capacity of local and national government officials to plan, implement and upscale EbA.

Outcome2:   Local communities at project intervention sites are implementing EbA to restore degraded ecosystems and maintaining hard infrastructure that Complements EbA by promoting topsoil and water conservation.

Outcome 3:  Government Ministries and Institutions in Bangladesh have access to improved scientific and traditional information on EbA to promote up-scaling of this approach.

## 1.3 Project Contacts

| Division(s) Implementing the project | Ecosystems Division |
| --- | --- |
| Name of co-implementing Agency |  |
| Executing Agency (ies) | Ministry of Environment and Forestry (MoEF) |
| names of Other Project Partners |  |
| UNEP Portfolio Manager(s) | Jessica Troni |
| UNEP Task Manager(s) | Moon Shrestha |
| UNEP Budget/Finance Officer | Bwiza Wameyo Odemba |
| UNEP Support Assistants |  |
| Manager/Representative | AKM Rafiqul Islam |
| Project Manager | Shahnaj Parvin |
| Finance Manager | Fakhrul Majid |
| Communications Lead, if relevant |  |

# 2 Overview of Project Status

## 2.1 UNEP PoW & UN

| UNEP Current Subprogramme(s): | Thematic: Climate action subprogramme |
| --- | --- |
| UNEP previous Subprogramme(s): | Thematic : Climate Change |
| PoW Indicator(s): | - Climate : (i) Number of national, subnational and private-sector actors that adopt climate change mitigation and/or adaptation and disaster risk reduction strategies and policies with UNEP support. - Nature: (iii) Number of countries and national, regional and subnational authorities and entities that incorporate, with UNEP support, biodiversity and ecosystem-based approaches into development and sectoral plans, policies and processes for the sustainable management and/or restoration of terrestrial, freshwater and marine areas - Nature: (iv) Increase in territory of land- and seascapes that is under improved ecosystem conservation and restoration |
| UNSDCF/UNDAF linkages | Aligned with priority thematic area 3 "Resilience, disaster risk reduction and climate change |
| Link to relevant SDG Goals | - Goal 9: Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation - Goal 15: Protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss |
| Link to relevant SDG Targets: | - 2.4 By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality - 15.9 By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts |

## 2.2. GEF Core and Sub Indicators

GEF core or sub indicators targeted by the project as defined at CEO Endorsement/Approval, as well as results

|  | Targets - Expected Value |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Mid-term | End-of-project | Total Target | Materialized to date |
| Area of degraded agricultural lands under restoration | fill | Fill | Fill |  |
| Terrestrial protected areas created or under improved management for conservation and sustainable use | Fill | Fill | Fill |  |

Implementation Status 2023: 4th PIR

## 2.3. Implementation Status and Risks

|  | PIR# | Rating towards outcomes (section 3.1) | Rating towards outputs (section 3.2) | Risk rating (section 4.2) |
| --- | --- | --- | --- | --- |
| FY 2025 | 5th PIR | S | S | L |
| FY 2024 | 4th PIR | S | S | L |
| FY 2023 | 3rd PIR | U | U | M |
| FY 2022 | 2nd PIR | MS | MS | L |
| FY 2021 | 1st PIR |  |  | M |
| FY 2020 | --Select-- |  |  |  |
| FY 2019 | --Select-- |  |  |  |
| FY 2018 | --Select-- |  |  |  |
| FY 2017 | --Select-- |  |  |  |
| FY 2016 | --Select-- |  |  |  |
| FY 2015 | --Select-- |  |  |  |

Summary of status

During the reporting period (July 2024 – June 2025), the project achieved steady progress in advancing Ecosystem-based Adaptation (EbA) interventions across the Barind Tract and Haor regions. The focus remained on ecosystem restoration, community empowerment, and institutional strengthening to enhance climate resilience.

Outcome 1 (Institutional Capacity):

The recruitment of the Policy Expert, M&E Specialist, and CCNRM Specialist has been completed. They are currently working on preparing documents for the EbA policy brief. Once the policy brief is finalized, institutional capacity strengthening activities will commence. Although policy integration remains below target, the overall outcome has not progressed adequately.

Technical guidelines for the Village Conservation Fund have been prepared by the PMU team under the leadership of the NPD and Project Manager. The VCG members received training on VCG functional and management, Management of village conservation fund, training on the ecosystem-based approaches to technology implementation , management and developing additional livelihood activities . Among these trainings, only the training on ecosystem-based approaches to technology implementation, management, and the development of additional livelihood activities was conducted during this reporting period.

Outcome 2 (Community-led EbA Interventions): This outcome demonstrated the most visible progress. A total of 25 Village Conservation Groups (VCGs) actively implemented EbA interventions such as pond and canal re-excavation, plantation, and rainwater harvesting. In the Barind Tract, 59,000 saplings were planted (cumulative 300,000) across 44 hectares, while 76 ponds and 2 canals were re-excavated . In the Haor region, 1,114 seedlings were planted, 10.2 km of canals were re-excavated, and 2 beels restored. Livelihood diversification in fish farming, spice cultivation, and small livestock and other livelihood activities improved both food security and income resilience.

Outcome 3 (Knowledge and Upscaling): During this reporting period, activities at Sylhet Agricultural University and Rajshahi University progressed smoothly, The university selection, PhD and Post doc student and supervisor enrollment already done. The PhD candidates and post-doctoral researchers will conduct studies on the environmental and socio-economic impacts of EbA interventions and associated hard infrastructure in the Barind Tract and Haor areas. Access to scientific and traditional knowledge has improved through this engagement.

Community-based planning models, partnerships with BMDA, BWDB, and UN Women, and initial knowledge management tools have been developed to support future replication. However, progress remains limited, as knowledge-sharing platforms and national upscaling strategies are not yet fully operational.

Overall, physical progress in the Barind stands at 80% and in the Haor at 50%. At communities have directly benefited 16,300 individuals (4,890 women, 11,410 men) and indirectly 54,400 individuals.

Challenges and Risks in Implementation:

Despite strong progress in Outcome 2, several challenges constrained implementation, particularly under Outcome 1 and parts of Outcome 3:

Slow Progress in Capacity Strengthening (Outcome 1):

- The recruitment of the Policy Expert, M&E Specialist, and CCNRM Specialist has been completed. They are currently working on preparing documents for the EbA policy brief. Once the policy brief is finalized, institutional capacity strengthening activities will commence. Although policy integration remains below target, the overall outcome has not progressed adequately.

- Technical guidelines for the Village Conservation Fund have been prepared by the PMU team under the leadership of the NPD and Project Manager. Based on these guidelines, 25 VCG members have received funds. The VCG members have also received training on VCG functional and management, Management of village conservation fund, training on the ecosystem-based approaches to technology implementation, management and developing additional livelihood activities .

Operational Challenges:

- Seasonal variability and unfavourable weather conditions were managed by adjusting activity timelines (e.g., rescheduling plantation and excavation) to minimize delays

- Community concerns over land use and soil dumping were resolved with support from sub-district and Union Parishad authorities, alongside mediation by local elites and community leaders.

Risks identified include:

- Political instability: Potential disruption of coordination may occur at both national and operational levels.

- Limited government prioritization of long-term EbA: There is a risk of reduced institutional support after project completion

- Unfavourable climate conditions in the drought-prone Barind area: Extreme weather events may threaten plantation survival and ecosystem restoration.

- Community engagement and sustainability: Communities may be unable to sustain EbA practices without continued support in the future.

## 2.4 Co Finance

| Planned Co-finance: | 122238045 (117017128 + 52209917) |
| --- | --- |
| Actual to date: | 122,691,503 |
| Progress | Justify progress in terms of materialization of expected co-finance State any relevant challenges: . Institutions; Plan ( USD); Co-finance Reported This Year (USD); Cumulative Actual Co-finance (USD). BMDA (Barind Multipurpose Development Authority); 52,20,917; 5,220,916.67; 11,768,833.33. BWDB (Bangladesh Water Development Board); 101,930,075.00; 101,930,075.00; 218,947,203.00. Total; 101,930,075.00; 107,150,991.67; 230,716,036.33. |

## 2.5. Stakeholder

| Date of project steering committee meeting | 2024-06-09 |
| --- | --- |
| Stakeholder engagement (will be uploaded to GEF Portal) | The stakeholder engagement plan is actively guiding the implementation of project activities during this reporting period. It has facilitated the smooth functioning of 25 Village Conservation Groups (VCGs) in the Barind and Haor regions. The project conducted skill-building training for VCG members on ecosystem-based approaches to adaptation, technology implementation, management, and development of additional livelihoods. A total of 688 participants attended these trainings, including 206 women and 482 men, with 12 facilitators from various government institutions, such as Agriculture Extension and Cooperatives, conducting different sessions. Additionally, several meetings and idea-exchange sessions with VCG members and local communities were held in collaboration with BWDB, BMDA, and local government institutions at the sub-district and union levels to expedite the targeted re-excavation of beels, ponds, and canals. During this reporting period, two Project Steering Committee (PSC) meetings were held: 7th PSC Meeting: List of Participants: - Member of Planning commission, Ministry of Planning - Secretary of Finance Division, Ministry of finance - Secretary of Economic Relations Division, Ministry of Planning - Secretary of Ministry of Water Resource - Secretary of Ministry of Agriculture - Member of Agriculture, Water Resources and Rural Institutions Division of the Planning Commission, - Additional Secretery of Ministry of Environment, Forest and Climate Change (MoEFCC) - Director General of Department of Environment - Director General of Bangladesh Haor and Wetland Development Department - Director General of Bangladesh Water Development Board (BWDB) - Executive Director of Barind Multipurpose Development Authority (BMDA) - Joint Chief Executive of Committee of National Economic Council (ECNEC) - Joint Secretary of Planning Department of Ministry Environment, Forest and Climate Change (MoEFCC) - Project Director of EbA Project, Department of Environment - Director of Planning, Department of Environment - Secretary of Ministry of Environment, Forest and Climate Change (MoEFCC) 8th PSC Meeting: List of Participants: - Member of Planning commission, Ministry of Planning - Secretary of Finance Division, Ministry of finance - Secretary of Economic Relations Division, Ministry of Planning - Secretary of Ministry of Water Resource - Secretary of Ministry of Agriculture - Member of Agriculture, Water Resources and Rural Institutions Division of the Planning Commission - Additional Secretery of Ministry of Environment, Forest and Climate Change (MoEFCC) - Director General of Department of Environment - Director General of Bangladesh Haor and Wetland Development Department - Director General of Bangladesh Water Development Board (BWDB) - Executive Director of Barind Multipurpose Development Authority (BMDA) - Joint Chief Executive of Committee of National Economic Council (ECNEC) - Joint Secretary of Planning Department of Ministry Environment, Forest and Climate Change (MoEFCC) - Project Director of EbA Project, Department of Environment - Director of Planning, Director of Environment Secretary of Ministry Environment, Forest and Climate Change (MoEFCC) |

Reports :

https://drive.google.com/file/d/11hUw2dm87kpEmMX3THOUXQQzObPRWy6n/view?usp=drive_link

https://drive.google.com/file/d/19SZ0F9kCdZ2yEKL1toPvNnKv4xAhxKeO/view?usp=drive_link

https://drive.google.com/drive/folders/1-LStrIPB_04qEaPv_-4jEsZdd_rr9YWF?usp=drive_link

## 2.6. Gender

| Does the project have a gender action plan? | Yes |
| --- | --- |
| Gender mainstreaming (will be uploaded to GEF Portal): | The project promoted gender equality, women’s leadership, and empowerment by ensuring 30% women's participation in activities, including monthly meetings, skill development trainings, Village Conservation Group (VCG) formation and functional activities, Village Conservation Fund (VCF) distribution, livelihood programs, and other capacity-building initiatives. Each VCG ensured that at least 30% of participants in their monthly meetings were women. During the reporting period, the project ensured the smooth functioning of 25 Village Conservation Groups (VCGs) in the Barind and Haor regions. The project implemented ecosystem-based approaches to adaptation, including technology deployment, management, and the development of additional livelihood options for VCG members. A total of 688 participants attended these trainings, including 206 women and 482 men. Out of a total of 750 VCG members, 225 are women and 525 are men. We note that this figure is lower than planned due, in part, to conservative social norms in both the Barind and Haor regions, which limit women’s mobility and engagement in public activities. To increase women’s involvement, the project is conducting counseling sessions during VCG meetings and integrating gender and women’s empowerment sessions in various training programs. These efforts aim to raise women’s participation to 40%. The Project Management Unit (PMU) team also provided guidance to increase women’s effective participation in various meetings, workshops, and other community activities. |

## 2.7. ESSM

| Moderate/High risk projects (in terms of Environmental and social safeguards) | Was the project classified as moderate/high risk CEO Endorsement/Approval Stage? No If yes, what specific safeguard risks were identified in the SRIF/ESERN? |
| --- | --- |
| New social and/or environmental risks | Have any new social and/or environmental risks been identified during the reporting period? No If yes, describe the new risks or changes? |
| Complaints and grievances related to social and/or environmental impacts | Has the project received complaints related to social and/or environmental impacts (actual or potential) during the reporting period? Yes If yes, please describe the complaint(s) or grievance(s) in detail, including the status, significance, who was involved and what actions were taken? A few complaints were received during the canal re-excavation in the Haor area. Some adjacent landowners expressed concern that the re-excavated soil might reduce their land productivity by washing away during the rainy season. Upon receiving the complaint, the Regional Manager informed the PMU. Following a discussion with the Project Manager, the Regional Manager visited the field and arranged a meeting with all relevant parties, including the local administration, community members, landowners, and the implementation partner. The implementation partner (BWDB) assured that the excavated soil would be used for slope protection, tree plantation, and raising the adjacent government premises as requested by the administration. With this clarification, all parties agreed to the plan, and the issue was resolved amicably. |
| Environmental and social safeguards management | ESS (Environmental and Social Safeguards) assessments have been conducted. The project conducted baseline studies and Environmental Impact Assessments (EIA) after selecting the schemes, followed by community consultation meetings to obtain consent. Furthermore, an ESS management plan has been prepared to guide risk mitigation and ensure safeguard compliance throughout project implementation. Efforts have been taken to recruit and environmental and social safeguards officer however no qualified applicants have yet been identified. The project will re-advertise to ensure that this critical position is filled. In the meantime, the project maintains a Grievance Redress Mechanism (GRM) at the regional office using a Grievance management register. Upon receiving complaints, the regional team promptly takes initiative to address and resolve them. The monitoring team and the Regional Project Management Team communicate with the community through Village Conservation Group (VCG) meetings and user group meetings to share information regarding grievances and the adopted management strategies. Based on the nature of complaints, the regional management team resolves them through dialogue and coordination with local authorities to ensure timely and appropriate support. #### 1. Unauthorized Earth Cutting from the Dyke of Madhibachhara Canal, Haor On October 21, 2024, the Regional Manager – Haor received a phone call from the community reporting that some individuals were illegally cutting soil from the dyke of the Madhibachhara Canal. This activity raised serious concerns regarding the sustainability of the canal's slope protection and led to social tensions that could have compromised the overall social safeguard situation. In response, the Regional Manager conducted a field visit on October 22, 2024, accompanied by the Chairman of Sujanagar Union, Baralekha. Following the visit, the Union Parishad Chairman convened a meeting involving the accused individuals, community representatives, and officials from the Bangladesh Water Development Board (BWDB), in the presence of the Upazila Nirbahi Officer (UNO) of Baralekha. Through joint coordination and community engagement, the issue was resolved, and the illegal earth cutting from the dyke was halted. #### 2. Community Concerns Regarding Canal Re-excavation, Excavation Strategy, and Soil Dumping at Madhibachhara Canal, Haor During the initial phase of the re-excavation of the Madhibachhara Canal at Sonapur Union, some community members raised concerns about a potential shortage of irrigation water during the excavation period. Additionally, adjacent landowners objected to the dumping of excavated soil on their farmland. In response, the Regional Manager communicated with local authorities, sub-district administration, community leaders, and residents. A joint field visit was conducted involving all administrative tiers, community representatives, and BWDB officials. Considering the concerns and inputs of the community, it was mutually agreed: - The re-excavation work would be rescheduled to begin in December (instead of November) to ensure adequate irrigation water availability. - The excavated soil would be dumped carefully along both sides of the canal, ensuring no damage to existing crops or private land. These measures were agreed upon and accepted by all stakeholders, allowing the project to proceed in a socially inclusive and environmentally responsible manner. |

## 2.8. KM/Learning

| Knowledge activities and products | NA |
| --- | --- |
| Main learning during the period | ### 1. Strong Collaboration with Community and Local Government Institutions We developed strong partnerships with the community and key local government institutions, including Department of Agricultural Extension (DAE), Department of Cooperatives, Forest Department, Department of Fisheries, Bangladesh Water Development Board (BWDB), and Barind Multipurpose Development Authority (BMDA). This multi-stakeholder collaboration has been crucial for the effective implementation, coordination, and long-term support of our project initiatives. ### 2. Smooth Functioning and Capacity Building of Village Conservation Groups (VCGs) A total of 25 Village Conservation Groups (VCGs) has played an instrumental role in project implementation and community engagement. - 10 VCGs in the Haor region received the second installment of the Village Conservation Fund (VCF) in recognition of their strong performance, transparent fund management, and effective utilization of resources. - 15 VCGs in the Barind region received the first installment of VCF after obtaining official registration from the Department of Cooperatives. All VCGs received comprehensive capacity-building training conducted by the Project Manager, Regional Managers, local government representatives (Agricultural Extension and Cooperatives), and implementation partners. on key areas, including: - Livelihood improvement - Ecosystem-based Adaptation (EbA) - Climate Change Adaptation (CCA) - Roles and responsibilities of VCGs in environmental management and building climate resilience in the community In addition, ecosystem-based adaptation technologies were introduced, including: pond and canal re-excavation, rainwater harvesting, climate-resilient plantations, and improved water management systems to strengthen community resilience, forestry, agriculture, fisheries, and skills development supported their implementation and promoted alternative livelihoods for VCG members. Government officials from the Department of Cooperatives, Department of Agricultural Extension, and BMDA also participated in the training sessions as resource persons, contributing their expertise to enhance the capacity of VCG members. |

## 2.9. Stories

| Stories to be shared | We have identified and collected some cases. In addition, we developed a plan to document success stories for each intervention as part of lesson learning and to highlight EbA modalities. |
| --- | --- |

# 3 Performance

## 3.1 Rating of progress towards achieving the project outcomes

| Project Objective and Outcomes | Indicator | Baseline level | Mid-Term Target or Milestones | End of Project Target | Progress as of current period (numeric, percentage, or binary entry only) | Summary by the EA of attainment of the indicator & target as of 30 June 2025 | Progress rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective To decrease the vulnerability of local communities living in the Barind Tract and Haor Area to the negative impacts of climate change using Ecosystem-based Adaptation approaches (EbA). | The number of individuals benefitting from project interventions is disaggregated by Gender. | Zero |  | At least 6,000 beneficiaries of which at least 40% will be women. | 16,300 including 30 % women | During this reporting period, the achievements comprise 48 ponds, including 1 rainwater harvesting pond, while in the previous year, 26 rainwater harvesters and 01 ponds were re-excavated. The cumulative achievements include the re-excavation of 76 ponds in the Barind area, of which 27 are rainwater harvesting ponds. During the reporting period, these re-excavated ponds directly benefited 8,600 individuals, including 2,580 females and 6,020 males. Additionally, the estimated number of indirect beneficiaries is 34,400, comprising 10,320 females and 24,080 males. The cumulative achievements directly benefited 16,300 individuals, including 4,890 women and 11,410 men. The cumulative indirect beneficiaries totaled 54,400, comprising 16,320 women and 38,080 men. In the previous year, the achievements included 7,700 direct beneficiaries, of which 3,080 were women and 4,620 were men as well as 20,000 indirect beneficiaries including female 8,000 and male 12,000 | S |
| Outcome 1: Strengthened capacity of the local and national government to plan, implement and upscale EbA. | The degree to which capacity of regional, national and sub-national government institutions to identify, prioritize, implement, | 1. Baseline study to be conducted at the project inception stage. 2. Currently organizations/ institutions including the Department of Environment (DoE) are identifying climate change risks and adaptation options, but not appropriate EbA interventions to manage these risks. Government institutions do not prioritize the implementation of EbA interventions. 3. Officials of relevant government departments including DoE, DAE, FD, DoF, SRDI, Department of Cooperatives (DoC), BMDA and BWDB, etc. have been trained on: i) the effects of climate change; ii) management and relief of climate-related disasters, and iii) climate-resilient crops for adaptation. However, government staff have not received training on EbA. |  | 1. Increase by 3 in the capacity score assessment of each institution. | 20% | The Policy Expert, M&E Specialist, and CCNRM Specialist were recruited in the reporting period. They are now working collaboratively on developing the training and assessing capacity in order to progress implementation on this outcome. | MU |
| Outcome 2: Adaptation technologies including EbA demonstrated in the Barind Tract and Haor Area to restore degraded ecosystems and promote topsoil and water conservation. | 1. Number of Village Conservation Groups (VCG) implementing and maintaining EbA interventions in the Barind Tract and Haor Area. | Zero |  | 25 | 75% | A total of 25 Village Conservation Groups (VCGs) in the Barind Tract and Haor areas were actively engaged in the implementation and maintenance of Ecosystem-based Adaptation (EbA) interventions at the community level in the reporting period. These groups received capacity-building training on livelihood skills, ecosystem-based adaptation, and life skills. The EbA interventions, namely homestead fish and spice cultivation were done by the VCG members. The Village Conservation Fund (VCF) serves as the centerpiece of the EbA model, providing financial resources to support livelihoods as climate change adaptation activities. In the Haor region, 10 VCGs received the second installment of the VCF, while in the Barind Tract, the remaining 15 VCGs received the first installment during this reporting period. The funds enabled VCG members to implement and maintain additional EbA interventions, including cow and goat rearing, homestead gardening, and small businesses, tailored to local environmental conditions and aimed at enhancing climate change adaptation and resilience capacity. | S |
|  | - Number of hectares of EbA demonstrated in degraded dry land and swamp forests. | Zero |  | EbA will be implemented in at least: (i) 50 hectares of degraded swamp forests; (ii) 50 hectares of degraded upland forests; (iii) 80 hectares of degraded dry land forests; (iv) 130 km of strips along roads, canals, ponds and embankments. | 70% | In the Barind Tract, 59,000 saplings were planted during the reporting period, with maintenance currently being carried out by the Barind Multipurpose Development Authority (BMDA) and Village Conservation Groups (VCGs). Cumulatively, a total of 300,000 saplings have been planted across 44 hectares of land. In the previous year, 241,000 saplings were planted over 38 hectares. A total of 1,114 seedlings were planted along the bank of the Madhachra canal and adjacent ponds during this reporting period. But no swamp forest plantations were carried out during this reporting period. The overall survival rate of the planation is 90%. | S |
|  | 4. Number of homesteads plantations established by the project. | Zero |  | 125 nos. homestead plantations. | 0 | During the reporting period, no homestead plantations were established. Cumulative progress is zero in this regard. | MU |
|  | 5. Number of adaptation technologies implemented to support EbA by conserving topsoil and water. | Zero |  | In this reporting period, i) 50 ponds are re-excavated in the Barind area; (ii) 18 ponds re-excavated in the Haor area; (iii) 2 canals re-excavated in the Barind area; (iv) 1 canal re-excavated in the Haor area; (v) 3 beels re-excavated in the Haor area; and (vi) 27 rainwater harvesting facility demonstrated in the Barind area. | 85 % | During this reporting period, the achievements comprise 48 ponds, including 1 rainwater harvesting pond. The cumulative achievements include the re-excavation of 76 ponds in the Barind area, of which 27 were designated as rainwater harvesting ponds, and the planting of 300,000 saplings in this region. In the Haor area, progress includes the re-excavation of 9 ponds, 16 km of canal, and the plantation of 1,100 saplings. These adaptation technologies are implemented in both regions to conserve topsoil and improve water management. | S |
|  | 6. Number of climate-resilient livelihoods introduced at intervention sites through providing equipment, training and technical support. | Zero |  | 1,545 (in at least four categories- fish production, farming gardens and spice cultivation). | 15 % | During the reporting period in Barind region, 140 participants cultivated fish in their homestead ponds, including 42 female and 98 male beneficiaries. They cultivated Ruhu, Katla, Carp, and other local fish species. In addition, 30 beneficiaries cultivated spices 9 women and 21 men. They have grown onion, mustard, turmeric, and garlic. In the Haor region, 65 beneficiaries engaged in fish cultivation, including 19 women and 46 men. They farmed Tilapia, Ruhu, Katla, Pangas, and other fish species. Additionally, 28 beneficiaries in Haor cultivated spices, including 8 women and 20 men. They primarily grown mustard and onion. Cumulative progress is the same as reported for this period, as these activities were not initiated in the previous year. | MS |
| Outcome 3: Improved access to scientific and traditional information on EbA to promote upscaling of this approach in Bangladesh. | 1. Number of government agencies using knowledge management tools developed by the project to share information on EbA. | Zero |  | At least 6 (including MoF, MoA, MoP, MoEFCC, MoL and MoWR). | 0% | The PMU team began developing knowledge management tools after recruiting the M&E Specialist, CCNRM Specialist, and Policy Expert in this reporting period. | MU |
|  | 2. Number of PhD candidates and post-doctorate researchers conducting research focused on the environmental and socio-economic impacts of the EbA interventions and hard infrastructure implemented through the LDCF-financed project in the Barind Tract and Haor areas. | Zero |  | At least two PhD students and 1 post-doctorate researcher have been/are conducting research. | 50% | During the reporting period partnerships were identified with universities and student selection and supervisor selection took place. The PMU held meetings with university registrars etc. in order to progress this output. | MU |
|  | 3. Number of strategies and models promoting the replication and upscaling of EbA interventions validated by the local and government. | Zero | 40% | At least 3 (One nationwide EbA upscaling strategy for Bangladesh and two business case models). | 10% | Strategic Partnerships and Collaborations: The project established strong partnerships with key government institutions, including the Bangladesh Water Development Board (BWDB), Barind Multipurpose Development Authority (BMDA), Department of Agricultural Extension (DAE), Department of Fisheries (DoF), Department of Cooperative, Forest Department (FD), local communities, and civil society organizations. These collaborations focus on providing sustainable, long-term support and maintenance for EbA initiatives, and have been recognized as effective by both local and government stakeholders, ensuring the sustainability and scalability of these interventions. Liaison and Networking for Long-Term Support: The project actively engaged in liaison and networking with organizations such as BRAC, UN Women, and the Cooperative Department of Bangladesh to secure long-term financial support, promote gender-sensitive leadership development, and enhance women’s empowerment for the 25 VCGs in both regions. These efforts have been recognized as essential for ensuring the sustainability of Ecosystem-based Adaptation (EbA) interventions. | MS |

## 3.2 Rating of progress implementation towards delivery of outputs (Implementation Progress)

| Component No | Output/Activity | Expected completion date | Implementation status as of previous reporting period (%) | Implementation status as of current reporting period (%) | Progress rating justification, description of challenges faced and explanations for any delay | Progress Rating |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Output 1.1: Policy briefs developed (and training provided) on proposed revisions to policies and strategies related to dry land and wetland ecosystem management to promote EbA. | 2025-06-30 | 10 | 50% | The newly recruited policy expert is working on this and shared the draft policy strategy with the PMU during this reporting period | MU |
| 1 | Output 1.2: Technical guidelines produced for the implementation of EbA to reduce the vulnerability of local community livelihoods to climate change. | 2025-12-31 | 50 | 90% | A technical guideline was developed on the utilization and management of the Village Conservation Fund, incorporating Ecosystem-based Adaptation (EbA) approaches to reduce the vulnerability of local community livelihoods to climate change. | S |
| 1 | Output 2.1 Training provided to national and local government staff, and VCG members on planning and implementing EbA Interventions. | 2025-12-31 | 30 | 70% | A total of 750 VCG members from 25 Village Conservation Groups (VCGs) received training on VCG activities, VCG functionality, and the utilization of Village Conservation Funds (VCF) in the Barind and Haor regions during the previous period. Additionally, 688 participants, including 206 women and 482 men from VCGs in both regions, received training on Ecosystem-based Approaches to Adaptation (EbA), focusing on technology implementation, management, and the development of alternative livelihoods for VCG members. The training sessions were supported by 12 resource people from the Department of Cooperatives at the sub-district level from both regions. The 12 resource persons are government officials, primarily from the Department of Cooperatives, Department of Agricultural Extension (DAE), and BMDA at the sub-district level, where the EbA interventions are being implemented. Their involvement is necessary because they are directly responsible for supporting and strengthening the VCGs in the future | S |
| 2 | Output 2.2. Local authorities, communities, committees and user groups in the Barind Tract and Hoar Area trained on EbA, maintaining hard infrastructure, and developing livelihoods to strengthen Adaptive capacity to climate change | 2025-12-31 | 20 | 80% | A total of 82 ponds, including 27 rainwater harvesters, and 3 beels, along with 22 km of re-excavated canals, have been developed in the Barind and Haor areas. All these hard infrastructures are being maintained by local authorities, communities, VCG committees, and user groups in both the Barind Tract and Haor region. These structures are also being utilized to support resilient livelihood activities by the local communities. | HS |
| 2 | Output 2.3. Degraded forests in the Haor area and Barind Tract rehabilitated using EbA | 2025-12-31 | 50 | 60% | In the Barind Tract, a total of 300,000 saplings were planted across 44 hectares of land. Among them, 59,000 saplings were planted during the reporting period. Maintenance of these plantations is currently being carried out by the Barind Multipurpose Development Authority (BMDA) and Village Conservation Groups (VCGs). Additionally, 1,114 seedlings were planted along the edges of the Madhachara canal and ponds. No swamp forest plantations were carried out during this reporting period. |  |
| 2 | Output 2.4 Hard infrastructure that reduces erosion in the Hoar Area and conserves water constructed in the Barind Tract and Haor area | 2025-12-31 | 30 | 80% | In the Haor area, 6 ponds and 10.2 km of canals were re-excavated during this reporting period to improve water management and reduce erosion. The canal uses slope protection mitigation strategy for as well planted tree on the ponds and canal, beel embankments embankment prevent erosion and reserve water conserve, Then the Barind area, 48 ponds, including 1 rainwater harvester, were established during the same period. All these hard infrastructures, aimed at reducing erosion in the Haor area and conserving water in both the Barind Tract and Haor regions, have been constructed to support climate-resilient resource management. | S |
| 2 | Output 2.5. Additional livelihoods are demonstrated to enhance the resilience of local communities to climate change. | 2025-12-31 | 2 | 65% | A total of 25 Village Conservation Groups (VCGs) in the Barind Tract and Haor areas received capacity-building training on livelihood skills, ecosystem-based adaptation, and life skills. Additionally, 10 VCGs in the Haor area received the second installment of the Village Conservation Fund (VCF), while the remaining 15 VCGs in the Barind area received the first installment of the VCF during the reporting period. In the previous year, only 10 VCGs in the Barind region received the VCF, as the remaining 15 VCGs obtained registration from the Department of Cooperatives during this reporting period. | S |
| 3 | Output 3.1: A central database for information on EbA lessons learned and cost-effectiveness from the Haor Area, Barind Tract and other regions across Bangladesh established or strengthened | 2025-12-31 | 0 | 5% | Terms of Reference we drafted and the procurement process was started for knowledge management website and database on lesion learning for scaling | MU |
| 3 | Output 3.2: Financial support provided to post-graduate and post-doctorate researchers to research specific climate change risks and the EbA interventions that are implemented by the project. | 2025-12-31 | 10 | 50% | The Post graduated and post doctorate researcher activities began with Sylhet agricultural university and Rajshahi university. Each university has two students, one is PhD and other is for Post Doc. | S |
| 3 | Output 3.3: A knowledge management plan developed to capture and share information on climate change impacts. | 2025-12-31 | 0 | 30% | A Knowledge Management Plan has recently been developed to capture and share valuable information on climate change impacts. At the field level, a range of activities is actively underway, including the formation and functioning of VCGs, management and use of VCFs, pond and canal excavation, tree plantation, and rainwater harvesting. The Sub-PMU and PMU are carefully documenting best practices, collecting successful case studies, and building a centralized database. These efforts are guiding the development of a systematic knowledge management approach to support the up scaling of EbA interventions, while also capturing lessons learned, challenges, and pathways forward. | MU |
| 3 | Output 3.4 Frameworks that support replicating and upscaling of EbA in Bangladesh developed. | 2025-12-31 | 0 | 10% | Frameworks to support the replication and upscaling of Ecosystem-based Adaptation (EbA) are being developed, building on the valuable lessons learned from ongoing interventions such as pond and canal excavation, rainwater harvesting, tree plantation, and community-based natural resource management. These frameworks will provide practical guidance on technical implementation, community engagement, and climate-resilient practices, while drawing on knowledge management tools like case study documentation, databases of best practices, and lessons learned. |  |

The Task Manager will decide on the relevant level of disaggregation (i.e. at either the output or activity level).

# 4 Risks

## 4.1 Table A. Project management Risk

Please refer to the Risk Help Sheet for more details on rating

| Risk Factor | EA Rating | TM Rating |
| --- | --- | --- |
| 1 Management structure - Roles and responsibilities | Low | Low |
| 2 Governance structure - Oversight | Low | Low |
| 3 Implementation schedule | Low | Low |
| 4 Budget | Low | Low |
| 5 Financial Management | Low | Low |
| 6 Reporting | Low | Low |
| 7 Capacity to deliver | Low | Low |

If any of the risk factors is rated a Moderate or higher, please include it in Table B below

## 4.2 Table B. Risk-log

Implementation Status (Current PIR)

Insert ALL the risks identified either at CEO endorsement (inc. safeguards screening), previous/current PIRs, and MTRs. Use the last line to propose a suggested consolidated rating.

| Risks | Risk affecting: Outcome / outputs | CEO ED | PIR 1 | PIR 2 | PIR 3 | PIR 4 | PIR 5 | PIR 6 | Δ | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Political instability at the national level. | Project interventions are delayed because of uncertain role allocation at the central level. | L | L | L | L | M | L |  |  | The country's political situation was unstable during this reporting period. However, project activities continued to be implemented by applying situational management and appropriate precautionary measures. |
| 2. Disagreement between stakeholders on the allocation of roles in the project | Project interventions are delayed because of uncertain role allocation. The effectiveness of project management is reduced. | M | M | L | L | M | L |  |  | The project has prepared a Stakeholder Engagement Plan and is actively implementing it. The PMU closely engages with Village Conservation Groups (VCGs), government institutions, and the community to ensure the participation of poor and marginalized groups. |
| 3. The central information database established in the MoEFCC is not utilized or maintained over time leading to limited inter-institutional data sharing or collaboration | Limited transfer of relevant project information amongst role players and end users resulting in the delayed or ineffective implementation of interventions. | M | M | M | L | L | L |  |  | The process of enhancing the database has started |
| 4. The long-term nature of adaptation. in particular EbA. may lead to limited government support for project activities in the selected area. | Loss of government support may result in a lack of prioritization of project activities. | M | M | M | L | L | L |  |  | The project is undertaking awareness raising interventions and engaging with government officials through consultation meetings, training. workshops. etc. with other stakeholders. |
| 5. High turnover of staff members in implementing agencies (in particular MoEFCC. DoE and CCU). | Changes in project-related government priorities and poor institutional memory result in disruptions or delays in project implementation and coordination. | M | M | M | M | M | L |  |  | There was no staff turnover during this reporting period. |
| 6. Increasing Overseas Development Assistance increases demands on time/capacity. | Increasing Overseas Development Assistance results in increased demands on time for implementing agency officials. which in turn results in disruptions or delays in project implementation and coordination. | M | M | M | L | M | L |  |  | A dedicated Project Management Unit (PMU) has been recruited to manage project implementation, thereby reducing the direct burden on government staff. The PMU coordinates closely with regional and local government authorities, providing guidance and technical support to ensure smooth and effective project execution according to the outline of the Pro-doc. |
| 7. Limited acceptance of stakeholders to accept change i.e. the adaptation alternative over the business-as-usual. This has the potential to affect the scaling up of project activities. | Communities may not adopt ecosystem restoration for adaptation activities during or after the project resulting in continued unsustainable use of resources. | M | M | M | L | L | L |  |  | The project conducts series of stakeholders' consultations. trainings and engages VCGs to build their capacity which will support scaling up of the project activities |
| 8. Disagreement over allocation of land for implementation of project activities. | Disagreement among stakeholders about site selection. | L | L | L | L | L | L |  |  | There is no disagreement among the stakeholders over the allocation of land for the implementation of project activities. |
| 9. Under-developed land tenure system of property rights undermines project interventions. | An insecure/unsure land tenure system decreases buy-in to EbA interventions by local communities. | M | M | M | L | L | L |  |  | The project has not encountered the issue. |
| 10. Unfavorable climate conditions including current climate and seasonal variability and/or extreme weather events. | Current climate and seasonal variability and/or hazard events result in poor restoration results. | M | M | M | L | L | L |  |  | The EbA project interventions such as water conservation, re-excavation of ponds and canals, climate resilient plantations, and livelihood diversification helped communities adapt to droughts, floods, and other climate stresses, thereby the projects directly and indirectly supporting to address and reduce climate vulnerabilities. |
| 11. Limited local technical capacity hinders project interventions. | Capacity constraints of local institutions and experts may limit the ability to undertake research and demonstration activities. | L | L | L | L | L | L |  |  | The project has planned interventions to strengthen the capacity of the local institutions and experts through consultation meetings, training and technical support. |
| 12. Limited commitment/ buy-in from local communities. | Lack of commitment/buy-in from local communities may result in the failure of demonstration projects. | M | M | M | L | L | L |  |  | The VCGs maintained liaison and coordination with local government officials to secure support for increasing community commitment and buy-in. Through this process, local communities and stakeholders were actively informed and engaged in EbA interventions such as water conservation, pond and canal re-excavation, climate-resilient plantations, and livelihood diversification. Their participation enhanced trust and encouraged communities to adopt and sustain these EbA practices for long-term resilience building and climate change adaptation |
| 13. Unsustainable land and natural resources use. | Unsustainable use of natural resources continues. leading to further degradation of ecosystems | H | H | H | L | L | L |  |  | To address the risk of unsustainable use of land and natural resources, the project promotes EbA interventions such as pond and canal re-excavation, rainwater harvesting, and climate-resilient plantations through nature-based solutions and integrated resource management to restore ecosystems and ensure long-term sustainability. Mitigation measures include enforcing monitoring with the active involvement of VCGs and local administration, reusing re-excavated soil for slope protection of ponds, canals, rainwater harvesting structures, and tree plantations, and allocating surplus soil for community welfare works—such as repairing school compounds, mosques, and graveyard areas—in consultation with communities and local authorities. |
| 14. Implemented interventions are not cost-effective. | Priority interventions are not cost-effective, which results in limited demonstration and will hamper the success of the interventions. Economic loss and budget allocation to other activities are reduced. | L | L | L | L | L | L |  |  | Cost-benefit analyses are conducted prior to implementation, and Environmental Impact Assessments (EIA) and Vulnerability Impact Assessments (VIA) are carried out. Proven high-impact interventions are prioritized, and resources are optimized using low-cost, nature-based solutions. Expenditures are closely monitored, and lessons learned, and best practices are documented to guide replication and upscaling. |
| 15. Local communities cannot access sufficient support to implement EbA interventions successfully. | Lack of sufficient support to implement EbA for local communities may result in the failure of demonstration projects. | M | M | M | L | L | L |  |  | Lack of sufficient support for local communities to implement EbA interventions may result in the failure of demonstration projects. To address this risk, the project strengthened the capacity of Village Conservation Groups (VCGs) and Village Conservation Funds (VCFs) through training, technical guidance, financial support, and by facilitating liaison with local government institutions. These measures enabled communities to effectively implement, manage, and sustain EbA practices, ensuring long-term resilience and prevent unsustainable use of natural resources. |

## 4.3 Table C. Outstanding Moderate, Significant, and High risks

Additional mitigation measures for the next periods

| Risk | Actions decided during the previous reporting instance (PIRt-1, MTR, etc.) | Actions effectively undertaken this reporting period | What | When | By Whom |
| --- | --- | --- | --- | --- | --- |

High Risk (H): There is a probability of greater than 75% that assumptions may fail to hold or materialize, and/or the project may face high risks.

Significant Risk (S): There is a probability of between 51% and 75% that assumptions may fail to hold and/or the project may face substantial risks.

Moderate Risk (M): There is a probability of between 26% and 50% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

Low Risk (L): There is a probability of up to 25% that assumptions may fail to hold or materialize, and/or the project may face only modest risks.

# 5 Amendment - GeoSpatial

Project Minor Amendments

Minor amendments are changes to the project design or implementation that do not have significant impact on the project objectives or scope, or an increase of the GEF project financing up to 5% as described in Annex 9 of the Project and Program Cycle Policy Guidelines. Please tick each category for which a change occurred in the fiscal year of reporting and provide a description of the change that occurred in the textbox. You may attach supporting document as appropriate

## 5.1 Table A: Listing of all Minor Amendment (TM)

| Minor Amendments | Changes |
| --- | --- |
| Results Framework: | No |
| Components and Cost: | Yes |
| Institutional and implementation arrangements: | Yes |
| Financial Management: | Yes |
| Implementation Schedule: |  |
| Executing Entity: | No |
| Executing Entity Category: | No |
| Minor project objective change: | No |
| Safeguards: | Yes |
| Risk analysis: | Yes |
| Increase of GEF financing up to 5%: | No |
| Location of project activity: | No |
| Other: | No |

Minor amendments

The PCA is amended to extend the project till 30 June 2025.

## 5.2 Table B: History of project revisions and/or extensions (TM)

| Version | Type | Signed/Approved by UNEP | Entry Into Force (last signature Date) | Agreement Expiry Date | Main changes introduced in this revision |
| --- | --- | --- | --- | --- | --- |
|  | Extension | 2022-09-08 | 2022-08-31 | 2025-12-31 | -Short term and long-term consultant position removed/added - No cost extension |
|  | Extension |  |  |  |  |

GEO Location Information:

GEO Location Information: The Location Name, Latitude and Longitude are required fields insofar as an Agency chooses to enter a project location under the set format. The Geo Name ID is required in instances where the location is not exact, such as in the case of a city, as opposed to the exact site of a physical infrastructure. The Location & Activity Description fields are optional. Project longitude and latitude must follow the Decimal Degrees WGS84 format and Agencies are encouraged to use at least four decimal points for greater accuracy. Users may add as many locations as appropriate. Web mapping applications such as OpenStreetMap or GeoNames use this format. Consider using a conversion tool as needed, such as: https://coordinates-converter.com Please see the Geocoding User Guide by clicking here

| Location Name (Required Field) | Type of Intervention | Latitude |  |  | Longitude |  |  | Geo Name ID | Location Description |  |  |  |  |  | Activity Description |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | LocLatDeg | local at Min | Lo cL at Sec | Loc Long Deg | Loc Long Min | Loc Long Sec |  | Name of Division | Name of District | Name of Upazilla (Sub-District) | Name of Union | Name of Village | Word No |  |
|  | Madabchhara Khal (down downstream.) | 24 | 39 | 15 | 92 | 7 | 38 | 60581477 | Sylhet | Moulvibazar | Barlekha | Sujanagar | Bholarkandi | 4 | House hold survey |
|  | MadabchharaKhal ( Mid-stream) | 24 | 39 | 02 | 92 | 8 | 04 | 60581477 | Sylhet | Moulvibazar | Barlekha | Sujanagar | Azimganj | 4 | House hold survey |
|  | MadabchharaKhal ( Upstream) | 24 | 38 | 11 | 92 | 13 | 22 | 60581477 | Sylhet | Moulvibazar | Barlekha | Dakkhinbhag Uttar | Kathaltoli | 4 | House hold survey |
|  | Mychlar Dak Beel | 24 | 39 | 47 | 92 | 04 | 40 | 60586510 | Sylhet | Moulvibazar | Juri | Jaifornagar | Jaifornagar | 5 | Household survey |
|  | Agder Beel | 24 | 38 | 39 | 92 | 03 | 31 | 60586510 | Sylhet | Moulvibazar | Juri | Jaifornagar | Jaifornagar | 4 | Household survey |
|  | Kachma Beel | 24 | 35 | 23 | 92 | 01 | 40 | 60586510 | Sylhet | Moulvibazar | Kulaura | Bhukshimail | Nababganj | 4 | Household survey |
|  | Harinbadi Pond | 24 | 42 | 31 | 92 | 9 | 59 | 60581494 | Sylhet | Moulvibazar | Barlekha | Talimpur | Mohodikona | 2 | House hold survey |
|  | Udbav Thakur Akhra Pond | 24 | 69 | 53 | 92 | 19 | 15 | 60581499 | Sylhet | Moulvibazar | Barlekha | Barlekha Paurashava | Pakhiwala | 7 | House hold survey |
|  | Brammangram Pond | 24 | 42 | 47.5 | 92 | 12 | 21.7 | 60581413 | Sylhet | Moulvibazar | Barlekha | Barlekha | Karargram | 4 | House hold survey |
|  | Gulua Dhighi | 24 | 44 | 40 | 92 | 09 | 04 | 5814237128 | Sylhet | Moulvibazar | Barlekha | Dasher Bazar | Gulua | 2 | House hold survey |
|  | Barlekha Govt. College Pond | 24 | 42 | 57 | 92 | 11 | 46 |  | Sylhet | Moulvibazar | Barlekha | Sadar | Barlekha Pourashava |  | House hold survey |
|  | Laxmichhara Pond | 24 | 39 | 5.5 | 92 | 12 | 20.3 | 60581480 | Sylhet | Moulvibazar | Barlekha | Uttar Dakshinbhag | Laxmichhara | 8 | House hold survey |
|  | Baro Dhamai Pond | 24 | 34 | 11 | 92 | 9 | 31 | 60583567 | Sylhet | Moulvibazar | Juri | Purba Juri | Baro Dhamai | 2 | House hold survey |
|  | Shahgonj Bazar Jame Mosjid Pond | 24 | 35 | 0 | 92 | 04 | 15 | 5835408488 | Sylhet | Moulvibazar | Juri | Jaifornagar | Shahapur |  | House hold survey |
|  | Shilghat Pond | 24 | 35 | 34.76 | 92 | 8 | 37.88 | 60583555 | Sylhet | Moulvibazar | Juri | Paschim Juri | Shilghat | 9 | House hold survey |
|  | Ratna Bazar Jame Mosjid Pond | 24 | 31 | 51 | 92 | 7 | 33 | 60583529 | Sylhet | Moulvibazar | Juri | Goalbari | Rutna | 8 | House hold survey |
|  | Sagornal High School Pond | 24 | 29 | 14 | 92 | 08 | 28 | 5835708076 | Sylhet | Moulvibazar | Juri | Sagornal | Hasnabad | 4 | House hold survey |
|  | Fultola Rajkie Durdamondir Pond | 24 | 24 | 40 | 92 | 07 | 16 | 5835274348 | Sylhet | Moulvibazar | Juri | Fultola | Rajkie TE | 7 | House hold survey |
|  | AC Land Office Pond | 24 | 31 | 47 | 92 | 02 | 23 | 5865344408 | Sylhet | Moulvibazar | Kulaura | Joychandi | Noadda Sadekpur | 2 | House hold survey |
|  | Pushainagar Pond | 24 | 32 | 29 | 92 | 03 | 21 | 5865411308 | Sylhet | Moulvibazar | Kulaura | Joychandi | Pushainagar | 5 | House hold survey |
|  | Miyerpara Koborestabn Pond | 24 | 25 | 42 | 91 | 57 | 27 | 5865748268 | Sylhet | Moulvibazar | Kulaura | Tilagaon | Miyerpara | 8 | House hold survey |
|  | Langla Railway Station Pond | 24 | 27 | 46 | 91 | 59 | 18 | 5865680208 | Sylhet | Moulvibazar | Kulaura | Rautgaon | Langla | 6 | House hold survey |
|  | Kulaura Upazila Pond | 24 | 31 | 38 | 92 | 02 | 03 | 5865454408 | Sylhet | Moulvibazar | Kulaura | Kulaura Pourashava | Kulaura Pourashava |  | House hold survey |
|  | Baburgul Pond | 24 | 35 | 49 | 92 | 6 | 39 | 60586513 | Sylhet | Moulvibazar | Kulaura | Bhatera | Berkuri | 4 | House hold survey |
|  | Road Side Plantation (km) | 24 | 33 | 22 | 92 | 7 | 21 | 60583555 | Sylhet | Moulvibazar | Juri | Paschim Juri | Khagteka | 1 | House hold survey |
|  | Road Side Plantation (km) | 24 | 38 | 22 | 92 | 7 | 21 | 60583555 | Sylhet | Moulvibazar | Juri | Paschim Juri | Khagteka | 1 | House hold survey |
|  | Road Side Plantation (km) | 24 | 67 | 6.81 | 90 | 4 | 620 | 60586513 | Sylhet | Moulvibazar | Kulaura | Bhatera | Noagaon | 5 | House hold survey |
|  | Swamp Forest (ha) | 24 | 67 | 68 | 92 | 4 | 62 | 60586513 | Sylhet | Moulvibazar | Barlekha | Talimpur | Haor Mouza | 5 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 43 | 34 | 92 | 2 | 10 | 60913836 | Sylhet | Sylhet | Golapgonj | Shorifgonj | Kadipur | 4 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 37 | 56.5 | 92 | 7 | 19.2 | 60583555 | Sylhet | Moulvibazar | Juri | Paschim Juri | Kalnigor | 1 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 60 | 95 | 92 | 1 | 79 | 60586510 | Sylhet | Moulvibazar | Kulaura | Bhukshimail | Shosharkandi | 1 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 36 | 34.3 | 92 | 1 | 5.7 | 60586510 | Sylhet | Moulvibazar | Kulaura | Bhukshimail | Shosarkandi | 1 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 43 | 34 | 92 | 2 | 3 | 60913836 | Sylhet | Sylhet | Golapgonj | Shorifgonj | Meherpur | 6 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 42 | 6.4 | 92 | 6 | 12.1 | 60581494 | Sylhet | Moulvibazar | Barlekha | Talimpur | Khutura | 9 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 41 | 26 | 92 | 6 | 0 | 60581494 | Sylhet | Moulvibazar | Barlekha | Talimpur | Halla | 9 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 35 | 05 | 92 | 01 | 47 | 60586510 | Sylhet | Moulvibazar | Kulaura | Bhukshimail | Shosharkandi | 1 | House hold survey |
|  | Fish Culture (Person) | 24 | 44 | 42 | 92 | 4 | 9 | 60913877 | Sylhet | Sylhet | Golapgonj | Uttar Bade Pasha | Supatek | 9 | House hold survey |
|  | Spice Cultivation (Person) | 24 | 44 | 6.5 | 92 | 5 | 36.8 | 60581415 | Sylhet | Moulvibazar | Barlekha | Barni | Saliha | 4 | House hold survey |
|  | Spice Cultivation (Person) | 24 | 41 | 59.5 | 92 | 6 | 6.8 | 60581494 | Sylhet | Moulvibazar | Barlekha | Talimpur | Khutaura | 9 | House hold survey |
|  | Spice Cultivation (Person) | 24 | 40 | 21 | 92 | 10 | 36 | 60581494 | Sylhet | Moulvibazar | Barlekha | Dakkhinbhag Uttar | Shimulia | 1 | House hold survey |
| Barind Area | Pond (19 nos) | 24 | 48 | 5 | 88 | 21 | 20 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Nolpukur | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 5 | 88 | 21 | 20 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Nolpukur | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 5 | 88 | 21 | 20 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Nolpukur | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 5 | 88 | 21 | 20 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Nolpukur | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 5 | 88 | 21 | 20 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Nolpukur | 3 | House hold survey |
|  | Fish Culture (Person) | 24 | 48 | 18 | 88 | 23 | 4 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kalitola | 6 | House hold survey |
|  | Fish Culture (Person) | 24 | 47 | 30.6 | 88 | 23 | 7.7 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | kolobuna | 1 | House hold survey |
|  | Vegetable Farming (Person) | 25 | 24 | 41.88 | 89 | 17 | 2.81 | 55857675 | Rangpur | Rangpur | Pirgonj | Roypur | Bahadurpur | 6 | House hold survey |
|  | Pond (19 nos) | 24 | 39 | 47 | 88 | 26 | 12 | 50819427 | Rajshahi | Rajshahi | Tanore | Badhair | Jotjibo | 6 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 39 | 44 | 88 | 26 | 12 | 50819427 | Rajshahi | Rajshahi | Tanore | Badhair | Jotjibon | 6 | House hold survey |
|  | Vegetable Farming (Person) | 24 | 38 | 0 | 88 | 26 | 31 | 50819427 | Rajshahi | Rajshahi | Tanore | Badhair | Ramdebpur | 8 | House hold survey |
|  | Pond (19 nos) | 24 | 44 | 7 | 88 | 24 | 46 | 50705657 | Rajshahi | Chapai Nowabgonj | Nachole | Nachole | Islampur | 8 | House hold survey |
|  | Pond (19 nos) | 24 | 44 | 7 | 88 | 24 | 46 | 50705657 | Rajshahi | Chapai Nowabgonj | Nachole | Nachole | Islampur | 8 | House hold survey |
|  | Pond (19 nos) | 24 | 44 | 9 | 88 | 24 | 46 | 50705657 | Rajshahi | Chapai Nowabgonj | Nachole | Nachole | Islampur | 8 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 11 | 88 | 21 | 25 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 11 | 88 | 21 | 22 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 9 | 88 | 21 | 26 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 7 | 88 | 21 | 25 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Block Plantation (ha) | 24 | 48 | 6 | 88 | 21 | 26 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 11 | 88 | 21 | 24 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Block Plantation (ha) | 24 | 48 | 7 | 88 | 21 | 26 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Pond (19 nos) | 24 | 48 | 9 | 88 | 21 | 21 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Bizlipara | 3 | House hold survey |
|  | Block Plantation (ha) | 25 | 24 | 41.88 | 89 | 17 | 2.81 | 55857675 | Rangpur | Rangpur | Pirgonj | Roypur | Bahadurpur | 6 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 8 | 88 | 20 | 17 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Jorpukur | 8 | House hold survey |
|  | Block Plantation (ha) | 25 | 35 | 57 | 89 | 15 | 01 | 55857654 | Rangpur | Rangpur | Pirgonj | Kumedpur | Rasulpur | 6 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 9 | 88 | 20 | 15 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Jorpukur | 8 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 10 | 88 | 20 | 11 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Chandona | 1 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 13 | 88 | 20 | 13 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Chandona | 1 | House hold survey |
|  | Block Plantation (ha) | 24 | 47 | 58 | 88 | 23 | 42 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Khandura | 7 | House hold survey |
|  | Block Plantation (ha) | 24 | 47 | 58 | 88 | 23 | 42 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Khandura | 7 | House hold survey |
|  | Block Plantation (ha) | 24 | 47 | 18 | 88 | 23 | 0 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kalitola | 7 | House hold survey |
|  | Block Plantation (ha) | 24 | 47 | 15 | 88 | 23 | 2 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kalitola | 7 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 57 | 88 | 23 | 40 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Khandura | 7 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 19 | 88 | 23 | 2 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kalitola | 4 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 16 | 88 | 23 | 3 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kalitola | 4 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 58.2 | 88 | 23 | 41.2 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Khandura | 7 | House hold survey |
|  | Road Side Plantation (km) | 24 | 47 | 34 | 88 | 23 | 43 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Khandura | 7 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 12 | 88 | 22 | 33 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kochrakolabona | 6 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 11 | 88 | 22 | 33 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kolabonakochra | 6 | House hold survey |
|  | Pond (19 nos) | 24 | 47 | 12 | 88 | 22 | 35 | 50705638 | Rajshahi | Chapai Nowabgonj | Nachole | Kasba | Kochrakolabona | 6 | House hold survey |
|  | Rain Water Harvesting | 24 | 48 | 53 | 88 | 21 | 18 | 50703784 | Rajshahi | Chapai Nowabgonj | Gomostapur | Rohanpur | Bhagolpur | 8 | House hold survey |
|  | Spice Cultivation (Person) | 25 | 24 | 41.88 | 89 | 17 | 2.81 | 55857675 | Rangpur | Rangpur | Pirgonj | Roypur | Bahadurpur | 6 | House hold survey |
|  | Pond (19 nos) | 25 | 29 | 33.28 | 89 | 22 | 7 | 55857663 | Rangpur | Rangpur | Pirgonj | Panchgachha | Amodpur | 1 | House hold survey |
|  | Block Plantation (ha) | 25 | 29 | 39 | 89 | 30 | 18 | 55857628 | Rangpur | Rangpur | Pirgonj | Bhendabari | Jatbaz | 8 | House hold survey |
|  | Block Plantation (ha) | 25 | 29 | 50.13 | 89 | 15 | 2.78 | 55857628 | Rangpur | Rangpur | Pirgonj | Bhendabari | Jotbaz | 8 | House hold survey |
|  | Pond (19 nos) | 25 | 25 | 8.17 | 89 | 16 | 25.49 | 55857675 | Rangpur | Rangpur | Pirgonj | Roypur | Shibpur | 4 | House hold survey |
|  | Vegetable Farming (Person) | 25 | 30 | 32.01 | 89 | 15 | 4.09 | 55857628 | Rangpur | Rangpur | Pirgonj | Bhendabari | Panbari | 9 | House hold survey |
|  | Block Plantation (ha) | 25 | 29 | 50.13 | 89 | 15 | 2.78 | 55857628 | Rangpur | Rangpur | Pirgonj | Bhendabari | Jotbaz | 8 | House hold survey |

Please provide any further geo-referenced information and map where the project interventions is taking place as appropriate. *

<p>NA</p>

[Annex any linked geospatial file]

Additional Supporting Documents:

| Filename | File Uploaded By | File Uploaded At |  |
| --- | --- | --- | --- |
| VCG Traing in Haor.pdf | ESS Admin | 2024-08-05 05:13:01 |  |
| 7th PSC minutes.pdf | CCA TM | 2024-08-02 09:04:01 |  |
| 8th PSC minutes.pdf | Executing Agency | 2024-07-30 10:23:35 |  |