GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

# PART I: PROJECT INFORMATION

| Project title: Development of Value Chains for Products derived from Genetic Resources in Compliance with the Nagoya Protocol on Access and Benefit Sharing and the National Biodiversity Economy Strategy |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | South Africa | GEF Project ID: |  | 5686 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  | 9255 |
| Other Executing Partner(s): | Implementing Partner: Department of Environmental Affairs (DEA) Responsible Parties: Agricultural Research Council (ARC), Council for Scientific and Industrial Research (CSIR) and Department of Science and Technology (DST) | Submission Date: Resubmission Date: Resumission Date: |  | 17 October 2017 16 April 2018 25 September 2018 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) |  | 60+ |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of Parent Program | N/A | Agency Fee ($) |  | 589,954 |

## Focal Area  Strategy Framework and Other Program Strategies

| ### Focal Area Objectives/Programs | ### Focal Area Outcomes | Trust Fund | (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | GEF Project Financing | Co-financing |
| BD3 - Program 8: Implementing the Nagoya Protocol on Access and Benefit Sharing | Outcome 8.1: Legal and regulatory frameworks, and administrative procedures established that enable access to genetic resources and benefit sharing in accordance with the provisions of the Nagoya Protocol Focal Area Indicator 8.1: National ABS frameworks operational score. [Refer to: (a) Project Results Framework indicator #1-4] | GEFTF | 6,210,046 | 35,870,563.86 |
| Total project costs |  | GEFTF | 6,210,046 | 35,870,563.86 |

## Project Description Summary

### Project Objective: to strengthen value chains for products derived from genetic resources that contribute to the equitable sharing of benefits and the conservation of biodiversity, with a focus on bioprospecting of indigenous plant species

| ### Project Components / Programs | ### Type | ### Project Outcomes | ### Project Outputs | Trust Fund | (in $) |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing | Confirmed Co-financing |
| Component 1) Research and development (R&D) of products in line with the definition of utilization of genetic resources of the Nagoya Protocol | TA | Outcome 1) Bioprospecting R&D that focuses on indigenous plants contributes to the national bioprospecting economy: - One flagship ABS monetary agreement negotiated for an ABS product derived from African Ginger - One ABS product developed and marketed. This is a product developed following Research and Development procedures and in accordance with the definition of genetic resources of the Nagoya Protocol - At least 1 (one) new patent registered - At least 4 (four) new market niches explored through sustainable and ABS-compliant value chains in the Northern Cape’s bioprospecting economy. | 1.1 R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. 1.2 Bioprospecting R&D in the Northern Cape is supported, boosting the local bioprospecting economy and establishing a strategically located ‘Bioproducts Development Hub’. | GEFTF | 1,510,500 | 9,600,064.94 |
| Component 2) Cooperation models support the conservation of and commercial trade in indigenous bioproducts | TA | Outcome 2) The ways of working, management conditions and techniques change within 5 (five) strategic value chains, and demonstrate how conservation and ABS-compliance can be simultaneously achieved through cooperation among bioprospecting economy players: - One flagship ABS monetary agreement negotiated for an ABS product derived from Rooibos. - Improved scores for the BD-8 Tracking Tool, Section 2, pertaining to the six ABS pilots foreseen under Component 2, and which sum 18 out 60 points in the baseline and increase to at least 32 out of 40 by project end. - No. of harvesters trained as per the sustainable harvester guidelines for three of the ABS pilots (i.e., Pelargonium, Aloe ferox and Honeybush) > 90 by project end, at least half of which are women. - Number of local community households for which members are employed in aloe ferox cultivation, harvesting and processing increase from <25 in the baseline to >80 by project end. - Total income (US$/annum) derived from project pilots increased (exact metrics to be defined): 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush - 450 hectares of Honeybush mitigate the current impact of habitat destruction and overharvesting of this species in the wild. | 2.1 The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. 2.2 Development of an Aloe ferox harvesting, processing and trading hub in the Eastern Cape for promoting sustainable and equitable benefit sharing across the value chain is supported. 2.3 Community-based enterprises in honeybush farming are supported, ensuring conservation and equitable benefit sharing outcomes across the Cyclopia spp. landscape in the Cape Region. 2.4 [*] The ABS implementation in Rooibos farming is strengthened, ensuring fairness, equity and sustainability in relevant relationships among TK holders and industry. [* The above Output was renumbered from 2.6 to 2.4, given that two outputs were dropped in response to GEF comments.] | GEFTF | 2,888,500 | 19,020,561.18 |
| Component 3) Bioprospecting and value addition knowledge transfer is enhanced for equitable benefit sharing | TA | Outcome 3) National capacity for the protection of traditional knowledge within the bioprospecting segment, as well as the general mainstreaming of both conservation and ABS compliance within them, is improved. - Level of mainstreaming of gender considerations in project monitoring (measured through scoring on the state of advancement in gender disaggregated data collection and analysis in ABS pilots), increase from 65% in the baseline to close to 100% by project end. -Increase in capacity scores for institutions implementing different aspects of ABS (as per the UNDP Capacity Scorecard and the ABS Tracking Tool Section 1) -A National Recordal System for Traditional Knowledge is fully functional and under utilisation | 3.1 The National Recordal System for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry. 3.2 A biotrade certification system for South Africa is developed with a view to safeguarding biodiversity conservation within bioprospecting value chains. | GEFTF | 1,365,000 | 4,721,593.00 |
| Component 4) Knowledge Management and M&E. |  | Outcome 4) Lessons learned and the application of a participatory and gender sensitive M&E framework effectively contribute to institutional, community and corporate learning on ABS -Number of project lessons generated and disseminated to share knowledge on implementation of ABS initiatives -Number of women and men participating and benefiting from project intereventions -50% women/50% men | 4.0 National and international stakeholders supported to participate in the project M&E and to systematize lessons learned from its implementation. | GEFTF | 150,330 | 820,222.65 |
| Subtotal |  |  |  |  | 5,914,330 | 34,162,441.77 |
| Project Management Cost (PMC) |  |  |  | GEFTF | 295,716 | 1,708,122.09 |
| Total project costs |  |  |  |  | 6,210,046 | 35,870,563.86 |

## Confirmed Sources of Co-financing for the Project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Department of Environmental Affairs (DEA) | Grants | 30,387,060.53 |
| Recipient Government | Department of Science and Technology (DST) | Grants | 769,230.76 |
| Recipient Government | Council for Scientific and Industrial Research (CSIR) | Grants | 2,783,777.00 |
| Recipient Government | Agricultural Research Council (ARC) | Grants | 1,415,110.96 |
| Recipient Government | South African National Boidiversity Institute (SANBI) | Grants | 515,384.61 |
| Total Co-financing |  |  | 35,870,563.86 |

## Trust FUND RESOURCES Requested by Agency(ies), COUNTRY(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b)2 | Total (c)=a+b |
| UNDP | GEFTF | South Africa | Biodiversity | NA | 6,210,046 | 589,954 | 6,800,000 |
| Total Grant Resources |  |  |  |  | 6,210,046 | 589,954 | 6,800,000 |

a ) Refer to the Fee Policy for GEF Partner Agencies

## Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| 1. Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | 50,000 Hectares5 |
| 6. Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: 1 |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: 1 |

## Does the project include a “non-grant” instrument?    No.

(If non-grant instruments are used, provide an indicative calendar of expected reflows to your Agency and to the GEF/LDCF/SCCF/CBIT Trust Fund) in Annex D.

# PART II:  PROJECT JUSTIFICATION

## Describe any changes in alignment with the project design with the original pif

### A.1. Project Description.

#### Overview of What Changed since PIF Stage

| Topic | At PIF Stage | At CEO Endorsement Stage |
| --- | --- | --- |
| Project Objective | The Project Objective had the following formulation: “To Strengthen Value Chains for Products Derived from Genetic Resources that contribute to the equitable sharing of benefits and the Conservation of Biodiversity” | No changes made. At the same time, a small caveat was added to the project objective with the aim of making the objective a bit more precise and in line with the argument presented in PRODOC Section II (Development Challenge). The objective statement in the PRODOC Section III (Strategy), under sub-section ‘Long-Term Solution’, reads as follows: “The proposed project Objective is to strengthen value chains for products derived from genetic resources that contribute to the equitable sharing of benefits and the conservation of biodiversity, with a focus on bioprospecting of indigenous plant species.” Adding the explicit reference to indigenous plant species was deemed important, because the universe of species used within the bioprospecting segment in South Africa may include other species but plants. It may include e.g. insects, other faunal species and micro-organisms. It may also include non-indigenous species. Yet, the focus of the GEF project is clearly limited to indigenous plant species within this context. Therefore, it was important to stress it. By March 2018: In response to Comments from GEF Secretariat at CEO Endorsement stage, several changes were made. These are marked and registered herein in the appropriate section. |
| Focal Area Strategy Framework | The following Focal Area Strategy Framework was proposed at the PIF stage: BD-3 Program 8: Implementing the Nagoya Protocol on Access and Benefit Sharing | No changes made. |
| Project Outcomes and Outputs | The PIF included many outputs organized under three core project Outcomes/Components: Outcome 1) Research and development of products in line with the definition of utilization of genetic resources of the Nagoya Protocol Outcome 2) Value chain development, biodiversity conservation and benefit-sharing for bioprospecting products Outcome 3) Capacity building of agencies to add value to genetic/biological resources; develop model contractual clauses; and negotiate, implement and monitor ABS agreements The core concepts behind the project Components were as follows: - R&D - Value Chains - Capacity Building for ABS (Output content at PIF is summarized further down.) | Summary of changes introduced: During the PPG stage, Project Strategy has been critically reviewed. Project’s scope and entry point are still the same. The core concepts behind the project Components and their order were also kept intact – namely (1) R&D; (2) Value Chains; (3) Capacity Building. There were only slight changes to the exact wording of Outcomes as follows: Outcome 1) Bioprospecting R&D that focuses on indigenous plants contributes to the national bioeconomy Outcome 2) The ways of working, management conditions and techniques change within 5 (five) strategic value chains, and demonstrate how conservation and ABS-compliance can be simultaneously achieved through cooperation among bioeconomy players Outcome 3) National capacity for the protection of traditional knowledge within the bioprospecting segment, as well as the general mainstreaming of both conservation and ABS compliance within them, is improved (as independently assessed). There were, however, more important changes at the output level, as it will be explained and justified in the next pages. Justification for the changes: Changes to project Outputs vis-à-vis the PIF – as well as to how project results are measured – were deemed necessary by the project owner, the Department of Environment (DEA). They were endorsed by UNDP and project stakeholders through a participatory/consultative process and were mainly triggered by the following elements: The viability of certain ABS partnerships, as they presented themselves at PPG stage (e.g. partnerships with the University of Pretoria were no longer considered viable), requiring the approach to partnerships to be revisited; Developments with respect to government policies and priorities, and within the bioprospecting sector itself; and not least also The need to address STAP and GEF Council critical comments. With respect to government priorities, it is worth noting that the PIF had been formulated at stage when the National Biodiversity Economy Strategy (NBES) had barely been proposed. Several elements regarding priority species for ABS value chain development, the context for the bioeconomy, as well as approaches to the implementaiton of ABS measures, needed further development and consolidation. In fact, several studies and assessments underpinned the development of the NBES. For example, in connection with the approval of the NBES, DEA published a seminal study in 2015, which surveyed the scope and extent of the utilization of indigenous biological resources by bioprospecting industries in South Africa. The results of the scoping study served to inform the review of project Outputs, as well as consultations with stakeholders. Refer to UNDP PRODOC Box 2 ‘Key conclusions and highlights from the 2015 Scoping Study on Bioprospecting’, for details. In the above-mentioned ‘Box 2’, it is explained that, in 2016, the scope and priorities for South Africa’s Bioeconomy were reviewed through a series of intense policy development workshops led by DEA – a process referred to as ‘Operation Phakisa’. The mentioned workshops were aimed at operationalizing the 14-year NBES and were crucial for defining priorities for bioprospecting R&D, value chain development and ABS capacity building. Operation Phakisa Outcomes – which are documented in DEA’s website – helped shape the adjustments to project design that were introduced during the PPG stage. The PIF, as it was designed in 2015, would not have been aligned with the Outcomes of Operation Pakhisa’. It is also worth noting that the bioprospecting R&D segment is rather dynamic. The set of species and products that are on focus tend to change quickly as a result of market demand and R&D. The current CEO ER takes into account these factors by prioritizing e.g. the development of a R&D hub for the Northern Cape Province and the processing one for Aloe ferox in the Eastern Cape. These are the core of current project outputs, which were not included in the PIF Concept. Hence, there were some changes to project design – in fact ‘adjustments’ to it – but no changes to its ‘scope’. In other words, the project is still a national ABS project with a focus on indigenous plant species and bioprospecting value chains. It has three components wich focus on (1) R&D, (2) Value Chains and (3) Capacity Building for ABS -- exactly as at PIF stage. Another result of the PPG process is that, the project’s Theory of Change is now fully developed. Refer to UNDP PRODOC, Sub-section ‘The Project’s Theory of Change (ToC)’, under Section II. As a result: The core concept behind certain outputs had been retained, but others were dropped, changed or moved to different components; The project strategy was consolidated either around ‘ABS pilots’ or ‘ABS systemic measures’ – a decisive element of logical organization behind the current project design; Priority species, value-chains, bioprospecting hubs and partnerships were consolidated. Additionally, a fourth ancillary component (#4), aimed at making the Project’s legacy available at national and international level was developed as per the new requirements of UNDP’s project design approach, as also encouraged by the GEF. At the PIF stage, this aspect was missing. It reads as follows: Outcome 4) Lessons learned and the application of a participatory and gender sensitive M&E framework effectively contribute to institutional, community and corporate learning on ABS. Overall, the project strategy at CEO Endorsement stage is much more thoroughly justified and described in the UNDP PRODOC (and also reproduced herein, further down). Refer to UNDP PRODOC, Section II. DEVELOPMENT CHALLENGE and Section III. STRATEGY for the justification. The details regarding the changes made at Outputs level under the different project components are explained below. By March 2018: In response to Comments from GEF Secretariat at CEO Endorsement stage, several changes were made. These are marked and registered herein in the appropriate section. |
| Component 1 Outputs | Summary of Component 1 Outputs, as formulated at PIF stage: Output 1.1 National Conservation assessment. Output 1.2 Ethnobotanical report completed Output 1.3 A central information- sharing hub Output 1.4 Data collected and analysed including: - pharmacodynamic assessment for potential efficacy which is required before clinical based studies can be performed. Output 1.5 Property rights ensured by clinical studies and research, conducted by the Council for Scientific and Industrial Research (CSIR), University of Pretoria and other institutions | Changes introduced to Component 1: Two Outputs, where R&D is an important element in the ABS pilots, were retained under Component 1: Output 1.1 R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. Output 1.2 Bioprospecting R&D in the Northern Cape is supported, boosting the local bioeconomy and establishing a strategically located ‘Bioproducts Development Hub’. Justification for the changes: The current Output 1.1 corresponds to PIF-stage Output 1.4, but it is now restricted to African ginger only. The inclusion of support to other types of clinical trials, as they had been proposed at PIF stage, were dropped, because they were not considered realistic or strategic. This is the case of PIF outputs and results relating to proving TB healing properties of Trimmune and liv green, as well as Hoodia Gordonii’s ability to reduce obesity. Without entering into the subject matter of the validity of such claims, DEA, UNDP and the PPG Team reached the conclusion that supporting that line of R&D towards product development would not be sufficiently strategic as a GEF ABS investment. Comments from STAP had namely warned about this and recommended caution in the selection of ABS pilots, in particular, those that involve R&D: STAP Comment [TOPIC 1]: “The project essentially proposes research into ten bio-products, and is strong in these explanations. A caution, however, is the timescale for the project at 60 months which is likely to be too short for new products researched under this component to complete clinical trials, which can take more than a decade.” Overall, those PIF stage pilots were considered a less effective GEF investment at CEO Endorsement stage, given the amount of funding available, the time needed for producing results and the complexity of partnerships that are required for achieving results. Also, the focus under the current Output 1.1. R&D pilot for African ginger (S. aethiopicus) is on the development of a medicinal product for asthma and allergies (working with CSIR), whilst also considering what would be needed for conserving the diversity of the plant’s gene pool in the wild. Additionally, Output 1.1 will ensure that CSIR’s agreement with the Traditional Healers Committee is made ABS-compliant with respect to the use of African ginger’s genetic resources. An agreement is in place but, according to the baseline analysis, it requires revision. In addition, agro-processing businesses will be able to accelerate the transition in methods used in the S. aethiopicus value chain -- from wild harvesting using degrading methods to cultivation, and thereby help lift the pressure on wild resources. As it is, S. aethiopicus is red-listed as ‘critically endangered’. This work will be pursued not with GEF funding but with national and provincial governments’ support. As for the current Output 1.2, it corresponds grosso modo to PIF-stage Output 1.3, except that the most important bioprospecting hub to be supported by the project will be based in the Northern Cape Province. The development of a hub ensures, first and foremost, a physical presence on the ground for achieving the proposed goals, rather than only a virtual one, which had been implied at PIF stage. A second provincial bioprospecting hub is also foreseen, but with a stronger focus on cultivation – and more specifically of Aloe ferox in the Eastern Cape -- rather than a vague focus on R&D. Therefore, the work under this second hub is addressed under Output 2.2. Regarding the PIF-stage Outputs 1.2 and 1.4, the core concept behind them were effectively sub-summed into the current Output 3.1 (on the development of a National Recordal System for TK, working with DST) and current Output 3.2 (regarding a BD-sustainability Certification System, where SANBI will be working in partnership with DEA to develop it). Refer otherwise to the following sections in the UNDP PRODOC Annex X-2 for more details on background: Section 2) Status Quo for the Management of Targeted Species Section 3) The Context of African Ginger agreement registration and cultivation Section 4) The Context of the Bioprospecting in Northern Cape Province Refer also to UNDP PRODOC Annex X-3, ‘Component 1. Bioprospecting R&D’ for the description of the work at hand. In response to Comments from GEF Secretariat at CEO Endorsement stage, a box was added to the PRODOC providing additional explanations: Box 9 (new) Win-Win A promising value chain with African Ginger and a gateway to sustainable use. |
| Component 2 Outputs | Summary of Component 2 Outputs, as formulated at PIF stage: Output 2.1 Value chains for Pelargonium sidiodes, Lippia javanica, Gelania africana, Aloe forex, Hoodia gordonii, LivGreen, TrImmune etc) developed and tested on the market for acceptability. Output 2.2 An online system in place providing information about abundance and availability of resources for bioprospecting activities (linked to the permitting application system) and an online permitting system for efficient access to resource by national, regional and international traders. Output 2.3 10 Biodiversity Management Plans developed and implemented according to permit conditions and harvesting guidelines produced and endorsed by stakeholders. Output 2.4 Harvest and collection processes respect and recognise customary rights of local and indigenous communities to use and manage collection areas. | Changes introduced to Component 2: It was necessary to revisit the focus of species and value chains under Component 2, not least also as a result of the priority-setting that took place under Operation Pakhisa. It would not have been realistic to retain the same set of species and value chains as those proposed at PIF stage. Six Outputs were retained under Component 2 as ‘on-the-ground’ ABS pilots: Output 2.1 The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. Output 2.2 Development of an A. ferox harvesting, processing and trading hub in the Eastern Cape for the promotion of sustainable and equitable benefit sharing across the value chain supported. Output 2.3 Community-based enterprises in honeybush farming supported, ensuring conservation and equitable benefit sharing outcomes across the Cyclopia spp. landscape in the Cape Region. Output 2.4 [*] The ABS implementation in Rooibos farming is strengthened, ensuring fairness, equity and sustainability in relevant relationships among TK holders and industry. [* The above Output was renumbered from 2.6 to 2.4, given that two outputs were dropped so as to provide an adequate response to GEF comments in February 2018.] Justification for the changes: The current value chain development aspect of PIF-stage Output 2.1 has been broken-down into four specific outputs under Component 2, but where the focus species are different than those at PIF stage. The current Output 2.1 is now restricted to P. sidoides, while A. ferox is covered under the current Output 2.2 (cultivation, habitat management and processing hub with focus on A. ferox). Species with the common name of Honeybush (Cyclopia spp.) are in turn targeted under current Output 2.3, where the focus is on landscape level management. Finally, Roiboos ABS deal issue is addressed under current Output 2.4. The subject matter of PIF-stage Output 2.2 (which mentioned an 'online system') has been effectively sub-summed into the current Output 3.1 (on a National Recordal System for TK), working with DST to achieve goals. In addition, it was considered that the creation of a virtual "market place" (also implied in the PIF-stage Output 2.2) could end up being counterproductive with respect to both ABS and conservation goals. DEA, UNDP and PPG Team considered that it could potentially create excess demand for specific bioproducts that are already rare at the landscape level, due to overharvesting, habitat loss or a combination of both. The conclusion reached during the PPG stage is that GEF resources would be better spent ensuring the sustainability and ABS-compliance of selected value chains, by focusing on where the project is able to make a significant change. This was considered more strategic than the proposal implied in PIF-stage Output 2.2. As for the subject matter of PIF-stage Output 2.3 (regarding biodiversity management plans), the work envisaged is now catered for under the current Output 2.1 (on P. sidoides), Output 2.2 (on A. ferox cultivation, habitat management and processing hub) and Output 2.3 (with focus on the Honeybush habitat). In addition, the PIF-stage Output 2.4 (on the recognition of customary rights of local and indigenous communities) focuses on reaching an ABS-compliant agreement between the Rooibos industry and the Koi-San Council and has the potential to be a ground-breaking contribution of the project in the matter of recognizing customary rights vis-a-vis genetic resources (not necessarily land tenure though, which is anyway outside the scope of the project). Further to this, broader and systemic measures regarding ABS-compliance are indeed included in the project, but under Component 3, changes to which are explained further down. Finally, the PPG baseline analysis indicated that the level of threat to bioresources Honeybush and African ginger would point to the need for strengthening their cultivation, as opposed to wild harvesting. A clear focus on conservation and sustainability – in addition to ABS, and as part of it – was not sufficiently strong at PIF stage. This is now addressed, not least also in response to STAP and GEF Council members critique of PIF design. Refer otherwise to the following sections in the UNDP PRODOC Annex X-2 for more details on background: Section 2) Status Quo for the Management of Targeted Species; Section 5) The Context of Pelargonium Management Plan; Section 6) The Context of Aloe ferox harvesting; Section 7) The Context of Honeybush species transition to cultivation; and Section 8) The Flagship Context of Rooibos. Refer also to UNDP PRODOC Annex X-3, ‘Component 2: Value Chain Development’ for the description of the work at hand. |
| Component 3 Outputs | Summary of Component 3 Outputs, as formulated at PIF stage: Output 3.1 Integrated training programme developed that encompasses all relevant government departments Output 3.2 Database of relevant training material, interactive and on-line tools and methodologies available to sector Output 3.3 Information exchange among all stakeholders on ABS, research and development including best practices | Changes introduced to Component 3: Only two Outputs were retained under Component 3 and as ‘systemic measures’ regarding ABS and/or sustainability – as follows: Output 3.1 The National Recordal System for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry. Output 3.2 A biotrade certification system for South Africa is developed in view of safeguarding biodiversity conservation within bioprospecting value chains. The PIF-stage Outputs 3.1, 3.2 and 3.3 have been merged into two broad ‘systemic-level capacity’ outputs. Current Output 3.1 focuses on the National Recordal System, working in partnership with DST, and current Output 3.2 focuses on a Biodiversity Certification System and on capacity building of key stakeholders for conservation and sustainability, where SANBI will lead and support DEA. Justification for the changes: The results (or outcomes) of ‘Operation Phakisa’ (mentioned further up) were crucial for defining priorities for bioprospecting and ABS capacity building. This helped shape the content of Component 3. In addition, between PIF approval and the design of the FSP PRODOC, a new GEF-financed global project with a focus on ABS capacity building became operational (title: ‘Strengthening human resources, legal frameworks, and institutional capacities to implement Nagoya Protocol’). South Africa is a participating country. After due analysis, it became clear that several capacity building activities that have been foreseen at PIF stage for Component 3 would be adequately catered for under the Global ABS project. DEA, UNDP and the PPG Team concluded that would be meaningless to duplicate efforts in the current project. Therefore, the priorities for Component 3 changed. Refer otherwise to the following sections in the UNDP PRODOC for more details on background: Annex X-2, Section 1) Status Quo of the Implementation of Nagoya Protocol in South Africa; and The following sub-sections under Section II. DEVELOPMENT CHALLENGE: - Context, issues and global significance; - The Biodiversity Economy of South Africa; - The Bioprospecting Segment; - Research & Development for Bioprospecting; and - ABS Frameworks and Sectoral Regulation. Refer also to UNDP PRODOC Annex X-3, ‘Component 3: ABS Capacity Building of key Stakeholders’ for the description of the work at hand. |
| Project Strategy | The PIF represented the initial development of the Project Concept and the Project Strategy. | The project’s overall strategy is now fully developed and the current approach consolidated: The Long-Term Solution for the project stands as follows: “the bioprospecting value chains deliver significant economic, social and environmental benefits through the negotiation of monetary (such as royalties and payments per sample) and non-monetary agreements or collaboration frameworks (such as biodiversity conservation, technology, research and training opportunities) between the providers and users of genetic resources”. Three Project Components and a fourth, ancillary one with focus on M&E and Knowledge Management will contribute to the Long-Term Solution. The Project’s Theory of Change (ToC) defined the expected results of the project within its scope and from a perspective of the ‘desired change’ and at the same time outlined the process of ‘getting there’ or achieving these results, where a set of pre-conditions were conceived in a logical causal chain. The project’s strategy is thereby consolidated, to the extent that these pre-conditions provide the key elements to the project’s revised outputs. The identified Barriers will be overcome by first identifying their drivers and root causes, as well as analysing the project’s baseline; secondly, by providing viable solutions to the challenges that these barriers represent, and thirdly by proposing a set of activities in the form of feasibility studies. Generally, there were ‘adjustments’ to the project design, but no major changes to its strategy and clearly no changes to the project ‘scope’. There were changes in certain priorities that informed the strategy. This is already discussed further up. Still, it is worth noting that one of the triggers the changes introduced since PIF stage have been comments from STAP: STAP Comment [TOPIC 3]: “The PIF is weak where it discusses how to develop value chains, implement field management plans, and ensure local benefit. Further effort to design inclusive and participatory processes and tools to benefit local and indigenous communities' participation in value chain development and also collection and management of the resource is required.” Definitely, the current project strategy is much stronger than at PIF stage. It is reproduced further down for better reference. Refer also to the UNDP PRODOC Section III. Strategy for more details. |
| Allocation of GEF funding | Was indicatively: Component 1) $914,330 Component 2) $4,000,000 Component 3) $1,000,000 KM and M&E) - PMC) $295,716 (is <5% of subtotal) --------------------------------------------- TOTAL $ 6,210,046 | Is now: Component 1) $1,510,500 (+65%, given the new proposed pilots) Component 2) $2,888,500 (-15%, still retaining most of the GEF’s budget) Component 3) $1,365,000 (-13%, modest but strategic) KM and M&E) $150,330 (new and added) PCM) $295,716 (unchanged) --------------------------------------------- TOTAL $ 6,210,046 (unchanged) The above adjustments to GEF funding allocation were needed, given the changes in the conceptualization of project Outputs, as explained further up. Refer to the UNDP PRODOC Section X ‘TOTAL BUDGET AND WORK PLAN’ for more details. |
| Co-financing | Was indicatively $ 22,215,042 | Effectively, $35,870,563.86 million were mobilized at CEO Endorsement stage, more than $13 million than at PIF stage, with letters making partners’ commitments explicit, including with the more rencent confirmation of co-financing from ARC and SANBI. Refer to the UNDP PRODOC, Subsection ‘The Project’s Incremental Reasoning’ under Section IV ‘RESULTS AND PARTNERSHIPS, Expected Results’ for more details and to ANNEX X-1 ‘Letters of Co-financing’ for the complete set of letters. |

#### 1) The global environmental problems, root causes and barriers that need to be addressed

Summary of Context and Scope:

- South Africa is a megadiverse country and this diversity is expressed in terms of both species richness and endemism. The conservation and sustainable use of South Africa’s biological diversity is of strategic importance for the country. So is the maintenance of ecosystem services – now and in the future. This species richness and associated genetic diversity provides an important basis for economic growth and development which underpins the well-being of society.

Under leadership of the Department of Environmental Affairs, South Africa launched in 2015 its National Biodiversity Economy Strategy (NBES). The Strategy is concerned with supporting the development of businesses and economic activities that are either directly dependent on biodiversity for their core business or that contribute to conserving biodiversity through their activities. An important segment of the NBES is ‘bioprospecting’, and under it ‘biotrade’.

The project will specifically support the implementation of the NBES by focusing on the use of indigenous plants' genetic resources and their current and potential applications, either in pharmaceuticals, personal care products, cosmetics, enzymes or similar non-food uses. It will address both conservation and Access Benefit Sharing (ABS) issues linked to the development of different bioprospecting value chains, while also helping key players overcome related barriers and challenges.

The Core Problem:

Growth in the bioprospecting industry can potentially have a significant positive impact on the national and local economy in South Africa, while contributing to national imperatives such as job creation, rural development and conservation of our natural resources. However, for the bioprospecting sector to achieve its full potential – and so that global biodiversity benefits are also generated – a strategic partnership between the state, private sector and communities is required.

The core problem that the project will address boils down to three aspects:

#1) The NBES emphasises that transformation in the bioprospecting value chain is inequitable.

#2) The role of traditional knowledge.

#3) Ecological sustainability.

These are discussed in detail in the UNDP PRODOC in the sub-section referred to further up.

Threats (to biodiversity), Root Causes and Barriers:

South Africa’s floral diversity is under threat in various parts of the country due to a variety of causes. Within the bioprospecting value-chains based on indigenous plants, the most prevalent threat to biodiversity is linked to overharvesting (i.e. when specific species are harvested beyond their natural regeneration rate), but also due to extant factors vis-a-vis the bioprospecting segment (namely, habitat shrinking, degradation and even climate change).

Increased demand for bioprospecting products, fuelled by R&D and innovation, is a double-edged sword (see PRODOC Figure 6). It can certainly contribute to improving livelihoods, sustainable development and economic growth. New discoveries based on genetic resources can potentially improve the well-being of humanity at large.

Yet, driven by market forces, bioprospecting economic actors within value chains will tend to explore targeted species in the wild beyond their regeneration capacity. At the level of landscapes, and depending on specific conditions that are contextual to each value-chain, individual species can be pushed into the extinction pathway. Overexploitation also leads to the degradation of species’ valuable gene pool and ultimately undermines the biotrade activity that it supports.

Additionally, South Africa is an ethnically diverse country and it is also home to ‘indigenous and local communities’, including the Khoi-San who identify themselves as one of the First Nations Indigenous groups. Indigenous and local communities are recognized as being bearers of TK on genetic resources and can potentially make claims to discoveries regarding the use of genetic resources indigenous to South Africa – as they have done in the past.

Although South Africa has made impressive progress towards ethnic inclusiveness – and although the country has a well-developed legal and policy framework for both ABS and biodiversity management – this has not immediately translated into compliance with ABS laws or sustainability across the different bioprospecting value chains.

Some of the root causes (or drivers) behind the degradation of biodiversity linked to bioprospecting value chains include: (1) Sub-optimal investments in sustainable and ABS-compliant R&D; (2) Value chains have a myopic view of what constitutes ‘value creation’, so economic players often overlook conservation concerns and the role of TK; and (3) Limited national capacity and inadequate institutional arrangements for ABS and conservation, which translates into incipient experience with ABS-compliance and sustainability.

Based on threat profile and contextual analysis contained in the general background section, the project’s barrier analysis was developed.

Three barriers impede the realization of the solution envisaged by the project, as follows:

- Barrier #1) Gaps in scientific knowledge on how to improve the benefits derived from bioprospecting

- Barrier #2) Challenges in ways of working, management conditions and techniques within bioprospecting value-chains – in particular with respect to the sustainability of supplies (i.e. plant raw materials).

- Barrier #3) Gaps in national capacity for ABS-compliance

These above barriers are thoroughly discussed in the UNDP PRODOC. The content of Barrier #2 has been slightly updated in light of comments from the GEF Secretariat to the first iteration of the UNDP PRODOC, with more emphasis on the the sustainability of supplies.

Refer to the UNDP PRODOC Section II. DEVELOPMENT CHALLENGE for more details.

An overview of specific sub-sections is listed below referring to the global environmental problems, the root causes and the project’s barriers. A summary of their content is also included further down for ease of reference:

Refer to UNDP PRODOC Section II, Context, issues and global significance, including:

- The Biodiversity Economy of South Africa;

- The Bioprospecting Segment;

- Research & Development for Bioprospecting;

- ABS Frameworks and Sectoral Regulation;

- Bioresources targeted in key Value Chains; and

- The Core Problem

UNDP PRODOC Section II, Threats, Root Causes and Barriers

#### 2) The baseline scenario or any associated baseline projects

Refer to the UNDP PRODOC Section II. DEVELOPMENT CHALLENGE for ample details on the status quo for the bioprospecting sector in South Africa, particularly with respect to the implementation of the Nagoya Protocol and the safeguarding of habitats, genetic resources and the rights of TK holders. This constitutes the baseline scenario.

Refer also to the UNDP PRODOC Annex X-2 for specific baseline information with respect to the project’s ABS pilots and systemic measures. PRODOC Table 3 below provides the reference.

PRODOC Table 3. Reference to background materials and their relevance for the project’s strategy

| Sub-sections in Annex X-2 | Relevance |
| --- | --- |
| 1) Status Quo of the Implementation of Nagoya Protocol in South Africa | Project Objective, more generally, and Component 3, more specifically |
| 2) Status Quo for the Management of Targeted Species | All project pilots (Outputs 1.1 through 2.4) |
| 3) The Context of African Ginger agreement registration and cultivation | Outputs 1.1 |
| 4) The Context of the Bioprospecting in Northern Cape Province | Outputs 1.2 |
| 5) The Context of Pelargonium Management Plan | Output 2.1 |
| 6) The Context of Aloe ferox harvesting | Output 2.2 |
| 7) The Context of Honeybush species transition to cultivation | Output 2.3 |
| 8) The Flagship Context of Rooibos | Output 2.4 (renumbered in light of changes to the set of outputs in response to comment from the GEF Secretariat to the first iteration of the UNDP PRODOC. |
| 9) The Project’s Baseline Finance Assessment | The underlying financial baseline |

The project’s baseline finance has been assessed at approximately $560 million, as summarized below (updated in light of confirmedco-financing from ARC):

PRODOC Table 5. Summary of baseline finance for the incremental cost calculation

| Baseline / Cofinancing | # | Baseline Investment (B) / Co-financing (C) | TOTAL ($M) | Of which, contribution to co-financing ($M) | Total Co-financing | Leveraged co-financing |
| --- | --- | --- | --- | --- | --- | --- |
| B&C | 1 | Department of Environmental Affairs (DEA) | $145.00 | $27.95 | $30.39 | $2.44 |
| B&C | 2 | Department of Science and Technology (DST), including CSIR | $16.00 | $0.50 | $0.77 | $0.27 |
| B&C | 3 | South Africa National Biodiversity Institute (SANBI) | $0.51 | $0.00 | $0.51 | $0.51 |
| B&C | 4 | Council for Scientific and Industrial Research (CSIR) | $2.78 | $2.78 | $2.78 | $0.00 |
| B&C | 5 | Agricultural Research Council (ARC) | $15.00 | $1.42 | $1.42 | $0.00 |
| B | 6 | Private Sector / Communities / Academia | $375.00 | 0 | 0 | $0.00 |
| B | 7 | Bilateral donors | $5.00 | 0 | 0 | $0.00 |
| B | 8 | Civil Society | $0.50 | 0 | 0 | $0.00 |
|  |  | TOTAL | $559.79 | $32.65 | $35.87 | $3.22 |

Refer to the UNDP PRODOC Annex X-2, Subsection 9 ‘The Project’s Baseline Finance Assessment’ provides the details for the above financial baseline analysis.

#### 3) The proposed alternative scenario, GEF Focal Area Strategies, with a brief description of expected outcomes and components of the project

From the project’s Theory of Change (included in full in the UNDP PRODOC), it is worth highlighting the project’s approach to (a) Conservation aspects and (b) ABS aspects, presented on PRODOC Figure 10 (reproduced herein), which shows strategies, measures and approaches that will be used in the project to achieve either ABS compliance or conservation goals.

Error! Reference source not found. is divided into two parts, of which the first one, Part (a) explains how the project has consistently applied the “Ecosystem Approach” in its specific context for producing global biodiversity benefits, while Part (b) explores the different strategies for ABS and how they apply to both project ‘pilots’ and ‘systemic measures’

Concerning Part (a), the project departed from a limited set of priority plant species -- all indigenous and all focused on the bioprospecting segment. This scope had already been defined at PIF stage and remained unchanged at PRODOC for CEO Endorsement stage. What is new is that the Ecosystem Approach has now helped shape the project strategy on the basis of “the species’ needs” – that is, putting their ‘survival’ in the face of threats first and, herein implied, ensuring also the ‘robustness of their wild gene pools’. Such approach equally implies putting the core focus on the conservation status of habitats in which these species occur in situ and where their gene pools may or may not be adequately conserved – something that the project needs to verify on a case-by-case basis.

The approach also recognizes that different species used in the bioprospecting segment occur in different types of ‘landscapes’ (or habitats), some of which are rather limited, while others have a more widespread distribution. As the species enter value chains, they may be subjected to differentiated and dynamic pressures (levels of threat). They also have different life cycle conditions and are subject to external threats. All of these factors, combined, influence the species’ resilience and the viability of their populations. They are determinants of whether it is feasible or not, from a project intervention point of view, to focus on sustainable use of wild resources or whether support to ‘cultivation’ is a better investment from a conservation – and ABS – point of view.

How these conditions specifically affect the species’ needs within an Ecosystem Approach is discussed in more detail in Annex X-6 (The dynamics of resource overexploitation in bioprospecting value chain). There are two main “take home” lessons from the mentioned annex: First, “Plant extractivism” (or wild harvesting) constitutes a very fragile economic basis, subject to the interference of several variables that neither users nor providers of genetic resources fully master or control. Therefore, a precautionary approach would be warranted. Secondly, an area of concern and a recommendation pertaining to the economics of wild-harvesting / plant extrativism is as follows “In the medium and long term, a pathway to sustainability should emphasize the importance of research policies aimed at plant domestication to simultaneously meet market growth and biodiversity conservation objectives.”

To reach useful conclusions on concrete cases (i.e. “real-life” situations and “on the ground”— as referred to by the GEF Secretariat) – and in order to shape -- specific studies are needed. While these are included in the set of activities that for part of the project strategy, for now, Error! Reference source not found.(a) placed the different species and systems across a gradient of land-uses that, from an ecological (and theoretical) perspective, vary from biotope to monoculture, with respect to the level of intactness of ecosystems, as defined under “Step 1”. This served to identify on a notional basis and through “Step 2” the ideal land-use management trend that the project should try and influence – shaping thereby specific interventions. With respect to the different species, the approach and strategy may be thus summarized:

(i) For the critically endangered African ginger (Siphonochilus aethiopicus), urgent and consistent measures are needed for it to recover from the extinction path. Within South Africa the distribution is quite restricted (only 35,324 km2 -- see Plant Distribution Sheet 1: African Ginger in PRODOC Annex X-2.2). In addition, the plant is highly sought after for its use in traditional medicine in South Africa, which lead to over-exploitation and resulted, over the years, in a possible regional extinction in the wild. Yet, there is uncertainty about the current conservation status of the species -- in South Africa, at least. The wild distribution of Siphonochilus aethiopicus (Schweinf.) B.L.Burtt is otherwise widespread from Ethiopia, west to Sierra Leone and then south to Southern Africa. Varieties across Africa differ in their genetic expression, so cross-fertilization with foreign gene pools may not be a viable strategy for securing species survival. Hence, it is first and foremost important to re-assess the conservation status of the species and thereafter pressures on wild harvested populations of Siphonochilus aethiopicus are expected to be reduced.

For DEA, in partnership with SANBI and ARC, the goal will be to devise a species-management and conservation plan for Siphonochilus aethiopicus. The plan may include investing in a sustainable harvesting program, where the project will help safeguard the ginger’s gene pool across its natural landscape. Such program may apply in areas outside of protected areas – within them, enforcement of no harvesting should apply and this is already being undertaken by baseline finance activities. Such measures may not be enough to secure the species survival in the wild and a rapid and sustainable transition to cultivation needs to be supported simultaneously.

ARC is already assessing the agronomical conditions that will likely make, in the near future, cultivation of African Ginger viable, including by the same local population that normally seek the plant’s wild resource. ARC is currently testing techniques for Siphonochilus aethiopicus cultivation in at least two experimental farms across South Africa. The Center is also ready and willing to provide – with own funds -- extension services to local communities who are willing to engage in cultivation of African Ginger, as a possible increase in demand can either have detrimental or a positive impact on the species’ survival. The project will shift conditions to ensure that it is the latter, namely avoiding extinction through the conservation of Siphonochilus aethiopicus, primarily as a genetic resource used in agro-industrial processes for the production of medicinal products, whose clinical efficacy is about to be proven, not least also due an incremental support from the project.

(ii) For Aloe ferox, Pelargonium spp. and wild-harvested Honeybush landscapes, the aim is (for now) to ensure that landscapes and resources are sustainably managed. In fact, DEA has recently published 2017(a) useful guidelines on this (see e.g. McGregor, 2017a).

(iii) For the Northern Cape hub, the project will help create better conditions for ecologically-adapted cultivation systems for species of interest to the bioprospecting value chains. However, cultivation and extension services are not the main goal of the hub.

(iii) As for Rooibos (Aspalathus linearis), the project will not focus on cultivation of Rooibos, but rather on addressing an ABS gap and legal gaps to achieving it. The strategy is therefore one of maintaining the status quo. The species’ gene-pool is considered to be well-conserved across multi-use landscapes. Its wild distribution falls mostly within the Western Cape and to a lesser extent the Northern Cape Province and covers an area of approximately 56,231 km2. Production of Rooibos for various purposes comes in 99% of the cases from cultivation.

Concerning Part (b) of Error! Reference source not found. concerns the strategies for the project’s different pilots, as well as policy measures with respect to ABS. Measures that typically apply to ABS projects / initiatives are the following:

- Assisting in designing harvesting, collection, and reproduction methods for genetic resources

- Designing monetary and non-monetary benefit-sharing options, including benefit-sharing trust fund design

- Implementing in-situ and ex-situ biodiversity conservation strategies

- Providing support on Free and Prior Informed Consent Procedures

- Supporting the design of checkpoints at all stages of the value-chain that include research, development, innovation and pre-commercialization

- Assisting with the value chain of products

- Facilitating negotiation processes between private companies and indigenous peoples and local communities.

How these measures apply to the differet project outputs is covered under Error! Reference source not found.(b).

UNDP PRODOC Figure 10. Theory of change behind the project strategy: (a) Conservation aspects and (b) ABS aspects

(a) Applying the Ecosystem Approach. Step 1) Classifying land-use gradients from an ecological perspective. Level of Intactness of ecosystems. Biotope; Natural Landscape Management; Active Landscape Management; Agro-forestry and inter-cropping models; Monoculture. Wilderness with abundant gene-pools – often land has, or should ideally have status as protected area, protected landscape or easement.; Wild harvesting of species with little or no known negative impacts on biodiversity, also no systematic plan is applied to resource harvesting activities; Planned and selective wild harvesting that avoids, minimizes and mitigates negative impacts on biodiversity, with some level of active planting and landscape restoration measures, where needed; Dynamic cultivation models that combine trees, shrubs, grasses, and crops; Single crop plantation which maximizes yield per unit of area and seeks the standardization of products obtained. Step 2) Ideal land-use management trends in the project’s context from an ecological perspective. Aloe ferox managed landscapes Northern Cape mixed systems Rooibos gene-pool conserved in the wild across varied landscapes African Ginger wild gene-pool Wild-harvested Honeybush Pelargonium spp. Cultivated Rooibos Cultivated African Ginger.

(b) Applying ABS strategies and measures. Specific ABS strategies to be applied to both project ‘pilots’ and ‘systemic measures’:; Project Outputs* [renumbered]. 1.2; 1.2; 2.1; 2.2; 2.3; 2.4; 3.1; 3.2. Assisting in designing harvesting, collection, and reproduction methods for genetic resources; x; X; x. Designing monetary and non-monetary benefit-sharing options, including benefit-sharing trust fund design; X; x; X; x; x. Implementing in-situ and ex-situ biodiversity conservation strategies; X; x; x; X; x; x. Providing support on Free and Prior Informed Consent Procedures; X; x; x; x. Supporting the design of checkpoints at all stages of the value-chain that include research, development, innovation and pre-commercialization; X; x; x; x. Assisting with the value chain of products; x; X; x; x. Facilitating negotiation processes between private companies and indigenous peoples and local communities.; X; x; X; x.

* Quick Reference to Project’s Outputs. --PILOTS-- 1.1 African Ginger product 1.2 N Cape R&D hub; 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush 2.4 Rooibos ABS deal; --SYSTEMIC MEASURES-- 3.1 Nat Recordal System 3.2 Certification System; Note: Project Outputs are presented further down under Section IV – Results and Partnerships.

In addition, the key working hypothesis that underpins the project strategy, which summarizes the multiple benefits that the project is bound to generate, can be thus formulated:

‘Bioprospecting can create viable income opportunities for local, rural communities to the extent that indigenous plant products have a market value and that this can be achieved through successfully harvesting, cultivating, processing and trading the species, its genetic resources and derivates thereof, without such activities representing a threat to biodiversity.’

Moreover, the above working hypothesis includes the assumption that these income opportunities can be achieved while at the same time also generating Global Environmental Benefits (GEB). These include:

The conservation of biodiversity and the sustainable use of its components, including:

species management measures (Siphonochilus aethiopicus African ginger in particular), given the level of threat)

of habitats that harbour key bioprospecting resources, such as Pelargonium sidoides and Aloe ferox through landscape-level management;

of gene-pools of a variety of species used in bioprospecting value chains among them Devil’s Claw (Harpagophytum procumbens); Kanna (or Kougoed, Sceletium tortuosum) and Cancer Bush (Sutherlandia frutescens) – but also of Honeybush (Cyclopia spp.)

Fair and equitable sharing of the benefits arising from the utilization of genetic resources, including by appropriate access to genetic resources, among them Rooibos (Aspalathus linearis) and the critically endangered African ginger (Siphonochilus aethiopicus).

Hence, addressing the core problem (which had been discussed in the section under ‘The Core Problem’ further up) is premised on two objectives: (i) moving towards commercial maturity of every species value chain, and (ii) increasing the throughput of every species value chain. A test of sustainability and ABS-compliance would then apply.

Refer to the UNDP PRODOC Section III. Strategy, The Project’s Theory of Change (ToC) a more complete discussion on the topics presented further up.

Strategy

The project Objective will be achieved through implementation of components, which address three key barriers for a sustainable and ABS-compliant development of bioprospecting value chains in South Africa, as follows:

Component 1 Research and development (R&D) of products in line with the definition of utilization of genetic resources of the Nagoya Protocol which has a strong focus on bioprospecting, in the R&D processes and overcoming context-specific barriers. One important output under this first component will focus on the Northern Cape Province, where an innovation and business support hub will be established. It will also accelerate the registration – and transition to cultivation -- of the critically endangered Siphonochilus aethiopicus (African Ginger) as a medicinal product for asthma and allergies, while also considering what would be needed for conserving the diversity of the plant’s gene pool in the wild. Under this Outcome an ABS monetary agreement will be negotiated for this medicinal product (African Ginger).

Component 2 Cooperation models support the conservation of and commercial trade in indigenous bioproducts which focuses on value-chain development. Both biotrade and landscape-level management feature prominently among the key activities under this outcome, where the goal is to ensure ABS compliance and sustainable management of species and landscapes. The species on focus will include Pelargonium sidoides, Aloe ferox, Honeybush (including at least three species of Cyclopia spp. used in the industry) and Rooibos (Aspalathus linearis). The government will specifically support extension services for the successful transition to cultivation for African ginger. This Outcome will also facilitate the negotiation of a second ABS monetary agreement for a product derived from Rooibos.

Component 3 on Bioprospecting and value addition knowledge transfer is enhanced for an equitable benefit sharing is designed to build the capacity of national stakeholders for understanding ABS issues, complying with national and international legislation and for better handling the complex relationships therein implied, including commercial relationships.

The above are the project’s three technical components. In addition to these, a fourth supporting component is concerned with the lessons learned from the project and how they will be made available nationally and, where applicable, internationally.

Component 4 Knowledge Management and M&E will facilitate the process of institutional learning through the active participation of all stakeholder groups in project implementation, the regular monitoring of project activities, as well as project review and evaluation within the applicable appropriate M&E framework for UNDP GEF projects.

Expected Results

The proposed project is carefully designed to achieve following Long-Term Impact -- with reference to the Global Environmental Benefits (GEB) that the project is expected to generate.

Project impact will be achieved via decreasing of levels of threats to biodiversity from overharvesting/habitat loss or degradation, and through the more systematic application of ABS legislation that ensures the protection of traditional knowledge and the equitable sharing of benefits derived from the disclosure of this knowledge and from a balanced and sustainable use of genetic resources.

Threat reduction and ABS compliance results (which summarizes the above) will be consolidated through the achievement of following impacts (5 years):

Bioprospecting R&D that focuses on indigenous plants will make a more significant contribution to the national bioprospecting economy owing to at least 1 (one) new patent being registered and at least 4 (four) new market niches being explored through sustainable and ABS-compliant value chains in the Northern Cape’s bioprospecting economy;

The ways of working, management conditions and techniques will change within 5 (five) strategic value chains, as they become examples of how conservation and ABS-compliance can be simultaneously achieved through cooperation among bioeconomy players; and

National capacity for the protection of traditional knowledge within the bioprospecting segment, as well as the general mainstreaming of both conservation and ABS compliance within them, will be gradually improved (as independently assessed).

The project has been organized into four outcomes, where the first three are considered technical outcomes, and where each of the Outcomes represented falls under a Project Component:

Outcome 1. Bioprospecting R&D that focuses on indigenous plants contributes to the national biodiversity economy.

Outcome 2. The ways of working, management conditions and techniques change within 5 (five) strategic value chains, and demonstrate how conservation and ABS-compliance can be simultaneously achieved through cooperation among bioprospecting economy players.

Outcome 3. National capacity for the protection of traditional knowledge within the bioprospecting segment, as well as the general mainstreaming of both conservation and ABS compliance within them, is improved.

Outcome 4. Lessons learned and the application of a participatory and gender sensitive M&E framework effectively contribute to institutional, community and corporate learning on ABS.

To ensure achievement of the above Outcomes, the project will deliver the following key Outputs (project products and services, and noting that rural extension services for agribusiness development are government sponsored):

| Component 1. Outputs (Bioprospecting R&D) |  |
| --- | --- |
| Output 1.1) R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. | The strategic focus of the proposed project is to add value to the S. aethiopicus value chain, through technology development (clinical studies) and commercial cultivation, to demonstrate the implementation of the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from their Utilisation of 2010 in South Africa. The key partners are: Council for Scientific and Industrial Research (CSIR) and Agricultural Research Council (ARC) with support from DEA. Core Activities: GEF funding will be directed at supporting the implementation of the following: 1 Amendment of the existing CSIR-Traditional Healers Committee Benefit Sharing Agreement to include clauses in alignment with the South African Biodiversity Act 2 Conduct clinical studies (clinical trials, adsorption/metabolism studies and observation studies) 3 Registration as a complementary medicine 4 Market and value chain analysis for commercial development 5 Identification of suitable sites for cultivation 6 Development (training, infrastructure, equipment, technical support, HR costs, marketing) of community-based agri-processing business/es to cultivate and harvest fresh rhizomes. |
| Output 1.2) Bioprospecting R&D in the Northern Cape is supported, boosting the local bioeconomy and establishing a strategically located ‘Bioproducts Development Hub’. | The proposed Northern Cape Bioprospecting RDI Hub (Research, Development and Innovation Hub for bioproducts) is envisaged to address the following challenges that the community projects face: - Provide a centrally-located (Upington) and accessible centre of excellence that would support community projects in production of priority species and related bio-products, - Develop a 3-year research, development and innovation plan for the Hub to implement, - Provide a repository for genetic material for priority species in the Northern Cape, - Propagate priority species and related seedlings for sale/supply for community project cultivation, - Investigate appropriate cultivation practices that is in synergy with current wild-harvesting practices, and that conserve genetic resources and improve production – with the support of appropriate resource assessment initiatives, - Provide know-how to communities in the form of cultivation training, harvesting plans, traceability systems, quality control, phyto-sanitary systems and other extension services where necessary, - Provide agro-processing support services, especially with respect to product development and quality control, - Supply material for clinical trials where required, - Establish a commercial and marketing support service, that is aligned to the R&D mandate (e.g. establishment of a certification system). The Department of Rural Development and Land Reform has been implementing an Agri-Parks program across the Northern Cape. The current facility in Upington, which is proposed to house the Hub, has been used to date to replicate such an initiative. This is why the current hub has a predominantly production-focussed mandate. It was initially envisaged that this mandate would expand into a stronger commercial and marketing mandate, ideally forming the basis for a bio-prospecting cooperative. The advent of the GEF project has accelerated this process, but more importantly, it helped gear the development in another direction – namely of supporting the Hub not only to replicate the Agri-Parks initiative, but mostly to have a much stronger angle on bioprospecting and R&D. Hence, the strategy for this output can be thus summarized: Departing from a baseline where the current hub simply lacks the mandate, the equipment and the human resources to function as a hub that can produce results in the field of bioprospecting, the GEF investment is made in a government-owned facility, with a view of changing this situation. With the project, a different type of entity will emerge, one that can be tagged as a ‘Research, Development and Innovation Hub in bioproducts’. As a token of government commitment, the ARC has availed more than $1.4 million in co-financing to the project. Part of DEA’s co-financing, which is in exccess of $30 million, will also be dedicated to enhancing the Hub in its functions. It can be said that the project will help coalesce both GEF and government investments, enhancing the results expected. GEF project will help realize in the Northern Cape regarding R&D. With GEF investment, the facility will become much more focused on R&D linked to plants’ genetic resources. It will prime innovation and service provision to a surrounding community of both users and providers of genetic resources. The key partners are: Department of Environmental Affairs (DEA), Department of Agriculture (Northern Cape) |

| Component 2. Outputs (Value Chain Development) |  |
| --- | --- |
| Output 2.1) The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. | The extractive use of the Pelargonium sidoides species required the development of a Biodiversity Management Plan (BMP). The aim of the BMP is to ensure the long-term survival of the species in the wild, and make sure that the livelihoods of stakeholders are respected. Recommendations have been made to ensure control of wild harvesting towards minimising impacts and making provision for restoration and avoiding long-term depredation of the associated landscapes. It is proposed that sustainable management practices will be developed and endorsed through the Pelargonium Working Group (PWG). The six objectives of the BMP-S are: - Wild collection of P. sidoides is carried out in a manner that maintains survival of the species in the wild; - Wild collection of P. sidoides does not affect the environment, other wild species or neighbouring eco-systems; - Collection and management activities are carried out under legitimate tenure arrangements and comply with relevant laws, regulations and agreements; - Customary rights of local and indigenous communities to use and manage collection areas are recognised and respected; - Trade is conducted in an equitable manner resulting in the fair allocation of benefits to all resource stakeholders in accordance with Chapter 6 of NEMBA, which deals with Bio-prospecting, Access and Benefit Sharing and the associated Bio-prospecting, Access and Benefit Sharing Regulations, and, - Wild collection of P. sidoides is based upon adaptive, practical, participatory and transparent management practices. The focus of the GEF-funded support to BMP will be to aid the DEA, DEDEAT and DESTEA (or the Pelargonium Working Group) in implementing the Pelargonium BMP-S. More specifically the funds will be used for: - Capacity building of National and Provincial agencies; - Updating the BMP; - Conducting of various scientific reports for supporting ecological and ABS outcomes; - Training of local collectors; and - Administration of the Pelargonium Working Group (PWG). The key partners are: The Pelargonium Working Group (PWG), Eastern Cape Department of Economic Development, Environmental Affairs and Tourism (DEDEAT) and Free State Department of Economic, Small Business Development, Tourism and Environmental Affairs (DESTEA) |
| Output 2.2) Development of an Aloe ferox harvesting, processing and trading hub in the Eastern Cape for promoting sustainable and equitable benefit sharing across the value chain is supported. | Aloe ferox is the most commercially utilized indigenous plant in South Africa, with bitters and aloe gels extracted from the leaves of the plants and utilized in cosmetics, hygiene products, manufactured food products, and as complementary medicines. The A. ferox industry provides significant socio-economic benefits to South Africa, including benefits to poor individuals who derive an income from harvesting of the plants (e.g. in Tyefu community). The industry also supports a range of businesses in the country, producing A. ferox products for the local and international market. The bulk of commercially harvested A. ferox is however for the export market, with very little secondary or tertiary processing in South Africa. The GEF-funding will focus on supporting the Tyefu community – through the Tyefu Traditional Council and the Tyefu Traditional Trust (Reg. IT 163/2013) – to establish, develop and manage A. ferox crop plantations on communal land in Tyefu. These A. ferox plantations will, in turn: (i) considerably ease the strenuous efforts of the – mostly female - harvesters and tappers; (ii) improve the income of these harvesters and tappers, with little capital and maintenance cost to the communal land owners; (iii) reduce the harvesting pressure on the existing wild aloe ferox populations; (iv) strengthen the quality controls of the aloe ferox gel processing methods; and (v) open up further opportunities for the Tyefu community to commercially develop, market and sell value-adding aloe ferox products. Furthermore, the project will act as a hub within the Eastern Cape for the processing and the transfer of agricultural know how to surrounding communities. The key partners are: Department of Environmental Affairs (DEA), Tyefu Traditional Leader (Chief Msutu), Tyefu Traditional Council (TTC), Tyefu Traditional Trust (TTT) Other partners may include SANBI and DAFF (EC). |
| Output 2.3) Community-based enterprises in honeybush farming are supported, ensuring conservation and equitable benefit sharing outcomes across the Cyclopia spp. landscape in the Cape Region. | There are six species of the genus Cyclopia spp. that have commercial value. Three main species currently make up the commercial honeybush industry. Of all honeybush processed in 2011, 70% is harvested in the wild while 30% is cultivated. The focus of the GEF funding will be to support emerging honeybush farmers in the Eastern and Western Cape through a grant system, which would be administered through a suitable grant-making mechanism to be selected during the procedural Local Project Appraisal Meeting, to be held once the PRODOC approved by UNDP and DEA. The grant programme will focus primarily on previously disadvantaged farmers and more specifically on female farmers. The purpose of the grants would be to ensure environmental sustainability by supporting farming and harvesting of honeybush. South Africa’s Bioprospecting, Access and Benefit Sharing regulations (BABS) regulates relationships between providers and users of genetic resources and caters for the adherence to the ABS permit’s conditions. It ensures that these relationships are Nagoya Protocol compliant, whether it they are restricted to national stakeholders or international relations between Parties to the Protocol. For the Output’s beneficiaries, across the honeybush landscapes, a key condition for applying and receiving grants will be compliance with BABS regulations. The key partners are: The Agricultural Research Council (ARC), Honeybush Community of Practice (HCoP), Department of Agriculture Forestry and Fisheries (DAFF), Department of Rural Development and Land Reform (DRDLR), Municipalities. |
| Output 2.4) The ABS implementation in Rooibos farming is strengthened, ensuring, fairness, equity and sustainability in relevant relationships among TK holders and industry. | Aspalanthus linearis is both farmed and harvested from the wild with less than 1% being wild harvested (Waarts and Kuit, 2008) and the majority being cultivated (Street and Prinsloo, 2013). In 2010, there were 350 to 550 rooibos farmers in South Africa, cultivating approximately 36 000 hectares of rooibos (Street and Prinsloo, 2013). The GEF funds will be used for strengthening ABS agreements and mechanisms in the rooibos industry. More specifically, the funds will be used to develop and set-up a TK benefit sharing monetary mechanism as a model the for industry. The key partners are: Other partners (Support), South African Rooibos Council (SARC), San & Khoi Traditional Council. Core Activities: GEF funding will be directed at supporting the implementation of the following: Investigate and develop a suitable TK benefit sharing mechanism that effectively captures the resource rent resulting from the TK rights – such a benefit sharing mechanism needs to be effective, transparent, minimise commercial risks and maximise TK benefits, and would require financial and economic modelling and forecasting; Investigate and develop non-monetary TK benefit sharing mechanisms which may support rights-holding communities through contributions-in-kind and related mechanisms by the private sector Develop and propose a suitable and simple governance and institutionalisation framework for implementing and monitoring the TK benefit sharing mechanism Record the current negotiation processes of SARC as a case study with a view to the creation of a “blueprint” for other products and TK agreements Disseminating the case study outcomes as example to ABS stakeholders in SA and beyond. |

| Component 3. Outputs (ABS Capacity Building of key Stakeholders) |  |
| --- | --- |
| Output 3.1) The National Recordal System (NRS) for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry. | The NRS, an initiative of the Department of Science and Technology (DST), supports communities and indigenous knowledge holders to document oral indigenous knowledge of traditional medicine and indigenous food that are closely associated with biodiversity. Its main objective is to protect, promote, manage and develop indigenous knowledge in alignment with the Indigenous Knowledge Systems Bill of 2016 (currently under Parliamentary process) which aims to protect the knowledge of indigenous communities from unauthorised use and misappropriation, promote public awareness and understanding of indigenous knowledge for the wider application thereof, and to create registers to catalogue, document and record indigenous knowledge held by communities. The initiative also brings together databases and processes for research, development and innovation across many government priorities, whilst supporting the NEMBA Regulations, and Bioprospecting Access and Benefit Sharing (ABS) process of the Department of Environmental Affairs. Due to the close association of indigenous knowledge with biodiversity, scientific authentication of the plants used by rural and local communities must be determined to ascertain legal certainty over the knowledge that is documented in the system. This can only be achieved by collecting samples of plant species, which will enable the South African Biodiversity Institute (SANBI) to correctly identify the plant species according to scientific taxonomies. The NRS will provide a knowledge platform to be mined by the National System of Innovation for research and development across various fields. An integrated system and a one-stop-shop will bring together all indigenous knowledge assets in the country towards future investment and development of indigenous knowledge systems. The National Recordal System (NRS) initiative is implemented through provincial IKS Documentation Centres (IKSDCs) which facilitate the documentation of indigenous knowledge at grassroots levels. Implementation of the documentation operations functions through IKSDCs, which serves as provincial hubs facilitating the documentation of IK. Ten branches of the NRS have been established in the following provinces: KwaZulu-Natal (2 satellite offices), Limpopo, Free State, Eastern Cape, Western Cape, Northern Cape, North West, Mpumalanga and Gauteng. Each IKSDC has an appointed Project manager and IKSDC Coordinator who implement the project at provincial and local levels. The initiative facilitates a community and its indigenous knowledge holders to document oral indigenous knowledge on traditional medicine and indigenous food that are closely associated with biodiversity. IK recorders appointed on the project are typically persons from the community who have an understanding of the community protocols and have a basic understanding of using a computer. All IK recorders are trained in the documentation methodologies including how to utilise the equipment to upload documented information. Specific activities envisaged by DST include: - Develop Community Bio-cultural protocols through workshops with participating communities - Appoint IK recorders to document IK on top 25 species in 10 communities; - Procure: (1) recording equipment and devices to document IK; and (2) collecting equipment to collect plant species for positive scientific name variety identification; - Conduct training sessions for IK recorders to: (1) understand the legal framework of the Access and Benefit sharing and data collection process; and (2) understand and implement plant species collection; - Develop NIKMAS (ICT system of NRS) to align the one-stop-shop with DEA. The key partners are: Department of science and Technology (DST), Department of Environmental Affairs (DEA) |
| Output 3.2) A biotrade certification system for South Africa is developed with a view to safeguarding biodiversity conservation within bioprospecting value chains. | A suitable bioprospecting certification system would provide a transparent mechanism for promoting biodiversity conservation, fair trade and product differentiation, across the value chain. These are all critical aspects required to unlocking the full potential of the bioprospecting value chain. DEA has envisaged the development of such a system since 2013 and this vision has been reaffirmed in the NBES, however, no action has been taken to date. SANBI has the necessary scientific knowledge to provide sustainability indicators upon which to base a suitable certification system. SANBI is already playing a key role in formulating Biodiversity Management Plans (BMPs) in several of the other project outputs – it is envisaged that a strong linkage exists between these BMPs and a Certification Standard, with the Standard likely adopting recommendations and guidelines from the BMPs. However, work needs to be done to formalise these sustainability indicators and associated best practise guidelines into a suitable Standard. Another major gap that exists relates to the institutional arrangements required for implementation. Various experienced and reputable organisations exist, through whom a certification system could be implemented (implementation agents). However, this requires a formalised consultation and development process. The proposed support initiative would: - Develop a documented Standard, comprising indicators and implementation guidelines - Conclude implementation agreements with at least one implementation agent - Complete a certification test case. The specific activities planned by SANBI include: - Undertake research and assessment, including field research on the status of key species linked to biotrade/ bioprospecting, especially those in this project for which data is limited (e.g. wild ginger); Non-detriment findings for target species will be undertaken as this tool identifies key risks to sustainable use (and potentially ecosystem resilience) and can assist in determining which risk factors need to be addressed through certification schemes; - Analysis of certification schemes and their benefits to determine the past effectiveness of key biotrade certification schemes in supporting biodiversity conservation, it is necessary to ascertain where they have been applied; - Development of an ABS-aligned model that optimises biodiversity conservation benefits for select South African biotrade species; - Engagement with key biotrade certification schemes and the National Focal Point on ABS; - Establish a monitoring and evaluation programme for ABS and conservation outcomes. Additional Capacity Building Activities to be pursued under Output 3.2, added in March 2018. Considering comments received from the GEF Secretary, it has been decided to include the South African National Biodiversity Institute (SANBI) as a responsible party (RP) a consolidated Outputs may be further developed during the Project Preparation Grant (PPG) phase. The additions include: Added Activity # 5: Provision of ABS Training and Capacity Building Services for Selected Communities Added budget $350 000 The key partners are: Department of Environmental Affairs (DEA), SANBI (South Africa Biodiversity Institute) |

| Component 4. Outputs (Knowledge Management & M&E) |  |
| --- | --- |
| Output 4.0) National and international stakeholders will be supported to participate in the project M&E and will systematize lessons learned from its implementation. | This component is a standard component and entails a specific knowledge management activity related to learning about best practices ABS and conservation related issues. M&E activities will provide sufficient information for adaptive management and learning via active participation of key stakeholders in the project implementation. Additionally output 4.0 formalises the implementation of the M&E schedule and framework set out in later sections in this project document fall under component 4. The dissemination of project lessons along with the application of appropriate, participatory and gender sensitive M&E framework will contribute to institutional, community and corporate learning on ABS through the active participation of all stakeholder groups in project implementation. A thorough description of M&E Activities is included in PRODOC Section VII (Monitoring and Evaluation Plan). A specific M&E budget is included in that section and it corresponds, for the ease of budgeting, to the budget allocated to Component 4’s in the project’s budget. As for Knowledge Management (KM), which both includes and is related to the project’s Theory of Change, its specific plans pertaining to Gender Mainstreaming and Stakeholder Engagement, as well as to aspects of Capacity Building and Lessons Learning, it is notable that activities are spread throughout the project document. |

Refer to UNDP PRODOC Section. IV Results and Partnerships for a description of the proposed alternative scenario, and to ANNEX X-3. Detailed description of project design: outputs and activities.

Project ABS Pilots and Systemic Measures

For each pilot, the project will focus on the interactions between key players in supply activities and how this affects species and habitats, taking into consideration the use of any associated traditional knowledge in it. The project will also focus on the subsequent bioprocessing and product development, removing barriers through R&D, stakeholder collaboration and capacity development through the pilots, complementing systemic measures.

Overall, the project will foster innovation, equitable sharing of benefits from genetic resources, while contributing to species and habitat conservation as key contributions to global biodiversity benefits.

While the geographic focus of the project is the broad landscapes where the species are distributed within the South Africa, (see representation in dark green the map below) the direct on-the-ground project interventions will be in an area covering over 50,000 hectares (consisting of Honeybush, Aloe Ferox and Pelargonium landscapes).

PRODOC Figure 14. Distribution of key species across the country and location of important protected areas

Notes:

[1] Species: Aloe ferox; Aspalathus linearis; Cyclopia Spp (C. sessiflora, C. intermedia, C. genistoides); Harpagophytum procumbens; Pelargonium sidoides; Siphonochilus aethiopicus.

[2] Distribution/ extent: All focal species have a combined natural distribution that covers approximately 651 031 km2. This area is spread throughout South Africa in all provinces.

[3] Refer to PRODOC Annexure for detailed maps per species and for the complete list of Protected Areas within the landscapes (relevant for the Tracking Tool)

Source: PPG Report 2017: Plant Distribution Sheet by Prime Africa

#### 4) Incremental cost reasoning and expected contributions from the baseline, the GEF TF and co-financing

#### 5) Global environmental benefits (GEFTF)

The expected contributions from the baseline and co-financing are captured in PRODOC Table 5, reproduced further up.

The project’s Incremental Cost Reasoning is summarized below:

PRODOC Table 6. The Project’s Incremental Reasoning

| Baseline (B) | The Alternative (A) | The Increment (A-B) |
| --- | --- | --- |
| At the baseline: - South Africa is a megadiverse emerging economy and it has home-grown R&D on genetic resources, well-developed ABS legal & policy frameworks and demand from biotrade markets (both domestic and export) – but yet few successful stories of equitable benefit-sharing that adequately recognize TK; - Bioprospecting value chains are promising – including for local communities and marginalized groups – but overharvesting of indigenous flora can threaten both business sustainability and conservation goals; National capacity for sustainable bioprospecting and biotrade value-chain development & ABS is still limited – the regulatory and practical governance of the bioprospecting segment still has a considerable learning curve to face. | The project will: - Strengthen sustainable value chain development for biosprospecting & biotrade, with focus on indigenous flora that have been associated with traditional medicinal use; - Develop collaborative partnerships involving state-research institutions-community-private sector in both R&D and in the commercialization of these flora; - Expand the national capacity for ABS, advancing the implementation of the Bioeconomy Strategy; - Catalyze the negotiation of agreements towards successful & equitable benefit-sharing, recognizing the contribution of TK; and - Generate socio-economic benefits to local communities involved in biotrade as a co-benefit, including through cultivation and improved techniques for value-addition and wild harvesting. Overall, through both pilots and systemic measures, the project will ensure that, whenever an indigenous plant species enters a bioprospecting value chain, the associated TK is respected with derived benefits more equitably shared, and that the commercial/profit-seeking aspect of the value-chains do not end up representing a threat to biodiversity and ecosystems. | GEBs will thus be generated: - Threats to selected indigenous flora species targeted by bioprospecting and biotrade in their natural habitats are mitigated through the development of biodiversity management plans - Bioprospecting and biotrade activities are: (i) more compliant with Nagoya Protocol; and (ii) based on a more sustainable management of biological and genetic resources at the landscape level More specifically, the GEBs that the project will generate will include: (i) The conservation of biodiversity and the sustainable use of its components, including: - of habitats that harbour key bioprospecting resources, such as Pelargonium spp. and Aloe ferox, applying landscape-level management measures; - of gene-pools of a variety of species used in bioprospecting value chains among them Devil’s Claw (Harpagophytum procumbens); Kanna (or Kougoed, Sceletium tortuosum) and Cancer Bush (Sutherlandia frutescens) – but also of Honeybush (Cyclopia spp.) (ii) The fair and equitable sharing of the benefits arising from the utilization of genetic resources, including by appropriate access to genetic resources, among them Rooibos (Aspalathus linearis). |
| Current baseline expenditure and investments at approx.: $559 M, broken down as in PRODOC Table 5, reproduced further up. | The Alternative: Baseline + GEF + Co-financing net of baseline: $599M | The incremental costs: GEF $6.2M |

Refer otherwise to the UNDP PRODOC X. ‘TOTAL BUDGET AND WORK PLAN’ which provides the details on the use of GEF TF resources.

#### 6) Innovativeness, sustainability and potential for scaling up.

The relevant UNDP PRODOC sub-section is reproduced below:

The sustainability of the specific project activities will be ensured by the continued availability of training materials and case-studies. These materials will be open access, available in electronic versions, and disseminated widely. They will provide comprehensive guidance for stakeholders, and will be used in future projects, as well as other countries of the region and beyond.

The emphasis on developing a comprehensive capacity-building strategy for the bioprospecting sector will ensure the continued engagement of government agencies, CSOs, CBOs and the private sector, complementing thereby the approach. This will include plans for cost-recovery for financial sustainability.

Lessons learnt on the implementation of projects incorporated in this proposal will be imparted to a broader stakeholder base in the planned Biennial Biodiversity Economy Indaba.

Innovation is otherwise weaved into the project’s approach and strategy, but made explicit in the following [UNDP PRODOC] Sections:

Long-Term Solution

The Project’s Theory of Change (ToC)

Project Areas and Pilots

In Annex X-3, Subsection: Component 4 (Knowledge Management & M&E), Outcome 4 (Lessons learned and the application of a participatory and gender sensitive M&E framework effectively contribute to institutional, community and corporate learning on ABS), and Output 4.0 (National and international stakeholders are supported to participate in the project M&E and will systemize lessons learned from its implementation).

Project pilots are conceived to be scalable examples of both ABS compliance and ecological sustainability, as explained in the relevant sections listed above. The scalability of pilots will be reinforced by systemic measures, such as those proposed under Component 3 of the project [ABS Capacity Building of key Stakeholders, described in UNDP PRODOC Annex X-3], as well as by lesson’s learning and Stakeholder Engagement approach, outlined in the UNDP PRODOC ANNEX X-5. Knowledge Management & Stakeholder Involvement Plan.

New sustainable practices and the strategy for stakeholders to adopt them are part and parcel of in Outputs 3.1 “The National Recordal System for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry” and Output 3.2 “A biotrade certification system for South Africa is developed in view of safeguarding biodiversity conservation within bioprospecting value chains”.

Sustainability and Innovation are embodied in the project’s work within the pilots, including both Component 1 and Component 2. Two bioprospecting hubs will be established, one in Northern Cape (through Output 1.2) and one in Eastern Cape (through Output 2.2) – the latter with focus on cultivation, habitat management and processing of Aloe ferox, including enhanced value addition.

Scaling up & Replication

Outcome 3 is stated as: “National capacity for the protection of traditional knowledge within the bioprospecting segment, as well as the general mainstreaming of both conservation and ABS compliance within them, is improved.”. Knowledge transfer schemes can be replicated in other projects.

Particularly Output 3.2 (certification scheme) has a strong potential for scaling up. The new species are entering into a given bioprospecting value chain and become a certified basis for value chain development in a view of biodiversity conservation. This mechanism is also envisaged to promote a fair trade and product differentiation across the value chain. It works with the participation of local certification entities in the country within specific standards. This mechanism can be successfully transferred to other projects.

Also, National Recordal System, described in Output 3.1, can be implemented on the ground building on other ABS projects.

The focus on ecosystem management practices envisaged under Output 2.1 Pelargonium and Output 2.3 Honeybush will cater for scale and sustainability.

Overall, sustainable practices’ adoption, uptake and spread are embedded in the key expected results from the project, as follows:

- bioprospecting R&D that focuses on indigenous plants will make a more significant contribution to the national bioeconomy through at least 1 (one) new patent being registered and at least 4 (four) new market niches being explored through sustainable and ABS-compliant value chains in the Northern Cape’s bioeconomy;

- the ways of working, management conditions and techniques will change within 5 (five) strategic value chains, as they become examples of how conservation and ABS-compliance can be simultaneously achieved through cooperation among bioeconomic players; and

- national capacity for the protection of traditional knowledge within the bioprospecting segment, as well as the general mainstreaming of both conservation and ABS compliance within them, will be gradually improved.

### A.2. Child Project?

If this is a child project under a program, describe how the components contribute to the overall program impact.

-- Not Applicable --

### A.3.  Stakeholders

Elaborate on how the key stakeholders engagement, particularly with regard to civil society organizations and indigenous peoples, is incorporated in the preparation and implementation of the project.

Relationships between providers and users of genetic resources involve the manufacturing industry (within and outside the country), local communities (among them, traditional knowledge holders), small businesses (among them bioprocessors), the scientific and research community and government at different levels.

The following groups of stakeholders were identified during PPG phase of the project including their roles and involvement in the project:

PRODOC Table 8. Project’s key stakeholders and their prospective roles in the project

| Stakeholder | Description | Role in project |
| --- | --- | --- |
| Government |  |  |
| Department of Environmental Affairs (DEA) | The DEA is mandated to give effect to the right of citizens to an environment that is not harmful to their health or wellbeing and to have the environment protected for the benefit of present and future generations. To this end, the department provides leadership in environmental management, conservation and protection towards sustainability for the benefit of South Africans and the global community. With reference to biodiversity and conservation, DEA’s purpose is to ensure the regulation and management of all biodiversity, heritage and conservation maters in a manner that facilitates sustainable economic growth and development. With regards to ABS, a strategic objective is to improve socio-economic benefits and improve access and fair and equitable sharing of benefits. | DEA is the implementing partner for the overall project. The project will specifically support the implementation of the National Biodiversity Economy Strategy (NBES) by focusing on the current use of indigenous plants' genetic resources and their potential, either in pharmaceuticals, personal care products, cosmetics and enzymes or similar non-food uses. It will address both conservation and Access Benefit Sharing (ABS) issues linked to their development. |
| Department of Science and Technology | The DST seeks to boost socio-economic development in South Africa through research and innovation. To achieve its goals, the Department provides leadership, an enabling environment and resources for science, technology and innovation. Through its Programmes (Administration; Technology Innovation; International Cooperation and Resources; Research Development and Support; and Socio-economic Innovation Partnerships) and several entities that work alongside it, the Department is accomplishing ground-breaking science and enhancing the well-being of all South Africans. | DST’s role in the project will be to implement Output 3.1: The National Recordal System for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry. |
| Agricultural Research Council | The ARC’s core mandate is to act as the principal agricultural research institution in South Africa to conduct research, drive research and development, drive technology development and the transfer of information in order to: - Promote agriculture and related industries; - Contribute to a better quality of life; - Facilitate/ensure natural resource conservation; and - Alleviate poverty. Specifically, Medicinal Plant Research focuses on the propagation, cultivation and processing of South African medicinal plants, especially those species that are highly utilised. | The ARC’s role is to implement Output 1.2: Bioprospecting R&D in the Northern Cape is supported, boosting the local Bioprospecting economy and establishing a strategically located ‘Bioproducts Development Hub’. |
| Council for Scientific and Industrial Research | The objectives of the CSIR are, through directed and particularly multi-disciplinary research and technological innovation, to foster, in the national interest and in fields which in its opinion should receive preference, industrial and scientific development, either by itself or in co-operation with principals from the private or public sectors and thereby to contribute to the improvement of the quality of life of the people of the Republic. With reference to bioprospecting and ABS, Biosciences Unit has strong competencies in process and product development in agroprocessing, bioprocessing and biomanufacturing. These capabilities are positioned to support the creation of novel industries in biotechnology-based services and products, as well as translating these into new companies or supporting the competitiveness of the existing industries. | The CSIR’s role is to function as the responsible party for Output 1.1: R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. CSIR will not be doing the clinical trials in view of developing a complementary medicine product. Rather, it will sub-contract the activity to a specialized service provider. |
| South African National Biodiversity Institute (SANBI) | The mandate of SANBI is broad and is derived from the National Environmental Management: Biodiversity Act (No10 of 2004), but also from other legislation and processes over the last decade. The mandate is to explore, reveal, celebrate and champion biodiversity for the benefit and enjoyment of all South Africans. With reference to bioprospecting and ABS, SANBI’s role is to: - Must monitor and report regularly to the Minister on the conservation status of all listed, threatened or protected species and listed ecosystems; - Must act as an advisory and consultative body on matters relating to biodiversity; - Must coordinate and promote the taxonomy of South Africa’s biodiversity; - Must collect, generate, process coordinate and disseminate information about biodiversity and the sustainable use of indigenous biological resources and establish and maintain databases in this regard. - Must undertake and promote research on indigenous biodiversity and the sustainable use of indigenous biological resources. | The role of SANBI is to provide technical support to the project PMU as well as to the individual project outputs, particularly Output 3.2 A biotrade certification system for South Africa is developed in view of safeguarding biodiversity conservation within bioprospecting value chains. |
| NGOs/CBOs/Other |  |  |
| TRAFFIC | TRAFFIC is an NGO that specialises in: - Investigating and analysing wildlife trends, patterns, impacts and drivers to provide the leading knowledge base on trade in wild animals and plants; - Informing, supporting and encouraging action by governments, individually and through inter-governmental cooperation to adopt, implement, and enforce effective policies and laws; - Providing information, encouragement and advice to the private sector on effective approaches to ensure that sourcing of wildlife uses sustainability standards and best practices; and - Developing insight into consumer attitudes and purchasing motivation and guiding the design of effective communication interventions aimed to dissuade purchasing of illicit wildlife goods. | The role of TRAFFIC would be to potentially provide support to the PMU specifically in Output 2.1: The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. |
| Pelargonium Working Group (PWG) | The PWG was established in 2007 and is represented by government, conservation, bioprospecting industries, public entities and research institutions. The responsibilities of the PWG include, but are not limited to: - Monitoring the implementation of the BMP for Pelargonium sidoides; - Ensuring that management of P. sidoides wild collection is supported by adequate and practical resource inventory, assessment, and monitoring of collection impacts. - Ensure that P. sidoides collection activities are carried out in a transparent manner with respect to management planning and implementation, recording and sharing information, and involving stakeholders. - Assist with establishing procedures for collecting, managing, and sharing information required for effective collection and management. - Contribute to the development of skills training for resource managers and collectors that will equip them to implement the provisions of the management plan. - Production of an annual report specifying progress in the implementation of the Biodiversity Management Plan as required by the Norms and Standards for BMP-S. - Drawing up proposals and fund raising for specific projects needed. - Implement the BMP for P. sidoides. | The role of the PWG would be to provide support to the PMU in implementing the activities proposed in Output 2.1: The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. |
| Tyefu Traditional Trust | The Tyefu Traditional Trust represents the Tyefu community. Tyefu is an area situated within the jurisdiction of the Ngqushwa Local Municipality of the Amathole District in the Eastern Cape Province. The Tyefu community consists of 10 villages that are under jurisdiction of and part of Chief Sizwe Msutu’s land. | The PMU and the Tyefu Traditional Trust will be directly responsible for coordinating the implementation of Output 2.2: Development of an Aloe ferox harvesting, processing and trading hub in the Eastern Cape for promoting sustainable and equitable benefit sharing across the value chain is supported. The Tyefu Traditional Trust will, as the legal entity representing the livelihood interests of the community, be the beneficiary of activities proposed in Output 2.2. |
| Honeybush Community of Practice (HBCoP) | The HBCoP was duly formed and launched by DEA on 4 November 2016. The role of the HBCoP is to: - Address issues of Governance - Legislation (Compliance and Permitting issues) - Sustainability & promotion of the Industry - Community upliftment and address TK issues - Knowledge Sharing - Funding - Local value addition & geographic Indicators - To add Accountability, Confidentiality - Incorporate the San and Khoisan | The role of the HBCoP in the project is to provide support to the PMU in the implementation of Output 2.3: Community-based enterprises in honeybush farming are supported, ensuring conservation and equitable benefit sharing outcomes across the Cyclopia spp. landscape in the Cape Region. |

Refer in addition to a detailed discussion of Stakeholder Engagement is provided in the UNDP PRODOC Section IV “Results and Partnership”, Subsection ‘Stakeholder Engagement’ (part of which is reproduced above). Additionally, UNDP PRODOC ANNEX X-4. ‘Stakeholders consulted during the PPG and UNDP PRODOC ANNEX X-5. ‘Knowledge Management & Stakeholder Involvement Plan’ provide further details.

### A.4. Gender Equality and Women's Empowerment.

Elaborate on how gender equality and women’s empowerment issues are mainstreamed into the project implementation and monitoring, taking into account the differences, needs, roles and priorities of women and men.

Gender Aspects

During the PPG phase, a gender specialist was engaged to conduct a gender analysis of the bioprospecting sector, following the UNDP Guide to Conducting a Participatory Gender Analysis and Developing a Gender Action Plan for projects supported by UNDP with GEF financing .

The research conducted revealed the following issues:

- in rural areas women and youth are very much engaged in food production, but have little or no access to the generated income, no governance rights over the land and limited access to infrastructure;

- the loss of biological resources and biodiversity particularly impacts women, as the most dependent and vulnerable from among all society members;

- the women present in bioprospecting sector are marginalised from decision making roles which are dominated by men. Women are over represented in the lower rungs of the value chains;

- South Africa faces a high youth unemployment challenge. The youth are marginalised in the bioprospecting sector because of their limited control of productive resources and marginalisation from the decision-making forums. The bioprospecting industry has potential to reduce youth unemployment by generating employment opportunities along the value chain;

- the government of South Africa, through DEA, acknowledged the role of women and youth in conservation and sustainable use of the natural resources, and prioritized gender mainstreaming, by developing a Strategy Toward Gender Mainstreaming in the Environment Sector and by other initiatives;

- there is a gap in consolidated data regarding gender issues in bioprospecting sector; and

- lack of attention to gender issues at a provincial level.

The project will respond to the above listed findings in a number of ways:

- mainstreaming gender in the initiatives where it does not exist;

- empowering local women by positioning them and promoting a greater involvement in decision making. The project will take measures to ensure adequate representation of women in the community-level management committees;

- building capacity through appropriate training conducted in a gender-sensitive manner. The training will ensure the improvement of sustainable cultivation and harvesting skills, as well as contribute to combating illiteracy among women and youth;

- all community-engagement and outreach activities will be designed and implemented considering gender dimensions, including household power relationships. Consultations with women are going to be conducted at all stages of Project’s implementation, through appropriate structures and in local languages, to ensure the participation of women;

- introducing licensing regimes, that will favour land controlled by local municipalities or the state, to empower women’s equity in its governance;

- targeting women as beneficiaries in specific interventions; and

- supporting the generation of gender disaggregated data in the bioprospecting sector.

The project falls within the Gender Targeted ranking (UNDP GEN 2 - Gender equality is not the main objective of the expected output, but the output promotes gender equality in a significant and consistent way): It will target a (50/50) of women, men or marginalized populations.  The project recognizes the role of culture and local customs in the way local communities govern access and control of natural resources. The bioprospecting sector value chains in South Africa exhibit distinct gender patterns, with women over-represented in labor-intensive and poorly remunerated activities (such as gathering and nursing of the species) and men dominating the trading and other superior value chain activities which are more profitable. Unemployment and lack of economic opportunities contribute to high rural-urban migration rate, unsustainable harvesting and commercialization of biodiversity species. The sustainability of initiatives to catalyse change in gender will extend beyond the project’s life cycle. Project interventions seeking to increase the participation and beneficiation of women from the biodiversity sector are included in the multi-year workplan and articulated in the gender mainstreaming action plan (see ANNEX X-7. Gender Mainstreaming in the PRODOC).

Furthermore, relevant gender representation on various levels of project governance will be pursued, i.e. through including rules for gender balance in conservancy governance, as well as adequate women representation on the project board. All project staff recruitment shall be specifically undertaken inviting and encouraging women applicants. The TORs for key project staff all incorporate gender mainstreaming related responsibilities.

The project will promote gender mainstreaming and capacity building within its project staff to improve socio-economic understanding of gender issues, and will appoint a designated focal point for gender issues to support development, implementation, monitoring and strategy on gender mainstreaming internally and externally. This will include facilitating gender equality in capacity development and women’s empowerment and participation in the project activities. The project will also work with UNDP experts in gender issues to utilize their expertise in developing and implementing GEF projects. These requirements will be monitored by the UNDP Gender Focal Point during project implementation.

Based on the findings of the gender analysis conducted during the PPG, the project will adopt the following Gender Action Plan to ensure that gender is comprehensively mainstreamed into the implementation of the project, through the project outputs.

| Outcome & Output | Considerations and planned actions |
| --- | --- |
| Outcome 1 – Research and development of products in line with the definition of utilisation of genetic resources of the Nagoya Protocol |  |
| Output 1.1 R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. | Output 1.1 will facilitate the validation and contribute to the preservation of indigenous knowledge of using plants for medicinal purposes, which is a domain of women in South Africa, through clinical testing. Women will also benefit from the community-level training, as well as from revision of the existing ABS agreements with the (CSIR) Scientific community to make it more ABS compliant and inclusive. |
| Output 1.2 Bioprospecting R&D in the Northern Cape is supported, boosting the local Bioprospecting economy and establishing a strategically located ‘Bioproducts Development Hub’. | Output 1.2 will increase women’s access to technology and participation in generating of the scientific information. Women will benefit from the knowledge generated by the scientific hub. They will also secure employment opportunities in the nursery, securing livelihoods from the seedlings cultivation at the hub. Therefore, the community will be able to secure income and increase access to the market through the linkages to demand for product by consumers and those involved in clinical trials. They will also benefit from knowledge disbursed by the extension officer. |
| Outcome 2 - Cooperation models support the conservation of, and commercial trade in, indigenous bioproducts |  |
| Output 2.1 The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. | Output 2.1 will contribute to generating benefits for women through capacity building to increase the participation of women in the Pelargonium value chain and representation in decision making structures. The output will help improving the visibility, participation and representation of women and their roles in the species’ cultivation and in the value chain by ensuring that women are represented in the selection of the staff for capacity building in the Eastern Cape. Women in the communities will benefit from the improved management of community based trusts and distribution of funds in line with the Nagoya Protocol. |
| Output 2.2 Development of an Aloe ferox harvesting, processing and trading hub in the Eastern Cape for the promotion of sustainable and equitable benefit sharing across the value chain. | Output 2.2 will generate employment for women as aloe harvesters, nursery worker’s, aloe processors, packers in the plantation and factory operations. This will allow women to save their time and gain professional skills and knowledge through training regarding sustainable aloe cultivation and health and safety practices. Women will benefit from increased income and diversified opportunities for income generation, as well as from the increased access to land as a result of the formal agreement between the project and the traditional authority. Women will also benefit from the contract agreements that will be concluded with manufacturers and consumers of the product. |
| Output 2.3 Community-based enterprises in honeybush farming are supported, ensuring conservation and equitable benefit sharing outcomes across the Cyclopia spp. landscape in the Cape Region | Output 2.3 will increase women’s land tenure security through the formalization of land control. The women will also benefit from capital input which will enable them to start their business. They will also benefit from increased output income and market access. They will gain skills through training interventions. They will benefit from support of a suitable grant-making mechanism to be selected during the procedural Local Project Appraisal Committee Meeting (LPAC), to be held once the PRODOC is CEO Endorsed by UNDP and DEA. |
| Output 2.4 The ABS implementation in Rooibos farming is strengthened ensuring, fairness, equity and sustainability in relevant relationships among TK holders and industry. | Output 2.4 activities will lead to benefitting women through the development of better governed ABS mechanisms. Women will be recognized as indigenous knowledge holders. Women will also benefit from the bursaries, training, outsourcing of business and business support opportunities that will arise from the project. Women will benefit from the increased number of opportunities to be represented and to participate in the governance and institutionalization framework for implementing and monitoring the TK benefit sharing mechanism, that will be developed. |
| Outcome 3 - Bioprospecting and value addition knowledge transfer is enhanced for an equitable benefit sharing |  |
| Output 3 .1 The National Recordal System for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry. | Output 3 .1 will enable women to benefit from their recognition as traditional knowledge holders. Their information will be recorded and recognized which will improve their capacity to benefit from ABS. Women will be employed to document and research on traditional knowledge holders. Women will benefit from increased access to information that will be generated by the output’s activities. |
| Output 3.2. A biotrade certification system for South Africa is developed in view of safeguarding biodiversity conservation within bioprospecting value chains. | Women will generally benefit from a protected and sustainable environment. They will also benefit from the recognition of their role in safeguarding the biodiversity and from the species conservation. They will benefit through recruitment for training and employment as certifiers. |

### A.5 Risk.

Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, the proposed measures that address these risks at the time of project implementation.(table format acceptable):

Refer to a detailed Risk Assessment is provided in the UNDP PRODOC Section V ‘Feasibility’, Subsections ‘Risk Management’ and ‘Social and environmental safeguards (SES)’, as well as in PRODOC ANNEX F (UNDP Social and Environmental and Social Screening Template - SESP). The sections are complemented by other relevant Annexes, namely PRODOC ANNEX G (Environmental and Social Management Plan - ESMP), PRODOC ANNEX H. (UNDP Project Quality Assurance Report) and PRODOC ANNEX I (UNDP Risk Log), respectively.

### A.6. Institutional Arrangement and Coordination.

Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

Refer to UNDP PRODOC Section VIII ‘Governance and Management Arrangements’ for a detailed presentation of the applicable project arrangements. Additionally, UNDP PRODOC Section IV. ‘RESULTS AND PARTNERSHIPS’ makes ample reference to coordination mechanisms under the following Subsections ‘Partnerships’ and ‘Stakeholder engagement’. A relevant tables are reproduced below.

PRODOC Table 7. Synergies, collaboration and partnerships

| Institutions, Programs, and Initiatives | Proposed contribution |
| --- | --- |
| Linkages and synergies with other GEF-funded projects / programs |  |
| UNDP GEF SLM project | The SLM project, titled: Securing multiple ecosystems benefit through Sustainable Land Management (SLM) in the productive but degraded landscapes of South Africa, currently is being implemented. The project is designed to contribute to supporting green economy in South Africa, by encouraging sustainable land management practices. |
| UNDP GEF Global ABS project | This project is a part of a Global ABS Project, titled: Strengthening human resources, legal frameworks, and institutional capacities to implement Nagoya Protocol. South Africa has been a Party to the Nagoya Protocol since its ratification. As a one of the most biodiverse countries of the world, South Africa recognizes the importance of the regulations of the access to genetic resources and the crucial role of the TK and therefore, has put in place the appropriate legislation and policy frameworks. This 3-year project that specifically aims at assisting countries in the development and strengthening of their national ABS frameworks, human resources, and administrative capabilities to implement the Nagoya Protocol. The project seeks to achieve this by a) strengthening the legal, policy and institutional capacity to develop national ABS frameworks; b) building trust between users and providers of genetic resources to facilitate the identification of bio-discovery efforts; and c) Strengthening the capacity of indigenous and local communities to contribute to the implementation of the Nagoya Protocol. The global project contributes to building the relevant capacity within South Africa that will be key to implementing the full-sized project, particularly among DEA staff. Synergies already exist, with many of the DEA staff involved in the global project already forming part of the institutional structure within DEA that oversees this new full-sized project. |
| Synergies with government programmes, projects and initiatives |  |
| The Department of Environmental Affairs (DEA) Bioeconomy | - The DEA, as a main entity responsible for creating the NBES and other related national policies and is the Implementing Partner for the project, influencing its shape in all stages of its development, particularly engaging in the bioprospecting aspects of the project. DEA is a key partner under the Component 1 of the Project and Output 1.2 in particular. |
| South African National Biodiversity Institute (SANBI) | - SANBI leads and coordinates research, and monitors and reports on the state of biodiversity in South Africa. The institute provides knowledge and information, gives planning and policy advice and pilots best-practice management models in partnership with stakeholders. It provides threatened plant locality data to land use decision makers to minimise further loss of threatened plant populations; informs provincial, national and international policy development for the conservation of threatened plant species; and works closely with the Department of Environmental Affairs (DEA) to develop the national lists for threatened and protected plant species as per the National Environmental Management: Biodiversity Act. The Threatened Species Research Unit investigates the threats, conservation and restoration of key species of plants. Under this project, SANBI will specifically be responsible for overseeing implementation of Output 3.2, whose main aim is to optimise global biodiversity benefits and environmental sustainability through the evaluation and improvement of biotrade certification schemes that provide a link between Access and Benefit Sharing (ABS) and biodiversity conservation in South Africa. |
| Council for Scientific and Industrial Research (CSIR) | - The CSIR research is focused, among others, on the natural environment and industry themes. The Council has already been working with the communities on cultivation of the species at Giyani in Limpopo. The CSIR will help in facilitating the transition from harvesting to sustainable cultivation of African Ginger through conducting research and training communities under Output 1.1. |
| Agricultural Research Council (ARC) | The ARC is the main agricultural institution in South Africa with a wide range of objectives related to agriculture, livelihoods, natural resources conservation, etc. As the Project’s main activities are about sustainable farming of the species and conserving them in the wild, the ARC will be significantly engaged in their implementation. In particular, the ARC is going to contribute to Output 1.2. |
| The Department of Science and Technology (DST) | - The DST, through its research, programs, leadership and partnerships is significantly contributing to socio-economic development of South Africa. The DST will support the project through its: - Green economy partnerships – aiming to support the R&D in certain sectors of South African economy, in order to facilitate county’s transition to green economy, - and through its programs - Programme 2: Technology innovation – supporting research on TK, - Programme 3: International Cooperation and resources – supporting knowledge transfers, - Programme 4: Research development and support – supporting the economic activities aiming to transform South African economy towards knowledge-based economy. - DST direct contribution to the Project will be its help in implementing Output 3.1. |
| Linkages to other donor funded programmes and projects |  |
| Multi-donor ABS Capacity Development Initiative | The ABS Capacity Development Initiative has global scope and has been rolled out in collaboration with the Governments of Brazil, India and South Africa, commissioned national studies to review each country’s experiences with Access and Benefit Sharing. Lessons learned from these experiences will inform the global implementation of the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from its Utilization (Nagoya Protocol). Country studies were prepared to provide background information in preparation for the first Dialogue on Practical Ways Forward for the Implementation of the Nagoya Protocol, hosted by the Government of South Africa on 30-31 January 2014 in Cape Town, South Africa and the second Dialogue on the same topic, co-organized with the Ministry of Environment and Forests of India, from 4-6 August 2014 in Goa, India. The National Study on ABS Implementation for South Africa was concluded in 2014and it provides information about status quo for year 2014 and therefore is extremely useful for the project as a ‘baseline’ of information. |
| JICA-SADC forest project | JICA and Southern African Development Community (SADC) are jointly implementing, since June 2015, their first regional technical cooperation project titled “Forest Conservation and Sustainable Management of Forest Resources in Southern Africa” –or the JICA-SADC forest project, in short. The project was launched during the sixth edition of the Tokyo International Conference on African Development (TICAD VI) which took place in Nairobi, Kenya in August 2016. GEF Council member Japan suggested collaboration with the mentioned project. The following applies with respect to partnerships: Within South Africa, the government focal point for the project will likely be the Department of Agriculture, Forestry and Fisheries (DAFF), which also functions as the focal point for phyto-sanitary oversight and regulation, including with respect to foreign trade aspects. ARC is an institution linked to DAFF and it is set to reach out to the mentioned JICA-SADC project during the GEF project’s inception phase. - Currently, the management of forest resources is not an immediately relevant topic for the subject matter of this GEF project, but it can be in the future, if e.g. forest products (in particular non-timber) may be used as genetic resources. ABS issues may then come into play, along with the sustainable management of these resources, not least also within a regional context. At that point, linkages to the mentioned JICA-SADC forest project will be much more actively sought and consolidated. |
| Swiss State Secretariat for Economic Affairs (SECO) initiative on ABS Compliant Biotrade in South(ern) Africa | The project aims to create a high-growth jobs-rich and innovative biotrade sector that complies with international and domestic ABS regulations. It will support sustainable development goals and contribute to the livelihoods of rural people and the productive use of South(ern) Africa’s plant biodiversity. It aims to create permanent and seasonal jobs in biotrade value chains, while substantially boosting the value generated from biotrade products from the region. The project will work with specific biotrade value chains and plant species, including some which straddle national borders. These will be identified based on criteria including traditional knowledge, ecological sustainability, market demand, potential for value-adding and job creation, and the participation of communities and small businesses. It has 3 components: Component 1: Technical assistance to: Overcome regulatory hurdles enabling access to new markets Empower community businesses and holders of traditional knowledge to participate effectively in biotrade value chains Improve the investment readiness of small businesses through financial and business planning support Component 2: Financial assistance to: Support innovation and growth of biotrade SMEs through a dedicated grant funding facility complementing government incentives Component 3: Supporting an enabling regulatory environment: Make ABS policy and regulations more practical and accessible through policy advice and technical support; Enable industry best practices to contribute to ABS objectives and development goals; Share and learn from regional and global experiences |

### A.7. Benefits.

Describe the socioeconomic benefits to be delivered by the project at the national and local levels. How do these benefits translate in supporting the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF)?.

The project is expected to bring certain socio-economic benefits, particularly through its Component 2: “Cooperation models support the conservation of, and commercial trade in, indigenous bioproducts”. This Component is to the greatest extent comprising the aspect of cooperation between local communities and various other stakeholders within the value chains.

The socio-economic benefits arising from the project’s activities go fully along with GEBs as co-benefits to them. All Outputs under Component 2 will contribute to general equity among involved communities and gender equity. The activities will enable job creation in a bioprospecting sector among the members of the local communities (e.g. nursery).

The Outputs under Component 2 (Outputs 2.1 to 2.4) will enable capacity building among the engaged stakeholders through implementing better cultivation techniques and limiting the unregulated harvesting. This way, not only the sustainability will improve but the communities will be able to benefit through building their knowledge, getting new jobs and improving their economic conditions.

For example, Output 2.2 will contribute to ensuring equity and improving the quality of life of poor A. ferox harvesters. It will also contribute to supporting national businesses, that produce A. ferox for the  domestic market, and for export. Output 2.4 – Rooibos deal, will bring the social equality and improvement of economic conditions among the engaged communities.

Refer also to PRODOC Section III: Strategy, Part Long-Term Solution and Section IV: Results and Pertnerships, as well as to PRODOC ANNEX X-7. ‘Gender Mainstreamin Action Plan’ for further details.

### A.8 Knowledge Management.

Elaborate on the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives (e.g. participate in trainings, conferences, stakeholder exchanges, virtual networks, project twinning) and  plans for the project to assess and document in a user-friendly form (e.g. lessons learned briefs, engaging websites, guidebooks based on experience) and share these experiences and expertise (e.g. participate in community of practices, organize seminars, trainings and conferences) with relevant stakeholders.

The project has a dedicated knowledge management component, Component 4 (“Knowledge Management & M&E”), in which KM is built in to ensure special emphasis is paid to documenting the current progress on the ABS implementation value chains.

Refer to Component 4 description in PRODOC ANNEX X-3. ‘Detailed description of project design: outputs and activities’.  In addition, PRODOC ANNEX X-5. (Knowledge Management & Stakeholder Involvement Plan) also covers the topic.

## Description of the consistency of the project with:

### B.1 Consistency with National Priorities.

Describe the consistency of the project with national strategies and plans or reports and assessments under relevant conventions such as NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, INDCs, etc.:

The Biodiversity Act instituted an ABS regime with respect to bioprospecting in South Africa already in 2004, which emerged relatively early, when compared to other countries. The Biodiversity Act also mandated the government to administrate a Bioprospecting Trust Fund, aimed at providing protection to traditional knowledge as key a contributor to the commercial or industrial application of biodiversity resources, and to ensure that royalties generated are not only received, but also equitably shared. Permits, agreements, consent forms and patents are some of the most common instruments used for enforcing ABS legislation.

The legal frameworks that govern ABS is composed of several pieces of legislation, including sections of South Africa’s Biodiversity Act of 2004, amendments to the Patents Act from 2005, which require patent applicants to disclose the origin of genetic material and traditional knowledge and show that they have obtained prior informed consent (PIC) and shared benefits, and – most importantly -- the Bioprospecting and Access and Benefit-Sharing Regulations (BABS) of 2008. An important recent initiative is the gazetting of the Intellectual Property Laws Amendment Bill (2010) which provides for copyright, designs and trademarks to be used for providing protection of names or features associated with traditional knowledge.

| Key national legislative and frameworks relevant to Nagoya Protocol implementation in South Africa: - CBD and Nagoya Protocol on Access to Genetic Resources & the Fair and Equitable Sharing of Benefits Arising from their Utilisation - Constitutional mandate & National Environmental Management Act (NEMA) - Constitutional Concurrent Mandate, Provincial Ordinance - White Paper on Conservation & Sustainable Use of South Africa’s Biodiversity of 2007 - NEMBA, BABS Regulations, TOPS Regulations & CITES Regulations - Patent Amendment Act - Indigenous Knowledge Systems Policy Bioprospecting Guidelines (see left): issued in 2012 for users, providers, and regulators. See https://www.environment.gov.za/sites/default/files/legislations/bioprospecting_regulatory_framework_guideline.pdf. |  |
| --- | --- |
| Principles of the NBES: - Conservation of biodiversity and ecological infrastructure - Sustainable use of indigenous resources - Fair and equitable benefit-sharing - Socio-economic sustainability - Incentive driven compliance to regulation - Ethical practices - Improving quality and standards of products | Principles of the BABS: - Anyone carrying out bioprospecting involving indigenous biological resources and, if applicable, associated traditional use or knowledge, requires a permit. - Anyone exporting indigenous biological resources for the purposes of bioprospecting or other research requires a permit. - A permit will only be issued if there has been material disclosure to stakeholders, if their prior informed consent to the bioprospecting has been obtained and if the Minister is satisfied that certain conditions, as set out in the legislation, have been met. |

Refer to UNDP PRODOC Section II ‘Development Challenge’ and particularly to Subsection ‘Project fit with SDGs, national policies and priorities’, which outlines the project’s consistency with national strategies and plans, and especially the relevance to national development priorities, global environment and/or adaptation issues, and the sustainable development goals (SDGs). Additionally, the following Subsection in PRODOC ANNEX X-2.1) ‘Status Quo of the Implementation of Nagoya Protocol in South Africa’ is relevant.

## Describe the budgeted m &e plan:

The full M&E Plan for the project is included in the UNDP PRODOC Section VII Monitoring and Evaluation (M&E) Plan. A summary is reproduced below.

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (USD) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop | UNDP Country Office | USD 11,330 |  | Within two months of project document signature |
| Inception Report | Project Manager | None | None | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework | Project Manager | Per year: USD 1,000 ($1000 x 5 yrs= $5000) | None | Annually |
| GEF Project Implementation Report (PIR) | Project Manager and UNDP Country Office and UNDP-GEF team | None | None | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office | Per year: USD 4,000 ($4000 x 5 yrs = $20,000) | None | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Manager | None | None | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager UNDP CO | None | None | On-going |
| Addressing environmental and social grievances | Project Manager UNDP Country Office BPPS as needed | None for time of project manager, and UNDP CO | None | On-going |
| Project Board meetings | Project Board UNDP Country Office Project Manager | Per year: USD 2,500 ($2,500 x5 yrs = $12,500) | None | Annually |
| Supervision missions | UNDP Country Office | None | None | Annually |
| Oversight missions | UNDP-GEF team | None | None | Troubleshooting as needed |
| Knowledge management as outlined in Outcome 4 | Project Manager | None | None | On-going |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP-GEF team | None | None | To be determined. |
| Mid-term GEF Tracking Tool to be updated by PMU in coordination with ARC, CSIR and DST | Project Manager | USD 2,000 | None | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 45,000 | None | Between 2nd and 3rd PIR. |
| Terminal GEF Tracking Tool to be updated by PMU in coordination with ARC, CSIR and DST | Project Manager | USD 2,000 |  | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | USD 45,000 |  | At least three months before operational closure |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | USD 142, 830 * |  |  |

*It is noted that the M&E budget is below 3% of the overall GEF investment.

Refer also to the UNDP PRODOC Annexes B & C, which contain the general M&E Plan with reference to several ProDoc Appendices and Tables.

The GEF tracking tools are attached and referenced in the UNDP PRODOC Annex D [attached as a separate file]. These will be updated at mid-term and at the end of the project and will be made available to the GEF Secretariat along with the project PIR report. As mentioned in the table further up, the mid-term review and the terminal evaluation of the project will verify the information of the tracking tool.

# PART III:  CERTIFICATION BY GEF PARTNER AGENCY(IES)

## GEF Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO endorsement under GEF-6.

| Agency Coordinator, Agency Name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu |  | 17 October 2017 | Phemo K. Kgomotso | +251912503309 | phemo.kgomotso@undp.org |

# ANNEX A:  PROJECT RESULTS FRAMEWORK

UNDP PRODOC Section VI with the Results Framework (reproduced below)

This project will contribute to the following Sustainable Development Goal (s): Goal 1 ending poverty: through rural development opportunities provided by community-engagement and livelihood improvement interventions through the engagement of small farmers and wild harvesters in bioprospecting and biotrade. Furthermore, the project touches upon Goal 5 - Gender equality and Goal 8 - decent work and economic growth, where key principles of inclusive growth – among them, gender sensitive & gender sensible growth – will guide the development of business models based on the bioprospecting value chains that will be supported by the project. Goal 9 - Industry, Innovation and Infrastructure is highly relevant for the subject matter of the project, to the extent that it will promote inclusive and sustainable industrialization and foster innovation through a wide range of value chains linked to bioprospecting and the bioeconomy. Goals 12 Sustainable Consumption and Production patterns will also be addressed, to the extent that the project will help infuse sustainability in the products and value chains supported by the project. Goal 15 Life on land: where efforts will be made through the project to improve the management of terrestrial ecosystems and of specific plant species that are found in them, including for the preservation of their genetic diversity. Goal 17 Means of implementation and partnerships: where South Africa is megadiverse country and a BRICS emerging economy, placing it strategically to show examples of how to operationalize the bioecomomy and meet a number of other SDGs in the process.

This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: Outcome 2: Increase in the number of sustainable ‘green jobs’ created in the economy; Stabilisation and reduction of carbon emissions and climate change mitigation and adaptation strategies fully operational. (Programme Component II: Climate Change and Greening South Africa’s Economy)

This project will be linked to the following output of the UNDP Strategic Plan: Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste

|  | # | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective: To strengthen value chains for products derived from indigenous plants' genetic resources in view of contributing to the equitable sharing of benefits and the conservation of biodiversity. | 1 | Increase in capacity to implement the Nagoya Protocol on ABS, as measured by the GEF6 Tracking Tool (TT) BD Program 8: (a) TT Section 1 (max points = 38) (b) TT Section 2 x 6 pilots (max points per pilot = 10; all pilots = 60) ----------------------------------------- (c = a + b) TT max points total = 98 | (a) 29 out of 38 (b) 16 out 60 (c) 53 out of 98 | (a) 31 out of 38 (b) 30 out 60 (c) 60 out of 98 | (a) 35 out of 38 (b) 44 out 60 (c) 74 out of 98 | R&D of products in line with NP’s definition of utilization of genetic resources of South Africa accumulates successful experiences with sustainable and ethical bioprospecting product development. Cooperation models across key bioprospecting value chains support ABS-compliant trade in indigenous plant species and related conservation measures. Knowledge transfer in bioprospecting and value addition is enhanced for an equitable sharing of benefits |
|  | 2 | Number of ABS monetary agreements negotiated for flagship products developed from genetic resources/derivatives of Rooibos and African Ginger) | 0 (outdated) ABS agreements | At least 1 ABS agreement | At least 2 ABS agreements (for products derived from African Ginger and Rooibos) |  |
|  | 3 | Area (ha) under landscape management systems that mainstream ABS principles: (a) Direct (pilots targeted landscape) (b) An ABS and biodiversity conservation certification system in place for key value chains | (a) XX ha (to be determined at project inception) (b) no system in place | (a) XX ha (to be determined at project inception) (b) An ABS and biodiversity certification system developed and being piloted | (a) XX ha (to be determined at project inception) (b) An ABS and biodiversity conservation certification system approved and adopted. |  |
|  | 4 | Level of mainstreaming of gender considerations in project monitoring (measured through scoring on the state of advancement in gender disaggregated data collection and analysis in ABS pilots): 1.1 African Ginger product registration 1.2 N Cape R&D hub 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush 2.4 Rooibos ABS deal ------------------------------------------- ALL PILOTS (max scoring for each pilot = 24 / sum for all pilots = 108, as of Scoring Matrix for composing Results Framework Indicator’) | Scores at the baseline: For pilot 1.1) 5 For pilot 1.2) 7 For pilot 2.1) 5 For pilot 2.2) 6 For pilot 2.3) 12 For pilot 2.4) 7 --------------------------------- ALL PILOTS = 42 / 144 (or 28%) Baseline scoring in PRODOC Table ‘Gender Mainstreaming Assessment’ (Annex X-7). | At least 60% for the sum of all pilots (i.e. around 65) | Close to 100% (i.e. around 100 and up) |  |
| Outcome 1. Bioprospecting R&D that focuses on indigenous plants contributes to the national bioeconomy | Outputs: 1.1 R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. 1.2 Bioprospecting R&D in the Northern Cape is supported, boosting the local bioeconomy and establishing a strategically located ‘Bioproducts Development Hub’. |  |  |  |  |  |
|  | 5 | Number of ABS products developed as a result of Research & Development (R&D) | 0 | 1 ABS product developed | 1 ABS product developed and marketed | South Africa is able to accumulate successful experiences with sustainable and ethical bioprospecting product development and facilitate ABS arrangements between providers and users of plant genetic resources. Pooling of R&D support enables local economies to develop successful bioprospecting supply chains that are both ABS-compliant and conservation-friendly. |
|  | 6 | Number of new and strengthened ABS-compliant supply chains facilitated in the Northern Cape’s bioeconomy | 0 new supply chains, 2 existing supply chains that could be strengthened (Devil’s Claw and Rooibos) | At least 1 new supply chain (for Kanna) and 1 strengthened supply chain (Rooibos) | At least 2 new supply chains (Kanna and Cancer Bush), and 2 strengthened Devil’s Claw and Rooibos supply chains |  |
|  | 7 | Number of patent registrations based on home-grown R&D facilitated by the project | 0 | n/a | 1 (for African ginger as a product for allergies and asthma) |  |
| Outcome 2. The ways of working, management conditions and techniques change within 5 (five) strategic value chains, and demonstrate how conservation and ABS-compliance can be simultaneously achieved through cooperation among bioeconomy players | Outputs: 2.1 The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders. 2.2 Development of an Aloe ferox harvesting, processing and trading hub in the Eastern Cape for promoting sustainable and equitable benefit sharing across the value chain is supported. 2.3 Community-based enterprises in honeybush farming are supported, ensuring conservation and equitable benefit sharing outcomes across the Cyclopia spp. landscape in the Cape Region. 2.4 [*] ABS implementation in Rooibos farming is strengthened, ensuring fairness, equity and sustainability in relevant relationships among TK holders and industry. * Output renumbered from 2.6 to 2.4, given that two outputs were dropped so as to provide an adequate response to GEF comments in February 2018.] |  |  |  |  |  |
|  | 8 | Increased score for implementation of Nagoya Protocol on ABS as per the GEF6 Tracking Tool BD Program 8, Section 2) ABS Pilots = X / max score 40 (10 x 4 pilots) --PILOTS-- 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush 2.4 Rooibos ABS deal | Score = 17 out of 40 --------------------------- For pilot 2.1) 2/10 For pilot 2.2) 5/10 For pilot 2.3) 2/10 For pilot 2.4) 8/10 | Score = 24 out of 40 For pilot 2.1) 5/10 For pilot 2.2) 6/10 For pilot 2.3) 4/10 For pilot 2.4) 9/10 | Score = 32 out of 40 For pilot 2.1) 10/10 For pilot 2.2) 8/10 For pilot 2.3) 4/10 For pilot 2.4) 10/10 | The effective implementation of Biodiversity Management Plans (BMPs) ensure that species’ carrying capacity are taken into account and that extraction rates are managed sustainably. A well-managed transition from wild harvesting to cultivation for supplying bioprospecting value chains reduces threats to targeted species and helps safeguard their wild gene-pools. Traditional knowledge holders are duly recognized as important providers of genetic resources and receive an equitable share of benefits through adequate agreements and frameworks. Conservation benefits and TK’s contribution are taken into consideration in ABS agreements and mainstreamed into the permitting system. Collaboration among economic players create opportunities for innovation and process improvement. |
|  | 9 | Number of harvesters trained as per the sustainable harvester guidelines for the following pilots: 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush | For pilot 2.1 = (data not available) For pilot 2.2 = 0 For pilot 2.3 = (data not available) | For pilot 2.1 = t.b.d. For pilot 2.2 = >50 For pilot 2.3 = t.b.d. | For pilot 2.1 = t.b.d. For pilot 2.2 = >50 For pilot 2.3 = t.b.d. |  |
|  | 10 | Number of local community households for which members are employed in aloe cultivation, harvesting and processing | <25 households | 64 households | >80 households |  |
|  | 11 | Total income (US$/annum) derived from project pilots that focus on cultivation 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush | X ZAR (data will be collected at pilot level during the project’s year 1) | X ZAR + Y% | X ZAR + Z% |  |
|  | 12 | Cultivation area for Honeybush to mitigate the current impact of habitat destruction and overharvesting | 147 ha | 300 ha | 450 ha |  |
| Outcome 3. Bioprospecting and value addition knowledge transfer is enhanced for an equitable benefit sharing | Outputs: 3.1 The National Recordal System for TK linked to bioprospecting is supported for ensuring ABS compliance in current and future agreements between indigenous and traditional knowledge holders and industry. 3.2 A biotrade certification system for South Africa is developed in view of safeguarding biodiversity conservation within bioprospecting value chains. |  |  |  |  |  |
|  | 13 | A certification system in place to promote biodiversity conservation in the biotrade sector focusing on threatened species - securing species’ survival - protection of wild gene-pools - habitat management - sustainable transition towards cultivation | No system in place, only planned through the project | A certification system developed for 1-2 value chains | A certification system in place and in place for at least 5 value chains | The strengthening of DST’s National Recordal System ensures the adequate recording, maintenance, dissemination and protection of traditional knowledge and a more equitable sharing of benefits derived from bioprospecting value chains. Targeted biodiversity conservation safeguards ensure that bioprospecting/biotrade economic activities will not deplete the stocks of indigenous biological resources or their gene pool – enabling thereby the effective contribution of value chains to conservation. |
|  | 14 | Number of Internationally Recognized Certificates of Compliance (IRCC) registered in the CBD’s ABS Clearing House Mechanism | 3 IRCCs as of July 2017 | 4-5 IRCCs by Mid-2020 | At least 6 IRCCs by End-2023 |  |
|  | 15 | A functional National Recordal System in place. | The current TK Recordal System is not functional (according to project’s baseline analysis – refer to Barrier #3) | The outline of the new National Recordal System is tested and approved by DST | The new National Recordal System is fully functional and under utilisation |  |
| Outcome 4) Lessons learned and the application of a participatory and gender sensitive M&E framework effectively contribute to institutional, community and corporate learning on ABS | Outputs National and international stakeholders supported to participate in the project M&E and to systemize lessons learned from its implementation. |  |  |  |  |  |
|  | 16 | Number of project lessons generated and disseminated to share knowledge on implementation of ABS initiatives | 0 lessons documented and disseminated | 3 lessons documented and disseminated | 6 lessons documented and disseminated | South Africa has an advanced ABS framework with fairly developed bioprospecting and biotrading sectors and has the capacity to share lessons with other countries in the region (including those it shares some plant genetic resources with, e.g. Lesotho) and beyond. Under this project, R&D will be supported and key scientific findings will be generated that will be of use to the global community. |
|  | 17 | Number of women and men participating and benefiting from project interventions 50% women/50% men | XX men (to be determined at project inception) XX women (to be determined at project inception) | XX men (to be determined at project inception) XX women (to be determined at project inception) | XX men (to be determined at project inception) XX women (to be determined at project inception) |  |

# ANNEX B:  RESPONSES TO PROJECT REVIEWS

(from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

- Comments at PIF Stage

### 1a) STAP Comments at PIF Stage and UNDP’s response

| STAP Comments | Responses | Document reference |
| --- | --- | --- |
| STAP Scientific and Technical screening of the Project Identification Form (PIF), dtd. March 14, 2016 |  |  |
| Overall STAP assessment at PIF stage: 2 = Minor issues to be considered during project design |  |  |
| STAP welcomes this initiative, which is an innovative project proposing a number of unique approaches. It is also timely, following as it does recent changes to legislation, formulation in 2015 of the Biodiversity Economy Strategy and the issuing of guidance to those wishing to develop and to market biodiversitydependent products under the Nagoya ABS protocol in South Africa. | UNDP thanks the STAP for insightful comments and wishes to structure its response around seven topics identified and marked by UNDP in the column to the left: | As below. |
| The threat analysis and data in the table of plant species currently exploited is a good snapshot of the key issues, emphasizing the tension between exploitation and conservation and the need to assure the sustainability of the biodiversity base. The project essentially proposes research into ten bio-products, and is strong in these explanations. [TOPIC 1] A caution, however, is the timescale for the project at 60 months which is likely to be too short for new products researched under this component to complete clinical trials, which can take more than a decade. | A different set of species than those proposed at PIF stage prevailed at CEO Endorsement stage, including in light of considerations for the long time needed for producing results through R&D. Overall, the project strategy at CEO Endorsement stage is thoroughly justified and described in the UNDP PRODOC. Both the content and the approach to Outputs, as they had been proposed at PIF stage, were thoroughly discussed among stakeholders during the PPG Inception Workshop. They were subsequently revised / reformulated. As a result, the project strategy strategy was consolidated either around ‘ABS pilots’ or ‘ABS systemic measures’. In addition, the priority species, value-chains, bioprospecting hubs and partnerships were consolidated. The current focus of ABS pilots can be summarized through the quick reference to project Outputs: 1.1 African Ginger product 1.2 N Cape R&D hub () 2.1 Pelargonium 2.2 Aloe ferox 2.3 Honeybush 2.4 Rooibos ABS deal By February 2018: In response to Comments from GEF Secretariat at CEO Endorsement stage, several changes were made. These are marked and registered herein in the appropriate section. Related issues and responses are as follows: - Where is conservation? A central question posed by the GEF Secretariat in several of its comments has been how the project’s proposed activities relate to conservation and sustainable use of biodiversity on the ground. Similar questions were also posed by STAP and GEF Council members. Project proposnents (i.e. DEA, with support from UNDP and the PPG Team) took these questions fully into consideration, with the understanding that the GEF Secretariat did not find sufficient “language connecting these activities with conservation on the ground” or that this language remained too implicit. This is e.g. prominent in GEF Secretariat’s Comment # 1, regarding the following species and corresponding methods of sourcing raw materials (quoting): “Aloe [ferox] (plantations), Roibos, African ginger (cultivation and agroprocesing), honeybush (farming) and Pelargonium spp. (harvesting).” Proponents also felt that this link was perhaps ‘too implicit’ in the PIF and that the PPG process should serve to strengthen it. However, as the current round of reviews served as an opportunity to make it even more explicit. Extensive literature and various subject matter experts in South Africa were consulted during the PPG process. Especially now with the currnet round of revisions to the PRODOC for CEO Endorsement, proponents made sure to make this link even more more explicit. - Wider benefit sharing? Furthermore, proponents also wished to strengthen the relationship between activities and direct and indirect benefits of conservation to communities, including how these translate into social benefits, which communities equally expect to obtain from value chain strengthening, as well as aligned with national policies. | UNDP PRODOC, Section II. DEVELOPMENT CHALLENGE and Section III. STRATEGY for the justification. UNDP PRODOC, STRATEGY, subsection ‘Project Areas and Pilots’ (under Section III) and Subsection ‘Bioresources targeted in key Value Chains’ (under Section II) Part I of this document for the text for project Outputs; + UNDP PRODOC Section IV. RESULTS AND PARTNERSHIPS. Added to current iteration of PRODOC (Feb 2018): Text that precedes and follows Figure number 10 from the PRODOC and CEO Endorsement Request are now added. Changes made, and content added to current iteration of PRODOC (*also included in the CEO Endorsement Request): PRODOC Annex X-2.2, Table 13. Species characteristics, conservation status, value chain development and research facts Box 6. New Sustainable Practices’ Adoption, Uptake and Spread + (updated) Linkages In PRODOC, Annex X-2.2, Plant Species Distribution Sheets #1, 2 and 3 |
| [TOPIC 2] In addition, STAP observes that while the legislative and regulatory context of implementation of the Nagoya ABS protocol in South Africa is comprehensive it is also complex. This in itself may be a major barrier to facilitation of local and indigenous communities' participation, although progress has been achieved since an earlier study of the topic (see Crouch et al, 2008). There are numerous useful activities/outputs described, but the cause-effect logic suggested between outputs and outcomes is unclear (both within the Project Summary Table, and between the Table and the narrative). Unless more attention is given to clarifying the operational logic of the project the delivery of benefits rests more on hope than design. | During the PPG process, the project’s Theory of Change was fully conceived. The project’s cause-effect logic is now made fully explicit and, as referred to further up, project outputs have been thoroughly revised. With respect to the government’s approach and priorities, it is worth noting that the PIF had been formulated at stage when the National Bioeconomy Strategy (NBES) had barely been proposed. Several elements regarding priority species for ABS value chain development, the context for the bioeconomy, as well as approaches to the implementaiton of ABS measures needed further development and consolidation, including for proper barrier identification and removal. In fact, several studies and assessments underpinned the development of the NBES. For example, in connection with the approval of the NBES, DEA published a seminal study published in 2015, which surveyed the scope and extent of the utilization of indigenous biological resources by bioprospecting industries in South Africa (see reference to the right). The results of the scoping study served to inform the review of project Outputs, as well as consultations with stakeholders. Refer to the relevant Barrier Analysis in the UNDP PRODOC. By February 2018: In response to Comments from GEF Secretariat at CEO Endorsement stage, several changes were made. We refer to the response to comment # from GEF Secretariat at CEO Endorsment stage, where the following response is given: It is important to note that compliance with South Africa’s Bioprospecting, Access and Benefit Sharing regulations (BABS) can be a powerful tool for promoting conservation and sustainable use of biodiversity – and not just a tool for ABS compliance. Furthermore, all species / products on focus will need to comply with BABS though the permitting system. In the BABS’s regulated relationships between providers and users of genetic resources caters for the adherence to the permit’s conditions, and thereafter, with the permit’s issuance the conditions imply that key trade information that has a bearing for sustainability has been disclosed according to the conditions of the permit. Regardless of whether business information relating to the permits will remain confidential or not, key information with a bearing for biodicersity management is necessarirly disclosed to DEA. This includes for example information on traded volumes, trade routes, resource origin, product development and beneficiation. And because BABS is hierarchically under the National Environmental Management Biodiversity Act (NEMBA), compliance with BABS implies also compliance with NEMBA and due diligence is necessarily carried out by government as applicable. This is why it may be said that BABS compliance (i.e. ABS or Nagoya Protocol compliance) is a powerful tool for promoting conservation and sustainable use of biodiversity. BABS compliance will be required of all value chains relevant for the project (including the relevant species-value chains highlighted: Aloe ferox, Roibos, African ginger, Honeybush and Pelargonium spp. | UNDP PRODOC, Sub-Section ‘The Project’s Theory of Change (ToC)’, under Section II. UNDP PRODOC Box 2 ‘Key conclusions and highlights from the 2015 Scoping Study on Bioprospecting’, for details: DEA (2015): The scope and extent of the utilization of indigenous biological resources by bioprospecting industries in South Africa. Department of Environmental Affairs, Government of the Republic of South Africa. (ISBN 978-0-621-42766-0). Added to current iteration of PRODOC in Feb 2018: Text that precedes and follows Figure number 10 from the PRODOC and CEO Endorsement Request are now added. Changes made, and content added to current iteration of PRODOC (*also included in the CEO Endorsement Request): PRODOC Annex X-2.2, Table 13. Species characteristics, conservation status, value chain development and research facts Box 6. New Sustainable Practices’ Adoption, Uptake and Spread + (updated) Linkages In PRODOC, Annex X-2.2, Plant Species Distribution Sheets #1, 2 and 3 |
| [TOPIC 3] Several issues are not discussed or are discussed at a superficial level, including risks/assumptions, global environmental benefits, incremental reasoning, stakeholders, and relevant knowledge / learning from other projects / literature, including GEF. The PIF is weak where it discusses how to develop value chains, implement field management plans, and ensure local benefit. Further effort to design inclusive and participatory processes and tools to benefit local and indigenous communities' participation in value chain development and also collection and management of the resource is required. | As referred to further up, the project strategy at CEO Endorsement stage is thoroughly justified and described in the UNDP PRODOC. Outputs were thoroughly revised and described -- and this was justified in the UNDP PRODOC, as well as herein. In terms of project development, the UNDP PRODOC represents a major improvement vis-à-vis the PIF. Refer to the UNDP PRODOC Section II. DEVELOPMENT CHALLENGE and Section III. STRATEGY for the project’s justification and approach. UNDP confirms that the following topics have been fully developed in the UNDP PRODOC: - Project Risks and Assumptions (see PRODOC Section V. FEASIBILITY, as well as The Project’s Theory of Change ToC, under PRODOC Section III - Strategy); - Global environmental benefits and incremental reasoning (See Part II, A.1-4 and A.1-5 further up for an easier reference); - Stakeholders and their engagement (see PRODOC Section IV, with cross-reference to several other relevant sections and sub-sections); - Relevant knowledge / learning from other projects (see Part II, A.1-6 further up for easier reference); and - Bibliography (UNDP PRODOC ANNEX X-8). Refer in particular to the following two PRODOC Annexes, which describe in detail the approach to ABS pilots and systemic measures: - ANNEX X-2. Project Context & Baseline: ABS frameworks & Species-value-chain interactions; and - ANNEX X-3. Detailed description of project design: outputs and activities | CEO Endorsement Request and UNDP PRODOC |
| For example, [TOPIC 4] STAP suggests that under Component 3 a succinct guide distilled from the BMP for local and indigenous communities may bridge the gap between science and practice and serve as a model for future BMPs. The BMP will provide a useful overview of status and threat, however alone this will likely not serve as an accessible tool for raising awareness and guiding collection and use. In addition, if BMPs are to be regarded as useful tools to be piloted for effective conservation and use of biodiversity then STAP recommends an explicit link with the Biodiversity Economy Strategy. Finally, given that SANBI is the designated lead authority for development of these Plans, it should appear in the list of stakeholders. | STAP suggestions have been incorporated into project designed, but in a slightly different way. Several outputs include ecosystem management for sustainability. This is specifically embodied in the project’s work in the pilots, including both Component 1 and Component 2. Furthermore, Output 3.2 (certification scheme) will provide biodiversity safeguards and has a strong potential for scaling up. Activity #3 under that output reads as follows: “Act. 3) Develop an approach to linking Biodiversity Management Plans (BMP) outputs to certification standards requirements. The purpose would be to take BMP outputs relevant to certification requirements relevant SANBI.” Ecosystem management practices are a key focus under two key Component 2 Outputs: namely Output 2.1 on Pelargonium spp. (under the advise of the Pelargonium Working Group - PWG) and Output 2.3 on Honeybush (for which a Community of Practice exists and will be involved). SANBI can and will advise both as needed. Two bioprospecting hubs will be established, one in Northern Cape (through Output 1.2) and one in Eastern Cape (through Output 2.2) – the latter with focus on processing of Aloe ferox and enhanced value addition. Yet, ecosystem management are also part of the work foreseen under these outputs. Attempts to bridge science and practice were made explicit is certain PRODOC passages. Refer to in particular to: - UNDP PRODOC Subsection ‘Bioresources targeted in key Value Chains’; - UNDP PRODOC ANNEX X-6. ‘The dynamics of resource overexploitation in bioprospecting value chain’. - Description of Outcome 3 (Bioprospecting and value addition knowledge transfer is enhanced for an equitable benefit sharing), through which knowledge transfer schemes can developed on the basis of both science and practice. - Annex X-3, Subsection: Component 4 (Knowledge Management & M&E), Outcome 4 (Lessons learned and the application of a participatory and gender sensitive M&E framework effectively contribute to institutional, community and corporate learning on ABS), and Output 4.0 (National and international stakeholders are encouraged to participate in the project M&E and will systemize lessons learned from its implementation). By February 2018: In response to Comments from GEF Secretariat at CEO Endorsement stage, several changes were made. Among them are changes to Component 3 with the inclusion of BMP. | UNDP PRODOC, STRATEGY, subsection ‘Project Areas and Pilots’ (under Section III) and Subsection ‘Bioresources targeted in key Value Chains’ (under Section II) UNDP PRODOC ANNEX X-3. Detailed description of project design: outputs and activities |
| [TOPIC 5] The overall presentation of the PIF gives the impression that project conceptualization has been rushed with limited participation of stakeholders, and currently the project appears to be in the very early stages of conceptualization. With good ideas that are workable, however STAP wishes to stress that much more care should be taken in designing the project logic, operationalization, and contribution to Global Environmental Benefits. Finally, the Knowledge Management statement must be carefully considered. Currently it contains aspects of outreach, but omits mention of the proposed databases and training materials to be developed by the project. In the PPG stage leading to the full project proposal STAP recommends significantly strengthening this section to identify how the project KM can contribute towards transformational change, regional sharing and sustainability of the proposed Global Environmental Benefits. | It is possible that GEF deadlines and requirements result in the rushing of project design processes, calling for the need to optimize them. Regardless, the PPG was fully participatory and this is widely evidenced in the UNDP PRODOC. Stakeholders engagement is thoroughly described in PRODOC Section IV, with cross-reference to several other relevant sections and sub-sections), including to the following UNDP PRODOC Annexes: - ANNEX X-4. Stakeholders consulted during the PPG - ANNEX X-5. Knowledge Management & Stakeholder Involvement Plan - ANNEX X-7. Gender Mainstreaming | UNDP PRODOC Section IV, Annexes X-4 and X-5 |
| End of response |  |  |

### 1b) GEF Council Comments at PIF Stage and UNDP’s response

With reference to Work Program version of the PIF:

South Africa, Development of Value Chains for Products derived from Genetic Resources in Compliance with the Nagoya Protocol on Access and Benefit Sharing and the National Biodiversity Economy Strategy, GEF ID = 9255

#### Comments from GEF Council member Germany

| GEF Council Comments | Responses | Document reference |
| --- | --- | --- |
| GEF Council member Germany, dtd. May, 2016 |  |  |
| II. Germany approves the following PIF in the work program but asks that the following comments are taken into account: Germany requests that the following requirements are taken into account during the design of the final project proposal: With regard to the ambitious aims and broad scope of the Biodiversity Economy Strategy and the intended contribution of this project for its implementation, Germany requests that three issues be dealt with specifically during the PPG and in the final project document: - [Issue 1] consultations and dialogue with a broader spectrum of companies (domestic / international) - [Issue 2] targeted analyses of market potentials of the supported value chains, including market trends in the respective business fields (incl. regional and other developing country markets) - [Issue 3] - capacity development in terms of market access / compliance issues (e.g. quality and regulatory standards in target markets) - Successful value chain development will also depend on workable access procedures and effective user measures in South Africa. While these issues will be dealt with in the mentioned Global UNDP Project and by the ABS Capacity Development Initiative), Germany considers it crucial that this project makes an explicit link to the activities of the other ABS support activities with respect to regulatory measures which are already ongoing. (Initial) outcomes of the UNDP and the ABS Initiative’s projects need to be reflected in the PPG and in the final project document. | UNDP thanks the Council member from Germany for the insightful and constructive comments. Issue 1) The Department of Environment (DEA) in South Africa has oriented the approach to stakeholder engagement with respect to relevant private sector companies, several of wich were consulted during the PPG phase. At the same time, DEA stressed that issues of TK and national competitiness can be sensitive and need to be tackled with due scrutiny, given the nature of GEF projects and their purpose. Else, UNDP confirms that the a detailed discussion of Stakeholder Engagement is provided in the UNDP PRODOC Section IV “Results and Partnership”, Subsection ‘Stakeholder Engagement’. (See in Section IV cross-reference to several other relevant sections and sub-sections, among them, the UNDP PRODOC ANNEX X-4. ‘Stakeholders consulted during the PPG and UNDP PRODOC ANNEX X-5. ‘Knowledge Management & Stakeholder Involvement Plan’ – the latter providing further details. Also, ANNEX X-7 ‘Gender Mainstreaming’provides information about stakeholder consultations with due consideration of gender aspect. In addition, we refer to a relevant UNDP PRODOC sub-section, part of which is reproduced below: “The sustainability of the specific project activities will be ensured by the continued availability of training materials and case-studies. These materials will be open access, available in electronic version, and disseminated widely. They will provide comprehensive guidance for stakeholders, and will be used in future projects, as well as other countries of the region and beyond. The emphasis on strategic partnerships, continued engagement of government agencies, CBOs, CSOs and the private sector will complement this approach. This will include plans for cost-recovery for financial sustainability. Lessons learnt on the implementation of projects incorporated in this proposal will be imparted to a broader stakeholder base in the planned Biennial Biodiversity Economy Indaba.” [end of quote] Issue 2) Several studies and assessments underpinned the development of the National Bioeconomy Strategy (NBES) proposed for national adoption as a key policy at the time of the approval of the PIF, and eventually published and adopted in 2016. During the PPG phase of the project, the information about market potentials of the supported value chains, including market trends in the respective business fields was included in the PRODOC, particularly in Section II. ‘Development Challenge’ under chapters ‘The Bioprospecting Segment’, ‘The Bioeconomy of South Africa’ and ‘Bioresources targeted in key value chains’, as well as referenced in several other chapters. In connection with the approval of the NBES, DEA published a seminal study published in 2015, which surveyed the scope and extent of the utilization of indigenous biological resources by bioprospecting industries in South Africa. See e.g.: DEA (2015): The scope and extent of the utilization of indigenous biological resources by bioprospecting industries in South Africa. Department of Environmental Affairs, Government of the Republic of South Africa. (ISBN 978-0-621-42766-0). Other key materials and publications relevant to the bioeconomy were also produced since. The results of the scoping study, as well as other materials and publications relevant to the subject matter of bioprospecting, served to inform the project design at CEO Endorsement stage, as well as consultations with stakeholders during the PPG. With reference to key materials and publications relevant to the bioeconomy mentioned further up: It is notable from these studies and publications that Germany represents a currently important and growing market for South African bioprospecting products. The project strategies concerning ABS compliance and sustainability have taken this piece of information into account. First bullet, Issue 3) The information requested is included in the respone to Issue 2 further up.. Second bullet, Issue 3) At CEO Endorsement stage, the UNDP GEF Global Project on referred in Germany’s comment has been fully approved and it is under implementation. The national project is closely linked to Global ABS Project, titled: Strengthening human resources, legal frameworks, and institutional capacities to implement Nagoya Protocol. South Africa has been a Party to the Nagoya Protocol since its ratification. As a one of the most biodiverse countries of the world, South Africa recognizes the importance of the regulations of the access to genetic resources and the crucial role of the TK and therefore, has put in place the appropriate legislation and policy frameworks. The national project aims to further improve the value chains in South Africa and at the same time to protect the biodiversity by conserving the endangered, harvested species. Objectives in both the global and national project are convergent and fully synergetic. Regarding relevant knowledge / learning from other projects see Part II, A.1-6 further up for easier reference. | Refer to Sections of the UNDP PRODOC mentioned in the responses column. See also Section A.3 (Stakeholders) in Part II further up for easier refernce. Refer to UNDP PRODOC Annexes X-4, X-5 and X-7, as well as to PRODOC Box 2 ‘Key conclusions and highlights from the 2015 Scoping Study on Bioprospecting’, for details. See also Part II, A.1-6 further up for easier reference on ‘Innovativeness, sustainability and potential for scaling up’ |
| End of response |  |  |

#### Comments from GEF Council member Japan

| GEF Council Comments | Responses | Document reference |
| --- | --- | --- |
| GEF Council member Japan, dtd. 16 May, 2016 |  |  |
| [Comment 1] A part of component 1 in this project seems to be addressed to business development activities, while it is unclear how the R&D for commercialization and marketing activities finally ensure better conservation and sustainable use of biological diversity in South Africa. We would like to see more explanation for this point. [Comment 2] JICA and Southern African Development Community (SADC), as a Regional Economic Community comprising 15 member states in South Africa established in 1992, are jointly implementing its first technical cooperation titled “the project for Forest Conservation and Sustainable Management of Forest Resources in Southern Africa (JICA-SADC forest project)” since June 2015. In order to create synergy, close coordination with JICA is highly recommended. | UNDP thanks the Council member from Japan for the constructive comments and suggestions for active collaboration with a JICA project. Response to Comment 1) Overall, the project strategy at CEO Endorsement stage is thoroughly justified and described in the UNDP PRODOC. Both the content and the approach to Outputs, as they had been proposed at PIF stage, were thoroughly discussed among stakeholders during the PPG Inception Workshop. They were subsequently revised / reformulated. As a result, the project strategy strategy was consolidated either around ‘ABS pilots’ or ‘ABS systemic measures’. In addition, the priority species, value-chains, bioprospecting hubs and partnerships were consolidated. To enhance the linkage between project activities with biodiversity conservation various parts of the PRODOC has been enriched with a new content. See especially UNDP PRODOC ‘Strategy’Section, as well as Boxes 9, 10 and 12. Refer otherwise to Part II, A.1, Overview of What Changed since PIF Stage, and Annex B: RESPONSES TO PROJECT REVIEWS 2) Comments at CEO Endorsement Stage further up for a thorough reference on how the strategy for Component 1 was revised at CEO Endorsement stage, as well as for other components, which deal both with R&D and Value Chain Development. Response to Comment 2) Synergies with the the JICA supported project on Forest Conservation and Sustainable Management of Forest Resources in Southern Africa is mentioned in UNDP PRODOC Section IV. RESULTS AND PARTNERSHIPS. See in particular PRODOC Table 7. Synergies, collaboration and partnerships, under the topic “JICA-SADC forest project”. | UNDP PRODOC, Section II. ‘Development Challenge’ and Section III. ‘Strategy’ for the justification. UNDP PRODOC, Subsection ‘Project Areas and Pilots’ (under Section III) and Subsection ‘Bioresources targeted in key Value Chains’ (under Section II) UNDP PRODOC Box 9, Box 10 and Box 12. Part I of this document for the text regarding the revised project Outputs under Component 1 (and others). UNDP PRODOC Section IV. ‘Results and Partnerships’, including PRODOC Table 7 (reproduced further up in section in Part I - A.6 ‘Institutional Arrangement and Coordination’). See also Part II, A.1-6 further up for easier reference on ‘Innovativeness, sustainability and potential for scaling up’ |
| End of response |  |  |

#### Comments from GEF Council member USA

| GEF Council Comments | Responses | Document reference |
| --- | --- | --- |
| GEF Council member USA, dtd. 16 May, 2016 |  |  |
| The United States also requests to re-review the proposal at least four weeks before CEO endorsement: Biodiversity South Africa: Development of Value Chains for Products derived from Genetic Resources in Compliance with the Nagoya Protocol on Access and Benefit Sharing and the National Biodiversity Economy Strategy (UNDP, $6,390,000) GEF ID 9255 The United States requests to re-review this proposal at least four weeks before CEO endorsement to allow UNDP provide additional clarity as to what the global environmental benefits will be generated from funding this proposal. Additionally, we urge the UNDP to consider the following technical comments: | The complete Agency Project Document (UNDP PRODOC) will be available for GEF Council circulation and comments prior to CEO Endorsement during the procedural period of four weeks. UNDP remains available during that period to provide additional explanations on the project, if required. UNDP thanks the Council member from USA for the insightful, thorough and constructive comments. The following specific answers are provided to USA’s comments: | As below. |
| 1. This proposal focuses too much on the commercialization and development genetic resources as opposed to the conservation of biological diversity. We recommend that this proposal be revised and the global environmental benefits be more clearly explained. We note that the Nagoya Protocol is intended to share benefits from utilization of genetic resources in order to . . . "contribute to the conservation of biological diversity and the sustainable use of its components" (Objective 1 of NP). It is not intended to help develop bioprospecting business and markets, nor is the GEF meant to provide funding to help support bioprospecting businesses. Some areas of this proposal seems to expand the Nagoya Protocol’s mandate by applying ABS regimes to commodities, not genetic resources. (e.g., references to food flavorings and oils on page 6, production of honey described in page 14). | Response to Comments 1) During the PPG stage, project Outcomes and Outputs had been critically reviewed. The results are reflected in the UNDP PRODOC. More specifically, both the content and the approach to Outputs, as they had been proposed at PIF stage, were thoroughly discussed among stakeholders during the PPG Inception Workshop. They were subsequently revised / reformulated. A clear focus on conservation and sustainability – in addition to ABS, and as part of it – was not sufficiently strong at PIF stage. This is now addressed. The global environmental benefits expected from the project have been more clarly defined and explained. For easier refererence, lookup Part II, A.1 (Project Description) further up, and under it, the following sub-sections: - Overview of What Changed since PIF Stage - Comments at CEO Endorsement Stage - Sub-section #4) Incremental cost reasoning and expected contributions from the baseline, the GEF TF and co-financing; and - Sub-section #5) Global environmental benefits (GEFTF) UNDP wishes to clarify that this GEF project will not necessarily support ‘bioprospecting businesses or markets’ as such – at least not through an excessive or inadequate focus on the commercialization aspect or on the development genetic resources for the sake of profit-seeking only. Clearly, the project focus is on ABS and this has guided the selection of value chains that constitute project pilots, as well as systemic ABS measures, where capacity building for Nagoya Protocol implementation is on focus. Hence, the approach to value chain strengthening is entirely focused on their contribution to the equitable sharing of benefits and the conservation of biodiversity – and this is not in opposition to the latter. Conservation is part and parcel of the project strategies and activities, as stressed in the content of sections mentioned further up. At the same time, viable economic activities are key in order to generate benefits. This is the entry point to Research & Development carried out in accordance with the definition of utilization of genetic resources of the Nagoya Protocol and the domestic trade aspect related to value chains of bioprospecting, where the GEF increment is meant to make a difference for ABS and conservation. As stated in Strategy Section of the UNDP PRODOC the following Global Environmental Benefits are going to be generated: - “The conservation of biodiversity and the sustainable use of its components, including: - species management measures (Siphonochilus aethiopicus African ginger in particular, given the level of threat) - of habitats that harbour key bioprospecting resources, such as Pelargonium sidoides and Aloe ferox through landscape-level management; - of gene-pools of a variety of species used in bioprospecting value chains among them Devil’s Claw (Harpagophytum procumbens); Kanna (or Kougoed, Sceletium tortuosum) and Cancer Bush (Sutherlandia frutescens) – but also of Honeybush (Cyclopia spp.) - Fair and equitable sharing of the benefits arising from the utilization of genetic resources, including by appropriate access to genetic resources, among them Rooibos (Aspalathus linearis) and the critically endangered African ginger (Siphonochilus aethiopicus)”. Overall, through both pilots and systemic measures, the project will ensure that, whenever an indigenous plant species enters a bioprospecting value chain, the associated TK is respected with derived benefits more equitably shared, and that the commercial/profit-seeking aspect of the value-chains do not end up representing a threat to biodiversity and ecosystems. In addition, the project’s focus is clearly on ABS and genetic resources -- and not on commodities. The PIF mentions food flavorings and oils on its page 6 because it is part of the definition of bioprospecting. Bioresources may have different uses and this needs to be taken into account, when a value chain is analyzed. This does not mean that the project will focus on commodities. In turn, bee products (which includes honey, but also bee wax, propolis and others) had been mentioned on page 14 of the PIF. This was meant only to show the importance of value addition, when it comes to retail value of final products. The focus of the project has been otherwise defined and narrowerd down to include only indigenous plant species. An explicit reference to indigenous plant species was in fact included in the project objective, because it was deemed important to stress it. Bee prodocts were not among the value chains considered under the project. Yet, it should be recognized that certain products, such as Rooibos e.g., may already constitute commodity due to international projection and an increased standardization in production that also seeks export markets. The Rooibos value chain is, by the way, targeted by the project, not with the aim of strengthening it as such, but for ensuring a fair and equitable benefit sharing between the San & Khoi Traditional Council and the South African Rooibos Council. The fact that Rooibos is already (or is bound to become) a global commodity actually makes a compelling case for why issues of ABS would need to be properly addressed through Research and Development for the development of an ABS product in the value chain. This is the project’s entry point in Output 2.4 [renumbered] (on the Rooibos deal). | Part I and II of this document. UNDP PRODOC Section IV. ‘Results and Partnerships’ UNDP PRODOC, Section II ‘Development Challenge’ and III ‘Strategy’ UNDP PRODOC ANNEX X-3. Detailed description of project design: outputs and activities UNDP PRODOC Box 9, Box 10 and Box 12. UNDP PRODOC Section IV. ‘Results and Partnerships’ and under it, PRODOC Table 6. The Project’s Incremental Reasoning |
| 2. The proposal should make clear its definition of indigenous biological/genetic resources and explain why its charaterization of bioprospecting only includes these resources. The Nagoya Protocol covers genetic resources and traditional knowledge associated with genetic resources; it does not distinguish “indigenous biological/genetic resources”. The United States also questions the global environment benefit of “bioprospecting” and therefore the applicability of this proposal to the GEF mandate. | Response to Comment 2) The project’s use of “indigenous” genetic resources is consistent with the Nagoya Protocol’s use of the concept of “country of origin” and minimizes the risk of using foreign/exotic genetic resources not covered by the access and benefit-sharing provisions (Articles 5 and 6) of the Nagoya Protocol. Article 6 (Access to Genetic Resources) of the Nagoya Protocol states that “…access to genetic resources for their utilization shall be subject to the prior informed consent of the Party providing such resources that is the country of origin of such resources…”. And Article 5 (Fair and Equitable Benefit-Sharing) states that “benefits arising from the utilization of genetic resources…shall be shared in a fair and equitable way with the Party providing such resources that is the country of origin of such resources…”. Please refer to the response above for the description of Gloal Environmental Benefits that this project will bring about. | Footnote 3 in the Project Document |
| 3. One of the species included in this proposal is identified as critically endangered and extinct in one region. We recommend that the proposal clarify how the project (and the bioprospecting of the species) will help protect this species instead of leading to overharvesting and further threat to the species. | Response to Comment 3) The baseline analysis for African ginger pointed out to possible solutions for securing the species gene pool through cultivation. ARC will lead those activities through Output 1.1 (on African Ginger cultivation). Baseline studies also showed that almost a quarter (24%) of the natural distributional range for Siphonochilus aethiopicus falls within protected areas, of which more than half of the surface (i.e. some 5,000 ha) are non-consumption protected areas. See in particular PRODOC Annexure, Section IV, PPG STUDY: Plant Distribution Sheet # 1: African Ginger. At the same time, during a PPG consultation process, a SANBI representative indicated the dire need to update the conservation status of African ginger. Furthermore, measures at the landscape level are also foreseen and can be implemented by ARC in Mpumalanga province, where the Center has a presence. Under Output 3.2 (Certification Scheme), the details of Act. #3, includes the following: “Develop an approach to linking Biodiversity Management Plans (BMP) outputs to certification standards requirements […] The purpose would be to take BMP outputs relevant to certification requirements of SANBI. Work on conservation of the African ginger (Siphonochilus aethiopicus) will take precendece over other species and could serve as a pilot. Co-financing for the purpose may be sought, if the need be.” | UNDP PRODOC ANNEX X-2. ‘Project Context & Baseline: ABS frameworks & Species-value-chain interactions’, and under it: - Subsection #2) Conservation and Social Benefits from Species Value-Chain interactions targeted by the Project - Subsection #3) The Context of African Ginger agreement registration and cultivation UNDP PRODOC ANNEX X-3. Detailed description of project design: outputs and activities: Output 1.1) R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner. Output 3.2) A biotrade certification system for South Africa is developed in view of safeguarding biodiversity conservation within bioprospecting value chains |
| 4. We question the appropriateness of including honey as an end product of the value chain development for Moringa oleifera, as honey is a commodity and not a genetic resource. | Response to Comment 4) The value chain for species Moringa oleifera will no longer be pursued under the project. Along with the pursuit of other possible pilots, the work on Moringa oleifera had been indicatively included at PIF stage, but as a possibility. The feasibility of project Outputs has been thoroughly explored during the PPG stage. The inclusion of activities involving a pilot with Moringa oleifera was considered a less effective GEF investment at CEO Endorsement stage, given the amount of funding available, the time needed for producing results and the complexity of partnerships that are required for achieving results. Other sepecies mentioned at PIF stage but no longer prioritised as pilots at CEO Endorsement stage include by the way Hoodia gordonii, Lippia Javanica, Euclea natalensis, Artemisia afra and Myrothamnus flabellifolius. The mention of products containing honey, both at PIF stage and at CEO Endorsement stage, serves only to stress the importance of value addition in the project’s background description, when it comes to retail value of final products. See e.g. PRODOC Box 2. Key conclusions and highlights from the 2015 Scoping Study on Bioprospecting, from where we quote: “The majority of retail products used Aloe ferox, Apis spp. (bee products), Aspalathus spp. (Rooibos) or Pelargonium sidoides as active indigenous ingredient.” Else, no work involving honeybees (Apis spp.) is foreseen at CEO Endorsement stage – or was foreseen at PIF stage. The choice of indigenous plant reources as the core project scope is maintained. | Part II, A.1 (Project Justification), sub-section ‘Overview of What Changed since PIF Stage’, with reference to the ‘Justification for the changes’ with respect to Components 1 and 2. UNDP PRODOC, Section II, Box 2 in topic ‘The Bioprospecting Segment’, under Sub-section ‘Context, issues and global significance’ |
| 5. We question the reference to this proposal targeting capacity building to facilitate ratification and entry into force of the Nagoya in section calls “link to GEF focal area strategy” on page 17. South Africa has already ratified the Nagoya Protocol, which has already entered into force, so it is unclear how this proposal will support that process. | South Africa signed the NP on the 11 May 2011 and ratified it on the 10 January 2013. Else, we refer to the content of Table 12 in the UNDP PRODOC (Descriptive Results from the ABS Tracking Tool, Section 1), where the gaps in ABS systemic measures are clearly highlighted. See also UNDP PRODOC Box 7 (ABS Procedures, Checkpoints and Flowchart), and which complements the above-mentioned table. The way the project will support the process of implementing the Nagoya Protocol in South Africa is cleary considered in the project’s Theory of Change. See in particular PRODOC Figure 9 (Theory of change behind the project strategy: Preconditions for Long-term Impact). | UNDP PRODOC, Annex X-2, Section ‘1) Status Quo of the Implementation of Nagoya Protocol in South Africa’ and more specifically to PRODOC Table 12. Descriptive Results from the ABS Tracking Tool, Section 1. UNDP PRODOC, Sub-Section ‘The Project’s Theory of Change (ToC)’, under Section II. |
| 6. The “global benefits” identified on page 21 are unclear, and do not seem to track with the rest of the proposal. For example, there is only one other reference to harvesting guidelines in the document, so it is unclear is this is a major focus of the proposal. Further, it is not clear how this proposal will reverse “threats to genetic integrity” or “ecosystem symbiosis”. We recommend that these concepts and processes be clarified, defined, and expanded upon before this proposal is accepted. For example, the concept of “ecosystem symbiosis” is not a common one, and we recommend that drafters clearly explain what it is and how their proposal helps protect it. | We refer to the response USA’s to comment #1 further up, where the argument around the global benefits and how they are reflected in the project at CEO Endorsement stage are thoroughly explained. A clear focus on conservation and sustainability – in addition to ABS, and as part of it – was not sufficiently strong at PIF stage. This is now addressed. The global environmental benefits expected from the project have been more clarly defined and explained (see the quotation in response to question 1). Refer to the UNDP PRODOC Annex X-2 for more details on background on the ABS frameworks and the species-value-chain interactions relevant for the project. Refer to the nex boxes added: Box 9, 10 and 12. Refer also to UNDP PRODOC Annex X-3, ‘Component 2: Value Chain Development’ for the description of the work at hand that is relevant to USA’s comment. In fact, the approach which refers to both genetic resources and ecosystem management is best illustrated by PRODOC Figure 10, titled ‘Theory of change behind the project strategy: (a) Conservation aspects and (b) ABS aspects’. All key concepts and processes have been clarified, defined, and expanded upon at CEO Endorsement stage. In terms of project development, the UNDP PRODOC represents a major improvement vis-à-vis the PIF. | UNDP PRODOC Annex X-2 ‘Project Context & Baseline: ABS frameworks & Species-value-chain interactions’ and Annex X-3 ‘Detailed description of project design: Outputs and Activities’ UNDP PRODOC, Sub-Section ‘The Project’s Theory of Change (ToC)’, under Section III. UNDP PRODOC Box 9, Box 10 and Box 12. |
| End of response |  |  |

- Comments at CEO endorsement Stage – NEW SECTION UPDATED ON 6 April 2018

## UNDP GEF Response Matrix

GEF Review CEO Endorsement Request, dated. January, 03rd 2018

| GEF ID: | 9255 |  |  |
| --- | --- | --- | --- |
| Country/Region: | South Africa |  |  |
| Project Title: | Development of Value Chains for Products derived from Genetic Resources in Compliance with the Nagoya Protocol on Access and Benefit Sharing and the National Biodiversity Economy Strategy |  |  |
| GEF Agency: | UNDP | GEF Agency Project ID: | 5686 (UNDP) |
| Type of Trust Fund: | GEF Trust Fund | GEF Focal Area (s): | Biodiversity |
| GEF-6 Focal Area/ LDCF/SCCF Objective (s): |  | BD-3 Program 8; |  |

| Topic | Comments | Responses | Document References |
| --- | --- | --- | --- |
| Project Design and Financing | From GEF Secretariat Review Sheet | Completed on: 29 March 2018 | In the UNDP PRODOC |
| 2. Is the project structure/ design appropriate to achieve the expected outcomes and outputs? | General comment: 1-3-18 Thanks for the submission of the CEO Endorsement. The GEF Secretariat identified a number of issues that are of concern, many of which also relate to the comments made by GEF Council Members at PIF stage. Here are the issues that need to be addressed in the project itself (as appropriate) and in the response matrix. | General Response: UNDP and DEA thank the GEF Secretariat for the comments. They were numbered for the ease reference, counting 18 comments and respective responses, starting after these general comments and responses. This Response Matrix provides the details of how GEF Secretariat’s comments (dated 1-3-18) were addressed. Because of the nature of the comments, more time than usual was needed for providing appropriate responses. The current version of the project documentation that form part of this submission reflect two important aspects: First, all comments the from GEF Secretariat and the GEF Council comments were fully taken into consideration herein. As a consequence, important changes were made to the project’s documentation for addressing these comments. They were addressed one-by-one in the best way possible and a response prepared. Second, the project remains, more than ever, a high priority to South Africa, with senior DEA staff at the Directorate for the Bioprospecting Economy fully behind it and available to provide additional clarifications to the GEF Secretariat, should these be needed. Both UNDP and DEA are determined to make the project eligible and viable. All changes made to the project’s documentation for CEO Endorsement were highlighted vis-a-vis the last submission version (dated 26 October 2017). In addition, a few elements are worth a small note: - Additional co-financing. Since that last PRODOC submission, two new letters of co-financing from the Agricultural Research Council (ARC) and SANBI were received by UNDP and DEA, providing $1,930,455.57 in co-financing. The baseline and co-financing tables were amended accordingly. All changes made to budgets and figures were equally highlighted. - Comments from GEF Sec and GEF Council members made at PIF stage: Thorough responses to those comments had been included in the previous iteration of the CEO Endorsement Request documentation. They were revisited and, where needed, updated, in light of the current changes made to the project’s content in response to GEF Secretariat’s from 03 January 2018. - Process ensued. In order to fully address the GEF Secretariat’s comments, the PPG Team was re-activated, and relevant partners in-country queried. They were engaged in providing adequate responses, SANBI included. Also, additional literature was consulted in order to provide more robust justification. - Where is conservation? A central question posed by the GEF Secretariat in several of its comments has been how the project’s proposed activities relate to conservation and sustainable use of biodiversity on the ground. Similar questions were also posed by STAP and GEF Council members. Project proponents (i.e. DEA, with support from UNDP and the PPG Team) took these questions fully into consideration, with the understanding that the GEF Secretariat did not find sufficient “language connecting these activities with conservation on the ground” or that this language remained too implicit. This is e.g. prominent in GEF Secretariat’s Comment # 1, regarding the following species and corresponding methods of sourcing raw materials (quoting): “Aloe [ferox] (plantations), Roibos, African ginger (cultivation and agroprocesing), honeybush (farming) and Pelargonium spp. (harvesting).” Proponents also felt that this link was perhaps ‘too implicit’ in the PIF and that the PPG process should serve to strengthen it. However, as the current round of reviews served as an opportunity to make it even more explicit. Extensive literature and various subject matter experts in South Africa were consulted during the PPG process. Especially now with the current round of revisions to the PRODOC for CEO Endorsement, proponents made sure to make this link even more explicit. - Wider benefit sharing? Furthermore, proponents also wished to strengthen the relationship between activities and direct and indirect benefits of conservation to communities, including how these translate into social benefits, which communities equally expect to obtain from value chain strengthening, as well as aligned with national policies. In preparing these responses, UNDP consulted with DEA and partners and discussed the implications of addressing the comments in the way they are proposed herein. DEA’s re-endorsement of the content of the current re-submission of the PRODOC for CEO Endorsement was obtained on 26 March 2018. | Revised PRODOC with highlights. Revised CEO Endorsement Request with highlights. |
|  | Comment #1: 1. There is a disconnect between the proposed activities and the conservation and sustainable use of biodiversity. This is particularly acute for the pilot species: Aloe (plantations), Roibos, African ginger (cultivation and agroprocesing), honeybush (farming) and Pelargonium spp. (harvesting). Please explain (in plain English) HOW the proposed activities on these species relate to the conservation of biodiversity on the ground. While the benefits for those involved in the different parts of the project can be seen, there is very little language connecting these activities with conservation on the ground. Figure 10 of the CEO Endorsement Request (p.13) is pointing in the right direction but difficult to visualize. The relationship between activities and conservation needs to be made explicit. The GEF suggest preparing a Table with the columns like: Species name (vernacular and scientific), proposed R&D interventions, status/proposed marketing and commercialization activities, conservation impact on the ground (Global Environmental Benefits). | Response to Comment #1: It is important to note that compliance with South Africa’s Bioprospecting, Access and Benefit Sharing regulations (BABS) can be a powerful tool for promoting conservation and sustainable use of biodiversity – and not just a tool for ABS compliance. Furthermore, all species / products on focus will need to comply with BABS through the permitting system. In the BABS’s regulated relationships between providers and users of genetic resources caters for the adherence to the permit’s conditions, and thereafter, with the permit’s issuance the conditions imply that key trade information that has a bearing for sustainability has been disclosed according to the conditions of the permit. Regardless of whether business information relating to the permits will remain confidential or not, applicants need to disclose to DEA key information with a bearing for biodiversity management. This includes for example information on traded volumes, trade routes, resource origin, product development and beneficiation. And because BABS is hierarchically under the National Environmental Management Biodiversity Act (NEMBA), compliance with BABS implies also compliance with NEMBA and due diligence is necessarily carried out by government as applicable. This is why it may be said that BABS compliance (i.e. ABS or Nagoya Protocol compliance) is a powerful tool for promoting conservation and sustainable use of biodiversity. BABS compliance will be required of all value chains relevant for the project (including the relevant species-value chains highlighted: Aloe ferox, Roibos, African ginger, Honeybush and Pelargonium spp. In addition, other tools for conservation, sustainable use and ABS will come into play in the project, and they are, or can potentially be within a given context, rather powerful tools for conservation. Their application was made explicit in the relevant activities. - Biodiversity Management Plans (BMP) for species (often BMP-S), but which by extension also applies to landscapes such as those for Pelargonium, Honeybush, - Develop best management practices (BMPs) for cultivation and harvesting planning (testing approaches, techniques and methodologies) for each species - Implement pre-existing Guidelines for the Sustainable Harvesting of Wild Honeybush - South African Medicines Control Council's (MCCZA) Good Agricultural and Collection Practices (GACP). - The Biotrade Certification System for South Africa (to be developed / organized by the project) in connection with Component 3. At the level of ‘activities’ and with reference to the above-listed ‘tools’, a simple screening of activities’ budgets yielded the following table regarding explicit and implicit linkages: Linkages with activities and the following elements (EXPLICIT unless when otherwise indicated); Project budget ($). Conservation / sustainable use; 305,000. Sustainable use; 253,000. Conservation / sustainable use / ABS compliance; 900,000. ABS compliance; 130,000. ABS compliance / scale up; 437,600. ABS compliance / Sustainable use; 167,000. IMPLICIT ABS compliance / Sustainable use; 1,037,000. IMPLICIT Conservation / sustainable use; 20,000. Grand Total; 3,249,600. In other words, the activity screening found that at least 30% of the GEF grant will explicitly support the implementation of tools that focus on conservation, sustainable use or ABS compliance and up to 50% if implicit cases are also considered. Furthermore, we draw the attention to several passages in the PRODOC where: [a] either the linkage between the project’s activities (or core proposals) and conservation / sustainable use was already part of the project strategy in the previous iteration; or [b] the linkage has been strengthened in the current iteration. The linkages and their reflection in the PRODOC are mentioned below: On the PRODOC cover page, where it reads: “This project will […] address both conservation and Access Benefit Sharing (ABS) issues linked to the development of different bioprospecting value chains, while also helping key players overcome related barriers and challenges.” [a] In Figure number 10 from the PRODOC, and which had also been included in the CEO Endorsement Request file with the same number. Indeed, it provided a theoretical framework for the Project Strategy. However, the information was too condensed for providing a meaningful explanation. Additional explanation regarding Figure 10 is now included in the PRODOC and in the CEO Endorsement Request. [a, b] The content of PRODOC Annex X-2 has been expanded, better edited and illustrated with at least three maps added in response to the current comments. [b] The descriptions of outputs for the relevant species has been significantly strengthened. This is more specifically presented in the responses further down in the responses to Comments #2, #3. [b] The title of Annex X-2.2 changed to: “Background for Conservation Benefits for Species targeted by the Project, plus ABS Compliance Angle”. [b] More specifically on the above-mentioned annex, the suggestion from the GEF Secretariat was accepted. PRODOC Table 13. Species characteristics, conservation status, value chain development and research facts already included basic information on the species. It was now expanded to include “Conservation Benefits” and “Social Benefits” in the current PRODOC iteration [a, b] Hence, at a closer look, we believe that the GEF Secretariat will be able to find several linkages between the proposed activities and the conservation and sustainable use of biodiversity could be found, rather than ‘a disconnect’. | Added to current iteration of PRODOC: Text that precedes and follows Figure number 10 from the PRODOC and CEO Endorsement Request are now added. Changes made, and content added to current iteration of PRODOC (*also included in the CEO Endorsement Request): PRODOC Annex X-2.2, Table 13. Species characteristics, conservation status, value chain development and research facts Box 6. New Sustainable Practices’ Adoption, Uptake and Spread + (updated) Linkages In PRODOC, Annex X-2.2, Plant Species Distribution Sheets #1, 2 and 3. |
|  | Comment #2. 2. Output 1.1. The clinical trials of African Ginger (I & II) must be based on R&D by a pharma company. Please state what active ingredients and applications are being sought out for this species? Who is to benefit from the applications if successful? | Response to Comment #2: The Council for Scientific and Industrial Research (CSIR) is proposed as the Responsible Party assigned the direct implementation of activities under Output 1.1. CSIR will sub-contract the specific activity to a specialized service provider. CSIR has already shortlisted a handful of potential companies and the procurement process for selection is on-going. A potential candidate service provider for carrying out African Ginger clinical trials, is a Cape Town based medium-sized company with over twenty years of experience in anti-allergic inflammatory agents, as well as a track record in validation and registration of a complementary medicine. For clarification: The aim is not of developing a “blockbuster drug” during the lifetime of this project, but rather to take the associated TK on African Ginger to “another level” through the development of a simple and safe complementary medicine product to treat allergies and inflammation. We stress that the Traditional Healers Committee (THC) are recognized as the TK holders for the use of African ginger against allergies and related illnesses. The plant has been used over generations by traditional communities and it has proven its safety and efficacy as a remedy. In direct response to a question from the GEF Secretariat on the medicinal application, we refer to the following sections which were revised to strengthen the response: - PRODOC Annex X-2.3 (The Context of African Ginger agreement registration and cultivation); and - PRODOC Annex X-3, Section on Component 1, sub-section on Output 1.1, whose title already provided the explanation: “Output 1.1) R&D barriers linked to clinical studies and registration of African Ginger (Siphonochilus aethiopicus) as a bioresource to treat inflammatory and allergic diseases are systematically overcome in an ABS-compliant manner.” We conclude this response by strengthening the argument on three important aspects: (1) Why are clinical trials actually needed; (2) Providing more information on the process proposed and background; and (3) What GEF funds will add to the process The content that follows regarding the above three points is now included in the UNDP PRODOC, Annex X-2.3 (The Context of African Ginger agreement registration and cultivation). (1) Why are clinical trials actually needed: Registering any complementary medicine – also termed herbal medicinal product (HMP) -- by the South African Medicines Control Council (MCCZA) normally requires clinical data on efficacy vis-à-vis the stated health enhancement claims. When the HMP is to register as a ‘low risk’ HMP, an abridged process of registration that dispenses clinical evidence is possible. However, in such cases, the applicant would only be able to label it as being effective for the “relief of minor symptoms” and “not related to a disease or disorder” Proving African ginger’s efficacy for treating asthma and allergies through clinical trials is currently the only major barrier to be overcome for product registration. It is in fact CSIR’s strategic choice for maximizing the potential benefits from years of R&D and a standing partnership with THC. (2) Process proposed and background: CSIR will be overseeing the work of clinical trials and co-financing it. Hence, the CSIR will be sharing the R&D risks with the GEF, in view of generating, through partnerships, tangible global biodiversity benefits. Given the past results from R&D, partners believe that the prospects of developing a viable commercial product are promising, in particular in the form of a HMP. The work of overseeing the clinical trials will be done in collaboration with the THC. Previously, CSIR and the THC had entered into several agreements and the CSIR has in fact conducted extensive R&D activities on African ginger. This led to the identification of several biochemical metabolites, expressed in this indigenous plant species, substances that are responsible for the anti-asthmatic and anti-inflammatory properties. Genetic fingerprinting of the species was undertaken through previous R&D to aid quality assurance and to prevent possible confusion with related species. The mentioned research conducted scientific studies and demonstrated the beneficial properties of the plant extract in the improvement of the symptomatology associated with allergic and inflammatory diseases. The research also provided scientific evidence substantiating its traditional use and potential inclusion in complementary medicinal products. The intellectual property was produced through the research and development and later protected through a patent system as a potential agent for the treatment of inflammatory and allergic diseases such as asthma. (3) What GEF funds will add to the process: On the backdrop of the above-described robust R&D baseline, the focused contribution of the GEF project is expected to facilitate three important shifts: First, the CSIR and the THC will reach a more comprehensive benefit sharing agreement regarding African ginger and the proposed use. They will do that in the framework of more current legislation, namely the South African legislation, National Environmental Management: Biodiversity Act 2004, Bioprospecting, Access and Benefit Sharing, 2008. This, in and on itself, represents a tangible ABS compliance benefit. Second, the Southern African variants of the species Siphonochilus aethiopicus (African ginger), will be part of a more a formal and nationally branded value chain, aimed at sustainably producing and trading a commercially viable HMP, with all due controls as required by national regulations the licensing and registration of such products in South Africa. In due course, this may lead to new partnerships, that will build on the hopefully successful outcome of clinical trials and product registration. The GEF project will help overcome specific barriers to that effect. The benefit that may be generated will likely be much more significant. Thirdly, the above aspect is linked to the species conservation status and this is important in the context of a GEF project. Currently, African ginger is already being used and traded in South Africa within the informal market for traditional medicines. In spite of the best intentions by organizations such as the THC, they acknowledged (e.g. in PPG event) that, without the typical ‘surveillance’ and ‘controls’ that the product would be imposed in compliance / formal markets, the high demand for the plant’s roots in home-made remedies has effectively resulted in the plant being red-listed as Critically Endangered where it occurs in Southern Africa. The Healer’s Council would like to ‘turn this stark reality around’, working with DEA, the scientific community through CSIR and possibly ARC, when it comes to extension services for cultivation. The above listed actions, are also supported by the GEF project through Output 3.2, as a way to address the threats to the species Siphonochilus aethiopicus. More specifically, it can be expected that, along with the product registration at the MCCZA, other requirements on sustainability at the landscape level also apply, namely of Good Agricultural and Collection Practices (GACP). The applicable MCCZA 2016 Guidelines on HMPs state the following: “Compliance with Good Manufacturing Practice (GMP), Good Laboratory Practice (GLP) and Good Agricultural and Collection Practices (GACP). All manufacturers of complementary medicines shall comply with all relevant aspects of Good Manufacturing Practice as outlined in the latest version of the MCC’s “Guide to Good Manufacturing Practice for Medicines in South Africa” and Good Laboratory Practice, as well as the WHO Guidelines on Good Agricultural and Collection Practices (GACP) for Medicinal Plants, if applicable. Any alternative standards must be specified, referenced and justified.” The above creates an ‘ABS-conservation lever’ for mainstreaming sustainable practices into the management of Siphonochilus aethiopicus within its South African habitats – as well as the envisaged transition to cultivation, which according to DEA and SANBI specialists, is what is needed for addressing threats. CSIR will develop partnerships to strengthen these aspects during implementation. Finally, Additional and R&D – not related to clinical trials – also needs to be undertaken in order to establish thresholds for sustainable harvesting and further pathways towards sustainable cultivation and for refining the mechanism that will ensure the sustainable supply of the species to the industry. | Changes made to: PRODOC, Annex X-2.3 (The Context of African Ginger agreement registration and cultivation) Added to current iteration of PRODOC (*also included in the CEO Endorsement Request): * Box (new) Win-Win A promising value chain with African Ginger and a gateway to sustainable use *In PRODOC, Annex X-2.2, Plant Species Distribution Sheet #1. |
|  | Comment #3. 3. Output 1.2. The proposed "Northern Cape Bioprospecting RDI Hub (Research, Development and Innovation Hub for bioproducts) is an expensive proposition. What is the GEF budget for this activity? What is the Government's secured (confirmed) investment for this RDI Hub? Based on the description of the Hub in the Project Document, this is mainly an agriculture facility (as in agriculture output) to be developed and run by the Agriculture Research Center (ARC). | Response to Comment #3. Proponents believe that there could have been a slight misunderstanding on the purpose of GEF support for this output and on the baseline that will underpin the GEF investment. As it is, the Department of Rural Development and Land Reform has been implementing an Agri-Parks program across the Northern Cape. The current facility in Upington, which is proposed to house the Hub, had been used to date to replicate such an initiative. This is why the current hub has a predominantly production-focussed mandate. It was initially envisaged that this mandate would expand into a stronger commercial and marketing mandate, ideally forming the basis for a bio-prospecting cooperative. The advent of the GEF project has accelerated this process, but more importantly, it helped gear the development in another direction – namely of supporting the Hub not only to replicate the Agri-Parks initiative, but mostly to have a much stronger angle on bioprospecting and R&D. It is not correct that the Hub was envisaged mainly an agriculture facility. Any text that could cast doubt on it has now been amended. The text in the above three paragraphs have been included in the PRODOC, Annex X-3, sub-section on Output 1.2. As a direct response to the comment, we include Box 10 into the PRODOC in view of strengthening the justification for the Output, covering three important aspects: (1) A strong baseline for the Northern Cape Bioprospecting hub; (2) What the GEF project will help realize in the Northern Cape regarding R&D; and (3) A token of government commitment The content that follows regarding the above three points is now included in the UNDP PRODOC, Annex X-2.4 (The Context of the Bioprospecting in Northern Cape Province): (1) A strong baseline supports the "Northern Cape Bioprospecting RDI Hub regarding ‘Research, Development and Innovation Hub in bioproducts’. The GEF investment is made in a government-owned facility. In the baseline, this facility functions mostly as an ‘agronomic’ small center, with some R&D activities being implemented, primarily focused on seeds improvement. The facility simply lacks the mandate, the appropriate equipment, the specialized human resources and access to technical capacity embedded in a strong parent institution. Most importantly, the center lacks the ability to network and to function as a hub that can produce results in the field of bioprospecting. (2) What the GEF project will help realize in the Northern Cape regarding R&D. With the investment by both GEF and government, the facility will become much more focused on R&D linked to plants’ genetic resources. It is expected to prime innovation and service provision to a surrounding community of both users and providers of genetic resources and with. All of these elements will be boosted for focusing on R&D. It will represent a ‘qualitative leap forward’ for the current Upington facility, namely to be transformed into a new ‘Research, Development and Innovation (RDI) Hub for Bioproducts in the Northern Cape’. (3) A token of government commitment. Regarding government the co-financing, it should be noted that the ARC has committed to $1,415,110.96 in co-financing and DEA has committed $30,387,060.53. Output 1.2 has indeed a budget of $900K. Whether it is ‘expensive’ or ‘a worthwhile investment’ in light of the project strategy is something that needs to be put into perspective in the current iteration of the PRODOC. UNDP and DEA call the attention to the fact that, in the description of Output 1.2 (PRODOC Annex X-3, under Component 1), there are several activities proposed, which shows that the proposed hub is not another agriculture facility to be ran by ARC, nor a mere agricultural output undertaking, but rather a novel RDI hub. The following activities are highlighted as most relevant: - Provide a centrally-located (Upington) and accessible centre of excellence that would support community projects in production of priority species and related bio-products, - Develop a 3-year research, development and innovation plan for the Hub to implement, - Provide a repository for genetic material for priority species in the Northern Cape, - Propagate priority species and related seedlings for sale/supply for community project cultivation, - Investigate appropriate cultivation practices that are in synergy with current wild-harvesting practices, and that conserve genetic resources and improve production – with the support of appropriate resource assessment initiatives, - Provide know-how to communities in the form of cultivation training, harvesting plans, traceability systems, quality control, phyto-sanitary systems and other extension services where necessary, - Provide agro-processing support services, especially with respect to product development and quality control, - Supply material for clinical trials where required, - Establish a commercial and marketing support service, that is aligned to the R&D mandate (e.g. establishment of a certification system). In hope that the GEF will find the arguments convincing, UNDP and DEA remain available for further clarifications. | Changes made to: PRODOC, Annex X-2.4 (The Context of the Bioprospecting in Northern Cape Province). Added to current iteration of PRODOC (*also included in the CEO Endorsement Request): *Box (new) Background: The value added of a RDI hub in the Northern Cape PRODOC Annex X-3, Section on Component 1, sub-section on Output 1.2 |
|  | Comment #4. 4. Output 2.1. The ultimate objective of this output is not clear. It is a mixed bag of activities. What are the tangible and measurable results on the ground to be funded by this output? This plan is traded in bulk under several brands. How is this output going to change the current practices? What are the suppliers and buyers in the proposed ABS agreements on Pelargonium sidoides? | Response to Comment #4. The content that follows is now included in the UNDP PRODOC in Annex X-2.5. Additional background to Output 2.1 (added to PRODOC Annex X-2, under Component 2) The ultimate objective of output 2.1 is to address threats to the species Pelargonium sidoides, more specifically, and biodiversity more generally, within the ‘Pelargonium landscape’. Preparing and implementing a new Biodiversity Management Plan (BMP) for the Pelargonium landscape is an important means to it. Harvesting of wild populations of P. sidoides is fuelled by demand from the pharmaceutical industry, both locally and internationally, and for manufacturing herbal medicinal products, in which the rootstocks (or lignotubers) are used in different preparations. The raw materials for the industry are mainly obtained from wild populations. Cultivation faces challenges, namely that it takes several years for plants to generate mature tubers with the desirable commercial characteristics. Additionally, P. sidoides is also used in the traditional remedies, but the value chains that supply the informal traditional medicine market are not well studied. More equitable terms of trade for harvesters, including through industry compliance with bioprospecting permit conditions as required by South Africa’s Bioprospecting, Access and Benefit Sharing regulations (BABS), are also an equally important aspect of Output 2.1, not only as way of sharing benefits in an inclusive and socially ethical way, but also as a means of advancing towards sustainability in the harvesting practices and greater supply security, as follows: Once permits are issued and permit conditions are adhered to, trade information, including traded volumes, trade routes, resource origin, product development and beneficiation will become available. Facilitating BABS compliance is part and parcel of implementing the BMP. Understanding the stakes at the landscape level with respect to the supplies of P. sidoides’ raw materials will also enable value chain stakeholders to work together to seek solutions for common problems regarding supplies perhaps also price. These stakes are illustrated in a new Figure, now included in the PRODOC: Figure (new) Brief History and stark reality of the P. sidoides supply chain. - See further down. By citing technical sources, the 2011 Official Biodiversity Management Plan for Pelargonium Sidoides indicates that, currently, the greatest threat to the species, is not the harvesting of its rootstocks (or lignotubers), but rather habitat transformation and degradation. Historically, the loss of populations due to changes in land uses, and hence habitat transformation as a result of urban development and agriculture, has occurred in most of the sites where P. sidoides once occurred (e.g. in Gauteng Province as well as at many sites in the Free State). However, unless it is sustainably managed within a landscape level approach, localized overharvesting has a detrimental effect on the species. In such local settings, the threat to the species has been fueled by a high and cumulative demand for plant raw material, coupled with a situation where the prices practiced at the landscape level have remained low for several years. Consequently, the value captured by harvesters has also remained low. It is assumed that the harvest is unsustainable because harvesters claim that plant resources are becoming increasingly rare across the landscape, requiring their harvesting efforts to be intensified. In fact, within a fairly large landscape, which is the case of that of P. sidoides – resource rents tend to be low. The value chain in question will display dynamics that are typical of nature-based economies, within which economic actors seek to maximize their profits through scale and by increasing yields. From a conservation point of view, these dynamics result in threats to the resource stock, and ultimately, to the extinction of the species. The project will address these challenges by assisting DEA, DEDEAT and DESTEA (entities that constitute the Pelargonium Working Group) in implementing the Pelargonium S. Biodiversity Management Plan. Above all, a much more effective and sustainable administration of the Pelargonium Working Group (PWG) with clear standards for the management of Pelargonium landscapes. The updated BMP, will lead to the implementation of sustainable management practices for wild populations of Pelargonium sidoides. For the stated objectives of the BMP are referred to PRODOC Annex X-2.5. --- In view of strengthening the justification for the Output, three important aspects are covered: (1) Additional background on suppliers and buyers in the proposed ABS agreements on Pelargonium sidoides (2) Tangible and measurable results on the ground (3) How GEF support will help change current practices The content that follows elaborates on the above three points and it is now included in the UNDP PRODOC, Annex X-3, under Component 2, Output 2.1 and placed in a new Box: (1) Additional background on suppliers and buyers in the proposed ABS agreements on Pelargonium sidoides According to 2011 Official Biodiversity Management Plan for Pelargonium Sidoides wild harvesting appears to be limited to the Free State, Eastern Cape and Lesotho, a large part of its range is currently not affected by harvest. The majority of P. sidoides plants occur on private, communal or state land that falls outside of formal protected areas. In order the understand the stakes for sustainability in the Pelargonium value chain, it is important to understand that the Pelargonium landscape is rather large -- it extends across an area of approximately 342,048 km2 covering much of Gauteng, North West, Mpumalanga, Free State, Eastern and Western Cape Province — even though, in South Africa, active harvesting takes place mostly in Eastern Cape and Free State. The core problem addressed by the project is that, for several years, the relationships between users and providers of the genetic resources within the Pelargonium landscape have not led to better harvesting practices that would both secure supplies and result in providers capturing a slightly better share of the total value across the value chain. With market forces that were left ‘unchecked’ for years—they were not moderated by regulation or by ABS-compliant biotrade—supply and demand for P. sidoides raw materials have simply responded to typical economic dynamics related to plant extractivism, more specifically (also discussed in Annex X-6): - Low economic returns from wild harvesting of useful plants across landscapes functions in the same way as ‘resource mining’ -- similar to the dynamics in the non-renewable natural resource sectors - Economic actors will tend to maximize the resource rents over time until the depletion of resource stocks, leading thereby to a decline in supplies, and ultimately also in stocks. - In the decline phase, the supply curve becomes inelastic – i.e. it does not respond adequately to price and demand feedbacks. These patterns have contributed to rather unequal terms of trade, and ultimately to unsustainable practices within the Pelargonium sidoides value chain. We herein refer to scientific publications by Jaci van Niekerk and Rachel Wynberg, who researched extensively about the value chain for Pelargonium sidoides through the Environmental Evaluation Unit at the University of Cape Town – in particular the ‘supply’ aspect. Based on their work, the supply chain, the players and the stakes are now illustrated in the PRODOC: see Figure 16 (new) Brief History and stark reality of the P. sidoides supply chain (also included further down). The researchers analysed the value chain drew a few conclusions that are relevant to the Project – as follows: (i) A ‘monopolistic’ behavior by users of P. sidoides genetic resources. This threatens in different ways the livelihood of harvesters (the suppliers) and creates disincentives to conservation at the landscape level, as well as to local value-addition. Harvesters have often low levels of education and are not well organized. The next link in the supply chain are small suppliers, who depend heavily on much larger buyers. The user’s behavior is also hierarchical, with strong managerial control and vertical integration. Harvesters remain vulnerable and they are unable to negotiate better prices. (ii) A ‘captive’ value chain. In order to help harvesters break out the “trap” and become protagonists in the implementation of the BMP for the Pelargonium Landscape, it is not enough to enter into ABS deals with a single community, as it had been the case in the past. The resource is widespread and a more comprehensive solution, which may be termed ‘sector-wide’ benefit-sharing agreement should be considered. The proposed ABS agreement between users and providers of P. sidoides is expected to improve the terms of trade of suppliers and provide them with a stronger bargaining power and improved market access. BABS compliance will also need to come with the strengthening of sustainability in harvesting methods. So, the project will cater for that. However, Niekerk and Wynberg also mentioned other barriers that are part of the “poverty trap” in which several harvesters find themselves into, including the lack of infrastructure, as well as insecure land tenure systems, limited access to capital, credit and technology. (2) Tangible and measurable results on the ground - The Pelargonium landscapes which shows that 60% of the Landscape is within Eastern Cape Province, will have improved management. Economic stakeholders will receive additional support for sustainability compliance. - The Pelargonium Working Group (PWG) will receive adequate support to aspects of sustainability and collaborative ways of working that are currently difficult for them. - The BMP will have with clear standards for this management. The above will be independently verified by the project’s evaluation exercise. (3) How GEF support will help change current practices - E.g. the Management approach by collective parties within the landscapes will be duly scrutinized, in particular with respect to the conservation and sustainable use outcomes of their activities and the applicable impacts – whether positive or negative – and pertaining to land use and biodiversity primarily, but also with respect to a suite of socio-environmental standards. This applies in particular to e.g. local cooperatives that may access the GEF grant. - Compliance will be subject to audit, either by DEA (in connection with enforcement efforts relating to BABS and BMP itself) or by a third Party. - The initiative will pilot the certification scheme foreseen under Output 3.2. - Stakeholders will receive expert advice, e.g. from SANBI on the certification. - To the extent that the plant materials sold will be used as Herbal Medicinal Products (HMP), applicable Guidelines from the South African Medicines Control Council (MCCZA), as of 2016, will also come into play. Those are namely: - Good Agricultural and Collection Practices (GACP) - Good Laboratory Practice (GLP) – in the case of primary processing of the plant drug in situ; and - Compliance with Good Manufacturing Practice (GMP) | Added to current iteration of PRODOC (*also included in the CEO Endorsement Request) *In PRODOC, Annex X-2.2, Plant Species Distribution Sheet #2. In PRODOC, Annex X-2.5 [The Context of Pelargonium Management Plan] and PRODOC Annex X-3, under Component 2, Output 2.1 [The implementation of the Pelargonium Biodiversity Management Plan (BMP) is supported in close collaboration between the Pelargonium Working Group, community businesses and CSO stakeholders]. Additions include: - Text from this response - * Box (new) Additional background on Sustainable Production and Primary Handling of Pelargonium sidoides. - Figure (new) Brief History and stark reality of the P. sidoides supply chain |
|  | Comment #5. 5. Output 2.2. Most of the proposed activities are in line with supporting an agri-business of a plant that is planted extensively across South Africa and traded worldwide (Aloe spp.). What is the R&D + value chain proposition of this output? There is also the proposition of another bioprospecting Hub (in the Eastern Cape), making the project more expensive and increasing the chances of overpromising and under- delivering. | Response to Comment #5. There seems to be a misunderstanding on the part of the GEF regarding what species of Aloe spp. that is on focus regarding the value chain work under Output 2.2. The output is not at all concerned with the genus Aloe spp. more broadly, which includes dozens of different species, and which from a ‘commodities classification’ point of view may be “bundled” together without much differentiation. Rather, output 2.2 has a clear focus on a specific species that is indigenous to South Africa (Aloe ferox), which grows wild in the southern regions of the country. Refer to Plant Distribution Sheet #3 (in PRODOC Annex ) now included herein. The output’s focus is also on a local community, located in the area where the plant grows, a community that has traditionally used Aloe ferox for generations and currently derives a livelihood from harvesting it within legally defined communal lands. Like several other communities in that part of South Africa, Tyefu Community faces challenges in terms of deriving value and benefit from a local plant which is beginning to experience increased market demand — namely the challenge making the activity of providing bio resources sustainable. Still with the aim of justifying the activity and clarifying a possible confusion, we draw the attention to the fact that Aloe ferox is quite different genetically and in terms of its useful properties from Aloe vera. The latter was indeed domesticated in various parts of the world, in historical times (meaning that country of origin may be difficult to determine from an ABS point of view), and noting that Aloe vera became more recently a major global commodity present in a wide variety of products (from mattresses to nappies, to soothing creams and even in neutraceutical drinks as pure gel). This is not the case for Aloe ferox. In turn, Aloe ferox extract is still by-and-large a niche product, with a restricted market, albeit developing, but a market that cannot grow too much further, unless issues of supply, ABS compliance and sustainability can be addressed — not to mention the issue of gender equity across the value chain, as gender roles and patterns get established. While the aim is not of developing an agribusiness undertaking, the value chain can never be sustainable and aim for export based solely on local wild harvesting — or wider scale overharvesting will be an inevitable outcome. In addition, many of the potentially useful properties of Aloe ferox are still to be explored, and some yet to be discovered. It is correct that the output’s proposal includes what had been termed ‘a second R&D hub’, but the level of ambition vis-a-vis the first is much more modest and should be better explained. An element of R&D has been identified as a need, by both government and the local community trust in Tyefu. Although full ‘product development’ is obviously beyond the level of ambition for the output, there is another more pressing need from the community, which the proposed GEF investment can address through a more basic type of R&D: namely to develop a process aimed at stabilizing the Aloe ferox sap before shipping. As it is, the process being currently utilized could be optimised, while the dry climate in the highlands of Eastern Cape create ideal conditions for the plant’s sap to crystallize. Currently, there are gaps in knowledge that could be explored through local experimentation and inputs from technical assistance, if only a small facility can be set up near where raw materials are collected. The core biodiversity management problem that output 2.2 addresses is linked with local overharvesting. As the demand for Aloe ferox products increases, a transition to cultivation appears as the best option for securing supplies and protecting the species gene pool in the natural landscape. Overall, the strategy behind the output comes from the need for demonstrating how the Aloe ferox value chain can be optimally developed. Yet, it was not conceived as an agribusiness enterprise, but targeting the generation of several public goods. The landscapes in Eastern Cape resemble nothing of a typical commodity production landscape. Herein UNDP and DEA attempted to explain the main issues of concern that the project is focusing on, while clarifying the distinction between the value chain on focus and that of a fully-fledged commodity. The background information that provides this justification is described in the PRODOC Annex X-2.6, titled “The Context of Aloe ferox harvesting.” The background information provided therein should be sufficient to justify why the intervention is needed and why it fits GEF priorities. Although output 2.2 has been assigned an important share of the project’s budget, the amount is balanced vis-a-vis ambitions, scope and needs. | Added to current iteration of PRODOC (*also included in the CEO Endorsement Request) In PRODOC, Annex X-2.2, *Plant Species Distribution Sheet #3 |
|  | Comment #6. 6. Output 2.3. An output closely associated to a SGP project (here on assistance to farmers to purchase or leasing land and start-up cost for suitable farming projects) with very little to no relationship with the Nagoya Protocol. Suggest removing. | Response to Comment #6. The reference to SGP has been removed from the PRODOC. A more suitable grant-making mechanism will be selected during the procedural Local Project Appraisal Meeting, to be held once the PRODOC is CEO Endorsed by UNDP and DEA. This will follow the UNDP Micro-Capital Grants Policy. The reference to land leasing and purchasing was removed from the PRODOC and CEO End Request, following GEF’s suggestion. | Mention to SGP has been removed from several passages in the PRODOC and in the CEO Endorsement Request. All changes marked. |
|  | Comment #7. 7. Output 2.4. Another output in the realm of Agriculture with very little to no relation to the Nagoya Protocol. This should be removed or restructured (if indeed possible). Comment #8. 8. Output 2.5. Another agricultural output (extension services, training and capacity building). This should be removed or restructured (if indeed is possible). Comment #9. 9. Outputs 2.3, 2.4 and 2.5 are closely aligned with agricultural development and loosely related to the objective of this project in support of the implementation of the Nagoya Protocol. Please provide a clear explanation of the relationship with the NP or remove from the project. | Outputs 2.4 and 2.5 have now been dropped as per the GEF Sec suggestion. Output 2.3 has not been dropped, the following paragraphs were added to PRODOC to show how the Output is linked to the Nagoya Protocol: “South Africa’s Bioprospecting, Access and Benefit Sharing regulations (BABS) regulates relationships between providers and users of genetic resources and caters for the adherence to the ABS permit’s conditions. It ensures that these relationships are Nagoya Protocol compliant, whether it they are restricted to national stakeholders or international relations between Parties to the Protocol. For the Output’s beneficiaries, across the honeybush landscapes, a key condition for applying and receiving grants will be compliance with BABS regulations.” See further explainations under the response to STAP Comment, Topic #3. . | PRODOC and CEO Endorsement Request: Various small corrections made to remove reference to now dropped outputs 2.4 and 2.5 Added to current iteration of PRODOC Annex X-3, Section on Component 2, sub-section on Output 2.3: |
|  | Comment #10. 10. Output 2.6. This is all about the TK Levy Mechanism. Please provide additional information regarding the way the Government of South Africa plants to implement this TK Levy Mechanism (whatever its structure) when there is a massive world market on Roibos (another commodity). is this Levy a tax-like instrument on exports? | Response to Comment #10. All reference to a levy, which had been erroneously mentioned in the PRODOC, are now removed. | Mention of a TK levy has been removed from several passages in the PRODOC and in the CEO Endorsement Request. All changes marked. |
|  | Comment #11. 11. Output 3.1. Appears to be a disconnect between Activity 1 (Bio- Cultural Protocols) and the rest (on IK recorders). Please clarify the relationship. What are the proposed 25 species? That may help narrow down the number of communities to be visited (currently 10 out of 826 = 1.2%). | Response to Comment #11. We highlight the following additions to the PRODOC in response to the comment: Activity 1: Bio-Cultural protocols are a mechanism that facilitates PIC and legitimate access to communities and puts in place community protocols for users to access the Genetic resource, knowledge and in some cases both. Activity 2: The proposed 25 species are the species identified by the Lab participants during the DEA-led initiative ‘Operation Phakisa’ as the top species that are currently regarded as priority species for bioprospecting and for which the knowledge holders/ communities are not known and should be identified. This is how the value chain will be strengthened. Access to the community: - Bio Cultural Protocol as a gate keeper for access - Resources identification and documentation (This is the work of the recorders who need to adhere to the Bio Cultural Protocol prior to documenting) (NRS) - Adherence to legal prescripts e.g.: Non-Disclosure Agreements, Prior Informed Consent (PIC), Benefit Sharing Agreements (ABS), Material Transfer Agreements (MTA), Information Transfer Agreements, etc. - This is the first level of to access The Resource (Genetic, Knowledge and /or both) The above was added to the justification of Output 3.1. in Box (new) Additional background on Bio- Cultural Protocols and the role of IK recorders Further to this, refer to PRODOC Box 7 (ABS Procedures, Checkpoints and Flowchart), where the following is highlighted and illustrated through a flow chart included further down (at the end of this Matrix) and corresponding text below: Particulars of bioprospecting permit applications -- See linked figure at the end of this Matrix: - To be eligible for a permit for bioprospecting derived from traditional knowledge, or from the traditional use of a biological resource, the applicant must disclose to stakeholders the full nature of the bioprospecting project. - The applicant must also gain the prior informed consent of the Indigenous community providing access, and have both a mutual transfer agreement and a benefit-sharing agreement in place. - The mutual transfer agreement must identify the particulars of the provider and the recipients of the biological resources, along with the type, area of source, quantity, purpose and present potential uses of the biological resource. - Similarly, the benefit sharing agreement must specify the characteristics of the indigenous biological resources subject to the agreement, the parties to the agreement, the scope of the use of the biological resources, regular review intervals, and the manner and extent to which communities will share in the royalties derived from bioprospecting. - Both respective agreements must be in a standard form, and are of no effect without Ministerial approval. - Approval is granted when the Minister is satisfied there has been adequate disclosure to affected stakeholders, and that the benefit-sharing agreement is equitable. - The Minister may also seek technical advice on the agreement, or interfere with the contractual terms to ensure that the equitable sharing of benefits occurs. Lastly, the holder of the permit is liable for all mitigation costs to remedy any adverse impact on the environment deriving from the bioprospecting project. --- End of quote -- | Added to current iteration of PRODOC Annex X-3, Section on Component 3, sub-section on Output 3.1: Box (new) Additional background on Bio- Cultural Protocols and the role of IK recorders Refer also to: PRODOC Box 7 on ABS Procedures, Checkpoints and Flowchart, which was pre-existing in the previous iteration of the PRODOC |
|  | Comment #12: 12. Output 3.2. Please clarify if the objective of this output is to come-up with a certification standard and/or a certification organization. Is this to certify that the value chain and end-product (derived from genetic resources) comply with the Nagoya Protocol? | Response to Comment #12: Additional information, clarifying the purpose and objective for a revised Output 3.2 was added to the PRODOC. The objective is to develop a certification system, as implied in the revised Output 3.2: A biotrade certification system for South Africa is developed with a view to safeguarding biodiversity conservation within bioprospecting value chains. New text was added to current iteration of PRODOC Annex X-3, Section on Component 3, sub-section on Output 3.2. Budgets were updated accordingly. | PRODOC and CEO Endorsement Request: Corrections made to update the content and budget of Output 3.2 |
|  | Comment #13: 13. As noted by the USA, many of the proposed activities will be carried out on plants that are traded as commodities rather than on genetic resources. A simple Google search shows the extent of the trade (plus some of the references included in the Project for Roibos). The table suggested above is a good place to clarify the proposed interventions that make these plants and activities fall under the Nagoya Protocol. | Response to Comment #13: The bulk of these products in the nutraceutical business are still very much niche bioprospecting or biodiscovery products, as opposed to commodities. Further to this, we provided a thorough response to USA on the question regarding commodities, because the PIF mentioned honey, even though the product was not targeted by the project, which has a clear focus on plants -- and indigenous plants, more specifically. Please refer to 9 pages of responses to GEF Council members in the CEO End Request. |  |
| 3. Is the financing adequate and does the project demonstrate a cost-effective approach to meet the project objective? | Comment #14: 1-3-18 The cost of the project is significant and can only be made if all the co- financing becomes affective during project implementation. Nevertheless, considering the structural issues of the project identified during the review of the CEO Endorsement, this item will be revisited after the resubmission. | Response to Comment #14: Additional co-financing. Since that last PRODOC submission, two new letters of co-financing from the Agricultural Research Council (ARC) providing $1,424,980 and SNBI, providing $515,384.61 in co-financing have been received. The baseline and co-financing tables were amended accordingly. All changes made to budgets and figures were equally highlighted. | All relevant figures updated. |
| 4. Does the project take into account potential major risks, including the consequences of climate change, and describes sufficient risk response measures? (e.g., measures to enhance climate resilience) | Comment #15. 1-3-18 Yes. Nevertheless, this item will be revisited after resubmission. | Response to Comment #15. UNDP takes note and provides assurances that a balanced approach to risk screening is applied, including through the consistent application of the UNDP’ Social and Environmental and Social Screening Template (SESP), in addition to regular risk assessment at project level. See e.g. PRODOC Annex F and PRODOC Part V – Feasibility, Section “Risk Management”. The latter has been reproduced in the CEO Endorsement Request. | -NA- |
| 5. Is co-financing confirmed and evidence provided? | Comment #16. 1-3-18 Yes , co-financing letters are provided with correct requested amounts. Cleared | Response to Comment #16. Additional co-financing. Since that last PRODOC submission, two new letters of co-financing from the Agricultural Research Council (ARC) and SANBI were received by UNDP and DEA. The co-financing amounts of $1,424,980 from ARC and $515,384.61 from SANBI are now formally recorded. The baseline and co-financing tables were amended accordingly. All changes made to budgets and figures were equally highlighted. | See annexes to PRODOC. |
| 6. Are relevant tracking tools completed? | Comment #17 1-3-18 Yes, BD Tracking tool provided. However, the targeted landscapes /seascapes of 65 million ha in 60 months and also indirectly target the total area of South Africa, 122,000,000 ha, seems very high and ambitious to me. This target will be revisited after the resubmission, specially considering the lack of geographic focus of the project. | Response to Comment #17. The direct target referred to the overlap of plant distribution sheets (see PRODOC annexure) and the indirect the country’s surface. The indirect target is now removed. |  |
| Agency Responses |  |  |  |
| GEF Council (Japan, Germany, USA) | Comment #18 1-3-18 The responses need to be revised as part of resubmission. | Response to Comment #18. Thorough responses to comments from GEF Council members had been included in the previous iteration of the CEO Endorsement Request documentation. These comments were now revisited and, where needed, updated, in light of the current changes made to the project’s content in response to GEF Secretariat’s from 03 January 2018. Refer to Annex B, Section 1b, herein (GEF Council Comments at PIF Stage and UNDP’s response). Highlights indicate the changes made. | CEO Endorsement Request Annex B, Section 1b, GEF Council Comments at PIF Stage and UNDP’s response |

#### Figure Linked to Response to Comment #11, already included in the PRODOC

Source: DEA (2012): South Africa’s Bioprospecting, Access and Beneﬁt-Sharing Regulatory Framework: Guidelines for Providers, Users and Regulators. Prepared for the Department of Environmental Affairs by: The Environmental Evaluation Unit, University of Cape Town and Natural Justice.

#### PRODOC Box 9 (new) Win-Win A promising value chain with African Ginger and a gateway to sustainable use

Additional explanation in connection with the February 2018 re-submission of the PRODOC The Output justification is strengthened by additional content covering three important aspects: (1) Why are clinical trials actually needed; (2) Providing more information on the process proposed and background; and (3) What GEF funds will add to the process

(1) Why are clinical trials actually needed: Registering any complementary medicine – also termed herbal medicinal product (HMP) -- by the South African Medicines Control Council (MCCZA) normally requires clinical data on efficacy vis-à-vis the stated health enhancement claims. When the HMP is to register as a ‘low risk’ HMP, an abridged process of registration that dispenses clinical evidence is possible. However, in such cases, the applicant would only be able to label it as being effective for the “relief of minor symptoms” and “not related to a disease or disorder” Proving African ginger’s efficacy for treating asthma and allergies through clinical trials is currently the only major barrier to be overcome for product registration. It is in fact CSIR’s strategic choice for maximizing the potential benefits from years of R&D and a standing partnership with THC.

(2) Process proposed and background: CSIR will be overseeing the work of clinical trials and co-financing it. Hence, the CSIR will be sharing the R&D risks with the GEF, in view of generating, through partnerships, tangible global biodiversity benefits. Given the past results from R&D, partners believe that the prospects of developing a viable commercial product are promising, in particular in the form of a HMP. The work of overseeing the clinical trials will be done in collaboration of the THC. Previously, CSIR and the THC had entered into several agreements and the CSIR has in fact conducted extensive R&D activities on African ginger. This led to the identification of several biochemical metabolites, expressed in this indigenous plant species, substances that are responsible for the anti-asthmatic and anti-inflammatory properties. Genetic fingerprinting of the species was undertaken through previous R&D to aid quality assurance and to prevent possible confusion with related species. The mentioned research conducted scientific studies and demonstrated the beneficial properties of the plant extract in the improvement of the symptomatology associated with allergic and inflammatory diseases. The research also provided scientific evidence substantiating its traditional use and potential inclusion in complementary medicinal products. The intellectual property was produced through the research and development and later protected through a patent system as a potential agent for the treatment of inflammatory and allergic diseases such as asthma.

(3) What GEF funds will add to the process: On the backdrop of the above-described robust R&D baseline, the focused contribution of the GEF project is expected to facilitate three important shifts: First, the CSIR and the THC will reach a more comprehensive benefit sharing agreement regarding African ginger and the proposed use. They will do that in the framework of more current legislation, namely the South African legislation, National Environmental Management: Biodiversity Act 2004, Bioprospecting, Access and Benefit Sharing, 2008. This, in and on itself, represents a tangible ABS compliance benefit. Second, the Southern African variants of the species Siphonochilus aethiopicus (African ginger), will be part a more a formal and nationally branded value chain, aimed at sustainably producing and trading a commercially viable HMP, with all due controls as required by national regulations the licensing and registration of such products in South Africa. In due course, this will may lead to new partnerships, that will build on the hopefully successful outcome of clinical trials and product registration. The GEF project will help overcome specific barriers to that effect. The benefit that may generated will likely be much more significant. Thirdly, the above aspect is linked to the species conservation status and this is important in the context of GEF project. Currently, African ginger is already being used and traded in South Africa within the informal market for traditional medicines. In spite of the best intentions by organizations such as the THC, they acknowledged (e.g. in PPG event) that, without the typical ‘surveillance’ and ‘controls’ that the product would be imposed in compliance / formal markets, the high demand for the plant’s roots in home-made remedies has effectively resulted in the plant being red-listed as Critically Endangered where it occurs in Southern Africa. The Healer’s Council would like to ‘turn this stark reality around’, working with DEA, the scientific community through CSIR and possibly ARC, when it comes to extension services for cultivation. These efforts, are also proposed supported by the GEF project through Output(s?) XXXX as a way to address the threats to the species Siphonochilus aethiopicus. More specifically, it can be expected that, along with the product registration at the MCCZA, other requirements on sustainability at the landscape level also apply, namely of Good Agricultural and Collection Practices (GACP). The applicable MCCZA 2016 Guidelines on HMPs state the following: “Compliance with Good Manufacturing Practice (GMP), Good Laboratory Practice (GLP) and Good Agricultural and Collection Practices (GACP) All manufacturers of complementary medicines shall comply with all relevant aspects of Good Manufacturing Practice as outlined in the latest version of the MCC’s “Guide to Good Manufacturing Practice for Medicines in South Africa” and Good Laboratory Practice, as well as the WHO Guidelines on Good Agricultural and Collection Practices (GACP) for Medicinal Plants, if applicable. Any alternative standards must be specified, referenced and justified.” The above creates a “good lever” for conservation and sustainable practices on the management of Siphonochilus aethiopicus within its South African habitats – as well as the envisaged transition to cultivation, which according to DEA and SANBI specialists, is what is needed for addressing the Finally, Additional and R&D – not related to clinical trials – also needs to be undertaken in order to establish thresholds for sustainable harvesting and further pathways towards sustainable cultivation and for refining the mechanism that will ensure the sustainable supply of the species to the industry.

#### PRODOC Figure 16 (new) Brief History and stark reality of the P. sidoides supply chain

Source: Jaci van Niekerk and Rachel Wynberg, Environmental Evaluation Unit University of Cape Town. In connection with an academic lecture titled: “The trade in Pelargonium sidoides: Rural livelihood relief or bounty for the ‘bio-buccaneers’?” - HSRC PRETORIA 25 February 2013

# ANNEX C:  STATUS OF IMPLEMENTATION OF PROJECT PREPARATION ACTIVITIES AND THE USE OF FUNDS

## Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: 182,648 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GETF/LDCF/SCCF/CBIT Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent Todate | Amount Committed |
| Actiivty 1. Conduct the following baseline studies: During the design stage, the following activities will be conducted to establish baseline for the implementation: - Analysis and confirmation of the 5 ABS products to be developed and marketed by the project, including confirmation of the species providing the genetic resources/derivatives, value chains, research and development needed, and industry uses of these five products. - Targeted analyses of market potentials of the supported value chains, including market trends in the respective business fields (including regional and other developing country markets) - Baseline assessment of the financial flows accruing to the Traditional Healers Committees and communities in the form of royalties generated from the commercialisation of the 5 products derived from genetic/biological resources. - Baseline assessment of sustainable community based business models. - Baseline assessment of the number of new local R&D innovations (patents, products etc.) and technologies which enter the bioprospecting sector - Baseline assessment of the nature and number of research collaborations between government authorities, private sector parties, holders of traditional knowledge and rural communities to develop and commercialise novel genetic/biological resources - Baseline assessment of the benefit-sharing agreements negotiated between industry and communities, the number of bioprospecting products in domestic & international markets; the number of bioprospecting products that have community involvement in the supply chain; and the number of jobs being created in the sector including for disadvantaged communities - Baseline assessment of indigenous biodiversity registration in regional and international inventories acknowledged for consumer use/trade; the product development and manufacturing potential of natural products in SA; and the scope and extent of domestic business incubator support. - Baseline assessment of Biodiversity Management Plans as a strategy to ensure the sustainable use of biological/genetic resources, assess threat and ensure the conservation of biodiversity. - Define a detailed plan to ensure Siphonochilus aethiopicus (identified as critically endangered and extinct in one region) is not overharvested if used by the project. - An assessment of the current number and nature of Small and medium size enterprises promoted within the bioprospecting sector through training and skills development, including the level of education, skills and training emanating from the sector - Additional baseline studies on the bioprospecting sector that will update the situational analysis done for the NBES process, and update the overall strategy. - Baseline assessment of the status of conservation of threatened species from where the plant resources in question will be harvested - Baseline assessment of sustainable harvesting practices/models of high potential biodiversity in the wild. - Baseline assessment of number of models on sustainable cultivation ventures of high potential biodiversity. Activity 2. Build Results Framework Activity 3. Conduct assessment of opportunities/risks identified during a Social and Environmental Pre Screening of the project PIF. Activity 4.Carry out a Capacity Assessment of the proposed Implementing Partners and Develop a capacity development plan by defining of monitoring and evaluation (M&E) plan, sustainability plan, management arrangements, and gender mainstreaming plan Activity 5. Prepare Financial planning and identifying co-financing investments Activity 6. Conduct stakeholders meeting and Validation workshop Activity 7. Completion of final documentation | 182,648 | 154,704.89 | 27,943.11 |
| Total | 182,648 | 154,704.89 | 27,943.11 |

# ANNEX D:  CALENDAR  OF EXPECTED REFLOWS (IF NON-GRANT INSTRUMENT IS USED)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/CBIT Trust Funds or to your Agency (and/or revolving fund that will be set up)

N/A

Project ID number remains the same as the assigned PIF number.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF and CBIT programming directions.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

Update the applicable indicators provided at PIF stage.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period.

For questions A.1 –A.7 in Part II, if there are no changes since PIF , no need to respond, please enter “NA” after the respective question.

DEA (2015): The scope and extent of the utilization of indigenous biological resources by bioprospecting industries in South Africa. Department of Environmental Affairs, Government of the Republic of South Africa. (ISBN 978-0-621-42766-0).

Such variables include (i) plant domestication processes (transition from wild harvesting to cultivation); (ii) the discovery of synthetic substitutes; (iii) competition with other economic alternatives; (iv) conditions of market growth and competitive uses of the same species; (v) the exhaustion of the extractive resource; and (vi) the interrelationship with other sectors of the economy -- plus several other variables. (refer to PRODOC Annex X-6 for more details)

This parameter was chosen because data on it is systematically collected by SANBI and, during project implementation, the institute can use it to make concrete recommendations for the conservation of species and habitats concerned by bioprospecting value chains.

McGregor, G.K. (2017). Guidelines for the sustainable harvesting of wild honeybush. Department of Environmental Affairs and Development Planning, Cape Town. [Link].

This is discussed further below and the summary argument is picked up again in sections ‘Threats, Root Causes and Barriers’ and in ‘Long-Term Solution’ further down.

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, SCCF and CBIT

Current supply of both Devil’s Claw and Rooibos are limited, although the markets exit. With support for increased supply through harvesting and production, processing and packaging, there is potential to increase benefits to the local communities in the Northern Cape region. The Northern Cape R&D Hub is meant to provide this support to the underdeveloped markets and value chains in this region.

This refers to Output 3.2. The proposed support initiative would: (i) Develop a documented Standard, comprising indicators and implementation guidelines; (ii) Conclude implementation agreements with at least one implementation agent; and (iii) Complete a certification test case.

The three key species (other than Rooibos) that are commonly used in projects by community business in Northern Cape are: Devil’s Claw (Harpagophytum procumbens); Kanna (or Kougoed, Sceletium tortuosum) and Cancer Bush (Sutherlandia frutescens). They will be on focus in the Nothern Cape hub, under Output 2.1.

Republic of South Africa (2016): The Medicines Control Council of South Africa: Registration of Medicines, Guidelines (CMs DS Safety & Efficacy), Complementary Medicines - Discipline-Specific Safety and Efficacy, version 3, June 2016 (7.01_CMs_SE_DS_Jun16_v3.doc). Accessed on 14 Feb 2018. [Link]

RSA Government Gazette, Vol. 553 Pretoria, 29 July 2011 No. 34487: Department of Environmental Affairs, 501 National Environmental Management: Biodiversity Act (10/2004): Draft Biodiversity Management Plan for Pelargonium Sidoides.

RSA Government Gazette, Vol. 553 Pretoria, 29 July 2011 No. 34487: Department of Environmental Affairs, 501 National Environmental Management: Biodiversity Act (10/2004): Draft Biodiversity Management Plan for Pelargonium Sidoides.

Quoted from: Medaglia et al (2014): Overview of national and regional measures on access and benefit sharing challenges and opportunities in implementing the Nagoya Protocol. Third Edition CISDL Biodiversity & Biosafety Law Research Programme, 25 June 2014. Source: DEA (2012): South Africa’s Bioprospecting, Access and Beneﬁt-Sharing Regulatory Framework: Guidelines for Providers, Users and Regulators. Prepared for the Department of Environmental Affairs by: The Environmental Evaluation Unit, University of Cape Town and Natural Justice.

Republic of South Africa (2016): The Medicines Control Council of South Africa: Registration of Medicines, Guidelines (CMs DS Safety & Efficacy), Complementary Medicines - Discipline-Specific Safety and Efficacy, version 3, June 2016 (7.01_CMs_SE_DS_Jun16_v3.doc). Accessed on 14 Feb 2018. [Link]

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.