GEF-7 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type: full Sized Project

Type of Trust Fund: GEF

part i: project information

| Project Title: Implementing the National Framework on Access and Benefit Sharing of Genetic Resources and Associated Traditional Knowledge in the Philippines |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Philippines | GEF Project ID: | 10079 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 6275 |
| Project Executing Entity(s): | Department of Environment and Natural Resources Biodiversity Management Bureau (DENR-BMB) | Submission Date: | 17 July 2020 2 Sept. 2020 |
| GEF Focal Area (s): | Biodiversity | Expected Implementation Start | 11 Feb 2021 |
|  |  | Expected Completion Date | 11 Feb 2027 |
| Name of Parent Program |  | Parent Program ID: |  |

- Focal/Non-Focal Area Elements

| ### Programming Directions | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| BD 3-9 | Further development of biodiversity policy and institutional frameworks through the Implementation of the Nagoya Protocol on Access and benefit sharing | GEFTF | 4,384,000 | 21,631,787 |
| Total project costs |  |  | 4,384,000 | 21,631,787 |

- Project description summary

| ### Project Objective: Increased economic opportunity and biodiversity conservation for local communities and indigenous peoples in the Philippines stemming from fair and equitable sharing of biodiversity benefits |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Component Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| - Strengthening the national framework for implementing ABS in accordance with the Nagoya Protocol | Technical Assistance | Strengthened national regulatory frameworks and clarified institutional mechanisms for ABS that are in compliance with the Nagoya Protocol measured by: - One inter-agency framework for monitoring and tracking use of GR and ABS transactions in place - One mechanism to channel ABS monetary and non-monetary benefits to local communities and Ips and support biodiversity conservation and sustainable use established and institutionalized. - One integrated knowledge management platform established and institutionalized to capture ABS documentation, including cataloguing of traditional knowledge (TK). | Output 1.1. Revised and harmonized rules and regulations to facilitate access and research towards ABS agreements taking into account gender and environmental and social safeguards Output 1.2 Clear procedure, protocols and guidelines for bioprospecting, research and development Output 1.3 Functional mechanism, including administrative system, institutional arrangements, monitoring and financing mechanism in place to facilitate implementation and compliance of the national ABS framework Output 1.4 Access and Benefits Sharing National Roadmap developed | GEFTF | 982,000 | 542,282 |
| - Awareness raising and capacity building for implementation of the national ABS framework | Technical Assistance | Enhanced understanding of the ABS regime and the value of traditional knowledge associated with genetic and biological resources for improved policy making and on the ground conservation, sustainable use and fair and equitable sharing of benefits measured by: -At least 30% increase in agency capacity as measured by UNDP ABS scorecard - One gender-responsive Communication, Education, and Public Awareness (CEPA) plan fully deployed - Change in knowledge, attitudes and practices (KAP) of target groups | Output 2.1 Awareness campaign targeted to different ABS stakeholders implemented. Output 2.2. Integrated training program and other capacity building measures for staff relevant to ABS agencies and stakeholders undertaken Output 2.3. Best practices and lessons of ABS documented and disseminated and traditional knowledge of IPLC catalogued and made accessible to all stakeholders | GEFTF | 1,374,300 | 422,322 |
| - Demonstrating benefit-sharing agreements | Technical Assistance | At least one ABS Agreement negotiated and finalized that demonstrate PIC and MAT and with clear provision on fair and equitable benefit sharing measured by: -At least two ABS products tested for potential commercial application: Pili (Canarium ovatum and Canarium luzonicum) and Banaba (Lagerstroemia speciosa) -Two biodiversity management plans for in-situ conservation and management of biological resources integrated into pilot agreements. -Two gender-smart and ABS value chains for Banaba and Pili mapped and with a strategic development road map. | Output 3.1 Research and development conducted for identified species (Pili and Banaba) Output 3.2 Strategic Roadmap for the identification and creation of benefits based on genetic resource development. Output 3.3 Negotiate and implement ABS agreement modeling FPIC and PIC processes Output 3.4 In-situ conservation measures to ensure the security of the concerned genetic resources are integrated into the negotiated MAT | GEFTF | 1,652,940 | 20,556,766 |
| - (Monitoring and Evaluation) | Technical Assistance |  |  | GEFTF | 166,500 | - |
| Subtotal |  |  |  | GEFTF | 4,175,740 | 21,521,370 |
| Project Management Cost (PMC) |  |  |  | GEFTF | 208,260 | 110,417 |
| Total project costs |  |  |  |  | 4,384,000 | 21,631,787 |

- confirmed sources of Co-financing for the project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| Recipient Country Government | Department of Environment and Natural Resources | Grant | Investment Mobilized | 3,439,864 |
|  |  | In-kind | Recurrent expenditures | 2,024,735 |
| Recipient Country Government | Department of Agriculture Regional Office No. 5 | Grant | Investment Mobilized | 2,752,600 |
| Recipient Country Government | Department of Science and Technology – Philippine Council for Agriculture, Aquatic and Natural Resources Research and Development | Grant | Investment Mobilized | 907,692 |
| Recipient Country Government | Local Government Unit – Province of Albay | Grant | Investment Mobilized | 1,000,000 |
| Recipient Country Government | Local Government Unit – Province of Sorsogon | Grant | Investment Mobilized | 1,000,000 |
| Other | Academic and Research Institutions (Central Luzon State University and Sorsogon State College) | Grant | Investment Mobilized | 6,527,247 |
| Other | Philippine Pili Industry Board | Grant | Investment Mobilized | 2,100,000 |
|  |  | In-kind | Recurrent expenditures | 1,408,800 |
| Private Sector | Herbanext Laboratories, Inc. | Grant | Investment Mobilized | 174,000 |
|  |  | In-kind | Recurrent expenditures | 52,200 |
| Private Sector | Pharmalytics Corporation | Grant | Investment Mobilized | 95,813 |
|  |  | In-kind | Recurrent expenditures | 38,419 |
| Other | United Nations Development Programme | In-kind | Recurrent expenditures | 110,417 |
| Total Co-financing |  |  |  | 21,631,787 |

The “Investments Mobilized” was determined through the identification and enumeration of existing and future investments of the project stakeholders that will contribute to the attainment of the Project objective and outcomes. These investments are mainly programs and projects which are currently in operation and in the pipeline for the next six years or during the Project implementation, including:

- Investments mobilized committed by the Department of Environment and Natural (DENR) will come from: (a) Protected Area Investment Plans; (b) allocation for thematic area on ABS under the Philippine Biodiversity Strategy and Action Plan (PBSAP); and c) National Greening Program.

- Investments mobilized from the Department of Agriculture Region V will be from its High Value Crop Development Program.

- Investments mobilized from the Department of Science and Technology-Philippine Council for Agriculture, Aquatic and Natural Resources Research and Development (DOST-PCAARRD) are from its Pili Research ad Development Center Program with seven component projects under DOST’s Accelerated R&D Program for Capacity-Building and Development Institutions and Industrial Competitiveness: NIche Centers in the Region for R&D (NICER).

- Investments mobilized committed by the Provincial Local Government Units (PLGUs) of Albay and Sorsogon are from its Program on Development of Pili Industry in the two Provinces.

- Academic and research institutions, specifically the Sorsogon State College and Central Luzon State University, will source its investment commitments from its research activities under the Sorsogon Pili Roadmap Program and Research and Development of Banaba Pharmaceutical Properties.

- The Philippine Pili Industry Board will provide investments of its members engaged in pili oil production.

- Investments mobilized from the private sector are from there R&D activities and technology development program.

Trust Fund  Resources Requested by Agency(ies),  Country(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNDP | GEFTF | Philippines | Biodiversity |  | 4,384,000 | 416,480 | 4,800,480 |
| Total GEF Resources |  |  |  |  | 4,384,000 | 416,480 | 4,800,480 |

- Does the project include a “non-grant” instrument?   NO

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency  and to the GEF/LDCF/SCCF Trust Fund).

- Project’s Target Contributions to GEF 7 Core Indicators

.

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use (Hectares) |  |
| 2 | Marine protected areas created or under improved management for conservation and sustainable use (Hectares) |  |
| 3 | Area of land restored (Hectares) |  |
| 4 | Area of landscapes under improved practices (excluding protected areas)(Hectares) | 41,662 |
| 5 | Area of marine habitat under improved practices (excluding protected areas) (Hectares) |  |
|  | Total area under improved management (Hectares) |  |
| 6 | Greenhouse Gas Emissions Mitigated (metric tons of CO2e) |  |
| 7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management |  |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (metric tons) |  |
| 9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (metric tons of toxic chemicals reduced) |  |
| 10 | Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent gTEQ) |  |
| 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment | 6,058 2,120 Women 3,938 Men |

The project will contribute to the following Aichi Targets: Target 14 -By 2020, ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being, are restored and safeguarded, taking into account the needs of women, indigenous and local communities, and the poor and vulnerable; Target 16; By 2015, the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from their Utilization is in force and operational, consistent with national legislation; and by 2020, knowledge, the science base and technologies relating to biodiversity, its values, functioning, status and trends, and the consequences of its loss, are improved, widely shared and transferred, and applied.

- Project Taxonomy

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing Models | Transform policy and regulatory environments |  |  |
| Stakeholders | Indigenous Peoples Local Communities Private Sector Civil Society Type of Engagement Communications | SMEs CBOs Academia Partnership Consultation Participation Awareness Raising Education Public Campaigns |  |
| Capacity, Knowledge and Research | Enabling Activities Capacity Development Knowledge Generation and exchange Learning Innovation Knowledge and Learning Stakeholder Engagement Plan | TOC Adaptive Management Indicators to measure change KM Innovation Capacity development |  |
| Gender Equality | Gender Mainstreaming Gender results areas | Beneficiaries Gender sensitive indicators Access and control over natural resources Access to Benefits and services Awareness raising |  |
| Focal Area/Theme | Biodiversity | Supplementary Protocol to the CBD | Access to Genetic Resources Benefit Sharing |
|  |  | Rio Markers | Climate Change Adaptation 1 |

part ii:  project justification

describe any changes in alignment with the project design with the original pif

1a. Project Description.

The most significant change from the PIF was the finalization of species selection the Pili tree (Canarium ovatum and Canarium luzonicum) and Banaba (Lagerstroemia speciosa). Pili was indicated during the PIF and confirmed during the PPG stage. Banaba was selected during the PPG stage. The choice of a species other than Sambong was triggered by the DENR and BMB’s decision to select an indigenous tree species which is within their mandate’s jurisdiction. The primary motivation for the change is for the Philippine’s to be able to maximize biodiversity resources which are indigenous and located within Key Biodiversity Areas and protected areas of the Philippines. During the PPG, based on deliberations with DENR and numerous stakeholder meetings, the species and site selected were Pili in Bicol and Banaba in Central Luzon. The selection was based on the following criteria: (1) the plant species being abundant and indigenous in the selected areas, while considering the possible effect on conservation status by the identified economic utilization; (2) the existing Indigenous Knowledge Systems and Practices and traditional knowledge (IKSP/TK), trade and other utilization in the market; (3) the available research and product development pointing to the potential of increasing the market value derived from such; and (4) the opportunity for greater local stakeholder inclusion in the value chain. Both species have existing industrial revenue streams derived from derivative food products. There are some initiatives towards non-food products (e.g. cosmetic, medicinal) yet they cannot be considered as widespread nor mainstream enough to establish its current impact to the industry and their regions. The location of these two species overlaps significantly with Key Biodiversity Areas (KBAs). Region 3, Central Luzon includes approximately 408,131 hectares of terrestrial KBAs.  In Bataan, Banaba has been surveyed within the ancestral domains that shares boundaries with the Bataan National Park and the Subic Forest Reserve.

Other than species selection there are no significant changes in the project design from the original PIF. During the PPG stage, the refinement of species and site selection enabled a more precise estimate of direct project beneficiaries from a total of 2000 (1000 women and 1000 men) to 6058 (2,120 women and 3,938 men). The beneficiary figures are further detailed in the UNDP Project Document (PRODOC) Section V. Project Results Framework, Annex 3 Monitoring Plan, and Annex 12.  Site Selection.

The co-financing amount has slightly increased from the PIF estimate of USD 19,100,000 to 21,631,787.

1b. Project Map and Geo-Coordinates. Please provide geo-referenced information and map where the project interventions will take place. Please see Annex E and PRODOC Annex 1.

1) Global environmental problems, threats, root causes and barriers to be addressed.

There are no significant changes from the PIF. Through the PPG process - threats, impacts, and barriers presented in the original PIF have been further refined and elaborated through consultations. The three main barriers include:

Barrier 1: Inadequate and weak enforcement of policies, institutional and regulatory frameworks on ABS implementation. The granting of access is delegated to three government agencies: DENR, DA, and PCSD  each of which  implement separately  the procedures and approval under the  Wildlife Act  and the  Bioprospecting Guidelines. There is also a weak coordinating mechanism among these agencies, including the need to streamline and harmonize their processes and procedures. Furthermore, there is a need to harmonize  ABS  policy with the PIC/FPIC process. Once the activity  falls under the Bioprospecting Guidelines, the applicant has to apply for  the Bioprospecting Undertaking (BU) where  the application  includes a  certification that  PIC or FPIC has been secured with  the resource  providers.   The  PIC procedures vary, depending on whether the area targeted for bioprospecting is within a protected area, private land, or ancestral domain. In addition, the procedure for FPIC  for bioprospecting falls within the project category of Extractives Intrusive Large Scale Activities (EILSA), where,  after the community  consent is secured by a Memorandum of Agreement (MOA),  the process of certification involves  various levels of approvals within NCIP up to the certification by its highest  body, the  NCIP Commission En Banc. The issuance of the BU is dependent on the timely issuance of PIC/FPIC.

Moreover, BU is  issued  by the  Secretary of  DENR or DA or  Chairman of  PCSD which is the Governor of Palawan. To date implementation of the rules is mired with inefficiency and uncertainty,  contrary to  the  goal of the NP to have more predictable conditions for access to genetic resources to ensure the sharing of benefits. There is also inadequate monitoring capability to detect and thereby enforce illegal collection of genetic resources. A more detailed overview of the current permitting process is provided in the PRODOC Annex 11. Situational Analysis.

Barrier 2 : Lack of awareness and weak capacity of key stakeholders on ABS implementation at the national and local level. The academic community, local government units, and industry have limited appreciation of the basic rules and rationale of existing ABS policies resulting in poor compliance and indifference. As a result, very few have  applied for access to genetic resources, negotiated bioprospecting agreements, or developed ABS products.  Similarly, there is low appreciation on patent information by researchers and scientists which contributed to the low patent applications from local researchers in the country. There was is also a lack of appreciation and awareness among universities and research institutes on the relevance of patent information in their R&D work and in the possible commercialization of their research outputs. Further, researchers and scientists often do not declare if the subject or source of their patent applications are related to or stem from local genetic resources or local traditional knowledge.

Capacities of research and academic institutions are also lacking in terms of facilitating Intellectual Property Right (IPR) applications, and in advancement of research into the next stages of product development and commercialization. In addition, the field offices of agencies in charge of implementing regulations, namely: DENR, DA and NCIP have weak capacities to assess research proposals, thus resulting in missed opportunities to secure benefits from further advance of bioprospecting research should these proceed to product development and eventual commercialization. At the national level, there is also a need to strengthen capacities for negotiating agreements, understanding industry business models, facilitating access to genetic resources, compliance monitoring and tracking of bioprospecting projects, handling cases related to implementation of the Nagoya protocol.

Other groups such as the private sector, lack access to information on genetic resource research projects that can be transformed into ABS products. IPLCs have limited capacities to manage their own genetic resources associated with traditional knowledge, while ensuring the quality of their raw materials and links in the value chain leading to the development of ABS products. Their skills in negotiations and awareness of opportunities and benefits of engagement in bioprospecting agreements are also limited.

While there are existing mechanisms available for use by IPLCs to protect their cultural heritage relating to genetic resources and traditional knowledge, very few of them are aware of these provisions that will enable them to facilitate issuance of FPICs. Finally, there is no systematic documentation of TK pertaining to utilization of genetic resources nor a database of ongoing and pipeline researches resulting in inefficiencies in advancing genetic resources research towards commercialization. Documentation has been sporadic, and the absence of acceptable protocols for recognition and registration of these TKs has discouraged many IPLCs from sharing their information with a central registry. Such documentation does not come with assurances or protection of the IPRs of IPLCs, thus the reluctance to share information with the science community and private sector.

Annex 14. Capacity Assessment includes the detailed results of capacity score cards and presents the self- identified capacity building needs by ABS institutions.

Barrier 3: Absence of good practices on ABS implementation from the initial stage of bioprospecting to research and development, product  innovation and commercialization: Since the passage of relevant ABS laws and issuance of policies to facilitate bioprospecting as early as 1995,  there  has not been a single case to cite as best practice that is compliant with the NP across the entire continuum of the ABS process from securing PIC/ FPIC to conducting of R&D up until the commercialization of research products and to the sharing of benefits down to indigenous peoples and local communities. This could be related to many factors including the inherent business risk of bioprospecting activities up through market introduction. There are government programs that encourage and provide funding for drug discovery yet not all private enterprises are enticed by this due to the shared patent ownership or profit sharing down the road.

Please refer to PRODOC Section II Development Challenge for details.

2) Baseline scenario or any associated baseline projects.

There is no significant change from the PIF. However, a more detailed analysis of the current policies, regulations, rules, and laws as well as relevant projects and initiatives has been conducted during the PPG (please see PRODOC Annex 11: Situational Analysis). In addition, a wider range of partners that would be involved in project implementation have been identified and consulted during the PPG process (please see PRODOC Annex 7: Stakeholder Engagement). Greater detail about the species selection including an overview of Pili and Banaba’s   distribution, threat level, R&D, value change as well as conservation and social benefits is included in PRODOC Annex 12: Site Selection.

A summary of the associated baseline projects is below. Annex 11: Situational Analysis includes a more comprehensive cataloguing and analysis of the current baseline.

Research and Development Programme on Medicinal Plants.  The Department of Science and Technology, the PCHRD and Philippine Council for Agriculture, Aquatic, and Natural Resources Research Development (PCARRD) are providing research and equipment grants to academic and research institutions focusing on discovery of novel compounds from indigenous/endemic terrestrial and marine species. In order to initiate this programme and encourage medicinal plant research in rural areas where the richness of Philippine biodiversity is evident, the government has established screening and extraction centers in various universities around the Philippines to study flora and fauna which are endemic and/or indigenous to the area. The DOST and its attached research councils have a total annual allocation for research and equipment grant not lower than PhP1B (US$20M). Through components 1 and 3 this project will identify the most advanced research which can be linked up with private sector.

Tuklas Lunas (Drug Discovery) Centers. The government has established at least 10 Tuklas Lunas (Drug Discovery) Centers in several regions in the country housed in select State Universities.  This aims to boost research in the regions and harness biodiversity.  This programme promotes the scientific validation of traditional and locally used medicinal natural products. These centers are currently studying hundreds of plant species that are locally used by local healers. Table below lists six of these centers with advanced research and the researches they are currently working on.

| Tuklas Lunas Center | R&D Project | Status |
| --- | --- | --- |
| Marcos Mariano State University | Phytochemical, Toxicologic Profiling and Anti-inflammatory Activity of Indigenous Medicinal Plants (Phase 1) | Screened 46 plant species used by local healers |
| Visayas State University | Molecular Discovery Project from Selected Philippine Indigenous Medicinal Plants for Treatment of Diabetes Mellitus | Covered 55 plant species with potential for anti-diabetic properties |
| Mindanao State University | Drug Discovery and Development from Indigenous Plants of Mindanao (Phase 2) | Combined biodiversity surveillance and pharmacological screening |
| Central Luzon State University | Mykomining of Wild Edible Mushrooms and Other Allied Species in Central Luzon for their Medicinal Properties | On-going |
| Central Mindanao University | Exploring the Potentials of Philippine Ferns and Lycopods as Source of Therapeutics for Chronic Inflammation and Cancer | Combined biodiversity surveillance and ethnobiological surveys of Philippine ferns and lycopods; Screened 28 species of ferns and lycopods |
| University of San Carlos | Identification, Isolation, and Characterization of Bioactive Metabolites from Terrestrial Plants and Marine Organisms Used by Herbalists in Cebu Province (Phase 1) | Extensive ethnopharmacological screening of indigenous plants in Cebu |

New centers are added to the list each year, based on evaluation by the DOST. Each center is given a budget of Php 20-50 Million per year (US$ 400,000 to 1 Million). Recently, the United Laboratories (UNILAB) – a local drug company, has been designated a Tuklas Lunas Center, and has committed Php 20 Million (US$ 400,000) to establish a facility for drug research.

Research program of DENR’s Ecosystem Research and Development Bureau (ERDB).  The DENR’s research arm is currently prioritizing research efforts on forest tree species with economic potential as well as medicinal value.  They have estimated an annual budget for R&D in the coming years of the current administration to be about $1M. Recently, the ERDB has developed a Roadmap for genetic research and development for 43 forest tree species for their potential for pharmaceutical, cosmetics, neutraceutical, industrial, and other values.

Other ABS related activities: In addition to the above several ABS related activities are on-going and planned. For instance, the DENR is undertaking policy review and development related to wildlife management and access and benefit sharing, protection and conservation of threatened species and their habitats, preparation of permits and agreements for the conduct of researches on wildlife. This has an estimated annual budget of USD 250,000. In addition, a roadmap on ABS under the Phil Biodiversity Strategy Action Plan from 2015 to 2028 has been prepared.

DENR-BMB’s flagship program on coastal and marine entitled “ Coastal and Marine Ecosystem Management Program (CMEMP): This program aims to improve the management of coastal and marine ecosystem thereby increasing their ability to provide ecosystem services and goods including the provision of raw materials for pharmaceutical purposes. The CMEMP will run until 2028 with an estimated annual budget allocation of PhP500M (USD 10M).

USAID PROTECT Wildlife Project. USAID recently launched a USD25 Million Project aimed at among others, combatting illegal trade of wildlife. Slated to be implemented initially in Palawan and Zamboanga provinces, the Project will also develop capacities for apprehension, enforcement, and work with communities to protect wildlife resources and conserve biodiversity, including genetic resources in critical sites. The Project started in 2016 and shall be implemented for the next five years.

3) Proposed alternative scenario, with brief description of expected outcomes and components of the project

The relevance and feasibility of the proposed outcomes and outputs have been confirmed (Refer Figure 5  for Theory of Change and Section IV, of PRODOC) through additional expert review and through extensive consultations during the preparation phase of the project (Refer PRODOC Section IV: Results and Partnerships, and Annex 7: Stakeholder Engagement Plan). Project indicators and targets have been refined to reflect on-ground practicalities and indicative pilot site selection (see PRODOC Annex 12: Site Selection). The main components have remained the same since the PIF.

Component 1:  Strengthening the national  framework for implementing ABS in accordance with the Nagoya Protocol: This component aims to update the current national ABS framework in accordance with the Nagoya Protocol and  harmonize current  policies on bioprospecting and scientific research on genetic resources and TKs and IKSPs  associated with genetic resources.  The project will enhance multi-sectoral and inter-agency collaboration with regard to on-going research up until its potential for commercialization. The institutional mechanism should be able to cross-check or inform other agencies of any research undertakings and link these with the private sector for possible uptake.

Component 2: Awareness raising and capacity building for implementation of the national ABS framework: A nation-wide communication, education and public awareness campaign on ABS and its related policies and procedures will be undertaken under this component. The capacity building will include: strengthening the research sector by developing an integrated and comprehensive ABS road map on genetic R&D; strengthening national systems on intellectual property rights by the researchers and Indigenous peoples and local communities (IPLCs); improving the capacities of national government and IPLCs to engage with private sector with regard to ABS; strengthening capacities in the assessment of research proposals including the monitoring and tracking of bioprospecting and related activities involving utilization of Philippine genetic resources and TKs; strengthening capacities of IPLCs in the use of mechanisms and provisions of the Intellectual Property Right Act (IPRA), Cultural Heritage Act, etc. to ensure their participation and recognition of their GRs associated TKs; strengthening capacities of IPLCs to manage their genetic resources associated TKs as well the benefits that come with it; establishment of a model research and development facility.

Component 3:Demonstrating benefit-sharing agreements: Under this component,  a key outcome is to facilitate the  negotiation of at least one ABS agreement. The project will support the design and review of  ABS agreements  so that they are in line with the national ABS framework and the provisions of the Nagoya Protocol.  This component will also support community protocols of securing Prior and Informed Consent and Free, Prior and Informed Consent (PIC/FPIC) and Mutually Agreed Terms (MAT) and ensuring the fair and equitable  sharing of  both monetary and non-monetary benefits for the use of the genetic material, products, and knowledge. Further under this component, conservation strategies of specific resource covered by the ABS agreement will be planned.  To this end the project will develop at least 2 bio-products from local genetic resources of Pili tree (Canarium ovatum and Canarium luzonicum) and Banaba (Lagerstroemia speciosa).

Response to Project Reviews is provided in Annex B of the GEFCEO ER.

4) Alignment with GEF focal area strategies

- The project aligns with program eight of the Biodiversity Focal area strategy: Implementing the Nagoya Protocol on Access and Benefit Sharing. The project activities will support national implementation of the Nagoya Protocol. The project specifically supports (i) Development and implementation of a strategy and action plan for the implementation of ABS measures. (e.g. monitoring of use of genetic resources, compliance with legislation and cooperation on trans-boundary issues); and (b) Building capacity among stakeholders (including indigenous and local communities, especially women) to negotiate between providers and users of genetic resources. The project will also build institutional capacity to carry out research and development to add value to the Philippines’ genetic resources and their traditional knowledge.

5) Incremental/additional cost reasoning

Baseline projects as well as other contributions to the project´s baseline and co-financing are given in PRODOC Section IV: Results and Partnership) for each project component, and Section IX: Financial Planning and Management).The indicative co-financing for the project has been confirmed with a  total of USD 21,631,787 (see Table C above).

In the baseline situation, updating the current national ABS framework in accordance with the NP and  harmonizing current  policies on bioprospecting and scientific research on genetic resources would take considerably longer, and it would be more difficult to achieve the international standards for best practice in ABS required by the CBD and the Nagoya Protocol. The lack of technical expertise towards the development of implementing regulations will affect the completion and quality of agreements. Inter-agency coordination for genetic resource development will remain weak, resulting in potential conflicts and confusion, which may adversely affect investor confidence.

Further, in a business-like-usual scenario, resources will not be adequate to support the level of capacity building needed to bring the DENR, checkpoint authorities and other stakeholders to implementation readiness in the short term, and local experience and information-sharing on the development of PIC/FPIC, MAT and benefit-sharing will remain inadequate. Bio-prospecting and use of traditional knowledge resources will continue to be weakly regulated, therefore IP communities across the country would remain at risk of losing out on the benefits associated with bio-prospecting and there will be little incentive for improving the security of biological resources at the local level. This issue will be compounded by the impact of COVID-19 on local communities which is currently being assessed.

Without the support of adequate resources, private investment would continue in its attempt to commercialize genetic resources, without the full help of the country’s institutions and with confusion regarding legal and contractual requirements. The supply chain for products related to Pili and Banaba would mobilize limited resources through these companies to a limited number of beneficiaries in Regions 3 and 5. Local communities may not be able to realize the full expectation of increased income that has been created and the process would likely be at risk of failure as the viability of such ventures is questionable, given the uncertainty of the legal, permitting and benefit sharing procedures. The communities would therefore likely increase their extraction activities, which in turn would increase ecosystem deterioration. Lack of investment in this project would therefore lead to financial, social and environmental losses.

Despite the resource investment in the baseline scenario, the impacts would not be competitive in comparison with other alternative uses of the land, which are currently better sources of income for the communities. The alternative of investing GEF resources will help to break commercial, legal and institutional barriers, and give momentum to a process which would not be otherwise competitive. This will be achieved using the three components outlined above, which complement each other, and which, when combined, will improve access to genetic resources and benefit-sharing, as a competitive alternative for the pilot sites, and for the country in general.

The alternative GEF scenario will facilitate and speed up negotiation for access and benefit-sharing agreements. ABS agreements and contracts do not currently exist and in light of the Nagoya Protocol, the GEF alternative will identify measures for total compliance with its provisions, including introducing a comprehensive ABS framework to enhance access and coordination of information for permitting and monitoring as well as support community protocols of securing PIC and MAT and ensuring the fair and equitable  sharing of  both monetary and non-monetary benefits for the use of the genetic material, products, and knowledge. See table 1 below for a summary of the detailed benefits.

6) Global Environmental Benefits

The GEF alternative will improve landscape management, allow the Philippines to better comply with the Nagoya Protocol, and provide benefits at the National and community level. This will be done by strengthen the commercialization of two genetic resources (Banaba and Pili) and the generation of benefit-sharing and distribution for identified IP communities (see PRODOC Annex 7:Stakeholder Engagement). The resources will allow the development of final products, strengthen local producers’ ability to sustainably manage the two identified genetic resources, improve the product material, increase supply capacity, promote commercialization, and validate a framework for benefit-sharing. The project will provide global environmental benefits through the sustainable use of Banaba and Pili.  and the successful implementation of the project will demonstrate that it is possible to create value chains with the sustainable use of these genetic resources. Through successful implementation the project will build trust regarding the financial opportunity which the use of biological and genetic resources offers, as an economic alternative to unsustainable exploitation of biological resources. With successful implementation the project has the added value of facilitating further R&D, which can lead to greater wealth creation for the country in the long-run.

A key global environmental benefit of the project is the equitable sharing of benefits derived from the utilization of Banaba and Pili. The project will improve the management of globally important biodiversity at the landscape level through the targeting of 41,662 Ha for pilot ABS initiatives. This will raise awareness among local communities of the importance of these landscapes for plant genetic resources and provide greater local support for strengthening the management and sustainable use of the genetic resources in these landscapes. At the species level, both Banaba and Pili will benefit directly from project interventions in terms of increased population viability as well as a greater understanding and appreciation of their medicinal and other values to society. Most importantly, the genetic resources and associated traditional knowledge will become more widely appreciated, all of which will strengthen conservation measures, given the high incidence of traditional lands/domains within KBAs that the pilot interventions will target.

Many of the Philippines’ plants and genetic resources remain undiscovered, others are yet to be thoroughly studied and large numbers remain under-utilized. A number of these species are likely to be at risk from reductions in their gene pool and, in the case of rare and endemic species within the landscape, a few may be facing extinction. In the Philippines, in a study commissioned by UNDP Philippines, it is estimated that the bioprospecting value of recorded endemic species in a closed canopy forest is USD 39.8 million annually in perpetuity. It was also estimated that the country loses around USD 8.1 million annually in foregone potential royalty fees for just one pharmaceutical product that was not patented.8 This demonstrates that as a mega-diverse country, the Philippines has considerable untapped wealth which can be generated from sustainable management of its rich genetic resources. The project will seek to change these patterns, by streamlining the current regulations, facilitating inter-governmental coordination and demonstrating successful benefits sharing utilizing in situ conservation measures.

To carry out this work the GEF will invest USD 982,000 in strengthening the national framework for implementing ABS in accordance with the Nagoya Protocol (Component 1 of the project). The counterpart funding for the achievement of Component 1 of the project is USD 542,282.  GEF will allocate USD 1,374,300 for raising awareness and building capacity building for implementation of national ABS Framework (Component 2) with counterpart funding of USD 422,322. Finally, GEF will allocate, USD 1,652,940 for demonstrating benefit-sharing agreements (Outcome 3) with counterpart funding of USD 20,556,766.

The project’s baseline finance has been assessed at approximately $187 million (Table 1), with USD 17.4 million leveraged through this project.

Table 1. Project Baseline Finance and Co-finance

| Baseline Investment (B) / Co-financing (C) | Total (USD) | In-kind co-financing (USD) | Leveraged co-financing (USD) | Total Co-financing (USD) |
| --- | --- | --- | --- | --- |
| DENR | 58,274,735 | 2,024,735 | 3,439,864 | 5,464,599 |
| DA |  |  | 2,752,600 | 2,752,600 |
| DOST - PCAARRD | 100,000,000 |  | 907,692 | 907,692 |
| LGUs |  |  | 2,000,000 | 2,000,000 |
| Industry - Research | 4,090,619 | 90,619 | 269,813 | 360,432 |
| Industry - PhilPili |  | 2,100,000 | 1,408,800 | 3,508,800 |
| State Universities |  |  | 6,527,247 | 6,527,247 |
| Bilateral | 25,110,417 |  | 110,417 | 110,417 |
|  |  |  |  | - |
| TOTAL | 187,475,772 | 2,190,619 | 17,416,432 | 21,631,787 |

Table 2 below presents a summary of the baseline situation, the GEF alternative, and the incremental intervention.

Table 2. Summary of GEF Incremental Intervention and Benefits

| Baseline situation (B) | GEF Alternative (A) | The Increment (B-A) |
| --- | --- | --- |
| Conservation and Sustainable Management of Genetic and Biological Diversity |  |  |
| Conservation of genetic resources and biological diversity does not take account of their full economic value and benefits to current and future generations as well as the transfer of economic benefits to local communities as incentive for their conservation Including: (I) No functional mechanism established for BS at community and local levels; (2) No mechanism for investing monetary and non-monetary benefits derived from the negotiation of benefit-sharing agreements; (3) No clear policy on how benefits are allocated; (4) Rules or system of reinvesting part of benefits from GR and TK into biodiversity conservation and community development are not in place | An incentive mechanism in place that ensures economic benefits to IPs and local communities Incentive system for the private sector to include biodiversity conservation in their business models A system which plows back revenues derived from products and processes of genetic resources and traditional knowledge to local areas where the resource is endemic or indigenous | Improved management and sustainable use of Banaba and Pili (though pilot ABS agreements and biodiversity management plans for in-situ conservation and management introduced into pilot agreement) Competitive pressures between uses of biodiversity and forest and biodiversity degradation and destruction reduced. Establishment and institutionalization of mechanism to channel ABS monetary benefits to local communities |
| National ABS Framework |  |  |
| Weak national regulatory and administrative system for ABS promotes overlapping and conflicting authorities for management of genetic resources and not in line with the Nagoya Protocol. Including: (1) ABS policies are in place (see Situational Analysis Annex 11) but not much progress has been made on bioprospecting and commercialization; (2) Access to GR has been highly bureaucratic with multiple agencies involved in issuing access and collection permits; (3) Processes for securing FPIC has been protracted; (4) Absence of coordination mechanism amongst ABS agencies at the national level and from local to national to promote compliance: (5) Absence of a systematic way to document and register TK has resulted in piracy of TK on medicines and industrial products developed by IPs and scientific research results of students, researchers and scientists; (6) No monitoring in place when gratuitous permits or its results are made commercial; (7) Current, ABS rules and regulations are not integrated in Research, Project Development plans | Enabling National ABS regulatory and permitting framework Streamlining the processes for clear procedures, protocols and guidelines for bioprospecting, research and development Functional mechanism, including administrative system, institutional arrangements, monitoring and financing mechanism in place to facilitate implementation and compliance of the national ABS framework System for protection of local and traditional knowledge | Increased wealth creation through safeguarding Philippines’ biological resources and its genetic diversity from unfair exploitation Improved knowledge and experience gained through the project contributes to global knowledge of ABS and international community of practice (through the integration of a KM platform established for on-going and pipeline researches, traditional knowledge of IPLCs, and access permits) Development of an inter-agency framework for monitoring and tracking GR |
| Capacity |  |  |
| Weak institutional capacity of state agencies constrain the development and implementation of national and local ABS norms, weak capacity and awareness of IP and local communities who hold traditional knowledge undermine the value of the genetic resources and their benefit and weak or limited understanding and awareness from the private and research sector limits the opportunities to engage on ABS partnerships. In the capacity assessment scorecard, 15 ABS institutions assessed themselves as having zero to one (some capacities exist) in ABS under five core areas (refer to Annex 14. Capacity Assessment). At the local level in both regions, they have no knowledge on ABS and have almost none on capacities generate, access, and use information and knowledge on ABS | Enhanced capacity and capability for the negotiation, implementation and monitoring of ABS Improved awareness and understanding of role and benefits of ABS A community of practice on ABS developed A national ABS KM platform/database linked with national biodiversity and genetic resources database | Increased knowledge and awareness of values of biodiversity and steps to conserve and use it sustainably will improve conservation status of species Improved capacity and skills to manage biodiversity and genetic resources improved conservation outcomes (as measured by increase in UNDP ABS scorecard) A better understanding of value of traditional knowledge on biological diversity enhances opportunity for its sustainable use and long-term conservation Improved financing for ABS related initiatives |
| Piloting of ABS Agreement |  |  |
| Limited in-country scientific research capacity and experience with negotiation and implementation of ABS agreements constraints the capture of economic benefits of genetic resources Including: (1) Commercial GR developers would continue product development at their own pace and priorities due to limited incentives, support mechanisms and precedence to pursue ABS; (2) Drug development based on Banaba is on track based on government support via Tuklas Lunas. However, developing inclusive value chains may not be prioritized given the lack of grounding on ABS principles, and may be satisfied to comply with minimum bioprospecting laws; (3) Pili industry cohesion and product development efforts would be fragmented, with individual members racing to produce first to market with primary motivation of attaining market share and/or cost leadership. This mindset may not support the industry's vision of an equitable Pili value chain leading to sustainable inclusive development and preservation of wild Pili plantations. | Demonstration of 2 pilot ABS agreements compliant with national legislation and Nagoya Protocol Demonstration of TK registers and the development of bio-community protocols On the ground experience and demonstration and lessons that will inform future negotiation of fair benefit sharing agreements | Improved knowledge and experience gained through the project contributes to global knowledge of ABS and international community of practice In situ conservation measures and improved management in place to ensure security of concerned species in pilot site targeting 41,662 Ha |
| Current baseline expenditure and investments at approx.: $187 M, broken down as in Table 1, above | Alternative: Baseline + GEF + Co-financing net of baseline: $192 M | The incremental costs: GEF $4.38M |

7) Innovativeness, sustainability and potential for scaling up.

Innovation: This is the first project on ABS that intends to demonstrate the full stream of compliance with Nagoya Protocol, from bioprospecting to R&D to product innovation and commercialization. Specific innovations of the project include the following: Enabling on-the-ground institutional mechanisms, customary laws as well as the community protocols of indigenous peoples and local communities, to be operationalized in line with a specific legal provision in Section 35 of the Indigenous Peoples’ Rights Act. This innovation is already covered by the law but very few are aware of it, other than some civil society organizations working with indigenous peoples and the Biodiversity Management Bureau who have been using it for quite some time. This institutional mechanism will complement the existing regulatory framework of the National Commission on Indigenous Peoples, especially in areas where it is the community that decides to use their customary laws and community protocol to deal with a specific bioprospecting application. In this sense, it is a supplementary institutional mechanism, which also serves to remedy the usual bottlenecks in administrative decision-making on access to biological and genetic resources concerns that are typical of national agencies with far-flung regional service centers. The use of customary laws and community protocols in securing fair and equitable benefit-sharing from the utilization of traditional knowledge associated with genetic resources is one innovation that has not yet been implemented and documented, at least in the Philippine setting.

Unlocking the full potential of both target genetic resources  will be done by reinforcing and corroborating the established benefits from traditional knowledge, current usage and R&D. For Pili, it will capitalize on the growing recognition of it being the healthiest nut by advancing its fatty acids, antioxidant and other micronutrient content into useful medicinal, cosmetic and functional food. Most of its by-products (e.g. pulp, discarded kernels, leaves) have existing R&D whose commercial feasibility will be pursued by applying suitable technology with an eye towards market competitiveness. Banaba on the other hand, can rely on its inclusion in other drug formulations as a means of overcoming the numerous patents on anti-diabetic claims. Ultimately, the innovation is further made more profound by the multi-benefit arrangement of ABS.  Table 2 below provides a summary of the R&D profile for both Pili and Banaba including a description of the genetic resources the project is targeting for R&D as well as the potential end product developed. More detail on the specifics for R&D are included in the PRODOC under the description for Component 3, as well as Annex 12. Site Selection.

Table 2. Summary of R&D Profile for Pili and Banaba

|  | Pili (Canarium ovatum, C. luzonicum) | Banaba (Lagerstroemia speciosa) |
| --- | --- | --- |
| Description of genetic resources and derivatives of Pili and Banaba | Bioactive alkaloids, flavonoids, glycosides, saponins, sterols, tannins, terpenens, and fatty acids found in pulp that support antioxidant and antibacterial claims. Terpineol, elemicine, elemol, dipentene, phellandrene and limonene derived from Pili sap that support antibacterial claims | Corosilic Acid, Ellagic Acid and Ellagtannins derived from dried Banaba leaves |
| Description of the biotechnology used to develop potential products from the genetic resources or derivatives of Pili and Banaba | Press extraction and refinement for pulp oil. Steam distillation for sap to become essential oil | Post-harvest drying then spray drying for raw material preparation. To be determined as crude formula or synthesized isolates in drug formulation |
| Potential products developed from project R&D | Cosmetic products with antioxidant and antibacterial benefits | Antiviral drug formulation |
| Private sector or public biotech/research organizations to carry out product development | Manufacturers under Philippine Pili Industry League Inc. (PhilPILI) which have pledged co-financing under project | Pharmalytics Corp, and Herbanext Corp. under Tuklas Lunas national drug development program |

The wildlife, biological and traditional knowledge research sectors in the Philippines are largely unaware of this decentralized mechanism and, for the first time, may be able to secure free and prior informed consent directly from the communities using customary laws and community protocols whereby they can be active partners with them in designing the research goals and objectives from the outset of the project through to completion. The application of the various monitoring and tracking mechanisms (checkpoints and the internationally recognized certificate of compliance), of the Nagoya Protocol is a first for a megadiverse country that affirms the rights of indigenous peoples and local communities.

A key aspect of  the ABS system is  the monitoring of the utilization of the genetic resources (GR) and associated TK and the negotiation and  implementation of the MAT, particularly  when the  GR and associated TK leave the Philippines. Towards this end,  a system of  tracking  such  utilization  and  implementation of the MAT will be  developed, and this system will be supported by a national ABS clearing house. This innovation will be integrated into a knowledge management platform for ABS to capture and disseminate lessons, case studies, and good practice nationally, regionally, and globally.

Sustainability: The basis for the environmental sustainability of the project’s outcomes lies mainly in the improved capacity of national and local stakeholders to utilize the ABS mechanism to support biodiversity conservation and its sustainable use. The project will support pilot initiatives to develop products derived from the utilization of genetic resources, which will generate monetary and non-monetary benefits to be used to support conservation efforts in the areas with KBAs. In addition, the project will consolidate a local base that will be essential for the long-term conservation of the biological and genetic resources present in these areas. This will be achieved by working closely with the local communities and IPs, who have a significant amount of traditional knowledge about these areas, and through the fair and equitable sharing of benefits derived from the utilization of genetic resources.

- Institutional sustainability will be achieved through the improved capacity of the stakeholders associated with ABS across the Philippines (government agencies, public and private research organizations, the private sector and key industries, and local communities/IPs) to effectively manage access to genetic resources and ensure the distribution of benefits. The establishment of fundamental and functional institutional arrangement for ABS management with involvement of national and local institutions associated both with access to biological resources and related traditional knowledge will provide an institutional structure that will be expected to provide the backbone for future ABS in the Philippines. At the national level, strengthening the national framework for implementing ABS in accordance with the NP will greatly contribute to change the way access and sharing benefit of genetic resources is managed in the Philippines, leading to a more equitable, fair and sustainable use of genetic resources. After the completion of the project, awareness and capacity of all stakeholders on implementation, compliance, monitoring and tracking of the national ABS framework will be significantly enhanced. Providers will better understand the value of genetic resources they own and become more capable of negotiating with the user on benefit sharing in accordance with the ABS principles. Users will be more aware of their responsibility to share benefits of genetic resources with the providers, thus creating a legal MAT for clarification and transparency related to use of genetic resources for commercial and research purposes, as well as ensuring benefits from utilization of genetic resources are shared equitably and fairly between the state and communities. This provides the basis for ensuring the sustainability of the public-private community partnerships in genetic resource use and management of ABS related concerns that overall contribute to biodiversity conservation and social security at the household and community levels.

- Social sustainability: The social sustainability of the project will be achieved by developing capacities among local communities and IPs regarding ABS and the Nagoya Protocol, including the negotiation of ABS agreements, obtaining PIC/FPIC, establishing MAT, and the sharing of benefits. Through the implementation of pilot initiatives on ABS, the selected communities will have direct experience in implementation of ABS and will be aware of the multiple derived benefits. Additionally, there will be capacity-building for other stakeholders such as private businesses and key industries and researchers to generate awareness of the benefits associated with biodiscovery and ABS agreements.

- Financial sustainability will be achieved through the development of a clear and transparent permit system, the project will contribute to encourage private investments in bioprospecting and lead to future benefits for other communities and ecosystems. Moreover, at the pilot scale, when products are successfully produced and sold, the value chain and the distribution of benefits derived from it will be maintained. The increases of  financial flow from users of genetic resources will not only directly benefit target pilot sites but also the broader communities living in genetic resource diversity areas due to increased opportunities for income from activities such as collecting, cultivating, harvesting and transporting the targeted species for commercialization products. Outcomes from Component 3 will demonstrate the various approaches to increased financial and economic sustainability. Through policy support for ABS, including delineating clear and accountable institutional arrangements and financing for ABS implementation, the project will also work to unlock available financing for ABS through the national budget.

Potential for scaling-up: The government is committed to replicating and scaling-up project results to other sectors and species and is committing national resources to ensure project success. Several strategies for replication are embedded in the project design including in improved capacities of GR producers to negotiate based on increased ABS awareness as well as improved capacities of NCAs to implement NP ABS compliance through the use of a digital national clearinghouse, which should lead to additional agreements.

Moreover, given the  high diversity of genetic resources and associated TK  in the country,  a national road map identifying  GR and associated TK with the highest potential for new discoveries supporting commercial (e.g. drug development, personal care and cosmetics, industrial biotechnology etc.)  and non-commercial uses (e.g. taxonomy, ecosystem analysis) will be developed.  The roadmap shall include components on research, capacity building, institutional arrangements, financing and cross cutting components on gender and rights empowerment.

Upscaling comprises enabling existing markets to expand once enterprises have consolidated their supplies of TK-based products and then mainstreaming models of best practices across other regions of the country. Given that there are at least 110 indigenous peoples in the Philippines scattered in recognized ancestral lands that are very often in or near to KBAs, upscaling of this project has every chance of being successful provided the management of genetic resources is shown to be demonstrably sustainable based on rigorous monitoring and evaluation procedures. Upscaling of traditional knowledge-based enterprises is also a key component of the Philippine Wealth Creation Program and, therefore, will be an important contribution towards the attainment of the Program’s objectives.

2.  Stakeholders.

Throughout the project development process stakeholders from national government, local government, the private sector, indigenous communities, academia and others have been actively engaged. This is evidenced by the overall consensus reached during the project’s validation workshop as well as the level of co-financing secured. Stakeholders participation will continue to be a top priority for the project and will be sustained throughout implementation.  The formulation of the stakeholder engagement plan aims to:  (a) identify the basic roles and responsibilities of the Project partners and stakeholders in relation to the three components of the Project;  (b) ensure their participation in project activities; and (c) build strong partnerships and collaboration to maximize their knowledge and skills to achieve measurable results. Ultimately, the stakeholder engagement plan aims to ensure long- term sustainability of the project achievements, based on transparency and the effective participation of the key stakeholders. A comprehensive gender-responsive stakeholder engagement plan is included in Annex 7 of the PRODOC.

Select what role civil society will play in the project:

X Consulted only;

X Member of Advisory Body; contractor;

Co-financier;

X Member of project steering committee or equivalent decision-making body;

Executor or co-executor;

Other (Please explain)

3. Gender Equality and Women's Empowerment.

According to the UNDP gender marker standards, the project has UNDP GEN2 gender marker.  Key gender-disaggregated indicators and targets in the project results framework and monitoring plan will be tracked throughout project implementation. The project has set targets to engage women in project activities at a rate that is greater than the percentage of women in the agencies. These targets mean that the project will preferentially target women for involvement in related project activities to proactively encourage the engagement and empowerment of women in the participating communities and ensure that women are key beneficiaries of the project.

At the project onset, efforts will be made to ensure that gender-differentiated roles and practices in relation to natural resource use and access and benefit sharing of the two target species are defined. This will be done through a gender-smart, ABS-compliant value chain analysis of Pili and Banaba in Regions 3 and 5, respectively, which will especially focus on the PIC/FPIC and MAT, and commercialization and conservation stages of the chain, which have been identified as gender gaps that need to be addressed.

The project will ensure that wealth is created and shared among Filipino women and men as a result of sustainable use of genetic resources and its associated traditional knowledge. As part of the effort to strengthen the national ABS framework, current ABS policies will be enhanced so that rights, roles and responsibilities of women and men are recognized and clearly defined and their legal access to genetic resources is facilitated. Similarly, awareness and capacity building on ABS shall empower women and men from different ABS-related fields and sectors – regulatory, science and research, business development and innovation, community development – to meaningfully participate in ABS; challenges such as the lack of confidence and skills of indigenous and local communities to communicate and negotiate ABS-related concerns shall also be addressed. The pilot ABS agreement targeted by the project shall also ensure equal access to business and other economic opportunities by women and men, mindful not to further gender stereotypes nor widen inequalities, and addressing socio-economic concerns such as unpaid care work so as not to add to the burden of women. Some key gender mainstreaming approaches are summarized in Table 3 below.

Table 3. Gender Mainstreaming Approaches by Project Component

| Component 1. Strengthening the national framework for implementing ABS in accordance with the Nagoya Protocol | - Gender will be strategically mainstreamed in the revised and harmonized rules and regulations for ABS - Women and men stakeholders and communities will meaningfully participate in bio-prospecting research and development processes - Functional mechanism shall be managed by a dedicated inter-agency working group on ABS with gender expert agencies (Note: This is a PBSAP indicator) - Gender-balance for membership n in national coordinating mechanism - Collection of gender-disaggregated data through the national ABS clearinghouse |
| --- | --- |
| Component 2. Awareness raising and capacity building for implementation of national ABS Framework | - Women and men will benefit from a national roadmap on ABS, which will include a recognition of their important roles in safeguarding biodiversity species conservation. - CEPA plan will deliberately target women to encourage their participation in the various aspects (R&D, science, business, conservation etc.) of ABS - Gender balance will be achieved in all capacity building programs and activities through equal opportunity for women and men trainers/resource speakers and participants. - ABS IEC and capacity building materials convey gender sensitivity and use of gender-fair language - Local knowledge (IP and non-IP) shall be validated, documented and disseminated to women and men stakeholders. - Gender balance for participation in any South-South Exchange - Documentation of good practices and lessons learned with gender perspective |
| Component 3: Demonstrating benefit-sharing agreements | - The R&D output shall include socio-cultural aspects, including the roles of women, men and children, in the natural resource use of Pili and Banaba - Women and men will benefit from the commercialization of Pili and Banaba and possible issues such as gender biases in the business and scientific community and gender pay gaps will be analysed and addressed - The model ABS agreement will provide opportunities to address gender inequalities and empower women such as by increasing women’s access to technology and participation in generating traditional and scientific knowledge, and securing livelihood opportunities for women and men along the Pili and Banaba value chains - The conservation measures that will be put in place will also allow women and men to save their time and gain and apply new knowledge and skills on sustainable Pili cultivation and Banaba harvest, including health and safety practices |

Does the project expect to include any gender-responsive measures to address gender gaps or promote gender equality and women’s empowerment? (yes X /no) If yes, please upload gender action plan or equivalent here. A full gender analysis and action plan are included in the PRODOC, Annex 9.

If possible, indicate in which results area(s)  the project is expected to contribute to gender equality:

X closing gender gaps in access to and control over natural resources;

X  improving women’s participation and decision making; and or

X  generating socio-economic benefits or services for women.

Does the project's results framework or logical framework include gender-sensitive indicators? (yes X/no )

# 4. Private Sector Engagement.

# The private sector and academia have also been actively engaged during the PPG process including committing 3.879 M USD  and 6.534 USD in co-finance, respectively. Industry will continue to be actively engaged throughout most project outputs including awareness raising on the ABS framework;  capacity-building;  preparation of the ABS R&D Roadmap; preparing and using policies, guidelines and protocols; providing resources and contributing to value chain development t; demonstrating PIC/FPIC and MAT, direct investments, facilitated access to genetic resources, using R&D results, and practicing ABS. Among the industries that have been initially identified that the Project will work with include:   Philippine Pili Industry League, Inc. (PhilPili), Herbanext, Pharmalytics, Leonie Agri Corporation, Chamber of Cosmetics Industries of the Philippines (CCIP)  and Chamber of Herbal Industries of the Philippines (CHIPI).

# Research institutions will be engaged to work with and benefit from the project’s support to research as well as communication, education and public awareness, and  capacity building activities for the implementation of national ABS framework to ascertain that their respective policies, plans, strategies, and programs involving genetic resources are compliant with the Nagoya Protocol. They  will participate in product development towards ABS agreements and its related studies like IKSP and TK documentation,  Ethnobotany studies, biodiversity surveillance and resource assessment (i.e., abundance and species richness, vegetation, structure), biogeography (identification of locations, ecological factors) characterization (morphological and molecular identification),  bioassays,  prototype product development,  sustainable production technology and use of raw materials,  technology transfers,  and  market and value chain analysis. and, and related activities to support in-situ conservation. They will also participate in reviewing existing policies,  formulating harmonized rules and regulations as well as procedures, protocols and guidelines for bioprospecting,  and creating structures, processes, mechanisms, and financing to facilitate the implementation and compliance of the ABS framework. PRODOC Section IV Results and Partnerships and Annex 12: Site Selection provide more details on how the private sector.

# 5. Risks.

# The identified project risks, their overall rating and the mitigation actions required during project implementation are provided in Annex 5 of the PRODOC. Risks are only shown if their rating is considered to be Moderate or High, with the exception of risks identified in the Social and Environmental Screening Procedure (SESP, Annex 4) which are all described.  As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk register (Risk Log, Annex 5).  Risks will be reported as critical when the impact and probability are high. Management responses to critical risks will also be reported to the GEF in the annual PIR.

# The SESP was finalised during project preparation, as required by UNDP’s Social and Environmental Standards (SES). The SESP identified eight risks for this project that could have potential negative impacts in the absence of safeguards, six of these risks were rated as Moderate and two as Low. Therefore, the overall SESP risk categorization for the project is Moderate. Depending on further revision to assessments of risks, detailed assessments and management plans may be required. The following safeguards are triggered: Human Rights; Gender Equality and Women’s Empowerment; Biodiversity Conservation and Natural Resource Management; Climate Change Mitigation and Adaptation; Cultural Heritage; and Indigenous Peoples. The Moderate risks are as follows:

# Risk 1 (Moderate): The Project could potentially discriminate against local communities and other indigenous peoples from other parts of the Philippines who share the same TKs/ IKSPs associated with the species selected in the Project in ABS agreements.  For ground level activities, the project has developed an ESMF (Annex 8) and a Stakeholder Engagement Plan (Annex 7).  Per the Philippine’s government’s preference an issue specific management plan for IPs has also been developed (Annex 13).  All aforementioned plans fully consider IPs rights and standards under the Nagoya Protocol, other international laws and agreements, and national laws and regulations.  The Project will mitigate this risk at the National Level by policy proofing through a process that follows Strategic Environmental and Social Assessment (SESA) principles.

# Risk 2 (Moderate): The Project could potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits if gender roles,  relations, and capacities in the Project area are not clearly understood and gender is not mainstreamed across all Project components and the implementation of the Gender Plan is inadequate.  At the policy level, gender will be strategically mainstreamed in the revised and harmonized rules and regulations for ABS, as well as in the functional mechanisms that will be put in place to operationalize it. In the work related to building awareness and capacities around ABS, women and men stakeholders will be provided with equal opportunities to be engaged in the various aspects (research and development or R&D, science, business, conservation, etc.) of ABS. In particular, local and indigenous stakeholders will be capacitated to communicate and negotiate more effectively for the conservation of biodiversity and access to both monetary and non-monetary benefits arising from ABS agreements. At the target site and species level (pili and banaba), the Project will specifically address the lack of gender-smart and ABS-compliant value chain models in the Philippines.

# Risk 5 (Moderate): Typhoons and other climate change exacerbated phenomena could affect the achievement of outputs and outcomes of the Project, especially under component 3. Currently, the timing, paths and intensity of typhoons do not follow previous patterns. Increased and more serious flooding have also been observed in recent years. Climate change resiliency measures and analysis will be made integral to ABS processes and reflected in partner community/ LGUs local plans.  The Project will also support data gathering on community resilience, climate change impacts including indigenous/ traditional indicators will be generated and analyzed for informed decision making.

# Risk 6 (Moderate): The Project proposes to access and develop genetic resources and associated IKSPs for commercial purposes. Exploitation of genetic resources in ancestral domains and associated IKSPs of IPs, including issues of authorship and ownership of intellectual property rights may arise. The Project recognizes IPs rights to GR and associated IKSPs in accordance with UNDRIP, UNCBD Nagoya Protocol, and IPRA and will mitigate the issue through FPIC Processes, MAT as well as policy proofing. The Project will ensure that the issues of democratization of knowledge production, authorship,  and intellectual property issues  are thoroughly discussed during the FPIC Process and are resolved in the MOA that will be signed between and among parties.

# Risk 7 (Moderate): The Project could potentially restrict access/use of natural resources by IPs. In consideration of the Expanded National Integrated Protected Area Systems (ENIPAS) Act, the Project will recognize IP rights to govern, maintain, develop, protect, and conserve such areas, in accordance with their customary law and IKSPs, with full and effective assistance from the NCIP, DENR and other concerned government agencies.  The Project will also recognize and respect indigenous governance and leadership structures and work with the established coordination and complementation structures and mechanisms between and among the IP leadership, NCIP, DENR, LGUs and civil society.  Furthermore, following the IPRA, restrictions of access which have impacts to IPs, whether positive or negative, also have to comply  with the FPIC requirements of the law.

# Risk 8 (Moderate): Indigenous, community-owned land arrangements and indigenous-claimed resources might be affected by commercial cultivation, threatening traditional cultural socio-economic dynamics and potentially generating conflict within indigenous communities. Overall, the Project is designed to strengthen the fair and equitable sharing of benefits derived from the access,  use, and commercialization of genetic resources, through both ABS pilots and other systemic measures. However, experience from  other business endeavors indicate that negative cultural change as well as tensions and divisions among IP communities arise with the influx of money from royalty payments.  As described in the Indigenous People’s Framework IPF, the Project will mitigate this with a range of capacity building activities (i.e. community organization, financial management).

In addition to the above moderate risks identified in the SESP, Annex 5 highlights a risk on COVID-19 or Similar Crises: COVID threats have been prevalent during the project design and are expected to have long-lasting impacts on people’s health, security, safety and economic conditions. COVID-19 or similar crises are expected to result in delays of project implementation, affecting health of beneficiaries, limiting areas in which the project can be implemented, limiting face-to-face consultations among stakeholders, further marginalizing the disenfranchised that have limited access to resources and technology. Due to the rapid spread of the pandemic, risk mitigation procedures will be developed to address possible operational delays or pauses on an ongoing basis, to follow the latest guidance and advisories from Government, UNDP and GEF Sec. Increased communication will be considered when consulting with local beneficiaries regarding possible impacts, and site specific protocols will be followed. Changes in the scope or timing of planned activities may be necessary through workplan adjustments. The Implementing Partner, together with the Project Board, will monitor and address significant financial constraints arising from exchange rate fluctuations and any delays or failures in co-financing delivery. Alternative access technology/communication tools that can be utilized during Project implementation will also be explored by the Implementing Partner, together with the Project Management Unit. WhatsApp and mobile phones, which many have access to, will be used for communication and exchange of information. The Project Management Unit will have to be mindful of the kind of resources that are available to beneficiary groups, specifically the communities with which the Mutually Agreed Terms (MATs) will be signed. The Communications Strategy will also include specific considerations for communication, public awareness and exchange of information under these circumstances.

Overall, the project is expected to result in positive impacts for  biodiversity conservation, aiming to ensure environmental sustainability mainstreaming into the bioprospecting sector of Philippine  economy. The envisaged long-term solution for the project highlights the environmental benefits that the project will generate and ensures that environmental and economic sustainability are mainstreamed into the bioprospecting sector. The Project is designed to include  in-situ conservation measures to ensure the security of the genetic resources; these measures will be integrated into the negotiated MAT. Among others, the Project will support the conduct of resource inventory of resources including geotagging of the resources  to  determine species abundance and availability of resources for bioprospecting. IPLCs  will be supported in preparing resource management plans and strengthening of their cultural practices in plant  propagation, nursery development, planting and harvesting protocols. The Project will work with LGUS from the barangay, municipal and provincial level to enforce and monitor conservation of genetic resources.  At the National Level,  a system of  tracking  such  as  utilization  and  implementation of the MAT will be  developed, and this system will be supported by a digital platform, the  national ABS clearing house

An Indigenous People’s Framework has been developed that provides guidance for ensuring that Indigenous Peoples are fully involved in decision-making in terms of resource use, livelihood and income generation investments and conservation action. The project will support the recruitment of an E&S Safeguard expert to help develop and monitor the application of FPIC principles, undertake social assessments in IP areas and train and sensitize staff in the application of FPIC principles and practices. For further information on social and environmental aspects and management measures refer UNDP SESP PRODOC Annex 4, the Environmental and Social Management Framework (PRODOC Annex 8), and Indigenous People’s Framework (PRODOC Annex 13).

In line with UNDP standard procedures, the Project will set up and manage a grievance redress mechanism (GRM)  that would address project affected persons’ (PAP) grievances, complaints, and suggestions. The GRM will be managed and regularly monitored by the PMU.

6. Institutional Arrangement and Coordination.

The Project will be implemented following UNDP’s National Implementation Modality (NIM), according to the Standard Basic Assistance Agreement between UNDP and Government of the Philippines and the Country Programme.

The Implementing Partner for this Project is the DENR-Biodiversity Management Bureau (BMB). As the Implementing Partner, DENR-BMB is the accountable agency for managing this Project, including the monitoring and evaluation of Project interventions, achieving Project outcomes, and for effective use of UNDP resources.

The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document. Please see PRODOC section VII. Governance and Management Arrangements for full details of the institutional arrangements of the project.

# 7. Consistency with National Priorities.

# The project aims to demonstrate how the provisions of the Nagoya Protocol (NP) on ABS can be applied to the Philippines’  national context, which is one of high biodiversity alongside high ethnic and linguistic diversity that has resulted in a wealth of knowledge about plant and aquatic genetic resources and IPLCs. The project builds on twenty years of initiatives on the part of the Philippine Government to implement Article 15 of the CBD and, more recently, applying the NP on ABS that came into force in 2015.  The project will  provide the enabling  administrative system including  building the capacity of government to implement the proposed  executive and legislative measures currently  under consideration by the President and  both Houses the Philippine Genetic Resources and Access and Benefit Sharing PGRABS  Bill (for HB 2163) which has been approved at the level of the House Committee on Science and Technology at the committee hearing (August 2018). The PGRABS bill  is “an act strengthening the national policy on wealth generation from access, benefit-sharing from the utilization of Philippine genetic resources and for other purposes.”

# The project is also consistent with the country’s Philippine Development Plan 2016-2022, specifically Chapter 20 which specifies ABS as a strategy in developing and expanding resource-based industries. This is also consistent with the area-based convergence programme entitled “Sustainable Integrated Area-Based Development” of the DENR which began implementation in 2017. It identified priority areas including the sites that are nominated as pilot/demonstration sites for this proposal.  Similarly, the project will contribute in the implementation of the key priorities defined in the Philippine Biodiversity Strategy and Action Plan 2015-2028, particularly the Roadmap for Realizing Access and Benefit-Sharing in the Philippines where close synergy among the various agencies for implementing Joint DENR-DA-PCSD-NCIP Administrative Order No. 1, Series of 2005 or the 2005 Guidelines for Bioprospecting under the Wildlife Act is called for. It will contribute to the goals and targets of the PBSAP through the strengthening of mechanisms for the assertion by the communities of their rights and the corresponding respect that must be given to such rights by interested stakeholders, particularly the research community and the private sector.

With the Philippines’ ratification of the Nagoya Protocol, the  DENR  has put forward  proposed  legislative  measures to fully  make ABS functional. A draft Executive Order on “Strengthening the National Policy on Wealth Generation From Access, Benefit- Sharing and Utilization of Philippine Genetic Resources”   is also pending at the Office of the President.  Included in these draft domestic  policy measures  are the institutional arrangements for implementing the Nagoya Protocol.  In terms of research, the roadmap designed under Component 1 will build on the identified major research agenda under the Philippines Wealth Creation Program: nutraceutical, cosmetic, pharmaceutical, industrial products. This roadmap will allow for the scaling-up . PRODOC Annex 11: Situational Analysis includes a detailed description of current policy measures as well as a table that outline’s the Philippine government intuitions’ current role under the Nagoya Protocol.

8. Knowledge Management.

Component 2 will target awareness raising and capacity building for implementation of national ABS Framework. As part of that component, output 2.3 of the project focuses on best practices and lessons of ABS documented and disseminated and traditional knowledge of IPLC catalogued and made accessible to all stakeholders. In addition, all the major activities of the project shall have a Process Documentation Research to document best practices, lessons  and insights learned, including documenting the role of women and other marginalized groups.  These processes may include policymaking, development of protocols and guidelines, FPIC and PIC process, developing, implementing and monitoring research roadmaps, negotiating and implementing ABS agreements and supporting in-situ biodiversity conservation efforts.  Results shall be published in different knowledge products.

In partnership with the National Museum, a museum display on the Philippine’s rights over genetic resources recognized by the Nagoya Protocol and the ABS implementation in the Philippines in the National Museum of National History to communicate, educate, and create awareness on genetic resources as our cultural heritage, our sovereign rights over them, the benefits that we can derive from them, and our responsibilities to protect and conserve these resources.  The display will also communicate and educate the public on ABS.   The display maybe conceived as similar to the display on National Integrated Protected Areas System (NIPAS) sites in the Philippines that was done in partnership between the DENR-BMB and the NM.  The Project may also explore the possibility of co-designing and implementing a travelling exhibit on ABS on Philippine genetic resources to various universities around the country.

Finally, the Project will support attendance to and/or conduct of learning events where academic and research institutions as well as concerned government agencies can share progress of ABS initiatives and lessons and insights gained.

9. Monitoring and Evaluation.

Please see PRODOC Section VII Monitoring and Evaluation (M&E) Plan. A table of the budget is reproduced below.

| Monitoring and Evaluation Plan and Budget: |  |  |
| --- | --- | --- |
| GEF M&E requirements | Indicative costs (US$) | Time frame |
| Inception Workshop | 8,000 | Within 60 days of CEO endorsement of this project. |
| Inception Report | None | Within 90 days of CEO endorsement of this project. |
| M&E of GEF Core Indicators and Project Results Framework | 36,000 | Annually and at mid-point and closure |
| GEF Project Implementation Report (PIR) | None14 | Annually typically between June-August |
| Monitoring of ESMF See ESMF Annex 8 and related management plans | Covered above under monitoring of project results framework | On-going. |
| Supervision missions | None | Annually |
| Independent Mid-term Review (MTR) | 48,000 | 12 February 2024 |
| Independent Terminal Evaluation (TE) | 48,000 | 11 August 2026 |
| Total Indicative Cost | 140,000 |  |

10. Benefits.

The strategic development of Pili and Banaba genetic resources have multiple inter-locking opportunities that have strong potential towards equitable wealth creation and inclusive development. The economic benefits may be the initial driver yet the investments towards social and environmental stewardship will determine the ultimate value of ABS.

At the national level, the project will help to facilitate  the use of genetic resources, while being cautious of environmental and social safeguards, through a more proactive and streamlined process to securing PIC/FPIC. As such, if implemented properly, compliance with the Nagoya Protocol will provide resources that will accrue to the specific sector concerned such as those involved in drug and cosmetic product development. More academic and research institutions as well as the private sector will be incentivized to invest in ABS-related researches and product development since financial returns can be expected.

At the local level, the increased activity will lead to added employment and job diversification primarily in participating sites and eventually into replicating regions. The formalization of these supply chains and coordinated R&D activities will lead to various roles well suited for local community stakeholders. Non-traditional roles such as research, audit, maintenance (e.g. conditions of expanded plantations and test fields) are strong compliments for the growth of traditional roles in farming, processing/manufacturing, logistics, quality control, marketing and retail created by developing industries. These are aligned with government programs such as the Department of Agriculture’s (DA) high value crops development but it is important to note the added opportunity when DENR’s National Greening Program (NGP) is supported by policies that allows people’s organizations (POs) that were designated to reforest allowed to gain from the produce of the trees they planted in exchange for continuous monitoring and maintenance. Ultimately, these diversified and added jobs can be protected through capacitating of local community enterprises (e.g. cooperatives, Community Based Forest Management (CBFM)) to become sustainable SMEs.

The viability of these added jobs is contingent on the stable and remunerative income genetic resource development is intended to contribute. Pili and Banaba are tree sources that are known to be relatively more resilient to weather disruption and climate change, thus reducing risk of income disruptions. Furthermore, adaptable technology (e.g. dryers for Banaba leaves), R&D (e.g. superior plant varieties) and capacity building (e.g. agri-trainings to IPs) may lead to extended farming and production seasons.

Fair pricing is a key component to remunerative income as the economic fruits of genetic resource development cannot be left unattended to traditional market players. Standardizing processes and evaluating evolving value chains creates an opportunity to establish fair wage and fair-trade standards based on productivity and quality of life indicators starting with participating communities and adapted to regional and national situations. This does not discount the existence of current and traditional livelihoods, yet it intends to diversify income streams that will generally uplift occupational standards and economic benefits primarily among local stakeholders.

PART IV: ANNEXES

Annex A: Project Results Framework (PRODOC Section V. Project Results Framework)

| This project will contribute to the following Sustainable Development Goal (s): Goal 10: Reduce inequalities – By developing ABS frameworks the project is supporting Goal 10 targets, specifically sustaining income growth and reducing cross border exploitation of resources. Goal 12: Ensure sustainable consumption and production patterns – ABS and sustainable use of biodiversity helps support Goal 12 targets of improving sustainable management and efficient use of natural resources in value chain and building awareness in local communities of life in harmony with nature Goal 15: Life on Land – By contributing to biodiversity conservation and sustainable use this project is contributing to achieving Life on Land Biodiversity targets, specifically, targets for sustainable management of forests, preventing degradation of habitats and loss of biodiversity, curbing demand for illegal biodiversity products, and especially increasing the capacity of local communities to pursue sustainable livelihood opportunities. |  |  |  |  |
| --- | --- | --- | --- | --- |
| This project will contribute to the following country outcome (UNDAF/CPD, RPD, GPD): UNDAF Outcome statement and CPD Outcome 2.3 Urbanization, economic growth, and climate change actions are converging for a resilient, equitable, and sustainable development path for communities. CPD Output statement: Partnerships strengthened, and economic models introduced to reduce biodiversity degradation from unsustainable practices and climate impact |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target |
| Project Objective: Increased economic opportunity and biodiversity conservation for local communities and indigenous peoples in the Philippines stemming from fair and equitable sharing of biodiversity benefits | Mandatory Indicator 1: Direct project beneficiaries disaggregated by gender (individual people, No.) - Female (35%) - Male (65%) GEF Core Indicator 11 | - 0 - 0 | 1.1 1,060 1.2 1,969 | - 2,120 - 3,938 |
|  | Mandatory Indicator 2: Area of landscapes under improved management (hectares; excluding protected areas) 2.1 Hectares Region 3 (Central Luzon) 2.2 Hectares Region 5 (Bicol) GEF Core Indicator 4 (Indicator 4.1 Area of landscapes under improved management to benefit biodiversity) | 2.1: 0 2.2: 0 | 2.1: 15,000 Hectares 2.2: 2,500 Hectares | 2.1: 35,828 Hectares 2.2: 5,834 Hectares |
|  | Indicator 3: Gender-responsive harmonized rules and regulations in place for the implementation of the Nagoya Protocol 3.1 Bioprospecting guidelines and relevant supporting rules and regulations 3.2. NCIP FPIC guidelines and relevant supporting rules and regulations | Rules and regulations for ABS exist but are uncoordinated, inconsistent, and not followed | 3.1 Bioprospecting guidelines and relevant supporting rules and regulations updated and harmonized 3.2. NCIP FPIC guidelines and relevant supporting rules and regulations updated and harmonized | 3.1 Bioprospecting guidelines and relevant supporting rules and regulations adopted 3.2. NCIP FPIC guidelines and relevant supporting rules and regulations adopted |
|  | Indicator 4: ABS Agreements negotiated (No.) | No ABS Agreements have been concluded and approved in compliance with Nagoya Protocol | At least 1 draft agreement completed | At least 1 ABS Agreement successfully concluded |
| Project component 1 | Strengthening the national framework for implementing ABS in accordance with the Nagoya Protocol |  |  |  |
| Project Outcome 1 Strengthening the national framework for implementing ABS in accordance with the Nagoya Protocol | Indicator 5: Mechanism for national implementation of ABS improved 5.1 Inter-agency framework for monitoring and tracking the use of GR and ABS transactions developed (No.) 5.2 Mechanism to channel ABS monetary and non-monetary benefits to local communities and IPs and support biodiversity conservation and sustainable use (No.) | No formal monitoring and tracking framework exist | 5.1: 1 initial draft framework for monitoring and tracking GR developed 5.2: 1 draft mechanism to channel ABS monetary benefits to local communities developed and tested | 5.1: 1 inter-agency framework for monitoring and tracking GR in place 5.2: 1 mechanism to channel ABS monetary benefits to local communities established and institutionalized1 |
|  | Indicator 6: Integrated knowledge management platform to capture ABS documentation including cataloging of TK (No.) | No single place to find centralized and curated information on genetic resources/ABS | 1 Beta version of Integrated knowledge management platform for ABS in place for trial and fine-tuning | 1 integrated knowledge management platform established and institutionalized for on-going and pipeline researches, traditional knowledge of IPLCs, and access permits |
| Outputs to achieve Outcome 1 | - Revised and harmonized rules and regulations to facilitate research and promote ABS agreements - Clear procedure, protocols and guidelines for bioprospecting research and development - Functional mechanism, including administrative system, institutional arrangements, monitoring and financing mechanism in place to facilitate implementation and compliance of the national ABS framework - Access and Benefits Sharing national roadmap developed |  |  |  |
| Project component 2 | Awareness raising and capacity building for implementation of national ABS framework |  |  |  |
| Outcome 2 Enhanced understanding of the ABS regime and the value of traditional knowledge associated with genetic and biological resources for improved policy making and on the ground conservation, sustainable use and fair and equitable sharing of benefits | Indicator 7: Improved capacities of relevant agencies and stakeholders for ABS implementation as measured by an increase in UNDP ABS capacity development scorecard 7.1 National government 7.2 Local government Region 5 7.3 Local government Region 3 | Limited capacity of relevant agencies for ABS implementation as shown by UNDP ABS capacity development score of 7.1 46%/(1.4/3) 7.2: 46% (1.4/3) 7.3: 20% (0.6/3) | 10% increase in agency capacity 7.1 56% 7.2: 56% 7.3 30% | At least 30% increase in agency capacity as measured by UNDP ABS scorecard 7.1 76% 7.2: 76% 7.3 50% |
|  | Indicator 8: Gender-responsive Communication, Education, and Public Awareness (CEPA) plan (No.) 8.1 CEPA 8.2 Change in knowledge, attitudes, and practices (KAP) of target groups | 8.1 None 8.2 None | 8.1 One CEPA developed and tested 8.2 One KAP carried out and initial survey results | 8.1 One CEPA fully deployed 8.2 One Final KAP survey results assessed |
| Outputs to achieve Outcome 2 | - Awareness raising campaign implemented targeted to different ABS stakeholders (user, providers, research institutions, etc.) - Integrated training program and other capacity building measures for staff of relevant ABS agencies and stakeholders undertaken - Best practices and lessons of ABS documented and disseminated and traditional knowledge of IPLC catalogued and made accessible to all stakeholders |  |  |  |
| Project component 3 | Demonstrating benefit-sharing agreements |  |  |  |
| Outcome 3 At least one ABS Agreement negotiated and finalized that demonstrate PIC and MAT and with clear provision on fair and equitable benefit sharing | Indicator 9: Number of potential ABS products identified and tested for potential commercial application (No.) 9.1: Pili (Canarium ovatum and Canarium luzonicum) 9.2: Banaba (Lagerstroemia speciosa) | Several products identified but not through ABS processes: 9.1 Pili (6): cooking oil, animal feeds, biofuel, industrial component (in thinner, paints, sealant, waterproofing), essential oils, cosmetic, medicinal ointment 9.2 Banaba (3): herbal teas, supplements, anti-dengue drug in clinical study | 9.1 At least 1 ABS product identified Pili 9.2 At least 1 ABS product identified Banaba | 9.1 At least 1 ABS product tested for potential commercial application Pili 9.2 At least 1 ABS product tested for potential commercial application Banaba |
|  | Indicator 10: Biodiversity management plan for in-situ conservation and management of biological resources integrated in pilot agreement (No.) 10.1 Region 3 10.2 Region 5 | 10.1 No such plan in place under ABS 10.2 No such plan in place under ABS | 10.1 Region 3: 1 Draft management plan for in-situ conservation developed 10.2 Region 5: 1 Draft management plan of in-situ conservation developed | 10.1 Region 3: 1 Management plan for in-situ conservation integrated into pilot agreement 10.2 Region 5: 1 Management plan for in-situ conservation integrated into pilot agreement |
|  | Indicator 11: Gender-smart and ABS compliant value chain for identified genetic resources mapped (No) 11.1 Region 3 11.2: Region 5 | 11.1 Several potential markets identified but not analyzed across the entire value chain 11.2 Several potential markets identified but not analyzed across the entire value chain | 11.1: 1 Draft value chain Banaba mapped with strategic development road map 11.2: 1 Draft value chain Pili mapped with strategic development road map | 11.1: 1 Value chain Banaba mapped with strategic development road map 11.2: 1 Value chain Pili mapped with strategic development road map |
| Outputs to achieve Outcome 3 | - Research and development conducted for identified species (Pili and Banaba) - Strategic Roadmap for the identification and creation of benefits based on genetic resource development - Negotiate and implement ABS agreement modeling FPIC and PIC processes - In-situ conservation measures to ensure the security of the concerned genetic resources are integrated into the negotiated MAT |  |  |  |

Annex B: Response to Project Reviews

| Comments | Response | Relevant Section of UNDP Project Document and - GEF CEO ER. |
| --- | --- | --- |
| Comments from GEFSEC Review |  |  |
| None |  |  |
| Comments from STAP |  |  |
| - Overall comment: STAP has some specific concerns about the lack of coherent theory of change that should be addressed during PPG phase to increase the likelihood of overall success . Finally, STAP recommends that the project proponents should reflect on the lessons learned and experience in other countries which have attempted to generate local benefits and biodiversity conservation outcomes with ABS. A useful recent review is https://www.ictsd.org/sites/default/files/research/access_to_genetic_resources_and_benefit_sharing_‐ _ruiz_final.pdf | During the PPG process a complete theory of change was developed that incorporated lessons learned and experiences from other countries. The design took into account the review highlighted by STAP as well as a number of other projects including the recently published GEF-funded ABS is Genetic Resources for Sustainable Development (2018), which highlights how 27 countries are “investing in biodiversity for people and planet,” a comprehensive paper Access to Genetic Resources and Benefit Sharing 25 Years on: Progress and Challenges (2018), which argues that there is evidence to suggest the need for a shift in the narrative on, and policy options for ABS that is adapted to a changing R&D landscape , and an earlier study Accessing Biodiversity and Sharing the Benefits: Lessons from Implementation of the Convention on Biological Diversity, (IUCN, 2004). From these and other projects key lessons were integrated into the project design, including: - Taking a multi-stakeholder approach in ABS implementation where the role of private sector as well as communities are emphasized, particularly in the project sites - Selecting species strategically to have both scientific and traditional uses as well as economic value; and - Replicating, the GEF-UNDP Global ABS Project’s methodology for designing a gender-smart, ABS-compliant value chain (Annex 9 Gender Analysis) | PRODOC Section III: Strategy (pp. 16-20) -TOC and lessons incorporate PRODOC Annex 12: Site Selection PRODOC Annex 9: Gender Analysis |
| - Not entirely clear that the total hectares targeted for improved management to benefit biodiversity (10,000 has) will necessarily result from the activities described in the project, particularly since it involves encouraging communities to farm the species involved rather than sustainably wild harvest, which presumably could provide incentives for forest conversion to agriculture rather than conservation (although not enough information is provided to understand this) | - During the PPG, based on deliberations with the Department of DENR, the lead implementing agency in this ABS development program and numerous stakeholder meetings, the species and site selected for the project have changed from the original PIF. The selection was based on the following criteria: (1) the plant species being abundant and indigenous in the selected areas, while considering the possible effect on conservation status by the identified economic utilization; (2) the existing IKSP/TK, trade and other utilization in the market; (3) the available research and product development pointing to the potential of increasing the market value derived from such; and (4) the opportunity for greater local stakeholder inclusion in the value chain. - The project been designed to include in-situ conservation measures to ensure the security of genetic resources; these measures will be integrated into the negotiated MAT (Output 3.4). Among others, the project will support the conduct of resource inventory of resources including geotagging of the resources to determine species abundance and availability of resources for bioprospecting. IPLCs will be supported in preparing resource management plans and strengthening of their cultural practices in plant propagation, nursery development, planting and harvesting protocols. The project will work with LGUs from the barangay, municipal and provincial level to enforce and monitor conservation of genetic resources. At the National Level, a system of tracking such as utilization and implementation of the MAT will be developed, and this system will be supported by a digital platform, the national ABS clearing house. - At the policy and program levels, there are adequate safeguards that ABS activities are pursued with conservation and sustainable use of biodiversity principles. | PRODOC Section III: Strategy (pp. 21-22) Annex 12: Site Selection provides details on the selected species, site selection and provides an overview of the two selected species’ distribution, threat level, R&D, value change as well as conservation and social benefits. |
| - Barrier 1 not particularly well titled, this is more about weak, inconsistent and uncoordinated application of policy framework and their enforcement rather than weak enforcement per see | Barrier 1 wording has been changed to “Inconsistent, uncoordinated application of policy, institutional and regulatory frameworks on ABS implementation” to better reflect the actual barrier . | PRODOC Section III (p. 13) |
| - Are the lessons learned from similar or related past GEF and non‐GEF interventions described; This project builds on several other related activities supported by the GEF, USAID, and others. Not clear that lessons learned from these projects are relevant or have been incorporated into this project apart from the fact that there are significant gaps in policies and capacity building related to ABS that this project hopes to fill. Given the general global failure of ABS to deliver on its perceived initial promise, learning lessons from successful and failed efforts globally is really important here ‐ what has been effective in overcoming roadblocks and securing local benefits and incentives elsewhere? There are very few examples of this really worked ‐ where has it worked and what has made the difference? | Please also see response above in no. 1 In addition, the project looked into the experience of India (GUPTA, Aman. Indian Traditional Knowledge: Leeway towards Sustainable Development. Journal of Intellectual Property Rights Law, [S.l.], v. 1, n. 2, p. 35-41, Feb. 2019. Available at: http://lawjournals.stmjournals.in/index.php/jiprl/article/view/145 . Date accessed: 04 Feb. 2020.) and has incorporated the following into Output 1.3: (i) ABS online filing system; and (ii) Traditional Digital Library. Other successful initiatives from countries supported by GEF were adopted by the project these include (i) the development of customized ABS community protocols and guidelines by local communities and indigenous peoples as potential providers of genetic resources and/ or associated TK (Output 1.2 Clear procedure, protocols and guidelines for bioprospecting, research and development); (ii) the case of Brazil which deregulated access to genetic resources to support more access and innovation, and has thereby received an increase in ABS applications. This is important for the Philippines to see as there is over-regulation but no implementation, monitoring and learning; and (iii) reports that ABS failure in other countries is due to a huge knowledge gaps with regards to understanding the business models of different industries using genetic resource. The project takes this into consideration and has secured commitment with major business players in the Banaba and Pili industry to apply as the resource users and working together with the DENR and ABS institutions towards an ABS product. In this way ABS regulations will be improved with the input of the private industry (Component 3, Annex 7: Stakeholder Engagement) | PRODOC Section IV: Results and Partnerships (Outputs 1.2, 1.3, p. 27, Component 3 pp. 29-31) PRODOC Annex 7: Stakeholder Engagement |
| - The links to in‐situ biodiversity conservation are not clearly articulated. Given that some forms of use of genetic resources do not require any on‐going wild harvest (and the project explicitly supports farming rather than wild harvest), how will such use of genetic resources incentivize ongoing biodiversity conservation? The relationship in component 3 between farming of the species and the BMPs is unclear ‐ will they be wild harvesting or farming? And what is the rationale for either? In relation to Sambong, it appears a patent already exists, and products are in commercial production ‐ so what is the role of securing FPIC (this does not appear to be possible)? More information is needed on the approach taken here and the rationale for this approach | Sambong is no longer one of the species targeted within this project (see response #2 above). The choice of a species other than Sanbong was triggered by DENR and BMB’s decision to select an indigenous tree species which is within their mandate’s jurisdiction. The primary motivation for this is to be able to maximize the country’s biodiversity resources which are indigenous and sets the Key Biodiversity Areas and protected areas of the Philippines apart from the other countries. Through the PPG process a more thorough baseline assessment of the two selected species, Pili and Banaba was undertaken. The project approach has been more fully articulated and the baseline for the targeted genetic resources has been more fully articulated (PRODOC Annex 12). The PPG process has also allowed for more in-depth stakeholder consultations to better narrow the approach which will combine both wild harvesting and farming. There are already resource management plans mandated for ancestral domains, and they have a biodiversity component. The harvesting to be done will require permits, inventory, use of sustainable harvesting protocols, and allowable quotas. | CEO ER #1a Project Description and #6 Global Environment Benefits PRODOC Annex 12: Site Selection PRODOC Annex 7: Stakeholder Engagement |
| - If the pilot isn't successful, for example, how will the project succeed in making the case that the Philippines should invest time and resources into building capacity, strengthening the legal framework, etc. | The project combines various approaches in developing critical ABS experience - working at the top where ABS specific interventions in capacity building and policy are envisioned across sectors (across all research agencies, state universities) and intra-sector (within an agency such as DENR, NCIP, DOH pharmaceuticals and cosmetics). There has also been significant co-financing commitment from the private sector and academia demonstrating commitment to the process. The basis for the environmental sustainability of the project’s outcomes lies mainly in the improved capacity of national and local stakeholders to utilize the ABS mechanism to support biodiversity conservation and its sustainable use. | CEO ER Table C, #7 Innovativeness, sustainability and potential for scaling up. PRODOC Section IV: Results and Partnerships |
| - Indicators, or methodologies, provided to demonstrate how the global environmental benefits will be measured and monitored during project implementation | Annex 12: Site Selection details the geographic areas the pilot projects will target and the methodology for calculating HA under improved management. The indicators for monitoring, sources of verification, responsibilities etc. are included in Annex 3 of the PRODOC. | PRODOC Annex 3: Monitoring Plan PRODOC Annex 12: Site Selection |
| - What activities will be implemented to increase the project’s resilience to climate change | Typhoons will affect the achievement of outputs and outcomes of the project, especially under component 3. Both Regions 3 and 5 are prone to typhoons. The issue is made complicated by climate change: currently, the timing, paths, and intensity of typhoons are not according to previous patterns. Increased and more serious flooding have also been observed. Climate change resiliency measures and analysis will be made integral to ABS processes and reflected in partner community/ LGUs local plans. The Project will support data gathering on community resilience, climate change impacts including indigenous/ traditional indicators will be generated and analyzed. At the site-level, the project will be led by the DENR field offices and local government units, these offices have climate change plans in place as mandated by climate change law, the project will use these plans to provide consistency and complementation of interventions. In region 3, where the partners include organized community groups such as indigenous peoples, they also have their ancestral domain management plans where the project can refer to and enhanced to ensure ABS activities are adequately supports and improves community resiliency. Generating more data at the species level for Pili and Banaba will also support species level conservation against climate change impacts. The project will work on tree species, these are sources that are known to be more resilient to weather disruption a d climate change. Safeguards are placed to ensuring that cultivation of tree species will not negatively affect traditional livelihoods | PRODOC Annex 5: UNDP Risk Register PRODOC Annex 4: SESP PRODOC Annex 8: ESMF |
| - The entire concept of ABS is innovative; however, this particular project doesn't include any additional innovations in terms of design, financing, etc. | The successful implementation of the Project will prove that it is possible to create value chains with the sustainable use of genetic resources, including medicinal plant and other non-timber resources and with local communities. In addition, the project will build trust regarding the financial opportunity which the use of biological and genetic resources offers, as an economic alternative to unsustainable exploitation of biological resources. Industry level- At the national and local level the project presents an opportunity to jumpstart a genetic resources industry which is rights based and equitable. Preferential support will be given to community organizations who are also the owner and manager of these genetic resources while at the same time promote GR develop respecting customary law and IKSPs. The project also provides an opportunity to build enterprises which are community- based and culturally appropriate but with linkages to SMEs. The genetic innovation derived from the R&D is expected to lead to the development of the following from each species. Pili cosmetic product development with PhilPILI The Pili industry has been exploring alternative products derived from Pili nut processing to leverage against volatile nut prices. Pili pulp and sap have been used in various products namely, cooking oil, animal feeds and resin. The most promising in terms of higher market value is through the development of cosmetic products founded primarily on its antioxidant and antibacterial traits. Multiple research areas have identified the high bioactive constituents of alkaloids, flavonoids, glycosides, saponins, sterols, tannins, terpenens, fatty acids in the pulp and terpineol, elemicine, elemol, dipentene, phellandrene and limonene derived from the sap. Pulp oil is commonly derived via crude press extraction which requires refining to eliminate impurities. While elemi oil is derived from the Pili tree’s sap via steam distillation extraction. Early developers of these raw materials have various skin care products that are in the market introduction stage and current analysis show negligible market share and limited awareness for these products based on distribution and availability in modern retail channels. These brands are mostly members of the Philippine Pili Industry League (PhilPILI) who have pledged co-financing for this project. These early innovators and PhilPILI have expressed the support needed to standardize specifications to bolster claims, and improve the yield and purity of these extracts, in order to produce a globally recognized ingredient such as Argan oil which is used widely in cosmetic products. Banaba antiviral drug development with Pharmalytics Corp under Tuklas Lunas program Banaba has numerous researches establishing its antidiabetic effects due to its hypoglycemic and glucose fat transport abilities. Most of these claims are based on its bioactive content, Corosilic Acid and Ellagtannins , derived from its leaves. A relatively new area of research for product development is on its anti-viral properties derived from its similar bioactives. Currently, Pharmalytics Corp. is undergoing clinical study phase 1 for an anti-viral drug against dengue under the Tuklas Lunas program. To date, the study has not yet reached the stage to determine whether to use crude ingredients or synthesized isolates from Banaba in their final product formulation. To that extent the process can be identified beyond their patent application, the preliminary step involves spray drying to powderize dried Banaba leaves. By extension, this project is trying to identify post-harvest protocols and raw material processing with Herbanext Corporation to secure quality and safety. This drug development project started in 2012 and has pledged co-financing to fulfill the timely completion of this innovative and urgent drug. | CEO ER #7 Innovativeness, sustainability and potential for scaling up. PRODOC Section III. Project Strategy PRODOC Section IV. Results and Partnerships |
| - Project Map and Coordinates. Please provide geo‐ referenced information and map where the project interventions will take place. map is included but no geo‐referencing | A map of all of Region 3 and Region 5 is included with the geospatial coordinates of the potential pilot sites for this project. The final pilot selection will be made during the first year of implementation. | CEO ER Annex E PRODOC Annex 1 |
| - The risks are reasonably comprehensive, and none are outside of the project's control. However, it is hard to see how the mitigation measures in the first risk really reduce this risk ‐ this is an economic assessment for the companies involved. Further, there may be a need to highlight the risk that communities may not provide FPIC in the case of the two selected case examples in component 3, which would mean these examples could not progress as planned. | Risk matrix has been updated to incorporate SESP. It better highlights risk of communities not providing FPIC or PIC and the SESP, ESMF, and Stakeholder Engagement Plan all delve into the work done during the PPF to engage IP communities. | CEO ER #5 Risk PRODOC Annex 5: UNDP Risk Register PRODOC Annex 4: SESP PRODOC Annex 7: Stakeholder Engagement Plan PRODOC Annex 8: ESMF |

Annex C: Status of Utilization of Project Preparation Grant (PPG)

PPG Grant Approved at PIF: $150,000

| Project Preparation Activities Implemented | GETF/LDCF/SCCF Amount ($) |  |  |
| --- | --- | --- | --- |
|  | Budgeted Amount | Amount Spent to Date | Amount Committed |
| Component A: Preparatory Technical Studies and Reviews - Engagement of Local PPG Team - National Expert on ABS Policy and Institutional Building - Stakeholder Engagement and Safeguards Specialist - Enterprise Development Specialist - Gender Specialist - Desktop and field-based studies and data collection - Desktop reviews - Gender Analysis - Environmental and Social Safeguards Assessments - Identification of project sites - Financial Planning - National and Site Level Inception Workshops - Field Missions for Data Gathering Component B: Formulation of the UNDP-GEF Project Document, CEO Endorsement and Mandatory and Project Specific Annexes - Engagement of International Project Development Officer who was responsible for the consolidation and finalization of all required documents (i.e., Project Document, CEO Endorsement Request, Annexes), with a specific focus on the following areas: - Theory of Change - Results Framework - Monitoring and Evaluation Plan and Budget - Stakeholder Engagement Plan - Gender Action Plan and Budget - Social and Environmental Standards - GEF Core Indicators - Project Management Arrangements - Completion of the required official endorsement letters - Technical Working Group Meetings and other Consultation Meetings Component C: Validation Workshop and Report | 82,200 33,000 25,800 2,000 7,000 | 51,479.95 33,000 21,096.46 1,235.28 6,638.89 | 30,720.05 - 4,703.54 764.72 361.11 |
| Total | 150,000 | 113,450.58 | 36,549.42 |

Annex D: Calendar of Expected Reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF Trust Funds or to your Agency (and/or revolving fund that will be set up)

NA

Annex E: Project Map(s) and Coordinates

.

Please see PRODOC Annex 1 for a larger version of the maps. Figure 1 includes a map of  all of Region 3 and Region 5, the regions where the pilot sites will be selected.

Figure 1. Location of Regions 3 and 5

Tables 1 and 2 below provide the geospatial coordinates of the potential pilot sites for this project. The final selection will be made during the first year of implementation.

Table 1. Region 3 Potential Sites Geospatial Coordinates

| Area | Latitude | Longitude |
| --- | --- | --- |
| Maporac | 15.1558416 | 120.061468 |
| Sitio Porac | 15.2466 | 120.026 |
| Camias | 15.088 | 120.4704 |
| Villa Maria | 15.089425 | 120.484529 |
| Barangay Biniritan | 14.799945 | 120.374007 |

Table 2. Region 5 Potential Sites Geospatial Coordinates

| Local Government Unit | Latitude | Longitude |
| --- | --- | --- |
| Sorsogon |  |  |
| Casiguran | 12.840319 | 124.041847 |
| Sorsogon City | 12.980654 | 124.02398 |
| Bulusan | 12.761898 | 124.112203 |
| Gubat | 12.81816 | 123.97204 |
| Juban | 12.81816 | 123.972 |
| Albay |  |  |
| Tabaco City | 13.350259 | 123.702029 |
| Bacacay | 13.284593 | 123.866835 |
| Malilipot | 13.303637 | 123.719937 |
| Malinao | 13.385597 | 123.662965 |
| Tiwi | 13.462066 | 123.638417 |
| Camarines Sur |  |  |
| Canaman | 13.643598 | 123.14459 |
| Pili | 13.591516 | 123.265126 |
| San Gabriel, Pamplona | 13.5664 | 123.095 |
| Nabua | 13.40238 | 123.338181 |
| Iriga City | 13.41667 | 123.4167 |

Figure 2 depicts the target provinces in the Bicol region (i.e., Sorsogon, Albay, Camarines Sur). Identified indicative sites per province are also shown which are represented by red points on the map. The potential sites were determined using the information provided by the Department of Agriculture Region 5 on the top recipients of pili sapling distribution.

Figure 2. Indicative Project Sites in Region 5

Figure 3 depicts the potential sites in the Central Luzon Region. Four of the identified sites (i.e., Maporac, New San Juan, Cabangan, Zambales; Villa Maria and Camias, Porac, Pampanga; and Brgy. Biniritan, Morong, Bataan) were declared as Indigenous and Community Conserved Areas (ICCAs) while the remaining one (i.e., Sitio Porac, Botolan, Zambales) is under a Community Based Forest Management Agreement (CBFMA) with the Department of Environment and Natural Resources.

Figure 3. Potential Project Sites in Region 3

Annex F: GEF 7 Core Indicator Worksheet

| Core Indicator 1 | Terrestrial protected areas created or under improved management for conservation and sustainable use |  |  |  |  |  |  |  |  |  | (Hectares) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Hectares (1.1+1.2) |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 1.1 | Terrestrial protected areas newly created |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  | Sum |  |  |  |  |  |  |  |  |  |
| Indicator 1.2 | Terrestrial protected areas under improved management effectiveness |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  | Hectares |  | METT Score |  |  |  |  |  |
|  |  |  |  |  |  | Baseline |  |  |  | Achieved |  |
|  |  |  |  |  |  |  |  | Endorsement |  | MTR | TE |
|  |  | Sum |  |  |  |  |  |  |  |  |  |
| Core Indicator 2 | Marine protected areas created or under improved management for conservation and sustainable use |  |  |  |  |  |  |  |  |  | (Hectares) |
|  |  |  |  |  |  | Hectares (2.1+2.2) |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage | Endorsement |  |  | MTR | TE |
| Indicator 2.1 | Marine protected areas newly created |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  | Sum |  |  |  |  |  |  |  |  |  |
| Indicator 2.2 | Marine protected areas under improved management effectiveness |  |  |  |  |  |  |  |  |  |  |
| Name of Protected Area | WDPA ID | IUCN category |  |  | Hectares | METT Score |  |  |  |  |  |
|  |  |  |  |  |  | Baseline |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  | Sum |  |  |  |  |  |  |  |  |  |
| Core Indicator 3 | Area of land restored |  |  |  |  |  |  |  |  |  | (Hectares) |
|  |  |  |  |  |  | Hectares (3.1+3.2+3.3+3.4) |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 3.1 | Area of degraded agricultural land restored |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 3.2 | Area of forest and forest land restored |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 3.3 | Area of natural grass and shrublands restored |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 3.4 | Area of wetlands (including estuaries, mangroves) restored |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 4 | Area of landscapes under improved practices (hectares; excluding protected areas) |  |  |  |  |  |  |  |  |  | (Hectares) |
|  |  |  |  |  |  | Hectares (4.1+4.2+4.3+4.4) |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Expected |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  |  |  |  |  | NA |  | 41,662 |  | 17,500 | 41,662 |
| Indicator 4.1 | Area of landscapes under improved management to benefit biodiversity |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  | Hectares Region 3 (Central Luzon) |  |  |  | NA |  | 35,828 |  | 15,000 | 35,828 |
|  |  | Hectares Region 5 (Bicol) |  |  |  | NA |  | 5,834 |  | 2,500 | 5,834 |
| Indicator 4.2 | Area of landscapes that meet national or international third-party certification that incorporates biodiversity considerations |  |  |  |  |  |  |  |  |  |  |
| Third party certification(s): |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 4.3 | Area of landscapes under sustainable land management in production systems |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 4.4 | Area of High Conservation Value Forest (HCVF) loss avoided |  |  |  |  |  |  |  |  |  |  |
| Include documentation that justifies HCVF |  |  |  |  |  | Hectares |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 5 | Area of marine habitat under improved practices to benefit biodiversity |  |  |  |  |  |  |  |  |  | (Hectares) |
| Indicator 5.1 | Number of fisheries that meet national or international third-party certification that incorporates biodiversity considerations |  |  |  |  |  |  |  |  |  |  |
| Third party certification(s): |  |  |  |  |  | Number |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 5.2 | Number of large marine ecosystems (LMEs) with reduced pollution and hypoxial |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Number |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 5.3 | Amount of Marine Litter Avoided |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Metric Tons |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 6 | Greenhouse gas emission mitigated |  |  |  |  |  |  |  |  |  | (Metric tons of CO₂e ) |
|  |  |  |  |  |  | Expected metric tons of CO₂e (6.1+6.2) |  |  |  |  |  |
|  |  |  |  |  |  | PIF stage | Endorsement |  | MTR |  | TE |
|  | Expected CO2e (direct) |  |  |  |  |  |  |  |  |  |  |
|  | Expected CO2e (indirect) |  |  |  |  |  |  |  |  |  |  |
| Indicator 6.1 | Carbon sequestered or emissions avoided in the AFOLU sector |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Expected metric tons of CO₂e |  |  |  |  |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  | Expected CO2e (direct) |  |  |  |  |  |  |  |  |  |  |
|  | Expected CO2e (indirect) |  |  |  |  |  |  |  |  |  |  |
|  | Anticipated start year of accounting |  |  |  |  |  |  |  |  |  |  |
|  | Duration of accounting |  |  |  |  |  |  |  |  |  |  |
| Indicator 6.2 | Emissions avoided Outside AFOLU |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Expected metric tons of CO₂e |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  | Expected CO2e (direct) |  |  |  |  |  |  |  |  |  |  |
|  | Expected CO2e (indirect) |  |  |  |  |  |  |  |  |  |  |
|  | Anticipated start year of accounting |  |  |  |  |  |  |  |  |  |  |
|  | Duration of accounting |  |  |  |  |  |  |  |  |  |  |
| Indicator 6.3 | Energy saved |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | MJ |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 6.4 | Increase in installed renewable energy capacity per technology |  |  |  |  |  |  |  |  |  |  |
|  |  | Technology |  |  |  | Capacity (MW) |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 7 | Number of shared water ecosystems (fresh or marine) under new or improved cooperative management |  |  |  |  |  |  |  |  |  | (Number) |
| Indicator 7.1 | Level of Transboundary Diagnostic Analysis and Strategic Action Program (TDA/SAP) formulation and implementation |  |  |  |  |  |  |  |  |  |  |
|  |  | Shared water ecosystem |  |  |  | Rating (scale 1-4) |  |  |  |  |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 7.2 | Level of Regional Legal Agreements and Regional Management Institutions to support its implementation |  |  |  |  |  |  |  |  |  |  |
|  |  | Shared water ecosystem |  |  |  | Rating (scale 1-4) |  |  |  |  |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 7.3 | Level of National/Local reforms and active participation of Inter-Ministerial Committees |  |  |  |  |  |  |  |  |  |  |
|  |  | Shared water ecosystem |  |  |  | Rating (scale 1-4) |  |  |  |  |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 7.4 | Level of engagement in IWLEARN through participation and delivery of key products |  |  |  |  |  |  |  |  |  |  |
|  |  | Shared water ecosystem |  |  |  | Rating (scale 1-4) |  |  |  |  |  |
|  |  |  |  |  |  | Rating |  |  |  | Rating |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 8 | Globally over-exploited fisheries Moved to more sustainable levels |  |  |  |  |  |  |  |  |  | (Metric Tons) |
| Fishery Details |  |  |  |  |  | Metric Tons |  |  |  |  |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 9 | Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products |  |  |  |  |  |  |  |  |  | (Metric Tons) |
|  |  |  |  |  |  | Metric Tons (9.1+9.2+9.3) |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | PIF stage |  | MTR | TE |
| Indicator 9.1 | Solid and liquid Persistent Organic Pollutants (POPs) removed or disposed (POPs type) |  |  |  |  |  |  |  |  |  |  |
| POPs type |  |  |  |  |  | Metric Tons |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 9.2 | Quantity of mercury reduced |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Metric Tons |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 9.3 | Hydrochloroflurocarbons (HCFC) Reduced/Phased out |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Metric Tons |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 9.4 | Number of countries with legislation and policy implemented to control chemicals and waste |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Number of Countries |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 9.5 | Number of low-chemical/non-chemical systems implemented particularly in food production, manufacturing and cities |  |  |  |  |  |  |  |  |  |  |
|  |  | Technology |  |  |  | Number |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 9.6 | Quantity of POPs/Mercury containing materials and products directly avoided |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Metric Tons |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | PIF stage | Endorsement |
| Core Indicator 10 | Reduction, avoidance of emissions of POPs to air from point and non-point sources |  |  |  |  |  |  |  |  |  | (grams of toxic equivalent gTEQ) |
| Indicator 10.1 | Number of countries with legislation and policy implemented to control emissions of POPs to air |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Number of Countries |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Indicator 10.2 | Number of emission control technologies/practices implemented |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Number |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
| Core Indicator 11 | Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment |  |  |  |  |  |  |  |  |  | (Number) |
|  |  |  |  |  |  | Number |  |  |  |  |  |
|  |  |  |  |  |  | Expected |  |  |  | Achieved |  |
|  |  |  |  |  |  | PIF stage |  | Endorsement |  | MTR | TE |
|  |  | Female |  |  |  | 1000 |  | 2,120 |  | 1,060 | 2,120 |
|  |  | Male |  |  |  | 1000 |  | 3,938 |  | 1,969 | 3,938 |
|  |  | Total |  |  |  | 2000 |  | 6,058 |  | 3,029 | 6,058 |

Annex G: GEF Project Taxonomy Worksheet

| Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- |
| Influencing models |  |  |  |
|  | Transform policy and regulatory environments |  |  |
|  | Strengthen institutional capacity and decision-making |  |  |
|  | Convene multi-stakeholder alliances |  |  |
|  | Demonstrate innovative approaches |  |  |
|  | Deploy innovative financial instruments |  |  |
| Stakeholders |  |  |  |
|  | Indigenous Peoples |  |  |
|  | Private Sector |  |  |
|  |  | Capital providers |  |
|  |  | Financial intermediaries and market facilitators |  |
|  |  | Large corporations |  |
|  |  | SMEs |  |
|  |  | Individuals/Entrepreneurs |  |
|  |  | Non-Grant Pilot |  |
|  |  | Project Reflow |  |
|  | Beneficiaries |  |  |
|  | Local Communities |  |  |
|  | Civil Society |  |  |
|  |  | Community Based Organization |  |
|  |  | Non-Governmental Organization |  |
|  |  | Academia |  |
|  |  | Trade Unions and Workers Unions |  |
|  | Type of Engagement |  |  |
|  |  | Information Dissemination |  |
|  |  | Partnership |  |
|  |  | Consultation |  |
|  |  | Participation |  |
|  | Communications |  |  |
|  |  | Awareness Raising |  |
|  |  | Education |  |
|  |  | Public Campaigns |  |
|  |  | Behavior Change |  |
| Capacity, Knowledge and Research |  |  |  |
|  | Enabling Activities |  |  |
|  | Capacity Development |  |  |
|  | Knowledge Generation and Exchange |  |  |
|  | Targeted Research |  |  |
|  | Learning |  |  |
|  |  | Theory of Change |  |
|  |  | Adaptive Management |  |
|  |  | Indicators to Measure Change |  |
|  | Innovation |  |  |
|  | Knowledge and Learning |  |  |
|  |  | Knowledge Management |  |
|  |  | Innovation |  |
|  |  | Capacity Development |  |
|  |  | Learning |  |
|  | Stakeholder Engagement Plan |  |  |
| Gender Equality |  |  |  |
|  | Gender Mainstreaming |  |  |
|  |  | Beneficiaries |  |
|  |  | Women groups |  |
|  |  | Sex-disaggregated indicators |  |
|  |  | Gender-sensitive indicators |  |
|  | Gender results areas |  |  |
|  |  | Access and control over natural resources |  |
|  |  | Participation and leadership |  |
|  |  | Access to benefits and services |  |
|  |  | Capacity development |  |
|  |  | Awareness raising |  |
|  |  | Knowledge generation |  |
| Focal Areas/Theme |  |  |  |
|  | Integrated Programs |  |  |
|  |  | Commodity Supply Chains (Good Growth Partnership) |  |
|  |  |  | Sustainable Commodities Production |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Financial Screening Tools |
|  |  |  | High Conservation Value Forests |
|  |  |  | High Carbon Stocks Forests |
|  |  |  | Soybean Supply Chain |
|  |  |  | Oil Palm Supply Chain |
|  |  |  | Beef Supply Chain |
|  |  |  | Smallholder Farmers |
|  |  |  | Adaptive Management |
|  |  | Food Security in Sub-Sahara Africa |  |
|  |  |  | Resilience (climate and shocks) |
|  |  |  | Sustainable Production Systems |
|  |  |  | Agroecosystems |
|  |  |  | Land and Soil Health |
|  |  |  | Diversified Farming |
|  |  |  | Integrated Land and Water Management |
|  |  |  | Smallholder Farming |
|  |  |  | Small and Medium Enterprises |
|  |  |  | Crop Genetic Diversity |
|  |  |  | Food Value Chains |
|  |  |  | Gender Dimensions |
|  |  |  | Multi-stakeholder Platforms |
|  |  | Food Systems, Land Use and Restoration |  |
|  |  |  | Sustainable Food Systems |
|  |  |  | Landscape Restoration |
|  |  |  | Sustainable Commodity Production |
|  |  |  | Comprehensive Land Use Planning |
|  |  |  | Integrated Landscapes |
|  |  |  | Food Value Chains |
|  |  |  | Deforestation-free Sourcing |
|  |  |  | Smallholder Farmers |
|  |  | Sustainable Cities |  |
|  |  |  | Integrated urban planning |
|  |  |  | Urban sustainability framework |
|  |  |  | Transport and Mobility |
|  |  |  | Buildings |
|  |  |  | Municipal waste management |
|  |  |  | Green space |
|  |  |  | Urban Biodiversity |
|  |  |  | Urban Food Systems |
|  |  |  | Energy efficiency |
|  |  |  | Municipal Financing |
|  |  |  | Global Platform for Sustainable Cities |
|  |  |  | Urban Resilience |
|  | Biodiversity |  |  |
|  |  | Protected Areas and Landscapes |  |
|  |  |  | Terrestrial Protected Areas |
|  |  |  | Coastal and Marine Protected Areas |
|  |  |  | Productive Landscapes |
|  |  |  | Productive Seascapes |
|  |  |  | Community Based Natural Resource Management |
|  |  | Mainstreaming |  |
|  |  |  | Extractive Industries (oil, gas, mining) |
|  |  |  | Forestry (Including HCVF and REDD+) |
|  |  |  | Tourism |
|  |  |  | Agriculture & agrobiodiversity |
|  |  |  | Fisheries |
|  |  |  | Infrastructure |
|  |  |  | Certification (National Standards) |
|  |  |  | Certification (International Standards) |
|  |  | Species |  |
|  |  |  | Illegal Wildlife Trade |
|  |  |  | Threatened Species |
|  |  |  | Wildlife for Sustainable Development |
|  |  |  | Crop Wild Relatives |
|  |  |  | Plant Genetic Resources |
|  |  |  | Animal Genetic Resources |
|  |  |  | Livestock Wild Relatives |
|  |  |  | Invasive Alien Species (IAS) |
|  |  | Biomes |  |
|  |  |  | Mangroves |
|  |  |  | Coral Reefs |
|  |  |  | Sea Grasses |
|  |  |  | Wetlands |
|  |  |  | Rivers |
|  |  |  | Lakes |
|  |  |  | Tropical Rain Forests |
|  |  |  | Tropical Dry Forests |
|  |  |  | Temperate Forests |
|  |  |  | Grasslands |
|  |  |  | Paramo |
|  |  |  | Desert |
|  |  | Financial and Accounting |  |
|  |  |  | Payment for Ecosystem Services |
|  |  |  | Natural Capital Assessment and Accounting |
|  |  |  | Conservation Trust Funds |
|  |  |  | Conservation Finance |
|  |  | Supplementary Protocol to the CBD |  |
|  |  |  | Biosafety |
|  |  |  | Access to Genetic Resources Benefit Sharing |
|  | Forests |  |  |
|  |  | Forest and Landscape Restoration |  |
|  |  |  | REDD/REDD+ |
|  |  | Forest |  |
|  |  |  | Amazon |
|  |  |  | Congo |
|  |  |  | Drylands |
|  | Land Degradation |  |  |
|  |  | Sustainable Land Management |  |
|  |  |  | Restoration and Rehabilitation of Degraded Lands |
|  |  |  | Ecosystem Approach |
|  |  |  | Integrated and Cross-sectoral approach |
|  |  |  | Community-Based NRM |
|  |  |  | Sustainable Livelihoods |
|  |  |  | Income Generating Activities |
|  |  |  | Sustainable Agriculture |
|  |  |  | Sustainable Pasture Management |
|  |  |  | Sustainable Forest/Woodland Management |
|  |  |  | Improved Soil and Water Management Techniques |
|  |  |  | Sustainable Fire Management |
|  |  |  | Drought Mitigation/Early Warning |
|  |  | Land Degradation Neutrality |  |
|  |  |  | Land Productivity |
|  |  |  | Land Cover and Land cover change |
|  |  |  | Carbon stocks above or below ground |
|  |  | Food Security |  |
|  | International Waters |  |  |
|  |  | Ship |  |
|  |  | Coastal |  |
|  |  | Freshwater |  |
|  |  |  | Aquifer |
|  |  |  | River Basin |
|  |  |  | Lake Basin |
|  |  | Learning |  |
|  |  | Fisheries |  |
|  |  | Persistent toxic substances |  |
|  |  | SIDS : Small Island Dev States |  |
|  |  | Targeted Research |  |
|  |  | Pollution |  |
|  |  |  | Persistent toxic substances |
|  |  |  | Plastics |
|  |  |  | Nutrient pollution from all sectors except wastewater |
|  |  |  | Nutrient pollution from Wastewater |
|  |  | Transboundary Diagnostic Analysis and Strategic Action Plan preparation |  |
|  |  | Strategic Action Plan Implementation |  |
|  |  | Areas Beyond National Jurisdiction |  |
|  |  | Large Marine Ecosystems |  |
|  |  | Private Sector |  |
|  |  | Aquaculture |  |
|  |  | Marine Protected Area |  |
|  |  | Biomes |  |
|  |  |  | Mangrove |
|  |  |  | Coral Reefs |
|  |  |  | Seagrasses |
|  |  |  | Polar Ecosystems |
|  |  |  | Constructed Wetlands |
|  | Chemicals and Waste |  |  |
|  |  | Mercury |  |
|  |  | Artisanal and Scale Gold Mining |  |
|  |  | Coal Fired Power Plants |  |
|  |  | Coal Fired Industrial Boilers |  |
|  |  | Cement |  |
|  |  | Non-Ferrous Metals Production |  |
|  |  | Ozone |  |
|  |  | Persistent Organic Pollutants |  |
|  |  | Unintentional Persistent Organic Pollutants |  |
|  |  | Sound Management of chemicals and Waste |  |
|  |  | Waste Management |  |
|  |  |  | Hazardous Waste Management |
|  |  |  | Industrial Waste |
|  |  |  | e-Waste |
|  |  | Emissions |  |
|  |  | Disposal |  |
|  |  | New Persistent Organic Pollutants |  |
|  |  | Polychlorinated Biphenyls |  |
|  |  | Plastics |  |
|  |  | Eco-Efficiency |  |
|  |  | Pesticides |  |
|  |  | DDT - Vector Management |  |
|  |  | DDT - Other |  |
|  |  | Industrial Emissions |  |
|  |  | Open Burning |  |
|  |  | Best Available Technology / Best Environmental Practices |  |
|  |  | Green Chemistry |  |
|  | Climate Change |  |  |
|  |  | Climate Change Adaptation |  |
|  |  |  | Climate Finance |
|  |  |  | Least Developed Countries |
|  |  |  | Small Island Developing States |
|  |  |  | Disaster Risk Management |
|  |  |  | Sea-level rise |
|  |  |  | Climate Resilience |
|  |  |  | Climate information |
|  |  |  | Ecosystem-based Adaptation |
|  |  |  | Adaptation Tech Transfer |
|  |  |  | National Adaptation Programme of Action |
|  |  |  | National Adaptation Plan |
|  |  |  | Mainstreaming Adaptation |
|  |  |  | Private Sector |
|  |  |  | Innovation |
|  |  |  | Complementarity |
|  |  |  | Community-based Adaptation |
|  |  |  | Livelihoods |
|  |  | Climate Change Mitigation |  |
|  |  |  | Agriculture, Forestry, and other Land Use |
|  |  |  | Energy Efficiency |
|  |  |  | Sustainable Urban Systems and Transport |
|  |  |  | Technology Transfer |
|  |  |  | Renewable Energy |
|  |  |  | Financing |
|  |  |  | Enabling Activities |
|  |  | Technology Transfer |  |
|  |  |  | Poznan Strategic Programme on Technology Transfer |
|  |  |  | Climate Technology Centre & Network (CTCN) |
|  |  |  | Endogenous technology |
|  |  |  | Technology Needs Assessment |
|  |  |  | Adaptation Tech Transfer |
|  |  | United Nations Framework on Climate Change |  |
|  |  |  | Nationally Determined Contribution |
|  |  |  | Paris Agreement |
|  |  |  | Sustainable Development Goals |
|  |  | Climate Finance (Rio Markers) |  |
|  |  |  | Climate Change Mitigation 1 |
|  |  |  | Climate Change Mitigation 2 |
|  |  |  | Climate Change Adaptation 1 |
|  |  |  | Climate Change Adaptation 2 |

Estimated value in USD is based on the UN official exchange rate (USD1 = Php50.678) at the date signature of the letter (January 2020), see https://treasury.un.org/operationalrates/OperationalRates.php

For Central Luzon State University only; Estimated value in USD is based on the UN official exchange rate (USD1 = Php50.977) at the date signature of the letter (February 2020), see https://treasury.un.org/operationalrates/OperationalRates.php

The costs of UNDP CO and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.