WWF GEF

Management Response

Integrated management of Cameroon’s forest landscapes in the Congo Basin (GEF Project ID 10287; WWF-US Agency Project ID G0021)

| Date of Management Response | 08 January 2026 |
| --- | --- |
| Date of Evaluation Report Author of Evaluation Report | 28 November 2025 Eco Markets & Measures LLC (in collaboration with Nature Plan and Lacy Consulting Services) |

# Part I. Accuracy and Quality of the Report

- Any errors or inaccuracies in the final report? Please reference the statement and page number.

No material factual errors were identified.

- Any clarifications needed or exceptions to statements made in the final report?  Please reference the statement and page number.

The project has a centralized data management system including version control and a centralized repository. Due to access policies the team was not able to share the whole system. (page 6).

- How would you rate the quality of this report (Choose one: HS, S, MS, MU, U, HU)? Please justify your rating.

HS (Highly Satisfactory). The report is evidence-based, balanced, and clearly presents findings and actionable recommendations, reflecting inputs from key stakeholders and available project documentation.

# Part II. Knowledge Management

- Any information or assessment, surprising or unexpected in this report?

No

- Key takeaways:

  - Future GEF projects (design or implementation):

- Consider how to address grievances related to human-wildlife conflict in future projects

- Engage discussion with the GEF Secretariat to update its policy in order to allocate more percentage of project funding to PMC and M&E

  - GEF operations or management:

- GEF considerations for future Projects: Given the operational limitations imposed by the current GEF definition of what constitutes a “GEF Agency”  – particularly the administrative interpretations of execution-role eligibility for legally independent organizations and not accredited GEF Agencies – it is recommended that the GEF reconsider this requirement for future projects, especially those implemented in complex or remote field contexts.

  - PMU operations or management:

- Reallocate funding from components to increase the budget for Monitoring and Evaluation, Communication and Knowledge Management

  - Institutional arrangements:

N/A

  - Other:

- Who should receive copies of this terminal evaluation report?

- GEF Secretariat

- GEF 7 IP Congo Bassin Regional Project Coordinator

- MINEPDED (Project Lead Executing Agency)

- GEF Operational Focal Point

- Government partners Ministries (MINFOF, MINAS, MINTOUL, MINEPAT)

- Conservators of supported National Parks (Lobeke, Campo)

- Project field executing partners

- WWF Cameroon

- Mayors of Project Landscapes Municipalities (Campo, Somalomo, Ngoyla, Mintom, Lomié, Salapoumbe and Moloudou)

- PMU staff

- Members of the national coordination team

- Members of the project steering committee

- Other comments:

# Part III. Follow-up Actions to Recommendations

| Specific Recommendations | Response and Priority | Response Actions | Timeframe | Person or Office Responsible | Tracking Status | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Specific recommendations listed below | Do you agree/ disagree with the recommendation? What priority would you place on the recommendation (low, medium, high)? Include any specific comments you have. | Indicate what actions should be taken in response to the recommendation. Insert new rows if you list multiple actions. | Indicate the deadline for each action to be completed. | Indicate who must carry out the action. | Progress on this response should be assessed 1x/year. Indicate below if each action is Complete, Partially Complete or Pending. | Provide any comments related to the status of each action. |
| Improve TOC-M&E Alignment: In the TOC narrative for each component, clearly reference associated activities, outputs, and outcomes (e.g., using numbering from the M&E plan). This would improve coherence between planning and evaluation tools and help ensure all outcomes – such as Outcome 2.3 – are captured. | Agree – High | Update TOC/Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–4 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.29 |
| Adopt Results Chains: To enhance clarity and functionality, it is recommended that the Project – and future initiatives – support the TOC description with a Results Chain. | Agree – Medium | Update TOC/Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–4 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.30 |
| Revisit the strategic approach: For each component, revisit the strategic approach to ensure that activities are adequately tailored and resourced to achieve outputs, and that assumptions are clearly linked to outcomes and impacts, monitored, practical and feasible. | Agree – Medium | Convene a working session to revisit the strategic approach and ensure its full alignment with outcomes and expected impacts | 0–6 months | PMU | Not started | Source: MTR report p.30 |
| Pathway to Scale: For any follow-on project, greater strategic emphasis should be placed on identifying pathways to scale, including sustainability, replication potential, and catalytic partnerships. | Agree – High | Revise the monitoring guideline for the implementation of project activities or groups of activities, to ensure that it takes into account the criteria of scaling up, sustainability, replication potential, and the development of catalytic partnerships. | 0–3 months | PMU / WWF-Cameroon | Not started | Source: MTR report p.30 |
| Assess hygiene: Assess hygiene conditions for NTFP processing and identify any risks or mitigation measures to ensure product quality and safety. | Agree – Medium | Conduct targeted technical assessment and adjust support packages if any; strengthen quality control/market linkages; monitor outcomes and scale what works. | 3–12 months | Executing Partners (livelihood leads) / PMU | Ongoing | Source: MTR report p.31 |
| Barriers to land tenure: Evaluate the relevance of official identification in accessing land tenure processes and explore whether the Project can facilitate linkages with national initiatives to reduce related barriers. | Agree – Low | Conduct targeted technical assessment and if possible, facilitate linkages with national initiatives to address any barriers not directly funded by the project. | 3–12 months | Executing Partners (livelihood leads) / PMU | Ongoing | Source: MTR report p.31 |
| Strengthen Coordination among Executing Partners: Strengthen inter-partner coordination through more frequent exchanges and clearer communication channels to ensure coherence and compound benefits across project components and geographies. | Agree – High | Organize executing partners meeting. | 0– 6 months | PMU / Project Steering Committee / WWF-Cameroon | Not started | Source: MTR report p.32 |
| Advance collaboration: Further operationalize collaboration with complementary initiatives – both GEF and non-GEF – through formal coordination platforms, shared reporting where appropriate, and joint learning exercises. Opportunities for knowledge sharing should be actively pursued to enhance effectiveness and sustainability. | Agree – Medium | Stakeholder platforms exist across the different landscapes, and the Project supports the holding of sessions for two platforms (around Lobeke and Campo Ma’an), while participating in all sessions of these platforms. Each annual session of these platforms will place emphasis on information sharing, lessons learned, and project documentation, as well as on planning to foster synergies and complementarity. | 12 months | PMU (M&E Lead) | Ongoing | Source: MTR report p.34 |
| Reallocate funds to Component 5: It is recommended that the Project revisit the scope and funding of Component 5 activities, with a view to reallocating resources from other components where feasible. This will help ensure the continuation of core functions such as monitoring, partner capacity building, and KM throughout the life of the Project. | Agree – High | Revise the project budget to reduce funds from components 1 to 4, where feasible, and reallocate them to component 5. | 0–3 months | PMU (FM) / WWF-Cameroon, with WWF-US support | Completed | Source: MTR report p.36 |
| GEF Project to better fund M&E activities: It is recommended that in the future GEF projects allot substantially more financial resources toward both management of the Project as well as toward activities and components which include M&E, KM, and stakeholder engagement. | Agree – High | Engage discussion with the GEF Secretariat to update its policy in order to allocate more percentage of project funding to PMC and M&E | 0–6 months | WWF GEF Agency | Not started | Source: MTR report p.36 |
| Complete co-financing reporting: It is recommended that the “Remarks” column in the Co-financing Summary Reports be systematically completed to provide context for any missing or delayed co-financing contributions. This could include explanations for why certain contributions have not yet been reported and any planned follow-up actions. | Agree – High | Systematically remind partners about their co‑financing reports and complete the summary table, including comments and observations in a separate column | 12 months | PMU (FM and ESSO) | Ongoing | Source: MTR report p.36 |
| Review technical reporting frequency and financial protocols and relay decisions clearly to partners: It is recommended that the Project undertake a review of the current technical and financial documentation protocols, balancing risk management with operational efficiency. As part of this process, it would be valuable to engage Executing Partners and communicate transparently about the rationale for either maintaining or adjusting the requirements. | Agree – Low |  | 0–6 months | PMU (FM, M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.38 |
| GEF considerations for future Projects: Given the operational limitations imposed by the current GEF policy framework – particularly the administrative interpretations of execution-role eligibility for legally independent organizations and not accredited GEF Agencies – it is recommended that the GEF reconsider this requirement for future projects, especially those implemented in complex or remote field contexts. | Agree – High | Develop an implementation plan addressing the recommendation; assign responsibilities, timeline, and monitoring. | 0–6 months | WWF GEF AGENCY | Not started | Source: MTR report p.41 |
| Support broader integration and uptake: Develop strategies—within the scope of a next Project or in partnership with other stakeholders—for: a) advancing regional planning that incorporates council-level LUPs, and b) facilitating implementation of the LUPs, either directly or through local partners, to reduce the risk of these plans not being used. | Agree – Medium | Convene meeting at national level with the participation of key sectoral ministries (MINEPAT, MINFOF, MINEPDED, MINMIDT, MINDEVEL, MINADER, MINAS...) and partners to facilitate the recognition of the Ngoyla and Mintom LUPs, and to promote the mobilization of financial resources and the establishment of partnerships for their effective implementation | 0–8 months | Project Partners (PADIDJA, ONACC)/ PMU | Not started | Source: MTR report p.45 |
| Reassess budget allocation: Given the substantial progress made under Component 1 and limited remaining needs, consider repurposing unused funds to address underfunded components more aligned with current implementation priorities. | Agree – High | Review budget execution and reallocations with Steering Committee; agree revised budget/AWP; document decisions and communicate to partners and GEF Agency. | 0–2 months | PMU (Project Manager & Finance) / WWF-Cameroon & WWF-US | Completed | Source: MTR report p.45 |
| Strengthen knowledge sharing and advocacy: Continue facilitating exchange between councils with and without LUPs, and engage with relevant authorities (e.g., MINEPAT, ONACC) to advocate for the integration of local plans into regional, national, and transboundary frameworks. | Agree – Medium |  | 0–8 months | Project Partners (PADIDJA, ONACC)/PMU | Not started | Source: MTR report p.45 |
|  |  | Organize an annual meeting with Ngoyla and Mintom municipal council members, along with government sector representatives and other partners, to ensure that the implementation of the LUP is taken into account in the municipal budget | Each Year | Project Partners (PADIDJA, ONACC)/PMU | Not started |  |
|  |  | Produce and disseminate Communication materials (flyers, article...) to share lessons learned on Ngoyla and Mintom LUP process | 0-8 months | Project Partners (PADIDJA, ONACC)/PMU | Not started |  |
| Revise and clarify Component 1 indicators: Ensure that indicators in the M&E system are specific, measurable, and aligned with intended outcomes. This includes: - Adding a quantitative indicator for area (e.g., hectares) under improved land use planning, in line with the measurable language of Outcome 1.1. - Finalizing the scorecard and clearly defining the methodology and criteria used to assess LUP quality. In cases where quality is lacking, further assess how the quality could be improved with the remaining funds or at a minimum how the planning could be improved in the future. - Ensuring that all Outcome indicators are adequately explained in the M&E Plan and reflected in the reporting tools. | Agree – High | Update component 1 Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. convene a working session to finalize the scorecard and adequately explained the outcome indicators | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Ongoing | Source: MTR report p.45 |
| Differentiate Project-Specific Contributions: Clearly distinguish activities and results financed or implemented directly by the Project from those supported by co-financing partners or other concurrent initiatives. This distinction should be systematically reflected in all key reporting instruments, particularly in the Annual Project Progress Reports and relevant outcome-level analyses. | Agree – Low | Include observations on the specific contributions of the project that have helped improve the IMET/METT scores in the project’s periodic reports (bi-annual and annual) | 0–6 months | PMU (M&E Lead) / WWF-Cameroon | Not started | Source: MTR report p.52 |
| Strengthen Attribution of IMET Score Changes: Given that variations in IMET scores can result from a diversity of external and internal factors beyond the direct influence of the Project (including from co-financed activities), it is important to ensure that claims of impact are grounded in clear evidence of attribution. To enhance the credibility and transparency of performance reporting, the Project should: Accompany IMET Reporting with Contextual Analysis: When presenting changes in IMET scores, include a concise narrative outlining (a) the specific Project interventions that may have plausibly influenced the observed changes, and (b) other contextual or systemic factors | Agree – Medium | Include observations on the specific contributions of the project that have helped improve the IMET/METT scores in IMETT/METT reporting, as well as change in internal factors of concern protected area | 0–06 months | PMU (M&E Lead) / WWF-Cameroon | Not started | Source: MTR report p.52 |
| Develop Clear Results Chains: Reassess current approaches and create a results chain that depicts causal linkages between monitored results (i.e., outcomes) and unmonitored results (i.e., assumptions) leading to threat reduction and conservation impact. This will improve strategic clarity and make it easier to detect if desired outcomes and impacts can logically be expected based on the current suite of implemented activities. | Agree – Low | Convene a working session to address this recommendation | 0–04 months | PMU (M&E Lead) / WWF-Cameroon | Not started | Source: MTR report p.53 |
| Strengthen M&E System: Revise outcome indicators to ensure all are SMART (Specific, Measurable, Achievable, Relevant, Time-bound), using metrics that reflect actual Project successes, such as IPLC engagement and grievance resolution. Finalize the scorecard mechanism and clearly document the procedures and results. | Agree – High | Convene a working session to address this recommendation | 0–04 months | PMU (M&E Lead) / WWF-Cameroon | Not started | Source: MTR report p.53 |
| Revise and expand indicators for Component 3: - Disaggregate NTFP and hardwood sub-components with distinct indicators that reflect their differing timeframes and theories of change. - Include a specific indicator to track the number of communities supported under Outcome 3.1. - Clarify and refine how "benefits" are defined and measured – going beyond participation counts to include tangible economic or social gains. - Reintroduce or clarify youth participation tracking, using practical methods for - estimation and self-identification as appropriate. | Agree – High | Convene a working session to update component 3 Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–4 months | PMU (M&E Lead) / t | Not started | Source: MTR report p.57 |
| Leverage existing data for improved reporting: The Project already collects valuable price and income data. Align the M&E system with these internal tools to improve reporting quality and better reflect the actual impact being achieved on the ground. | Agree – Medium | Convene a working session to address this recommendation | 0–6 months | PMU (M&E Lead) / t | Not started | Source: MTR report p.58 |
| Deepen market systems analysis for NTFPs: Conduct a broader assessment of the NTFP market system to understand value chain dynamics, market actors, and demand trends. This will support more strategic design for scale and inform engagement with new private sector partners, particularly if hardwood activities are reduced or discontinued. | Agree – Medium | Update market and feasibility assessment; engage multiple private sector actors; | 3–12 months | Executing partners /PMU / Technical leads, with external consultant as needed | Not started | Source: MTR report p.57 |
| Establish sustainable market linkages: Transition from the Executing Partners intervening in sales to direct connections between communities and buyers before Project closure. Until communities can independently negotiate and transact, the value chain remains vulnerable and lacks long-term sustainability. | Agree – Medium | Organize at least one capacity-building session for communities on sales and negotiation of NTFPs (Non-Timber Forest Products) by the end of the project. | Each year | Executing partners | Ongoing | Source: MTR report p.58 |
| Critically assess the future of the hardwoods sub-component: Given the limited scale of the Ebony Project as it currently operates, the Project should consider either phasing it out (once current commitments conclude) or challenging partners to propose a scalable, high-impact model. This could include linkages with NTFP communities, exploring seedling sales, or a wider market systems approach in conjunction with major buyers of hardwoods (fruits, nuts, wood, etc.). | Agree – Medium | Discuss with UCLA of a linkage between NTFP communities and Ebony Project communities to explore seedling sales, or a wider market systems approach in conjunction with major hardwood buyers. | 3–12 months | PMU / Technical leads, with external consultant as needed | Not started | Source: MTR report p.57 |
| Reassess the strategic direction of Component 4: With the lack of readiness for sustainable gorilla tourism, revisit the broader strategy for this component. Use results chains to refine objectives and assess whether gorilla tourism should remain a core focus or if resources should be redirected toward other interventions, such as turtle tourism, complementary conservation activities, or biodiversity monitoring. | Agree – High | Organize a working session with tourism stakeholders in the CAMPO landscape to review the tourism development strategy for Campo and identify actions to be undertaken by the various partners. | 0–6 months | PMU / Executing partners (WWF-Cameroon, AWF) | Not started | Source: MTR report p.61 |
| Reallocate funds, if necessary: If no viable tourism strategy emerges in the short term, consider reallocating unspent Component 4 funds (in part or in full) to underfunded components, such as M&E (Component 5), where there is clear demand. | Agree – High | Analyze and reallocate available funds to component 5 | 0–3 months | PMU (PM &FM) | Completed | Source: MTR report p.61 |
| Engage multiple private sector actors: Avoid over-reliance on a single tour operator. Engage a broader set of market actors – including tourism associations, eco-lodge investors, and regional tour operators – to stimulate competition, diversify offerings, and build a more resilient tourism sector. | Agree – Low | Convene a meeting with MINTOUL to discuss on this recommendation and agree on a way forward action to diversify private sector investment on sustainable development tourism in Campo | 3–12 months | PMU / Technical leads, | Not started | Source: MTR report p.62 |
| Conduct a comprehensive tourism market assessment: In order to identify private sector actors, replace or supplement feasibility studies with a market systems assessment that identifies: - Existing and potential demand for tourism to the region - Constraints and enabling environment factors - Opportunities for value chain development, for future collaboration if not within the scope of this Project - Key market actors (private sector, NGOs, tour operators) and their incentives for investing in t | Disagree | Update existing data on tourism development in Campo, including markets, and private sector engagement | 0–8 months | PMU / Consultant |  | Source: MTR report p.61 |
| Revise and expand indicators for Component 4: - Strengthen ecotourism and biodiversity monitoring indicators: Develop distinct outcomes and indicators for gorilla and turtle tourism that capture both conservation and livelihood benefits. Incorporate ecologically relevant metrics (e.g., gorilla groups monitored, nesting success rates, reduction in nest poaching) into the formal M&E system – even if not required under GEF Core Indicators – to ensure alignment with the project’s overarching conservation goals. Integrate existing field data from monitoring teams (such as nest counts, sightings, patrol effort, and threat detection) into reporting processes so that biodiversity outcomes are systematically tracked and used to inform adaptive management. - Improve benefit attribution: Refine the measurement of IPLC benefits. Distinguish between short-term participation (gap salaries) and sustained economic or non-economic benefits. Also consider tracking ongoing income generation, skill development, or changes in attitudes toward conservation linked to tourism efforts. - Include youth disaggregation: Apply the same standard of demographic disaggregation used for gender to youth. When the number of participants is low (as in this case), self-reported age ranges or estimates are acceptable and easily implemented. | Agree- Medium | Convene a working session to address this recommendation and shared it with relevant project executing partners for their inputs | 4-8 months | PMU/Project executing partners | Not started | Source: MTR report p.62 |
| Increase budget for Component 5: Restructure the Project budget to ensure adequate funding for the remainder of the project’s M&E, KM, and coordination activities. This revision should account for previously overlooked or underestimated costs, as well as inflation and evolving implementation needs – including an updated M&E plan. | Agree – High | Reallocate available budget from other components to component 5. | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Completed | Source: MTR report p.66 |
| Revise the M&E system and indicators: - Update the M&E tracking sheet and plan to ensure indicators clearly reflect what is being measured. - If the tracking of publications targeting women and vulnerable groups is no longer feasible, update the indicators accordingly; if it remains a priority, ensure it is tracked consistently. - Clarify distinctions between “plans” and “published documents” to align reporting with intended targets. - Strengthen the quality of communication and outreach indicators – consider moving beyond output counts to metrics such as distribution channels, publication venues, and audience reach (e.g., readership, online engagement, radio listenership) to better capture the impact of knowledge products. | Agree – High | Update TOC/Results Framework and M&E Plan to reflect the recommendation; . Update/clarify methodology to capitalize data on communications contributions to address relevant points of this recommendation | 0–4 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.66 |
| Update the Communication and KM Plan: With expert guidance, refocus the plan to (a) target communications that directly support specific components and strategies, ideally using results chains, and (b) outline a KM strategy that enhances the organization and packaging of information for easy sharing, in alignment with the communications plan. Clearly differentiate KM from M&E by defining its role in capturing, organizing, and applying lessons learned. | Agree – Medium |  | 4–12 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.66 |
| Strengthen the M&E system for GEF Core Indicators: - Clearly define and document methodologies for each indicator, especially regarding beneficiary counts and hectares under improved management. - Include assumptions, data sources, and verification protocols in the M&E Plan and reporting templates. - Ensure that “improved management” reflects sustained changes in practice, policy, or institutional capacity – not just isolated activities. - Avoid over-reporting by ensuring direct versus indirect impacts are clearly distinguished and beneficiaries are not double counted. | Agree – High | Update Results Framework and M&E system to reflect the recommendation; | 0–4 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.67 |
| Systematically document and share emerging success stories: Develop learning briefs, stakeholder exchanges, or contributions to national platforms to highlight promising practices and scalable models from this Project. | Agree – High | Document and share emerging success stories to reflect the recommendation | 0–6 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Ongoing | Source: MTR report p.73 |
| Strengthen qualitative monitoring: Integrate participatory and narrative-based methods (e.g., case studies, storytelling) into the M&E framework to better capture nuanced social and behavioral impacts that may not be reflected in quantitative indicators. | Agree – High | Update and M&E framework to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–6 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.73 |
| Develop strategies to address obstacles: Revise project strategies and results chains to directly address these remaining obstacles, incorporating more flexible funding approaches and clear pathways for sustainable implementation and benefit sharing. | Agree – High | Discuss with stakeholders of components 3 and 4 to develop and validate strategy to put in place to address the recommendation | 0–9 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.74 |
| Revise resource allocations: Explore options to increase flexibility in resource allocation and strategic planning to better support scaling initiatives. | Agree – High | Review budget execution and reallocations with Steering Committee; agree revised budget/AWP; document decisions and communicate with partners and GEF Agency. | 0–6 months | PMU (Project Manager & Finance) / WWF-Cameroon & WWF-US | Completed | Source: MTR report p.75 |
| Assess scalability: Conduct a comprehensive assessment of scalability with Executing Partners before the next agreement cycle, differentiating clearly between scaling within existing contexts and replication in new areas. Evaluate the specific opportunities and constraints related to each component to inform realistic scale-up plans. | Agree – Low | Assess and discuss the potential for scalability with executing partners to identify options that can be implemented within budgetary constraints, as well as those that could be considered by other partners or future projects | 4–12 months | PMU / Executing partners | Not started | Source: MTR report p.75 |
| Develop an exit strategy for sustainability: As the project moves forward, it would benefit from the development of a clear exit strategy that supports long-term sustainability. This should include practical steps for transitioning responsibilities, strengthening local ownership, and reducing dependency on external funding over time. | Agree – High | Hold a working session to develop an exit strategy or sustainably plan, and share it with project executing partners for input, adoption and implementation. | 4–12 months | PMU /project executing partners | Not started | Source: MTR report p.77 |
| Assess aspects of the Project that lack a pathway to sustainability: Identify Project components that currently rely on external funding and develop alternative strategies to ensure their sustainability beyond the Project's end. This should include assessing where clear pathways to sustainability are lacking and prioritizing actions to strengthen local ownership, capacity, and long-term resource mobilization. | Agree – Medium | Convene a working session to develop an exit and sustainability plan, and engage project executing partners in its review, adoption, and implementation, focusing especially on activities dependent on external funding | 4–12 months | PMU/ project executing partners | Not started | Source: MTR report p.78 |
| Refine component strategies, building upon current risk assessments and mitigation plans: Building on the ProDoc’s initial risk analysis for the broader project and the annual risk mitigation planning that the Project undertakes, assess risks by component and refine the strategies and mitigation measures to address key vulnerabilities. Through the development of results chains by component (previously recommended) with appropriate identification of risks, the Project would then refine strategies | Agree – High | Update the risk assessment by component and refine the implementation strategies and mitigation measures for the identified risks in order to address key vulnerabilities. | 4–12 months | PMU (Safeguards/Gender Focal Point / Supported by WWF-US ESS/Gender Specialist; Executing partners | Not started | Source: MTR report p.80 |
| Revise and expand the M&E plan: Revise the M&E plan to go beyond GEF requirements and reflect the broader ambitions of the Project, including indicators for ecological impacts, safeguards, and cross-cutting issues such as gender, youth, and IPLCs. WWF-US has modeled an alternative approach in Asia, which could be replicated here. Use the ProDoc Appendix 3 as a baseline and build from there. | Agree – High | Update Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.84 |
| Update the Tracking Tool: Maintain the tracking tool consistently to reflect actual project implementation. Ensure it is complete, well-labeled, and housed in a clearly identifiable M&E folder. Populate missing fields such as budget tracking and disaggregated data, or make it clear the Project will not be tracking this information. | Agree – High | Update Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.84 |
| Measure impact on all target beneficiaries: Include disaggregation by ethnicity (IPLC vs non-IPLC) and by age (youth 18–35) for all relevant indicators to better assess equity and inclusion. | Agree – High | Update the data recording sheet by incorporation a column on age group direct beneficiary (less than 35 and more than 35 years) | 0–3 months | PMU (M&E Lead) | Not started | Source: MTR report p.84 |
| Monitor threats and Conservation Targets: Incorporate data from existing threat and biodiversity monitoring systems (e.g., wildlife and social monitoring under Outcome 2.2) to help track ecological changes and assess project impact. | Agree – High | Update Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. This will concern only component 2 | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.84 |
| Document overachievement: When the Project has exceeded targets, but cannot report greater than 100% be sure the notes and/or accompanying narrative capture the full scope of success and improve learning. | Agree – High | Update Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.85 |
| Review and revise specific outcome indicators: Revise indicators, especially 1.1, 2.2, 3.1, 3.2, and 5.1, to improve clarity, consistency with baseline data, and alignment with project outcomes. | Agree-High | Update Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 0–3 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support |  | Source: MTR report p.85 |
| M&E capacity building: Train Project staff and partners to ensure effective and consistent data collection, analysis, and use. | Agree-Medium | Include capacities building of project staff during field M&E meeting to address this recommendation | 4-8 months |  | Ongoing | Source: MTR report p.85 |
| Establish clear KM Procedures: Establish clear KM procedures for knowledge capture, sharing, use, and organization including mention of version control, document finalization, and maintenance of a centralized storage of key project documents. Audit and update the shared drive to ensure that all essential documents are clearly labeled and up to date. | Agree – Medium | Update the Communication/KM plan; systematically document lessons and disseminate products; align visibility with donors and stakeholders. | 0–6 months | PMU (Comms/KM focal point) / WWF-Cameroon | Not started | Source: MTR report p.85 |
| Avoid double counting participants: Ensure that each participant signs in individually. For example, include a question such as “Have you participated in a previous activity?” (Yes/No) to reduce the risk of double-counting and better track actual reach. | Agree – High | Update attendance sheets by incorporation a column on age group direct beneficiary (less than 35 and more than 35 years) as well as the participation in a previous activity Enter systematically all the attendance sheet in an Excel data base and delete the double counting | 4–12 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Not started | Source: MTR report p.87 |
| Strengthen Indigenous leadership roles within the Project: Engage more IPLCs in leadership roles, including through formal advisory or liaison positions, to improve cultural relevance, build trust, and enhance communication with remote and traditionally underrepresented communities. | Agree – Medium | Engage with project executing partners to explore approaches for enhancing and sustaining the leadership roles of IPLCs, particularly Indigenous Peoples, throughout the implementation of project activities. | 4-12 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Not started | Source: MTR report p.88 |
| Explore strategies to engage remote populations: Expand the number of local representatives or facilitators gathering feedback in remote areas, particularly those inhabited by Indigenous Peoples, to ensure their views are more consistently captured. | Agree – Medium | Several executing partners have established local facilitators/focal points, while others have participatorily identified community relays across the various villages. In response to this recommendation, the Project will collaborate closely with partners to strengthen and systematize the frequency of outreach activities and the flow of information from these facilitators and community relays within the framework of project implementation.- | 4-12 months | PMU (Safeguards/Gender focal point) / Executing partners | Not started | Source: MTR report p.88 |
| Collect youth demographics: As part of all community engagements, collect basic demographic information at sign-in, including a checkbox for "What is your age range? (18–35 / 36+)". | Agree – Medium | Update the data recording sheet by incorporation a column on age group direct beneficiary (less than 35 and more than 35 years) | 4-12months | PMU (Safeguards/Gender focal point) / | Not started | Source: MTR report p.88 |
| Develop youth engagement strategies: Consider developing specific engagement strategies for youth, possibly through schools, vocational groups, or youth associations, to improve their participation and ownership in project activities. | Agree – Low | Strengthen inclusive facilitation/participation (IPLCs, women, youth); document actions and feedback/GRM use. | 4-12 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Not started | Source: MTR report p.88 |
| Expand partnerships with health organizations: Collaborate with local health or social service providers to proactively address risks related to alcohol abuse and gender-based violence. | Disagree | Support executing partners in raising awareness among communities about the risks associated with excessive alcohol consumption and gender-based violence. | 4-12months | PMU / Project Steering Committee / WWF-Cameroon | Not started | Source: MTR report p.90 |
| Strengthen inclusive facilitation practices: Ensure all Project staff and partners are trained in facilitation techniques that support inclusive dialogue, with specific attention to women, youth, and Indigenous participants. | Agree –Medium | Strengthen inclusive facilitation (IPLCs, women, youth); document actions and feedback/GRM use. | 4–12 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Not started | Source: MTR report p.90 |
| Engage youth directly: Facilitate structured engagements with youth across communities to capture their perspectives, and systematically document participation and insights. | Agree – Medium | Strengthen inclusive facilitation (IPLCs, women, youth); document actions and feedback/GRM use. | 4–12 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Not started | Source: MTR report p.90 |
| Build capacity with local partners: Revisit funding and targeted training to BACUDA, and seek out new opportunities to engage with local organizations that may have a willingness to support safeguard-related activities but currently lacks adequate capacity. | Agree – High | Continue strengthening the capacity of local organizations managing the grievance mechanism within the Project, in collaboration with the National Human Rights Commission. | 4-12 months | PMU (ESS/Gender focal point, supported by WWF-US ESS/Gender specialist and the PMU M&E Specialist | Not started | Source: MTR report p.90 |
| Integrate safeguards into the results chain: Hire a qualified safeguards specialist to revise the Project’s results chain, explicitly linking safeguard risks and mitigation measures to Project success indicators. This will support more holistic planning and monitoring. | Agree – Medium | Update Results Framework and M&E Plan to reflect the recommendation; adjust indicators/means of verification; integrate into AWPs and reporting. | 4-12 months | PMU (M&E Lead) / WWF-Cameroon, with WWF-US support | Not started | Source: MTR report p.90 |
| Position WWF as a connector: While WWF is not expected to solve complex social issues alone, it could actively partner with specialized organizations and serve as a messenger or convener to help address grievances raised through the GRM. | Agree – Low | Integrate recommendation into SEP and safeguards implementation | 4-12 months | PMU (Safeguards/Gender focal point) / WWF-Cameroon | Not started | Source: MTR report p.91 |
| Allocate, identify or advocate for additional funding: Explore alternative sources of funding, including requesting supplemental GEF resources, to support the effective implementation and operationalization of the GRM in project landscapes. Continue support on regular capacity building to improve expertise of staff and of entities responsible for the functioning of the GRMs in all three landscapes. | Agree – High | Review budget execution and reallocations with Steering Committee; agree revised budget/AWP; document decisions and communicate to partners and GEF Agency. This is a GEF-7 project and it seems unrealistic to request more GEF funding at this point. | 0–6 months | PMU (Project Manager & Finance) / WWF-Cameroon & WWF-US | Completed | Source: MTR report p.91 |
| Build capacity of local partners: Continue to provide targeted training and corresponding financial support to BACUDA and other trusted local organizations in all three landscapes to support GRM-related issues that exceed the technical scope of the Project team. | Agree – Medium | Continue strengthening the capacity of local organizations managing the grievance mechanism within the Project, in collaboration with the National Human Rights Commission. | 4-12 months | PMU (ESSO) / WWF-Cameroon & WWF-US | Ongoing | Source: MTR report p.91 |
| Consider how to address grievances related to human-wildlife conflict in future projects: Future projects should prioritize addressing human-wildlife conflict within GRM, as this remains one of the most frequently reported yet unresolved issues. When these grievances go unaddressed, the entire system risks losing credibility, leading to a decline in participation and trust. | Agree – High | Consult with the GEF Operational focal point during the formulation of future GEF projects. | 2–8 months | PMU / GEF Focal point | Not started | Source: MTR report p.91 |
| Expand GRM outreach in remote areas: Increase the number of community-based representatives trained to manage and explain the GRM, particularly in hard-to-reach areas. This includes providing tailored outreach and regular follow-up, which is reportedly planned but not yet fully implemented. | Agree – Medium | Develop an implementation plan addressing the recommendation with the executing partners (RACOPY and BACUDA). | 0–6 months | PMU (Safeguards/Gender Focal Point)/ Executing Partners | Not started | Source: MTR report p.91 |