REQUEST FOR CEO ENDORSEMENT

Project Type:

Type of Trust Fund:

PART I:

Project INformation

| Project Title: Introduction of new agricultural methods for the conservation and sustainable use of biodiversity, including plant and animal genetic resources, in productive landscapes in selected areas of Cuba (COBIMAS). |  |  |  |
| --- | --- | --- | --- |
| Country: | Cuba | GEF Project ID: | 9435 |
| GEF Agency(ies): | FAO | GEF Agency Project ID: | 639973 |
| Other Executing Partner(s): | Ministry of Agriculture (MINAG) | Resubmission Date: | 31 May 2018 |
| GEF Focal Area (s): | BD | Project Duration(Months) | 60 |
| Name of Parent Program | N/A | Project Agency Fee ($): | 282,462 |

- Focal Area Strategy framework

| ### Objectives/Programs | ### Expected Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Co-financing |
| BD 3: Sustainably use biodiversity/Program 7: Securing Agriculture’s Future: Sustainable Use of Plant and Animal Genetic Resources | Outcome 7.1 Increased genetic diversity of globally significant cultivated plants and domesticated animals that are sustainably used within production systems. |  | 1,261,328 | 11,225,020 |
| BD 4: Mainstream biodiversity conservation and sustainable use into production landscapes and seascapes and production sectors/ Program 9: Managing the Human-Biodiversity Interface | Outcome 9.1 Increased area of production landscapes and seascapes that integrate conservation and sustainable use of biodiversity into management. Outcome 9.2 Sector policies and regulatory frameworks incorporate biodiversity considerations. |  | 1,711,960 | 15,234,980 |
| subtotal BD focal area |  |  | 2,973,288 | 26,460,000 |
| Total Project Cost |  |  | 2,973,288 | 26,460,000 |

- Project Description Summary

| ### Project Objective: To promote the conservation and sustainable use of agro-biodiversity in selected areas of Cuba, through the introduction of sustainable agricultural production intensification and the conservation, adaptation and rescue of globally important plant and animal genetic resources. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### GEF Project Financing ### ($) | ### Confirmed Co-financing ($) |
| ### 1. Knowledge, mapping and planning of plant and animal genetic resources those are important for the future of agriculture. | ### TA | ### .Plant and animal genetic resources for food and agriculture are better known in Cuba. -Nineteen (19) national relevant researches institutions enhance its organizational capacities and its technicians and researchers around 1500 will receive special training to held the implementation, systematization and diffusion of experiences, addressed to adopt conservation practices of the GRFA and the SCPI (Sustainable Crop Production Intensification). -12 Globally Important Genetic Recourses are managed and conserved. 5 ZRFA improve it conservation status changing to a minor threat category. | 1.1.1 Analysis of globally-important plant and animal resources living in Cuba, their valuation and ways and means for conservation. 1.1.2 A catalogueof globally important plant and animal diversity (focused on wild species). 1.1.3 Maps and databases updated through geographical information systems (GIS) considering production potential, fragility and importance of targeted ABD species. 1.1.4 Existing plant and animal breeding programs supported for the adaptive trials of advanced lines and production of early generation seeds. 1.1.5 A knowledge management platform designed for monitoring and analyzing factors of agro-biodiversity conservation and use, and alerts for major threats. | ### GEFTF | ### 1,000,000 | ### 9,540,000 |
| ### 2. Implementing the Save and Grow approach in productive landscapes | ### TA | 2.1. Increased adoption of production systems that integrate biodiversity conservation through the creation of connectivity corridors, bringing together agricultural and natural ecosystems. -610 000 ha of productive and natural landscapes are benefitted. 30 000 ha directly benefitted through the implementation of the “Save and Grow” approach while are conserved globally important GRFA. Others 580 000 ha are indirectlycovered. -2000 farmers are benefited by strengthening of capacities about adoption of ABD conservation practices and SCPI. -50% of producers from selected cooperatives with increased confidence in SCPI practices (2715 producers in all). -800 producers improve their incomes by 30%. | 2.1.1. A landscape production strategy agreed by stakeholders, with particular attention to gender and youth, applying the Save and Grow approach. 2.1.2. Sustainable agricultural intensification practices along the lines of the Save and Grow principles and practices piloted, tested, adapted to the context, and scaled-up including conservation corridors and ecosystem connectivity. 2.1.3. In situ and ex situ conservation actions, in place. 2.1.4. Capacity development program for rural communities, cooperatives and protected areas managers on management, incentives and best practices/technologies, with a gender focus. Output 2.1.5. Value chains for new products related to agrobiodiversity developed to promote the conservation of agroecosystem in rural production. | ### GEFTF | ### 1,283,900 | ### 10,200,000 |
| ### 3. Strengthening the enabling environment for sustainable agriculture and conservation of PGRFA in Cuba | ### TA | 3.1. Enhanced inter-institutional coordination, closer technical cooperation and regulatory coherence have supported the mainstreaming of agro-biodiversity conservation and use in public policies. -Not less than 2 new Laws about management and conservation of PGRFA and ZGRFA. | 3.1.1. A detailed review of the current legal and regulatory frameworks on agrobiodiversity conservation and sustainable agriculture. 3.1.2. A road-map for legal and regulatory coherence within the country (on agrobiodiversity conservation and sustainable agriculture). 3.1.3. A manual that illustrate the process of sustainable management of production landscapes to facilitate the scale-up at national level. | ### GEFTF | ### 401,103 | ### 4,530,371 |
| ### 4.Monitoring, evaluation and dissemination of project information | ### TA | ### 4.1: Project implementation based on RBM and lessons learned/good practices documented and disseminated | 4.1.1. The project management, monitoring and evaluation system in place and providing systematic information on progress made to achieve planned results and objectives. 4.1.2. Mid-term review and final evaluations carried out, finalized implementation and sustainability strategies tailored to recommendations. 4.1.3. Communication strategy and dissemination of project actions. 4.1.4. Publication of best practice and lessons learned | ### GEFTF | ### 146,700 | ### 1,000,000 |
| Subtotal |  |  |  |  | ### 2,831,703 | ### 25,270,371 |
| Project management Cost (PMC) |  |  |  |  | ### 141,585 | ### 1,189,629 |
| Total project costs |  |  |  |  | ### 2,973,288 | ### 26,460,000 |

- Confirmed sources of Co-financing for the project by Name and Type ($)

| Sources of Co-financing | Name of Co-financier (source) | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Ministry of Agriculture(Soil Fund) | Cash | 3,600,000 |
| Recipient Government | Ministry of Agriculture(Soil Fund) | In kind | 5,000,000 |
| Recipient Government | Flora and Fauna Business Group | In kind | 5,610,000 |
| Recipient Government | Flora and Fauna Business Group | Cash | 4,000,000 |
| Recipient Government | National Forestry Department/FONADEF | In kind | 2,000.000 |
| Recipient Government | National Forestry Department/FONADEF | Cash | 6,000.000 |
| GEF Agency | FAO | Cash | 250 000 |
| Total |  |  | 26,460,000 |

- Trust fund resources requested by agency, country, focal area and the programming of funds.

| GEF Agency | Type of Trust Fund | Focal Area | Country Name | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount(a) | Agency Fee (b) | Total c=a+b |
| FAO | GEFTF | Biodiversity | Cuba | 2,973,288 | 282,462 | 3,255,750 |
| Total Grant Resources |  |  |  | 2,973,288 | 282,462 | 3,255,750 |

- Project’s contributions to target environmental benefits:

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| 1. Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | Direct coverage: 30,000 hectares Indirect coverage: 580,000 hectares |

- Does the project include a “non-grant” instrument?

NA

part ii:project JustiFication

- Describe any changes in alignment with the project design of the original PIF

A.1		Project Description

- Global environmental and/or adaptation problems, root causes and barriers that need to be addressed

No significant changes to the PIF. However, following STAP recommendations the section on barriers was reorganized and reformulated, kindly see section 1.2.3.of the FAO GEF Project Document.

- The baseline scenario or any associated baseline projects

No significant changes to the PIF. Addressing STAP comments, the analysis has been strengthened and baseline figures confirmed.

- The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project

There have been a number of changes between the components, outputs and indicator targets of the projects as set out in the Project Framework of the PIF and that now proposed in the Results Framework. The differences between the indicators and target values proposed in the PIF and those currently proposed are included on following comparison table:

| PIF | Full project proposal | Justification |
| --- | --- | --- |
| Project objective: To conserve and sustainably use biodiversity in selected areas of Cuba, through the introduction of sustainable agricultural production intensification and the conservation, adaptation and rescue of globally-important plant genetic resources. | Project objective: To promote the conservation and sustainable use of agro-biodiversity in selected areas of Cuba, through the introduction of sustainable agricultural production intensification and the conservation, adaptation and rescue of globally important plant and animal genetic resources. | To address STAP comments, the project objective was slightly rephrased to add more detail on the type of biodiversity that will be conserved and sustainable used. |
| Component 1: Conservation of plant genetic resources that are important for the future of agriculture. | Component 1: Knowledge, mapping and planning of plant and animal genetic resources that are important for the future of agriculture. | Addressing STAP comments, component 1 has been reframed to focus on knowledge, mapping and planning of plant and animal genetic resources that are important for the future of agriculture. The outcome to be achieved under this component and related indicators and were reformulated accordingly (see below). |
| # Outcome 1.1: The diversity of plant genetic resources for food and agriculture (PGRFA) has been increased in project areas. Target indicator: Enhanced genetic diversity in at least 100,000 hectares of production landscapes, including crop species and wild relatives. Indicator BD 7.1: Diversity status of target species (measured by the BD tracking tool). | Outcome 1.1.Plant and animal genetic resources for food and agriculture are better known in Cuba. Indicator 1: Strengthened capacities of research institutes (through hands-on experience) |  |
| Output 2.1.4: Analysis of globally-important plant species living in Cuba and their valuation. | Output 1.1.1.Analysis of globally-important plant and animal species living in Cuba, their valuation and ways and means for conservation | The output was moved here from component 2 in the process of redefining the two components, as requested by STAP. |
| Output 1.1.1: A catalog of globally-important plant diversity (focused on timber and non-timber forest species, fruit trees, and crops with an emphasis on wild species, pollinators, and microorganisms). | Output 1.1.2.A catalogue of globally important plant and animal diversity (focused on wild species). | Renumbered and redefined, as a result of the activities carried out during the PPG, especially the consultations of experts, government assessments and more detailed evaluations during the visits to the areas |
| Output 1.1.2: In situ and ex situ conservation actions, in place. Target: 100,000 hectares and x seed banks (number to be defined during full project preparation) | Output 1.1.4.Existing plant and animal breeding programs supported for the adaptive trials of advanced lines and production of early generation seeds. | Adjusted area and move to the output 2.1.3 |
| Output 1.1.4: A knowledge management platform designed for monitoring and analyzing factors of agro-biodiversity conservation and use, and alerts for major threats. | Output 1.1.5.A knowledge management platform designed for monitoring and analyzing factors of agro-biodiversity conservation and use, and alerts for major threats. | Renumbered |
| Component 2: Production landscapes integrate conservation and sustainable use of biodiversity. | Component 2: Implementing the Save and Grow approach in productive landscapes Indicator: Quality of data and analysis shared to demonstrate the scientific and technical validity of the Save and Grow approach in Cuba. | Addressing STAP comments, component 2 has been reframed. |
| Output 2.1.2: Landscape management practices adopted (based on 2.1.2), including sustainable production systems, conservation corridors and ecosystem connectivity. | Output 2.1.2. Sustainable agricultural intensification practices along the lines of the Save and Grow principles and practices piloted, tested, adapted to the context, and scaled-up including conservation corridors and ecosystem connectivity. | Reformulated to provide more detail on which landscape management practices will be promoted, a requested by STAP. |
| Output 1.1.2. In situ and ex situ conservation actions, in place. | Output 2.1.3.In situ and ex situ conservation actions, in place. | Moved from Component 1 to component 2 as per STAP request. |
| Output 2.1.3: Capacity development program for rural communities, cooperatives and protected areas managers on management, incentives and best practices/technologies, with a gender focus. | Output 2.1.4. Capacity development program for rural communities, cooperatives and protected areas managers on management, incentives and best practices/technologies, with a gender focus. | Renumbered |
| Output 2.1.5: Innovative market or public incentives, including labelling, that promote the conservation of agroecosystems in rural production. | Output 2.1.5. Value chains for new products related to agrobiodiversity developed to promote the conservation of agroecosystem in rural production. | Redefined to better reflect the activities that will be implemented. |
| Component 3: Enhanced Policy and Legal Framework | Component 3.1: Strengthening the enabling environment for sustainable agriculture and conservation of PGRFA in Cuba | Following STAP recommendations, this component including outcome and related outputs, was revised, kindly see details below. The title was rephrased to better describe these changes. |
| Outcome 3.1: Policy, regulatory and legal frameworks for agricultural production in Cuba have mainstreamed agro-biodiversity conservation and use. | Outcome 3.1. Enhanced inter-institutional coordination, closer technical cooperation and regulatory coherence have supported the mainstreaming of agro-biodiversity conservation and use in public policies. |  |
| Output 3.1.1: Legal and regulatory framework revised by including agrobiodiversity conservation and sustainable use criteria and integrating the perspectives from production to governance. | Output 3.1.1. A detailed review of the current legal and regulatory frameworks on agrobiodiversity conservation and sustainable agriculture. |  |
| Output 3.1.2: At least 2 national, 3 provincial and 1 local legal and regulatory frameworks have integrated methods and tools for genetic diversity rescue and conservation. | Output 3.1.2. A road-map for legal and regulatory coherence within the country (on agrobiodiversity conservation and sustainable agriculture). |  |
| Output 3.1.3: Legal and informative manuals that illustrate the process of sustainable management of production landscapes, published, to facilitate the scale-up at national level. | Output 3.1.3. A manual that illustrates the process of sustainable management of production landscapes to facilitate the scale-up at national level. |  |
|  | Component 4: Project management, monitoring and evaluation (M&E) Outcome 4.1. Project implemented, lessons learned and good practices documented and disseminated. Output 4.1.1: The project management, monitoring and evaluation system works to provide systematic information on progress made to achieve planned results and objectives Output 4.1.2: Mid-term review and final evaluations carried out, finalized implementation and sustainability strategies tailored to recommendations. Output 4.1.3: Communication strategy and dissemination of project actions Output 4.1.4: Publication of best practice and lessons learned | A dedicated component for monitoring and evaluate was included to facilitate the documentation and dissemination of project results and lessons learned. |

Feasibility studies carried out during project preparation show that 4 years would not be enough to achieve the proposed objectives On this regard and with the aim of being able to adequately evaluate the results, taking into account the duration of the biological processes that the project intends to attend, especially those associated with the rescue, conservation and improvement of genetic resources. Project duration has been increased to 60 months.

- Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, CBIT and co-financing

The incremental cost reasoning remains in general as proposed in the PIF. For more details on expected contribution from the baseline, the GEF and co-financing kindly refer to the FAO GEF project document, section 1.

- Global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF)

There have been the following changes in relation to the PIF:

| Focal area | PIF | CEO Endorsement |
| --- | --- | --- |
| BD | An increase of at least 300,000 hectares of productive landscapes managed with a view toward conservation and sustainable use of biodiversity. | 610 000 ha of productive and natural landscapes in the 3 target localities are benefitted. 30 000 ha directly benefitted through the implementation of the “Save and Grow” approach while are conserved globally important GRFA. Others 580 000 ha are indirectly covered. |
|  | Diversity status of targeted agro diversity species (target to be measured with the BD tracking tools) Enhanced genetic diversity in at least 100,000 ha. | The genetic diversity of 12 globally important agrobiodiversity species and varieties will be improved in around 30000 ha of farming systems implementing the “Save and Grow” approach. |

- Innovativeness, sustainability and potential for scaling up.

No significant changes to the PIF.

A.2. Child Project If this is a child project under a program, describe how the components contribute to the overall program impact.

N/A

A.3. Stakeholders. Identify key stakeholders and elaborate on how the key stakeholders’ engagement is incorporated in the preparation and implementation of the project. Do they include civil society organizations (yes/no)?and indigenous peoples (yes/no)?

Primary stakeholders

The primary stakeholders of the project will be small- and medium-scale farmers managing threatened and globally-important agrobiodiversity in the 3 target localities. Around 70% of the actors are small-scale producers whose production is used for consumption and seeds and 50-70% is for sale.

Studies carried out during the project preparation phase indicate that most of the target producers have diverse livelihood support strategies, combining subsistence production with varying levels of market production of grains and vegetables, complemented by the raising of livestock (cattle and/or pigs and poultry), collection of timber and non-timber forest products, off-farm labor and commerce. The relative importance of each of these elements in any given family depends on a range of factors, including availability of family labor and land, and access to financial capital or complementary income. Producers who specialize in specific productive activities, or who have developed collaborative forms of production and business, are in many cases represented by community-based organizations. The following organizations were selected during PPG studies in the target communities:

- CCS Fernando Echenique

- CCS Terencio Combar

- CCS Ramón Ramos

- CCS Manuel Piti Fajardo Rivero

- UEB Integral Agropecuaria Río Cauto

- CCS Bienvenido Pardillo

- CCS 1ro de Enero

- CCS 10 de Octubre

- CCS Antonio Maceo

- CCS Luis La O

- CCS  Antonio Maury

- UEB Unión de Reyes

- UEB Ciénaga Occidental

- UEB Agropecuaria

The project will also interact closely with other established organizations in the target communities, which function as mechanisms for stakeholder representation and natural resource governance. These include:

Key institutional stakeholders

| Institutions | Roles | Responsibilities in the project |
| --- | --- | --- |
| Ministry of Agriculture. Department of Science and Technical. (MINAG) | Main government project partner | Leads in-situ and ex-situ conservation of agro biodiversity in Cuba It is responsible for project execution and overall coordination, will coordinate the relationship between all the institutions engagement in the project at national level through the Science and Technical Department and will also provide co-financing resources to complement GEF project activities. It will support all the components of the project |
| Ministry of Science, Technology and Environment (CITMA). | Political and Operational GEF Focal Point | The 3 components of the project National environmental authority and project partner. CITMA will ensure the accomplishment of the environment requirements of project implementation and it is responsible for the bases initiatives execution for the agro-biodiversity conservation. |
| Ministry of Higher Education (MES) | Implementing partner | Components 1,2 and 3.Their regional universities and research centers will support the project performance with qualified experts, whit knowledge and experience in innovative practices in the agricultural systems and rural communities They will prepare studies and support training actions related to sustainable use of agro-biodiversity resources. |
| Local Governments (at Popular Power at community, municipal and province level) | Local and regional authorities | Components 2 and 3. At most responsible of the project decisions at local and regional level. They facilitate the interchanges and coordinating spaces among different stakeholders The coordination role ensure integration of conservation and sustainable use of agro-biodiversity in regional strategies, including the necessary allocation of resources to support these activities. They are essential in the support and coordination of activities related to strengthening and inclusion of poor communities, young and women, and creation of conditions to developing local markets and specific alliances linked to tourism and gastronomy activities, labeling and certification standards, capacity development, research and networking, and strengthening the linkages between the production, market and public policies for the valorization of agro-biodiversity and cultural heritage on a territorial basis. |
| Local communities Including small farmer producers | Beneficiaries | Component 1, 2 and 3: Models of sustainable production on agro-biodiversity, conservationist and productive pilots systems. Mechanisms to strengthen and consolidate the participation in and for policy decision making processes. The farmers are responsible of the application of approach focused on agro biodiversity conservation and sustainable agricultural production through the diversified livelihood support systems and the identification of the synergies between the management, marketing and conservation of ABD |
| FAO | GEF Implementing Agency | Provision of technical assistance on sustainable natural resource management, rural development, biodiversity preservation, land degradation, and sustainable forest management. Support of methodologies according to international standards. Support and monitoring of project implementation. FAO will closely supervise the execution of the project, supervise the OP in the provisions of the OP Agreement, and will provide overall orientation. |
| Institute of Fundamental Research into Tropical Agriculture ¨Alejandro de Humboldt¨ (INIFAT) | Implementing partner, | Led the vegetal germoplasm guard in the country. It is the technical stakeholder leader in the project and responsible for the research +development activities in the 3 components, to collect and process the information obtained and to strength the capacity development activities with experts and researchers. It will also provide co-financing resources |
| Research Centre for Tropical Agriculture Animal Improvement (CIMAGT) | Implementing partner | It is the institution responsible of the led the animal germoplasm guard in the country. It is responsible for the research +development activities, mainly in the 1 and 2 components, to collect and process the information obtained and to strengthen the capacity development activities with experts and researchers, particularly in the rabbit and goat genetic breeding. It will also provide co-financing resources |
| Protected Areas Management Units (including biological station) | Beneficiaries | It will support all project components with information and research It manages programs of conservation of natural resources and participation and environmental education (component 1)and administrates several production centers in the implementation areas (component 2) It will participate in the construction of the particular strategy. in each zone and will also provide co-financing resources |
| National Association of Small Farmers (ANAP)(Municipal, province and national level) | Contributors | Organization that represent farmer’s interest in the country and provide coordination of activities with cooperatives and farmers. Component 2: Replication of production practices at local level. Component 3: Participation in the dissemination of evidences and knowledge on sustainable natural resource management |
| Cuban Women’s Federation(FMC) | Contributors | Women Organization in the country which represent women’s interest at local, municipal, province and national level. Participate in the construction of each local strategy, in order to provide a gender perspective. |
| Cuban Association of Agricultural and Forestry Technicians (ACTAF) at municipal, province and national level | Contributors | Components 1 and 2. Support the capacities development process in several areas (agroecology, organic certification; market chain, seed management; rural development, gender equity, etc.) |
| Cuban Association of Animal Production (ACPA) at municipal, province and national level | Contributors | Components 1 and 2. Support the capacities development process in livestock issues and will support the multiplication of creole animal races included in the project. Multiplication of creole animal races |

The local communities stakeholders have been fully involved in consultations and design process during the formulation phase, in order to ensure the effective participation of the different stakeholder groups described above in project implementation, including effective representation of their interests in project decision-making and to obtain their consent for the project’s actions in their specific communities, with the principles of access and benefit sharing.

Several workshop (3) in each zone of the project were hold during the PPG phase which key stakeholders participated in the identification of the genetic resources to manage during the project, the cooperatives and producers to engagement, to evaluate troubles, proposals and alternatives in each zone and to validate the results framework and the proposed arrangements for project implementation and stakeholder participation.

Key elements of this engagement plan include the following:

Strengthening of the capacities of farmers, technicians and authorities to influence policies and institutions in favor of the ABD

Emphasis on ensuring the representation and participation of women, young people and vulnerable communities in project activities and the distribution of benefits

Propitiate interactions among the different stakeholders at different sectors and levels in order to improve the conservation and sustainable use of the ABD approach

Permanent consultation and dialogue with the local communities, authorities, leaders and grassroots organizations

During the first months of project implementation the stakeholder and gender strategies will be updated, validated and finalized, in the specific context of the target localities and in full consultation with the relevant project stakeholders. In this manner, stakeholder representatives will be involved in the mid-term and final external evaluations, where they will be consulted about the adequacy of their participation in project design and implementation.

There´s no indigenous people neither indigenous organizations. The landowners cooperatives and farmers won´t be affected with the project’ actions, on the contrary, the project implementation will improve the labor and live conditions of the local people and the community capacities, and will strength self-development process embedded in their local identity and cultural heritage.

A.4. Gender Equality and Women's Empowerment. Elaborate on how gender equality and women’s empowerment issues are mainstreamed into the project implementation and monitoring, taking into account the differences, needs, roles and priorities of women and men. In addition, 1) did the project conduct a gender analysis during project preparation? Yes; 2) did the project incorporate a gender responsive project results framework, including sex-disaggregated indicators? Yes; and 3) what is the share of women and men direct beneficiaries? At least 20% of women.

The project will focus on promoting participation of women, empowering them to foster their participation in planning and decision-making and to improve their productivity, income and living conditions, taking in to account the differentials needs, roles, priorities and expectations of women and men and the social disadvantage status of the women. The data will be disaggregated by sex for monitoring differential impacts of the project, and women producers will be particularly involved in all project activities. The project will target not only women working in the agriculture sector, but also those women that are currently out of the labor market, offering them capacity development opportunities, with a target of 100 new jobs created for women.

Where relevant, project indicators have been made gender sensitive, specifically:

Outcome 2.1 indicators: Enhanced animal and plant genetic diversity for F&A in at least 30,000 hectares of production landscapes, including crop wild relatives. (Target specifies 20% controlled by women; % of farmers with increased confidence in innovative sustainable practices (higher productivity and sustainable natural resources management are possible). (Target specifies “50% of producers from selected cooperatives (20% of whom are women) with increased confidence in SCPI practices (2715 producers in all); 30 000 hectares of production landscapes that integrate biodiversity conservation and sustainable use into their management with certification. (Target specifies “(20 % controlled by women)”; Number of producers who increase their incomes through an implementation of “Save and Grow” approach (including access to new markets). (Target specifies “800 producers improve their income”.

Output 2.1.3 is “In situ and ex situ conservation actions, in place, including young and women participation

Output 2.1.4 indicator: Number of farmers and extension workers trained in SCPI and ABD conservation. (target specifies “2000 producers, 600 of them are women”)

Output 2.1.5 indicator: Number of people in selected production and marketing chains (excluding agricultural producers) who received economic benefits based on their implementation with an equity focus (target specifies “70 people benefited by chain implementation (30 of them are women)”

Outcome 4.1.4 indicator: Number of annual publications on best practices and lessons learned and other technical publications with gender and intercultural approach.

A.5    Risk. Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, the proposed measures that address these risks at the time of project implementation:

| Risk description | Impact | Likelihood of occurrence | Mitigation actions | Responsible |
| --- | --- | --- | --- | --- |
| Institutional risk at local and national level: coordination difficulties between participating national institutions, cooperatives, farmers’ organizations, local businesses and governments as a result of territorial competences, conflicts of interest, misinformation or changes of officials. | VL: Implementation of activities and decision-making processes will be affected, particularly with regard to national co-financing implementation mechanisms | L | The project will establish a permanent mechanism of inter-institutional coordination between participants promoting integration, information exchange and partnership at local and national level. - joint drawing up of proposals for sustainable management of agrobiodiversity (local and national) - Operation of multi-stakeholder working spaces to promote communication and partnership. - joint actions for the exchange of experiences and learning (workshops, trips and tours) - strategy of communication and dissemination of project contributions and knowledge gained | General project coordination |
| Risks due to weather events (which may or may not be as a result of climate change): possibility of occurrence of extreme events such as droughts and hurricanes that involve significant changes in the project's natural baseline conditions | H activities and objectives may be jeopardized due to possible impact on protected areas that results in destruction of the ecosystems and makes it impossible to carry out collections and inventories in the areas; damage to the productive infrastructures of cooperatives and producers that affect their performance; acute water scarcity that prevents certain crops from growing | M | The recommendations established in the local studies of vulnerability and risk will be followed to face severe climate events. These studies carried out by experts from the Ministry of Environment and other institutions in each municipality are available in each intervention ​​project area. - Project Infrastructure works for mini-industries, ecology stations and for storage will be reinforced in accordance with nationally established guidelines and regulations to face hurricanes and floods. -The Save and Grow approach contains per se several practices which improves the resilience of the agroecosystems. - Crop planting activities will be planned observing the behavior of rain patterns and local experience. - Will be adopted special measures for the water storage and its disposal during the dry period. - It will be a priority to cultivate varieties of plants and animal breeds tolerant to water stress. - The planning of the crops will consider the periods of climatic eventualities to avoid greater losses. -the topography will be an important factor to establish animal breeding farms avoiding floods. -It will be guaranteed to conserve the important conservation varieties ex situ (in genebanks). - The project will be supported by risk maps and local monitoring systems. - Work Relations will be maintained with the Municipal Centers for Prevention and Risk Management attached to the government in each municipality. -The Agro meteorological bulletins will be an important tool for crop management. -The Cooperatives will access the crop insurance system. | Project coordination team |
| Risks for biodiversity. Possible conflicts between the interests of conservationists and natural resource users. | L: Possible lack of compatibility between conservation actions and needs of communities and productive sectors may have an impact on natural ecosystems and protected areas | L | - Establishment of agreements and plans between interested parties. - Demonstration of shared benefits and responsibilities. Training and awareness processes with all relevant stakeholders. - Inclusion of local experts in each area with capacity to implement a participatory and self-restructuring approach. -Inclusion of community interests in restructuring actions. - Management of agrobiodiversity to promote employment and income sustainably. - Drawing up of lists of permitted species for silvopastoral systems, excluding those that could behave invasively even when already present in agro systems and protected areas - Establish strict measures for GRFA in terms of scaling up and conservation. - Constant monitoring of selection of species used in silvopastoral systems, GRFA management areas and compliance with SCPI principles. | Project coordination team |
| Social risk: Producers and inhabitants show no interest in agrobiodiversity conservation strategies for fair and sustainable development | L: Low capacity to demonstrate and extend new fair and sustainable management practices | L | - Promotion of methods of practical and cooperative learning between producers, technicians and officials with new innovative strategies. - Knowledge management platform with participation of all stakeholders. - Strengthening of capacities and infrastructure to reduce obstacles to adoption. - Prioritize women and young people with opportunities for access to resources and capacity-building. - Promote strategies to support women and domestic–family activity developed by local stakeholders and the FMC (Cuban Women’s Federation) -Promote policy changes to drive sustainable ABD management | Project coordination team |

A.6. Institutional Arrangement and Coordination. Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

The Food and Agriculture Organization of the United Nations (FAO) is the GEF agency responsible for supervising and providing technical support during project implementation. Furthermore, at the request of MINAG (see section 2.2.2), FAO will be responsible for project financial and operational implementation as well as acting as the implementing body. This means that FAO will provide recruitment services in accordance with FAO standards and procedures while providing financial services to manage GEF resources.

The Ministry of Agriculture will appoint a National Project Director (NPD) who will be responsible for supervising and providing guidance on policies and priorities supported by the project. The NPD will also be responsible for coordinating activities with all stakeholders in project components in conjunction with the National Project Coordinator. He or she will be responsible for promptly requesting the disbursement of GEF funds for project implementation, strictly based on the approved Project Work Plan (Appendix 2) and the Annual Work Plan (AWP). This office includes the National Project Director and other three researchers/specialists who will participate in the support and coordination of the different activities for project implementation (financed by the Cuban Government). On the other hand the participating institutions involved in the execution of the project will be incorporated into the three project components with 56 professionals, 10 doctors in science, 18 researchers, 19 specialists and 8 technicians.

A Project Team (PT) will be setup funded by the GEF. The main function of the PT, following the guidelines of the Steering Committee, is to ensure project coordination and implementation through the effective implementation of annual work plans. It will be made up of a National Operations Officer (NOO) as well as two accounting and finance assistance and specialist consultants (communication, specialists in plant and animal genetic resources, sustainable land and natural resource management) who will be recruited for shorter periods.

For project strategic decisions, a Project Steering Committee (PSC) will be established, made up of MINAG, MINCEX, CITMA, CIMAGT, INIFAT and Flora y Fauna and will include the four regional coordinators and the FAO Representation in Cuba. Its main function is to guide project implementation, verify and approve annual work plans, approve financial and technical reports and provide the strategic guidance necessary for carrying out the project.

The organizational structure of the project is outlined in the diagram below. For further details kindly refer to Section 3.2 of the FAO GEF Project Document.

Coordination with other initiatives

FAO, MINAG and the project partners will collaborate with the implementing agencies of other programs and projects to identify opportunities and facilitate synergies with other relevant GEF projects, as well as projects supported by other donors. This collaboration will include: (i) informal communications between GEF agencies and other partners in implementing programs and projects; and (ii) exchange of information and outreach materials between projects.

The project implementation team will establish contact with representatives of a number of other relevant GEF-funded initiatives in order to ensure that opportunities for coordination of effort and exchange of lessons learned are fully realized throughout the project implementation period. This communication will initially be achieved by inviting the representatives of the other projects to the project inception workshop: they will also be included in the target audiences for communication materials generated by the project, and will be invited, when relevant, to participate in further dissemination and planning workshops held by the project, and potentially also in the Technical Consultative Committee of the project to advise on specific issues.

Projects of particular relevance, which will be prioritized for communication and coordination, will include the following:

“Conservation of agrobiodiversity in biosphere reserves in Cuba: Connecting managed and natural scenarios” (UNDP/GEF). This aimed to complement plant genetic resource rescue and conservation actions by means of agricultural management practices focusing on food security. Contributions included: development, incorporation and supervision of an Agrobiodiversity Programme that has been incorporated into the CNAP system general plan and each relevant management plan in protected areas; strengthening of the farmer–farmer relationship among communities from different provinces of Cuba, promoting agroecological management practices and agrobiodiversity conservation in PAs and the growing sector of small farms and family allotments. This project revealed a lack of coordination between the various Cuban agencies in terms of coming up with holistic views that facilitate real care for agrobiodiversity with the application of a form of farming designed to protect natural resources.

Supporting Implementation of the Cuban National Programme to Combat Desertification & Drought (NPCDD) GEF Project This capacity-building project involved the MINAG, Soil Institute (IS) and the ANAP. It was designed to promote practices favoring agrobiodiversity and those able to help stop land degradation and rehabilitation by the selection and use of indigenous trees, traditional varieties and so on.

Agrobiodiversity Conservation and Man and the Biosphere Reserves in Cuba: Bridging Managed and Natural Landscapes (Proyecto COBARB) (UNEP/GEF) It aim is to conserve agrobiodiversity within PAs and in areas of influence by establishing bridges with conservation actions of landscapes associated with these areas. This project will be implemented from 2013 up to 2017-2018.

A landscape approach to the conservation of threatened mountain ecosystems. (UNDP/GEF).  It is a project focused on threatened mountain ecosystems located in the principal mountain ranges of the country, which are legally considered as Special Sustainable Development Regions (REDS) and managed by Mountain Organisms. It will work across altitudinal gradients reaching from mountain ridges to foothills in order to maintain functional connectivity. The project will take a combined BD SO 1 and SO 2 approach, to strengthen the management of PAs, expand PA coverage and ensure the compatibility of PA management with the conservation of BD in production sectors and landscapes.

Incorporating multiple environmental considerations and their economic implications into the management of landscapes, forests and production sectors in Cuba (GEF/UNDP).

The objective of the project will be to promote the generation of multiple environmental benefits based on the integrated economic valuation of ecosystem goods and services, as a tool for decision-making at different levels. (2016-2022)

In addition, FAO will facilitate collaboration, exchange of information, experiences and lessons learned with other initiatives related with the conservation and sustainable use of agrobiodiversity, namely: i) FAO/GEF Project 9068 on Establish a Network of National Important Agricultural Heritage Sites in Chile; ii) FAO/GEF Project 9380 on Securing the Future of Global Agriculture in the Face of Climate Change by Conserving the Genetic Diversity of the Traditional Agro-ecosystems of Mexico; iii) FAO/GEF Project 9092 on Sustainable management of agro-biodiversity and vulnerable ecosystem recuperation in Peruvian Andean regions through Globally Important Agricultural Heritage Systems (GIAHS) approach of Peru.

A.7 Benefits. Describe the socioeconomic benefits to be delivered by the project at the national and local levels. How do these benefits translate in supporting the achievement of global environment benefits.

It is expected that almost 800 farmers (20 % women)  and its families, will increase it total incomes through the implementation of “Save and Grow” approach and because of including access to new markets, development of production chains, sustainable production and 4new mini-industries.

A.8 Knowledge Management. Elaborate on the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives (e.g. participate in trainings, conferences, stakeholder exchanges, virtual networks, project twinning) and plans for the project to assess and document in a user-friendly form (e.g. lessons learned briefs, engaging websites, guidebooks based on experience) and s hare these experiences and expertise (e.g. participate in community of practices, organize seminars, trainings and conferences) with relevant stakeholders.

Four outcome and seven of the project outputs specifically address the issue of knowledge management

Output 1.1.5: A knowledge management platform designed for monitoring and analyzing factors of agro-biodiversity conservation and use, and alerts for major threats

The project will develop management programs of agro-biodiversity as part of the management plans of each AP including buffer zones and connectivity elements - with updated information on identification, management and mapping of species of interest information and other actions strengthen the protection of the PA's phyto and zoogenetic resources.

The project will support the creation of a national network of sponsors that will connect different key stakeholders and will provide and access information, experiences, knowledge and promote actions based on the sustainable management of phyto and animal genetic resources.

The set-up of knowledge management centers or national observatory of phyto and animal genetic resources in the country will allow a better monitoring of threats, analysis, use and conservation of agrobiodiversity.

Output 2.1.2: Sustainable agricultural intensification practices along the lines of the Save and Grow principles and practices piloted, tested, adapted to the context, and scaled-up including conservation corridors and ecosystem connectivity.

The output foresees to extend the preliminary results of the introduction of the SCPI, towards other similar areas, contributing to the improvement of the associated ecosystems and better conservation of related ABD.

It is planned to implement a group of different management practices in relation to those traditionally used in the intervention sites, as well as to encourage spaces for sharing the lessons learned among producers and producers/specialists, in order to achieve an adequate dissemination of the experiences that facilitate the Escalated to other areas. These spaces can be fairs, workshops, meetings with local authorities, etc.

Output 2.1.4: Capacity development program for  rural communities, cooperatives and protected areas managers on management, incentives and best practices/technologies, with a gender focus.

For this output, activities will include the elaboration of a base document on the training needs (of men and women) of all the stakeholders involved in the intervention zones. This program will contemplate the objectives to be achieved, thematic modules, modalities (formal and informal), activities and forms of evaluation. It is important to maintain the link between theory and practice and exchange trips for comparative analysis. Three (3) training workshops will be organized to disseminate and promote the basic principles of Sustainable Crop Production Intensification with emphasis on the main advantages and challenges for soil recovery and conservation.

A report will be prepared on the impact of training of farmers and extension workers on the issue of SCPI for the implementation of new management practices, incorporating experiences of women, and will be valued with all actors, especially producers. Relevant amendments to curricular training plans included in PA management plans will be evaluated with all stakeholders, particularly producers.

Output 4.1.1: The Project Management, Monitoring and Evaluation System in place and providing systematic information on the progress made to achieve the expected results and objectives.

From PY1 until the end of the project, the project coordinator will prepare semiannual progress reports Project (PPR). PRPs will include the project's results framework with the relevant results and performance indicators, the baseline and objectives, the risk matrix, the monitoring of new potential risks and the mitigation measures to reduce unforeseen risks. Regularly, the project coordinator will provide information to the Lead Technical Officer (LTO) and with this, the LTO-FAO will prepare the Annual Project Implementation Review (PIR). The PIR includes the project results framework with relevant results and results indicators, the baseline and objectives, the risk matrix and will determine the potential risks and mitigation measures to reduce unforeseen risks.

Output 4.1.2: Midterm review and final evaluation carried out, finalized implementation and sustainability strategies adjusted to the recommendations.

After 31 months of project execution, a Mid-Term Review will be carried out by independent consultants (national and international) under the supervision of the FAO Representative in Cuba and the LTO, in consultation with the project team. including the FAO-GEF Coordination Unit, the Technical Officer (HQ Technical Officer) and other partners.

Six months before the end of project execution (month 54), a final independent evaluation will be carried out by independent consultants (national and international) under the supervision of the Independent Evaluation Office (OED) of  FAO, in consultation with the team of the project, including the FAO-GEF Coordination Unit, the LTO and other partners.

Output 4.1.3: Communication strategy and visibility of project actions.

The communication strategy, the project logo, bulletins and publications related to the project will be designed. Likewise, project results will be presented and shared on an updated web page designed to promote the implementation of SCPI practices and the conservation of genetic resources.

Output 4.1.4: Publication of best practices and lessons learned.

Bulletins will be prepared and disseminated periodically to report on the progress, results and achievements of the project that will be socialized with institutional and community stakeholders (including decision makers).

Starting with PY2, annual best-practice workshops will be held in each area of intervention with the participation of representatives of the areas, the scientific and academic world and public services, FAO and other relevant stakeholders to analyze the lessons learned. .

In addition, technical reports containing best practices and lessons learned will be published annually (5 in total), including successful cases and failures. The specific topics to be dealt with in these publications will be defined during the implementation of the project. All publications will be uploaded to the project website and to other institutions that run them, and printed copies (in a limited number) will be distributed to government representatives and local partners.

B. DESCRIPTION OF THE CONSISTENCY OF THE PROJECT WITH:

B.1 Consistency with National Priorities. Describe the consistency of the project with national strategies and plans or reports and assessments under relevant conventions such as NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, INDCs, etc.:

No changes from that proposed in the PIF.

Project consistency with national priorities

| Alignment with national priorities | General Strategic Goals – National Environmental Strategy: - Establish priorities and lines of action to achieve higher levels in the protection and rational use of natural resources, public environmental awareness and quality of life of the population. - Contribute to the pursuit of food security by promoting the rational use of soil, water, biodiversity and other natural resources. - Achieve a significant impact on the protection and rehabilitation of the environment in Cuba through prevention, minimization and systematic solution of the major environmental problems in the country. - Improve the implementation of policy instruments and environmental management. - Promote the implementation of instruments and mechanisms of a financial nature to evaluate and manage environmental elements related to economic and social activities. Specific Goals – National Environmental Strategy: - Develop sustainable agriculture in harmony with the environment, that is conducive to the efficient use of plant and animal genetic resources, including seeds, varieties, technological discipline, and plant protection. - Maintain, restore and rehabilitate ecosystems in order to increase their level of resilience, enhance the provision of goods and services and their role in the adaptation and mitigation of climate change. - Promote the conservation of ecosystems, habitats, species and genes, focusing on areas with significant biodiversity losses, controlling the main threats. - Harmonize and integrate the objectives of conservation and sustainable use of biodiversity in the country’s policies and development strategies and in decision-making processes at all levels Fifth national report to the Convention on Biological Diversity: - Prioritize living and preserved biological collections as a way of “ex situ conservation” and concerning intangible heritage. - Devote greater efforts to the evaluation and protection of traditional knowledge and the gender component, taking into account the current undervaluation and limited dissemination of goods and services provided by biodiversity, including those that can be valued economically. - Diversification of agricultural production based on the recognition of indigenous species and traditional knowledge and practices and the need for conservation of phyto and animal genetic resources National Biodiversity Plan: - 1. Biodiversity conservation - 1.1 Generate new knowledge of the components of biological diversity, to ensure their conservation. - 1.2 Address the underlying causes of fragmentation to achieve ecosystem connectivity. - 1.3 Identify environmental indicators that affect biodiversity and develop methodologies to evaluate the services of mountain, coastal marine and agricultural ecosystems. - 2. Use and management of biodiversity - 2.1. Develop proposed plans of restoration and/or rehabilitation of prioritized ecosystems. - 2.2. Implement the use of biomarkers and environmental technologies aimed at the application of bioremediation and treatment of major pollutants. - 2. 3. Develop the planning of biodiversity. - 2.4. Differentiate the formulation of adaptation and mitigation measures to avoid the loss of biodiversity. |
| --- | --- |

C.  DESCRIBE THE BUDGETED M &E PLAN:

The project’s M&E plan is detailed in Section 3.5.4 of the FAO GEF Project Document. The monitoring and evaluation roles and responsibilities are summarized in the table below. M&E activities will be undertaken through: (i) day-to-day monitoring and project progress supervision missions; (ii) technical monitoring of indicators; (iii) mid-term review and final evaluation (independent consultants and FAO Evaluation Office); and (v) monitoring and supervision missions (FAO). Project M&E activities are estimated at USD 106,000 USD.

Summary of main monitoring and evaluation activities

| M&E activity | People in charge | Timeframe/periodicity | Budgeted costs |
| --- | --- | --- | --- |
| Launch workshop | Project team; FAO Cuba (with the support of the LTO and the FAO-GEF Coordination Unit) | Two months after starting the project | 5,450 USD |
| Project start-up report | Project team, M&E Specialist and FAO Cuba (to be approved by the LTO) | Immediately after the launch workshop | _ |
| Monitoring impact on the ground | Project team; project partners, local organizations | Ongoing | 10,000 USD (9 per cent of project coordination time, technical workshops for identifying indicators, monitoring and follow-up workshops) |
| Supervision visits and evaluation of progress in PPR and APRR | Project team; FAO (FAO Cuba, LTO), FAO-GEF Coordination Unit can participate in visits if necessary. | Annual, or as required | FAO visits costs will be borne by GEF agency fees. Project coordination visit costs will be borne by the project travel budget. |
| Project Progress Reports (PPRs) | Project team, with contributions from project partners and other institutions participating in execution. | Half-yearly | 3,000 USD (3.5 per cent of project coordination time) |
| Annual project review reports (APRR) | Drawn up by the Project team with the supervision of the LTO and BH. Approval and submission to GEF by the FAO-GEF Coordination Unit | Annual | FAO staff time costs will be borne by GEF agency fees. PNC time covered by project budget. |
| Co-financing reports | Project team with input from other co-financiers | Annual | 1,000 USD (1 per cent of coordinator’s time) |
| Technical reports | Project team and FAO (LTO, FAO Cuba) | As required |  |
| Mid-term review | FAO Cuba, External consultant. Supervision by LTO and FAO-GEF Coordination Unit | Halfway through project implementation | 30,000 USD for external consultancy |
| Independent final evaluation (IFE) | External consultant, FAO independent evaluation unit in consultation with the project team, including the FAO-GEF Coordination Unit and other stakeholders. | At the end of project implementation | 50,000 USD for external consultancy. Costs for FAO staff travel expenses and time will covered by GEF agency fees |
| Final Report | Project team; FAO (FAO Cuba, LTO, FAO-GEF Coordination Unit, TCS Reporting Unit) | Two months prior to the project end date | 6,550 USD |
| Total budget |  |  | 106,000 USD |

PART III:	Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | signature | Date(MM/dd/yyyy) |
| --- | --- | --- | --- |
| Enrique Moret Hernández | GEF Operational Focal Point, Cuba, Ministry of Sciences, Technology and Environment |  | February , 2018 |

- GEF agency(ies) certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| Alexander Jones Director, Climate and Environment Division FAO Rome |  | 31 May 2018 |  |  |  |
| Jeffrey Griffin Senior Coordinator GEF Unit Investment Center |  |  |  |  |  |

### ANNEX A:	PROJECT RESULTS FRAMEWORK `

| Chain of results | Indicators | Baseline | Mid-term target | Final target | Means of verification | Recruitments |  | People in charge |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project objective: To promote the conservation and sustainable use of agrobiodiversity in selected areas of Cuba, through the introduction of sustainable agricultural production intensification and the conservation, adaptation and rescue of globally important plant and animal genetic resources. |  |  |  |  |  |  |  |  |
| Component 1: Knowledge, mapping and planning of plant and animal genetic resources that are important for the future of agriculture. |  |  |  |  |  |  |  |  |
| Outcome 1.1. Plant and animal genetic resources for food and agriculture are better known in Cuba. | Indicator 1: Strengthened capacities of research institutes (through hands-on experience) Indicator 2: Conservation and diversity status of target species. | 0* 0 | Diagnosis and training carried out for management and conservation of species of interest (Initial conditions created for GR conservation) | -Nineteen (19) national relevant researches institutions enhance its organizational capacities and its technicians and researchers around 1500 will receive special training to held the implementation, systematization and diffusionof experiences, addressed toadopt conservation practices of the GRFA and the SCPI(Sustainable Crop Production Intensification). 7 PGR managed and conserved 5 AGR managed and conserved move to a lower threat status -12 Standard Operating Procedures (for each of the genetic resources to be worked with) and evaluation scales. | Workshop completion report, infographics, annual, mid-term and final reviews. Curriculum of each course/ workshop and corresponding participation certificates Visits to intervention areas. Meeting reports and reporting to decision-makers Validation report and / or minutes. Specimen documents |  | INIFAT and CIMAGT will focus their conservation actions at national level. Management plans for the various PAs will include the agrobiodiversity management programme. |  |
| Output 1.1.1. Analysis of globally-important plant and animal species*** living in Cuba, their valuation and ways and means for conservation | Number of researchers and technicians trained in the practice of evaluating ABD and facilitating its conservation as well as implementing SCPI. Number of research institutions strengthening their organizational capacities. Number of expeditions, collections, samples and field evaluations in intervention areas. Number of population and ecosystem inventories and characterizations. | 0 0 0 0 | 800 2 Institutions 7 (3) One for each area of intervention (partial version). | 1500 2 Institutions 11 (3) One for each area of intervention. | Evaluation reports Reports on workshops/ courses delivered and participation certificates Infographs Documents and reports |  |  | INIFAT, CIMAGT, IIG, INIVIT, IILD, IIFT Flora y Fauna and MINAG regional coordinators |
| Output 1.1.2. A catalogue of globally important plant and animal diversity (focused on wild species). | Number of catalogues produced | 0 | -- | (3) Three (one for each area of intervention). | Documents |  |  | INIFAT AND CIMAGT |
| Output 1.1.3. Maps and databases updated through geographical information systems (GIS) considering production potential, fragility and importance of targeted ABD species. | Number of maps containing spatial information on species | 0 |  | (3) three (one for each area of intervention). | Updated maps and databases |  |  | INIFAT, Flora y Fauna |
| Output 1.1.4. Existing plant and animal breeding programs supported for the adaptive trials of advanced lines and production of early generation seeds. | Number of improvement programmes linked to varieties and/or breeds identified as bearers of genes potentially tolerant to abiotic stress conditions. | 0 |  | (4) programmes 3 associated with plant species and 1 animal. | Documents and reports. Invoices for equipment procured |  |  | INIFAT, CIMAGT and Flora y Fauna |
| Output 1.1.5. A knowledge management platform designed for monitoring and analysing factors of agro-biodiversity conservation and use, and alerts for major threats. | Number of PA agrobiodiversity management programmes, including buffer zones and bridging elements. Number of national knowledge management centres and monitoring centres National network of agrobiodiversity sponsors | 0 0 0 |  | (4) One for each PA Enablement and equipping of 1 national centre and 3 local centres for knowledge management One operating network | Programme documents and amended management plan for each PA Operational platform with updated information |  |  | MINAG, IES, CNAP and Flora y Fauna |
| Component 2: Implementing the Save and Grow approach in productive landscapes |  |  |  |  |  |  |  |  |
| Outcome 2.1 Increased adoption of production systems that integrate biodiversity conservation through the creation of connectivity corridors, bringing together agricultural and natural ecosystems. | Number of hectares of production landscapes that integrate biodiversity (including ABD and CWR) conservation and sustainable use into their management with certification % of farmers with increased confidence in innovative sustainable practices (higher productivity and sustainable natural resources management are possible). Number of producers who increase their income through a implementation of “Save and Grow” approach (including access to new markets) | 0 0 0 | 15,000 hectares (10% managed by women) with SCPI at the initial stage 50 % of producers, (of which 20% women) committed to the application of SCPI practices. Conditions created in production systems for implementation of SCPI | 30,000 hectares (20% managed by women) with SCPI approach and certified through PGS. 50% of producers from selected cooperatives (20% of whom are women) with increased confidence in SCPI practices (2715 producers in all). 800 producers (of whom 20% women) improve their incomes by 30%.****. |  | National and local authorities are interested in implementing sustainable agrobiodiversity management and the “Save and Grow” method. Conditions created for implementing the "Save and Grow" approach in project intervention areas and support obtained from government and community bodies at local and national level |  |  |
| Output 2.1.1. A landscape production strategy agreed by stakeholders, with particular attention to gender and youth, applying the Save and Grow approach. | Diagnosis and strategy of productive systems in intervention sites | 0 | Tools drawn up and diagnoses completed | One (1) strategy drawn up for each intervention area | Diagnostic documents and strategies. Meeting and workshop reports |  |  | INIFAT, CIMAGT FMC, ACTAF, ACPA, ANAP, MINAG and Flora y Fauna |
| Output 2.1.2. Sustainable agricultural intensification practices along the lines of the Save and Grow principles and practices piloted, tested, adapted to the context, and scaled-up including conservation corridors and ecosystem connectivity. | Number of practices proven and implemented in intervention areas. Number of conservation corridors and ecosystem bridges established | 0 0 | 3 0 | 6 2 | Reports Visits to intervention areas. Infographics Workshop report Project Progress Report |  |  | INIFAT, CIMAGT, ACTAF, ACPA, ANAP, MINAG and Flora y Fauna |
| Output 2.1.3. In situ and ex situ conservation actions, in place, including young and women participation. | Number of community seed banks Number of gene pools on farms. Number of agrobiodiversity and innovation fairs with participation by women (30%) Number of productive units dedicated to the in situ conservation of plant and animal genetic resources Number of Crop Wild Relatives Reserves devoted to in situ conservation in PAs (wild relatives) | 0 0 0 0 0 | 0 0 3 18 0 | 3 (one in each intervention area) 3 (one in each intervention area) 6 (two in each intervention area) 18 3 | Project Progress Report Reports, visits to areas, infographics Signed minutes containing the commitment of all those involved Workshop report Documents recording dates, varieties/breeds and staff/entities involved |  |  | INIFAT, MINAG, CIMAGT and Flora y Fauna |
| Output 2.1.4. Capacity development programme for rural communities, cooperatives and protected areas managers on management, incentives and best practices/technologies, with a gender focus. | Number of farmers and extension workers trained in SCPI and ABD conservation. Percentage of producers including new management practices and conservation technologies based on training received. | 0 0 % | 1000 30 % | 2000 (600 of them are women) 70% (out of 2320 producers) | Workshop participation reports Reports on visits to production centres by the local MINAG office |  |  | INIFAT, ACTAF, ACPA, ANAP, FMC, MINAG and Flora y Fauna |
| Output 2.1.5. Value chains for new products related to agrobiodiversity developed to promote the conservation of agroecosystem in rural production. | Number of production and marketing chains set up. Number of people in selected production and marketing chains (excluding agricultural producers) who received economic benefits based on their implementation with an equity focus | 0 0 | Advance studies carried out for implementation of mini-industries, new products and marketing outlets. Training carried out for staff involved in chains identified | 4 (four) mini industries: 1 for Annonaceae pulp 2 for native goat cheese production 1 for ham production. 4 new products. 4 marketing outlets. 70 people benefited by chain implementation, 30 of them are women. | Mini industries and products marketed |  |  | INIFAT, ANAP, FMC, MINAG, Flora y Fauna, MINCIN, MINTUR, CIMAGT |
| Component 3.1: Strengthening the enabling environment for sustainable agriculture and conservation of GRFA in Cuba |  |  |  |  |  |  |  |  |
| Outcome 3.1. Enhanced inter-institutional coordination, closer technical cooperation and regulatory coherence have supported the mainstreaming of agro-biodiversity conservation and use in public policies. | Indicator BD4.9. The degree to which sector policies and regulatory frameworks incorporate biodiversity considerations. | Despite the existence of laws on plant and animal genetic resources, their implementation is poor, inter-ministerial institutional frameworks do not secure implementation processes at national and local level and there are no laws on agrobiodiversity. | PGR and AGR regulatory framework survey and study | Decision-making bodies have analytical documents that serve as input to ensure that new plant and animal genetic resource bills incorporate agrobiodiversity conservation principles. At least two decree laws on the use and conservation of PGRs and AGRs | Official Gazette and national and local regulatory documents | The current regulatory and legal framework covers the main aspects to be taken into account in genetic resource management and agrobiodiversity conservation. |  |  |
| Output 3.1.1. A detailed review of the current legal and regulatory frameworks on agrobiodiversity conservation and sustainable agriculture. | Number of local workshops for coordination with local stakeholders and beneficiaries over the current status of the legal and regulatory framework associated with agrobiodiversity conservation. Number of documents on the BD regulatory framework in Cuba reviewed. | 0 0 | 3 50% of documents reviewed | 5 74 | Meeting and workshop reports Meeting and workshop reports |  |  | - Local government - Local MINAG Department - PA Directors - Legal status of each territory |
| Output 3.1.2. A road-map for legal and regulatory coherence within the country (on agrobiodiversity conservation and sustainable agriculture). | Current regulatory framework diagnosis and evaluation document. Workshops to validate the proposed road map with local stakeholders and beneficiaries. | 0 0 | Documents associated with ABD and sustainable agriculture regulatory frameworks identified at basic level. Analysis plan established | 1 Three (3) local and one (1) national | Workshop meeting reports and road map document |  |  | - Local government - Local MINAG Department - PA Directors |
| Output 3.1.3. A manual that illustrates the process of sustainable management of production landscapes to facilitate the scale-up at national level. | Technical Manual | 0 | Proposed manual design | 1 manual | Manual |  |  | INIFAT, CIMAGT, IES, Flora y Fauna regional coordinators |
| Component 4: Project management, monitoring and evaluation (M&E) |  |  |  |  |  |  |  |  |
| Outcome 4.1. Project implemented, lessons learned and good practices documented and disseminated. | Project results show sustainability |  | 40% of project results achieved | 100 % of project results achieved | PRP PIR Mid-term evaluations and final evaluation | The Project monitoring and evaluation system supervises activities and checks results against established indicators |  |  |
| Output 4.1.1: The project management, monitoring and evaluation system works to provide systematic information on progress made to achieve planned results and objectives | Project launch workshop Half-yearly progress reports Steering Committee meetings | 0 0 0 | 4 progress reports (2 PPR and 2 PIR) | 1 (first year) 8 progress reports (4 PPR and 4 PIR) 3 (one for each of years 2, 3 and 4) |  |  |  | MINAG, MINCEX, CITMA, INIFAT, FAO, CIMAGT and Flora y Fauna |
| Output 4.1.2: Mid-term review and final evaluations carried out, finalized implementation and sustainability strategies tailored to recommendations. | Mid-term review Final evaluation | 0 0 | 1 | 1 1 | MT evaluation report Final evaluation report |  |  | FAO, GEF, External consultants |
| Output 4.1.3: Communication strategy and dissemination of project actions | Project logo Project newsletters Website | 0 0 0 | 1 4 (half-yearly frequency) 1 | 1 8 (half-yearly frequency) 1 | Registration certificate Printed specimens International visibility | Decision-makers are involved on a greater scale in SCPI practices |  | INIFAT, CIMAGT, Flora y Fauna and MIANG |
| Output 4.1.4: Publication of best practice and lessons learned | Number of annual publications on best practices and lessons learned and other technical publications with gender and intercultural approach. | 0 | 2 technical documents | 4 technical documents | Publications PPR / PIR |  |  | INIFAT, CIMAGT, Flora y Fauna and MIANG |

*Capacity building will be measured by means of FAO methodology regarding organizational capacity development.www.fao.org/capacity/development/resources/fao-learning-material/learning-modules/es/

**The scale is designed on the basis of the following aspects: agricultural holding systems that offer a variety of socioeconomic and environmental benefits and are related to productivity, soil health, crops and varieties, water management, plant health protection, policies and institutions.http://www.fao.org/agriculture/crops/thematic-sitemap/theme/spi/scpi-home/framework/en/

***Oryza spp. (rice); Ipomoea spp. (Sweet potato); Zea mays (maize); Manihot esculenta (cassava); Capsicum spp. (chilli pepper); Annona spp. (sugar apple and soursop); Citrullus lanatus (melon); Creole Goat; Cubalaya Chicken, Creole Pig; Cuban Brown Rabbit and Melipona bee.

**** According to annual incomes of Cubans farmers, ONEI, 2015.

ANNEX B: RESPONSES TO PROJECT REVIEWS

| Nº | STAP review comments | Responses |
| --- | --- | --- |
| 1 | Overall, STAP feels that this PIF does not adequately lay out the global environmental benefits (GEBs) it is targeting except in the most general terms. It is difficult to know if it targets agro-biodiversity, natural biodiversity, which species, and why these species are important. | The project targets agrobiodiversity. A detailed analysis of expected GEBs to be achieved through project implementation is included in the FAO GEF project document in section 1.3.4, including the indicators referenced in the tracking tools. Tables 8 and 9 in section 1.1.2 provide detailed description of targeted species, their global environmental importance and data on the baseline and conservation status. |
| 2 | In addition, the project objective is unclear. What type of biodiversity is the project aiming to conserve the agro-biodiversity? What is "sustainable agricultural production intensification"!? What is "conservation, adaption and rescue of globally-important plant genetic resources"? The vague, all-meaning objective reflects the relatively vague description of the problem in the PIF. The justification for which species and varieties are to be conserved, and why also remains generic and theoretical, rather than specific and operational. The PIF never defines what it means by "genetic diversity" and "target species". | The project objective was slightly rephrased for better clarity, kindly refer to the Resuts Framework in Appendix 1 of the FAO GEF project Document. A more detailed description of the problem the project aims to address is included in section 1.2.1, while the justification for the selected species is detailed extensively in section 1.2.2 (table 9). The ProDoc also includes a much more detailed description of the Sustainable Crop Production Intensification (SCPI) concept in section 1.3.1. |
| 3 | The proposed scale of impact (400,000 hectares) seems to be highly over-optimistic given the uncertainties in the project and the weak baseline. | Project targets have been revised based on feasibility studies carried out during project preparation: the project will directly impact 30,000 hectares through the implementation of the "Save to grow" approach and the conservation of the species identified in the project. In addition, 585,000 ha will be indirectly benefited. |
| 4 | The section root causes and barriers is weak. The trade of between more diverse but lower productivity "traditional agriculture" and its high demand for land, and modern high-input agriculture (with a lower demand for land?) needs to be carefully considered. | The section on barriers was reorganized and strengthened, see section 1.2.3. For the purposes of the project, a comparison between traditional and high-input agriculture is not relevant, since this project proposes a third alternative route, Sustainable Crop Production Intensification (SCPI), with the objective of increasing production in the same areas but without degrading natural resources and promoting agrobiodiversity. |
| 5 | The root causes for why agriculture is disjointed from natural resource protection need to be carefully analyzed, because without this understanding, the project lacks a clear theory of change. | In section 1.2.1 direct reference is made to the impacts of agriculture on biodiversity in Cuba, as well as in section 1.2.3 barriers analysis. |
| 6 | The discussion on protected area buffer zones and corridors lacks specificity. | The relationship between buffer zones of PAs and biological corridors and the effects of agriculture's impact on biodiversity in the four PAs of the project is described in section 1.3.1, section 1.1.2, and annexed maps 7.1 - 7.4. Barrier 2 section 1.2.3. |
| 7 | These issues need to be outlined in detail with respect to the three areas where interventions are planned. | A detailed analysis of these issues is included in the ProDoc, section 1.1.2 on Project implementation areas. |
| 8 | The section describing the project baseline is general, with no dollar figures. It appears that not much is happening except for one FAO project and some civic activities in the agroecological movement in Cuba. | Section 1.2.2. Baseline initiatives describe in detail project baseline initiatives, including information on financing. |
| 9 | The biodiversity baseline provides a generic listing of species in a useful table. However, the connection between these species /varieties, outcomes/outputs, why these constitute GEBs, and the geographic scope of the project is not clear. It is hard to see how this project can be designed without this specificity unless it is reframed and Component 1 maps biodiversity, while Component 2 experiments with landscape approaches in three sites (see below). | The importance for the global environment of the chosen species and its description is detailed in section 1.2.2 and table 9. In addition, components 1 and 2 have been reshaped taking into consideration the suggestion below, kindly refer to the Results Framework in Appendix 1. |
| 10 | In terms of project design, the methods of achieving the stated objectives are not yet convincing, or clear. | Section 1.3 includes a detailed description of the project strategy to achieve the stated objectives. |
| 11 | Generically, a combination of knowledge (1.1.4), maps and databases (1.1.3) and a catalogue (1.1.1) plus in situ and ex-situ conservation may increase plant genetic diversity (outcome 1.1). However, the specifics on exactly how 100,000 hectares and x seed banks are going to be implemented remains vague in the document. This needs to be clarified before Project approval. | Based on this recommendation, the results framework was reformulated. Kindly refer to Appendix 1 of the ProDoc and to Section A1 of the CEO Endorsement Request for more details on these changes. |
| 12 | Outcome 2.1 anticipated an increase of 300,000 hectares of productive landscapes that integrate biodiversity through sustainable use, certification, corridors and labelling. The feasibility of this in not addressed adequately and before approval the ProDoc needs to be much more specific about what landscape management practice will be adopted, how, where and why (2.1.2), and what capacities (2.1.3) and incentives (2.1.5) are feasible. | Project targets in terms of hectares have been revised based on feasibility studies conducted during project preparation, in addition the timeframe has been extended to allow sufficient time to strengthen stakeholders’ capacities in the application of new practices. A detailed description of management practices to be adopted is included in Section 1.3 describing the GEF alternative. |
| 13 | There seems to be some confusion in the program framework with output 2.1.4 (analysis of species and values) seeming to belong more with component 1, and output 1.1.2 (conservation actions) belonging more with component 2. | Based on this recommendation, the results framework was reformulated. Kindly refer to Appendix 1 of the ProDoc and to Section A1 of the CEO Endorsement Request for more details on these changes. |
| 14 | In the ProDoc, the sequencing of how to achieve Component 3 needs to be carefully assessed. As it stands, this looks more like a top-down office exercise. Serious consideration should be given to utilizing the process of field implementation to build a community of practice and test and develop regulatory frameworks (3.1.1, 3.1.2) and manuals (3.1.3). Please refer to the GEF/UNDP South African grasslands project for an excellent example of adaptive, bottom-up, multi-stakeholder platforms for developing policy and legal frameworks. | Based on this recommendation, the results framework was reformulated. Kindly refer to Appendix 1 of the ProDoc and to Section A1 of the CEO Endorsement Request for more details on these changes. |
| 15 | The match between component descriptions and outcomes/outputs is also confusing. It is suggested that Component 1 is renamed to include the knowledge, mapping and planning elements and Component 2 to include field action elements. | Based on this recommendation, the results framework was reformulated. Kindly refer to Appendix 1 of the ProDoc and to Section A1 of the CEO Endorsement Request for more details on these changes. |
| 16 | Stakeholders are identified and roles specified in a very general way. Roles and responsibilities will needs to be clarified considerably in PPG stage. | The roles and responsibilities of the stakeholders involved are detailed in section 1.3.3 of the ProDoc and in table 13. |
| 17 | In terms of risks, there are clearly considerable risks that the methods selected (which are not specified) will not work in the time frame of the project. These risks can and should be averted by adding considerable clarity in the PPG stage about what methods of conservation will be tried in which specific area, the costs and benefits of these approaches, and mechanisms to encourage uptake by communities. | Taking into account this observation, the extension of the project from 4 to 5 years has been foreseen. The rest of the suggestions were addressed in the logical framework, the results matrix appendix 1, section 1.3.1. Project strategy and appendix 4 risk matrix. |
| 18 | Regarding socio-economics, no data is given about the number of people affected, direction/magnitude of impact, etc. | Data is provided in table 6 of section 1.1.2. Areas of implementation, section 4.1 and appendix 4 risk matrix. |
| 19 | Finally, there is no indication of learning from other projects or the literature. This needs to be seriously rectified at PPG stage with clear citations of where proposed methods have been tested before, and how well they worked (or didn't). | To address this suggestion, details on lessons learned from other projects have been included in section 1.4 of the Prodoc. |

| Nº | USA comments | Responses |
| --- | --- | --- |
| 1 | - The overarching objective and organization of the proposal should be refined moving forward. The proposal seems to focus on boosting agricultural production in Cuba, rather than preserving biodiversity. While the project may reduce the need to convert more protected lands into agricultural production and there is a clear benefit to preserving and enhancing the genetic diversity of agriculture in Cuba, the global environmental benefits should be made more explicit. In addition, the project would be improved if FAO could demonstrate how Component 1, which includes the catalogue of plant genetic diversity, relates to or supports the other components of the project. The catalogue will focus on species listed in annex III, but will these species also come into play in the interventions at three project sites under Component 2? The proposal would be more compelling if it included references to the contribution of plant genetic diversity and biodiversity/ecosystems to food security. In addition, the context description, specifically the threat of agricultural systems to biodiversity, should be made clearer. Additional documentation (i.e. references) to support the activities planned in many of the sections of the proposal are needed. The proposal does, however, make clear links to relevant conventions, which the United States supports. | The objective of the Project has been reformulated to clarify that the fundamental purpose is the conservation of agrobiodiversity, with emphasis on races, varieties and threatened species, which contributes to the expected global environmental benefits. The species to be conserved were defined, which are the same ones that will be addressed in the intervention areas. Reference to the contribution of the targeted ABD to food security has been included in the project document. A detailed analysis of threats to biodiversity is included in section 1 of the FAO GEF project document. |
| 2 | - Some parts of the proposal suggest large-scale monoculture operations are decreasing and other parts suggest they are increasing. If they are increasing, then that justifies the proposal, but renders the proposed activities ineffective. If they are decreasing, then that may mean the proposed work is less relevant, but the activities would be appropriate. We hope FAO will clarify this in the project document. | Although in some areas of the country monoculture is maintained, polyculture is favored as a strategy of agricultural development fundamentally associated with small producers. The will of the government is to test options, such as those proposed by the project, as a mean to improve the conservation of genetic resources, while also having a positive impact on preventing agriculture from pressuring biodiversity and protected areas. In this regard, please see context and baseline of the project. In addition, several text descriptions were included in the project document in order to clarify this and other aspects. |
| 3 | - From our view, the statement on page 14 about the Geographical Indication (GI) is not entirely accurate. GI protection is often based on official registration that confers exclusive rights of use to GI producers who conform to the standards associated with the product. The authors seem to imply that once a GI is established that farmers will automatically benefit, but this is not always the case. Marketing and packaging also play an essential role in attracting buyers that are willing to pay for GI products, so this might need some more consideration, especially since it is presented as one of the project outputs. | The project will mainly focus on strengthening the value chains of product related to the targeted ABD to create added value and improve livelihoods of producers. Therefore the project will fist support producers in the development of new products (Annonacea pulp, watermelon juice, Creole pig jam and native goat cheese), adequate postharvest management and transformation in compliance with quality and environmental standards. Quality certification of products, processes and farms will be implemented through Participatory Guarantee System.The project will also support products access to market through capacity development on marketing strategies, knowledge exchange, dissemination of good practices, packaging. A strategy to position ABD products on the market will be developed in a participatory manner during PY 1. This will include proposals for the enhancement of marketing networks and research on different labelling options that are adequate to the selected products. The project will explore GI labelling among other labelling options. The project strategy does not imply that once a GI is established that farmers will automatically benefit. GI and other type of labeling are considered instead as one of the factors of complex strategy aimed to strengthen value chains of ABD products as a mean to improve the sustainability of the conservation of genetic resources in the context of rural areas of Cuba. |
| 4 | - As this proposal is developed, the methodology that will be used to tackle the broad barriers discussed in Component 1 should be further refined. Additional details on the approaches and procedures to be used to address barriers should also be provided for Component 2. For example, the “Save and Grow” approach is mentioned several times throughout the proposal. Save and Grow is indeed an ecosystem approach to agriculture that aims at improving productivity while conserving natural resources. However, this approach draws on decades of research in areas such as minimum tillage, timing and methods of planting, use of biological control agents, crop rotation, mulching, manure, composting, and fertilizing, usually for implementation by smallscale farmers. It is not clear from this proposal if “Save and Grow” approaches are already available for the wide range of crops, forest species, and animals mentioned in the proposal. Plant breeding programs to develop high yielding and adapted varieties, germplasm collections from where genes will be obtained for breeding programs, and extension work for technology transfer are absent from this proposal but are essential components of “Save and Grow” programs. We hope such activities will be considered as this project is developed. Co-financing of other projects mentioned in this proposal for this Component does not warrant implementation of “Save and Grow” approaches, much less on a short term basis. | The FAO Save and Grow approach works for a wide range of crops and breeds and specifically those selected by the project. The technology transfer and extension that support breeding programs have been included among the purposes and activities (kindly refer to output 1.1.4). Project financing plus co-financing, such as the National Soil Conservation and Improvement Program, guarantees the implementation of the "Save and Grow" approach. |
| 5 | - In Component 3, the FAO should continue to address how the associated laws will be created and enforced, as well as how they will overcome the barriers outlined on Page 9 of the proposal. | Description of component 3 has been expanded. It includes the elaboration of two Decree-laws on the conservation and use of plant and animal genetic resources respectively (see barrier analysis and results matrix).The component was designed to address revised barriers identified during preparation phase. |
| 6 | - We are pleased at how the proposal outlines the collaborations and stakeholder engagement envisioned. However, additional consideration should be given to the following: the project should further include youth groups as the proposal states that young people are leaving rural areas to cities for a better life. The project may also benefit from increased collaboration with universities and academic/research institutions engaged in this type of research; The proposal notes that women’s groups will be included in the full project preparation process; however, those groups are not identified in the proposal. Finally, this proposal may benefit from coordination and knowledge sharing with a similar project that has been funded in Ecuador (GEF Project #4777). | Women groups and young people mentioned in the PIF stage has been included in the full project phase. Please see gender valuations and local stakeholders. A Platform for Knowledge Management proposed includes universities and the academic and research sector and these sectors have a leading role in guaranteeing key activities. FAO will ensure knowledge sharing between the two projects and that lessons learned from the Ecuador project are fully incorporated in the implementation of this project proposal. During project preparation, consultation were conducted with The Cuban Women Federation (Federación de Mujeres Cubanas) which represents the Cuban women at all levels, especially locally at the places where the project will be implemented. |
| 7 | - With regards to project financing, it is unclear whether GEF funding will be allocated to a specific part of the project or whether it will be spread among the project objectives. Although the project leverages significant matching from partners, we believe the proposal would benefit from additional details on how the project will be sustained beyond its 48-month duration. We believe the FAO should also elaborate on how the project will be assessed upon its completion, as well as how lessons learned will help improve project activities. Furthermore, the project proposal notes that trends in public awareness and attitudes in support of biodiversity will be a measure of success—how will these trends be measured? | GEF funding will be allocated among the project objectives. The co-financing commitments were evaluated in detail to ensure compliance with each component, result and product during the 60 months of the project (see budget). The project will synergize with related projects that are implemented nationally and in the region. The lessons learned from projects already implemented were considered. An M&E component has been added to the design of the project, to allow adaptive management and improvement of project activities. The success trend will be measured through impact evaluation tools of the training and the scope of the replication of the experience. Although the project proposes some actions to create public awareness about biodiversity, it has not been included in the final proposal as an indicator of measurement. |
| 8 | - While climate change is discussed in several places, it would be helpful for the FAO to provide additional details on how climate change will affect the project, as well as how risks might be mitigated. The FAO should also take into account the effects that changes in international trade restrictions might have. | A thorough analysis of potential risks and related mitigation measures has been carried out during project preparation and included in the risk matrix, appendix 4 of the FAO GEF Project Document. |

ANNEX C:  status of implementation of project preparation activities and the use of funds

n/a. NOT yET completed the PPG Activities.

- provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: usd $ |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount Plan Initiation (A) | Amount Spent To date (B) | Amount Committed(C) |
| Salaries Professional | 7,143 | 0 | 7,143 |
| National Consultants | 62,500 | 30,630 | 18,415 |
| International Consultants | 12,500 | 3,156 |  |
| Contracts |  |  |  |
| Locally Contracted Labour |  |  |  |
| Travel | 19,857 | 26,634 | 56.00 |
| Training | 44,000 | 13,894 | 45,445 |
| Non expendable procurement | 4,000 | 4,627 |  |
| TOTAL | 150,000 | 78,941 | 71,059 |

annex D: calendar of expected reflows (if non-grant instrument is used)

NA

The Sustainable Crop Production Intensification (SCPI) is an approach developed by FAO, usually known as “Save and Grow”.

Idem foot note 4

The 5 ZRFA that improve it conservation status going to the minor threat category are: Creole Goats, Cubalaya Chicken, Melipona Bees, Creole Pigs and Cuban Brown Rabbit.

Target globally important genetic resources are: Oryza spp., Ipomoea spp., Zea mays ,Manihot esculenta, Capsicum spp., Annona spp., Citrullus lanatus, Creole Goats,  Cubalaya Chicken, Creole Pigs, Cuban Brown Rabbit, Melipona Bees.

This catalog will be integrated to the national catalog of biodiversity species.

Major threats on ABD in Cuba are related to: land use (including agriculture negative impacts), land cover by type of vegetation, variability and climate change factors (including droughts and fires).

Indirectly benefitted hectares: it include those hectares out of the targeted by the project’s site direct influence. The areas  receive the benefits of changes of polices, promoting learning exchanges and training, results of capacity building strategies addressed to farmers and producers(According  to the BD Tracking Tools)

It refers to the Government staff.

The role of women is central, since in Cuba 37.9% of active labor force is made of women

Reformulated  and  modified by a new one

Modified by a new outcome

Adjusted area and included  in de component 2, outcome 2.1, indicator 3

Moved to the component 2,  outcome 2.1

New indicator

Moved from the  component 2, output 2.1.4

Change to the Output 1.1.2.

Adjusted area and move to the output 2.1.3

A new developed output

Moved from the component 1

Reformulated

Reformulated

Reformulated

Adjusted,  see project description summary, target  outcome 3.1

There´s no indigenous population

Credits and Services Cooperative (Cooperativa de Créditos y Servicios)

Basic Unit Enterprise (Unidad Empresarial de Base)

This is linked to outputs 2.1.1 and 2.1.2. The objective of these capacity development actions is to support the implementation of sustainable productive landscapes, as agreed in output 2.1.2 by the stakeholders.

Government staff

The role of women is central, since in Cuba 37.9% of active labor force is made of women.

National Environmental Strategy 2011-2015 http://www.educambiente.co.cu/index.php?option=com_content&view=article&id=52&Itemid=37.

Ibidem

Fifth National Report to the Convention on Biological Diversity (2014).

Ibidem

Ibidem

Spanish acronyms of the national relevant Research Institution and Universities that will enhance its capacities through the project implementation:IES(biodiversity and wild species), INIVIT(eatable roots), INIFAT(exsitu conservation bank PGRFA,soil and basic agriculture researches), CIMAGT(livestock, ex situ conservation ZGRFA), IIP(pigs), IIA(poultry), IIG(grains), IILD(vegetables), CIAPI(bees), CENSA (National Center for animal health), IIFT (Institute of research in tropical fruit growing), IAGRIC (Agricultural Engineering Institute), INCA(grains), ICA(animal feeding and health), IIPF(animal feeding), EEPF”IndioHatuey” (animal feeding),  Matanzas University, Sancti Spíritus University, and Granma University.

The Sustainable Crop Production Intensification (SCPI) is an approach developed by FAO, usually known as “Save and Grow”.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent funds, Agencies can continue undertake the activities up to one year of project start. No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for activities.