UNDP PROJECT DOCUMENT

Government of the Democratic People’s Republic of Algeria

National executing agency: Ministry of Agriculture and Rural Development

United Nations Development Programme

UNDP Project ID PIMS 5311 / GEF Project ID PMIS 5808

Developing a national strategy and legal and institutional framework on access to genetic resources and related benefit sharing and traditional knowledge in line with the CBD and its Nagoya Protocol in Algeria

Brief Description Algeria’s size and geographical location make it an important country in terms of ecosystem and species diversity. There is a general trend towards biodiversity loss and ecosystem degradation across vulnerable regions in Algeria. This erosion of biological and genetic diversity and of ecosystem services implies fewer livelihood options for local populations and fewer options to confront continued environmental pressures, for both the present and future generations. Algeria has addressed and made good progress on a number of fronts relating to the first and second objectives of the Convention on Biological Diversity (CBD) – the conservation of biodiversity and its sustainable use, respectively – through building and managing a protected areas system, sustainable natural resource management practices and similar activities, but challenges remain. Working towards the third objective of the CBD – the fair and equitable sharing of the benefits derived from accessing and using genetic resources (ABS) – remains a major challenge, although it could offer important avenues to address a range of issues. The long-term solution is the creation, development and implementation of a comprehensive national legal, regulatory and institutional framework for ABS. This will activate the potential that Algeria’s genetic resources and traditional knowledge represent for generating economic benefits to the nation and key stakeholders, including local populations where appropriate, in the form of business, employment, technology transfer and capacity development. The project will achieve the proposed long-term solution through two components: 1) Developing a national policy, legal and institutional framework to enable the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources; and, 2) Building and strengthening the capacity of national research and regulatory institutions to apply ABS rules and principles. Through the implementation of these two components, the project will achieve global environmental benefits through enhanced national contribution towards the achievement of the three objectives of the CBD and of the goals of its Strategic Plan for 2011-2020 by contributing to reduced rates of biodiversity loss in Algeria through the following mechanisms: 1) increasing awareness about existence, use and option values of biological resources among key audiences, and about the existence of markets based on the sustainable use of biodiversity and its components; 2) enabling the government and other stakeholders to derive greater economic benefits from genetic resources and generate incentives which can favour in-situ and ex-situ conservation and ecosystem management; 3) facilitating the generation of monetary and non-monetary benefits from the access to and use of genetic resources, particularly through the interest of industry, commercial firms and academic and research institutions; and, 4) provide local populations that maintain genetic resources in their lands and have developed and accumulated traditional knowledge with new livelihood options resulting in economic benefits that reduce pressures on ecosystems and contribute to the maintenance of regional and global ecosystem services.

SIGNATURE PAGE	Country: ALGERIA

Project title: Developing a national strategy and legal and institutional framework on access to genetic resources and related benefit sharing and traditional knowledge in line with the Convention on Biological Diversity and its Nagoya Protocol in Algeria

Outcome(s) of the Strategic Cooperation Framework (CdCS): Outcome 3: By 2020, the living environment and resilience of citizens are improved thanks to sustainable participatory management of natural and urban ecosystems.

Expected CPAP Output(s): Output 2: The capacity of principal national and local actors are strengthened to operationalize strategies/plans for the sustainable management of natural and urban ecosystems based on the improvement of the resilience and living environment of citizens.

Outcome 1 of the Strategic Plan: Growth is inclusive and sustainable and includes production capacities which create employment and means of subsistence for the poor and the excluded.

Output 1.3 of the Strategic Plan: Solutions have been developed at the national and sub-national level for sustainable management of natural resources, ecosystem services, chemicals and waste

Indicator 1.3.1:  The number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or sub-national level

Sub-indicator 1.3.1.A.1.1:  The number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or sub-national level

Outcome 2 of the Strategic Plan: Countries are equipped with strengthened institutions to assure progressive universal access to basic services

Output 2.5 of the Strategic Plan: Legal and regulatory frameworks, policies and institutions are equipped with the means to assure the conservation, sustainable use and access to benefits from natural resources, biodiversity and ecosystems, as well as sharing in such benefits, in line with international conventions and national legislation

Indicator 2.5.1: Extent to which legal, policy and institutional frameworks are in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems

Sub-indicator 2.5.1.A.1.1: Extent to which legal frameworks are in place for conservation, sustainable use, and/or access and benefit sharing of natural resources, biodiversity and ecosystems

Sub-indicator 2.5.1.C.1.1: Extent to which institutional frameworks are in place for conservation, sustainable use, and/or access and benefit sharing of natural resources, biodiversity and ecosystems

Implementing Agency:		United Nations Development Programme (UNDP)

National executing agency: 	Ministry of Agriculture and Rural Development (MADR)

Responsible Partners/Parties: 	General Forest Authority (DGF)

| Project duration: | 48 months |  | Total Project Resources: | $ 7,224,320 |
| --- | --- | --- | --- | --- |
| Project tentative start: | September 2015 |  | Total resources in TBW: | $ 2,120,000 |
| ATLAS Award ID: | 00093558 |  | GEF | $ 1,940,000 |
| ATLAS Project ID: | 00086265 |  | UNDP (TRAC) | $ 180,000 |
| GEF PMIS #: | 5808 |  |  |  |
| UNDP PIMS #: | 5311 |  | Others: |  |
| Mgt Arrangement: | NIM |  | Government of Algeria (in kind) | $ 3,000,000 |
| PAC Meeting Date: | TBD |  | Government of Algeria (cash) | $ 2,104,320 |

Agreed by the Government of the People's Democratic Republic of Algeria:

Name:

Date:					Signature:

Agreed by the Ministry of Agriculture and Rural Development/General Forest Authority (DGF):

Name:

Date:					Signature:

Agreed by UNDP:

Name:

Date:					Signature:

Table of Contents

Section I: Project Description	7

Part 1: Situation analysis	7

1)	Biodiversity status and threats	7

2)	The environmental legal and institutional framework in Algeria	9

3)	Barriers and long-term solution	11

4)	Baseline Analysis	12

Part 2: Strategy	14

1)	Project Rationale and Policy Conformity	14

2)	Project Description: Objective, Outcomes and Outputs	15

3)	Stakeholder Analysis	18

4)	National and global environmental benefits	20

5)	Incremental cost analysis	20

6)	Socio-economic and development benefits and gender aspects	22

7)	Innovativeness, sustainability and potential for scaling up	23

Part 3: Management Arrangements	23

Part 4: Monitoring and Evaluation Framework	27

1)	Key Monitoring and Evaluation Activities	27

2)	Learning and knowledge sharing	30

3)	Communications and transparency requirements	30

Part 5: Legal Context	31

Section II: Strategic Results Framework	32

Section III: Total Budget and Work Plan	36

1)	Total Budget and GEF Work Plan	36

2)	Budget Notes	37

3)	Overall Project Financing (USD)	38

Section IV: Additional Information	39

Part 1: Other Agreements	39

1)	GEF focal point Endorsement Letter	39

2)	Co-financing letter from the Government of Algeria	40

3)	Letter of Agreement between UNDP and the MADR of Algeria	42

4)	Co-financing letter from UNDP	46

Part 2: Risk Analysis	47

Part 3: Terms of Reference for Project Personnel	50

1)	List of Project Personnel and Consultants	50

2)	Context for the Terms of Reference (standard for all posts)	53

3)	National Project Director (DNP)	54

4)	National Project Coordinator (NPC)	55

5)	Lead Technical Advisor	56

6)	Financial and Administrative Assistant	57

7)	Consultants	59

Part 4: Project Annexes (UNDP / GEF)	81

1)	UNDP Social and Environmental Screening Procedure (SESP)	81

2)	GEF ABS Tracking Tool (Beta Version)	94

3)	National ABS Institutional Capacity Development Scorecard (UNDP)	100

Acronyms and Abbreviations

ABS  	Access and Benefit-Sharing

AEWA	African-Eurasian Waterbird Agreement

ANN	National Nature Conservation Agency

AU	African Union

AWP	Annual work plan

CBD  	Convention on Biological Diversity

CdCS	Strategic Cooperation Framework

CDARS 	National Centre for the Development of Agriculture in Sahara Regions

CITES	Convention on International Trade in Endangered Species

CMS  	Convention on Migratory Species

CNIAAG	National Centre on Artificial Insemination and Genetic Improvement

CNRA 	National Research Centre on Socio-Cultural Anthropology

CNRDB 	National Centre for Development of Biological Resources

CNRDPA 	National Research Centre for the Development of Fisheries and Aquaculture

CNRPAH 	National Research Centre on Prehistory, Anthropology and History

CPAP	Country Programme Action Plan

CRBT 	Biotechnology Research Centre

CRSTRA 	Centre of Scientific and Technical Research on Arid Regions

CSO	Civil society organizations

ENSA 	National Higher School of Agronomy

ENSSMAL	National Higher School of Marine Sciences and Coastal Management

ERBM 	Enhanced Results Based Management

GEF	Global Environment Facility

GR	Genetic resources

HCDS	High Commission for the Development of the Steppe

IA	Implementing Agency

INRAA 	National Agronomic Research Institute of Algeria

INRF 	National Institute of Forestry Research

IPPC	International Plant Protection Convention

IP	Intellectual Property

IPR	Intellectual Property Rights

IR	Inception report

IRRF	Integrated Results and Resources Framework

ITAFV 	Technical Institute for Fruit Trees and Vines

ITCMI 	Technical Institute for Vegetable and Industrial Crops

ITEDAS 	Technical Institute for the Development of Saharan Agronomy

ITELV 	Technical Institute of Livestock Breeding

ITGC	Technical Institute for Large Cultures

ITPGRFA	International Treaty on Plant Genetic Resources for Food and Agriculture

IUCN	International Union for the Conservation of Nature

IW	Inception workshop

KAP	Knowledge, Attitudes and Practices

MAE	Ministry of Foreign Affairs

MADR	Ministry of Agriculture and Rural Development

MC	Ministry of Culture

ME 	Ministry of Energy

MESRS 	Ministry of Higher Education and Scientific Research

MICL	Ministry of the Interior and Local Collectivities

MIM 	Ministry of Industry and Mines

MPRH 	Ministry of Fisheries and Marine Resources

MREE	Ministry of Water Resources and Environment

MTA	Ministry of Tourism and Crafts

M&E	Monitoring and evaluation

NAPE-SD 	National Action Plan for Environment and Sustainable Development

NBSAP 	National Biodiversity Strategy and Action Plan

NIM	National Implementation Modality

NGO	Non-governmental organizations

NPD	National Project Director

NSC 	National Steering Committee

PA  	Protected Area

PIC	Prior informed consent

PMU	Project Management Unit

PPP	Public-private partnership

Ramsar	Convention on Wetlands of International Importance

RCU	Regional Coordinating Unit

SNAT 	National Scheme of Land Planning 2030

TK	Traditional knowledge

TRIPS	Agreement on trade-related aspects of intellectual property rights

UNCCD	United Nations Convention to Combat Desertification

UNCLOS 	United Nations Convention on the Law of the Sea

UNDP	United Nations Development Programme

UNDP-CO	United Nations Development Programme Country Office

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNFCCC 	United Nations Framework Convention on Climate Change

UPOV	International Union for the Protection of New Varieties of Plants

WHC 	Convention concerning the Protection of the World Cultural and Natural Heritage

WIPO	World Intellectual Property Organization

WTO	World Trade Organization

# Section I: Project Description

## Part 1: Situation analysis

Governing access to genetic resources (GR) and assuring the fair and equitable sharing of benefits arising from their use in accordance with the Convention on Biological Diversity (CBD) is a newly emerging challenge for Algeria, as is the protection of traditional knowledge (TK) associated with GR. A workshop was held from 28-30 April 2013 in Algiers on Access and Benefit Sharing (ABS) and the Nagoya Protocol (NP), during which representatives of national and international institutions discussed the implementation of ABS/NP through National Biodiversity Strategy and Action Plans (NBSAPs). At the workshop a national project for capacity development on access and benefit-sharing was conceived. On 9 July 2013 the Algerian Ministry of Foreign Affairs (MAE) submitted a project concept on ABS to UNDP, requesting UNDP’s support in applying for Global Environment Facility (GEF) funding under the STAR-5 allocation to implement the said ABS project. Based on this request from the Algerian Government, UNDP and the Algerian Government developed a PIF, submitted on 12 May 2014 and approved 21 May 2014. This Project Document is the result of the PPG phase.

### Biodiversity status and threats

Algeria is located in the north-western section of Africa and with 2,381,741 km2 is the continent’s largest country. Bound by the Mediterranean Sea in the north, it shares borders with Morocco, the Western Sahara, Mauritania, Mali, Niger, Libya and Tunisia. Its geographical location makes it an important country in terms of ecosystem and species diversity: its territory comprises mountain, agricultural, desert, steppe, wetland, forest, and marine ecosystems. Its marine ecosystems contain over 4,000 species and its terrestrial ecosystems more than 9,000 species. Yet, the biodiversity-poor Sahara desert covers almost 84% of the national territory, meaning that the majority of Algeria’s biodiversity exists in only 16% of the national territory, and the most biodiverse zone – the littoral – only makes up 0.07% of the national territory.

Biodiversity and GR (and its associated traditional and local knowledge) are especially important in Algeria due to the prevailing social, cultural, economic and demographic structures. Human development and well-being depend directly on biodiversity on many levels: as a source of food (from both land and sea), animal forage, cultural inspiration, tourism and so forth. The agricultural, fisheries and industrial sectors are the primary users of biodiversity and, together, make up to 20-30 % of GDP depending on the year. This percentage rises to 40% when hydrocarbons are excluded. Species representing a potential genetic resource or origin of crops cultivated by humans in agriculture, forestry, industry and ethno-botany number around 400-500. 14% of Algeria’s population is dedicated to agriculture and economically exploits less than 1% of biological species. This indicates that there is significant potential for the use of biological and genetic resources in the country for sustainable development.

Yet, Algerian biodiversity is unevenly inventoried and knowledge varies widely by taxon. Higher plants and vertebrates are relatively well known, but data is lacking on invertebrates (especially marine invertebrates). Knowledge of viruses, bacteria and protozoans is even more fragmented. In 2014, terrestrial vertebrates included 108 species of mammals, 378 bird species, 80 reptile species, 14 amphibian species and 71 fish species. Marine vertebrates included 11 mammal species, 328 fish species, and 2 reptile species. There is a general trend towards biodiversity loss and ecosystem degradation across vulnerable regions in Algeria. The IUCN Red List for Algeria contains 185 species, including 21 critically endangered species, 22 endangered species, 58 vulnerable species, 70 near threatened species and one lower-risk/near threatened species. The Red List species include flora and fauna from both marine and terrestrial ecosystems. According to the 5th National Report on the Implementation of the Convention on Biodiversity, the most exposed mammals are wild ungulates (gazelles, antelopes, Barbary sheep, Barbary stag), the fennec fox, the otter, the honey badger, the caracal, the serval, the leopard, the monk seal, and the Barbary macaque. Among the reptiles, turtles, vipers and other snakes make up the majority of protected species, while almost half of amphibians are protected. Nearly one third of bird species are protected, most notable among which are the Algerian nuthatch, Audoin’s gull and the northern bald ibis. Invertebrates are poorly protected, with no protection granted to marine invertebrates. Approximately 14% of spermaphytes are protected, the most significant being the Saharan (Tassili) Cypress, the Laperrine olive, black pine, and desert thyme.

This erosion of biological and genetic diversity and of ecosystem services implies fewer livelihood options for local populations and fewer options to confront continued environmental pressures, for both the present and future generations. The main threats to biodiversity are driven by human activity and most notably include: the over-exploitation of biological resources including through poaching; the destruction or degradation of natural habitats most notably through an expansion of cultivated areas linked to an increased demand for food (the surface of natural steppe vegetation has decreased by 50% since 1989); growth of human populations and related urbanization and infrastructure development; and extractive activities and pollution. Of all natural ecosystems, forests have suffered the greatest impact: over the past 150 years, Algeria’s forests have diminished by over 50%, from 9.2 million ha to 4.2 million ha, making up a mere 1.7% of the country’s land area.

Marine and coastal ecosystems also face strong anthropogenic pressures, most notably from pollution, alien invasive species and overfishing (in the fisheries sector, the number of fishing vessels increased from 2,400 in 1999 to 4,000 in 2005, considerably increasing fishing pressure). This increasing pressure on biodiversity is compounded by the effects of climate change, with the predicted impacts in Algeria by 2030 being: a temperature increase of 1° C; a decrease in rainfall of 20 to 40 % from east to west and a shift of agro-climates 100 km to the north; a decrease in solid precipitation (snow) of 50%; and a movement of isohyets to the north. The highlands, the steppes and the Sahara will be most critically affected – e.g. from increasing desertification (a severe threat for present and future generations in semi-arid, arid and desert ecosystems). Marine ecosystems are also expected to be affected such as by changes/losses in commercial fisheries. The littoral is under heavy pressure, with 2/3rds of the Algerian population living on only 4% of the national territory, making urbanization a major threat to biodiversity and ecosystem integrity.

Freshwater ecosystems and wetlands are some of the most threatened by pollution and drought, and their conservation must be considered a priority. Mountain ecosystems, which make up 3.66% of the country’s land area, play a very important role for biodiversity in Algeria, but are under serious pressure and are considered to be some of the most threatened by climate change in the Mediterranean region. It is expected that over 60% of mountain flora will be extirpated by 2080. The steppes, which make up 10% of the land area, are extremely degraded. Alfa, considered to be a keystone species, has disappeared from some steppe regions and vegetation cover has decreased from 30% to 15%.

Algeria has addressed and made good progress on a number of fronts relating to the first and second objectives of the CBD – the conservation of biodiversity and its sustainable use, respectively – through building and managing a protected areas system, and through sustainable natural resource management practices and similar activities. Algeria has an important protected areas system: over 44% of the national territory is subject to some form of protection (national park, natural reserves, cultural parks, etc.). 50 wetlands of international importance exist in Algeria, with a surface area of more than 3 million hectares (an estimated 50% of wetland area). There are 904 legally protected species in Algeria, 546 of which are plants (14% of Algerian plant species), and 358 of which are animals (127 invertebrates/231 vertebrates). The vertebrates include 125 bird species, 54 mammal species, 46 reptile species, and 127 insect species. The Algerian list of protected species is much greater than the IUCN Red List species, but fish are notably absent.

However, challenges remain. PA management effectiveness and the resources made available can be strengthened. The administrative institutional model is insufficient and does not entirely respond to present challenges in biodiversity management, hindering effective implementation of biodiversity related laws, regulations and policies (e.g. the NBSAP). Synergy, coordination and effectiveness of actions across ministries and between different sectors and agencies involved in biodiversity management and oversight can be improved. Although biodiversity conservation dimensions have been incorporated into school curricula, awareness remains insufficient and must be further enhanced across among a broader range of actors and stakeholders, particularly in regard to genetic resources. Participation of local populations in conserving and sustainably using biodiversity and GR must be encouraged and increased. In addition, working towards the third objective of the CBD – the fair and equitable sharing of the benefits derived from accessing and using GR – remains a major challenge in Algeria, although it could offer important avenues to address a range of the challenges identified here.

### The environmental legal and institutional framework in Algeria

Algeria has signed and ratified various international and regional agreements in the field of environmental protection, biodiversity and natural resource management, including most notably: the CBD (entered into force for Algeria on 12 November 1995) with its Cartagena Protocol on Biosafety (the country has not signed the Nagoya-Kuala Lumpur Supplementary Protocol on Liability and Redress) and the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from their Utilization (signed but not yet ratified); the Bonn Convention on Migratory Species (CMS) with its African-Eurasian Waterbird Agreement (AEWA) and Agreement on the Conservation of Cetaceans of the Black Sea, Mediterranean Sea and Contiguous Atlantic Area; the Convention on Wetlands of International Importance (Ramsar); the Convention on International Trade in Endangered Species (CITES); the UN Convention to Combat Desertification (UNCCD) as well as the Protocol to Combat Desertification in African Countries; the UN Convention on the Law of the Sea (UNCLOS) and Fish Stocks Agreement; the UN Framework Convention on Climate Change (UNFCCC) and its Kyoto Protocol; the Barcelona Convention for Protection against Pollution in the Mediterranean Sea and its Protocols concerning Cooperation in Preventing Pollution from Ships and in Cases of Emergency Combating Pollution of the Mediterranean Sea, and concerning Specially Protected Areas and Biological Diversity in the Mediterranean; the Convention concerning the Protection of the World Cultural and Natural Heritage (WHC), International Plant Protection Convention (IPPC), and the African Convention for the Protection of Nature and Natural Resources 1968. Algeria is also a member of IUCN. Algeria was the first country to ratify the 2003 UNESCO Convention for the Safeguarding of the Intangible Cultural Heritage, and recently ratified the 2005 UNESCO Convention on the Protection and Promotion of the Diversity of Cultural Expressions (enters into force May 26, 2015).

Algeria in December 2002 acceded to the FAO International Treaty on Plant Genetic Resources for Food and Agriculture (ITPGRFA) but it is not nationally implemented. Algeria is moreover a member of the World Intellectual Property Organization (WIPO). However – and while negotiations are in process – the country is not yet a member of the World Trade Organization (WTO) and, consequently, is not yet a party to the TRIPS Agreement (on Trade Related Aspects of Intellectual Property Rights, Including Trade in Counterfeit Goods) and not bound by its obligations. Algeria is also not a member of the UPOV International Convention for the Protection of New Varieties of Plants, but is presently in contact with the Office of the Union to obtain assistance in the development of laws based on the UPOV convention.

In terms of its national environmental and related sustainable development framework and legislation, in keeping with its policy on environmental protection and sustainable development, Algeria has a number of legal and regulatory instruments relevant to biodiversity, notably: Law 83-03 on Environmental Protection; Law 83-17 on the Water Code; Law 1984-12 on the General Regime for Forests; Law 87-17 on Phytosanitary Protection; Law 90-25 on Land Principles; Law 01-11 on Fisheries and Aquaculture; Law 01-19 on Waste Management, Control and Elimination; Law 03-10 establishes the General Law for the Environment and Sustainable Development, which includes references to biodiversity; Laws 02-02, 04-03 and 11-02 deal with the conservation and sustainable development of coastal areas, mountain areas and protected areas, respectively; Law 05-03 on Seeds, Plants and Plant Variety Protection; Law 04-07 on Hunting; Law 08-16 on Agriculture Principles; and Law 14-07 on Biological Resources. Regulatory instruments include Order 75-43 on the Pastoral Code, Decrees 93-285 and 95-429 establishing a list of protected cultivated plants and the rules governing their export, import, exchange, use, transport and sanitary conditions; Order 06-05 on the protection and preservation of certain threatened species; Order 09-88 on the classification of critical zones on the littoral, Order 09-114 on the conditions for a coastal management plan, its contents and implementation modalities; Order 2010-31 establishes the modalities of extending the protection of the sea floor in the littoral and determining offshore industrial activities; Order 12-03 on protected non-cultivated plant species; and Order 12-235 on protected non-domesticated animals. Moreover, Algeria has a comprehensive set of standards relating to trademark, copyright and patents – Law 2003-19 on Patents for Invention is the central law governing inventions and innovations. Law 1998-04 on the protection of cultural heritage is the only national legal instrument in existence stipulating and defining the implementing legislation for the conservation of intangible cultural heritage. Algeria has just created a UNESCO Category 2 Centre dedicated to the preservation of Africa’s intangible cultural heritage. Phytogenetic resources are provided intellectual property protection under Law 2005-03 on Seeds, Plants and Plant Variety Protection

Regarding biological and genetic resources and the third objective of the CBD more specifically: Algeria was one of the first countries to sign the Nagoya Protocol on ABS in February 2011. While the Protocol has not yet been ratified, Law 2014-07 on Biological Resources was adopted by Parliament on 9 August 2014 with the goal of establishing conditions for the collection, circulation and use of biological resources and associated traditional knowledge for sustainable and beneficial development in the national interest. It contains a number of provisions relevant to ABS, but eight regulations must be adopted under the law to create a functional ABS regime, notably on:

- The composition, attributes and modalities of operation of the national administrative body on biological resources (Article 4)

- The model and content for the permit for access to biological resources for commercial or scientific purposes (Article 7)

- The involvement of Algerian scientists and banking of duplicate samples (Article 10)

- The content of dossiers for requests for access, the documents required for prospection, collection or sampling for scientific or commercial purposes, as well as the conditions, clauses or modalities relative to the engagements made by the requestor (Article 12)

- The modalities of obtaining prior informed consent (PIC) from local authorities, professional organizations, associations, and/or holders of biological resources and associated TK (Article 13)

- The content and modalities for managing the public register of biological resources and access requests (Article 15)

- The function, use and management of the national authority’s database on biological resources and associated TK (Article 16)

- The mechanisms for fair and equitable benefit sharing resulting from the use of biological resources and associated traditional knowledge (Article 17)

- All other necessary regulatory modalities required to apply the law (Article 23)

The regulations are currently being discussed and drafted, with six in the inter-ministerial consultation phase, and this process will be supported under Component 1 of this project.

The following government agencies are mandated to develop policies, regulations and oversee and manage different sets of ecosystems, resources and biodiversity components: Ministry of Agriculture and Rural Development (MADR); Ministry of Water Resources and Environment (MREE); High Commission for the Development of the Steppe (HCDS); Ministry of Interior and Local Collectivities (MICL); Ministry of Fisheries and Marine Resources (MPRH); Ministry of Energy (ME); Ministry of Commerce; Ministry of Education; Ministry of Higher Education and Scientific Research (MESRS); Ministry of Industry and Mines (MIM); Ministry of Culture (MC); Ministry of Tourism and Crafts (MTA); National Centre for Development of Biological Resources (CNRDB); General Directorate of Forestry (DGF); National Development Agency of University Research; National Agency for Nature Conservation (ANN); and National Centre for the Development of Agriculture in Sahara Regions (CDARS). Their functions are separated according to specific legal competences, expertise and areas of incidence. Strategies for implementation are found in several national plans and respond to global objectives on the conservation of biodiversity, e.g. the MREE Action Plans, the MADR Action Plan, the MPRH Action Plan, the MESRS Action Plan, and the Ministry of Culture Action Plan.

The following technical public institutions focus more directly on fundamental research (e.g. on taxonomy, species distribution, ecosystem degradation) and applied research (e.g. identification and management of useful forest resources, agricultural improvement, livestock breeding, etc.), often specialized on specific ecosystems or biodiversity components (e.g. trees, livestock, GR): Centre of Scientific and Technical Research on Arid Regions (CRSTRA); National Higher School of Agronomy (ENSA); National Institute of Forestry Research (INRF); National Higher School of Marine Sciences and Coastal Management (ENSSMAL); Technical Institute for Fruit Trees and Vine (ITAFV); Technical Institute for the Development of Saharan Agronomy (ITEDAS); Technical Institute of Livestock Breeding (ITELV); Technical Institute for Large Cultures (ITGC); Technical Institute for Vegetable and Industrial Crops (ITCMI); National Agronomic Research Institute of Algeria (INRAA); National Research Centre for the Development of Fisheries and Aquaculture (CNRDPA); Biotechnology Research Centre (CRBT); National Research Centre on Prehistory, Anthropology and History (CNRPAH); National Research Centre on Socio-Cultural Anthropology (CNRA); and National Centre on Artificial Insemination and Genetic Improvement (CNIAAG). Several of these institutions are inter alia dedicated to conserving agricultural GR.

### Barriers and long-term solution

While Algeria has made progress on the conservation and sustainable use of biological diversity, it is still in the process of adopting the regulatory and institutional basis for working towards the third objective of the CBD - regulating access to GR and sharing the benefits from their use fairly and equitably. This poses an obstacle to the effective implementation of the CBD by depriving Algeria of the benefits resulting from the utilization of genetic resources.

Barriers include insufficient awareness and understanding of the legal, policy, technical and financial dimensions of ABS across large sectors of society, including resource holders/suppliers, government agencies, resource users, and the private sector. No comprehensive national regulatory framework under the Law on Biological Resources exists, yet such a framework is necessary for long term success in implementing the three objectives of the Convention on Biodiversity (conservation, sustainable use, and access and fair and equitable benefit-sharing), and the objectives of the Nagoya Protocol. The lack of an ABS framework is a barrier to addressing the above threats to biodiversity because ABS can help raise the value of genetic resources by generating economic benefits, empower local populations through benefit sharing, and provide greater incentives and financing for the government and private sector to protect and integrate the value of genetic resources into sectorial policies and plans. The potential of genetic resources is not well known or understood, and many valuable resources may be lost before they are utilized due to climate change and the ongoing loss of biodiversity. It is also difficult to identify representatives of local populations, the holders of genetic resources and associated traditional knowledge because they have not been catalogued.

The long term solution to overcome these barriers and assign a higher value to genetic resources involves the creation, development and implementation of a comprehensive national regulatory and institutional framework for ABS by defining a specific set of norms. The regulatory framework will be overseen both through a specialized national agency established under the Law on Biological Resources, and by assigning specific ABS functions and competences to existing agencies. In addition to making Algeria more compliant with the CBD’s ABS principles and the Nagoya Protocol (e.g. PIC, mutually agreed terms (MAT), checkpoints for GR, and benefit-sharing mechanisms), this will activate the potential that Algeria’s GR and TK represent for generating economic benefits to the nation and key stakeholders, including local populations where appropriate, in the form of business, employment, technology transfer and capacity development. These new opportunities are expected to strengthen the economic case and political motivation as well as the financing required for the conservation of biodiversity and the sustainable use of its components containing genetic resources. Where genetic resources are accessed from protected areas, benefits can be directed to funding the Algerian protected area system and protecting endangered species. Special emphasis will need to be given to reinforcing the capacities of civil society and local populations, as well as the empowerment of women.

The establishment of a comprehensive national ABS framework will moreover ensure that Algeria’s sovereign right to regulate access to GR and associated TK is respected. The development of the ABS framework in turn requires the strengthening of capacities across relevant stakeholder groups, including in the government agencies responsible for overseeing and implementing the related requirements. Developing and operationalizing an ABS framework can help address several of the challenges regarding biodiversity management and conservation in the country by leveraging additional monetary and non-monetary resources for conservation and sustainable use of biodiversity, the management and conservation of biological and genetic resources, as well as generating increased stakeholder awareness and interest.

### Baseline Analysis

Working towards the above mentioned long-term solution, the Government will over the project duration of four years invest an estimated $4,000,000 on matters relevant in the context of ABS and TK in the widest sense. This includes also the work on the process of ratification of the Nagoya Protocol and the adoption of the general law on the use of biological resources in Algeria (led by the MARD, which currently hosts the CBD-ABS focal point); relevant research into genetic, marine and agricultural resources; and the management of biodiversity and natural resources as well as intensive participatory involvement of local populations in key protected areas through the UNDP-GEF project “Conservation of globally significant biodiversity and sustainable use of ecosystem services in Algeria’s cultural parks” (GEF # 3952); which is scheduled to last until 2019 and will overlap fully with the here-proposed project). The Government is moreover engaged in the UNEP-GEF project “National biodiversity planning to support the implementation of the CBD 2011-2020 Strategic Plan in Algeria” (GEF # 4987), which is revising the national policies and strategies on biodiversity and ABS and preparing the new NBSAP. The project is expected to conclude in February 2016.

The German Agency for International Cooperation (GIZ) under a bilateral cooperation agreement with the Government of Algeria supports a new program on environmental governance and biodiversity (global budget USD 4,400,000 / EUR 4,000,000 for four years), which includes a component on the creation of ABS value chains at the local level based on the sustainable use of biodiversity (the budget share was estimated to USD 830,500 / EUR 755,000). MREE is the lead executing agency for this programme. The present UNDP-GEF/Government project will from the onset work closely with the GIZ-funded programme (which already started and is fully complementary) to align planning and activities to maximize all possible synergies and cost-effectiveness. The ABS Capacity Development Initiative and its partners will carry out a country evaluation and provide technical support services under the GIZ-funded program, in cooperation with the National Focal Point on ABS and other pertinent stakeholders. Based on the results of the evaluation, a roadmap will be developed that details the capacity-building activities that will be carried out with the support of the ABS Initiative in the coming years.

The baseline scenario does not allow for the preparation of a comprehensive regulatory and institutional framework for ABS and TK, and does not seek to build specific awareness and capacity on ABS and TK-related matters across the wide range of interested stakeholders. In absence of such a framework, ABS-compliant agreements cannot be developed and implemented between government, private sector and local populations, including holders of TK. This impedes the creation of livelihood and wider economic and benefit-sharing opportunities through ABS agreements. Until a comprehensive regulatory and institutional framework is adopted, ABS will remain a missed opportunity for Algeria.

The following GEF alternative scenario includes a description of the project’s components, as well as incremental cost reasoning assessing expected contributions from the baseline, from UNDP co-financing and the GEF-TF.

## Part 2: Strategy

### Project Rationale and Policy Conformity

#### Conformity with National Strategies and Objectives

The proposed project is in line and consistent with the country’s existing national policies, laws, strategies and plans relevant for biodiversity. That said, there are two levels to consider: firstly, general references to the conservation and sustainable use of biological resources; and secondly, specific references to GR and ABS-related matters. On the former, references are made in the National Strategy and Action Plan for the Sustainable Use of Biological Diversity (NBSAP) established in 1997, strengthened in 2002 and under revision in 2015-2016; and in the National Action Plan for Environment and Sustainable Development (NAPE-SD), which is also under revision. These policies incorporate global and national objectives advocating the conservation of biodiversity at the ecosystem, habitat and biome levels, most notably through the creation of protected areas in conformity with Law 11-02.

The Algerian Government completed its Fifth National Report to the CBD in 2014 to report on progress made in implementing the Strategic Plan for 2010-2020 and, in particular, towards its objective of reducing biodiversity loss at the national level. This assessment report will be catalytic in pushing forward the proposal for a new NBSAP to 2020, which integrates the National Strategy for Wetlands that is now being finalized, which accords with the provisions of the CBD Strategic Plan for Biodiversity 2011-2020. The project in the wider sense is moreover consistent with the National Scheme of Land Planning 2030 (SNAT), which defines the basic strategic guidelines and requirements of national policy development and sustainable development planning; the SNAT through Territorial Action Programmes has a direct relationship with biodiversity, such as on “Soils and steppes” (preservation and enhancement of the steppe ecosystem and land in an integrated and coordinated manner) and “Nature and cultural parks” (preservation and enhancement of natural and cultural parks in the highlands by the creation of parks and cultural centres around archaeological sites). The project is also consistent with the Master Plan for Natural Spaces and Protected Areas and with the Master Plan for Coastal Development (which promotes the conservation and recovery of fragile and coveted ecosystems in coastal areas). Biodiversity considerations are moreover integrated into several sectorial strategies, including the National Strategy for Sustainable Agricultural and Rural Development, and Policy on Rural Renewal.

At the same time, specific references to GR (including on ABS and associated TK) are still relatively weak in the prevailing policies – the NBSAP refers to the need to avoid bio-piracy (the challenges of regulating access to GR, as well as their collecting and trading); the need for scientific research and experiments on GR on species native to Algeria by national laboratories; the need to regulate the access by foreigners to the country’s genetic material, seeking compensation through technology transfer and the sharing of benefits from their utilization; the integration of genes and their values into the common national biological heritage; the issuance of patents based on payable usage rights; and the need to expand surveys on ethno-botanical knowledge and practices and on TK to define the baseline and complete databases.

#### Conformity with GEF Strategies and Objectives

The project addresses the GEF-5 BD-4 Focal Area objective – Build capacity on access to genetic resources and benefit sharing, contributing directly towards Outcome 4.1 “Legal and regulatory frameworks, and administrative procedures established that enable access to genetic resources and benefit sharing in accordance with the CBD provisions” and Output 4.1 “Access and benefit-sharing agreements that recognize the core ABS principles of Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) including the fair and equitable sharing of benefits”. The project is also consistent with the eligibility criteria and priorities of the GEF Trust Fund, as it will support the Government of Algeria in developing a national ABS framework and related capacity to implement this regime, with appropriate consideration to PIC; TK holders; promoting bioprospecting and related value chains; and ensuring that benefits generated (both monetary and non-monetary) are fairly shared. In addition, the project will facilitate private sector engagement, as well as projects targeting investments in the conservation and sustainable use of GR in in-situ and ex situ conditions.

The GEF project is closely aligned with the Strategic Cooperation Framework and the Country Programme Action Plan. Outcome 3 of the CdCS states that by 2020, the living environment and resilience of citizens are improved thanks to sustainable participatory management of natural and urban ecosystems, and Output 2 states that the capacity of principal national and local actors are strengthened to operationalize strategies/action plans for the sustainable management of natural and urban ecosystems based on the improvement of the resilience and living environment of citizens.

### Project Description: Objective, Outcomes and Outputs

This project is needed to enhance the implementation of all three objectives of the CBD, including the conservation and sustainable use of biodiversity. The project will also contribute to reducing biodiversity loss by: 1) increasing awareness about the existence, use and option values of biological resources among key audiences; and the existence of markets based on the sustainable use of biodiversity and its components; 2) enabling the government and other stakeholders to derive greater economic benefits from GR and generate incentives that favour in-situ and ex-situ conservation and ecosystem management; 3) enabling the generation of monetary and non-monetary benefits from the access to and use of GR through partnerships with industry, commercial firms and academic and research institutions; and 4) provide local populations that maintain GR in their lands and possess associated TK with new livelihood options resulting in economic benefits that reduce pressures on ecosystems and contribute to the maintenance of national, regional and global ecosystem services.

Designing, establishing and implementing an ABS framework will facilitate and streamline the negotiation and development of ABS contracts that comply with CBD and Nagoya Protocol requirements on PIC, MAT and benefit-sharing with holders of GR and associated TK, and other stakeholders. The project will enable different actors (i.e. public institutions, the private sector, local populations and research institutions) to take full advantage of Algeria’s biodiversity and GR in line with international and national conservation and sustainable development obligations and priorities stemming from the CBD.

This project will represent an important further and innovative step towards collaborative, inclusive and participatory governance of natural resources in Algeria. Developing the ABS framework is also expected to mobilize new revenue for biodiversity management. The outcomes of the project, which is part of the first cohort of such projects globally, can provide valuable lessons to be applied subsequently through the dissemination of project results, experiences and best practices in the development and early implementation of national ABS frameworks, including on ABS agreements and PIC processes. A scaling up is expected at national level as ABS agreements will increasingly be adopted by both users and providers of GR once the regulatory and institutional framework is in place.

The here-proposed project will address the aforementioned barriers and achieve the proposed long-term solution through two complementary components, to be implemented in close coordination with the baseline activities, notably the development of a national policy, legal and institutional framework, and the building and strengthening of the capacity of national institutions.

The project's objective is to consolidate actions to conserve and sustainably use genetic resources and related traditional knowledge in Algeria through the development and implementation of a national policy and legal and institutional framework on ABS in line with the CBD and the Nagoya Protocol.

#### Component 1: Developing a national policy, legal and institutional framework

Under component 1, Developing a national policy, legal and institutional framework to enable the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources, the expected Outcomes are:

- 1.1: NBSAP 2.0 with aspects pertaining to ABS is adopted by the Government and used to orient project interventions

- 1.2: A comprehensive and coherent national legal framework on ABS and the protection of TK has been approved and is established and operational

- 1.3: A coherent national institutional framework with the necessary capacities and mandates has been approved and is established and operational

- 1.4: An effective ABS mechanism and model ABS agreement have been developed.

A series of outputs and activities will work towards these Outcomes. To achieve output 1.1 (national legislation on ABS and related issues on intellectual property (IP) and TK prepared and submitted for adoption by relevant Algerian authorities, following national consultations and participatory stakeholder engagement), support must be provided to develop regulations that complete the Law on Biological Resources, and other laws must be analysed to establish their conformity with ABS requirements. In this light, the project will:

Implement the ABS policy components of the NBSAP.

Review and revise the legal and regulatory framework for ABS and related issues regarding intellectual property rights (IPR) and TK.

Contribute, as needed, to the development of regulations for the implementation of the Law on Biological Resources.

Through the development of new regulations under the Law on Biological Resources, the project will achieve output 1.2 (an institutional framework on ABS and traditional knowledge defined and established with supporting policies and measures enabling implementation of legislation on ABS and TK). The regulations will define and establish the required institutional framework on ABS and associated TK, together with a coherent set of supportive policies and measures to operationalize the new Law. These need to be clear, transparent, and predictable, and provide legal certainty to those involved in the permitting process. There is a need to coordinate the use of existing instruments and regulatory measures which consider or address ABS issues, notably those relating to the conservation of GR (e.g. land law, forest law, and environmental law). The new African Union Strategic and Practical Guidelines on the Coordinated Implementation of the Nagoya Protocol, adopted at AMCEN 15, will be used as inspiration for the regulations and institutions.

To achieve output 1.3 (formal coordination mechanisms established between in-country institutions having a mandate in the implementation of the national ABS and related TK framework), existing weaknesses in institutional coordination will be addressed by establishing a national competent authority in the form of a dedicated agency created under the Law on Biological Resources, and defining its mandate, as well as creating formal coordination mechanisms between in-country institutions with a mandate in the implementation of the national framework on ABS and its associated TK. To coordinate the approach of relevant institutions, the creation of an intersectorial scientific and technical committee to support the work of the national competent authority was proposed in stakeholder consultations during the PPG phase, and Article 23 of the Law allows for the creation of such a committee.

In order to address the question of TK, registries must be established to collect the information which remains pertaining to genetic resources. It is likely that much knowledge was lost in the colonial and post-colonial era, and it remains unclear how much inter-generational knowledge has been preserved. Support for the development of community protocols can be used to protect the interests of local populations in the early phases of the project while rules and procedures on ABS are developed, including model contracts and PIC procedures that address the interests of local populations. This should allow for the protection of the intellectual interests of local populations in regards to their TK, and for these populations to participate in benefit sharing schemes.

In order to meet output 1.4 (an effective financial mechanism with the ABS legal framework established for receiving, on a voluntary basis, a percentage of monetary benefits derived from ABS projects for redistribution towards the conservation and sustainable use of biodiversity in perpetuity), the project will work to establish an effective financial mechanism (such as a Trust Fund managing endowment, sinking or revolving funds) in conformity with the ABS framework that will receive a percentage of monetary benefits derived from ABS projects, on a voluntary (non-mandatory) basis by users and providers of GR and associated TK, for redistribution towards the conservation and sustainable use of biodiversity.

#### Component 2: Building and strengthening capacity of national institutions

Designing and putting in place the institutional and legal framework on ABS and the protection of TK is only the first step towards realizing and complying with the CBD ABS principles and Nagoya Protocol objectives. Establishing and reinforcing the capacity of national research and regulatory institutions to apply ABS rules and principles is critical for ensuring that the Law on Biological Resources and forthcoming regulations are successfully implemented. Since ABS is a fairly new issue in Algeria, there is limited implementation capacity within national institutions. Once regulations are adopted to create the national agency overseeing the implementation of the Law, capacity will need to be built to ensure that the agency effectively satisfies its role.

The expected Outcomes under Component 2 are:

- 2.1: Improvement of at least 50% of the capacity of existing or new competent national authorities on ABS

- 2.2: 80% of relevant national stakeholders are informed of the regulatory and institutional framework pertaining to ABS and TK and its different dimensions.

- 2.3: At least 5 bioprospecting projects have been identified by project end..

In order to achieve outcome 2.1, work under Component 2 will begin by focusing on output 2.1, which entails the following: the project will firstly undertake a Knowledge, Attitudes and Practices (KAP) survey to provide a baseline assessment of the awareness and knowledge regarding the national ABS legal and institutional framework and the CBD and Nagoya Protocol. In addition to government, this will include specific groups that will use or benefit from ABS transactions (e.g. relevant researchers, local populations and industry players).

In order to achieve outcome 2.2, the project will use the KAP survey to strengthen institutional and technical capacities in national government institutions set to provide regulatory oversight over ABS procedures (per output 2.2) by targeted training on inter alia key obligations under the Nagoya Protocol, ABS access applications, negotiating ABS agreement, defining scope and application of regulations, and implementing compliance mechanisms and monitoring activities (e.g. for bioprospecting projects or value chains). Trainings will be conducted for at least 100 representatives from the ABS authority, ABS/CBD focal points and agencies with complementary functions: MADR and, in particular, DGF, HCDS, INRAA, ANN, ITDAS, ITELV and CDARS; MREE and the CNRDB; MICL; MDIPI, MPRH; ME; Ministry of Education; MESRS; MIM; MC; Ministry of Tourism and Arts; and National Agency for the Development of University Research.

As a next step, outreach and training on ABS and TK must be directed at research agencies and higher education institutions in ex situ and in situ centres and collections, with holders of GR (especially local populations) and the prospective users who will need to develop new administrative procedures and comply with new sets of requirements pertaining to ABS. To that aim, per outputs 2.3 and 2.4, stakeholder-targeted brochures, posters, manuals and training modules on the national ABS legal and institutional framework will be developed and implemented, covering inter alia the authority of the state and its regulatory mandate over biodiversity and its components, ABS procedures for users and providers of GR, PIC protocols, ABS agreement (MAT) examples and negotiation strategies, customary law, research procedures, the dimensions of ABS-related intellectual property, the defensive protection of GR/TK issues, bioprospecting and value-chains, and misappropriation implications. These trainings will be accompanied by a national communication and engagement strategy and campaign targeting the key stakeholder groups more broadly. Target groups include parliamentarians, public and private sector users, pharmaceutical laboratories, cosmetics laboratories, agri-food industries, distillers, herbalists, artisans, producers/suppliers (e.g. farmers, harvesters), and the media (newspapers, radio, television). An information sharing network on ABS and GR will also be created.

While the framework is established, awareness increased and technical capacities built, the project will identify existing and emerging initiatives and opportunities for research and bio-discovery projects in the agricultural, crop protection, food/beverage, industrial biotechnology, botanical, cosmetics and pharmaceutical industries. The goal will be to identify and facilitate the development of ABS pilot schemes to start generating the benefits to be shared. To that end, the project will focus on establishing the foundation for negotiating ABS agreements by developing ABS model agreements (per output 2.5) inspired by the AU Guidelines on the Nagoya Protocol. The project will coordinate cross-sectorial efforts and convene stakeholders interested in e.g. bioprospecting, ethno-botany, bio-trade and plant breeding, to catalyse the development of ABS schemes in Algeria. Finally, per output 2.6,  the project will compile databases on a) existing and emerging ABS-relevant projects as well as the identified users and providers (institutions, private sector and local populations) of GR and its associated TK; and b) ex-situ collections of GR of Algerian origin.

### Stakeholder Analysis

With regard to the institutional setting for implementing and overseeing the project to develop an ABS framework, the technical information sheet attached to the Algerian Government request for this project (No 2270/MAE/DGRECI/DEDD) indicates that the following Ministries will be directly involved: MAE, MADR, MREE, MESRS, the Ministry of Health, Population and Hospital Reform (MSPRH), MIM, and ME. The information sheet also indicates that there are a number of key stakeholders, such as: national focal points for ABS, biodiversity, climate change, combat against desertification; CMS, CITES, AEWA, IUCN, etc. The table below provides an overview of the key project partners with a preliminary description of their roles, which will be confirmed and validated through a consultative process based on holding workshops in the start-up phase of the project to provide institutional anchoring.

- Table 1 – Stakeholder Involvement

| Stakeholder/actor | Implementation role |
| --- | --- |
| Ministry of Agriculture and Rural Development | MADR is the National Executing Agency which will ensure delivery and coordinate the involvement of all relevant stakeholders to set up a coherent nationwide legal and regulatory framework and its related institutional arrangements. It is responsible for initiating and implementing laws and regulations in its area of competence, and overseeing their implementation. They are also responsible for developing qualified human resources for specific needs. The General Forest Authority (DGF), a subsidiary agency, will be responsible for project execution. |
| Ministry of Water Resources and Environment | MREE is a horizontal Ministry that hosts the GEF Focal Point as well as CBD and Biosafety Focal Points. It is inter alia in charge of the revision and overall implementation of the NBSAP, and will play an important role as a leading partner in all stages of the here-proposed project. |
| Ministry of Interior and Local Collectivities | MICL will intervene and facilitate discussions with civil society, part of which holds traditional knowledge, and are in direct contact with the populations concerned |
| Ministry of Fisheries and Marine Resources | MPRH will intervene on all matters concerning the marine environment and marine GR under its mandate. |
| Ministry of Culture | Will intervene on matters relating to traditional knowledge and intangible heritage of which it is the national focal point. |
| German Agency for International Cooperation (GIZ) | GIZ has a capacity-building project with MREE on environmental governance and biodiversity with an ABS component that is focused on practical case studies at the local level. The implementation of the UNDP-GEF project will be carried out in tandem with the GIZ project in a synchronized manner and lessons learned will be shared. |
| UN Food and Agriculture Organization (FAO) | FAO will work with their country partners to contribute relevant expertise in agriculture, fisheries and forestry to ensure a holistic approach to preserve livelihoods and assure the sustainable use of natural resources. |
| Universities and research institutions | Universities and research institutions will be targeted for efforts that aim to strengthen research programmes on taxonomy, GR and the sustainable use of related biodiversity materials. Communication channels will also be strengthened to ensure research results are widely disseminated in the context of building national capacity on ABS. |
| Private sector / industry (as users and/or providers of genetic resources) | As a key partner the private sector, most notably through leading and committed representatives, will be involved in all project milestones - contributing to awareness-raising within the private sector, identifying suitable GR, resource providers and value chains. |
| Civil society organizations (NGO, others) | CSOs (e.g. Association for Reflection, Exchange and Action for Environment and Development, National Women and Rural Development Association) will play an active role in liaising with local populations and raising public awareness with regard to ABS economic opportunities and positive social impacts. They are also expected to enrich and contribute to the design and implementation of a coherent legal framework. |
| Providers of genetic resources (e.g. local populations, farmers, etc) | The providers of genetic resources will be consulted to facilitate and contribute to the compilation and assessment of GR and associated traditional knowledge. Awareness will be raised amongst local populations involved in ABS matters and capacities built through a CEPA strategy. |

### National and global environmental benefits

The project in Algeria will achieve national environmental benefits by enabling the completion of the framework Law on Biological Resources, which is presently unimplemented due to a lack of implementing regulations and supporting institutions. With a coherent legal, regulatory and institutional framework pertaining to biological and genetic resources, Algeria will be better positioned to conserve biodiversity, sustainably use the products of biodiversity, and share in the benefits resulting from the use of genetic resources. The project also provides an opportunity to simultaneously operationalize the ITPGRFA in Algeria, which will enhance the protection of the high value plant genetic resources for food and agriculture present in the country. Furthermore, moneys directed to the financial mechanism established by the project will be used to support the conservation and sustainable use of biodiversity in Algeria in perpetuity, which can generate significant national environmental benefits.

The project will achieve global environmental benefits through enhanced national contribution towards the achievement of the three objectives of the CBD (especially Objective 3 on ABS) and of the goals of its Strategic Plan for Biodiversity 2011-2020. Specifically, the project will contribute towards reduced rates of biodiversity loss in Algeria by: increasing awareness about existence, use and option values of biological resources among key audiences, and about the existence of markets based on the sustainable use of biodiversity and its components; enabling the government and other stakeholders to derive greater economic benefits from GR and generate incentives which can favour in situ and ex-situ conservation and ecosystem management; facilitating the generation of monetary and non-monetary benefits from access to and use of GR, particularly through the interest of industry (mainly cosmetics and pharmaceuticals), commercial firms (e.g. sustainable trade in products of biodiversity) and academic and research institutions; provide local populations that maintain GR in their lands and have developed and accumulated TK (e.g. herbalists and others that have yet to be determined) with new livelihood options resulting in economic benefits that reduce pressures on ecosystems, support the conservation and sustainable use of biodiversity and contribute to the maintenance of national, regional and global ecosystem services.

At the global level, the project will contribute towards the achievement of the following CBD Aichi Targets: Target 1, by increasing the awareness of people in Algeria on the values and potential of biodiversity and how to conserve and sustainably use it; Target 12, by preventing the extinction and/or improving the conservation status of (economically valuable) threatened species; Target 13, by safeguarding the genetic diversity of socio-economically valuable species and cultivated plants (where these are also source of useful genetic materials and components for research and development); Target 18, by better involving, protecting and promoting local traditional knowledge relevant for the conservation and sustainable use of biodiversity; and Target 20, by adding an untapped financing mechanism to the portfolio of resource mobilization options for biodiversity in Algeria.

### Incremental cost analysis

The project's objective is to consolidate actions to conserve and sustainably use genetic resources and related traditional knowledge in Algeria through the development and implementation of a national policy and legal and institutional framework on ABS in line with the CBD and the Nagoya Protocol. Component 1 involves developing a national policy, legal and institutional framework to enable the implementation of the Nagoya Protocol. The incremental activities under this component involve participating in the NBSAP revision process to ensure that ABS is fully taken into account in Algeria's biodiversity policies; supporting the regulatory process to ensure the adoption of regulations that are efficient and effective in promoting access and benefit-sharing and that associated traditional knowledge is protected; ensuring that an institutional framework is in place on ABS and traditional knowledge in place and that formal coordination mechanisms exist between in-country institutions; and the creation of a voluntary financial mechanism for the collection and redistribution of funds towards conservation and sustainable use goals. The incremental activities under Component 2 of the project have to do with capacity building, notably: increasing the capacity of new and existing national agencies with ABS competencies by at least 50%, based on information gathered through knowledge, attitudes and practices (KAP) surveys; ensuring that 80% of national stakeholders are informed about the regulatory and institutional framework for ABS by carrying out targeted training for at least 100 representatives from national authorities and agencies; development of communication, education and public awareness materials (e.g. posters, brochures, manuals, training modules) to educate stakeholders, namely parliamentarians, public and private sector users, pharmaceutical labs, cosmetics labs, agri-food enterprises, distillers, herbalists, suppliers, local populations and the media; establishing a national communication and public awareness campaign strategy to familiarize stakeholders with ABS, bioprospecting and value chains; developing a model ABS agreement(s) to provide a basis for negotiating fair and equitable benefit-sharing; and compiling a database on existing and emerging ABS projects, users and providers of genetic resources, and ex-situ collections of genetic resources of Algerian origin.

- Table 2 - Incremental Cost Matrix

| Cost/ Benefit | Baseline | Alternative | Increment |
| --- | --- | --- | --- |
| BENEFITS |  |  |  |
| Global benefits | Under the baseline scenario, the governance of biological resources will be carried out through a variety of independent legal frameworks. The legal framework for ABS will remain unimplemented due to a lack of implementation texts, and inadequate awareness and institutional capacity will impede the implementation of a national ABS regime. Lack of value assigned to biodiversity is leading to its rapid degradation which precludes future use options for genetic resource conservation. | The project aims to establish national policy, regulatory and institutional frameworks to support ABS and to develop the capacities of stakeholders involved in order to activate the potential of Algeria’s genetic resources and associated traditional knowledge. This solution will enable the development of a national bio-prospecting industry, equitable participation in international bio-prospecting programs and attracting investments in Algeria by international bio-prospecting companies to catalyse discovery and development of new products including pharmaceuticals and cosmetics. These new opportunities will enhance the economic rationale and political motivation as well as the necessary funding for the conservation and sustainable use of biological diversity containing genetic material. Strategic awareness raising and capacity building will be conducted for target groups and a financial mechanism will be established to receive proceeds from ABS agreements for re-investment in biodiversity conservation. | The GEF funding will contribute in an incremental manner to removing the barriers to establishing national policy, regulatory and institutional frameworks to support ABS The introduction of an effective national ABS regime and increased awareness of the existence, use and option values of biological resources among key audiences will contribute towards biodiversity conservation and encourage sustainable use of globally significant genetic resources. This will contribute towards the maintenance of global ecosystem services by contributing to actions to mitigate GHG emissions and desertification/land degradation. |
| National and local benefits | Bio-prospecting and use of TK will continue to be unregulated and providers and local communities will be at risk of losing out on national benefits associated with bio-prospecting. Ongoing loss of TK and absence of incentives for conservation and sustainable use of biodiversity as a source of genetic material will result in continued loss and degradation of biodiversity. | The solutions implemented by the project will establish a legislative, regulatory and institutional framework for ABS that will enable the generation of economic and non-economic benefits for the country and key stakeholders, including local communities, in the form of markets, employment, technology transfer and capacity building. The project will enable regulation of bio-prospecting activities through the establishment of the national ABS regulatory and institutional framework, training of institutional and other stakeholders, and develop supporting information management tools such as databases of GR and TK. | Increased awareness about the potential economic and non-economic benefits from genetic resources and an enabling framework for ABS provide incentives to the government, local populations that are holders of genetic resources and associated traditional knowledge, and other relevant stakeholders for the conservation and sustainable use of biodiversity. |
| COSTS |  |  |  |
| Component 1: Developing a national framework on ABS consistent with the CBD and its Nagoya Protocol | Baseline: $2,000,000 | Alternative: $2,900,000 | GEF: $900,000 COF: $2,000,000 SUBTOTAL $2,900,000 |
| Component 2: Building capacity for implementing the national ABS framework | Baseline: $2,755,000 | Alternative: $3,747,956 | GEF $863,636 COF: $2,884,320 SUBTOTAL $3,747,956 |
| Project Management | Baseline: N/A | Alternative: $576,364 | GEF $176,364 COF: $400,000 SUBTOTAL $576,364 |
| TOTAL COSTS | Baseline: $4,755,000 incl. $4,000,000 project co-finance | Alternative: $7,224,320 | GEF $1,940,000 COF: $5,284,320 TOTAL $7,224,320 |

### Socio-economic and development benefits and gender aspects

Given the economic significance of biological and genetic resources in Algeria, it is expected that the project will create significant socio-economic and development benefits for the country. Local populations and holders of associated traditional knowledge, as well as national users (private enterprises) of genetic resources are expected to benefit through newly created commercial and economic opportunities, employment opportunities, and through the fair and equitable sharing of monetary and non-monetary benefits. Positive social impacts are expected from the new livelihood opportunities generated by ABS and the increased local capacities generated, including contributing to greater resilience, life expectancy and poverty eradication. These socio-economic benefits will help ensure that local populations that maintain GR in their lands and have developed and accumulated TK (e.g. herbalists and others that have yet to be determined) have new livelihood options that can reduce pressures on ecosystems and contribute to the maintenance of national, regional and global ecosystem services.

Women are widely recognized as important holders of genetic resources and associated traditional knowledge. The implementation of this project will take into account the 2015-2020 Gender Plan of Action under the Convention on Biological Diversity adopted at COP 12. In keeping with the objective of mainstreaming gender considerations described by the Plan of Action, stocktaking exercises will adequately account for the differences in uses of biodiversity between women and men. Furthermore, women will be effectively engaged as members of all stakeholder groups, and the importance of traditional knowledge and customary practice held by men and women in the protection of biodiversity will be identified and used in supporting implementation. Women’s groups already active in related sectors such as agriculture, fisheries, and forestry will also be engaged. These actions will help contribute to gender equality and women’s empowerment.

### Innovativeness, sustainability and potential for scaling up

The project is innovative at national and global levels. ABS and the protection of the associated local traditional knowledge are new emerging and highly complex issues and the project will enable the different stakeholders – including public institutions, the private sector, local populations and research institutions – to take full advantage of Algeria’s biodiversity and GR in line with international and national conservation and sustainable development obligations and priorities. Newly designing, establishing and implementing an ABS framework should facilitate and streamline the negotiation and development of ABS contracts that fully comply with CBD requirements on PIC, MAT and benefit-sharing with local populations and other stakeholders; this will represent an important further and innovative step towards collaborative, inclusive and participatory governance of natural resources.

Developing the ABS framework is also expected to mobilize new revenue for biodiversity management. The outcomes of the project, which is part of the first cohort of such projects globally, can provide valuable lessons to be applied subsequently through the dissemination of project results, experiences and best practices in the development and early implementation of national ABS frameworks including on ABS agreements and PIC processes. A scaling up is expected at national level when ABS agreements will increasingly be adopted by both users and providers of GR, and at global level through the development of similar projects aiming at the further promotion of ABS legal and institutional frameworks.

## Part 3: Management Arrangements

The project’s implementation and execution arrangements will focus on maintaining strong collaboration and cooperation. It will also aim to avoid duplication of effort. The project will be nationally executed, in line with the Standard Basic Assistance Agreement between the UNDP and the Government of Algeria, and the Country Programme Action Plan (CPAP), which is known as the CdCS in Algeria. The DGF/MADR (hereinafter referred to as the national executing agency) will ensure delivery and coordinate the involvement of all relevant stakeholders in order to set up a coherent nationwide legal, regulatory and institutional framework, and capacity building activities. Implementation will be carried out following UNDP and UNDP-GEF guidelines for Government of Algeria projects and UNDP’s programmatic approach on human rights, gender, environment, results-based management, communication for development and south-south cooperation.

As the national executing agency, the DGF will sign the project document alongside the UNDP. The DGF will be accountable to UNDP for the disbursement of funds and for achieving the project’s objectives in accordance with the annual work plans. It is the national executing agency’s responsibility to ensure: 1) the coordination of activities to achieve the project’s expected objectives; 2) the certification of expenditures in accordance with UNDP-NIM guidelines and approved work plans; 3) the facilitation, monitoring and reporting on the implementation of activities and realization of outputs; 4) the coordination of actions financed by the UNDP/GEF and other relevant parallel activities in order to benefit from additional and complementary synergies; 5) the validation of terms of reference for consultants and tender documents for subcontracting, and 6) reporting to UNDP on the project’s results and impacts.

The DGF will appoint a senior official as the National Project Director (NPD). The official will be responsible for providing State oversight and guidance on the project’s implementation. The project management arrangements involve two levels of consultation and strategic decision-making, namely:

Tripartite (Outcome Board): An annual tripartite meeting, co-chaired by a representative of the Ministry of Foreign Affairs and the Resident Representative of the UNDP (or their representative), where a representative of the MADR, other than the NPD and member of the project steering committee, will participate. The tripartite meeting shall be held at least once per year and as needed, in order to evaluate the results and impact of the project. This meeting will allow the participating members to follow the progress of the project, to agree to corrective measures required, as well as general and strategic direction to align the project with national priorities in order to increase efficacy and efficiency.

Project Steering Committee: Project monitoring activities are the responsibility of the Project Steering Committee (PSC), whose annual meetings will be chaired by a senior DGF official other than the NPD and the Resident Representative of the UNDP (or their representative). It shall be set up at the project’s launch in order to support the project’s decision-making body. The PSC will provide the project with strategic guidance and supervise its execution according to the annual work plan. The PSC is constituted of representatives serving in three different capacities: executive (DGF and UNDP), senior officials from related government agencies (representatives from the Ministry of Foreign Affairs, Ministry of Water Resources and Environment, GEF Focal Point and other relevant Ministries) whom provide guidance on the project’s overall and technical feasibility, and senior beneficiaries (INRAA, INRF, and other relevant entities). The PSC shall meet at least once a year, and the Project Management Unit (PMU) shall act as the secretariat for the project. The PSC is responsible for taking decisions on the project’s management, including prior approval of work plans, the budget, project revisions, and key objectives, which must receive final UNDP approval through the UNDP-GEF Regional Coordinating Unit. The PSC shall also provide guidance on the project’s technical feasibility and must: 1) ensure coordination with relevant government agencies; 2) lead the program’s implementation process and synchronize the project with national and local planning processes and policies; 3) ensure that activities are fully integrated into other development initiatives on ABS at the national, regional and local levels (e.g. GIZ environmental governance and biodiversity initiative & ABS Capacity Development Initiative); 4) monitor the work done by executing units, follow up on progress made and endorse reports; and 5) oversee the effectiveness of the project’s execution.

The PSC will play a key role in monitoring and evaluating the project by ensuring the quality of activities and outputs, and by conducting evaluations to improve performance, accountability and learning. It will ensure that required resources are committed to the project, arbitrate any conflicts that arise within the project, and is responsible for negotiating and finding solutions to any problems that may occur with external agencies. Based upon the approved work plan, the PSC may consider and approve deviations from initial plans. To ensure UNDP’s ultimate accountability for the project’s results, the decisions of the PSC will be made in accordance with results-based management standards such as best value for money, equity, fairness, integrity, transparency and effective national and international competition.

UNDP is the sole GEF Implementing Agency (IA) for the Project and its duties will be facilitated by independent external assessments, technical and strategic support, and quality monitoring. This will guarantee that management requirements and project milestones are in line with the project’s objectives. The UNDP Country Office (UNDP-CO) will be responsible for: 1) ensuring that the project proceeds towards the expected results; 2) providing financial and audit services to the project; 3) overseeing financial expenditures against project budgets approved by the PSC; 4) carrying out regular monitoring activities, such as periodic site visits; 5) appointing independent financial auditors and evaluators; and 6) ensuring that all activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures.

A UNDP staff member will be assigned responsibility for management and control over project finances.

As the project’s success must be independent from its management, the PSC and UNDP may entrust the PMU with specific responsibilities.

The NPD is responsible for the project’s central management. The Director’s primary duty is to ensure delivery of the expected project outcomes mentioned in the project document, according to quality standards and taking into account time and budgetary constraints. The NPD will lead on and manage strategic issues to ensure the project’s success. Furthermore, the NPD is responsible for reporting progress on implementation to the PSC for assessment by its members.

In addition, the NPD will coordinate directly with UNDP and hold a monthly meeting for regular monitoring of planned activities and associated budgets elaborated in the project’s annual work plan. The NPD may manage the project on behalf of the PSC and will be responsible for decision-making and daily project management. The NPD shall 1) ensure that the overall project management and monitoring is consistent with UNDP rules on managing UNDP/GEF projects; 2) facilitate communication and networking among PMU and technical implementation partners; and 3) organize PSC meetings.

The PMU will be based in Algiers under the NPD’s general direction and undertake day-to-day project management. A national project coordinator, recruited according to UNDP rules, will head the PMU with support from an administrative assistant, a lead technical advisor and external consultants where necessary. The PMU will manage the implementation of all project activities, including 1) the preparation/updating of work plans and budget forecasts, related record-keeping and project accounting responsibilities, and the production of quarterly and annual progress reports; 2) the  drafting of terms of reference, technical specifications and other documents; 3) the identification and pre-screening of consultants for approval by the PSC, coordination and supervision of consultants, sub-contractors and suppliers; 4) organizing duty travel, seminars, public outreach activities and other project events; and 5) maintaining contacts with project partners at the central, regional and local levels.

The PMU is responsible to the DGF, PSC and UNDP for the quality, timeliness and effectiveness of the activities carried out, as well as the proper use of funds. The PMU will produce annual work plans and budgets for approval by the PSC and UNDP. These plans will serve as the basis for resource allocation for planned activities. The PMU will also produce quarterly operational project review/project implementation reports (QPR/PIR) to submit to the PSC and UNDP. These reports will summarize the project’s progress towards expected outcomes and outputs, explaining any discrepancy and detailing necessary adjustments. The QPR/PIR will be the main reporting tool for the project’s activities. The PMU will be provided technical support by duly contracted national and international service providers. All specialized services will be contracted in consultation with UNDP and MADR.

An approved auditor will produce an annual audit of the project in accordance with UNDP rules and regulations.

Management Arrangements Organigram

Tripartite (Outcome Board)

Representative of UNDP

Representative of Ministry of Foreign

Affairs

Representative of Ministry Agriculture and Rural Development

Project Steering Committee

Representatives of MAE, MREE, MESRS, MICL, MPRH, GEF Focal Point, etc

Representatives of INRAA, INRF, CNIAAG, CNRDPA, CRBT, CRSTRA, ENSA, ENSSMAL, ITAFV, ITEDAS, ITELV, ITCMI, etc.

Representative of MARD/DGF (EA) Representative of UNDP (IA)

Project Assurance

UNDP (CO and RCU) as GEF IA

Project Management Unit (PMU)

(Based at DGF)

National Project Director

National Project Coordinator

Lead Technical Advisor

Service providers (e.g. research & technical institutions) sub-contracted to implement specific project activities

Universities, research institutes, business, NGO, associations, local populations, etc.

National and international consultants contracted for specific purposes

## Part 4: Monitoring and Evaluation Framework

Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures and will be provided by the project team and UNDP Country Office (UNDP-CO) with support from the team of the UNDP/GEF Regional Technical Advisor. The strategic results Framework provides performance and impact indicators for the project’s execution along with their corresponding means of verification. The current GEF tracking tool for integrated biodiversity projects will serve as the standard monitoring instrument. The M&E plan includes: an initial report, quarterly and annual reviews, and an independent final evaluation. The following sections outline the main components of the Monitoring and Evaluation Plan and indicative cost estimates related to M&E activities. The project's M&E Plan will be presented and finalized at the Project's Inception Report following a collective fine-tuning of indicators, means of verification, and the full definition of project staff M&E responsibilities.

### Key Monitoring and Evaluation Activities

A Project Inception Workshop (IW) will be conducted within the first two months following signature of the project document with parties that have been assigned a role in the project's organizational structure, the UNDP-CO and, where appropriate, a regional technical advisor or representative from the UNDP-GEF regional unit, as well as other stakeholders. The inception workshop is essential to take ownership of the project's outcomes and prepare the project's first annual work plan. The inception workshop should address a number of important issues:

- Introduce project staff to the UNDP-GEF team which will support the project during its implementation, namely the CO and responsible UNDP-GEF Regional Coordinating Unit staff based in Istanbul;

- Assist all partners in fully understanding and taking ownership of the project. Detailing the roles, supporting services and complementary responsibilities of UNDP-CO and UNDP/GEF-RCU staff towards the NPD, Steering Committee and PMU. Discuss roles, functions and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms;

- The Terms of Reference for project staff and decision-making structures will be discussed, if necessary, in order to clarify the responsibilities of each party during the project's execution phase;

- Review and approval/revision of the results framework (precise and measurable performance indicators, baselines, targets, means of verifications, risks and assumptions), provide additional details if necessary, and upon this exercise finalize the first annual work plan (AWP) in a way that is appropriate with the project's expected outcomes;

- Provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements. The monitoring and evaluation plan must be planned and followed through;

- Financial resources as well as the monitoring and evaluation plan must be agreed and programmed;

- Inform the project team on UNDP’s project related budgetary planning, budget reviews, and mandatory budget restructuring;

- Discuss procedures regarding financial reporting and the annual audit;

- Plan and establish a calendar for the Steering Committee’s meetings. The roles and responsibilities of all project structures should be clarified and meetings scheduled. The first Steering Committee meeting shall be held within 12 months following the inception workshop.

A Project Inception Report (IR) will be prepared immediately following the Inception Workshop. It will include a detailed first year annual work plan divided in quarterly time-frames detailing the activities and progress indicators that will guide implementation during the first year of the project. This work plan should include a calendar of specific field visits, support missions from the UNDP-CO or the Regional Coordinating Unit (RCU) or consultants, as well as time-frames for the meetings of the project's decision making structures. The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the annual work plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 month time-frame. The inception report will include a more detailed account of the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners. In addition, a section will be included in terms of progress regarding the establishment and start-up activities and an update of any changed external conditions that may affect the project’s execution. After finalization, the report will be circulated to project partners who will be given a one-month period to respond with comments or queries. Prior to the IR’s circulation, the UNDP Country Office and UNDP-GEF's regional coordinating unit will review the document.

Quarterly progress report. The national coordinator is responsible for daily monitoring of the project's implementation on the basis of the annual work plan (AWP) indicators. The project team will inform UNDP of any delays or difficulties encountered during implementation so that appropriate support or correctives measures may be provided in a timely manner. Project progress will be monitored through the UNDP Enhanced Results Based Management (ERBM) Platform. Based on the initial risk analysis submitted, a risk log will be regularly updated in ATLAS. Risks become critical when their impact and probability are high. Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically categorized as critical on the basis of their innovative nature (their high and uncertainty combined with the lack of previous experience justifies their categorization as critical). Based on the information recorded in Atlas, quarterly progress reports can be generated in the Executive Snapshot platform. Other ATLAS logs can be used to monitor issues, lessons learned etc. The use of these functions is a key indicator for the UNDP Executive Balanced Scorecard.

Periodic Monitoring through site visits: UNDP CO and UNDP-GEF RCU will conduct visits to project sites to assess with first hand project progress. Other members of the Steering Committee may also join these visits. A field visit Report/BTOR will be prepared by the SC and UNDP RCU and will be circulated among the project team no less than one month after the visit of the Steering Committee.

Annual Project Implementation Reports (PIR): This key report is prepared to monitor progress made since the project’s outset and especially for the previous reporting period (1st July to June 30). The PIR combines both UNDP and GEF in terms of reporting requirements and will be submitted to the GEF once finalized. The PIR includes reporting on:

- Cumulative progress made towards project objective and project outcomes - each with indicators, baseline data and end-of- project targets

- Project outputs delivered per project outcome

- Payments and expenditure reports

- Risk and phased management

- Portfolio level indicators (such as tracking tools for the GEF's focal point) are used by most focal areas on an annual basis as well

The project will undergo an independent Mid-Term Review (MTR) at the mid-point of project implementation. The MTR will determine progress being made toward the achievement of outcomes and will identify course correction if needed. It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management.  Findings of the MTR will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the MTR will be decided after consultation between the parties to the project document. The Terms of Reference for the MTR will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF. The management response and the evaluation will be uploaded to UNDP corporate systems, in particular the UNDP Evaluation Office Evaluation Resource Centre (ERC).  The relevant GEF Focal Area Tracking Tools will also be completed during the mid-term evaluation cycle.

Independent Terminal Evaluation (TE): The TE shall be held six months before the project’s closure, in accordance with UNDP-GEF guidelines. The TE will focus on the delivery of the project's results as initially planned (and as corrected after the mid-term evaluation, if any such correction took place). It will look at project outcomes and their sustainability, including the contribution to capacity development and the achievement of global environmental benefits/goals. The Terms of Reference for the TE will be prepared by the UNDP CO based on guidance and approval from the UNDP/GEF RCU. The TE should also provide recommendations for follow-up activities and requires a management response which should be uploaded to PIMS and to the UNDP Evaluation Office Evaluation Resource Centre (ERC).  Relevant monitoring tools of the GEF focal point will also be completed.

During the project’s last three months, the project team will prepare the Final Project Report. This comprehensive report will summarize the achieved results (objectives, outcomes, outputs), lessons learned, problems encountered and areas where results may not have met expectations. It will also present recommendations for any further steps that may need to be taken in order to ensure sustainability and replicability of the project's results.

The Government will provide UNDP’s Resident Representative with certified periodic financial statements and an annual audit of financial statements on the status of UNDP (including GEF) funds in accordance to established procedures set out in Programming and Finance manuals. The audit will be conducted according to UNDP’s financial regulations, rules, and audit policies by the legally recognized auditor of the Government of Algeria, or by a commercial auditor recruited by the Government of Algeria.

Table 3 - Indicative Monitoring and Evaluation Work Plan and Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Manager - UNDP CO, UNDP GEF | $10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation | Annually prior to ARR/PIR and to the definition of annual work plans |
| PIR | - Project manager and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Evaluation | - Project manager and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Indicative cost: $30,000 | At the mid-point of project implementation. |
| Final Evaluation | - Project manager and team, - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Indicative cost : $30,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and team - UNDP CO - local consultant | $0 / printing costs (PMU expense) | At least three months before the end of the project |
| Audit | - UNDP CO - Project manager and team | Indicative cost per year: $3,000, ($12,000 total) | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST (Excluding project team staff time and UNDP staff and travel expenses) |  | US$ 82,000 |  |

### Learning and knowledge sharing

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyse, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

### Communications and transparency requirements

Full compliance is required with the GEF's Communication and Visibility Guidelines (www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf the "GEF Guidelines"). Amongst other things, the GEF Guidelines explain when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment. The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Full compliance is also required with UNDP's Branding Guidelines (http://intra.undp.org/coa/branding.shtml) and specific guidelines on UNDP logo use (http://intra.undp.org/branding/useOfLogo.html). Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects need to be used. In order to clarify any doubts, the UNDP logo needs to be used alongside the GEF logo. The GEF logo can be accessed at www.thegef.org/gef/GEF_logo and the UNDP logo at http://intra.undp.org/coa/branding.shtml.

## Part 5: Legal Context

This document constitutes a Project Document as referred to in the Standard Basic Assistance Agreement (SBAA) signed between UNDP and the Ministry of Foreign Affairs the 20th of July, 1977.

Consistent with the Article III of the SBAA, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999).

The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# Section II: Strategic Results Framework

| This project will contribute to achieving the following Country Programme Outcome as defined in CPAP or CPD: Outcome 3: By 2020, the living environment and resilience of citizens are improved thanks to sustainable participatory management of natural and urban ecosystems. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CPAP Outcomes/Outputs from CPD: Output 2: The capacity of principal national and local actors is strengthened to implement strategies/plans for the sustainable management of natural and urban ecosystems in order to improve the quality and lifespan of citizens. |  |  |  |  |  |
| Country Programme Outcome Indicator: 2.2 The number of strategies, institutional and legal arrangements and action plans implemented for the conservation of biodiversity |  |  |  |  |  |
| Applicable GEF Strategic Objective and Program: GEF-5 BD-4 Focal Area objective – Build capacity on access to genetic resources and benefit sharing |  |  |  |  |  |
| Applicable GEF Expected Outcomes: Outcome 4.1 “Legal and regulatory frameworks, and administrative procedures established that enable access to genetic resources and benefit sharing in accordance with the CBD provisions” |  |  |  |  |  |
| Applicable GEF Outcome Indicators: Output 4.1 “Access and benefit-sharing agreements that recognize the core ABS principles of Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) including the fair and equitable sharing of benefits.” |  |  |  |  |  |
| Objective/Components of Results | Indicator | Baseline | Targets End of Project | Source of verification | Assumptions |
| Project Objective To consolidate actions to conserve and sustainably use genetic resources and related traditional knowledge in Algeria through the development and implementation of a national strategy and legal and institutional framework on access and benefit sharing (ABS) in line with the CBD and the Nagoya Protocol | Number of new ABS value chains on record with government authorities and academia | None with government, to be defined for academia | 5 new ABS value chains on record with government authorities or academia | Government ABS records, new national and international research papers on ABS; national reports on implementation of the Nagoya Protocol | A climate of mutual trust exists between users and providers of genetic resources which is conducive to the establishment of effective value chains There exists sustained political will and economic interest on the part of providers and users of genetic resources |
|  | Number of valid expressions of interest by 1) users and 2) providers (communities, associations, businesses) of genetic resources to develop ABS agreements in Algeria | Low to moderate level of interest and no expressions of interest on record | 3-5 expressions of interest to develop specific ABS agreements have been deposited with national ABS authorities, by users and/or providers of genetic resources | Government records, university and research centre documents, information submitted to the national ABS clearing house, national reports on the implementation of the Nagoya Protocol. | Sufficient economic interest by users in relation to the country’s genetic resources and their associated potential for eventually developing ABS agreements and value chains; sufficient interest by providers of TK and GR to grow and/or collect or otherwise provide materials with GR and related TK |
|  | Mechanisms for sharing monetary and non-monetary benefits generated through ABS agreements and mechanisms for 1) biodiversity conservation and sustainable use, 2) local populations | None | At least 5 formal benefit sharing structures (national/ local trust funds, community funds, mechanisms for the sharing of results of research, training and infrastructure/ equipment) are reflected in the ABS national framework and have been set up | Government records, university and research centre documents, information submitted to the national ABS clearing house, national reports on the implementation of the Nagoya Protocol. | There is sufficient political will and the sustained interest and capacity of potential users and providers to conclude agreements that can produce monetary and/or non-monetary benefits. |
|  | UNDP IRRF Sub-indicator 2.5.1.A.1.1: Extent to which legal frameworks are in place for conservation, sustainable use, and/or access and benefit sharing of natural resources, biodiversity and ecosystems | The Law on Biological Resources of 2014 has been formally adopted, but a comprehensive legal framework is not in place due to a lack of implementation regulations. | A comprehensive and coherent national legal framework on ABS and the protection of TK has been approved and is established and operational | Draft regulations submitted to the General Secretariat of the Government for consultation and approval; Regulations published in the Official Journal; information submitted to the national ABS CHM; project reports; national reports on implementation of the Nagoya Protocol |  |
| Component/Outcome 1 Developing a national policy, legal and institutional framework to enable the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources. | Outputs associated with Component/Outcome 1 1.1. National legislation on ABS and related issues on intellectual property (IP) and TK prepared and submitted for adoption by the relevant Algerian authority, following national consultations and participatory stakeholder engagement. 1.2. An institutional framework on ABS and traditional knowledge defined and established with supporting sectorial policies and measures enabling implementation of legislation on ABS and TK. 1.3. Formal coordination mechanisms established between in-country institutions having a mandate in the implementation of the national ABS and related TK framework. 1.4. An effective financial mechanism in line with the ABS legal framework established for receiving, on a voluntary basis, a percentage of monetary benefits derived from ABS projects, for redistribution towards the conservation and sustainable use of biodiversity in perpetuity. |  |  |  |  |
|  | Existence of a national policy framework for the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources. | No national policy framework approved by the Government. | Outcome Target 1.1: NBSAP 2.0 with aspects pertaining to ABS is adopted by the Government and used to orient project interventions | Report of GEF project 4987 “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Algeria”. | Project GEF 4987 will conclude in February 2016 with the adoption of a revised NBSAP. |
|  | Existence of a national legal framework for the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources. | The Law on Biological Resources 2014 has been formally adopted, but a comprehensive legal framework does not exist due to the lack of implementing regulations. | Outcome Target 1.2: A comprehensive and coherent national legal framework on ABS and the protection of TK has been approved and is established and operational | Draft regulations submitted to the General Secretariat of the Government for consultation and approval; Regulations published in the Official Journal; information submitted to the national ABS CHM; project reports; national reports on implementation of the Nagoya Protocol | There is sufficient political will and institutional/regulatory capacity to develop and adopt an effective regulatory framework. |
|  | Existence of a national institutional framework for the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources. | The Law on Biological Resources 2014 has been formally adopted, but a comprehensive institutional framework does not exist due to the lack of implementing regulations. | Outcome Target 1.3: A coherent national institutional framework with the necessary capacities and mandates has been approved and is established and operational . | Draft regulations submitted to the General Secretariat of the Government for consultation and approval; Regulations published in the Official Journal; information submitted to the national ABS CHM; project reports; national reports on implementation of the Nagoya Protocol | There is sufficient political will and institutional/regulatory capacity to develop and adopt an effective institutional framework. |
|  | Existence of an effective mechanism for access and benefit sharing and a model ABS agreement | No such mechanism or model agreement | Outcome Target 1.4: An effective ABS mechanism and model ABS agreement have been developed | Government records / official bulletins; information submitted to the national ABS CHM; project reports; national reports on implementation of the Nagoya Protocol | There is sufficient political will and institutional/regulatory capacity to develop and adopt an effective ABS mechanism and a model ABS agreement. |
| Component/Outcome 2. Building and strengthening the capacity of national research and regulatory institutions to apply ABS rules and principles. | Outputs associated with Component/Outcome 2 2.1. Knowledge, attitudes and practices (KAP) surveys undertaken to assess awareness about the national ABS legal and institutional framework and the CBD and Nagoya Protocol, amongst specific groups that may use or benefit from ABS transactions (e.g. relevant researchers, local populations and industry players). 2.2. Targeted training conducted for 100 representatives of national ABS competent authority, ABS/CBD focal points and agencies with complementary functions, regarding: key obligations under the Nagoya Protocol, ABS access applications, negotiating ABS agreement, defining scope and application of regulations, and implementing compliance mechanisms and monitoring activities (e.g. for bioprospecting projects or value chains). 2.3. A national communication and engagement strategy and campaign on the national ABS framework and bioprospecting and value-chains undertaken targeting key stakeholders. 2.4. Stakeholder-targeted manuals and training modules developed and implemented on the national ABS legal and institutional framework (ABS procedures for users and providers of genetic resources, PIC protocols, ABS agreement negotiation strategies, ABS-related IP, customary law, bioprospecting and research procedures, etc.). 2.5. ABS model agreement(s) that facilitate the negotiation of monetary (i.e. upfront payments and royalties) and non-monetary (i.e. training/ research opportunities) benefits between users and providers of genetic resources developed and adapted to national needs and circumstances. 2.6. Database(s) compiled on a) existing and emerging projects, including users and providers of genetic resources and its associated traditional knowledge (i.e. institutions, private sector and local populations); and b) ex-situ collections of genetic resources of Algerian origin. |  |  |  |  |
|  | Change in capacity within competent agencies and by other stakeholders on the subject of the content and principal requirements of the Nagoya Protocol and its scope of application, measured by the UNDP and GEF ABS Tracking Tools | GEF ABS Tracking Tool: 13 UNDP ABS Tracking Tool: 11 | Outcome Target 2.1: Improvement of at least 50% of the capacity of existing or new competent national authorities on ABS | Project reports, GEF and UNDP Tracking Tools | Stakeholders have a sustained interest in ABS and in advancing the implementation of the Nagoya Protocol. Improved understanding and capacity on ABS will lead to the adoption of actions that support the effective implementation of the Nagoya Protocol in Algeria. |
|  | Percentage of researchers, local authorities and industry, representatives of local populations aware of of the regulatory and institutional framework pertaining to ABS and TK and its different dimensions | None | Outcome Target 2.2: 80% of relevant national stakeholders are informed of the regulatory and institutional framework pertaining to ABS and TK and its different dimensions. | KAP surveys | Stakeholders are inclined to fill out KAP surveys and provide accurate responses |
|  | Number of potential bioprospecting projects | None | Outcome Target 2.3 At least 5 bioprospecting projects have been identified by project end. | Government records / official bulletins; information submitted to the national ABS CHM; project reports; national reports on implementation of the Nagoya Protocol. | Resources and capacities are deployed as predicted. |

# Section III: Total Budget and Work Plan

### Total Budget and GEF Work Plan

| ATLAS Project Award ID: | 00093558 | GEF project ID: | 5808 |
| --- | --- | --- | --- |
| ATLAS Project ID: | 00086265 | UNDP project ID: | 5311 |
| Business Unit: | DZA10 |  |  |
| Project Title: | Developing a national strategy and legal and institutional framework on access to genetic resources and related benefit sharing and traditional knowledge in line with the CBD and its Nagoya Protocol in Algeria |  |  |
| Implementing partner: | Ministry of Agriculture and Rural Development/ DGF |  |  |

| GEF Component (result) / Atlas Activity | Donor Name | Fund ID | Responsible Party / Implementing Agent | Atlas Budgetary Account Code | Atlas Budget Description | Total Amount (USD) | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1 – Developing a national policy, legal and institutional framework to enable the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources. | GEF-TF | 62000 | MADR/DGF | 71200 | International Consultants | 198,000 | 45,000 | 54,000 | 45,000 | 54,000 | 1 |
|  | GEF-TF | 62000 | MADR/DGF | 71300 | National Consultants | 237,000 | 56,250 | 62,250 | 56,250 | 62,250 | 2 |
|  | GEF-TF | 62000 | MADR/DGF | 72100 | Contractual Services -Companies | 172,500 | 48,125 | 41,459 | 41,458 | 41,458 | 3 |
|  | GEF-TF | 62000 | MADR/DGF | 71600 | Travel | 112,500 | 28,125 | 28,125 | 28,125 | 28,125 | 4 |
|  | GEF-TF | 62000 | MADR/DGF | 71400 | Contractual Services – Individ. | 180,000 | 45,000 | 45,000 | 45,000 | 45,000 | 5 |
|  | GEF Comp 1 | 62000 |  |  |  | 900,000 | 222,500 | 230,834 | 215,833 | 230,833 |  |
|  | Government Comp 1 |  |  |  |  | 2,000,000 | 500,000 | 500,000 | 500,000 | 500,000 |  |
|  | Sub-total Cofinancing Component 1 |  |  |  |  | 2,000,000 | 500,000 | 500,000 | 500,000 | 500,000 |  |
|  | SUB-TOTAL Component 1 |  |  |  |  | 2,900,000 | 722,500 | 730,834 | 715,833 | 730,833 |  |
| Component 2 – Building and strengthening the capacity of national research and regulatory institutions to apply ABS rules and principles | GEF-TF | 62000 | MADR/DGF | 71200 | International Consultants | 178,000 | 40,000 | 49,000 | 40,000 | 49,000 | 1 |
|  | GEF-TF | 62000 | MADR/DGF | 71300 | National Consultants | 212,000 | 50,000 | 56,000 | 50,000 | 56,000 | 2 |
|  | GEF-TF | 62000 | MADR/DGF | 72100 | Contractual Services-Companies | 193,636 | 53,409 | 46,743 | 46,742 | 46,742 | 3 |
|  | GEF-TF | 62000 | MADR/DGF | 71600 | Travel | 100,000 | 25,000 | 25,000 | 25,000 | 25,000 | 4 |
|  | GEF-TF | 62000 | MADR/DGF | 71400 | Contractual Services – Individ. | 180,000 | 45,000 | 45,000 | 45,000 | 45,000 | 5 |
|  | GEF Comp 2 | 62000 |  |  |  | 863,636 | 213,409 | 221,743 | 206,742 | 221,742 |  |
|  | Government Comp 2 |  |  |  |  | 2,884,320 | 721,080 | 721,080 | 721,080 | 721,080 |  |
|  | Sub-total Cofinancing Component 2 |  |  |  |  | 2,884,320 | 721,080 | 721,080 | 721,080 | 721,080 |  |
|  | SUB-TOTAL Component 2 |  |  |  |  | 3,747,956 | 934,489 | 942,823 | 927,822 | 942,822 |  |
| Project Management | GEF-TF | 62000 | MADR/DGF | 71400 | Contractual Services – Individ | 64,000 | 16,000 | 16,000 | 16,000 | 16,000 | 6 |
|  | GEF-TF | 62000 | MADR/DGF | 72100 | Contractual Services-Companies | 20,000 | 5,000 | 5,000 | 5,000 | 5,000 | 7 |
|  | GEF-TF | 62000 | MADR/DGF | 72400 | Acquisition of audio-visual & communication Equip | 30,000 | 15,000 | 5,000 | 5,000 | 5,000 | 8 |
|  | GEF-TF | 62000 | MADR/DGF | 74500 | Miscellaneous Expenses | 8,705.18 | 2,176.30 | 2,176.30 | 2,176.29 | 2,176.29 | 9 |
|  | GEF-TF | 62000 | MADR/DGF | 74598 | UNDP Direct Project Costs | 53,658.82 | 13,414.70 | 13,414.70 | 13,414.71 | 13,414.71 | 10 |
|  | GEF | 62000 | MADR/DGF |  |  | 176,364 | 51,591 | 41,591 | 41,591 | 41,591 |  |
|  | UNDP | 04000 | MADR/DGF | 71400 | Contractual Services - Individ | 140,000 | 35,000 | 35,000 | 35,000 | 35,000 | 11 |
|  | UNDP | 04000 | MADR/DGF | 71600 | Travel | 32,000 | 8,000 | 8,000 | 8,000 | 8,000 | 12 |
|  | UNDP | 04000 | MADR/DGF | 72200 | Office Furniture | 8,000 | 5,000 | 1,000 | 1,000 | 1,000 | 13 |
|  | UNDP | 04000 |  |  |  | 180,000 | 48,000 | 44,000 | 44,000 | 44,000 |  |
|  | GOVERNMENT |  |  |  |  | 220,000 | 55,000 | 55,000 | 55,000 | 55,000 |  |
|  | Sub-total Project Management Cofinancing |  |  |  |  | 400,000 | 103,000 | 99,000 | 99,000 | 99,000 |  |
|  | SUB-TOTAL Project management |  |  |  |  | 576,364 | 154,591 | 140,591 | 140,591 | 140,591 |  |
|  | Total GEF |  |  |  |  | 1,940,000 | 487,500 | 494,168 | 464,166 | 494,166 |  |
|  | Total UNDP |  |  |  |  | 180,000 | 48,000 | 44,000 | 44,000 | 44,000 |  |
|  | Total GOVERNMENT |  |  |  |  | 5,104,320 | 1,276,080 | 1,276,080 | 1,276,080 | 1,276,080 |  |
|  | Total Cofinancing |  |  |  |  | 5,284,320 | 1,324,080 | 1,320,080 | 1,320,080 | 1,320,080 |  |
|  | Total budget - Project |  |  |  |  | 7,224,320 | 1,811,580 | 1,814,248 | 1,784,246 | 1,814,246 |  |

### Budget Notes

| Budget Notes | Explanation |
| --- | --- |
| 1 | International project consultants (125 weeks of short-term expertise at a rate of $3,000 US/week). There are five proposed experts and information on the profile for each expert is shown in the table “Project Staff and Consultants”. This includes $36,000 for the recruitment of one international expert consultant on project evaluation for two evaluation teams (mid-term and final) for the project |
| 2 | National project consultants (224 weeks of short-term expertise at a rate of $2 000 US/week). There are twelve proposed consultants and information on the profile for each expert is shown in the table “Project Staff and Consultants”. This includes $24,000 for the recruitment of one national expert consultant on ABS and biodiversity for two evaluation teams (mid-term and final) for the project |
| 3 | Commercial contractual services are provided for in the budget with $366,136 available for consultations, training, and conferences, as well as all other services required by the project activities, including $10,000 for the inception workshop. |
| 4 | Travel: A sum of $212,500 has been earmarked for travel for national and international consultants as well as the project team (director, coordinator and technical advisor) for both components of the project. Part of this sum is reserved for exchange missions in countries with advanced experience with ABS. |
| 5 | Contractual services in support of the work program on capacity development, advise on management and coordination to formulate regulations under the Biological Resources Law. A budget of $360,000 is proposed for 6 resource persons, 3 supporting each component (component 1 & 2). |
| 6 | Contractual services for the project's coordinator, lead technical advisor and administrative/financial assistant, a total of $64,000 of GEF funds, supplemented by UNDP funding (see note 11). |
| 7 | Contractual services from companies have been provided for up to $20,000 for: 1) audit and control related costs; 2) communication fees; 3) costs of printing and copying various documents. |
| 8 | An amount of $30,000 has been provided to acquire information technology, communication and audio-visual equipment, for phone charges, etc. |
| 9 | Miscellaneous: A sum of $8,705.18 has been attributed under “Miscellaneous” for the entire project. The precise cost of some ground activities is difficult to anticipate. Miscellaneous expenses will cover for additional expenses of the project where necessary. |
| 10 | UNDP Direct Project Costs: $53,658.82 has been attributed to cover UNDP DPC for financial, human resources, purchasing, travel, general administration, and revenue management service costs |
| 11 | UNDP will provide $140,000 toward contractual services for the project's coordinator, lead technical advisor and administrative/financial assistant (see budget note 6) |
| 12 | UNDP will provide up to $32,000 for travel costs associated with project management responsibilities |
| 13 | UNDP will provide an $8,000 budget to purchase furniture for the project management unit. |

### Overall Project Financing (USD)

| GEF Component (result)/ Atlas Activity | Donor Name | Total Amount (USD) | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| Component 1: Developing a national policy, legal and institutional framework to enable the implementation of the Nagoya Protocol and the conservation and valuation of genetic resources. | GEF | $900,000 | $222,500 | $230,834 | $215,833 | $230,833 |
|  | GOVERNMENT | $2,000,000 | $ 500,000 | $500,000 | $500,000 | $500,000 |
|  | TOTAL COST – Component 1 | $2,900,000 | $722,500 | $730,834 | $715,833 | $730,833 |
| Component 2: Building and strengthening the capacity of national research and regulatory institutions to apply ABS rules and principles. | GEF | $863,636 | $213,409 | $221,743 | $206,742 | $221,742 |
|  | GOVERNMENT | $2,884,320 | $721,080 | $721,080 | $721,080 | $721,080 |
|  | TOTAL COST - Component 2 | $3,747,956 | $ 934,489 | $ 942,823 | $ 927,822 | $ 942,822 |
| Project Management Unit | GEF | $176,364 | $51,591 | $41,591 | $41,591 | $41,591 |
|  | UNDP | $180,000 | $48,000 | $44,000 | $44,000 | $44,000 |
|  | GOVERNMENT | $220,000 | $55,000 | $55,000 | $55,000 | $55,000 |
|  | TOTAL COST – Project Management | $576,364 | $156,591 | $139,925 | $139,924 | $139,924 |
| Overall Total | GEF | $1,940,000 | $487,500 | $494,168 | $464,166 | $494,166 |
|  | UNDP | $180,000 | $48,000 | $44,000 | $44,000 | $44,000 |
|  | GOVERNMENT | $5,104,320 | $1,276,080 | $1,276,080 | $1,276,080 | $1,276,080 |
|  | TOTAL CO-FINANCING | $5,284,320 | $1,324,080 | $1,320,080 | $1,320,080 | $1,320,080 |
|  | OVERALL TOTAL PROJECT | $7,224,320 | $1,811,580 | $1,814,248 | $1,784,246 | $1,814,246 |

# Section IV: Additional Information

## Part 1: Other Agreements

### GEF focal point Endorsement Letter

### Co-financing letter from the Government of Algeria

### Letter of Agreement between UNDP and the MADR of Algeria

### Co-financing letter from UNDP

## Part 2: Risk Analysis

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Management response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Low participation and involvement of government staff and public officials may impede project implementation | 12/05/2014 | Political | Were this risk to occur, the potential effect would thwart both aspects of the project. P = 1 I = 5 | Providing targeted training to government agencies involved in ABS issues will engage officials from the competent authorities and other related agencies. This will increase the depth of experience and skills available and the commitment to the project and future ABS work. | UNDP | UNDP in PIF, International Consultant for PRODOC | 03/05/2015 | No change |
| 2 | Difficulties and delays in adopting the national regulatory framework on ABS and protection of traditional knowledge. | 12/05/2014 | Regulatory | Were this risk to occur, the potential effect would be to thwart the project outcomes P = 1 I = 5 | The project will conduct extensive consultation and advocacy campaigns with stakeholders to create awareness and political will to undertake the required steps to develop a national ABS/traditional knowledge regulatory and institutional framework. This will also help to provide information to decision-makers and other stakeholders to help them understand the importance of the framework and the Nagoya Protocol. The project will conduct a series of consultations, awareness raising activities and seminars to inform about the potential and advantages of having an ABS framework. | UNDP | UNDP in PIF, International Consultant for PRODOC | 03/05/2015 | No change |
| 3 | Stakeholders are not interested in the project and/or not committed to participating in its activities. | 12/05/2014 | Organizational | Were this risk to occur, it would compromise the ability to meet project objectives P = 1 I = 5 | Methods for engagement of actors and stakeholders will vary. In the case of government officials, high level requests to participate and the selection of suitable venues for training are important. For local populations measures will be developed focused on a new set of ABS-related livelihood opportunities ensuring interest. In the case of the private sector, highlighting values and business opportunities can also play a role. | UNDP | UNDP in PIF, International Consultant for PRODOC | 03/05/2015 | No change |
| 4 | Adequate cash financing not obtained in budget bill | 03/05/2015 | Financial | Were this risk to occur, it would compromise the ability to achieve project objectives P = 1 I = 5 | Partners at the DGF have requested that the project be included in the budgets for fiscal years 2016-2020 and have the support of the Department. | UNDP | International Consultant, National Consultants | 03/05/2015 | No change |
| 5 | Continuing loss of biodiversity | 03/05/2015 | Environmental | Were this risk to occur, it would reduce genetic diversity, thus thwarting the goal of sharing the benefits of access to genetic resources by reducing the resources available P = 2 I = 5 | Support the government in implementing the ABS provisions of the Law Biological Resources to ensure that financial resources are available to combat biodiversity loss | UNDP | International Consultant, National Consultants | 03/05/2015 | Increasing |
| 6 | Serious adverse impacts of climate change on Algeria’s biodiversity | 03/05/2015 | Environmental | This will occur and will reduce genetic diversity and compromise ecosystems, impeding the goal of sharing the benefits of access to genetic resources by reducing the resources available P = 3 I = 5 | Support the government in implementing the ABS provisions of the Law on Biological Resources to ensure that financial resources are available to combat biodiversity loss. Focus on supporting the completion of a national gene bank to ensure that GR are preserved despite the impacts of climate change. | UNDP | International Consultant, National Consultants | 03/05/2015 | Increasing |

## Part 3: Terms of Reference for Project Personnel

The following provide indicative ToR for project personnel. The project will be supervised by the National Project Director and will be staffed by a full-time National Project Coordinator, a full-time technical counsellor, and a financial and administrative assistant, which will be nationally-recruited positions. The ToRs for further staff, consultants and sub-contractors will be further discussed with UNDP and (further) developed before and during the Inception Workshop so that roles and responsibilities and UNDP-GEF reporting procedures are clearly defined and understood, together with selection and hiring procedures.

### List of Project Personnel and Consultants

| Staff | Designation | Salary / Month (USD) | Units | Main role (See below for ToR) |
| --- | --- | --- | --- | --- |
| Project Management Unit (PMU) |  |  |  |  |
| National Project Director | DNP | Unpaid | 48 | Overall administration of the project, including obligations relating to project management and financing. Supervision of the overall preparation of the project's two components and of consultations with stakeholders. Responsible for timely elaboration and finalization of the project's objectives. |
| National Project Coordinator | CNP | $2500/month | 48 | Coordination of the day-to-day administration of the project, including obligations relating to project management and financing. Coordination of the overall preparation of the project’s two components and consultations with stakeholders Responsible for coordinating the timely elaboration and finalization of the project’s objectives |
| Lead Technical Advisor | CTP | $3000/month | 12 | Responsible for technical support relating to the elaboration and finalization of the project’s objectives. |
| Administrative and Financial Assistant | A-UGP | $1000/month | 48 | Support administrative and financial management within the Project Management Unit (PMU) |
| International Consultants (320,000) |  |  |  |  |
| International expert on national and international implementation of the Nagoya Protocol | EI1 | $3000/week | 36 | Provides high-level assistance through consulting and capacity reinforcement services for the implementation of a regulatory and institutional framework adapted at country level. |
| International Lawyer specializing in intellectual property rights in relation to ABS | EI2 | $3000/week | 16 | Contributes to the team responsible for preparing the regulatory framework, focusing on the specificities of intellectual property rights regarding GR and sui generis protection of Traditional Knowledge. |
| International expert on the implementation of the Nagoya Protocol in relation to the international private sector | EI3 | $3000/week | 25 | Acts as a contact person to work as an intermediary with the international private sector, for technical assistance to international companies represented in Algeria in the implementation of the Nagoya Protocol and ABS. |
| International governance and inter-institutional coordination expert, as well as on developing organizational strategies on biodiversity and genetic resources | EI4 | $3000/week | 16 | Provides technical assistance to the team responsible for legal and institutional aspects, through the provision of advice in organizational strategies. Ensures the incorporation of the Nagoya Protocol on ABS and related international instruments into national law. |
| International expert on communication and public awareness regarding ABS | EI5 | $3000/week | 20 | Develop a national communication strategy and awareness on ABS, with a list of topics, calendar, activities, assessment tools, and of a list of target-groups. Advice and support the coordinator to promote the project's results. |
| National consultants (425 000) |  |  |  |  |
| National legal expert on environmental law, biodiversity and ABS | EN1 | $2000/week | 30 | Assumes a role of coordination and contact person for the implementation of an appropriate regulatory and institutional framework for implementation of the Nagoya Protocol. Lead author of the draft regulations implementing the Law on Biological Diversity 2014 in collaboration with other national and international consultants. |
| National expert on inventory and protection of traditional knowledge associated with genetic resources | EN2 | $2000/week | 16 | Plays a key part in the team of consultants with regard to the role and rights of local populations, for the protection of traditional knowledge associated with genetic resources in the context of ABS. |
| National expert on GR and dialogue with national research institutions | EN3 | $2000/week | 26 | Plays a key part in the team of consultants with regard to documentation of existing genetic resources in Algeria. Works closely with specialized national contact persons on categories of GR (agricultural, wild plants, marine, domestic fauna, wild animals, microorganisms, etc.). Provides relevant technical and scientific information to legal experts and to expert interacting with the private sector. Takes on a coordination role and resource person for the project's planned training activities on GR. |
| National expert on economic valorisation of biodiversity and genetic resources | EN4 | $2000/week | 15 | Performs specific tasks for developing a mid-term mobilization plan of endogenous and exogenous financial resources to implement the national ABS framework, and a promoting/commercialization strategy of products derived from biodiversity and genetic resources, for the purpose of valorisation and economic development, as well as a support plan to cooperatives and production associations with a potential role for ABS systems. |
| National expert on organization and animation workshops with local populations | EN5 | $2000/week | 15 | Resource person for consultations with representatives of local populations and NGOs, to reflect their expectations and propose appropriate measures to strengthen the capacity of civil society and LCs, with particular emphasis on the role of women in relation to ABS. Also acts as a moderator during meetings in the domain of capacity building for local populations regarding the ABS negotiation process. |
| National expert on education and public awareness for biodiversity and ABS | EN6 | $2000/week | 35 | Participates in the elaboration of the national communication strategy and awareness on ABS, in collaboration with the international consultant responsible for PR. Following the strategy's definition, he takes charge of the effective implementation of activities as defined in the output on public awareness. Responsible for activities related to the assessment of knowledge, skills and practices (KAP) targeting specific groups and aiming at assessing the impact of public awareness campaigns on Law on Biological Resources 2014, CBD and Nagoya Protocol. |
| National expert on information and database management related to GR and associated TK | EN7 | $2000/week | 15 | Design and delivery of the ABS database Management System (DBMS), suited for each type of record and according to needs of use, in cooperation with the project coordinator and the focal point for ABS and the CHM. |
| National expert on inventory and valorisation of forest genetic resources and MAP | EN8 | $2000/week | 20 | Works closely with the national expert on genetic resources management (EN3). His role will be to prepare and analyse data (databases) on the identification component of forest GR and MAP GR that may be subject to valorisation under the ABS framework. Assumes a contact person role for this type of GR and provides expertise in training workshops on those GR. |
| National expert on inventory and valorisation of RG for food and agriculture | EN9 | $2000/week | 10 | Preparation and data analysis (databases) on the identification component of genetic resources for food and agriculture that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. |
| National expert on inventory and valorisation of marine GR | EN10 | $2000/week | 10 | Preparation and data analysis (databases) on the identification component of marine genetic resources that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. |
| National expert on inventory and valorisation of GR wild and domestic animal genetic resources | EN11 | $2000/week | 10 | Preparation and data analysis (databases) on the identification component of genetic resources for wild and domestic animals that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. |
| National expert on inventory and valorisation of GR and microorganisms. | EN12 | $2000/week | 10 | Preparation and data analysis (databases) on the identification component of genetic resources for microorganisms that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. |

### Context for the Terms of Reference (standard for all posts)

The Government of Algeria seeks to pilot a project aiming at the elaboration of a national strategy and a legal and institutional framework on access to genetic resources and the fair and equitable sharing of benefits resulting from their utilization and associated traditional knowledge in like with the Convention on Biological Diversity (CBD) and its Nagoya Protocol in Algeria. The project benefits from funds provided by the GEF, with UNDP co-financing, and from the Algerian Government. Due to its size and geographical location, Algeria is an important country in terms of ecosystem and species diversity, which can make a country attractive for bioprospecting. This provides the potential to explore to create new wealth and favour development, in conformity with the new national strategy for biological diversity. Article 15 of the Convention on biological diversity seeks to define international law with regards to the relationship between suppliers and users of biological and genetic resources through a system of Access and Benefit-sharing (ABS). This regime is an opportunity to considerably strengthen the objectives and measures for the protection and conservation of biodiversity and its sustainable use, by allowing the creation of new capital flows and additional resources. Yet, Algeria does not currently have a functional regulatory and institutional framework governing the sustainable use, conservation and benefit sharing of biodiversity. In 2014, the Law on Biological Resources was adopted, but the absence of a national regulatory framework on ABS has left a wide range of opportunities untapped, namely benefit-sharing. It is therefore necessary that an efficient ABS regime be developed in close consultation with stakeholders in order to facilitate access to genetic resources and allow the fair sharing of revenues derived from their sustainable use and benefit both biodiversity and the suppliers of those resources. The development of such a framework requires harmonizing current legal and regulatory instruments in the field of genetic and biological resources. This framework must comply and be compatible with the CBD and the Nagoya Protocol, it must consider other relevant international processes, and also be coupled with the necessary backing in order to strengthen national capacities in various fields, for an efficient implementation at national and local levels. The development of a legal and institutional framework requires the implementation of the Law on Biological Resources 2014 through the adoption of regulations and establishment of institutions, and harmonisation with existing legal and regulatory instruments pertaining to genetic and biological resources. The framework should be compatible with the CBD and its Nagoya Protocol, taking into account other pertinent international processes, and must also be coupled with the support necessary to build national capacities in various areas, in order to ensure efficient implementation at the national and local levels. This is the context in which this UNDP-GEF project has been launched. Its objective is to consolidate actions for the conservation and sustainable use of genetic resources and associated traditional knowledge in Algeria through the development and implementation of a national strategy and legal and institutional framework on access and benefit sharing (ABS) in line with the CBD and the Nagoya Protocol. To achieve its objectives, the project will work based on the following two components: 1. Developing a national policy and legal and institutional framework 2. Creating and strengthening the capacity of national institutions The General Forest Authority, based in the Ministry of Agriculture and Rural Development, in partnership with UNDP Algeria, is recruiting a qualified candidate for the post mentioned below. The renewal of the one-year contract will be based on performance and a positive evaluation of the results of the candidate. The conditions of employment will vary depending on the position.

### National Project Director (DNP)

| Location: | Algiers, Algeria |
| --- | --- |
| Application deadline: | 30 days after publication |
| Category | Environment |
| Type of contract: | Service contract |
| Languages required: | Arabic and French. English desirable. |
| Starting date | As soon as possible |
| Duration of initial contract: | One year (renewable) |
| Expected duration of assignment: | 48 months a priori (if funding allows) |

Tasks and responsibilities

- The National Project Director, under the authority of the Project Steering Committee (PSC), will have management tasks (50%) and technical tasks (50%) - Objectives - Administration of the project, including management responsibilities linked to project management and financing. - Supervise the overall process of implementing the two components of the project as well as stakeholder consultations - Be responsible for the finalization of the objectives aimed for by the project with the established timelines - Main Management Tasks - Ensuring that the project objective, outcomes, outputs and activities are undertaken in the established timeline and in an appropriate manner. - Develop detailed work plans and detailed budgets (including descriptions of activities and a timeline), and submit them to the PSC and the UNDP Country Office for approval. - Liaise with national and international organizations, and other relevant partners that may contribute to the project's objectives; - Ensure timely submission of progress reports in accordance with instructions from the steering committee and UNDP; - Liaise with all other initiatives and programs with outcomes and outputs that match the project's objective - All others project related tasks entrusted by the steering committee Main technical tasks: - Lead the team of consultants involved in the ABS project and bear overall responsibility for timely preparation and delivery of documents to UNDP and GEF, strictly respecting schedules and applying quality control protocols. - Ensure that the launch meeting leads to the delivery of a clear road map on the scope of services and project tasks to be undertaken under the supervision of key implementing partners and UNDP technical staff. - Submit revised preliminary versions of all studies and reports on ABS project activities for reviewing and finalization to key implementing partners, national consultants, and UNDP technical staff. - Lead the development of the project's technical work plan and coordinate consultants' contributions and output, and ensure quality control of technical deliverables. - Ensure delivery of results and implementation according to approved work plans. - Develop a comprehensive mapping and implementation plan of executing partners towards the project's activities. - Play a driving role in the implementation of the CHM. - Prepare the project's monitoring reports, and more specifically the short PIR, risk log, final report, and report on lessons learned.

### National Project Coordinator (NPC)

| Location: | Algiers, Algeria |
| --- | --- |
| Application deadline: | 30 days after publication |
| Category | Environment |
| Type of contract: | Service contract |
| Languages required: | Arabic and French. English desirable. |
| Starting date (Date when candidate is expected to start) | As soon as possible |
| Duration of initial contract: | One year (renewable) |
| Expected duration of assignment: | 48 months a priori (if funding allows) |

Tasks and responsibilities

- The National Project Coordinator, under the authority of the Project Steering Committee (PSC), will only have management tasks (100%). - Objectives - Assist the National Project Director (NPD) in the exercise of his/her functions according to the procedures established by the NPD (see mandate for NPD) - Main Management Tasks - Coordinate the work of the team tasked with preparing and revising work plans and financial programmes, ensure the submission of financial reports, quarterly progress reports, the annual report and other reports within the expected timelines - Develop ToR for contractual services companies, consultants, experts, and all necessary project documents in liaison with the NPD and UNDP; - Facilitate, guide and oversee consultants' works, and endorse deliverables in liaison with the PSC and other relevant bodies; - Contribute to organize project activities when necessary. This may include planning meetings, local and national workshops, field visits and other project related activities; - Coordinate the development and implementation of an agreed training programme for personnel with the goal strengthening collaborative management capacities and competencies on the subject of ABS. - Regularly organizes training workshops, field studies and consultations with different country actors, and provide all support necessary for these activities - Contribute to the creation of a Secretariat in order to provide services to the PSC and tripartite review meetings. - Provide operational support to UNDP-GEF missions, notably in the framework of programmed independent evaluations. - Keep records of PSC meetings, decisions, actions, etc; - Coordinate with other initiatives and programmes which have results and outcomes related to the objectives of this project - All others project related tasks entrusted by the steering committee.

Competencies/Qualifications

Core qualifications - Efficient communication skills (orally and in writing), in order to transmit complex technical information to both technical staff and the general public; - Good leadership, coordination and facilitation skills; - Good knowledge of environmental issues in Algeria; - Proven ability to draft project documents (publications, reports and related documents); - Proven ability to collect, verify and analyse information, as well as to finalize and present research with a high degree of accuracy and technical quality; - Good knowledge and understanding of decisions and processes related to the CBD and Nagoya Protocol; - Previous experience in the development of ABS strategies is an asset. Additional skills: - Negotiates effectively in difficult situations; - Focuses and achieves project goals, persuading and convincing others, working with them; - Ability to effectively coordinate a large multi-disciplinary team of experts and consultants; - Facilitates and chairs meetings effectively and efficiently, and resolves conflict as they arise; - Sets priorities, produces quality outputs, meets deadlines and manages time efficiently; - Shares knowledge and is willing to provide support to others who request advice or help; - Works toward creative solutions by analysing problems carefully and logically; - Demonstrates sufficient technical knowledge to perform effectively in his own specialty; - Inspires and supports the team's decisions; - Maintains strong relationships with partners and clients; - Ability to work in multicultural environments; - Good interpersonal skills and the ability to work in a multicultural setting, with experience working with partners at all levels (ministries, donors, the private sector, NGOs and grassroots community organizations). Experience required: - Advanced university degree preferably advanced (master or doctoral degree) in natural, environmental sciences, economic or social, or management; - At least 5 years of experience in managing national or international projects - at least 3 in a management position - in the field of policy or management of biodiversity and genetic resources; - Solid monitoring and evaluation competencies; - Previous experience of work with GEF projects is a considerable asset; - Excellent command of Arabic and French. Working knowledge in English is an asset.

### Lead Technical Advisor

| Location: | Algiers, Algeria |
| --- | --- |
| Application deadline: | 30 days after publication |
| Category | Environment |
| Type of contract: | Service contract |
| Languages required: | Arabic and French. English desirable. |
| Starting date | As soon as possible |
| Duration of initial contract: | One year (renewable) |
| Expected duration of assignment: | 12 months (3 months/annum) a priori (if funding allows) |

Tasks and responsibilities

The lead technical advisor, working under the National Project Director (NPD) and National Project Coordinator (NPC) will have purely technical tasks (100%) - Objectives - Provide technical support to project activities and quality control to project interventions; - Ensure general coordination and supervision of the technical support team, participate if necessary to the work of each team member and oversee the elaboration of corresponding reports; Main technical tasks: - Direct the team of other consultants involved in the ABS project and assume overall responsibility for the elaboration of technical project documents for submission to the UNDP and GEF, strictly respecting timelines and ensuring quality control. - Ensure that the launch meeting leads to the delivery of a clear road map on the scope of services and project tasks to be undertaken under the supervision of key implementing partners and UNDP technical staff. - Lead the development of the project's technical work plan and coordinate consultants' contributions and output, and ensure quality control of technical deliverables. - Ensure delivery of results and implementation according to approved work plans. - Identify implementation partners for the execution of project activities and elaborate a global work plan. - Provide technical support in the preparation of project evaluation reports, most notably the abridged PIR, the risk log, the final report and reports on lessons learned

Competencies/Qualifications

Core qualifications: - Efficient communication skills (orally and in writing), in order to transmit complex technical information to both technical staff and the general public; - Good leadership, coordination and facilitation skills; - Good knowledge of environmental issues in Algeria; - Proven ability to draft project documents (publications, reports and related documents); - Proven ability to collect, verify and analyse information, as well as to finalize and present research with a high degree of accuracy and technical quality; - Good knowledge and understanding of decisions and processes related to the CBD and Nagoya Protocol; - Previous experience in the development of ABS strategies is an asset. Additional skills: - Negotiates effectively in difficult situations; - Focuses and achieves project goals, persuading and convincing others, working with them; - Sets priorities, produces quality outputs, meets deadlines and manages time efficiently; - Shares knowledge and is willing to provide support to others who request advice or help; - Works toward creative solutions by analysing problems carefully and logically; - Demonstrates sufficient technical knowledge to perform effectively in his own specialty; - Inspires and supports the team's decisions; - Maintains strong relationships with partners and clients; - Good interpersonal skills and the ability to work in a multicultural setting, with experience working with partners at all levels (ministries, donors, private sector, NGOs and grassroots community organizations). Experience required: - Advanced university degree preferably advanced (master or doctoral degree) in natural or environmental sciences; - At least 10 years of experience in the field of policy or management of biodiversity and genetic resources; - Solid monitoring and evaluation competencies; - Previous experience of work with GEF projects is a considerable asset; - Excellent command of Arabic and French. Working knowledge in English is an asset.

### Financial and Administrative Assistant

| Location: | Algiers, Algeria |
| --- | --- |
| Application deadline: | 30 days after publication |
| Category | Environment |
| Type of contract: | Service contract |
| Languages required: | Arabic and French. English desirable. |
| Starting date | As soon as possible |
| Duration of initial contract: | One year (renewable) |
| Expected duration of assignment: | 48 months a priori (if funding allows) |

Duties and Responsibilities

The Administration and Finance Assistant will be working under the full guidance of the National Project Coordinator (NPC). Main Tasks: - Participate in the project's day-to-day administrative and financial management within the Project Management Unit (PMU). - Prepare accounting documents, payment and advance requests, and financial reports. - Collection and classification of project data and information. - Contributing to monitoring the programming, budgeting and overall time frame of the project and the identification of bottlenecks. - Maintenance and regular update of databases developed under the ABS project, including those on registered agreements on access and benefit sharing from the utilization of GR and associated TK; to major in situ and ex situ collections of genetic resources existing in Algeria, to the list of national ABS experts; - Contribution to the project's communication activities. - Participation and organization of project follow-up meetings and drafting of minutes. - Participation in preparation, launch and follow-up of project services markets, and preparation of project contracts and agreements. - Preparation and management of letters. - Participation in the organization of workshops and seminars. - Preparation and facilitation of field missions.

Qualifications/Skills

Education- Diplomas: - University degree (minimum 2 years) with a solid foundation in accounting and financial management. Experience: - A minimum of 3 years of experience in finance and administration. Other required criteria: - Proficiency in Arabic and French. - Experience in project management, preferably in development. - Experience in office administration. - Experience in organizing events and meetings. - Knowledge of partner institutions at local and national levels. - Proficiency in computer skills, especially Word, Excel, Access and to Internet access. - Excellent teamwork skills. - Good organizational and communication skills.

### Consultants

| Consultant | Number of weeks | Tasks, deliverables and selection criteria |
| --- | --- | --- |
| International consultants |  |  |
| International expert on national and international implementation of the Nagoya Protocol (EI1) | 36 | Objectives: Provides high-level assistance through consulting and capacity reinforcement services for the implementation of a regulatory and institutional framework on the Nagoya Protocol adapted to the national context. Proposes potential and logical solutions, based upon their international experience, on strategic options for a national approach on the implementation of ABS. These options may include the overall policy direction (market-based or protective approach), the type of regulatory system, the authorization system' structure (centralized or decentralized), the operation of checkpoints (continuous monitoring or ad hoc), etc. Follows-up on development and implementation of both components of the project, and provides reasoned advice on legal and institutional aspects in collaboration with national and international consultants providing capacity development services. Main tasks: - Under supervision of the National Project Director, national executing partners and UNDP, assist in ensuring that the Inception Workshop' results leads to a clear project roadmap. - Assist the NPD in developing a detailed work plan, determining the project scope and budget, identifying additional executing partners, and coordinating all the activities and deliverables including contributions to, and results from, consultants and service providers. This will involve reviewing ToR and providing support in recruitment of consultants and service providers. - Oversee, support and provide technical guidelines to consultants and working groups involved in the ABS project, ensuring high quality project deliverables. - Ensure the integration of findings from various studies into the national ABS framework. - Develop a step-by-step analysis for measuring and comparing expected results to obligations with respect to Nagoya Protocol obligations. - Propose options and guidelines to develop and implement the national/regional strategy/policy on ABS. - Determine further steps to take for local and national implementation of the Nagoya Protocol. - Contribute towards the required steps for developing regulations for the Law on Biological Resources and a law on intellectual property rights, in accordance with the CBD, Nagoya Protocol (NP), related international instruments, and adapted to national circumstances following consultations with stakeholders. - Contribute towards taking the required steps for developing an institutional framework (including relevant national authorities and support measures), allowing implementation of the Law on Biological Resources, thus providing legal certainty, clarity and transparency for commercial and research purposes. - Contribute to the steps required to develop and implement a system to protect traditional knowledge. - Contribute, with experiences from other countries, to targeted training on handling access requests to the ABS, negotiating ABS agreements, facilitated access to genetic resources, compliance monitoring, monitoring of bioprospecting projects, and addressing Nagoya Protocol issues, ex for competent national authorities (CNA), national focal points (NFP), and related organizations. - Contribute to the development of ABS model agreements that facilitate the negotiation of monetary (i.e. up-front payments on signature and royalties) and non-monetary payments (i.e. opportunities for training / research and technological transfers), and benefit users and providers of genetic resources. - Evaluate deliverables providing models, guidelines, and training programs on the national ABS framework (ABS procedures for users and providers of genetic resources, PIC protocols, negotiation strategies for ABS agreements, ABS related IPR, bioprospecting and investigation procedures) developed by the project team. - Identify mandatory elements included in a sample Agreement in Principle for non-commercial purposes. - Identify mandatory elements included in a sample Agreement in Principle for non-commercial or potentially commercial purposes. - Participate in meetings and workshops organized within the framework of the project. - Work closely with the National Project Coordinator and other team members. - Contribute to the preparation of the final project report. Contribution / assessment of the following deliverables: - Recommendations for an institutional and regulatory framework. - Nationally appropriate regulations on ABS. - Document providing ABS sample agreements that facilitate the negotiation of monetary (initial contracts and royalties) and non-monetary payments (i.e. opportunities for training / research and technological transfers), and benefits users and providers of genetic resources. - Document on mandatory elements to be included in a sample Agreement in Principle for non-commercial or potentially commercial purposes. - Assessment of all other project reports. - Contribute to the preparation of the final project report. Selection criteria: - Preferably a PhD or a postgraduate degree (MSc) in Natural Sciences or Environment, with international experience in managing genetic resources and ABS processes, gained either in policy or field work; - Excellent knowledge of the CBD, Nagoya and Cartagena Protocols. - Proven experience in analyzing legal texts on ABS; - Prior experience in managing the interface between the environment, development and communication; - Proven ability to collect, verify and analyze information, as well as to finalize and present research with a high degree of accuracy and technical quality; - Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes; prior experience with NBSAPs is an asset; - Excellent knowledge and understanding of CBD and ABS' decisions and processes. Prior experience in developing national and regional ABS policies; - Excellent command of French is required. Knowledge of Arabic is an asset. |
| International Lawyer specializing in intellectual property rights in relation to ABS (EI2) | 16 | Objectives: Participates in the team responsible for preparing the regulatory and institutional framework to implement the Nagoya Protocol and plays an active role in the transposition of its mechanisms into national law, focusing on the specificities of intellectual property rights regarding GR and sui generis protection for TK. Main tasks: - Conduct an analysis of nationally ratified international treaties on biodiversity, intellectual property rights regarding GR and associated traditional knowledge relevant to ABS; - Analyze measures taken by other countries in the field of IP related to GR and the protection of associated TK, examining the impact on ABS; - Contribute to the analysis / synthesis conducted by legal experts on the national regulations in preparation, and national institutions regarding the environment, biodiversity, intellectual property, user rights and genetic resources; - Conduct surveys with organizations active in the field of Intellectual Property in Algeria (Ministry of Culture, MESRS, etc.) - Participate in the preparation and presentation of options for the appropriate ABS regulatory and institutional framework (draft regulations/amendments) for implementation of the Nagoya Protocol, including a component on IP on uses of genetic resources and associated traditional knowledge; - Participate in the animation of consultation and validation workshops for the draft regulations prior to their introduction; - Participate in the animation of consultation and validation workshops for institutional platforms / structures that will be involved in accreditation, consultation, control, negotiations and of the sole competent national authority; - Develop recommendations for the implementation of the new regulations; - Participate in the formulation of a document on "recommendations for an institutional and regulatory framework"; - Contribute to the preparation of a concerted Public-Private (producers / users) model agreement, inspired by more experienced countries in this field, but adapted to the national framework for the implementation of the Nagoya Protocol; - Contribute to the implementation of capacity building programs for national users, in particular those that build national expertise in matters of legislation, institutions and specialized ABS-Nagoya MAT negotiations; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Summary document pertaining to nationally ratified international treaties on biodiversity, intellectual property rights relevant to GR and associated TK in the ABS context. - Analytical document presenting the experiences of some countries and arrangements in the field of IP on GR and the protection of associated TK, examining the impact on ABS; - Recommendations for an institutional and regulatory framework; - National laws and regulations appropriate to ABS, including aspects related to intellectual property of genetic resources and associated traditional knowledge; - Preparation of the final project report. Selection criteria: - Preferably a PhD or a postgraduate degree (LLM) in Intellectual Property Law or Environmental Law, with excellent knowledge of the CBD, Nagoya and Cartagena Protocols, including aspects regarding genetic resources and associated traditional knowledge; - Proven experience of reviewing and analyzing institutional systems as well as international and national legal texts; - Proven ability to draft relevant documents (publications, reports and related documents); - Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes; prior experience in patents and other forms of IPRs on biological resources is an asset. - Excellent command of French is required. Knowledge of Arabic is an asset. |
| International expert on the implementation of the Nagoya Protocol in relation to the international private sector (EI3) | 25 | Objectives: As resource person, enliven the interface with the international private sector by providing technical assistance to international companies represented in Algeria in the implementation of the Nagoya Protocol and ABS. Works with other consultants on the project, including those involved in research and the national public-private partnership (PPP) expert, and interacts with national private companies. Main tasks: - Contribute to raising awareness and providing technical assistance to private companies on the implementation of the Nagoya Protocol and ABS; - Contribute to the production of manuals on best practices on the sustainable use of biodiversity and genetic resources; - Contribute to designing and supporting the deployment of bioprospecting and ABS opportunities, as well as comprehensive strategies for biodiversity conservation incorporating ABS; - Participate in training workshops on ABS challenges and on processes of Certifications such as Organic Agriculture, Fair Trade, UEBT, etc. - Participate in Environmental and Social Responsibility diagnostics of ecosystems services between international value chains and production areas; - Contribute to the development of sample Public-Private or Producers-Users model contracts, adapted to the national context for the implementation of the Nagoya Protocol; - Contribute to capacity building training, particularly in the initiation and development of PPPs between providers and users to establish value chains consistent with ABS principles, as well as enhancing the value of biodiversity and genetic resource through streamlining supply chains, optimizing value chains, obtaining certification, etc.; - Contribute to designing effective mechanisms (e.g. provisions, working capital or sinking funds) to benefit from ABS agreements for the conservation of biodiversity and the sustainable use of its components; - Contribute to the development of tools for raising public awareness and campaigns targeting key stakeholders on the national ABS framework; - Assist in capacity building of local actors and structuring of value chains; - Participate in the formulation of a document on "recommendations for an institutional and legal framework "; - Contribute to the preparation and drafting of sample contracts and specialized agreements for the transfer of genetic material; - Participate in the animation of consultation and validation workshops for draft regulations prior to their introduction into the adoption process; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Strategic elements and practical implications for bioprospecting on GR and collection of associated traditional knowledge in accordance with the Nagoya Protocol; - Methodological approaches to define GR value chains in specific contexts in Algeria; - Factors to be taken into account to facilitate the integration of the national and international private sector into the ABS process and for valorization of GR; - Awareness raising pamphlets on ABS for the private sector; - Propose effective mechanisms (e.g. provisions, working capital or sinking funds) to benefit from ABS agreements for the conservation of biodiversity and the sustainable use of its components; - Recommendations for an institutional and legal framework; - National legislative framework adapted to ABS; - National institutional framework adapted to ABS; - Contribution to the final project report. Selection criteria: - Preferably a graduate degree (MSc) in Marketing and International Business, with excellent knowledge of the CBD, Nagoya Protocol and Cartagena Protocols, and "market research" for the valorization of biodiversity and GR products; - Proven experience in providing technical assistance to private enterprises for the implementation of the Nagoya Protocol and ABS; in sustainable investment and corporate responsibility; - Experience in capacity building of local, state, private and NGOs; - Proven ability to draft relevant documents (publications, reports and related documents); - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; - Knowledge and understanding of ABS decisions and processes; - Prior experience in working with national and international private sector is an asset. |
| International governance and inter-institutional coordination expert, as well as on developing organizational strategies on biodiversity and genetic resources (EI4) | 16 | Objectives: The consultant will provide technical assistance to the team responsible for legal and institutional aspects. Plays an active role in the development of policies related to ABS and the protection of traditional knowledge, providing legal development advice, notably through regulatory and institutional aspects, and the development of organization strategies on the management of biodiversity and genetic resources. Main tasks: - Contribute to setting up the national regulatory framework for the implementation of the Nagoya Protocol, particularly on matters related to post-access and compliance measures; - Contribute to setting up the national legislative framework for the implementation of ABS, particularly on aspects related to the international governance of genetic resources (e.g. NP related legal instruments) and implications for the implementation of national laws; - Conduct an analysis of inter-institutional arrangements by other countries to manage ABS processes; - Participate in the assessment of existing institutional arrangements in Algeria on genetic resources management, in particular regarding their role in terms of authorization processes, management and governance of genetic resources; - Contribute in required steps for developing an institutional framework (including relevant national authorities and support measures), allowing implementation of the national ABS Law, legal certainty, clarity and transparency for commercial and research purposes; - Participate in the animation of consultation and validation workshops for institutional platforms / structures for accreditation, consultation, control, negotiations and of the competent national authority; - Contribute in the initiation and completion of capacity reinforcement programs for national actors of GR in terms of monitoring, indicators and financing; - Contribute to the design and execution of training programs for national GR actors on legislation, inter-institutional governance and negotiations for ABS; - Produce "policy notes" for policy makers on national GR and significance of traditional resources; - Participate in the animation of consultation and validation workshops; - Develop recommendations for the implementation of the new regulations to the Law on Biological Resources - Participate in the formulation of a document on "recommendations for an institutional and regulatory framework"; - Contribute to the preparation of a concerted Public-Private (producers / users) pilot framework agreement, inspired by more developed countries in this field, but adapted to the national framework for the implementation of ABS; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Analytical document on inter-institutional arrangements used by other countries to manage ABS processes; - Assessment document on existing institutional arrangements in Algeria on genetic resources management, in particular regarding their role in terms of authorization processes, management and governance of genetic resources; - Policy briefs for policy makers on national GR and the significance of traditional resources and intellectual property rights; - National regulatory framework adapted to ABS; - National institutional framework adapted to ABS; - Contribution to the final project report. Selection criteria: - Preferably a PhD or a postgraduate degree (LLM) in Law (biodiversity law, environmental law, intellectual property law and international trade law); - Excellent knowledge of the CBD, Nagoya and Cartagena Protocols, including the protection of traditional knowledge; - Proven experience of reviewing and analyzing legal texts, institutional systems and inter-institutional governance; - Proven ability to draft relevant documents (publications, reports and related documents); - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes; prior experience of the Nagoya Protocol is an asset. |
| International expert on communication and public awareness regarding ABS (EI5) | 20 | Objective: Expert responsible for developing a national communication strategy and awareness on ABS, with a list of topics, calendar, activities, assessment tools, and a list of target-groups. In coordination with the national project coordinator and other consultants, identifies target groups, defines appropriate messages for each group, and designs appropriate tools for raising awareness. Advises and supports the coordinator to promote the project's results (visits with various key groups including journalists, creation of a project website, and production of various information tools). Main tasks: - Develop a national communication strategy and awareness on ABS, with a list of topics, calendar, activities, assessment tools, and a list of target-groups. Important activities include: 1) Identification of key target groups and desired behavior changes. 2) Conducting investigations to ascertain the level of awareness of key target groups. 3) Establishment of a roster of communication, legal and technical experts on ABS; and 4) Organizing a discussion and validation workshop on elements of the national awareness raising strategy on ABS. - Create or adapt awareness raising tools on ABS issues; - List the objectives and define intended messages, including for the following target groups: policy-makers, members of Parliament and other elected officials, local authorities, general public, scientists and researchers, children / youth at school, local populations, potential users (private and public) international and national, national regulatory and supervisory bodies, customs and enforcement officers, media, magistrates and the judiciary; - Develop campaign plans for key stakeholders on the national ABS framework in cooperation with the Project Management Unit; - Ensure the Project Management Unit disseminates the awareness raising and training tools at national, regional and local level, to all public sector actors and civil society, through existing communication channels (audiovisual media, print, internet, etc.); - Participate in the animation of multi-stakeholder workshops at national and regional level, on ABS / TK issues to raise awareness among stakeholders that well-conducted ABS contracts and bioprospecting can contribute to development and conservation; - Conduct a training session on Communication and Information to national entities involved on ABS; - Organize and facilitate media coverage of project-related events or actions - Advise the project coordinator on developing and maintaining relationships with various media and organizing meetings with journalists to create ABS-awareness networks; - Advise the Project Coordinator on the creation and regular update of the project website; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - National communication strategy and awareness document on ABS, with a list of topics, calendar, activities, assessment tools, and a list of target-groups; - Proposals for awareness raising and training tools on ABS issues; - Coverage reports of national events organized by the project; - Structuring elements for the creation and regular update of the project website; - Contribution to the final project report. Selection criteria: - Graduate degree (MA/MSc) in Communication education / awareness on issues related to environmental protection and sustainable development, with excellent knowledge of the CBD and Nagoya Protocol; - Proven experience in communication with institutional officials, civil society, professional associations; - Proven experience in designing and developing communication tools; - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes is an asset. |
| National consultants |  |  |
| National legal expert on environmental law, biodiversity and ABS (EN1) | 30 | Objectives: Assumes a role of coordination and resource person for the implementation of an appropriate regulatory and institutional framework for implementation of the Nagoya Protocol. Main tasks: - Conduct an inventory of existing regulations on access to genetic resources and associated traditional knowledge, and / or benefit sharing in national and regional policies and strategies in relevant sectors such as biodiversity, forestry, fishing, agriculture, research, science and technology; intellectual property, culture, etc. - Analyze ABS legislation adopted in other countries and regions; - Analyze the gaps of key legal national texts on biodiversity and genetic resources with regards to ABS; - Contribute in conducting surveys amongst legal services departments responsible for the management of natural resources, particularly genetic resources; - List existing institutional arrangements and evaluate those that could play a role in terms of authorization processes, management and governance of genetic resources; - Participate in the animation of consultation and validation workshops for institutional platforms / structures for accreditation, consultation, control, negotiations and of the competent national authority; - Conduct consultations and engage stakeholders in the development of legal, regulatory, administrative mechanisms for the protection of genetic resources and associated traditional knowledge, in accordance with the CBD, Nagoya Protocol (NP), and related international instruments; - Participate in the animation of thematic/sectorial workshops for explaining and discussing new ABS regulations; - Prepare and present options for the appropriate ABS legal framework for implementation of the Nagoya Protocol, including aspects on traditional knowledge - Develop recommendations for legal implementation; - Coordinate the production of a document entitled "recommendations for an institutional and legal framework "; - Prepare and present the proposition for the appropriate ABS legal framework to implement the Nagoya Protocol with the corresponding structures of administration, consultation, negotiation and control; - Contribute to the preparation of a concerted Public-Private (producers / users) pilot framework agreement, inspired by more developed countries in this field, but adapted to the national framework for the implementation of the Nagoya Convention; - Contribute to initiate and carry through capacity reinforcement programs for national users, in particular building national expertise in matters of legislation, institutions and specialized ABS-Nagoya negotiations; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Analysis / synthesis of national legislation (existing or in preparation) and national institutions regarding the environment, biodiversity, intellectual property, user rights and genetic resources; - Proposition of a national legal framework adapted to ABS; - Mapping of institutional actors to be involved in developing the implementation strategy (e.g. forestry, agriculture, health, local populations, research and technology, professional associations); - Mapping of actors involved in the management and governance of biological resources (e.g. authorities responsible for protected areas, local populations and breeders); - Mapping of actors impacted by the implementation of a national ABS legislation (e.g. actors previously mentioned, health sector, research institutions, private sector using the BR / GR and associated local knowledge); - Proposition of a national institutional framework adapted to ABS; - Contribution to the final project report. Selection criteria: - Preferably a PhD or a postgraduate degree (LLM) in environmental law, with excellent knowledge of the CBD, the Nagoya and Cartagena Protocols; - Proven experience of reviewing and analyzing national texts and institutional systems; - Proven ability to draft relevant documents (publications, reports and related documents); - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes; prior experience in NBSAP is an asset. |
| National expert on inventory and protection of traditional knowledge associated with genetic resources (EN2) | 16 | Objectives The consultant plays a key part in the team of consultants with regard to the role and rights of local populations, for the protection of traditional knowledge associated with genetic resources in the ABS framework. Assumes a role of resource person towards sub-national and national consultation processes regarding all project related activities, in order to define the role of local populations the function of TK associated to GR. Main tasks: - Ensure the integration of traditional knowledge in the design of the project's annual planning and implementation activities; - Evaluate relevant provisions regarding local populations' rights as specified in the constitution, legislation and specific regulations; - Identify and document traditional knowledge, including customary laws and rules of access, subject to the agreement of local populations concerned; - Create, on the basis of this documentation, a TK database in relation with ABS (digital library); - Conduct a study on means of protecting TK through case studies of advanced countries, and propose elements for a national TK protection system; - Evaluate the feasibility of implementing a sui generis protection system of traditional knowledge associated to genetic resources; - Organize workshops of the TK protection system including PIC and MAT protocols and gather stakeholders’ feedback on the proposed system; - Finalize the elements of proposed system; - Develop guidelines on TK, notably in terms of access to TK, and appropriate structures at all levels; - Participate in awareness-raising and capacity reinforcement activities of communities, relevant ministerial departments, stakeholders and agencies; - Participate in capacity and expertise reinforcement activities for communities in terms of negotiation; - Assist target communities for the preparation et implementation of ABS development plans, follow-up their execution and report to the NPD together with questions/problems raised; - Participate in meetings and workshops organized within the framework of the project; - Contribute to capacity and expertise reinforcement operations for communities in terms of negotiation; - Contribute to the consultation and validation of the draft Law and implementing legislation for the implementation of the Nagoya Protocol, integrating the legislative, institutional analysis and partner' recommendations; - Contribute to the preparation of a Public-Private model Convention adapted to the national context, taking into account the rights of local populations; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Mapping of current and potential users of traditional knowledge associated to genetic resources, including specific uses; - Synthesis paper on Algerian intellectual property rights and environmental legislation with regard to users' rights of local population; - Synthesis paper on traditional and local knowledge regarding regional products in Algeria; - Guideline document on the protection of traditional knowledge and appropriate access measures. Selection criteria: - Preferably a PhD or postgraduate degree (MSc) in anthropology or rural sociology, with excellent knowledge of the CBD, Nagoya and Cartagena Protocols, and human rights; - Proven experience in dealing with local populations and in studying local traditional knowledge; - Involvement in ABS related discussions related and the protection of traditional knowledge, and interactions with local NGOs; - Proven ability to draft relevant documents (publications, reports and related documents); - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes. |
| National expert on GR and dialogue with national research institutions (EN3) | 26 | Objectives: The national expert on genetic resources management plays a key role in the team of consultants with regard to documentation of existing genetic resources in Algeria. Works closely with specialized resource persons on categories of GR (agricultural, wild plants, marine, domestic fauna, wild animals, microorganisms, etc.). Provides relevant technical and scientific information to legal experts and to expert interfacing with the private sector. Ensures the dialogue with national research institutions. Takes on a coordination role and resource person for the project's planned training activities on GR. Main tasks: - Produce a mapping of institutions/universities conducting research on biological/genetic resources particularly on their (bio) chemical composition, genetic characteristics, agronomic and medical uses, etc. including associated traditional knowledge; - Conduct a mapping of current and potential users of genetic resources, including specific uses; - Identify relevant actors and existing expertise for implementing the Nagoya Protocol (national network databases); - Develop a national CHM ABS development plan aimed at national and international information in order to use the best communication tools for ABS related activities; - Contribute to set up relevant information on national GR and their valorization potential within the national CHM ABS; - Produce a list of indicators to follow-up national-level implementation of ABS at the national level, to ensure monitoring and compliance; - Develop a plan to set up checkpoints to monitor the use of genetic resources, including the designation of one or more checkpoints. - Contribute to develop a guideline document on national genetic resources, their characteristics and valorization potential; - Develop training programs on ABS and genetic resources for scientific and technical staff; - Participate in design and animation of training sessions scheduled within the capacity building component for various categories of ABS stakeholders; - Contribute to developing model agreements / contracts, inspired by more developed countries but adapted to the national framework; - Contribute to develop a handbook on national and international conditions for GR economic transactions; - Contribute to the preparation of a Public-Private model Convention adapted to the national context for the implementation of the Nagoya Protocol; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the project's long-term consultant and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Synthesis paper of available information (documents, theses, publications and reports) on research related to the country's genetic resources; - Key elements of a research and development strategy for knowledge and GR valorization (objectives, approach, Project leader and partners); - Mapping of institutions/universities conducting research on biological/genetic resources particularly on their (bio) chemical composition, genetic characteristics, agronomic and medical uses, etc. including associated traditional knowledge; - Mapping of current and potential users of genetic resources, including specific uses; - Mapping of institutional actors to be involved in developing the implementation strategy (e.g. forestry, agriculture, health, local populations, research and technology, professional associations,..); - Mapping of actors involved in the management and governance of biological resources (e.g. authorities responsible for protected areas, local populations, gene banks, breeders); - Mapping of actors impacted by the implementation of a national ABS legislation (e.g. actors previously mentioned, health sector, research institutions, private sector using the BR / GR and associated local knowledge); - Document on the implementation within the national CHM APA, relevant information on national and RG valorization potential; - Document on setting up relevant information on national GR and their valorization potential within the national CHM ABS; - List of indicators to follow-up national-level implementation of ABS at the national level, to ensure monitoring and compliance; - Training programs on ABS and genetic resources for scientific and technical staff. Selection criteria: - Preferably a PhD or postgraduate degree (MSc) in genetic resources, with excellent knowledge of the CBD, Nagoya and Cartagena Protocols; - Proven experience of conducting research on national genetic resources, in research networks, and in following-up negotiations on the Nagoya Protocol; - Proven ability to conduct training sessions and draft relevant documents (publications, reports and related documents); - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; - Knowledge and understanding of ABS decisions and processes is an asset. |
| National expert on economic valorisation of biodiversity and genetic resources (EN4) | 15 | Objectives: The consultant is in charge of performing specific tasks for developing a mid-term mobilization plan of endogenous and exogenous financial resources to implement the national ABS framework, and a promoting/commercialization strategy of products derived from biodiversity and genetic resources, for the purpose of valorisation and economic development, as well as an assistance plan to cooperatives and production associations with a potential role for ABS systems. He will work in collaboration with the team of other consultants, including the international expert in relation to the international private sector. Main tasks: - Develop a mid-term mobilization plan of financial resources to implement the Nagoya Protocol and the ABS framework; - Identify business opportunities in relevant sectors for transmission to private potential users (cosmetics, pharmaceuticals, agriculture, horticulture, MAP, non-timber forest and marine products, others.); - Develop an assistance plan to cooperatives and production associations with a potential role for ABS systems (e.g. MAP, marine and regional agricultural products) including marketing channels, administration methods, bookkeeping, etc.; - Contribute to design effective mechanisms (e.g. provisions, working capital or sinking funds) to benefit from ABS agreements for the conservation of biodiversity and the sustainable use of its components; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Options and mobilization plan of endogenous and exogenous financial resources to implement the Nagoya Protocol and the ABS framework; - Promotion/commercialization strategy of products derived from biodiversity and genetic resources, for the purpose of valorisation and economic development, based upon real cases in the following sectors: cosmetics, pharmaceuticals, agriculture, horticulture, MAP, non-timber forest and marine products, others; - Business opportunities in relevant sectors for the valorisation of GR (cosmetics, pharmaceuticals, agriculture, horticulture, MAP, non-timber forest and marine products, others.); - Assistance plan to cooperatives and production associations with a potential role for ABS systems (e.g. MAP, marine and regional agricultural products) including marketing channels, administration methods, bookkeeping, etc. Selection criteria: - Graduate degree (Masters) in economics, environmental economics or related field with demonstrated experience in economic valorisation and financing of biodiversity, and public-private (PPP) partnerships; - Proven ability to draft relevant documents (publications, reports and related documents); - Proven ability to collect, verify and analyze information, as well as to finalize and present research with a high degree of accuracy and technical quality; - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes; - Excellent command of French and English is required, knowledge and understanding of ABS decisions and processes is an asset. |
| National expert on organization and animation of local populations (EN5) | 15 | Objectives: The consultant plays a key part in the team with regards to the role and rights of local populations, their organization and animation for the protection of traditional knowledge associated with genetic resources in the ABS framework. Assumes a role of resource person regarding all project related activities, notably regarding consultations with local populations and NGOs, to reflect their expectations and propose appropriate measures to strengthen the capacity of civil society and local populations, with particular emphasis on the role of women in relation to ABS. Also performs an animating role in meetings and capacity development activities for local populations regarding the ABS negotiation process. Main tasks: - Conduct inquiries and group interviews with representatives of local populations to gather their expectations with regard to the ABS process, in 2 or 3 regions of Algeria to be defined as samples with the project's general coordinators. The surveys' results will serve as the basis for the following tasks: - Propose special reinforcement capacity measures of local populations, with particular emphasis on the role of women in relation to ABS; - Ensure the integration of the gender approach in the project's process; - Contribute to develop an assistance plan to cooperatives and production associations with a potential role for ABS systems (e.g. MAP, marine and regional agricultural products) including marketing channels, administration methods, bookkeeping, etc.; - Contribute to create a full list of partners involved in GR, especially NGOs and local cooperatives; - Participate, along the national consultant on TK, to identify and document traditional knowledge, including customary laws and rules of access, subject to the agreement of local populations concerned; - Participate in animating workshops along with NGOs and representatives of local populations, to discuss TK protection systems, including PIC and MAT protocols, and gather stakeholders’ feedback, notably from LCs, on the system proposed by the national TK consultant; - Conduct awareness-raising and capacity reinforcement activities amongst local populations and NGOs; - Conduct capacity and expertise reinforcement activities and meetings for local populations in terms of negotiation; - Participate in Assessment of knowledge, skills and practices (KAP) activities targeting specific groups (local authorities and representatives of local populations) to assess end of the project the impact of awareness on the right National APA, the CBD and the Nagoya Protocol; - Contribute to develop a communication plan on the valorization of GR and implementation of the Nagoya Protocol; - Contribute to develop a handbook on national genetic resources (socio-economic component), on their characteristics and valorization potential; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - Proposition of appropriate measures to reinforce capacities of local populations, with particular emphasis on the role of women in relation to ABS; - Factors and conditions for integrating gender approach in the project's process; - Brief reports on workshops conducted for training NGOs and LCs representatives; - Contribute to develop an assistance plan to cooperatives and production associations with a potential role for ABS systems (e.g. MAP, marine and regional agricultural products) including marketing channels, administration methods, bookkeeping, etc.; - Contribute to create a full list of partners involved in GR, especially NGOs and local cooperatives; - Contribute to the mapping of current and potential users of traditional knowledge associated to genetic resources, including specific uses; - Contribute along the TK consultant to the synthesis paper on traditional and local knowledge regarding regional products and the main genetic resources in Algeria; - Contribute along the TK consultant to the guideline document on the protection of traditional knowledge and appropriate access measures; - Contribution to the final project report. Selection criteria: - Preferably a graduate degree (Masters) in coaching groups and participatory animation in rural environments; - Good knowledge of the CBD and Nagoya Protocol; - Proven experience of accompanying communities in implementing local development programs and capacity reinforcement of local government representatives; - Field experience, working with local NGOs, implementation of tools and action plans for good local governance in terms of Public-Private Partnership; - Ability to work in a multicultural setting, with experience working with partners at all levels (ministries, donors, private sector, NGO's and grassroots community organizations); - Proven ability to draft relevant documents (publications, reports and related documents); - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes is an asset. |
| National expert on education and public awareness for biodiversity and ABS (EN6) | 35 | Objectives: This national expert is in charge of participating to the elaboration of the national communication strategy and awareness on ABS, in collaboration with the international consultant responsible for communication. Following the strategy's definition, he takes charge of the effective implementation of activities as defined in the project's output on public awareness. Carry out, along the project's coordinators, the completion of awareness raising campaigns targeting key stakeholders regarding the national ABS framework. Also responsible for activities related to the assessment of knowledge, skills and practices (KAP) targeting specific groups and aiming at assessing the impact of public awareness campaigns on national ABS Law, CBD and Nagoya Protocol. Main tasks: - Participate in developing the national communication strategy and awareness on ABS, in collaboration with the international consultant on CEPA / ABS; - Create the awareness-raising and communication tools on issues related to access and benefit-sharing, ensuring translations in local languages across regions; - List the objectives and define intended messages, including for the following target groups: policy-makers, members of Parliament and other elected officials, local authorities, general public, scientists and researchers, children / youth at school, local populations, potential users (private and public) international and national, national regulatory and supervisory bodies, customs and enforcement officers, media, magistrates and the judiciary; - Carry out, along the project's coordinators, the completion of awareness raising campaigns targeting key stakeholders regarding the national ABS framework; - Ensure the Project Management Unit disseminates the awareness raising and training tools at national, regional and local level, to all actors of the public sector and civil society, through existing communication channels (audio-visual media, print, internet, etc.); - Participate in the animation of multi-stakeholder workshops at national and regional level, on ABS / TK issues to raise awareness among stakeholders that well-conducted ABS contracts and bioprospecting can contribute to development and to the national / local conservation program; - Participate in the animation of training session on Communication and Information to national entities involved on ABS; - Set out a KAP rating grid (knowledge, skills and practices) by specific group based on awareness-raising and training activities; - Conduct KAP assessments following trainings organized for different target groups; - Conduct KAP assessments amongst different types of stakeholders, during the project's 2nd and 3rd years, to verify the level of integration of provisions on fair and equitable sharing of benefits and / or the protection of traditional knowledge in access contracts / agreements for commercial and / or non-commercial use, and the capacities to deal with intellectual property rights; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the National Project Coordinator and other team members; - Contribute to the preparation of the final project report. Contribution to the following deliverables: - National strategy paper on communication and awareness-raising on ABS, with topic list, calendar, activities, assessment tools and a list of target groups; - Proposition on awareness-raising and training tools regarding the issues of access and benefit-sharing; - Reports on media coverage of national events organized by the project; - Assessment reports on knowledge, skills and practices (KAP) targeting specific groups (researchers, local authorities, relevant industry stakeholders, representatives of local populations) who might use or benefit from ABS transactions, in order to assess the impact of public awareness campaigns on national ABS Law, CBD and Nagoya Protocol; - Structuring elements of a documentary film on national GR, ABS and their valorization for improving living conditions of local populations; - Structuring elements for the creation and regular update of the project website; - Contribution to the final project report. Selection criteria: - Graduate degree (Masters) in Communication education / awareness on issues related to environmental protection and sustainable development, with excellent knowledge of the CBD and the Nagoya Protocol; - Proven experience in communication with institutional officials, civil society, professional associations; - Proven experience in designing and developing communication tools; - Ability to communication effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences; knowledge and understanding of ABS decisions and processes is an asset. |
| National expert on information and database management related to GR and associated TK (EN7) | 15 | Objectives: This national expert is responsible for design and delivery of the ABS Database Management System (DBMS), suited for each type of record and according to needs of use, in cooperation with the project coordinator and the focal point for ABS and the CHM. This DBMS includes, among other things, a system to control the quality and control of data (from surveys or other data sources), a compilation of various databases from different editions and the preparation of a database's user guide. Main tasks: - Carry out a general data and information review into a database; - Design the databases' structure according to different user needs, in consultation with the project coordinator and the focal point for ABS and the CHM; - Databases can be connected or independent, searchable and scalable at will. They will include: - Laws and regulations on genetic resources, traditional knowledge and intellectual property; - Registered agreements on access and sharing of benefits arising from the use of traditional associated knowledge; - The list of existing online databases and records on GR and associated TK in Algeria and abroad; - Key in situ and ex situ collections of genetic resources existing in Algeria and evaluate the current situation for their medium and long term preservation; - Depending on information availability, a database of active ingredients and biochemical properties in national genetic resources; - TK associated to national GR; - Regularly updated list of national ABS experts; - Preparation of entry screens to reflect Algerian linguistic specificities; - Preparation of additional screens on newly produced notes; - Implementation of an efficient mechanism to manage misplaced entries for reconstitution of the database: transfer, reception and base consolidation (country level, region level); - Implementation of a data security system, to ensure users' autonomy with an initialization and operation software; - Definition and parametric settings of the whole system to integrate the Algerian ABS framework; - Definition and implementation of different editions; - Design and proposition of a system to control data inputs and the quality of data-surveys, as well as statements' anomalies to edit by survey type for cleansing files; - Preparation of a database's user guide; - Training assistance of Algerian PMU and CHM staff on the use of the BAS Database Management System (DBMS). Deliverables: - Installation CD of fully functional ABS database management software in Algeria (4 copies); - Comprehensive Software Guide on: software overall presentation and architecture, data entry, date update, data edition, misplaced entries management, databases reconstitution, backup management. Selection criteria: - Have at least a programmer analyst developer degree in Computer Science; - Have five (5) years minimum experience and relevant references in DBMS development; - Have proven experience in the design of management software for public accounting and specifically on communal management; - If possible have good knowledge and command of software on environmental management. |
| National expert on inventory and valorisation of forest genetic resources and MAP (EN8) | 20 | Objective: Specialist researcher in forest genetic resources, and MAP GR in Algeria, with good knowledge of ABS issues. Will work closely with the national expert in genetic resources management (EN3). His role will be to prepare and analyse data related to the identification component of forest GR and MAP GR that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. Main tasks: - Contribute to the mapping of institutions/universities conducting research on forest/genetic resources, and MAP GR in Algeria, particularly on their (bio) chemical composition, their genetic characteristics, their silvopastoral, agronomic, and medical uses, etc. including associated traditional knowledge; - Contribute to prepare a guideline document on national genetic resources, for forest genetic resources and MAP GR in Algeria, with their characteristics and valorization potential; - Participate in the design and animation of training sessions scheduled within the capacity building component for various categories of ABS stakeholders, notably on sessions dealing with forest genetic resources and MAP GR in Algeria; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the national expert in GR management and other team members; - Contribute to the preparation of the final report. Contribution to the following deliverables: - Synthesis paper of available information (documents, theses, publications and reports) on research related to the country's genetic resources, notably on forest genetic resources and MAP; - Key elements of a research and development strategy for knowledge and GR valorization (objectives, approach, Project leader and partners); - Mapping of institutions/universities conducting research on biological/genetic resources particularly on their (bio) chemical composition, genetic characteristics, agronomic and medical uses, etc. including associated traditional knowledge; - Training programs on ABS and genetic resources for scientific and technical staff. Selection criteria: - Preferably a PhD or a postgraduate degree (MSc) in biodiversity and genetic resources, with excellent knowledge of the CBD and Nagoya Protocol; - Proven experience of conducting research on forest genetic resources and / or MAP in Algeria; - Proven experience of conducting training sessions and drafting relevant documents (publications, reports and related documents). |
| National expert on inventory and valorisation of RG for food and agriculture (EN9) | 10 | Objectives: Specialist researcher in genetic resources of agricultural biodiversity, with good knowledge of ABS issues. Will work closely with the national expert in genetic resources management (EN3). His role will be to prepare and analyse data related to the identification component of food and agricultural GR that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. Main tasks: - Contribute to the mapping of institutions/universities conducting research on genetic resources for food and agriculture in Algeria, particularly on their (bio) chemical composition, their genetic characteristics, their agronomic and medical uses, etc. including associated traditional knowledge; - Contribute to prepare a guideline document on national genetic resources, for food and agriculture in Algeria, with their characteristics and valorization potential; - Participate in the design and animation of training sessions scheduled within the capacity building component for various categories of ABS stakeholders, notably on sessions dealing with food and agricultural genetic resources in Algeria; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the national expert in GR management and other team members. Contribution to the following deliverables: - Synthesis paper of available information (documents, theses, publications and reports) on research related to the country's genetic resources, notably on genetic resources for food and agriculture; - Key elements of a research and development strategy for knowledge and GR valorization (objectives, approach, Project leader and partners); - Mapping of institutions/universities conducting research on food and agricultural biological/genetic resources particularly on their (bio) chemical composition, genetic characteristics, agronomic and medical uses, etc. including associated traditional knowledge; - Training programs on ABS and genetic resources of agricultural biodiversity for scientific and technical staff. Selection criteria: - Preferably a PhD or a postgraduate degree (MSc) in agronomy, biodiversity and genetic resources, with excellent knowledge of the CBD and Nagoya Protocol; - Proven experience of conducting research on genetic resources for food and agriculture in Algeria; - Proven experience in conducting training sessions and drafting relevant documents (publications, reports and related documents). |
| National expert on inventory and valorisation of marine GR (EN10) | 10 | Objective: Specialist researcher in genetic resources and marine biodiversity, with good knowledge of ABS issues. Will work closely with the national expert in genetic resources management (EN3). His role will be to prepare and analyse data related to the identification component of marine GR that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. Main tasks: - Contribute to the mapping of institutions/universities conducting research on marine genetic resources in Algeria, particularly on their (bio) chemical composition, their genetic characteristics, their cosmetic and medical uses, etc. including associated traditional knowledge; - Contribute to prepare a guideline document on national genetic resources, for marine genetic resources in Algeria, with their characteristics and valorization potential; - Participate in the design and animation of training sessions scheduled within the capacity building component for various categories of ABS stakeholders, notably on sessions dealing with marine genetic resources in Algeria; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the national expert in GR management and other team members. Contribution to the following deliverables: - Synthesis paper of available information (documents, theses, publications and reports) on research related to the country's genetic resources, notably on marine genetic resources; - Key elements of a research and development strategy for knowledge and GR valorization (objectives, approach, Project leader and partners); - Mapping of institutions/universities conducting research on marine genetic resources particularly on their (bio) chemical composition, genetic characteristics, cosmetic and medical uses, etc. including associated traditional knowledge; - Training programs on ABS and marine genetic resources for scientific and technical staff. Selection criteria: - Preferably a PhD or a postgraduate degree (MSc) in biodiversity and genetic resources, with excellent knowledge of the CBD and Nagoya Protocol; - Proven experience of conducting research on biodiversity and marine genetic resources in Algeria; - Proven experience in conducting training sessions and drafting relevant documents (publications, reports and related documents). |
| National expert on inventory and valorisation of GR wild and domestic animal genetic resources (EN11) | 10 | Objectives: Specialist researcher in wild and domestic animal genetic resources, with good knowledge of ABS issues. Will work closely with the national expert in genetic resources management (EN3). His role will be to prepare and analyse data related to the identification component of wild and domestic animal genetic resources that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. Main tasks: - Contribute to the mapping of institutions/universities conducting research on wild and domestic animal genetic resources in Algeria, particularly on their (bio) chemical composition, their genetic characteristics, their cosmetic and medical uses, etc. including associated traditional knowledge; - Contribute to prepare a guideline document on national genetic resources, for wild and domestic animal genetic resources in Algeria, with their characteristics and valorization potential; - Participate in the design and animation of training sessions scheduled within the capacity building component for various categories of ABS stakeholders, notably on sessions dealing with wild and domestic animal genetic resources in Algeria; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the national expert in GR management and other team members. Contribution to the following deliverables: - Synthesis paper of available information (documents, theses, publications and reports) on research related to the country's genetic resources, notably on wild and domestic animal genetic resources; - Key elements of a research and development strategy for knowledge and GR valorization (objectives, approach, Project leader and partners); - Mapping of institutions/universities conducting research on wild and domestic animal genetic resources, particularly on their (bio) chemical composition, genetic characteristics, cosmetic and medical uses, etc. including associated traditional knowledge; - Training programs on ABS and wild and domestic animal genetic resources for scientific and technical staff. Selection criteria: - Preferably a PhD or a postgraduate degree (MSc) in biodiversity and genetic resources, with excellent knowledge of the CBD and Nagoya Protocol; - Proven experience of conducting research on wild and domestic animal genetic resources in Algeria; - Proven experience in conducting training sessions and drafting relevant documents (publications, reports and related documents). |
| National expert on inventory and valorisation of GR and microorganisms (EN12) | 10 | Objectives: Specialist researcher in genetic resources of microorganisms, with good knowledge of ABS issues. Will work closely with the national expert in genetic resources management (EN3). His role will be to prepare and analyse data related to the identification component of microorganisms' genetic resources that may be subject to valorisation under the ABS framework. Assumes a resource person role for this type of GR and provides expertise in training workshops on those GR. Main tasks: - Contribute to the mapping of institutions/universities conducting research on genetic resources of microorganisms in Algeria, particularly on their (bio) chemical composition, their genetic characteristics, their cosmetic and medical uses, etc. including associated traditional knowledge; - Contribute to prepare a guideline document on national genetic resources, for microorganisms' genetic resources in Algeria, with their characteristics and valorisation potential; - Participate in the design and animation of training sessions scheduled within the capacity building component for various categories of ABS stakeholders, notably on sessions dealing with genetic resources of microorganisms in Algeria; - Participate in meetings and workshops organized within the framework of the project; - Work closely with the national expert in GR management and other team members. Contribution to the following deliverables: - Synthesis paper of available information (documents, theses, publications and reports) on research related to the country's genetic resources, notably on microorganisms; - Key elements of a research and development strategy for knowledge and GR valorization (objectives, approach, project leader and partners); - Mapping of institutions/universities conducting research on genetic resources of microorganisms, particularly on their (bio) chemical composition, genetic characteristics, cosmetic and medical uses, etc. including associated traditional knowledge; - Training programs on ABS and microorganisms for scientific and technical staff. Selection criteria: - Preferably a PhD or a postgraduate degree (MSc) in biological sciences, biodiversity and genetic resources, with excellent knowledge of the CBD and Nagoya Protocol; - Proven experience of conducting research on biodiversity and genetic resources of microorganisms in Algeria; - Proven experience in conducting training sessions and drafting relevant documents (publications, reports and related documents). |

## Part 4: Project Annexes (UNDP / GEF)

### UNDP Social and Environmental Screening Procedure (SESP)

#### Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Developing a national strategy and legal and institutional framework on access to genetic resources and related benefit sharing and traditional knowledge in line with the CBD and its Nagoya Protocol in Algeria |
| - Project Number | UNDP Project ID PIMS 5311 / GEF Project ID PMIS 5808 |
| - Location (Global/Region/Country) | Algeria |

#### Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

The Project is based on a transparent, participatory, democratic and consultative process which aims to ensure equitable access to development opportunities and gains across society. This is underlain by commitment to recognize the value of economic, political, social, civil and cultural rights to achieve the best possible project outcomes. The outcomes aim to lead to the adoption of a governance framework which supports the inclusive and sustainable development of economic partnerships based on the biological and cultural heritage of local populations, which will ultimately lead to sustainable human development. Socio-economic and development benefits are expected to accrue to local populations and holders of genetic resources and traditional knowledge based on the new livelihood opportunities created by bioprospecting (e.g. commercial opportunities, employment opportunities, and the fair and equitable sharing of monetary and non-monetary benefits). Positive social impacts are expected to result from the new livelihood opportunities generated by ABS and increased local capacities, including contributing to greater resilience, reducing inequality and exclusion, and poverty eradication. Civil society will be involved in every level of the project and their capacities on ABS reinforced.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The Project is likely to improve gender equality and women’s empowerment by creating new economic opportunities for the holders of genetic resources and associated traditional knowledge, many of whom are women. In keeping with the objective of mainstreaming gender considerations described by the CBD Plan of Action on Gender 2015-2020, stocktaking exercises will adequately account for the differences in uses of biodiversity between women and men. Furthermore, women will be effectively engaged as members of all stakeholder groups, and the importance of traditional knowledge and customary practice held by men and women in the protection of biodiversity will be identified and used in supporting implementation. Women’s groups already active in related sectors such as agriculture, fisheries, and forestry will also be engaged in consultations and the dissemination of capacity-building materials.

Briefly describe in the space below how the Project mainstreams environmental sustainability

The Project mainstreams environmental sustainability by seeking to satisfy all of the objectives of the Convention on Biological Diversity by operationalizing the key benefit-sharing mechanism conceived of by the Convention in its Article 15 on Access to Genetic Resources. In doing so, the Project will generate new financial resources to support the conservation of biodiversity and the sustainable use of its components. Completing the regulatory and institutional framework associated with the Law on Biological Resources 2014 will help put the conservation and sustainable use of biodiversity into the mainstream of development and policy-making in Algeria, given the potential economic (monetary and non-monetary) benefits associated with ABS. A communications, education and public awareness component to the Project will also make an important contribution to mainstreaming biodiversity given the very broad target audience, ranging from parliamentarians, government employees, the private sector, the media, local communities, to the public at large.

#### Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |
| --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |
| Risk 1: Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | I = 3 P = 1 | Low | The Project could indirectly adversely impact economic and cultural rights of marginalized groups if stakeholder views are not fully taken into account. |  | Project aims to further the realization of economic, social and cultural rights of the population, and holders of GR and TK in particular, including marginalized groups, through the implementation of ABS in conformity with the CBD and Nagoya Protocol. |
| Risk 2: Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | I = 3 P = 1 | Low | The Project may have adverse impacts on local populations if their needs and rights are not fully taken into consideration in the planning process. |  | Project aims to avoid discriminatory adverse impacts on the realization of economic, social and cultural rights of the Algerian population and holders of GR and TK in particular, including marginalized groups. The project aims to uphold the principles of accountability and the rule of law, participation and inclusion, and equality and non-discrimination. |
| Risk 3: Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | I = 3 P = 1 | Low | ABS reform will regulate access to genetic resources and traditional knowledge, which could have negative impacts on marginalized individuals or groups |  | The project will support the meaningful, effective and informed participation of stakeholders in the formulation, implementation, monitoring and evaluation of project activities |
| Risk 4: Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | I = 3 P = 1 | Low | Local populations may be difficult to contact and consult due to the size of the country and this may lead to the exclusion of marginalized local populations from decision-making processes. |  | The Project aims to uphold to implement reform based on the principles of accountability and the rule of law, participation and inclusion, and equality and non-discrimination. |
| Risk 5: Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | I = 3 P = 2 | Low | Limited experience in ABS leaves an ongoing risk of bio-piracy if users are not informed and lack the capacity to meet their obligations under the regulatory system |  | Capacity building for stakeholders on user obligations is part of Component 2 of the project, which will moderate the risk of duty-bearers not having the capacity to meet their obligations once a fully functional ABS framework is effect. |
| Risk 6: Is there a risk that rights-holders do not have the capacity to claim their rights? | I = 3 P =2 | Moderate | Limited knowledge by local populations of legal rights to resources and knowledge may impede rights-holders from claiming their rights |  | A CEPA campaign targeting all stakeholders is key to achieving of Component 2 of the Project. |
| Risk 7: Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | I = 3 P =2 | Moderate | A risk exists of reinforcing gender-based inequalities if ABS is not implemented in a gender-sensitive manner |  | The Project explicitly takes into account this risk and will aim to promote gender equality and the empowerment of women in the ABS context. Women will be |
| Risk 8: Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | I = 3 P =2 | Moderate | The project could perpetuate existing inequalities e.g. participation in design and implementation or access to opportunities and benefits in relation to ABS |  | The Project explicitly takes into account this risk and will aim to promote gender equality and the empowerment of women in the ABS context. |
| Risk 9: Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? | I = 3 P =2 | Moderate | The Project may limit the ability of women to use, develop and protect natural resources if gender disparities exist in the ABS |  | Project will seek to reduce gender inequalities in access to and control over resources and the benefits of development |
| Risk 10: Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | I = 1 P =1 | Low | The indirect effect of the project will be to facilitate the utilization of genetic resources and fair and equitable benefit sharing |  | The Project will aim to ensure that regulations and institutions relevant to ABS enable the sustainable collection of genetic resources and that benefits derived from their utilization are shared in a fair and equitable manner, consistent with the Convention on Biological Diversity and the Nagoya Protocol. |
| Risk 11: The proposed Project will may result in interventions that adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices) | I = 3 P = 1 | Moderate | New interest in intangible forms of culture may result in negative interventions if the process of access to traditional knowledge associated with genetic resources is not done in a well regulated manner |  | The Project aims to put in place regulations and institutions that ensure conformity with the Convention on Biological Diversity and the Nagoya Protocol, aimed at mitigating the potential for adverse impacts on the intangible cultural heritage of local populations |
| Risk 12: The Project proposes to utilize tangible and/or intangible forms of cultural heritage for commercial or other purposes? | I = 3 P=3 | Moderate | Project proposes to create a legal framework and institutions that regulate the use of intangible cultural heritage for commercial and non-commercial use. |  | The Project proposes to develop or reform laws on protection of traditional knowledge. Local populations will be informed of their rights under new Law, the scope and nature of access to traditional knowledge, and the potential consequences. The Project aims to ensure that the use of intangible cultural heritage of local populations does not happen without meaningful, effective participation of affected groups and unless (i) good faith negotiations result in a documented outcome, and (ii) the access provides for fair and equitable sharing of benefits from any commercialization of such knowledge, innovation, or practice, consistent with the affected community’s customs and traditions. |
| Risk 13: The proposed Project may affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | I= 3 P= 2 | Moderate | Local populations may have customary rights to land, territories and resources that are affected. Algeria’s Constitution does not recognize potential customary arrangements, property rights or customary rights to land, territories or resources. |  | The Project proposes to examine whether the existing property rights regime enables or constrains ABS transactions. Customary utilization rights are may be addressed in a law reform proposal. |
| Risk 14: Indigenous peoples (“local populations”) are present in the Project area (including Project area of influence)? | I = 3 P =3 | Moderate | Although not officially recognized as indigenous peoples by the Algerian Constitution, some local populations possess characteristics which fit the definition of indigenous peoples found in relevant international declarations. |  | The Project will seek to collect many stakeholder viewpoints in the development of the regulatory and institutional framework for ABS, which will include consultation with local populations and associations in regards to their rights over genetic resources and traditional knowledge. |
| Risk 15: The proposed Project may affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas) | I = 3 P =3 | Moderate | The project will regulate access and ownership rights over genetic resources |  | In completing the legal and institutional framework in Algeria, access to genetic resources will be regulated across the national territory, most of which is Constitutionally owned by the State. There will need to be consideration of customary usage rights in the elaboration of implementing legislation. |
| Risk 16: There is an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | I = 3 P =3 | Moderate | Culturally appropriate consultations with all local populations may not be possible to carry out given Algeria’s size and project budget. |  | Social assessment and management measures are required to ensure that local populations and associations are consulted in the development of implementing regulations. |
| Risk 17: Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | I = 3 P = 2 | Moderate | The Project aims to facilitate access to genetic resources on the whole national territory |  | Genetic resources will be accessed across the national territory and measures must be taken to ensure that access is done with the consent or approval and involvement of local populations. |
| Risk 18: Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | I = 3 P = 1 | Moderate | The Project may affect the traditional livelihoods of local populations |  | If traditional knowledge is successfully commercialized in Algeria, measures need to be taken to ensure that local populations are benefiting from the access that took place to provide for more livelihood options |
| Risk 19: Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | I = 3 P =2 | Moderate | The Project proposes to facilitate ABS relating to traditional knowledge associated with genetic resources |  | Measures must be taken to ensure that the commercialization of traditional knowledge leads to positive outcomes for local populations. |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  | Comments |
|  | Low Risk |  |  | ☐ |  |
|  | Moderate Risk |  |  |  | The upstream Project activities have potential adverse social and environmental risks and impacts. The indirect nature of the project means that the risk is limited in scale, can be identified with a reasonable degree of certainty, and can be addressed through application of standard best practice, mitigation measures and stakeholder engagement during Project implementation. |
|  | High Risk |  |  | ☐ |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |
|  | Check all that apply |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  |  | Economic, social and cultural rights must be monitored |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  |  | Women are recognized as significant holders of genetic resources and traditional knowledge and, as such, will be involved in ABS transactions. Social assessment measures must be used to ensure greater gender equality and the empowerment of women in the process. |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  |  | Implementing a functional access and benefit-sharing system will lead to access to genetic resources. The Project will aim to ensure that national institutions have the capacity and responsibility to oversee the social and environmental aspects of ABS transactions. KAP studies will be used as an assessment measure and the information will be used to manage risk. |
|  | 2. Climate Change Mitigation and Adaptation |  |  | ☐ |  |
|  | 3. Community Health, Safety and Working Conditions |  |  | ☐ |  |
|  | 4. Cultural Heritage |  |  |  | Traditional knowledge, innovations and practices are being accessed for commercial purposes. Social assessment and management measures are required to address potential risks to the cultural heritage of local populations. Also see Risk 6. |
|  | 5. Displacement and Resettlement |  |  |  | Community based property rights and customary rights to resources and territories could be impacted by the creation of the regulatory framework on genetic resources. Social assessment and management measures are required to make sure that customary rights of local populations to resources and territories are not affected. |
|  | 6. Indigenous Peoples |  |  |  | Some local populations may possess the relevant characteristics in Algeria to qualify as indigenous peoples as recognized in international declarations. Social assessment measures are required to monitor the impacts of ABS transactions on local populations. |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | ☐ |  |

#### Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | - UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

#### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks | Answer |
| --- | --- |
| Principles 1: Human Rights |  |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | Yes |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | Yes |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | Yes |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | Yes |
| 5. Are there measures or mechanisms in place to respond to local community grievances? | No |
| 6. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | Yes |
| 7. Is there a risk that rights-holders do not have the capacity to claim their rights? | Yes |
| 8. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 9. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | Yes |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | Yes |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 3. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | Yes |

| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| --- | --- |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | Yes |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |

| Standard 2: Climate Change Mitigation and Adaptation |  |
| --- | --- |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | No |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | Yes |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | Yes |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | Yes |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | Yes* |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas)? | Yes* |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | Yes* |
| 6.4 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | Yes* |
| 6.5 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.6 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.7 Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | Yes |
| 6.8 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | Yes |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

### GEF ABS Tracking Tool (Beta Version)

|  | Tracking Tool for Biodiversity Projects in GEF-4 and GEF-5 |
| --- | --- |
| Objective 4: Build Capacity for the Implementation of the Nagoya Protocol on Access and Benefit Sharing (ABS) |  |

| I. General Data | Please indicate your answer here | Notes |
| --- | --- | --- |
| Project Title | Developing a national strategy and legal and institutional framework on access to genetic resources and related benefit sharing and traditional knowledge in line with the CBD and its Nagoya Protocol in Algeria |  |
| GEF Project ID | 5808 |  |
| Agency Project ID | 5311 |  |
| Implementing Agency | UNDP |  |
| Project Type | MSP | FSP or MSP |
| Country | Algeria |  |
| Region | Arab States / North Africa |  |
| Date of submission of the tracking tool | May 21 2015 | Month DD, YYYY (e.g., May 12, 2010) |
| Name of reviewers completing tracking tool and completion date | Salah Chouaki, National ABS Expert Consultant; Hamid Hemdani, National ABS Expert Consultant; Frederic Perron-Welch, International ABS Expert Consultant, 2 May 2015 | Completion Date |
| Planned project duration | 4 years | Years |
| Actual project duration | 4 years | Years |
| Lead Project Executing Agency (ies) | UNDP |  |
| Date of Council/CEO Approval | PIF approval : May 21, 2014 | Month DD, YYYY (e.g., May 12, 2010) |
| GEF Grant (US$) | $2,000,000 |  |
| Cofinancing expected (US$) | $ 5,284,320 |  |

| II. For each question please identify any intended actions that will improve the implementation of the Nagoya Protocol |  |  |  |  |
| --- | --- | --- | --- | --- |
| Issue | Please select your score from drop down menu | Scoring Criteria |  |  |
| Capacity to ratify and implement basic measures of the NP |  |  | Comment | Next Steps |
| 1) Has the country carried out a stocktaking and assessment of ABS issues including legal framework and institutional capacity to develop and implement the Nagoya Protocol? | 2 | 0: The country has not carried out a stocktaking and assessment on either the legal or institutional capacity on ABS 1: The country has carried out an assessment and stocktaking of the legal framework 2: The country has carried out an assessment and stocktaking of both legal and institutional capacity. 3: The country has carried out the assessment and stocktaking and is using it to advance the national ABS agenda | Algeria has adopted a Law on Biological Resources but lacks a good understanding of its institutional capacities on the matter | Assess institutional capacity to implement the Protocol |
| 2) Did the country sign and ratify the Nagoya Protocol? | 1 | 0: The country has not signed or ratified (accession) the protocol. 1: The country has only signed the Protocol. 2: The country has accessed the protocol (i.e. signing and ratifying). 3: The country is preparing an action plan for implementation of basic measures of the Nagoya Protocol | Algeria signed the Nagoya Protocol in 2011 and is preparing an action plan for implementation of basic ABS measures | Inform legislators on why they should ratify the Nagoya Protocol |
| 3) Is there a national legal and regulatory framework governing ABS? | 1 | 0: The legal and regulatory framework has not been developed 1: The country is developing a legal framework on ABS 2: The country has a legal framework ready for approval by the legislature. 3: The country has a legal and regulatory framework that has full force and is ready to be linked to the administrative system. | Legal framework (Law on Biological Resources) was passed in 2014 but requires 8 or more regulations | Develop regulations to fully implement the law and adequately govern ABS |
| 4) Is there a communications and public awareness plan to explain the Nagoya Protocol, including challenges and opportunities for users and providers of genetic resources? | 1 | 0: Little or no official information on ABS or the Nagoya Protocol is available to the general public 1: Information on ABS and the Nagoya Protocol is available to specialized audiences 2: Information on ABS and the Nagoya Protocol is widely available and a communication and awareness campaign is being designed 3: A formal communications and awareness plan is fully developed and operational | Very limited info available, e.g. no information available on MREE or other government websites; some information available to specialists | Develop and implement a CEPA plan |
| Capacity to administer the measures of the Nagoya Protocol |  |  | Comment | Next Steps |
| 5) Have the National Focal Point and Competent National Authority (ies) been designated and have the capacity to facilitate and administer the implementation of the protocol? | 2 | 0: The country has no National Focal Point or Competent Authority 1: The National Focal Point and Competent Authority(es) have been designated but not operational. 2: The structure of the Administrative Systems, including the National Focal Point and Competent Authority(es) is under development 3: The competent National Authorities have the human and technical resources necessary to administer the implementation of the NP | NP focal point has been designated but must be changed; structure of administrative systems are now being developed | Ratify NP & complete regulations establishing institutional framework for implementation |
| 6) Are there clear administrative procedures for users and providers of genetic resources to develop and implement ABS agreements with proper Prior Informed Consent (PIC), Mutually Agreed Terms (MAT) and Benefit Sharing (BS)? | 1 | 0: The country does not have the administrative procedures to develop and implement ABS agreements with PIC, MAT and BS. 1: The country is developing the administrative procedures for user and providers to engage in ABS agreements under the provisions of the Nagoya Protocol. 2: The country has sufficient administrative procedures to facilitate ABS agreements but have not been deployed by the administrators 3: The country has all administrative procedures available to develop ABS agreements. | Regulations need to be adopted under the Biological Resources Law the before these procedures are in place | Develop these administrative procedures through the adoption of relevant regulations |
| 7) Is there installed capacity to monitor compliance with the protocol and the utilization of genetic resources, including the designation of one or more checkpoints and directing benefits toward conservation and sustainable use of biodiversity? | n/a | 0: The monitoring systems are up and running, including designated check points 1: There are check points designated but not monitoring systems in place. 2: The check points and monitoring systems, linked to the administration are ready to be used 3: There is full capacity to monitor the compliance with the NP, including directing benefits toward the conservation and sustainable use of the biological resources. | Nothing is in place, Algeria is not a Party to the Protocol and has no obligation to set up checkpoints or monitoring systems | Ratify NP and ensure that monitoring and compliance mechanisms are in place |
| Capacity of countries to develop their endogenous research capabilities to add value to their own genetic resources |  |  | Comment | Next Steps |
| 8) Is there institutional capacity to carry out the research and development associated with the valorization of genetic resources? | 2 | 0: There is no capacity for research and development associated with the valorization of genetic resources. 1: The institutional capacity to carry-out research and development is under development 2: Though basic institutional capabilities (i.e. laboratories and research centers) are being used in at least initial stages of R&D. 3: The country has advanced capabilities for research and development and is engaged with technology transfer with partner institutions | National institutes exist to carry out R&D, but capabilities are still basic/intermediate. | Continue to build institutional capacity, especially in relation to national gene bank + technology transfer |
| 9) Is there capacity for the identification of commercial value of genetic resources, and to develop, update and maintain databases on genetic resources? | 1 | 0: There is no institutional or human capacity to engage in the identification of potential commercial value of genetic resources. No data bases available 1: There is basic capacity to engage in the identification of commercial value of genetic resources, including testing data bases. 2: There is advanced capacity to work on the identification of commercial value of genetic resources including basic data bases. 3: There is full capacity for the identification of commercial value of genetic resources and the data bases are operational. | Given that Algeria is only now creating a market economy, there is limited capacity to determine the commercial value of GR | Build capacity to identify the commercial value of genetic resources |
| Capacity needs and priorities of indigenous and local communities and other relevant stakeholders |  |  | Comment | Next Steps |
| 10) Do Indigenous and Local Communities (ILCOs) have the information to understand the challenges and opportunities that the NP has to offer and to actively engage in ABS agreements? | 0 | 0: The ILCOs do not have the information to understand the challenges and opportunities that the NP has to offer and to active engage in ABS agreements 1: The ILCOs have the necessary documentation to understand the NP but have not used it to engage in ABS agreements. 2: The ILCOs have the necessary information and are being trained on the challenges and opportunities that the NP has to offer. No ABS agreements yet. 3: The ILCOs have the necessary information and training on the NP and are engaged in developing ABS agreements. | Local populations generally do not have any information on the Nagoya Protocol or ABS | Develop a CEPA Strategy |
| 11) Are there model contractual clauses to obtain Prior Informed Consent (PIC) for the utilization of genetic resources and associated Traditional Knowledge (TK)? | 0 | 0: There are no model contractual clauses to obtain Prior Informed Consent (PIC) for the utilization of genetic resources and associated TK. 1: The contractual models to obtain PIC for the utilization of genetic resources and associated TK are being developed for at least some ILCOs 2: The contractual models are being tests on pilot projects on ABS agreements 3: The contractual models are widely available and used as part of ABS agreements | Model clauses have not yet been developed because the Law on Biological Resources was only recently adopted | Develop model contractual clauses using the AU Strategic Guidelines as inspiration |
| 12) Are there minimum requirements for Mutually Agreed Terms (MAT) to secure fair and equitable sharing of benefits arising from the utilization of TK associated with genetic resources? | 1 | 0: There are no requirements for Mutually Agreed Terms (MAT) to secure fair and equitable sharing of benefits arising from the utilization of TK. 1: The requirements for MAT associated with TK are being developed. 2: The requirements for MAT are being tested with some pilot projects on ABS agreements. 3: The requirements are being used widely and in conjunction with PIC and benefit sharing clauses. | Minimum requirements for MAT have not yet been established through regulation but are being developed | Support the development of regulations on minimum MAT requirements using the AU Strategic Guidelines as inspiration |
| 13) Are there model contractual clauses for benefit-sharing arising from the utilization of TK associated with genetic resources? | 1 | 0: There are no model contractual clauses for benefit-sharing arising from the utilization of TK associated with genetic resources. 1: The contractual models for benefit-sharing are being developed. 2: The contractual models are being tested on pilot projects on ABS agreements 3: The contractual models are widely available and used as part of ABS agreements in conjunction with PIC and MAT clauses. | There are no model clauses because the Law on Biological Resources was only recently adopted | Support the development of regulations |

| III. Questions for projects developing and implementing ABS agreements |  |  |  |  |
| --- | --- | --- | --- | --- |
| Issue | Please select your score from drop down menu | Scoring Criteria | Comment | Next Steps: |
| 1) Have the users of genetic resources obtained Prior Informed Consent to the access and use of genetic resources? | n/a | 0: The project does not have PIC yet 1: The users of genetic resources are working with the providers to obtain PIC 2: The project has Prior Informed Consent for the users to access the genetic resources | No ABS agreements will be established as part of the project |  |
| 2) Are there Mutually Agreed Terms (MAT) between users and providers of genetic resources? | n/a | 0: The project does not have MAT yet 1: The users and providers of genetic resources are working on the MAT 2: There are MAT between users and providers of genetic resources project | No ABS agreements will be established as part of the project |  |
| 3) Are the monetary and non-monetary benefits derived from access and utilization of genetic resources clearly stated in the ABS agreement? | n/a | 0: The project does not have Benefit Sharing clauses yet 1: The users and providers of genetic resources are working on the Benefit Sharing clauses 2: There are clear Benefits for users and providers for the access and use of genetic resources. | No ABS agreements will be established as part of the project |  |
| 4) Is the project in line with relevant sub-national laws and regulations including those established and enforced by Indigenous and Local Communities (ILCOs)? | n/a | 0: The project is not in compliance with sub-national laws and regulations including those of the ILCOs 1: The project is working towards compliance with these laws and regulations 2: The project is in compliance with these laws and regulations | No ABS agreements will be established as part of the project / there are no sub-national laws and regulations |  |
| TOTAL SCORE | 13 |  |  |  |

### National ABS Institutional Capacity Development Scorecard (UNDP)

| Strategic Area of Support | Issue | Scorecard | Initial Evaluation | Evaluative Comments |
| --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, laws, strategies and programmes | The Access and Benefit-Sharing (ABS) agenda is being effectively championed / driven forward | 0 -- There is essentially no ABS agenda; 1 -- There are some persons or institutions actively pursuing an ABS agenda but they have little effect or influence; 2 -- There are a number of ABS champions that drive the ABS agenda, but more is needed; 3 -- There are an adequate number of able "champions" and "leaders" effectively driving forwards an ABS agenda | 1 | Some persons are active in the ABS arena, but their capacity needs to be built |
|  | There is a legally designated institution(s) responsible for ABS with the capacity to develop a national ABS framework (i.e., laws, policies and/or regulations) | 0 -- There is no institution(s) responsible for ABS; 1 – The institution(s) has financial resources but has limited personnel and expertise; 2 – The institution(s) has financial resources and personnel but limited expertise; 3 – The institution(s) has sufficient financial resources, personnel and expertise. | 0 | A institution is foreseen in the Law on Biological Resources but has not yet been established |
| 2. Capacity to implement policies, legislation, strategies and programmes | There is a legally designated ABS institution(s) responsible for ABS that can facilitate the implementation of the national ABS framework. | 0 – The institution(s) does not have the financial resources, personnel, and planning/management skills; 1 – The institution(s) has financial resources but has limited personnel and planning/management skills; 2 – The institution(s) has financial resources and personnel but limited planning/management skills; 3 – The institution(s) has sufficient financial resources, personnel and planning/management skills. | n/a | A institution is foreseen in the Law on Biological Resources but has not yet been established |
|  | The ABS institution (s) is effectively led | 0 – The ABS institution(s) has a total lack of leadership; 1 – The ABS institution(s) has weak leadership and provides little guidance; 2 – The ABS institution(s) has a reasonably strong leadership but there is still need for improvement; 3 – The ABS institution(s) is effectively led | n/a | A institution is foreseen in the Law on Biological Resources but has not yet been established |
|  | Human resources for ABS management are well qualified and motivated | 0 -- Human resources are poorly qualified and unmotivated; 1 -- Human resources qualification is spotty, with some well qualified, but many only poorly and in general unmotivated; 2 – Human Resources in general reasonably qualified, but many lack in motivation, or those that are motivated are not sufficiently qualified; 3 -- Human resources are well qualified and motivated. | 2 | Not enough information available to accurately determine the qualifications and motivation of human resources for ABS management. |
|  | The ABS institution(s) is audited and publicly accountable | 0 – The ABS institution(s) is not being held accountable and not audited; 1 – The ABS institution(s) is occasionally audited without being held publicly accountable; 2 – The ABS institution(s) is regularly audited and there is a fair degree of public accountability but the system is not fully transparent; 3 – The ABS institution(s) is highly fully audited, and publicly accountable. | n/a | No ABS institution yet established |
|  | Enforcement of ABS regulations | 0 -- No enforcement of regulations is taking place; 1 -- Some enforcement of regulations is taking place but it is largely ineffective; 2 -- ABS regulations are regularly enforced but are not fully effective; 3 -- ABS regulations are highly effectively enforced. | n/a | No ABS regulations yet in place |
|  | Individuals are able to advance and develop professionally | 0 -- No career tracks are developed and no training opportunities are provided; 1 -- Career tracks are weak and training possibilities are few and not managed transparently; 2 -- Clear career tracks developed and training available; HR management however has inadequate performance measurement system; 3 -- Individuals are able to advance and develop professionally. | n/a | No ABS institution yet established |
|  | Individuals are appropriately skilled for their jobs | 0 -- Skills of individuals do not match job requirements; 1 -- Individuals have some or poor skills for their jobs; 2 -- Individuals are reasonably skilled but could further improve for optimum match with job requirement; 3 -- Individuals are appropriately skilled for their jobs | n/a | No ABS institution yet established; it is too early to speak of individual competencies |
|  | Individuals are highly motivated | 0 -- No motivation at all; 1 -- Motivation uneven, some are but most are not; 2 -- Many individuals are motivated but not all; 3 -- Individuals are highly motivated | 2 | No ABS institution yet established, but many individuals are motivated. |
|  | There are appropriate mechanisms of training, mentoring, and learning in place to maintain a continuous flow of new staff | 0 -- No mechanisms exist; 1 -- Some mechanisms exist but unable to develop enough and unable to provide the full range of skills needed; 2 -- Mechanisms generally exist to develop skilled professionals, but either not enough of them or unable to cover the full range of skills required; 3 -- There are mechanisms for developing adequate numbers of the full range of highly skilled ABS professionals | n/a | No ABS institution yet established |
| 3. Capacity to engage and build consensus among all stakeholders | ABS has the political commitment | 0 -- There is no political will at all, or worse, the prevailing political will runs counter to the interests of ABS; 1 -- Some political will exists, but is not strong enough to make a difference; 2 -- Reasonable political will exists, but is not always strong enough to fully support ABS; 3 -- There are very high levels of political will to support ABS. | 2 | The Law on Biological Resources finally gained enough political will to be adopted last year, and there is a fair chance that a reasonable level of political will shall continue. |
|  | Degree of public support on ABS issues | 0 -- The public has little interest in ABS and there is no significant lobby for ABS; 1 -- There is limited support for ABS; 2 -- There is general public support for ABS and there are various lobby groups strongly pushing them; 3 -- There is tremendous public support in the country for ABS. | 0 | The public is ill informed about ABS, meaning that there is limited interest due to lack of understanding. |
|  | The ABS institution(s) is mission oriented | 0 -- Institutional mission is not defined; 1 -- Institutional mission is poorly defined and generally not known and internalized at all levels; 2 -- Institutional mission well defined and internalized but not fully embraced; 3 – Institutional mission is fully internalized and embraced. | n/a | There is no ABS institution |
|  | The ABS institution(s) can facilitate the partnerships needed to achieve its objectives | 0 – The ABS institution(s) operate in isolation; 1 – The ABS institution(s) has facilitated some partnerships but significant gaps and existing partnerships achieve little; 2 – The ABS institution(s) has facilitated many partnerships with a wide range of national and local agencies, private sector and NGOs but there are some gaps and partnerships, are not always effective and do not always enable efficient achievement of ABS objectives; 3 – The ABS institution(s) has facilitated effective partnerships with national and local agencies, private sector and NGOs to enable achievement of ABS objectives in an efficient and effective manner. | n/a | There is no ABS institution |
| 4. Capacity to mobilize information and knowledge | The ABS institution(s) has the information it needs to enforce the national legal/policy ABS framework and to facilitate ABS deals | 0 -- Information is virtually lacking; 1 – The ABS institution(s) has access to some information, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 – The ABS institution(s) has access to a lot of information which is mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 – The ABS institution(s) has the information it needs to enforce the national legal/policy framework and facilitate ABS deals. | n/a | There is no ABS Institution and information is generally limited |
|  | Individuals from the ABS institution(s) work effectively together as a team | 0 -- Individuals work in isolation and don't interact; 1 -- Individuals interact in limited way and sometimes in teams but this is rarely effective and functional; 2 -- Individuals interact regularly and form teams, but this is not always fully effective or functional; 3 -- Individuals interact effectively and form functional teams. | n/a | There is no ABS institution |
| 5. Capacity to monitor, evaluate, report and learn | There is a legally designated institution(s) responsible for ABS and able to update the ABS national framework | 0 – The institution(s) does not have the financial resources, personnel, and expertise; 1 – The institution(s) has financial resources but has limited personnel and expertise; 2 – The institution(s) has financial resources and personnel but limited expertise; 3 – The institution(s) has sufficient financial resources, personnel and expertise. | n/a | There is no ABS Institution, meaning that financial resources, human resources and expertise are not present. |
|  | ABS policy or law is continually reviewed and updated | 0 -- There is no policy or law or it is old and not reviewed regularly; 1 -- Policy or law is only reviewed at irregular intervals; 2 – Policy or law is reviewed regularly but not annually; 3 -- Policy or law is reviewed annually. | 1 | Law was adopted only one year ago, so no reviews have yet been undertaken |
|  | Society monitors ABS projects | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the ABS projects. | 1 | Due to a general lack of social awareness regarding ABS, society is generally not engaged. However, some dialogue is taking place within specialized circles. |
|  | Institutions are highly adaptive, responding effectively and immediately to change promoted by implementation of the national ABS framework (i.e., laws, policies and/or regulations). | 0 – There is no implementation of the national ABS framework at the moment; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change. | 2 | The Law on Biological Resources has been adopted but remains to be implemented. Institutions will adapt in response to change but it may take some time. |
|  | The ABS institution(s) has effective internal mechanisms for monitoring, evaluation, reporting and learning on ABS projects | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning. | n/a | There is no ABS institution |
|  | Individuals from ABS institutions are adaptive and continue to learn | 0 -- There is no measurement of performance or adaptive feedback; 1 -- Performance is irregularly and poorly measured and there is little use of feedback; 2 -- There is significant measurement of performance and some feedback but this is not as thorough or comprehensive as it might be; 3 -- Performance is effectively measured and adaptive feedback utilized | n/a | There is no ABS institution |
| TOTAL SCORE | 11 |  |

* Algeria does not recognize indigenous peoples as such, but does recognize the existence of “local populations” residing on the national territory, some of which may consider themselves as having customary rights over resources, territories and knowledge.