Request for CEO endorsement/Approval

Project Type:

the GEF Trust Fund

Submission Date:  01/21/2011

Resubmission: 2/10/2010

| Expected Calendar (mm/dd/yy) |  |
| --- | --- |
| Milestones | Dates |
| Work Program (for FSPs only) | Nov 2009 |
| Agency Approval date | Mar 2011 |
| Implementation Start | June 2011 |
| Mid-term Evaluation | Dec 2014 |
| Project Closing Date | Oct 2016 |

part i:  project Information

GEFSEC Project ID: 4075

gef agency Project ID: P115963

Country(ies): Benin

Project Title: SPWA: Support to Protected Areas Management

GEF Agency(ies): , ,

Other Executing partner(s): CENAGREF

GEF Focal Area(s):

GEF-4 Strategic program(s): BD-SP1-PA, BD-SP3-PA)

Name of parent program/umbrella project:  WEST AFRICA BIODIVERSITY PROGRAM- SUB-COMPONENT FOR BIODIVERSITY  PROJECT FRAMEWORK

- Project framework

| Project Objective: To enhance protection of biodiversity in Northern Benin Savannah Ecosystems through conservation measures and by reducing human pressure on parks |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Invest-ment TA, or STA** | Expected Outcomes | ### Expected Outputs | ### GEF Financing* |  | Other Financing * |  | Total ($) c=a+ b |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |
| 1. Support to CENAGREF management capacity |  |  |  | 1.80 | 24.66 | 5.50 | 75.34 | 7.30 |
| Sub-cp 1.1: Strengthened capacity of the CENAGREF-Direction Générale (DG) | TA | Parks management activities in Northern Benin coordinated and harmonized. Conservation actions required to enhance the status of the forest reserves of Agoua, Lama, Wari Maro and Mont Kouffè in Central and Southern Benin defined. | A communication strategy is developed and implemented. Study reports to inform potential upgrade of the status of Central & Southern Forest Reserves are available and submitted to Government Trainings on environment and social safeguards, biodiversity conservation, and fiduciary standards to strengthen CENAGREF-DG leadership. | 0.27 | 45.80 | 0.32 | 54.20 | 0.59 |
| Sub-cp1.2: Strengthened operational management capacity of the CENAGREF decentralized units (Direction du Parc National de la Pendjari (DPNP) and Direction du Parc National W (DPNW) | Invest-ment | Key wildlife-based abundance direct & indirect indicators in Pendjari and W National parks (through sighting and/or habitat) improved. PA METT scores increased from 85 to 88 for the Pendjari national park and from 68 to 75 for the W national park Core recurrent costs of protected areas are covered | Parks infrastructures rehabilitated GIS-based ecological monitoring rehabilitated Parks management plans and business plans updated and implemented Cost-effective management and financial tools applied by all actors implementing the management plans Systems in place to monitor and report on the impact of conservation and sustainable management of the savannah parks. | 1.53 | 27.27 | 4.08 | 72.73 | 5.61 |
| Sub-cp 1.3: Support to strengthening administrative capacity of the CENAGREF |  | Enhanced capacity of CENAGREF to effectively coordinate and implement project activities and oversee environmental and social safeguards activities. CENAGREF consolidated analytical and financial reports published within three month of each calendar year. | Routine administration activities including budgeting & planning, and procurement reportingThe ESMF and Process Framework implemented An FM software is installed at CENAGREF-DG. | 0 | 0 | 1.1 | 100 | 1.1 |
| 2. Development & implementation of Income-Generating Activities for communities adjacent to the Savannah National Parks | Invest-ment | Number of micro-enterprises functional at the Community level | Number of micro-enterprises created at the community level. | 0 | 0 | 1.5 | 100 | 1.5 |
| 3. Creating an enabling environment for a long-term financing mechanism for biodiversity conservation in Northern Benin Savannah Ecosystems | TA | The FSOA is operating in line with its Articles of Association, By-laws, Operating Manual, Investment Policy, Communication and Fund raising strategy | The FSOA’s Articles of Association are finalized and its by-law developed. Procedures Manual, Investment Policy, communication and funds raising strategies developed and implemented. | 0.1 | 20 | 0.4*** | 80 | 0.5 |
| 4. Project management |  |  |  | 0 |  | 0 |  | 0 |
| Total Project Costs |  |  |  | 1.9 |  | 7.4 |  | 9.3 |

*    List the $ by project components.  The percentage is the share of GEF and Co-financing respectively to the total amount for the component.

** TA = Technical Assistance;  STA = Scientific & Technical Analysis.

*** This amount is parallel financing from KfW for the operating costs of the Foundation.

B.  Financing Plan Summary For The Project ($)

|  | Project Preparation a | Project Grant b | Total c = a + b | Agency Fee | For the record: Project Grant at PIF |
| --- | --- | --- | --- | --- | --- |
| GEF | 0 | 1,900,000 | 1,900,000 | 190,000 | 1,900,500 |
| Co-financing | 0 | 7,400,000 | 7,400,000 |  | 9,675,000 |
| Total | 0 | 9,300,000 | 9,300,000 | 190,000 | 11,575,500 |

C.   Sources of confirmed Co-financing for project

| Name of co-financier (source) | Classification | Type | Project Preparation | Project | Total | %* |
| --- | --- | --- | --- | --- | --- | --- |
| IDA Grant | IDA | Grant | 0 | 5,000,000 | 5,000,000 | 67 |
| Government of Benin | Government | In-kind | 0 | 2,000,000 | 2,000,000 | 27 |
| KfW* | Bilateral | Grant | 0 | 400,000 | 400,000 | 6 |
| Total Co-financing |  |  | 0 | 5,400,000 | 7,400,000 |  |

*:  Percentage of each co-financier’s contribution at CEO endorsement to total co-financing.

*:  This represents a parallel financing from KfW (please see ICA for further details).

D.  GEF Resources Requested by Agency(ies), Focal Area(s) and Country(ies)

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | PPG (a) | Project (b) | Agency Fee ( c) | Total d=a+b+c |
| Total GEF Resources |  |  |  |  |  |  |

*  No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.  Consultants working for technical assistance components:

| ### Component | ### Estimated person/weeks | ### GEF amount($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 140 | 100,000 | 978,065 | 1,078,065 |
| ### International consultants* | 70 | 300,000 | 0 | 300,000 |
| ### Total | 210 | 400,000 | 978,065 | 1,378,065 |

*  Details to be provided in Annex C.

f.   Project management Budget/cost –  Non applicable

| ### Cost Items | ### Total Estimated person /months | ### GEF amount ($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* |  |  |  |  |
| ### International consultants* |  |  |  |  |
| ### Office facilities, equipment, vehicles and communications* |  |  |  |  |
| ### Government in-kind contribution |  |  |  |  |
| ### Travel* |  |  |  |  |
| ### Others** |  |  |  |  |
| Total |  |  |  |  |

*  Details to be provided in Annex C.   ** For others, it has to clearly specify what type of expenses here in a footnote.

G.  Does the project include a “non-grant” instrument? yes     no

H.  describe the budgeted m&E PLAN:

- The objectives of the monitoring and evaluation (M&E) for the project are:  (a) to assess and document timely progress towards outputs, outcomes, and impacts as agreed in the annual work plans and budget; (b) to identify implementation gaps for proactive corrective actions; and (c) to document and incorporate lessons learned into project implementation. The M&E system is based on the Results Matrix (see Annex 1 for details) and the outputs and outcome indicators associated with the annual work plans and budget for project interventions.

- The data for park management outcome will come from the GEF Management Effectiveness Tracking Tool (METT) and the ecological monitoring tools in use by CENAGREF decentralized units to assess fauna indicators.  The CENAGREF and its decentralized units, i.e. the  DPNP and of the DPNW have the technical capacity for data collection, for assessing progress in relation to set targets, and for reporting monitoring information.

- The project will finance Technical Assistance to collect data on income-generating activities through surveys and socio-economic studies at project mid-term and project closure to assess the number of the micro-enterprises financed with IDA funds as well as their economic impact in the community.  Furthermore, at mid-term review and at project completion, overall project impacts assessment will be conducted by an independent consultant financed by the project through IDA funds.

- During the early stages of project implementation, project monitoring will focus on progress of procurement activities against the agreed procurement plan, implementation of the agreed annual work plans and budget, and implementation progress on income generating activities.  Starting from 2013 monitoring will focus on progress in: (i) improvement of key wildlife-based abundance indicators in PNP and PNW (through sighting and/or habitat); (ii) increasing the METT scores in the Northern Benin Savannah ecosystems; (iii) sustainability of micro-enterprises; (v) progress towards the creation process and endowment of the CTF capital; and (vi) progress towards development of feasibility studies in Central and Southern Benin forest reserves.

- During regular implementation support and supervision missions, the Bank team will work closely with the PMU at the CENAGREF DG and park decentralized units as well as the AVIGREFs to evaluate implementation progress.  The cost of data collection, monitoring and evaluation will be covered by the operating budget of the Project Management Unit and Technical Assistance budget earmarked by the project under the PMU budget, and sub-component 1b (Strengthened operational management capacity of the CENAGREF decentralized units).  M&E costs will be financed with IDA funds.

part ii:  project justification:

State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

- The Northern Benin Savannah Ecosystems, i.e. the Pendjari National Park (PNP) and the W National Park (PNW) cover 40% of a contiguous transboundary Protected Areas network called “W-Arly-Pendjari” (WAP, 33,871 Km2) shared with Burkina Faso (36%) and Niger (24%). The WAP is the largest and most important continuum of terrestrial, semi-aquatic and aquatic ecosystems in the West African savannah belt and the most viable natural refuge available to most of the vulnerable and/or threatened animal species in Benin, Burkina Faso and Niger.  In addition to important bird, plant, invertebrate and small vertebrate species, the area holds significant populations of large herbivores and their predators. Important threatened or endangered large mammal species include leopard, korrigum antelope and spotted hyena.  The PNP also has recent recorded observations from cheetah and African wild dogs. The WAP is the most significant range area for elephant conservation in the entire West African sub-region. The flooded areas along the rivers of both the PNP and PNW are wetlands with international importance. Benin has recently added the PNP to the indicative list of natural World Heritage Sites to become one of the elements of the future trans-boundary WAP World Heritage Site. The PNP is also a biosphere reserve.

- Despite support from various donors over the past decade to Nothern Benin Savannah Ecosystems management, the following weaknesses remain to be addressed:  (i) weak capacity of the Centre National de Gestion des Réserves de Faune (National Center for Wildlife Management – CENAGREF), the entity responsible for the management of the country’s protected areas and adjacent zones; (ii) deterioration of basic infrastructure within the parks; and, (iii) insufficient alternative community livelihood schemes to prevent local populations from illegal poaching, fishing and use of natural vegetation for agriculture.

- Support from the GEF and other donors to the Benin National Parks Conservation and Management Program between 2002 and 2007, and subsequent support from the German- ProCGRN (Program for the Conservation and Management of Natural Resources) led to significant progress in the long-term management of the Northern Benin savannah ecosystems.  However, despite regular contribution from the public budget, and increase of revenues from tourism and sport hunting, the financial analysis of current and planned costs and revenues show that core recurrent costs for the implementation of the management plans of the protected areas and surrounding zones will only be reliably and consistently covered through a mix of funding sources, including a predictable sustainable funding mechanism.  Without such mechanism, the results achieved over the last years will be significantly threatened, with an immediate adverse impact on the conservation of the outstanding biodiversity of the Northern Benin savannah ecosystems.

- To address the above issue, the Government of Benin has decided, based on feasibility studies conducted between 2001 and 2003, to create a Foundation that will manage a Conservation Trust Fund (CTF).   The aim of the trust fund is to generate a sustainable source of income for the country’s savannah ecosystems management that will complement variable allocations from the public budget, sport hunting and tourism.

- GEF and IDA-blended resources aim to support the Government’s efforts through: (i) the provision of technical assistance to the Government with a view to facilitate the process of setting up the Foundation in collaboration with KfW; and (ii) financing the management plans of the Pendjari and W parks, in order to maintain the required level of protection and conservation of the parks’ biological resources in the short run, while the CTF is being set up and operationalized to serve as the sustainable financing instrument of the parks core recurrent costs after project closure.

- The Government of Benin has also undertaken actions for potential extension of the Protected Areas network at the National level, i.e: the National Strategy on Biodiversity Conservation and its Action Plan (NBSAP, 2002) recommended the creation of several new Protected Areas in the biogeographical zones (humid zones in the Center and South of Benin, Mono department’s dry Savanna, mangrove, marine ecosystem and Ouémé valley) that are not yet represented. In line with this strategy, several studies were conducted since 2004 and four sites have been identified for potential upgrade to Protected Areas status, namely the forest reserves of Agoua, Lama, Wari Maro and Mont Kouffè.  These reserves remain to be studied to assess their biodiversity importance, and determine what conservation measures and other actions that might be taken by the Government in the long run to improve their current status.  The project will finance technical assistance to undertake these studies which will lay the seeds for potential expansion of Benin PA network at the National level.

- The proposed GEF-IDA blended contribution will play a critical role not only by: (i)  supporting the establishment process of the Foundation; (ii)  financing the core recurrent costs of the Northern Benin Savannah Ecosystems management plans as a transition funding during the course of setting up & operationalizing the Foundation; (iii) laying the seeds for potential expansion of the Benin PA system at the National level;  but also (iv) to leverage other sources of funding, in particular through the implementation of a fundraising strategy targeting both the public and private sector, to increase the CTF endowment capital.

- Project interventions will specifically contribute to protect biological diversity of global importance through management of parks natural resources which will be sustained after project closure thanks to the CTF that the project will help established.

- Describe the consistency of the project with national and/or regional priorities/plans:

- In 1994, the Government of Benin approved a Strategic Plan for the Conservation and Management of Protected Areas. This plan provides the major orientations and guiding principles regarding the institutional aspects of the National Protected Areas Strategy. It specifically underlines the need for decentralization of responsibilities and benefits in order to encourage the effective participation of local communities in protected area management. As called for in the above described Strategic Plan, the CENAGREF was created in 1996.  By 1998, CENAGREF had drafted an Action Plan for the conservation and management of national parks (including the buffer zones and the transition areas). The Action Plan outlines the required actions, approaches, budgets and implementing arrangements and led to PCGPN, as presented above.

- The Government has also adopted a strategy to ensure long term and sustainable financing of protected area management. The strategy hinges on four pillars: (i) improving the level of resources generated by national parks, including through tourism revenues (a key component of the country’s growth strategy), (ii) maintaining sustainable level of costs associated with the management of parks, (iii) ensuring minimum and regular state financing, and (iv) searching for additional financing to support protected areas management effectiveness.

- The project is fully consistent with a new law adopted in 2004, on sustainable management and protection of wildlife and biodiversity. The 2004 law includes special provisions for the protection of critical habitats, management of protected Areas, and prescribes participation of neighboring communities. The project will help implement the Programme for the Conservation and the Management of National Parks (Programme de Conservation et de Gestion des Parcs Nationaux-PCGPN) included in the National Strategy for Biodiversity Conservation adopted in 2002.  The project is also consistent with: (i) the Government Poverty Reduction Strategy Paper (PRSP) and Growth Strategy for Poverty Reduction 2007-2009 which also highlights biodiversity conservation as a national priority; (ii) the Country Assistance Strategy (CAS 2009-2012) pillar 5 “Promoting balanced and sustainable development”, through “greater territorial equity, as a means of protecting the environment, and sustainable management of natural resources”, including biodiversity conservation.

- Describe the consistency of the project with gef strategies and strategic programs:

- The project is fully consistent with the Biodiversity Program's first Strategic Objective: To Catalyse the Sustainability of PA systems, and fulfils the eligibility criteria of the Strategic Programme 1: Sustainable Financing of Protected Area Systems at the National Level, through supporting the establishment of an endowment fund for the long-term funding of the Northern Benin savannah ecosystems. The project also fits within the Strategic Objective 3: Strengthening terrestrial PA networks as the ultimate objective of the fund will be the promotion of sustainable financing mechanisms for the whole WAP Complex, i.e. including neighboring parks and reserves in Niger and Burkina Faso.

- justify the type of financing support provided with the gef resources.

- The GEF funding through both investment and technical assistance will support activities to address specific threats to globally significant biodiversity at Northern Benin Savannah Ecosystems, as well as to ensure sustainable coverage for financing the costs of management plans of the parks so that park integrity is maintained across the existing network, after project closure, through creating an enabling environment to establish a CTF for subsequent initial endowment by the Government of Benin and KfW.

- Investment activities will mainly support rehabilitation of parks infrastructure and technical assistance will support activities to establish the CTF, i.e:  legal assistance to the Government of Benin for the review of the CTF Articles of Association and the development of its by-laws, consultant services for the development of the CTF strategic management tools.

- Outline the Coordination with other related initiatives:

- The project has been designed as a transition funding of the Northern Benin Savannah parks core recurrent costs, while complementing activities led by KfW for the establishment of a long-term financing mechanism for biodiversity conservation (i.e CTF).

- The IDA funds will be blended with the GEF Funds to:  (i) finalize the development and strengthen the implementation of the CTF strategic and management tools (including a monitoring plan), and (ii) serve a bridge-fund to finance management plans of the PNP and PNW in the short term while the CTF is being set up and subsequently operationalized to ensure long-term financing of the parks core recurrent costs.

- KfW has been financing the creation process and will provide, along with the Government of Benin, the initial endowment capital of the CTF, expected at Euro 10.5, USD13.1 equivalent.  KfW contribution is expected at euro 8 million, and Government of Benin, euro 1.5 million.

- In addition, the European Union has indicated an interest in similarly contributing to the strengthening of the fund’s capacity to operate, as a way to maintain long-term impact of its investment in the W park over the last years. Preliminary discussions have also been initiated with the French Government (AFD and FFEM) for a potential contribution to the fund’s capital and process.

- Discuss the value-added of GEF involvement in the project  demonstrated through incremental reasoning :

- CENAGREF is responsible for managing two national parks which cover a surface area of 8,533 Km2, corresponding to about 8% of the national territory.   It includes two of Africa’s best known parks which host an abundance of flora and fauna species: (i) the Pendjari Biosphere Reserve, commonly called the Pendjari National Park (PNP, 2,761 km2), and (ii) the "W" National Park. Please refer to Annex 8 of the Project Document for a detailed incremental cost analysis.

- In the absence of GEF under the baseline scenario, IDA funds added to revenues from tourism, sport hunting and Government contribution will be insufficient to cover the needs of the CENAGREF to implement Northern Savannah parks management plans. Thus, the baseline scenario would not lead to satisfactory conservation and management of the Benin’s outstanding biodiversity, particularly leading to (a) Insufficient maintenance of existing infrastructure within the parks, (b) Limited control of illegal poaching, fishing and use of natural vegetation for agriculture and (c) Monitoring and evaluation systems with no biodiversity conservation indicators being tracked.

- With GEF support in the alternative scenario, sufficient funds will be available for biodiversity conservation until the CTF is established and operational, to provide an enabling environment for catalyzing financing to ensure stable and sustainable conservation financing streams and to develop and implement a long term strategic biodiversity conservation vision, ensuring resources address the most urgent and dominant threats. Specific outcomes would include:

- Full implementation of biodiversity conservation and management plans for Northern Benin Savannah ecosystems; and

- Ecological fauna monitoring, as well as the use of GEF PA-METT to monitor management of the Savannah parks;

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved and outline risk management measures:

- Please refer to the ORAF in Project Appraisal Document.

- explain how cost-effectiveness is reflected in the project design:

- The project is expected to be cost effective because it will build on efforts already undertaken for the creation and operation of the CTF.  Cost effectiveness will be further enhanced by the fact that, the project will aim to ensure that tools, such as analytical accounting, are put in place at the CENAGREF to increase the cost-effectiveness in financial management of project funds.  Building capacities and systems for cost effective management will also ensure that future revenues from the CTF and other sources are used efficiently.

part iii:  institutional coordination and support

- Key entities involved in the project are: (i) the  Centre National de Gestion des Réserves de Faunes (CENAGREF) Direction Générale (DG) in Cotonou which will house the Project Management Unit (PMU) composed of a project coordinator and project fiduciary staff; (ii) the CENAGREF decentralized units (DPNP and DPNW); and (iii) the Associations Villageoises de Gestion des Réserves de Faune (AVIGREFs).

- Project implementation will be based on the existing organization already established to coordinate projects on biodiversity conservation being financed by the Government and development partners.  This organization comprises:

- The CENAGREF Board of Directors chaired by the Minister of Environment and Nature Protection, has high level representation, including from the Ministry of Finance and Economy, Minister of Tourism, Minister of Higher Education and representatives from Conservation International and National NGOs.  As the Project Steering Committee, the Board will be responsible for: (a) approving policy guidelines and providing overall supervision for project implementation; (b) approving the annual work plans and budget; (c) approving the annual procurement plan; and (d) reviewing the annual implementation performance report to be prepared by the Project Management Unit, and overseeing the implementation of corrective actions, when necessary.

- The Project Director: The CENAGREF General Director will be the Project Director and will guide the PMU on overall project management.

- Project Coordinator:  A Project Coordinator will be competitively recruited and will be responsible for day-to-day project activities coordination and execution.  The Project Coordinator will report to the Project Director and  will be responsible for: (a) preparation of project overall annual work plans including consolidated DPNP & DPNW proposals; (b) monitoring of DPNP & DPNW activities for annual work plans implementation in PAs; (c) supervision of overall progress and evaluation of project impacts through the M&E Specialist; (d) accounting and financial administration of project funds using the FM Specialist; (d) procurement  of goods and services using the Procurement Officer; (f) ensuring due diligence of the ESMF and Process Framework through the Environmental and Social Safeguards Specialist; and (g) arranging for a financial audit to be performed annually.

- Project fiduciary staff: The Coordinator will be assisted by a fiduciary team competitively recruited (a Financial Management Specialist, a Procurement Officer, an Environmental Specialist and an M&E Specialist).

- The CENAGREF decentralized units based in Kandi (DPNW) and in Tanguieta (DPNP):  The DPNW and DPNP will be responsible for on-the-ground implementation of annual work plans in each National Park.  They will prepare and submit to the PMU, the parks annual work plans and budget proposals including co-management annual work plans and budgets from the AVIGREFs.  They will report to the Project Coordinator on the progress of implementation in the field.

- The AVIGREFs: The AVIGREFs of W and Pendjari parks will continue to co-manage parks activities.  They will prepare their co-management annual work plans and budgets for submission to their respective decentralized park units:  the DPNW and the DPNP.  They will also be responsible for supporting the communities in the implementation of income generating activities. Micro-enterprises selected to be financed by the project will be included in their annual work plans and budgets. To facilitate the implementation and monitoring of these activities, a tri-partite agreement between the Decentralized parks directions, the AVIGREF and the Communes will be put in place, clarifying roles and responsibilities of each of these actors in the design and implementation of micro-enterprises investments.  An income generating activities manual will also be developed before negotiations. The following chart presents the organizational arrangements of the Project.

part iv:  explain the alignment of project design with the original PIF:

- The project as designed at conceptualization has been modified as a result of findings and developments during the preparation phase. These are detailed below.

- At the PIF stage, it was expected that the Conservation Trust Fund (CTF) would be in place by 2010.  It was therefore envisaged that GEF funds would be allocated as follows: (i) USD1,510,450  for the Endowment capital of the CTF; (ii) USD200,000 to co-finance with KfW the development of the Strategic and management tools of the CTF and the legal and management tools to operate in Benin; and (iii) USD190.050 for Project Management.  It was also envisaged that a parallel financing of USD3 million from the IDA-funded urban environment project would be channeled through the CTF pending return on its capital investments in order to: (i) finalize CTF development and strengthen the implementation of its strategic and management tools, and (ii) test CTF operating procedures through providing grants to the parks and other beneficiaries in order to strengthen their management capacity.

- During project preparation, the team assessed progress towards CTF setting up and closely monitored its establishment process.  It turned out that the process was taking much longer than initially expected, mainly due to the lack of capacity at the Government level to conduct the process.  To date, while the profile of the Foundation is finalized, its Articles of Association are still in draft form.  Several steps still need to be undertaken for full operationalization of the CTF, including: (i) review of the Articles of Association by the Beninese Government; (ii) development of its by-laws; (iii) nomination of the CTF founding members; (iv) selection of its Board members; (v) recruitment of its Executive Board; (vi) registration of the CTF in the UK; and (v) obtaining the Public Entity status in Benin.  These steps need several months to be completed, and could probably be more delayed due to the elections period, planned to begin in March 2011.

- This will further delay the CTF endowment capitalization expected from KfW (Euro 8 million) and Government of Benin (Euro 1.5 million), as well as the availability of the first returns, which are not expected before two to three years.  In addition, the current donors’ projects which finance the core recurrent costs of the parks management plans will come to an end in February 2011 leaving biodiversity conservation unfunded in these parks of global significance.  Given this timing issue, the Government and Bank team opted to review the financing structure of the project to ensure that park integrity is maintained across the existing network, including the CTF creation process as an activity of the project.

- This option will ensure that: (i) a satisfactory level of biodiversity conservation is maintained in Northern Benin Savannah ecosystems while the CTF process creation is underway; and (ii) Government is adequately supported by the project through technical and legal assistance for the CTF creation process.  It is expected that the CTF will be fully operational by project closure to ensure sustainability of project achievements.

- Significantly, during preparation to support this change in the project financing and meet the gap, IDA resources have been leveraged for an amount of  USD5 million which will be fully-blended with the GEF to directly support investments activities  to finance park management plans as well as to develop income-generating activities for parks adjacent communities. Additionally, the Government of Benin has decided to expand its PA network to Central and Southern Benin by selecting priorities reserves for potential upgrade to PA status.   GEF resources will support this expansion process through financing studies to determine conservation actions that might be required to improve the status of these reserves. The GoB will provide in-kind support to the project.

- As a result the project objective, components and financing have been revised to better reflect the actual scenario in the context of the country and keep the project realistic and measurable (see justification matrix below).

| ### At PIF | ### At CEO |  | Justification |
| --- | --- | --- | --- |
| PDO/GEO: To strengthen sustainable management of the Northern Benin Savannah Ecosystems areas through enhanced management capacity and the establishment and operation of a conservation trust fund. | # PDO/GEO: To enhance protection of biodiversity in Northern Benin Savannah Ecosystems through conservation measures and by reducing human pressure on parks |  | The objective of the project has been finetuned to better reflect the outcomes of the project given the delay in the creation of the Trust Fund. |
| Components | # Revised Components | Revised financing |  |
| 1. Strengthened management capacity in Northern Benin Savannah Ecosystems GEF: US$0 Co financing: US$1,250,000 | # 1. Support to CENAGREF management capacity: This component seeks to enhance the capacity of the CENAGREF and its decentralized units (DPNP and DPNW) to manage the Northern Benin Savannah Ecosystems, and to assess the feasibility of improving the status of selected forest reserves in Central and Southern Benin. Sub-cp1.a: Strengthened capacity of the CENAGREF-Direction Générale (DG). The objective of this sub-component is to strengthen the capacity of the CENAGREF-DG to: (i) coordinate and harmonize park management activities in Northern Benin; (ii) conduct feasibility studies to identify conservation actions that might be required to enhance the status of the forest reserves of Agoua, Lama, Wari Maro and Mont Kouffè in Central and Southern Benin; and (iii) enhance technical skills and fiduciary capacity through trainings. Sub-cpt 1b: Strengthened operational management capacity of the CENAGREF decentralized units (Direction du Parc National de la Pendjari (DPNP) and Direction du Parc National W (DPNW) This sub-component aims at supporting the DPNP and DPNW based in Kandi and Tanguieta in Northern Benin, to enhance their capacity to execute parks’ activities depicted from parks management plans. Sub-cpt 1c Support to strengthening administrative capacity of the CENAGREF : This component will ensure overall project coordination, monitoring and evaluation of project activities and ensure timely and effective implementation of project activities. | US$7.3m of which GEF 1.8 m IDA 3.5m GoB 2m (in-kind) US$590,000 GEF: USD270,000 IDA: US$320,000 USD5.61 GEF USD1.53m IDA: USD2.28m. GoB: USD1.80m (in-kind US$1,1,00,000 IDA: US$900,000 GoB: US$200,000 (in-kind) | The overall approach of this revised component is aligned with the component 1 at PIF. The outcomes at PIF stage remain relevant, but are complemented by additional outcomes as outlined on page 2 of this memo. The component has been split into three subcomponents for better clarity and coherency in the outputs to be achieved. The changes are justified owing to: (i) IDA co-financing was increased from USD3 million to 5 million, (ii) GEF resources will not be used for the CTF initial endowment capital due to the delay in establishing the CTF, initially scheduled to be in place by 2010; (iii) current donors projects supporting the Northern Savannah parks are ending in February 2011, with no CTF returns to contribute to financing core recurrent costs of these parks. This component was therefore redesigned in order to: (i) directly finance the parks management plans to secure a satisfactory level of conservation in the parks while the process of establishing the CTF is underway; (ii) strengthen the institutional capacity of the CENAGREF to better coordinate park management activities. Additionally, GoB has requested Bank support for potential upgrade of selected forest reserves in the Central and Southern Benin to expand its protected areas network. The component has been redefined to respond to this request through financing studies to determine conservation actions that might be required to improve the status of these reserves. At appraisal/negotiations, it was agreed to merge management cost for the project with component 1 1 given that the component overall deals with capacity enhancement.. Notably, no GEF resources will be used for such project management activities as the IDA came in to bear the total costs, in addition to in-kind contribution from the GoB. This change has enabled to redirect GEF funds to biodiversity conservation activities instead of project operating costs for greater impact. |
|  | 2: Development and implementation of Income-Generating Activities for communities adjacent to the Savannah National Parks: This component aims to support the development & implementation of income generating activities for parks communities in order to reduce human pressure on the parks. | IDA: US$1,5m | This newly introduced component is fully funded by IDA to contribute to alleviate poverty at the community level. It was added to the project as a result of the increase of IDA’s contribution to the project. It is also key for GEF as it is expected to take human pressure off the parks through diversification of parks communities’ revenue sources. |
| ### Components | ### Revised Components | ### Revised financing | ### Justification |
| 2. Effective operation of trust fund for Northern Benin Savannah Ecosystems GEF: US$200,000 Co financing: US$750,000 | 3. Creation of an enabling environment for a long-term financing mechanism for biodiversity conservation This component aims to create an enabling environment for the establishment and operationalization of a Foundation that will manage a CTF to ensure long term financing for the Northern Benin Savannah ecosystems management plans and maintenance of the park’s integrity across the existing network after project closure. | USD500,000 GEF: US$100,000 KfW: US$400,000 (parallel financing) | Given that the CTF creation process is behind schedule, component 2 & 3 at the PIF stage were replaced by a single component to include the CTF creation process as an activity of the project. It is expected the CTF will be set up by project mid-term and capitalized initially by KfW (euro 8 million) and GoB of Benin (Euro 1.5 million), and fully operational by end of project. |
| 3. Endowment of trust fund for long-term funding of Northern Benin Savannah Ecosystems GEF: US$1,510,450 Co financing: USD6,675,000 |  |  |  |
| 4.Project management GEF: USD 190,050 Co financing: USD 1,000000 | Activities of this component were merged with component 1. . |  | Given that IDA resources were able to bear the cost of project management related activities as part of component 1, the GEF resources allocated for the component were redirected towards conservation activities. |

part v:  Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO Endorsement.+

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Karin Shepardson GEF Agency Executive Coordinator |  | 2/10/2010 | Paola Agostini Regional Coordinator Africa Region | (202) 473 7620 | pagostini@worldbank.org |

# Annex A

# Results Framework and Monitoring

COUNTRY:  Benin: Support to Protected Areas Management Project

Results Framework

| PDO Level Results Indicators* | Core | Unit of Measure |  | Baseline | Cumulative Target Values** |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | YR 1 | YR 2 | YR3 | YR 4 | YR5 |  |  |  |  |
| Indicator one: PNP METT score has increased from 85 to 88 points |  | Value | 85 |  | 85 | 87 | 89 | 91 | 93 | Annual | Progress report | DPNP |  |
| Indicator two: PNW METT score has increased from 68 to 76 points |  | Value | 68 |  | 68 | 70 | 72 | 74 | 76 | Annual | Progress report | DPNW |  |
| INTERMEDIATE RESULTS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Intermediate Result (Component One): Support to CENAGREF management capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Intermediate result indicator one: A communication strategy is developed & implemented |  | Yes/No | No |  | No | Yes | Yes | Yes | Yes | Annual | Progress report | CENAGREF DG |  |
| Intermediate result indicator two: Feasibility studies to inform potential upgrade of the status of Central & Southern Forest Reserves are submitted to Government |  | Yes/No | No |  | No | No | No | Yes | Yes | Annual | Progress report | CENAGREF DG |  |
| Intermediate result three: improvement of key wildlife-based direct and indirect indicators in PNP (through sighting and/or habitat). - Western buffon kobs - Buffalos - Roan antelopes |  | Value | 15 54 66 |  | 16 56 66 | 17 56 66 | 19 60 68 | 20 60 68 | 21 62 70 | Annual | Fauna monitoring reports | DPNP |  |
| Intermediate result ourive: improvement of key wildlife-based direct & indirect indicators in PNW (through sighting and/or habitat). - Roan antelopes - Western buffon kobs - Buffalos |  | Value | 10 40 35 |  | 11 40 35 | 13 42 40 | 14 42 40 | 15 44 44 | 16 45 45 | Annual | Fauna monitoring reports | DPNW |  |
| Intermediate Result indicator five: CENAGREF consolidated analytical and financial reports are published within three month of each calendar year. |  | Yes/No | No |  | No | Yes | Ye | Yes | Yes | Annual | Progress reports |  | CENAGREF DG |
| Intermediate results six: Technical and financial management progress reports are prepared & timely submitted |  | Yes/No | No |  | Yes | Yes | Yes | Yes | Yes | Quarterly | Progress reports |  | CENAGREF DG |
| Intermediate results seven: The ESMF and Process Framework and implemented |  | Yes/No | No |  | Yes | Yes | Yes | Yes | Yes | Quarterly | Progress reports |  | CENAGREF DG |
| Intermediate Result (Component Two): Development and Implementation of Income Generating Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Intermediate result one: Number of micro-enterprises created and functional at the community level (of which % of micro-enterprises created by women |  | Number | 0/0 |  | 0/0 | 0/0 | 15 (50%) | 30 (60%) | 50 (80%) | mid-term and annually thereafter | Progress report | AVIGREF, DPNP and DPNW |  |
| Intermediate Result (Component three): Creating an enabling environment for a long-term financing mechanism for biodiversity conservation in Northern Benin Savannah Ecosystems |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Intermediate Result indicator: The FSOA’s Articles of Association, By-laws, Operating Manual, Investment Policy, communication and funds raising strategies are developed |  | Yes/No | No |  | No | No | Yes | Yes | Yes | Annual | Progress reports | CENAGREF DG |  |

Annex B: Responses to Project Reviews (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF)

1. GEF SEC comments (Review Sheet of 9/08/09)

- Please confirm cofinancing

Reponse:  The financing plan for the project has been revised with a small decrease in cofinancingessentially due to the fact that the CTF was not in place as scheduled in 2010.  Therefore KfW co-financing of euro 8 million equivalent for the endowment, and GoB, euro 1.5 million equivalent were removed from this project.  However, IDA contribution to the project was increased from 3million to 5 million and  KfW funds for the CTF were confirmed during the bilateral negotiations between Germany and the GoB last October 2010.  Furthermore, Benin has earmarked and deposited its participation in the endowment capital in a private Bank.  These funds are expected to form the initial endowment capital of the CTF when created. The total cofinancing is now US$ 7.4 million.

- Include M&E plan

Reponse:  Please see results matrix in annex 1.  Furthermore, project implementation manual under preparation will guide the operationalization of the M&E.

- Provide the Tracking Tools

- The Pendjari and W parks tracking tools are attached.

2. STAP review comments (Review Sheet of 10/8/09)

No pending comments to be addressed.

3. Response to Comments of GEFSEC Review sheet (2/9/2011)

Comment - We will be pleased to receive a revised letter before the end of the webposting period when the project will have been recommended for clearance.

Response: Letter will be provided and is work underway.

Comment: Incremental reasoning Please rephrase the reasoning. It is not appropriate to say that the GEF will pay the recurrent costs for the management of both national parks. We understand that the GEF will serve as an interim partner, while providing a support to make the Trust Fund operational and help the development of the PA network.

In the GEF memo and in the annex on incremental reasoning, it is always important to explain what is the use of GEF resources, and how would the project and global environmental benefits be affected if GEF does not invest. Could you add a section on that in the Cover memo and in the incremental reasoning? Thanks.

Response: The information has been better clarified in the documents. It should however be pointed out that as presented the incremental cost annex in the Project document explains the baseline scenario without the GEF and what GEF will bring to the table. This however is now clearly reflected in the CEO memo where earlier only a reference was drawn.

In the Annex C, could you confirm that consultant rate are per week?

International consultants for the legal aspects and the trust fund are budgeted for $100,000 for 20 weeks.

Response: The figures have now been clarified and are in weeks. Since the project will use firms the amounts are lumpsum for the entire activity, using more than one consultant. Please see revised figures in Annex C of the Memo.
Annex c: consultants to be hired for the project using gef resources

| Position Titles | $ person month* | Estimated person weeks** | Tasks to be performed |
| --- | --- | --- | --- |
| For Project Management |  |  |  |
| Local |  |  |  |
| None | None | None | None |
| International |  |  |  |
| None | None | None | None |
| Justification for Travel, if any: |  |  |  |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Financial Management | 50,000 (lumpsum @ roughly $715/wk | 70 | The consultant firm will train CENAGREF-Central Direction FM staff and accountants in analytical accounting for production of parks management quarterly financial reports |
| Communication | 50,000 (lumpsum @ roughly $715/wk | 70 | The Consultants(2) will support the CENAGREF-Central Direction to develop a communication strategy and tools for the harmonization of parks management activities including surveillance/poaching control and awareness raising on biodiversity conservation. |
| International |  |  |  |
| Biodiversity | 200,000 (lumpsum @ 4000/wk) | 50 | The consultant firm will conduct feasibility studies to determine conservations measures needed to upgrade the status of selected forest reserves in Central and Southern Benin |
| CTF/legal consultants | 100,000 (lumpsum@ 5000/wk) | 20 | The consultants (2-3) will provide legal and operational assistance to the Government of Benin to review the Foundation legal documents, to develop the Foundation by-laws, and support the Foundation Board of Directors with development of the Foundation operating instruments. |
| Justification for Travel, if any: |  |  |  |

*  Provide dollar rate per person week.    **  Total person weeks  needed to carry out the tasks.

Annex d:  status of implementation of project preparation activities and the use of funds

- explain if the ppg objective has been achieved through the ppg activities undertaken.  N/A

- describe findings that might affect the project design or any concerns on project implementation, if any:  N/A

- provide detailed funding amount of the ppg activities and their implementation status in the table below: N/A

annex e:  calendar  of expected reflows

Provide a calendar of expected reflows to the GEF Trust Fund or to your Agency (and/or revolving fund that will be set up) N/A