Project Identification Form (PIF)

Project Type: Full Sized project

the GEF Trust Fund

Submission Date:  August 25, 2009

Re-submission Date:  September 2, 2009

| Indicative Calendar |  |
| --- | --- |
| Milestones | Expected Dates |
| Work Program (for FSP) | November 2009 |
| CEO Endorsement/Approval | September 2010 |
| GEF Agency Approval | November 2010 |
| Implementation Start | January 2011 |
| Mid-term Review (if planned) | January 2013 |
| Implementation Completion | December 2014 |

part i:  project IDentification

GEFSEC Project ID:

gef agency Project ID: P115963

Country(ies): BENIN

Project Title: SPWA- Support to Protected Areas Management

GEF Agency(ies): , ,

Other Executing partner(s): CENAGREF

GEF Focal Area (s): ,,

GEF-4 Strategic program(S): BD-SP1-PA

Name of parent program/umbrella project: West Africa Biodiversity program- Sub-component for Biodiversity

- Project framework  (Expand table as necessary)

| Project Objective: To strengthen sustainable management of the Northern Benin Savannah Ecosystems areas through enhanced management capacity and the establishment and operation of a conservation trust fund] |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Investment, TA, or STA** | Expected Outcomes | ### Expected Outputs | ### Indicative GEF Financing* |  | Indicative Co-financing* |  | Total ($) |
|  |  |  |  | ### ($) | ### % | ### ($) | ### % |  |
| 1. Strengthened management capacity in Northern Benin Savannah Ecosystems | Investment | 1. PA METT scores are increased by at least 20 points 2. Core recurrent costs of protected areas and neighboring communities are reliably and consistently covered through various funding sources, including the trust fund | 1a. Participatory management plans implemented in all protected areas 1b. Business plans developed in all protected areas, and updated every year 2a. Cost-effective management and financial tools are applied by all actors implementing the management plans 2b. Systems are in place to monitor and report on the impact of conservation, sustainable management and eco-development activities | 0 |  | 1,250,000 | 100 | 2,250,000 |
| 2. Effective operation of trust fund for Northern Benin Savannah Ecosystems | TA | 1. Trust Fund has adequate legal and management tools to operate in Benin 2. Strategic and management tools of the trust fund are fully developed and implemented | 1a. Full legal recognition of the trust fund as a foreign charity is granted in Benin 1b. Management structure (Executive Director and staff) is operational. 2a. Procedures Manual (including grant-making procedures) is implemented and regularly updated 2b. Investment Manager is in place and Investment Policy is under implementation 2c.Communications materials are prepared and distributed 2d. Fundraising strategy is implemented 2e. Monitoring plan is used to generate good quality information to support sound management decision making. 2f. Results and lessons learned, including annual reports, are available and disseminated. | 200,000 | 21 | 750,000 | 79 | 950,000 |
| 3. Endowment of trust fund for long-term funding of Northern Benin Savannah Ecosystems | Investment | 1. Trust fund generates c. 30% of the core recurrent costs to implement the management plans of Northern Benin Savannah Ecosystems | 1a. Capitalization of the trust fund | 1,510,450 | 23 | 6,675,000 | 77 | 6,700,500 |
| 4. Project management |  |  |  | 190,050 | 16 | 1,000,000 | 84 | 1,190,050 |
| Total project costs |  |  |  | 1,900,500 |  | 9,675,000 |  | 11,575,500 |

*   List the $ by project components.  The percentage is the share of GEF and Co-financing respectively to the total amount for the component.

** TA = Technical Assistance;  STA = Scientific & technical analysis.

B.   Indicative Financing Plan Summary For The Project ($)

|  | Previous Project Preparation Amount (a)* | Project (b) | Total c = a + b | Agency Fee |
| --- | --- | --- | --- | --- |
| GEF | 0 | 1,900,500 | 1,900,500 | 190,050 |
| Co-financing |  | 9,675,000 | 9,675,000 |  |
| Total | 0 | 11,575,500 | 11,575,500 | 190,050 |

*   Please include the previously approved PDFs and planned request for new PPG, if any.  Indicate the amount already approved as 
            footnote here and if the GEF funding is from GEF-3.

C.   Indicative Co-financing for the project (including project preparation amount) by source and
       by name (in parenthesis) if available, ($)

| Sources of Co-financing | Type of Co-financing | Amount |
| --- | --- | --- |
| Project Government Contribution | Grant | 1,675,000 |
| GEF Agency(ies) | IDA | 3,000,000 |
| Bilateral Aid Agency(ies) |  |  |
| Multilateral Agency(ies) | EU | 5,000,000 |
| Total co-financing |  | 9,675,000 |

D.   GEF Resources Requested by Focal Area(s), agency (ies) share and country(ies)*

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Project Preparation | Project | Agency Fee | Total |
| Total GEF Resources |  |  |  |  |  |  |

*  No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

part ii:  project JustiFication

- State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

- This project aims to strengthen and consolidate the ongoing efforts for biodiversity conservation, sustainable natural resources management and eco-development in Northern Benin savannah ecosystems, by securing long-term funding of these activities.

- Northern Benin savannah ecosystems include the National Parks and Biosphere Reserve of Pendjari and “W”, including surrounding hunting and community zones, and are a significant part (43%) of the W-Arly-Pendjari (WAP) Complex, an area of outstanding biodiversity significance. The WAP is the largest and most important continuum of terrestrial, semi-aquatic and aquatic ecosystems in the West African savannah belt and the most viable natural refuge available to most of the vulnerable and/or threatened animal species in Benin, Burkina Faso and Niger.  In addition to important bird, plant, invertebrate and small vertebrate species, the area holds significant populations of large herbivores and their predators. Important threatened or endangered large mammal species include cheetah, leopard, korrigum antelope and spotted hyena. Pendjari National Park also has recent recorded observations from cheetah and African wild dogs. The WAP is the most significant range area for elephant conservation in the entire West African sub-region. The flooded areas along the rivers of both “W” and Pendjari National Parks are wetlands with international importance. Benin has also recently added Pendjari National Park on the indicative list of natural World Heritage Sites to become one of the elements of the future trans-boundary WAP World Heritage Site.

- From 2002 to 2007, the GEF-WB, the European Union as well as the Dutch, French and German Governments jointly provided support to the Government of Benin in the implementation of the “Programme de Gestion et de Conservation des Parcs Nationaux” (PCGPN) to conserve the biodiversity in Pendjari and “W” National Parks and their adjacent hunting areas and buffer zones. This included: (i) increasing the institutional capacity of Benin's Centre National de Gestion des Réserves de Faune (National Center for Wildlife Management – CENAGREF), the entity responsible for the management of the country’s protected areas and adjacent zones, a public interest establishment with administrative and financial autonomy; (ii) developing alternative community livelihood schemes to take pressure off the parks' natural resources; (iii) improving basic infrastructure within the parks; (iv) expanding environmental awareness and education; and, (v) developing a conservation trust fund to provide sustainable financing for conservation programs.

- Thanks to the commitment of the Government of Benin, the support of the PCGPN and subsequent support from other projects such as the German-funded Programme de Conservation et de Gestion des Ressources Naturelles (ProCGRN – Program for the Conservation and Management of Natural Resources), much progress has been accomplished over the recent years for the long-term management of the Northern Benin savannah ecosystems. Both National Parks are implementing management plans endorsed at the Government level. Strong improvement in the involvement of local communities, surveillance and ecological monitoring are widely recognized. Business plans or financial plans have been developed at the headquarters and park level, together with the gradual implementation of more analytical and transparent accounting practices.

- However, despite regular contribution from the public budget, and sustained increase of revenues from tourism and sport hunting, the financial analysis of current and planned costs and revenues show that core recurrent costs for the implementation of the management plans of the protected areas and surrounding zones will only be reliably and consistently covered through a mix of funding sources, including a predictable sustainable funding mechanism.  Without such mechanism, the results achieved over the last years will be significantly threatened, with an immediate adverse impact on the conservation of the outstanding biodiversity of the Northern Benin savannah ecosystems and the WAP generally.

- Based on positive recommendations of feasibility studies carried out in 2001 and 2003, the Government of Benin and some of its partners therefore firmly committed to the creation and endowment of a private conservation trust fund with a view to generate a sustainable source of income for the country’s savannah ecosystems, with a view to complement other more variable allocations coming from the public budget, sport hunting and tourism. Through a broad national participatory process involving representatives from the Government, private sector, scientific sector and donor community, the “profile”, i.e. the main characteristics of the trust fund, have been designed.

- The primary objective of the fund will be to contribute to long-term funding of the conservation, sustainable natural resources management and eco-development in Northern Benin savannah ecosystems but with a secondary long-term objective to strengthen regional collaboration through funding of the conservation and management of the WAP. It is therefore proposed to call the fund “Fondation des Savanes Ouest-Africaines” (West African Savannah Foundation) but to provide the possibility to have several “financial windows”, starting with one window to the benefit of the Northern Benin savannah ecosystems.

- To ensure that it has the adequate legal structure, the fund will be registered as a charity under UK laws and fully recognized as a foreign charity with legal capacity to operate in Benin through a Country Agreement. The proposed governance structure will aim at minimizing costs while ensuring maximum technical efficiency. It is therefore proposed to have one independent and mixed Board of Directors with a majority of representatives from the non-governmental sector. The Board will be composed of a minimum of five members and a maximum of nine.  It will be responsible for overall management of the fund. An Executive Director, with support from a lean structure, will be responsible for the implementation of the Board’s decisions, and daily management.  An internationally recognized investment manager will manage the invested assets on the basis of guidelines provided by the Board.

- It is expected that the fund will be created during the third quarter of 2009 and that it will be fully recognized as a UK charity during the first semester of 2010. Current founders include the Government of Benin, which already formally set aside from its 2008 and 2009 budgets about 1,675,000 USD for the initial endowment of the fund, and the Government of Germany, which made a firm commitment in January 2009 to contribute to the capital of the fund for an amount to be defined later in 2009. However, further capitalization of the fund will be required if sustainable financing is to be secured: based on current financial estimates, which will be updated in 2010, the fund’s targeted endowment is about 21 million US (based on an estimated average annual return of 4%).  The proposed GEF contribution will play a critical role not only by increasing the amount of the fund’s capital and contributing to its start-up operation, but also to leverage other sources of funding, in particular through the implementation of a fundraising strategy targeting both the public and private sector.

- It is expected that the start-up phase of the fund’s operation will receive additional financial support from the German Government (through KfW) up to the end of 2010. Pending return on investment of the fund’s capital, the proposed GEF and IDA contributions, with potential other funding sources such as the European Union, would therefore be instrumental in two respects: (i) they will allowthe fund to: (a) finalize the development and strengthen the implementation of its strategic and management tools (including a monitoring plan), and (b) test its operating procedures through providing grants to the parks and other beneficiaries, and (ii) very importantly, they will provide the necessary means to ensure that, through those grants, the technical and financial management capacity is strengthened in the Northern Benin savannah ecosystems, by gradually scaling up efforts already in place to adopt more business-like practices in the protection, sustainable management and eco-development of the protected areas and adjacent zones.

- Describe the consistency of the project with national priorities/plans:

In 1994, the Government of Benin approved a Strategic Plan for the Conservation and Management of Protected Areas. This plan provides the major orientations and guiding principles regarding the institutional aspects of the National Protected Areas Strategy. It specifically underlines the need for decentralization of responsibilities and benefits in order to encourage the effective participation of local communities in protected area management. As called for in the above described Strategic Plan, the CENAGREF was created in 1996. By 1998, CENAGREF had drafted an Action Plan for the conservation and management of national parks (including the buffer zones and the transition areas). The Action Plan outlines the required actions, approaches, budgets and implementing arrangements and led to PCGPN, as presented above. The Government has also adopted a strategy to ensure long term and sustainable financing of protected area management. The strategy hinges on four pillars: (i) improving the level of resources generated by national parks, including through tourism revenues (a key component of the country’s growth strategy), (ii) maintaining sustainable level of costs associated with the management of parks, (iii) ensuring minimum and regular state financing, and (iv) searching for additional financing to support protected areas management effectiveness.  The project is fully consistent  with new law adopted in 2004, related to the sustainable management and protection of wildlife and biodiversity. The 2004 law includes special provisions for  the protection of  critical habitats, management of protected Areas, and prescribe participation of neighboring communities. The project will help implement the Programme for the Conservation and the Management of National Parks (Programme de Conservation et de Gestion des Parcs Nationaux-PCGPN) included in the National Strategy for Biodiversity Conservation adopted in 2002. This program  is highlighted in the on going PRSP (SCRP 2007-2009, Chapter 8), for its expected contribution to the sustainable and stable development of the country. As indicated above, the government of Benin has clearly shown its commitment to the creation of the trust fund as a key element of this strategy, through the creation of a steering committee responsible for guiding the creation of the fund and several decisions at the highest level to provide support to the creation process. The most significant evidence of Government’s ownership is however, as indicated above, the formal allocation to the fund’s endowment of an initial amount of c. 1,675,000 USD from the 2008 and 2009 state budget. As indicated above, at the field level, management plans have been developed and endorsed by the Government for both National Parks and successes recorded in the involvement of local communities, surveillance and ecological monitoring. Efforts have also been made at both headquarters and field level to increase the adoption of more business-oriented management practices.

- Describe the consistency of the project with gef strategies and strategic programs:

- The project is fully consistent with the Biodiversity Program's first Strategic Objective: To Catalyse the Sustainability of PA systems, and fulfils the eligibility criteria of the Strategic Programme 1: Sustainable Financing of Protected Area Systems at the National Level, through the establishment and capitalization of an endowment fund for the long-term funding of the Northern Benin savannah ecosystems. The project also fits within the Strategic Objective 3: Strengthening terrestrial PA networks as the ultimate objective of the fund will be the promotion of sustainable financing mechanisms for the whole WAP Complex, i.e. including neighboring parks and reserves in Niger and Burkina Faso.

- Outline the Coordination with other related initiatives:

- As mentioned above, the creation of the trust fund is the result of efforts coordinated by CENAGREF and the Government of Benin, with support from several partners, in particular the German Government (also represented in the steering committee responsible for the fund’s creation) which: (i) currently provides support to the creation process through its ProCGRN, and (ii) is expected to provide additional operational support as from mid-2009 to the end of 2010 with a view to finalize the creation and provides start-up support to the fund, in addition to its proposed endowment. This work is carried out in close cooperation with IUCN and its regional project on strengthening protected area management in Western and Central Africa (PAPACO).

- The IDA-funded proposed project on urban environment and national resource management project is also expected to contribute to the long-term funding strategy of the Northern Benin savannah ecosystems as it would channel funding through the trust fund pending return on investment to allow it to: (i) finalize the development and strengthen the implementation of its strategic and management tools (including a monitoring plan), and (ii) test its operating procedures through providing grants to the parks and other beneficiaries in order to strengthen their management capacity.   The European Union has indicated an interest in similarly contributing to the strengthening of the fund’s capacity to operate, as a way to maintain long-term impact of its investment in W over the last years. Preliminary discussions have also been initiated with the French Government (AFD and FFEM) for a potential contribution to the fund’s capital and process.

- Discuss the volue-added of GEF involvement in the project  demonstrated through incremental reasoning :

- Since the creation of the National Parks in Benin, several interventions have taken place with technical and financial support from the international community, but have come to an end, or are about to be completed. New project ideas are currently being developed with international partners to maintain or to improve the national protected area network and its performance but, despite Government’s contributions and field-based successful income-generating activities such as tourism and sport hunting, there is ultimately a financing gap that can only be filled through a long-term sustained flow of income such as that from a conservation trust fund. Without such a mechanism, serious negative effects will occur on the overall capacity to manage the Northern Benin savannah ecosystems. This includes, in particular, a lack of surveillance to ensure wildlife protection, and decreased cooperation between the national parks administrations and surrounding populations, both leading to detrimental over-exploitation of biodiversity resources.

- GEF’s contribution will not only be critical to increase the endowment of the fund and contribute to its effective operation, it will also be a key tool to convince other partners from the public sector, such as the European Union, German Government and French Government, and from the private sector, whether to contribute in capital or through channeling their funding via the trust fund.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved, and if possible including risk measures that will be  taken:

| Risks | Rating | Management Strategy |
| --- | --- | --- |
| - Poor governance and institutional instability of the trust fund | Moderate | The trust fund will be established as a private charity. As such, it will be independent from the Government, and not directly affected by institutional and political changes. Daily management staff will be kept to a minimum, competitively selected and will not be public agents. The fund will be overseen by a mixed Board with a majority of representatives from the non-governmental sector. The operations manual will provide for ways to ensure continued coordination between the fund and the authorities responsible for natural resource management, to ensure that joint priorities are addressed. |
| Return on initial capital from endowment fund insufficient to cover the costs of core management activities for the Northern Benin savannah ecosystems | High | Returns on the initial endowment will only be sufficient to cover partially core management needs but will come in addition to revenues from tourism, hunting and fishing, as well as contribution from the Government budget. Pending full endowment, a strategic exercise will take place on an annual basis to prioritize needs and allocate overall revenues accordingly. In addition, initial capital is expected to provide a strong signal to other donors and will help to gradually raise the necessary additional funds to cover the gap. |
| Other financiers will be reluctant to channel their funding via the trust fund | Moderate | The process to create the trust fund has involved a number of partners which, so far, have all have responded positively to the concept. They have, however, expressed a desire to see the fund operating in a sound, transparent fashion prior to placing their funding there. The capacity to manage IDA funds would provide the fund with an opportunity to demonstrate its financial and technical performance. |
| Climate change could have a negative impact upon the key biodiversity and habitats within the parks. | Low | Little information is currently available on the specific probable impact of climate change upon the West African savannah environment of the WAP Complex. The whole Complex has a good potential to mitigate climate change effects because of its immense surface and diverse landscapes. Currently, an ecological monitoring system is already taking place in Pendjari National Park and this will help assessing the level of impact and adopting adequate measures on the basis of recent and upcoming literature. . Especially the vulnerable RAMSAR sites in wetlands are closely surveyed. Keeping this monitoring system in place and extending it to other PAs should be one of the key activities to be funded in the future. |

- describe, if possible, the expected cost-effectiveness of the project:

- The project is highly cost effective because it will build on efforts already undertaken for the creation and initial funding of the operation of the fund. In addition, it is planned that the governance structure of the fund will be kept very light and administrative costs kept to a minimum. Cost effectiveness will be further enhanced by the fact that, rather than focusing on revenues alone, the project will aim to ensure that tools, such as analytical accounting, are put in place at all levels to increase the cost-effectiveness in financial management. Building capacities and systems for cost effective management will help to ensure that future revenues from the fund and other sources are used efficiently. .

- Justify the comparative advantage of GEF agency:

- The World Bank has a comparative advantage in this project by virtue of a pre-established partnership in supporting biodiversity conservation in Benin through the PCGPN untill 2005. Through this project, the World Bank has been helping to implement new approaches of independent co-management of the Benin National Parks and has developed significant experience and commitment during this period.  Furthermore, the World Bank continues to bring its global knowledge on biodiversity conservation and particularly the establishment of conservation foundations to the country, in particular by ensuring the involvement of staff also working on similar initiatives in the Congo Basin. The World Bank also brings the singular advantage of its ongoing macro-economic dialogue with the country, consistently ensuring that issues of biodiversity conservation remain a priority at the highest levels of Government.  Lastly, the World Bank continues to play its role in convening other donors and partners to join this effort to support biodiversity conservation in Benin and to help mobilize both operational funding and capital for the trust fund for Northern Benin Protected Areas, including through its own proposed IDA contribution.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the  country endorsement letter(s)  or regional endorsement letter(s) with this template).

| (Enter Name, Position, Ministry) Delphin AIDJI, Director Minitsry of Environemnt | Date: (Month, day, year) 07.21.2009 |
| --- | --- |

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO Endorsement.

| Agency Coordinator, Agency name | Signature | Date | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Steve Gorman Executive Coordinator The World Bank |  | September 1, 2009 | Paola Agostini | (202) 473 7620 | pagostini@worldbank.org |

Response to GEFSEC comments (Review Sheet of 8/31/09)

Comment 1 (Q3). Please, confirm the total amount of GEF resources needed for this project. In the available PIF, the GEFSEC understands that there will be no PPG request.

$2.2 million is the amount included in the Program Framework Document approved at the November 2008 Council. Here, the letter of endorsement mentions $2.1 million for the project GEF grant, including fees and any project preparation grant.

Response: No PPG funds will be requested for the project.

The GEF grant amount currently in the PIF is in line with the amount endorsed by the government who based ii on the available information that they possess on the allocation available. Given the tight timeline it is not possible to secure a revised letter now. However a revised letter with the allocated amount will be secured prior to CEO endorsement and the component cost will be adjusted accordingly to match the total allocation of 2.2 million under the SPWA.

Comment 2 (Q4). Please, revise the project name and include the prefix SPWA- as this is the practice for projects developer under a programmatic approach. If you confirm the same name, the right formulation will become: SPWA- Support to Protected Area Management.

- On the p1 (Part I - Identification, last section) please include the name of the parent program: Strategic Program for West Africa: Sub-component for Biodiversity.

Response: Changes have been made.

Comment 3 (Q6). Please, revise the total amounts in the last column, table B, p2

Response: Error has been corrected

Comment 4 (Q10). The project is doubtlessly a strong priority of Benin. However, the PIF needs to link this project with strategic and policy documents related to the environment, the biodiversity, and the sustainable development of the country.

Please include the relation with key national strategies and documents (PRSC, Biodiversity National Strategy, Ministry of Environment Strategic Plan, etc).

Response:  The linkages have been drawn in the revised PIF (see section B)

Project ID number will be assigned initially by GEFSEC.