REQUEST FOR BIODIVERSITY enabling activity

Proposal for Funding Under the GEF Trust Fund

part i:  project IDentifiers

| EA Title: | National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Botswana |  |  |
| --- | --- | --- | --- |
| Country(ies): | Botswana | GEF Project ID: | t.b.d. |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 4844 |
| Other Executing Partner(s): | Department of Environmental Affairs (Ministry of Environment, Wildlife and Tourism) | Submission Date: | October 19, 2011 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) | 42 |
| Check if applicable: | NCSA NAPA | Agency Fee ($): | 20,700 |

A:	EA framework

EA Objective: To integrate Botswana’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative “biodiversity planning” and strategizing process, including revising the country’s NBSAP to reflect effectively the emerging issues identified in the CBD Strategic Plan for 2011-2020

| ### EA Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Grant Amount ### ($) | ### Confirmed Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
| 1) Stocktaking and national target setting | TA | - By end of 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By 2012, national targets in response to the global Aichi Targets are developed. | 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in a participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to Botswana’s reality. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, Botswana taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). | 35,818 | 130,624 |
| 2) NBSAP update | TA | By early 2014, the Botswana’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP | 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for Botswana becomes ‘anchored’ into national development frameworks; it is revised and updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAP for Botswana is submitted to the CBD within the deadline set by the COP. | 107,382 | 167,132 |
| 3) National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms |  | - By 2013, complete the updating and improvement of national clearing-house mechanisms - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment | 3.1 National framework for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 A CHM section of the National Environmental Information System (www.eis.gov.bw) website is created according to guidance on CHMs; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity and it is kept up-to-date. 3.3. Immediate CBD reporting obligations are met by Botswana in a timely manner: the Fifth National Report is sent to the CBD by 31 March 2014. | 45,800 | 144,376 |
| Subtotal |  |  |  | 189,000 | 442,132 |
| EA Management Cost |  |  |  | 18,000 | 107,876 |
| Total EA Cost |  |  |  | 207,000 | 550,008 |

a   List the $ by EA components.

B:	Co-financing for the EA by source and by name

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | Ministry of Environment Wildlife & Tourism, Department of Environmental Affairs (Programme Cost-Sharing under the UN Operational Programme)* | Grant | 265,008 |
| National Government | Ministry of Environment Wildlife & Tourism | In-Kind | 120,000 |
| GEF Agency | UNDP Country Office Gaborone with own core funds* | Grant | 165,000 |
| Total Co-financing |  |  | 550,008 |

*  Both the Programme Cost-Sharing amount and the UNDP core funds (TRAC) have been budgeted for and will be managed together with the GEF contribution under the same budgetary award. Refer to Annex C for details. Refer also to co-financing letters in a separate file.

C:	Grant  Resources Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | EA Amount (a) | Agency Fee (b) | Total (c)=(a)+(b) |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF TF | Biodiversity (Focal Area Set Aside) | Botswana | 207,000 | 20,700 | 227,700 |
| Total Grant Resources |  |  |  | 207,000 | 20,700 | 227,700 |

D:	EA Management Cost

| ### Cost Items | ### [GEF only] Total Estimated Person Weeks | ### Grant Amount ($) | ### Co-financing ($) | ### EA Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 60 | 18,000 | 73,200 | 91,200 |
| ### International consultants* | 0 | 0 | 0 | 0 |
| ### Office facilities, equipment, vehicles and communications* |  | 0 | 10,676 | 10,676 |
| ### Travel* |  | 0 | 24,000 | 24,000 |
| ### Others** |  | 0 | 0 | 0 |
| Total |  | 18,000 | 107,876 | 125,876 |

*   Details to be provided in Annex A.     ** Other items to be clearly specified.

Additional information for Table D, if applicable:

If costs for office facilities, equipment, vehicles and communications, travels are requesting for GEF financing, please provide justification here:

n/a

part ii:  Enabling Activity JustiFication

A. Enabling Activity Background and Context

Botswana is a landlocked semi arid country of 582,000 square kilometres, and it shares a border with South Africa, Zimbabwe, Namibia and Zambia. The country is relatively flat, at 900 metres above sea level with occasional rocky outcrops. The bio-physical and natural resource endowments and their distribution partly account for the varied population density. The population of Botswana was estimated to be 1.7 million during the last census of 2001, and is concentrated in the eastern part of the country where extensive arable farming is practised, on account of the relatively more favourable climatic and soil conditions. Botswana’s major towns and villages are also found in this part of the country. The eastern part has relatively better infrastructure and economic development as compared to other parts of the country which explains the higher population densities. Botswana’s climate is semi-arid with seasonal and highly variable rainfall. The mean annual rainfall varies from less than 250 mm in the extreme south-western part of the country to over 650 mm in the north. The rains fall mostly in summer between October and March. Winter rainfall, though a rare phenomenon, has been recorded during some years between May and September. Botswana has achieved significant economic growth rates, which are amongst the highest in the world. Real economic growth averaged 13% in the twenty years after political independence. The high growth rates reflect the low resources at independence and the transformation of the economy from a primarily agrarian economy to a mineral dominant one. However, in recent years, the tourism sector of Botswana, which is largely biodiversity dependent, has grown significant in its contribution to the country’s economy. Still, the remarkable economic growth rates conceal social inequalities. The proportion of people living below the poverty datum line fell from 49% in 1993/4 to 30% in 2002/03 and is estimated to have reduced further to 23% by 2009. Poverty and unemployment remain major issues. These problems are further compounded by the declining rural economy, the narrow base of the non-mining productive sector and the inadequacy of human resources and entrepreneurial talent. The Government of Botswana continues to address these issues by delivering programmes on agriculture and manufacturing mostly targeted at the rural poor. Botswana’s major comparative advantage, as far as economic growth is concerned, is its diverse abundant wildlife and unique habitats. These resources are sought after by tourists globally and are a significant contributor to all developments that take place within the country. The tourism sector holds major potential for sustainable economic growth and job creation. Direct employment in the sector is estimated at between 10 000 and 15 000 employees, i.e. between 3% and 4% of the formally employed labour force. Tourist arrivals into the country have increased at a higher rate during the past six years, it is estimated that the sector’s contribution to GDP has grown to more than 4.5% while tourist arrivals grew from 794 544 to 1 036 558 at an average rate of 6.7 % during the same period. Though much of the country is characterized by nutrient-poor sandy soils, fossil river valleys and pans, with sporadic rainfall, Botswana harbours significant biodiversity, and it is counted among the 50 most species-rich countries in the world. The country is an in situ conservation front-runner, having established an impressive PA estate which incorporates some 40% of the total land territory or approximately 243,000 km, of which about 7.7% constitutes national parks, 10.3% game reserves, and 24% Wildlife Management Areas. An area of important biodiversity is the Okavango Delta and associated wetlands in Northern Botswana. The Okavango, a perennial river flowing into Botswana through Namibia from the Angolan highlands, drains into the Kalahari Desert to form a large complex of permanent and seasonal wetlands. These wetlands support viable populations of many threatened or endangered species of mammal and bird. They form a major part of the Zambezian Flooded Savannah ecoregion, one of WWF’s top 200 ecoregions of global significance. The Okavango Delta is one of the largest Ramsar sites in the world. Also part of this ecoregion is the Chobe-Kwando-Linyanti ecosystem in the north-east. Its variable flood regime and complex mosaic landforms all combine to create unusually high beta diversity. The ecosystem is home to huge herds of elephant, buffalo, and Burchell's zebra and high densities of predators such as Lion, Leopard, Spotted hyena and Cheetah; rare antelope species like Roan and Sable, Puku, Tsessebe, Eland, Red Lechwe, Waterbuck, and about 440 species of birds. The area is also listed as one of the 12 Important Bird Areas (IBA) in Botswana. In spite of this impressive endowment, Botswana’s biodiversity is under threat from a variety of factors. Threats include climate change, pollution and overexploitation. Botswana is a dry country with a fragile ecosystem and at a threat of being affected by climate. Botswana is expected to be faced with increased temperatures accompanied by unpredictable rainfall therefore affecting the biodiversity of the country as it will change the prevalent vegetation and vegetation cover, in turn affecting species types, composition and distribution. It is also projected that Botswana will experience decreased rainfall which could lead to water scarcity, and that climate change is likely to affect the Okavango delta (Botswana Environmental and Climate Change analysis, 2008). Water scarcity for an extended period would results in drought which leads to devastating effects on agriculture and biodiversity. Okavango delta faces a threat of reduced inflow from upstream and rainfall over the delta and the lower envelope of flooding is expected to be reduced by 68% (Okavango delta Management Plan, 2008). Pollution to water and air threatens biodiversity in Botswana. Air pollution occurs as a result of various human activities such as mining (sulphur and heavy metals), and agricultural (spraying of insecticides for control of tsetse fly in the Okavango delta). Water pollution, both surface and underground occur due to poor disposal of hazardous chemical from mines, industrial sites and human waste which contaminate the water sources. Leaching of toxic chemicals as a result of agricultural activities pollutes the underground water reducing its quality for consumption and other purposes. Overexploitation of natural resources leads to loss of biodiversity. Veld products such as phane, grapple plant and thatching grass are faced with a threat of being exploited and in Botswana these resources are essential for subsistence and thus buffers for poor people. A survey conducted in villages around Makgadikgadi area showed that natural resources used for subsistence purposes are firewood, grass and wild fruits/berries. It also indicated that 86.5% of all households use wood for purposes of cooking and lighting which could lead to their depletion (Makgadikgadi Framework Management Plan, 2010). Population pressure has led to exploitation of the natural resources thereby affecting biodiversity. Land area under pastoral farming has increased rapidly creating pressure on the rangelands. It has being shown that bush encroachment is likely to occur within several years and there is clear evidence of vegetation changes around livestock watering points and settlements (Biodiversity Analysis and Technical support team, 2008). The Department of Environmental Affairs (DEA) in the Ministry of Environment, Wildlife and Tourism (MEWT) is the national focal point for the CBD and for most of MEAs. The department is responsible for coordination of environmental issues to ensure environmental sustainability. It works on CBD issues in partnership with relevant stakeholders nationally. Key among the stakeholders is the Department of Wildlife and National Parks (DWNP) which deals with the fauna aspect, the Department of Forestry and Range Resources (DFRR) dealing with flora, and the Ministry of Agriculture (MoA) on issues relating to agro-biodiversity. In ensuring sustained stakeholder engagement and more enhanced decision making processes as well the provision of overall guidance in the management of biodiversity is the National Biodiversity Authority (NBDA). It is multi-stakeholder committee that works with the national focal point on all national issues that concern the management of biodiversity. The management of biodiversity in Botswana continues to improve as mechanisms have been put in place to provide support to NGOs/CBOs. MEWT has the Community Conservation Fund, Community Trust Fund and the NGO Assistance Fund. Through these modalities, community organisations continue to benefit financially and technically. This greatly assists in terms of biodiversity management at the grassroots level. In terms of sustainability in the availability of financial mechanisms for biodiversity related activity, the MEWT has recently established the National Environment Fund (NEF) which will be used to Fund biodiversity related activities and other environmental management proposed by all stakeholders. It will be used to also tap on the willingness of the private sector to engage financially and output wise on the environmental agenda. It is a structure that will enhance the achievement of convention objectives. The current challenges in attaining visible impact in biodiversity management in Botswana speak mainly to disparate biodiversity planning and the low integration of biodiversity concerns and targets in other sectors, especially production sectors. Pilot work done through the University of Botswana’s Okavango Research Centre, UNDP and the GEF has provided some of the impetus to increase visibility of biodiversity management. The current planning in Botswana cascades from the 11 District Development Plans to the National Development Plan. The challenge is to reflect enough of the community-level development issues which include the management of biological resources and production inputs, and their conservation requirements; as well as review of sectoral plans and policies to identify potential threats to biodiversity. The NDP has been a sector-based plan but changed the current one (NDP-10) to focus on themes that cover multiple sectors. This presents a better opportunity for integrating biodiversity into planning. An additional challenge to biodiversity planning is the lack of evidence on economic benefits of biodiversity mainstreaming into the various production sectors. Work through the UNDP/UNEP Poverty and Environment Initiative is only starting but presents an opportunity for generating the economic evidence to link agriculture, tourism and water sectors to biodiversity. - National Reporting to CBD. Reports; Date of Submission to CBD Secretariat; Current Status*; Comments. National Biodiversity Strategy and Action Plan; 5th May 1998; Final; Was under implementation for approximately 6-7 years. It became outdated sometime in the mid 2000s.. Revision of NBSAP; 14th October 2010; Final; The strategy was finalised in 2007 and covers the period 2006-2011. It was implemented but was only formally submitted to the CBD in 2010. It is now due for updating again, to address new guidance from the Convention, as well as a number of emerging threats to biodiversity and new opportunities for integrating biodiversity into national development planning.. 1st National Report; 5th May 1998; Final; Submitted to the CBD.. 2nd National Report; 16th May 2001; Final; Submitted to the CBD.. 3rd National Report; 14th May 2005; Final; Submitted to the CBD.. 4th National Report; 19th May 2009; Final; Submitted to the CBD.. - Capacity Needs Assessments carried out YES NO. Start Date: 2004; End Date: 2009. Please list all of the CBD Program of Work and cross-cutting themes that were addressed in the Biodiversity Enabling Activities Capacity Needs Assessments:; Dates. - Assessment of Capacity Building Needs in biodiversity monitoring programmes, including taxonomy; 2004-2008. - National Capacity Self- Assessment: Cross-cutting capacity needs assessments for the implementation of the Rio Conventions This was conducted, with a focus on government institutions with mandates for implementation of CBD, UNFCCC, and UNCCD.; 2004- 2009. 3) Clearing House Mechanism (CHM) established?; YES NO. CHM link(s):; The Department has completed the groundwork necessary for establishing a national CHM website as part of the National Environmental Information System (www.eis.gov.bw). As part of this project, the architecture will be created to complete the process, establishing the CHM facility online and linking it to the CBD’s global CHM networks to enable reporting and information and knowledge exchange on biodiversity.. Is the CHM website maintained up to date?; YES NO. How many people currently operate and maintain the national CHM?; n/a. How many people visited the national CHM website in the past 12 months?; n/a.

B. Enabling Activity Goals and Objectives

The Baseline Project: The Current NBSAP and the new CBD Strategic Plan The new CBD Strategic Plan, adopted at CoP-10 in 2010 in Nagoya, clearly addresses the need for updating NBSAPs, stating in Target 17 that “By 2015, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan.” The strategic plan also covers a range of issues that will need to be incorporated into the revised NBSAPs, including guidance to countries to: a) fully realise the value of biodiversity and ecosystem services, and incorporate these values into national and local development and poverty reduction strategies (Targets 1 and 2); b) increase the global terrestrial protected area estate from 12% to 17% and the marine estate from 6% to 10% (Target 11); c) restore and safeguard key ecosystem services, especially for water, health and livelihoods (Target 14); and d) strengthen ecosystem resilience to climate change and promote ecosystem-based approaches to climate change adaptation and mitigation (Target 15). Although the 2nd NBSAP for Botswana was concluded in 2007, and implementation of some elements began at that time, it was formally submitted and accepted by the CBD only at a late stage – in October in 2010. The 2nd NBSAP was prepared to cover approximately a 5 year period, although some activites have a longer time frame. Although many of the strategy’s elements are under implementation, its time span is reaching the end. A number of new factors are now in operation, necessitating the development of a revised NBSAP for the period 2012 - 2016. Firstly, there are a number of new policies, frameworks and laws that have been put in place since 2007, including the Framework Management Plan for Makgadikgadi Wetlands Systems, the Okavango Delta Management Plan, the Environmental Management Bill, the Draft Forest Policy and the Draft Wildlife Conservation Act. Secondly, the picture has changed since the last revision of the threats to biodiversity, with new knowledge on the threats posed by climate change, and emerging threats from increased poaching and wildfires, which need to be addressed in innovative ways. Finally, there are exciting new opportunities for mainstreaming biodiversity into local, district and national development planning, using the new structure of the National Development Plan. This includes ensuring that biodiversity objectives are taken up in development programmes, such as Botswana’s Poverty Eradication Drive, food production initiatives under Agriculture, Rural Development and Economic Diversification Drive. A particular opportunity exists for this enabling activities project to draw on and add value to the GEF-funded project on “Strategic Partnerships to Improve the Financial And Operational Sustainability of Protected Areas” currently under implementation, which aims to develop a strategy and implementation plan for PA financing, as this is an important element of the overall plan to resource strategic priorities for biodiversity conservation nationally. Synergy with existing tools will also be ensured, with a new emphasis on economic valuation, in line with the outcomes of the 10th Conference of the Parties to the CBD. The NBSAP will create the framework through which biodiversity concerns can be incorporated into plans, programmes and projects using Strategic Environmental Assessment and Environmental Impact Assessment, Natural Resources Accounts (water, minerals and livestock), Economic Valuation of some key resources (Okavango Delta Ramsar Site and Makgadikgadi Wetland Systems) and the Botswana Environment Outlook and State of the Environment Report. Finally, there is a need to ensure better synergy between the NBSAP and the country’s approach in terms of the other major Conventions - to adaptation to climate change and sustainable land management. The adoption of the CBD Strategic Plan sets a higher bar for biodiversity management worldwide and the Government of Botwana sees the need to step up its efforts to help meet global targets. Much of the importance of the 3rd NBSAP will lie in its ability to catalyze active stakeholder participation in the process, rather than simply emphasizing the production of a document. This enabling activities project is designed in such a way as to draw stakeholders into the process of tackling the key elements of the CBD Strategic Plan’s Aichi Targets, setting appropriate national targets, drawing out the implications for stakeholder mandates and budgets, and keeping the targets and mechanisms to achieve them top of mind at all times. The new NBSAP will include: - A plan for integrating the value of biodiversity into national and local development and poverty reduction strategies and planning processes, and natural resources accounting process (undertaken for minerals, livestock and water) and reporting systems, as appropriate (Target 2) - A plan for creating incentives and removing harmful subsidies (Target 3) - A plan for developing landscapes that have sustainable production and consumption and ensure the use of natural resources falls well within safe ecological limits. (Target 4) - A plan for fully implementing the Programme of Work on Protected Areas, including increased protection and landscape/seascape connectivity (Target 11) - A plan for restoring and safeguarding ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being (Target 14) - A plan for strengthening ecosystem resilience and the contribution of biodiversity to carbon stocks, including the restoration of at least 15 per cent of degraded ecosystems (Target 16) - A plan for the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources (Target 20). Proposed Response and Rationale: The new generation of BD EA. This project seeks to fully incorporate the above issues into the NBSAP. This ‘new generation’ of NBSAP will help set a regional standard of excellence by creating a national road map for achieving the Aichi Targets. Special emphasis will be placed on mainstreaming biodiversity into development plans, incorporating protected area networks and sustainable production systems into ecosystem-based climate adaptation and resilience plans, and creating sustainable finance for biodiversity conservation through the full valuation of key ecosystem services. Alignment with GEF Focal Area Outcome(s): BD5 Objective: Integrate CBD Obligations into National Planning Processes through Enabling Activities (herein serving as the ‘Project Development Goal’): Focal Area Outcome 5.1: Development and sectoral planning frameworks at country level integrate measurable biodiversity conservation and sustainable use targets. The Project Objective is: To integrate Botswana’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020. This will be achieved through the following Outcomes (corresponding to components described in detail below): - Outcome 1 – A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets - Outcome 2 – The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience - Outcome 3 – National frameworks for resource mobilization, Convention reporting and exchange mechanisms are established and strengthened Refer to Part I, Table A and to the next section for more details. How the project plans to build national capacity Botswana has previously undertaken assessments of existing capacity, including through the National Capacity Self-Assessment process and the National Biodiversity Support Programme. It has also completed activities to build capacity for the implementation of the UNCCD, UNFCCC and CBD as well as in related specialised areas such as environmental impact assessment. Despite these efforts, the impressive qualifications of staff in some departments, as well as the institutional mechanisms that have been established, individual, institutional and systemic capacity constraints are still perceived. These constraints include: - lack of technical skills in specialised areas (e.g. operating climate change models and interpreting results) - lack of specific competencies, such as environmental law, intellectual property or reviewing EIA reports - the absence or inadequacy of holistic thinking within the different disciplines involved in environmental management, which is increased by limited team work - lack of prioritisation of issues that should be addressed, given limited capacity in some departments - fragmented responsibilities across institutions (for biodiversity management) - insufficient coordination between government institutions - inadequate financial and technical capacity within community organisations - absence of measures of the impact of environmental interventions - lack of negotiation skills - discontinuous and inadequate engagement with the secretariats of the MEAs between the meetings of the Conference of Parties. A number of these areas will be addressed through the project, which aims to develop capacity in Botswana at the individual level, the organizational level and the systemic level. Examples of each of these in elation the gaps identified above are outlined in the table below. Individual; It is anticipated that all the individuals participating in the process of undertaking biodiversity planning to support the implementation of the CBD Strategic Plan 2011 – 2020 will develop their capacity significantly through the process. This includes local project staff and consultants, as well as the member of the multi-stakeholder working group and the specialist sub-group of the working group. The specialist group, in particular, will benefit from being part of the national target setting exercise, guided by the experience of the international consultant. The process of taking stock of biodiversity planning efforts until now will develop participants’ evaluative capacity, while participating in defining strategic priorities will develop their analytical capacity. The teamwork involved and the broad, interdisciplinary nature of the exercise will contribute towards the development of holistic thinking within the different disciplines involved in environmental management. This will be further enhanced by the widening of the discussion to include mainstreaming into national development planning – examining the links between biodiversity conservation and socio-economic development, and the implications for different economic sectors and national development trajectories.. Organizational; UNDP’s approach to Biodiversity Enabling activities in GEF-5 goes beyond the production of documents and the development of a website. Much of the importance of the 3rd NBSAP will lie in its ability to draw various levels and sectors of government into the process of tackling the key elements of the CBD Strategic Plan’s Aichi Targets, contributing to the achievement of national targets. The involvement of these role-players in this enabling activities project will develop their capacity by actively involving them in drawing out the implications of the targets for their mandates and approaches to resource allocation. Organizational capacity will also be built through the process of developing a permanent framework for reporting to the CBD and for maintaining the CHM with vital, up-to-date information. Specifically, organizational capacity will be built through taking stock of the existing NBSAP and identifying barriers to its implementation, setting targets and priorities, developing implementation plans for the revised NBSAP, working out how to develop capacity further, developing the clearing-house mechanism, and developing a permanent framework for reporting to the CBD.. Systemic; The approach that UNDP has developed for Biodiversity Enabling Activities in GEF5 is transformational with respect to systemic capacity elements (i.e. policy, economic, regulatory, and accountability frameworks within which organizations and individuals operate). The aim is to ensure that the objectives, targets and guidance from the CBD Strategic Plan (2011-2020) become fully anchored into national development frameworks. This will be achieved by the development of the following new aspects of the CBD strategic plan: (i) the valuing of ecosystem goods and services; (ii) mainstreaming; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. The knowledge developed through these activities will become part of Botswana’s new NBSAP and will have a greater chance of influencing and even becoming policy. In particular, the following activities are specially targeted at building systemic capacity: - assessing and integrating ecosystem services through economic valuation - mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies - incorporating climate change issues into NBSAPs - integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan - securing sustainable finance for NBSAP implementation - monitoring and reporting on the status of biodiversity under climate change scenarios..

C. Describe the Enabling Activity and Institutional Framework for Project Implementation

Detailed Description of Activities per Project Component / Outcome The description that follows indicates precisely how the project will develop national capacity and how the project will ensure the sustainability of its outcomes. This description has been organized in five modules (I -V), following the GEF’s guidance, but which for the sake of simplicity were grouped within the three already mentioned Components / Outcomes. The following are the modules: Component; Outline of modules for NBSAP Revision and Related Activities; Indicative percentage of total GEF funding in the proposal. 1; I. Preparation; 10%. II. Setting national targets, principles, & main priorities of the strategy; 10%. 2; III. Strategy and action plan development; 55%. 3; IV. Development of implementation plans and related activities; 10%. V. Institutional, monitoring, reporting and exchange; 15%. Component 1. Stocktaking and national target setting Key outputs expected under this component includes the following: 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to Botswana’s reality. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, Botswana taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). Key products or publications (may be combined into one): - Brief Review of the Biodiversity Planning Process in Botswana - Biodiversity Targets for Botswana as part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 In connection with the above outputs and deliverables, and as a result of the activities outlined below, Botswana will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By end of 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By 2012, national targets in response to the global Aichi Targets are developed. Key activities (I-II): - Preparing for the NBSAP revision - Taking stock of the NBSAP and identifying barriers to its implementation: This activity will involve the Group of experts in biodiversity and economic and development sectors in Botswana. Under the leadership of the Enabling Activities Technical Manager and with support from the NBSAP Lead Consultant, they will undertake a rapid stock-take of existing plans, policies and practices, and of the root causes of biodiversity loss. The aim of the stock-take is not only to identify key threats, but to understand the drivers behind these threats, as well as the key aspects of the policy environment that are barriers and challenges to effective conservation/sustainable use. Based on existing studies and analyses, the emphasis of this activity will be on identifying key gaps in the existing Botswana NBSAP, understanding the primary drivers and root causes, and identifying the means of overcoming existing barriers and challenges. Because of the emphasis in this new NBSAP on mainstreaming into national development planning, the scope of the stock-taking exercise will be broad. - Stakeholder consultation and participation: Beyond the Group of experts in biodiversity and economic and development sectors, which is a more restricted, the Enabling Activities Technical Manager will establish and convene a wider working group (or several thematic working groups to be defined) to oversee a robust consultative process that engages representatives from key sectors, administrative leaders, and traditionally under-represented groups. Within this working group, the specialist sub-group will work more closely with the lead NBSAP consultant to support the development of specific products under this project and ensure the broad participation (TOR are in Annex A.) The aim is to develop and sustain a participatory process in order to increase the likelihood of successful implementation of the NBSAP. This is especially important relative to the goals of mainstreaming biodiversity into national development plans, and promoting resilient landscapes that include production sectors. - Specific steps in this process will include: - Establishing a multi-stakeholder working group involving relevant stakeholders interested in biodiversity conservation and development issues to oversee the enabling activity project and development of the NBSAP - Explicitly identifying key stakeholders’ interests, and desired outcomes - Identifying potential conflicts and trade-offs, and work towards mutually acceptable solutions, including strategies that serve mutually beneficial interests and achieve mutually beneficial outcomes - Embedding and institutionalizing these strategies in the institutions, policies, agreements, programs and mechanisms of each sector. - Setting targets - Setting targets and priorities: This activity will be overseen by the specialist group within the working group, guided by the Project Steering Committee, and supported by an international consultant with technical expertise in biodiversity target setting. The process will focus on setting specific, measurable, achievable and time-bound targets for the 3rd NBSAP, based on the global Aichi Targets, including targets on restoration of ecosystems, protected area coverage, overall biodiversity loss, and other aspects of the Strategic Plan. Botswana’s target setting, which will be linked to priority setting among different aspects within the NBSAP, will be completed by CoP-11. Component 2. NBSAP Update Key outputs expected under this component includes the following: 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for Botswana becomes ‘anchored’ into national development frameworks; it is revised and updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. . This is supported by consultations and the following specific studies: - Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) - “Localisation” of the TEEB (The Economics of Ecosystems and Biodiversity): Assessing and capturing value in ecosystems’ goods and services in Botswana - Exploring and costing options for ecosystem-based adaptation to climate change in Botswana 2.2 The updated and fully endorsed NBSAP for Botswana is submitted to the CBD within the deadline set by the COP. Key products or publications: - Third National Biodiversity Strategy and Action Plan for Botswana - Sub-product 1: Challenges and Opportunities for Botswana’s Protected Areas in the 21st Century - Sub-product 2: Study on Ecosystem Valuation and Sectoral Mainstreaming of Biodiversity in Botswana - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Botswana In connection with the above outputs and deliverables, and as a result of the activities outlined below, Botswana will strive to achieve the following outcome vis-à-vis its CBD obligations: - By early 2014, the Botswana NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP. Key Activity (III): - Developing the NBSAP This step will seek to achieve the following: (i) Developing the strategy and actions to implement the agreed targets though national consultations; (ii) Application of the NBSAP to sub-national entities through sub-national and local consultations; and (iii) Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations. While the project will focus on updating all aspects of NBSAP, it will place particular emphasis on those aspects that are highlighted in the 2011-2020 CBD Strategic Plan. These include the following: - Assessing the implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) in light of emerging trends affecting Protected Areas in the 21st Century: During the CBD COP10, UNDP launched in collaboration with the GEF and the CBD Secretariat, a seminal publication on the lessons and it has learned from its GEF portfolio with respect to protected areas. Following the methods outlined in the publication, Botswana’s performance will be evaluated in relation to these lessons about the management of protected areas, especially in light of key challenges that these will face in the 21st century, such as increased competition for land and water, climate change and scarcity of public funding. This study will be part and parcel of the sub-products that will corroborate to Botswana new NBSAP. The following themes will be touched upon: - Enabling Policy Environment for Protected Areas - Management Planning, Research, Monitoring and Assessment - Assessment of Threats to Protected Areas and of ecosystem restoration needs - Protected Area Governance and Participation - Protected Area Capacity - Sustainable Finance - Protected Area Networks and Ecological Gap Assessments (including in scenarios of climate change) - Connectivity Corridors and Transboundary Protected Areas - Assessing and integrating ecosystem services through economic valuation: The study on The Economics of Ecosystems and Biodiversity (TEEB) has drawn attention to the global economic benefits of biodiversity and ecosystem services and to the growing costs of biodiversity loss and degradation. Botswana has done some valuable groundwork through the UNEP-UNDP Poverty Environment Initiative (PEI), which needs to be built on through this enabling activities project. However, Botswana has not yet explicitly linked the value of biodiversity and ecosystem services to its own national development goals, including poverty eradication and sustainable livelihoods. Through this activity, the project will be able to demonstrate the benefits and values of ecosystems and biodiversity at a national level, and better link ecosystems and priority sectors in national development plans, in order to guide allocation of resources. The aim is to strengthen the point that biodiversity not only underpins human well-being, but that biodiversity and associated ecosystem services can make a significant contribution to poverty reduction and economic development. By engaging national specialists and providing support from global specialists, hard economic data will be collected and processed at the country level to demonstrate the costs and benefits of investing in biodiversity management. Capacity to carry out the assessments and make important links to priority economic sectors will be simultaneously built within the country. The local consultant will access the relevant data and the international consultant will provide support on analysing the data to “make the case” for biodiversity and facilitate the process of mainstreaming biodiversity into sectoral planning through concrete biodiversity valuation examples. - Specific steps in this process include: - Identify and assess the full range of values of key ecosystem services within the country, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the national TEEB valuation results, the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g., water, carbon), and existing global and regional maps and overlays of key ecosystem services - Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use. - Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. - Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. - Mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies: Mainstreaming has been defined as the internalization of biodiversity conservation goals into economic and development sectors, policies and programs, such that they become an integral part of their functioning of these sectors. - The Project Steering Committee, guided by the NBSAP lead consultant, will make a selection of 4-5 priority sectors to focus on for the proposed Biodiversity Planning process, selecting from the following list: Agriculture Forestry Wildlife Livestock Tourism, Trade, Transport Energy Mining Development Planning & Finance Water - The Project Steering Committee, guided by the NBSAP lead consultant, will make a selection of 4-5 priority development areas / topics to focus on in the project, selecting from the following list: Land-use management, including spatial and infrastructural development planning Development finance Poverty alleviation Rural development and livelihoods Food security Local development and decentralization Rights of indigenous groups Gender Climate change mainstreaming Population & urban planning Health provision, including traditional medicine - Incorporating climate change issues into NBSAP: The previous NBSAP did not adequately address aspects of climate change. Botswana already has a gap analysis completed in 2009 of the protected area estate in relation to biodiversity conservation priorities. This will be updated through this activity, taking into account the following additional factors, and feeding the results into the NBSAP: - identifying, protecting and appropriately managing areas important for carbon sequestration; - updating the country’s ecological gap assessment to include predicted future distribution of biodiversity under climate change scenarios; - assessing the impact of climate change on the functioning of ecosystem services, such as water; - identifying areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors - identifying areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation. Component 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms Key outputs expected under this component includes the following: 3.1 National frameworks for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBSAP; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 A CHM section of the National Environmental Information System (www.eis.gov.bw) website is created according to guidance on CHMs; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity and it is kept up-to-date.. 3.3 Immediate CBD reporting obligations are met by Botswana in a timely manner: the Fifth National Report to the CBD by is due by 31 March 2014. Key products or publications (first two may be combined into one): - Straightforward and feasible NBSAP implementation plan, which ensures the effective implementation of the Action Plan contained in the NBSAP - Fully functional CHM for Botswana, based on best international practice on the matter - Fifth National Report In connection with the above outputs and deliverables, and as a result of the activities outlined below, Botswana will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By 2013, complete the updating and improvement of national clearing-house mechanisms - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment Key Activities (IV-V): - Developing implementation plans This activity will focus on developing an overall plan for implementing the NBSAP. This implementation plan will include the following components: - Developing an overall implementation plan: The primary output of this activity is an overall implementation plan that delineates major steps, responsible parties, costs for main activities, expected outcomes and a timeline - Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan: Botswana will place particular emphasis on those aspects of Target 11 from the CBD Strategic Plan, including our plans for improving management effectiveness, sustainably financing protected areas and integrating protected areas into the wider landscape. - Securing sustainable finance for NBSAP implementation: Article 20 of the Convention mentions the need for Parties “to provide, in accordance with its capabilities, financial support and incentives in respect of those national activities which are intended to achieve the objectives of this Convention.” In the past few years, there has been a wide proliferation of innovative biodiversity finance mechanisms, such as payments for ecosystem services, conservation trust funds, biodiversity offsets and bio-carbon funding, among many others. We are still in the early stages of exploring these mechanisms. This activity is critical in ensuring that resources are in place to implement the NBSAP. It will focus on the following: - Identifying the existing financial gap for implementing the NBSAP - Identifying potential sources of revenue for filling these gaps - Assessing the feasibility for these revenue sources - Developing a detailed plan for operationalizing these revenue sources - Assessing and strengthening capacity needs: One of the primary areas of enabling activities is the assessment of capacity needs. The decisions at CoP-10 place new and ambitious demands on countries, including requirements to protect and sustainably manage their lands and water, to develop comprehensive plans that integrate climate change into their land use, development and sectoral plans and strategies, and to develop appropriate biodiversity and climate policies, laws and incentives. This activity will ensure that Botswana develops a road map for strengthening these specific capacities. As per the NCSA report, Botswana is currently faced with a number of challenges on prevailing capacity needs. The ‘Needs Assessment’ will be incorporated into the NBSAP Implementation Plans. The critical components vary from systemic, institutional down to individual capacity. Building on existing capacity needs assessment, and using existing guidance, the Enabling Activities Technical Manager, with support from the Working Group and the Lead NBSAP Consultant, will identify the following gaps inter alia, along with capacity-building strategies to fill those gaps: - Development of relevant and specific biological diversity (BD) regulatory framework under overarching national environmental polices including development of ABS legislation: policy, regulations and guidelines - Development of district specific biodiversity action plans for purposes of role clarity and implementation and prioritise biodiversity projects based on specific needs of respective districts - Designation of various NFP across the economy for the programmes of work under the CBD and operationalize the obligations and regulations of the convention. - There is need for skills that implementers within and outside government need including Environmental law, Ecology, Biotechnology. The staff from different implementing departments need skills on raising awareness and implementation of the CBD including budgeting and financial management and Project management - Institutionalizing, monitoring and reporting - Monitoring and reporting on the status of biodiversity under climate change scenarios: Monitoring and reporting on the status of biodiversity is a key aspect of several Programmes of Work within the CBD. To date, efforts to monitor and report on the status of biodiversity have been sporadic and have typically not taken into full account the status and trends of biodiversity, the status of effective conservation, the contribution of ecosystem services (such as water and carbon), and the likely impacts of climate change on biodiversity and ecosystem services. Through this project, we will ensure that future monitoring and reporting on the status of biodiversity and ecosystem services is comprehensive, and fully incorporates climate change issues. - Developing clearinghouse mechanisms (CHM): Botswana has a done the groundwork to gather information for an up-to-date CHM which captures not only biodiversity information but includes all thematic areas within the environment domain. This project will enable this information to be made available online through the National Environmental Information System (www.eis.gov.bw) and to link to the CBD network and other international networks. - Developing a permanent framework for reporting to the CBD: Parties to the CBD committed to submitting a fifth national report by 2014. In this project, Botswana will submit a 5th National Report that fully covers the NBSAP, key changes in the status and trends in biodiversity status, threats and conservation, and will develop a long-term reporting framework that will enable us to better track changes over time. This framework touches three aspects, which will be strengthened by a number of different activities under this project: (i) the abovementioned setting up of the CHM for Botswana; (ii) the strengthening of national capacity and leadership for managing biodiversity planning in the country; and (iii) the availability of national finance on a recurrent basis for the purpose of CBD reporting, so that GEF and other mechanisms become gradually complementary in this respect. Project consistency with national strategies and plans or reports and assessments relevant for the CBD, as well as other cross-cutting assessments and priority setting exercises Botswana ratified the UN Convention of Biological Diversity in 1995 and it is making important efforts to fulfil its obligations under it, as well as to implement the Convention at the national level, including several of its Programmes of Work. Yet, there are gaps linked to national capacity and which Botswana needs external assistance to address. Part II, Section A in this proposal contains a matrix listing different reports and assessments relevant for the CBD, as well as other cross-cutting assessments and priority setting exercises. This proposal fits well with the progress presented in the matrix, including the several gaps that need to be fulfilled in connection with this progress so far. This proposed enabling activities project is consistent with the following national policy, legislation, plans and strategies: - National Biodiversity Strategy and Action Plan (2007), although now outdated - Framework Management Plan for Makgadikgadi Wetlands Systems - Okavango Delta Management Plan - Wetlands Inventory Report - Emerging legislation: Environmental Management Bill, Draft Forest Policy, Draft Wildlife Conservation Act Project implementation arrangement: The project will be implemented over a period of 3.2 years. The Department of Environmental Affairs (DEA) under the Ministry of Environment, Wildlife and Tourism (MEWT) is the government institution responsible for the implementation of the project and will act as the Executing Agency. UNDP is the Implementing Agency for the project and accountable to the GEF for the use of funds. The project is nationally executed (NEX), in line with the Standard Basic Assistance Agreement (SBAA, 15-Feb-1982) between the UNDP and the Government of Botswana (GoB). The overall responsibility for the project implementation by DEA implies the timely and verifiable attainment of project objectives and outcomes. The DEA will provide support to, and inputs for, the implementation of all project activities. The DEA will nominate a high level official who will serve as the National Project Director (NPD) for the project implementation. The NPD will chair the Project Steering Committee (PSC) as well as the working group and specialist sub-group set up to drive the stock-taking and target setting work in Component 1, and will be responsible for providing government oversight and guidance to the project implementation. The NPD will not be paid from the project funds, but will represent a Government in kind contribution to the Project. The NPD will be technically supported by the Enabling Activities Technical Manager and his/her team, as well as by the UNDP’s technical backstopping provided by the UNDP/GEF Regional Technical Advisor responsible for the project and the UNDP Environment Focal Point at the Country Office. All consultants hired by the project will be recruited using standard recruitment procedures of the Executing Agency (Department of Environmental Affairs) and will report directly to the Enabling Activities Technical Manager and indirectly to the NPD. Some of the first tasks of the Enabling Activities Technical Manager with respect implementation are to: (1) refine the TORs for project consultants assigning clear responsibility for specific products in accordance with the profiles of the selected candidates; (2) prepare detailed workplans for the project; and (3) ensure that consultants complete time sheets detailing activities. It is possible that technical expertise and support to implementation can be sourced from the University of Botswana, particularly from the Okavango Research Institute. Working closely with the DEA, the UNDP Country Office (UNDP-CO) will be responsible for: (i) providing financial and audit services to the project; (ii) recruitment of specialised consultants and service providers (when requested by DEA); (iii) overseeing financial expenditures against project budgets approved by PSC; (iv) appointment of independent financial auditors; and (iv) ensuring that all activities, including procurement and financial services, are carried out in strict compliance with UNDP/GEF procedures. A UNDP staff member will be assigned with the responsibility for the day-to-day management and control over project finance. The existing National Biodiversity Authority (NBDA) will serve as the Project Steering Committee (PSC) and will be convened by the DEA, and will serve as the project’s coordination and decision-making body. The PSC will include representation of all the key project stakeholders. It will meet according to the necessity, but not less than once in 6 months, to review project progress, approve project work plans and approve major project deliverables. The PSC is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document. The day-to-day administration of the project will be carried out by a dedicated Project Coordinating Unit (PCU), comprising a Enabling Activities Technical Manager and Project Assistant, who will be located within the DEA offices. The Enabling Activities Technical Manager will liaise and work closely with all partner institutions to link the project with complementary national programs and initiatives. The Enabling Activities Technical Manager is accountable to the DEA, and the PSC for the quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds. UNDP’s comparative advantage for Biodiversity Enabling Activities UNDP has historically been the largest GEF implementing agency in terms of assisting countries in undertaking biodiversity enabling activities, having assisted more than 100 countries with it through several projects. These projects helped countries prepare their original Biodiversity Strategy and Action Plans, prepare their reports to the CBD COP, from the first to the fourth, and assess capacity needs in a number of countries. UNDP supported Botswana with its first generation of Biodiversity Enabling Activities. The project was financially closed in 2005 and produced all of its expected results. Botswana accessed funding for its fourth national report through the GEF UNDP-UNEP project in 2008 and also produced the expected report. The monitoring of this global project was carried out by the Botswana Country Office. Furthermore, UNDP has a large and active GEF biodiversity portfolio in Botswana and two professional staff dedicated to monitoring it. These synergies will be created primarily with the following projects, but not restricted to them: - The newly approved UNDP/GEF project under development “Improved Management Effectiveness of the Chobe-Kwando-Linyanti Matrix of Protected Areas” - The UNDP/GEF BiOkavango Project “Building Local Capacity for Conservation and Sustainable Use of Biodiversity in the Okavango Delta” - The UNDP/GEF Project “Strategic Partnerships to Improve the Financial and Operational Sustainability of Protected Areas” - The WB/GEF project “Human-Wildlife-Coexistence Management Project in Northern Botswana” The UNDP Country Office in Gaborone, Botswana includes an Energy and Environment Programme, with a dedicated Environmental Focal Point (EFP) supported by technical and administrative staff. The EFP is also supported by the Regional Technical Advisor for Ecosystems and Biodiversity for Eastern and Southern Africa, based at the Regional Services Centre in Pretoria, South Africa. Successful implementation of this proposed enabling activities project will also rely on UNDP's country-level coordination experience in integrated policy development, human resources development, gender issues, institutional strengthening, and non-governmental and community participation. All of these elements are all part of UNDP’s programme in Botswana. Project’s alignment with UNDP’s programme for Botswana This project is in line with the objectives of the United Nations Development Assistance Framework (UNDAF) for 2010 - 2016, which prioritises the environment and the fight against poverty. The UN-GoB Programme & Operational Plan of 2010-2014 places special focus on environmental matters and the protection of the Botswana’s biodiversity endowment as a key to its successful development. The relevant Environment Outputs identified by the Country Programme with respect to this project are: - Global environmental concerns and commitments integrated in national planning and policy - Improved awareness and understanding among decision makers and the public of linkages between environmental sustainability and human poverty and well-being - Improved national capacity to negotiate and implement global benefits. Stakeholder involvement in the implementation of the project NGO Fund under MEWT to assist NGOS in implementation of biodiversity related projects - allocated $500,000 during NDP 9 (2003-2009) Creation of Environment Fund to fund environmental reclamation projects by Community Based Organizations (CBOs) The stakeholder involvement element is embedded in the description of several activities within this proposal which will have a consultative and participatory character. A full stakeholder involvement plan will be developed in connection with the preparation of the UNDP Project Document that will operationalise this proposal at the level of UNDP, allowing Botswana to access the funding. The following is an indicative and non-exhaustive list of stakeholders to be involved: - 21 Community Trusts in Okavango region - Community Trusts in Chobe-Linyanti region, e.g. the Chobe Enclave Conservation Trust-CECT,Kazungula Lesoma Pandamatenga Community Trust-KALIPA - Ngamiland District CBNRM Forum - CBNRM Forum and support programme - People and Nature Trust - CARACAL - Ditshwanelo-Human Rights - Botswana Community Based Organisation Network - Botswana Council of Non-Governmental Network - Trust for Okavango Cultural and Development Initiatives - Birdlife Botswana - Kalahari Conservation Society - Private sector, especially game lodges, trophy hunting and safari companies - University of Botswana - Botswana College of Agriculture - Okavango Research Institute - Department of Environmental Affairs - Department of Wildlife and National Parks - District Land Use Planning Unit - Makgadikgadi Pans Wetland System - Ministry of Communications, Science and Technology - Ministry of Environment, Wildlife and Tourism - Ministry of Finance and Development Planning - National Liaison Committee These stakeholders will be consulted in the establishment of a multi-stakeholder working group, and where appropriate will be directly involved in the working group, which will drive the stock-taking and target-setting work to be undertaken in Component 1. They will equally be involved in the implementation of the remainder components. It will be important at this early stage of the project to draw on the wide range of expertise represented by these stakeholder groupings which includes: - tertiary and research institutions with extensive local scientific, technical and research capacity - government departments and non-governmental organisations with experience in policy formulation and implementation - NGOs and community-based organizations with experience in implementing biodiversity conservation and sustainable development work on the ground, as well as an understanding of the needs of local communities whose livelihoods are directly dependent on biodiversity, and who are vulnerable in specific ways to climate change - private sector role-players who are currently investing in biodiversity conservation and tourism, and have the potential to contribute further to closing the biodiversity “funding gap” - sectors of government at various levels whose mandate influences or is influenced by biodiversity conservation and who have the potential to contribute to mainstreaming biodiversity conservation into development planning and resource allocation. Gender marking Gender equality is enshrined in Botswana's constitution, and women have the same civil rights as men. The Botswana government has, however, identified the need to ensure that all legislation fully supports this principle. This is a complex undertaking because the country has a dual legal system in which common law and customary law exist side by side, as well as a long history of traditional laws, upheld by tribal structures and customary courts. As a result, the position of women in rural areas can be affected by restrictions on women’s property rights and economic opportunities. UNDP works with national and local partners in the region to accelerate the integration of gender sensitive policies in all sectors, including the environment, creating more an inclusive environment for both women and men. More specifically, this project will explore the nexus gender-biodiversity in Botswana through the different studies that will contribute to the country's new NBSAP. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men. Furthermore, gender marking implies the production of the following data by the project's year 2 and by its end: - Total number of full-time project staff that are women - Total number of full-time project staff that are men - Total number of Project Steering Committee members that are women - Total number of Project Steering Committee members that are men - The number of jobs created by the project that are held by women - The number of jobs created by the project that are held by men

D. Describe, if possible, the expected cost-effectiveness of the project:

Botswana has achieved an economic growth which is amongst the highest in the world, partly through transformation of the economy from a totally agricultural to a mineral-dominant economy. However, in recent years, the tourism sector of Botswana, which is largely biodiversity-dependent, has grown and contributed to the country’s economy. Government recognizes the importance of the biodiversity and tourism sector to the economy, but this has not yet been reflected fully in budgeting and planning processes, partly because the links between conservation and development have not been made clear. The proposed GEF project will ensure that a national strategy and action plan guides all stakeholders and partners in the conservation of these precious resources, in order to avoid duplication and to ensure the application of resources in the most critical areas. The cost-effectiveness of the proposed activities will further be ensured by combining government internal, national and international experience in implementing similar projects. Consultation costs financed by GEF will be kept to a minimum, as government and UNDP can finance much of it from co-financing resources. Other options were considered, e.g. the sub-contracting of an NGO or a management consultancy to carry the Enabling Activity on behalf of government. This was considered costly and also not effective with respect to stakeholder ownership and capacity building. It could also create a risk of bias in the development of what is to be a veritable national strategy.

E. describe the budgeted M&E Plan:

These costs are part and parcel of the project’s budget (see Annex E). They may be funded by either GEF or UNDP funds, including the Programme Cost-Sharing. Type of M&E activity; Responsible Parties; Budget US$ Excluding project team staff time; Time frame. Measurement of Means of Verification for Project Purpose Indicators, Project Progress and Performance (measured on an annual basis); Oversight by Project Manager Project team; To be finalized during the inception phase and determined as part of the Annual Work Plan's preparation.; Annually prior to ARR/PIR and to the definition of annual work plans. Simplified Biodiversity Enabling Activities Annual Project Review / Project Implementation Report (APR/PIR); Project Team UNDP-CO UNDP-GEF; None; Annually. Quarterly progress reports (QOR); Project team; None; Quarterly. Terminal Report; Project team UNDP-CO local consultant; $1,000 for printing costs; At least one month before the end of the project. Lessons learned; Project team UNDP-GEF Regional Coordinating Unit (suggested formats for documenting best practices, etc.); To be determined as part of the Annual Work Plan's preparation.; Yearly. Audit; UNDP-CO Project team; $2,000 in total To be included in the CO audit plan.; Yearly. TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses; ~ US$ 3,000.

F. Explain the Deviations from typical Cost Ranges (where applicable):

-- n/a--

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the country endorsement letter(s) with this template).

| Name | Position | Ministry | Date |
| --- | --- | --- | --- |
| Ingrid Mpundu Otukile | Chief Natural Resources Officer | Environment, Wildlife and Tourism | 09-29-2011 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Biodiversity Enabling Activity approval. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| Yannick Glemarec, UNDP/GEF Executive Coordinator |  | October 19, 2011 | Alice Ruhweza, Regional Technical Advisor, EBD Africa. | +27123548120 | alice.ruhweza@undp.org |

Annex A. Consultants to be hired for the Enabling Activity

| Position Titles | $ / Person Week [GEF only] | Estimated Person Weeks [GEF only] | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management |  |  |  |
| Local |  |  |  |
| Project Assistant (3.2 years or 168 weeks in total, of which 60 weeks are financed by GEF and the rest by the Programme Cost Sharing) | 300 | 60 | - Provide support on the general administrative requirements of the project, including those related to project management and funding. - Assist in ensuring that project Objective, Outcomes, Outputs and Activities are executed in a timely and appropriate manner. - Facilitate, guide and monitor the work of consultants, and approve their deliverables in association with the Project Committee. - Assist in project related activities, where required. These may include planning for meetings, local and national consultations, trips, and other project related activities. - Maintain linkages with national and international organizations and persons which/who can be of assistance to the objectives of the Project. - Maintain records of Project Committee meetings, decisions, actions etc. - Any other duties assigned by the Project Manager that have direct relevance to the project. Selection criteria: should have a Bachelor’s degree in management, administration, environmental management or related field with a minimum of 2 years project management experience. Knowledge and understanding of the relevant UN Convention, environmental issues in Botswana, good leadership, coordination, communication, and facilitation skills are essential. |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Enabling Activities Technical Manager (3.2 years or 168 weeks in total, of which 60 weeks are financed by GEF and the rest by the Programme Cost Sharing) | 600 | 60 | Managerial responsibilities (funded by co-financing covering approx 81 weeks): - Be responsible for the all general administrative requirements of the project, including those related to project management and funding. Technical responsibilities (60 weeks funded by GEF and the rest by co-financing): - Ensure that project Objective, Outcomes, Outputs and Activities are executed in a timely and appropriate manner. - Develop annual work plans and budgets, and submit these to the Steering Committee and to the UNDP Country Office for approval. - Develop TORs for Consultants for technical services, consultants, experts, and specifications of materials as required by the project, in consultation with the Project Director/UNDP. - Facilitate, guide and monitor the work of consultants, and approve their deliverables in association with the Project Committee. - Organize and assist in project related activities, where required. These may include planning for meetings, local and national consultations, trips, and other project related activities. - Establish and maintain linkages with national and international organizations and persons which/who can be of assistance to the objectives of the Project. - Provide timely reporting of project status as required by the Project Committee and the UNDP. - Maintain records of Project Committee meetings, decisions, actions etc. - Coordinate with other initiatives and programs whose outcomes and outputs are relevant to this project’s objectives. - Any other duties assigned by the Project Committee that have direct relevance to the project. Selection criteria: should have a Bachelor’s degree in management, administration, environmental management or related field with a minimum of 5 years management experience at a senior level, or an advanced degree with 3 years management experience. Knowledge and understanding of the relevant UN Convention, environmental issues in Botswana, good leadership, coordination, communication, and facilitation skills are essential. |
| NBSAP Lead Consultant ($90K over 3 years, of which $36K are financed by GEF and the rest by the Programme Cost Sharing). | 1000 | 36 | - Review and stocktaking of products and results from previous biodiversity planning processes at the national level and are carried out in participative manner. - Develop national biodiversity targets are developed in a manner that is attuned to Botswana’s reality. - Revise and update the National Biodiversity Strategy and Action Plan (NBSAP) for Botswana in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. - Develop national frameworks for NBSAP implementation and this includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. - Develop an effective, user-friendly and easily updatable country-driven CHM site; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. Key Deliverables: - Botswana’s NBSAP finalised and Validated after due national consultation (will be produced with the assistance of other consultants) - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP Contributions to: - Fully functional CHM for Botswana, based on best international practice on the matter - Sub-product 1: Challenges and Opportunities for Botswana’s Protected Areas in the 21st Century - Sub-product 2: Study on Ecosystem Valuation and Sectoral Mainstreaming of Biodiversity in Botswana - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Botswana |
| Group of experts in biodiversity and economic and development sectors | 500 | 18 | To assist the Enabling Activities Technical Manager and the NBSAP Lead Consultant in taking stock of the success of the existing NBSAP, developing national targets in line with the global Aichi Targets and updating Botswana’s NBSAP. The experts will cover the main sectors and areas linked to biodiversity conservation (Agriculture, Economics, Forestry, Tourism, Trade, Travel and Transport, Fishery, Land-use management, including spatial and infrastructural development planning, Food security, Gender, Climate change mainstreaming, Population & urban planning). The group will be formed by 4-5 specialists in key domains. The key tasks of the group related to all described areas and sectors are: - Stocking of existing plans, policies and practices in Botswana that result in biodiversity conservation or loss. - Identify the root causes of biodiversity loss in Botswana by first identifying the threat and then the drivers behind the threats. - Identify the key barriers and challenges in the policy environment to effective biodiversity conservation/sustainable use. - Based on existing studies and analyses, identify key gaps in the existing NBSAP in each sector or area. - Identify the means to overcome existing barriers and challenges. - Submit all required information by team leaders for finalizing the NBSAP activities. The group of experts will work extensively with all consultants responsible for specific products. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Botswana - Second National Biodiversity Strategy and Action Plan for Botswana - Sub-product 1: Challenges and Opportunities for Botswana’s Protected Areas in the 21st Century - Sub-product 2: Study on Ecosystem Valuation and Sectoral Mainstreaming of Biodiversity in Botswana - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Botswana - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP - Fully functional CHM for Botswana, based on best international practice on the matter |
| International |  |  |  |
| Consultant on Technical Biodiversity and Mainstreaming Issues (23 weeks, of which 5 weeks are financed by GEF and the rest from UNDP TRAC funds and the Programme Cost Sharing) | 3000 | 5 | - Provide assistance on technical issues where international experience is of particular relevance. This list and key deliverables under this consultancy will be more fully developed during project implementation, but is likely to include the following: - Analysing data and technical information to set biodiversity targets - Incorporating climate change adaptation factors into the gap analysis of protected areas - Collating and analysing conservation and development data, particularly economic valuation data on key ecosystem services in Botswana in relation to socio-economic development - Crafting simple and powerful messages that make the case for biodiversity conservation as a key strategy for achieving national economic development and poverty reduction goals - Supporting the biodiversity sector within government and the EA Project Manager in liaising directly with senior government officials and politicians in other sectors, in making the case for mainstreaming biodiversity into local, district and national development planning and for increasing resource allocation to strategic biodiversity conservation priorities highlighted in the NBSAP. |

Annex B. Chronogramme of activities

| Comp | Modules | Guiding activities under each module | 2011 | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q4 | Q1 | Q2 | COP 11 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | COP 12 | Q4 |
| 1 | I. Preparation | 1. Rapid stocktaking and review of relevant plans, policies and reports | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2. Identification of stakeholders; consultations and awareness | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3. Rapid assessment of the causes and consequences of biodiversity loss highlighting the value of biodiversity and ecosystem services and their contribution to human well-being |  | X | X |  |  |  |  |  |  |  |  |  |  |
|  | II Setting national targets, principles, & main priorities of the strategy | 4. Setting national targets, principles, & main priorities of the strategy though national consultations |  | X | X | d |  |  |  |  |  |  |  |  |  |
| 2 | III. Strategy and action plan development Completion before COP12 | 5. Developing the strategy and actions to implement the agreed targets though national consultations |  |  |  | X | X | X | X |  |  |  |  |  |  |
|  |  | 6. Application of the NBSAP to sub-national entities through sub-national and local consultations |  |  |  |  |  | X | X | X |  |  |  |  |  |
|  |  | 7. Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations |  |  |  |  |  | X | X | X | X | D |  |  |  |
| 3 | IV. Development of Implementation plans and related activities | 8. Development of a plan for capacity development for NBSAP implementation. |  |  |  |  |  |  |  | x | X | X | X |  |  |
|  |  | 9. Technology needs assessment |  |  |  |  |  |  |  |  | x | X | X |  |  |
|  |  | 10. Development of a communication and outreach strategy for the NBSAP. |  |  |  |  |  |  | x | x | x | X | X |  |  |
|  |  | 11. Development of a plan for resource mobilization for NBSAP implementation |  |  |  |  |  |  |  | x | x | X | X | X |  |
|  | V. Institutional, monitoring, reporting and exchange | 12. Establishment/ strengthening of national coordination structures |  |  | x | x | x | x | x | x | x | x | X | X | x |
|  |  | 13. CHM development. |  | x | x | x | x | x | x | x | x | x | x | X | X |
|  |  | 14. Development of indicators and monitoring approach |  | x | x | x | x | x | x | x | x | x | x | X | X |
|  |  | 15. Fifth national report (deadline Mar 2014) |  |  |  |  |  | x | x | x | x | x | D |  |  |

D = delivery.

Annex C. UNDP Total Budget and Workplan

| GEF Component (Outcome) /Atlas Activity | Impl. Agent | Fund ID | Donor Name | ERP / ATLAS Budget Code | Atlas Budget Description | TOTAL Amount (USD) | Year 1 (USD) | Year 2 (USD) | Year 3 (USD) | Year 4 (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comp 1. Stocktaking and national target setting | NEX | 62000 | GEF-10003 | 71400 | Contractual Services - Individ | 9,750 | 750 | 3,000 | 3,000 | 3,000 | a |
|  | NEX | 62000 | GEF-10003 | 71600 | Travel | 12,500 |  | 12,500 |  | 0 | b |
|  | NEX | 62000 | GEF-10003 | 72800 | Information Technology Equipmt | 7,000 |  | 5,000 | 1,000 | 1,000 | c |
|  | NEX | 62000 | GEF-10003 | 74200 | Audio Visual & Print Prod Costs | 6,568 | 1,068 | 3,500 | 2,000 | 0 | d |
|  | GEF Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  | 35,818 | 1,818 | 24,000 | 6,000 | 4,000 |  |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71200 | International Consultants | 35,000 |  | 10,000 | 18,000 | 7,000 | e |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71600 | Travel | 24,000 |  | 7,000 | 12,000 | 5,000 | f |
|  | NEX | 04000 | UNDP TRAC - 00012 | 72300 | Materials & Goods | 45,324 |  | 12,000 | 17,000 | 16,324 | g |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71300 | Local Consultants | 24,800 |  | 8,000 | 6,000 | 10,800 | h |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 74500 | Miscellaneous Expenses | 1,500 |  | 500 | 500 | 500 | i |
|  | Cash Co-finance Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  | 130,624 | 0 | 37,500 | 53,500 | 39,624 |  |
| TOTAL ACTIVITY 1 (Comp 1) |  |  |  |  |  | 166,442 | 1,818 | 61,500 | 59,500 | 43,624 |  |
| Comp 2. NBSAP update | NEX | 62000 | GEF-10003 | 71200 | International Consultants | 10,000 |  |  | 5,000 | 5,000 | e |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 15,000 |  | 5,000 | 10,000 | 0 | h |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 9,000 |  | 9,000 |  |  | j |
|  | NEX | 62000 | GEF-10003 | 71400 | Contractual Services - Individ | 18,450 |  | 6,150 | 6,150 | 6,150 | a |
|  | NEX | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 15,000 |  | 6,000 | 7,000 | 2,000 | k |
|  | NEX | 62000 | GEF-10003 | 74100 | Professional Services | 10,000 |  |  | 5,000 | 5,000 | l |
|  | NEX | 62000 | GEF-10003 | 74200 | Audio Visual & Print Prod Costs | 14,000 |  | 5,000 | 5,000 | 4,000 | m |
|  | NEX | 62000 | GEF-10003 | 71600 | Travel | 15,000 |  |  | 15,000 |  | f |
|  | NEX | 62000 | GEF-10003 | 74500 | Miscellaneous Expenses | 932 | 232 | 400 | 200 | 100 | i |
|  | GEF Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  | 107,382 | 232 | 31,550 | 53,350 | 22,250 |  |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71200 | International Consultants | 20,000 |  |  | 10,000 | 10,000 | e |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71400 | Contractual Services - Individ | 24,000 |  | 8,000 | 8,000 | 8,000 | a |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71300 | Local Consultants | 29,200 |  | 7,200 | 11,000 | 11,000 | h |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71600 | Travel | 21,932 |  |  | 10,966 | 10,966 | n |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 74100 | Professional Services | 12,000 |  |  | 6,000 | 6,000 | o |
|  | Cash Co-finance Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  | 107,132 | 0 | 15,200 | 45,966 | 45,966 |  |
| TOTAL ACTIVITY 2 (Comp 2) |  |  |  |  |  | 214,514 | 232 | 46,750 | 99,316 | 68,216 |  |
| Comp 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms | NEX | 62000 | GEF-10003 | 71200 | International Consultants | 5,000 |  |  | 5,000 |  | e |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 21,000 |  | 4,000 | 7,000 | 10,000 | h |
|  | NEX | 62000 | GEF-10003 | 71400 | Contractual Services - Individ | 7,800 | 4,700 | 3,100 |  |  | a |
|  | NEX | 62000 | GEF-10003 | 71600 | Travel | 12,000 |  | 2,000 | 5,000 | 5,000 | m |
|  | GEF Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  | 45,800 | 4,700 | 9,100 | 17,000 | 15,000 |  |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71300 | Local Consultants | 10,000 |  |  | 5,000 | 5,000 | j |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71600 | Travel | 30,000 |  |  | 15,000 | 15,000 | n |
|  | NEX | 04000 | UNDP TRAC - 00012 | 72100 | Contractual Services-Companies | 8,000 |  |  | 4,000 | 4,000 | p |
|  | NEX | 04000 | UNDP TRAC - 00012 | 72300 | Materials & Goods | 8,000 |  |  | 3,000 | 5,000 | g |
|  | NEX | 04000 | UNDP TRAC - 00012 | 72400 | Communic & Audio Visual Equip | 4,000 |  |  | 4,000 |  | q |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 74100 | Professional Services | 9,000 |  |  | 4,000 | 5,000 | r |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 74200 | Audio Visual&Print Prod Costs | 10,876 |  |  | 5,876 | 5,000 | o |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 74500 | Miscellaneous Expenses | 4,500 |  | 2,000 | 1,500 | 1,000 | i |
|  | Cash Co-finance Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  | 84,376 | 0 | 2,000 | 42,376 | 40,000 |  |
| TOTAL ACTIVITY 3 (Comp 3) |  |  |  |  |  | 130,176 | 4,700 | 11,100 | 59,376 | 55,000 |  |
| 4. Project Mgt | NEX | 62000 | GEF-10003 | 71400 | Contractual Services - Individ | 18,000 | 4,000 | 5,000 | 5,000 | 4,000 | a |
|  | GEF Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  | 18,000 | 4,000 | 5,000 | 5,000 | 4,000 |  |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71400 | Contractual Services - Individ | 73,200 | 1,068 | 22,000 | 25,000 | 25,132 | a |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 71600 | Travel | 24,000 |  | 15,000 | 5,000 | 4,000 | s |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 72100 | Contractual Services-Companies | 4,000 |  | 4,000 |  |  | t |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 72700 | Hospitality/Catering | 1,000 |  | 500 | 400 | 100 | u |
|  | NEX | 00070 | Progr Cost Sharing - 30071 | 73200 | Premises Alternations | 5,000 |  |  |  | 5,000 | v |
|  | NEX | 04000 | UNDP TRAC - 00012 | 74500 | Miscellaneous Expenses | 676 | 676 |  |  |  | i |
|  | Cash Co-finance Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  | 107,876 | 1,744 | 41,500 | 30,400 | 34,232 |  |
| TOTAL ACTIVITY 4 (Project Management) |  |  |  |  |  | 125,876 | 5,744 | 46,500 | 35,400 | 38,232 |  |
|  |  |  |  |  |  | . |  |  |  |  |  |
|  | SUB-TOTAL GEF |  |  |  |  | 207,000 | 10,750 | 69,650 | 81,350 | 45,250 |  |
|  | SUB-TOTAL CASH CO-FINANCE (GOVT & UNDP) |  |  |  |  | 430,008 | 1,744 | 96,200 | 172,242 | 159,822 |  |
|  |  |  |  |  |  | . |  |  |  |  |  |
|  | GRAND TOTAL (in cash) |  |  |  |  | 637,008 | 12,494 | 165,850 | 253,592 | 205,072 |  |

| Budget Notes |  |
| --- | --- |
| a | Project Support Staff over 3.2 years: (1) Enabling Activities Technical Manager @ US$600 per week (i.e. a total of US$100,800); and (2) Project Admin Assistant @ US$300 per week (i.e. a total of US$50,400). The 3.2 year duration corresponds to 168 weeks in total, of which 60 weeks are financed by GEF and the rest by the Programme Cost Sharing. Both positions are full time and are budgeted for here under Contractual Services Individual budget lines combined. The GEF portion of the Project Admin Assistant is budgeted for under GEF Management Costs. |
| b | Air-Travel for International Consultant, with provision for DSA and local travel. |
| c | 1 laptop computer for Project manager, printer and scanner to support documentation and upload onto CHM. |
| d | Communicating the progress and results of the project to wider stakeholder body through print and electronic media. |
| e | International Consultant on Technical Biodiversity and Mainstreaming Issues - US$69,000 ($15,000 of GEF funds) - total of 23 weeks @ US$3000 per week (from all International Consultant budget lines combined). |
| f | Local-Travel by road, DSA for participants attending district workshops. |
| g | Workshop running costs (venue & meals) for workshop participants @ US$3,000 each. |
| h | NBSAP Lead Consultant totalling US$90,000 financed by GEF ($36K) and Programme Cost-Sharing (from all Local Consultant budget lines combined). |
| i | Bank charges, insurance and other miscellaneous expenses. |
| j | Group of experts in biodiversity and economic and development sectors |
| k | Upgrading Botswana's CHM: Satellite images, data sets, publications. |
| l | Editorial & layout services for Final Report. Audit and translation to local languages. |
| m | Printing services for the final report and the Country-study Reports. |
| n | Travel DSA for district stakeholders workshops x 6 and a national validation workshop x 2 @ US$16,000 |
| o | Editorial, printing and publicity services |
| p | Workshops and meetings, including facilitation and hosting services. |
| q | Communication costs |
| r | Web design |
| s | International travel for Conference Participation |
| t | Miscellaneous services to be defined. |
| u | Cleaning services, coffee and tea. |
| v | Office upgrading |

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources.

World Conservation Monitoring Center (1994) Priorities for conserving global species richness and endemism. Caldecott, J.O., Jenkins, M.D., Johnson, T. and Groombridge, B. World Conservation Press, Cambridge, UK. 36 pp

www.teebweb.org

Ervin, J., N. Sekhran, A. Dinu. S. Gidda, M. Vergeichik and J. Mee. 2010. Protected Areas for the 21st Century: Lessons from UNDP/GEF’s Portfolio. New York:  United Nations Development Programme and Montreal: Convention on Biological Diversity.

Petersen, C and B. Huntley. 2005. Mainstreaming Biodiversity in Productive Landscapes. Working Paper 20. Washington DC: GEF.