Document of

The World Bank

FOR OFFICIAL USE ONLY

Report No.: PPXX

INTERNATIONAL BANK FOR RECONSTRUCTION AND DEVELOPMENT

PROJECT paper

ON A

PROPOSED GRANT FROM THE GLOBAL ENVIRONMENTAL FACILITY TRUST FUND IN THE AMOUNT OF US $3 MILLION

TO THE

People’s republic of China FOR A Landscape Approach to Wildlife Conservation in Northeast China PROJECT June 20, 2015 This document has a restricted distribution and may be used by recipients only in the performance of their official duties. Its contents may not otherwise be disclosed without World Bank authorization.

CURRENCY EQUIVALENTS

(Exchange Rate Effective June 7, 2015)

| Currency Unit | = | CNY |
| --- | --- | --- |
| CNY 6.20 | = | US$1 |

FISCAL YEAR

| January 1 | – | December 31 |
| --- | --- | --- |

ABBREVIATIONS AND ACRONYMS

| BOF CQS | Bureau of Finance Consultants’ Qualifications | LOP METT |  | Life of Project Management Effectiveness Tracking Tool |
| --- | --- | --- | --- | --- |
| DA | Designated Account | M&E |  | Monitoring and Evaluation |
| DRC DWCNRM EMDP | Development Reform Committee Department of Wildlife Conservation and Nature Reserve Management Ethnic Minority Development Plan | MOF MTR NCB NFPP |  | Ministry of Finance Mid Term Review National Competitive Bidding National Forestry Protection Program |
| EIRR EPG | Economic Internal Rate of Return Environmental Protection Guideline | NFU NR NTRP NTFP |  | Northeastern Forestry University Nature Reserve National Tiger Recovery Program Non-timber Forest Product |
| EMP ECOP FRC FY | Environmental Management Plan Environmental Code of Practice Feline Research Center Fiscal Year | NNR NPMO PAO |  | National Nature Reserve National Project Management Office Project Audit Office |
| FM FMM FYP GEO GTGP | Financial Management Financial Management Manual Five Year Plan Global Environmental Objective Green to Green Program | PE PFB PF PMO PMP |  | Project Entity Provincial Finance Bureau Process Framework Project Management Office Pest Management Plan |
| GTI | Global Tiger Initiative | PDIFPI |  | Planning & Design Institute of Forestry Production Industry |
| HFC | Heilongjiang Forestry Corporation | PDO |  | Project Development Objective |
| HFD HPAO | Heilongjiang Forestry Department Heilongjiang Provincial Audit Office | PNR PPMU |  | Provincial Nature Reserve Provincial Project Management Unit |
| JFD JPAO ICR IDA IFR | Jilin Forestry Department Jilin Provincial Audit Office Implementation Completion Report International Development Association Interim Financial Report | QBS SFA SMP TEV TRC WWF |  | Quality-Base Selection State Forestry Administration Social Management Plan Total Economic Value Tiger Range Countries World Wide Fund for Nature |

| Regional Vice President: |  | Axel van Trotsenburg |
| --- | --- | --- |
| Country Director: |  | Bert Hofman |
| Senior Global Practice Director: |  | Paula Caballero |
| Practice Manager: |  | Iain Shuker |
| Task Team Leader(s): |  | Garo Batmanian |

CHINA

LANDSCAPE APPROACH TO WILDLIFE CONSERVATION IN NORTHEAST CHINA

TABLE OF Contents

I.	STRATEGIC CONTEXT	4

A.	Country Context	4

B.	Sectoral and Institutional Context	4

C.	Higher Level Objectives to which the Project Contributes	6

II.	PROJECT DEVELOPMENT OBJECTIVE	6

A.	Project Beneficiaries	7

B.	PDO Level Results Indicators	7

III.	PROJECT DESCRIPTION	7

A.	Project Components	7

B.	Project Financing	11

IV.	IMPLEMENTATION	12

A.	Institutional and Implementation Arrangements	12

B.	Results Monitoring and Evaluation	14

C.	Financial Management and Disbursements	15

D.	Procurement	17

E.	Social Safeguards	20

F.	Environmental  Safeguards	23

G.	Role of Partners	25

H.	Overall Risk Rating and Explanation of Key Risks	25

Annex 1: Results Framework and Monitoring	27

ANNEX 2: EXPECTED Outputs by Partner	32

| APPRAISAL DATA SHEET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| China |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Landscape Approach to Wildlife Conservation in Northeast China (P122383) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT PAPER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EAST ASIA AND PACIFIC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GENDR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Report No.: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Basic Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project ID |  |  |  |  |  |  |  |  | EA Category |  |  |  |  |  |  |  |  |  |  |  |  | Team Leader(s) |  |  |  |  |  |  |  |  |  |  |
| P122383 |  |  |  |  |  |  |  |  | B - Partial Assessment |  |  |  |  |  |  |  |  |  |  |  |  | Garo J. Batmanian |  |  |  |  |  |  |  |  |  |  |
| Lending Instrument |  |  |  |  |  |  |  |  | Fragile and/or Capacity Constraints [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Investment Project Financing |  |  |  |  |  |  |  |  | Financial Intermediaries [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Series of Projects [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Implementation Start Date |  |  |  |  |  |  |  |  | Project Implementation End Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01-Jul-2015 |  |  |  |  |  |  |  |  | 31-Dec-2018 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expected Effectiveness Date |  |  |  |  |  |  |  |  | Expected Closing Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01-Aug-2015 |  |  |  |  |  |  |  |  | 30-Jun-2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Joint IFC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | GEF Focal Area |  |  |  |  |  |  |  |  |
| No |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Biodiversity |  |  |  |  |  |  |  |  |
| Practice Manager/Manager |  |  |  |  |  | Senior Global Practice Director |  |  |  |  |  |  |  | Country Director |  |  |  |  |  |  |  |  |  | Regional Vice President |  |  |  |  |  |  |  |  |
| Iain G. Shuker |  |  |  |  |  | Paula Caballero |  |  |  |  |  |  |  | Bert Hofman |  |  |  |  |  |  |  |  |  | Axel van Trotsenburg |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval Authority |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CD Decision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrower: People's Republic of China |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Agency: State Forestry Agency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact: |  |  |  | Ms. An Lidan |  |  |  |  |  |  |  |  |  | Title: |  |  |  | DDG, State Forestry Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | 86-1-84238530 |  |  |  |  |  |  |  |  |  | Email: |  |  |  | anlidan@forestry.gov.cn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Financing Data(in USD Million) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Project Cost: |  |  |  |  |  | 20.58 |  |  |  |  |  |  |  | Total Bank Financing: |  |  |  |  |  |  |  |  |  | 0.00 |  |  |  |  |  |  |  |  |
| Financing Gap: |  |  |  |  |  | 0.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Financing Source |  |  |  |  |  |  |  |  |  |  |  |  | Amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrower |  |  |  |  |  |  |  |  |  |  |  |  | 17.58 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Global Environment Facility (GEF) |  |  |  |  |  |  |  |  |  |  |  |  | 3.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  | 20.58 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expected Disbursements (in USD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fiscal Year |  | 2016 |  |  | 2017 |  | 2018 |  |  |  |  | 2019 |  |  | 0000 |  | 0000 |  |  |  | 0000 |  |  | 0000 |  |  |  | 0000 |  |  | 0000 |  |
| Annual |  | 300,000 |  |  | 1,000,000 |  | 1,000,000 |  |  |  |  | 700,000 |  |  | 0.00 |  | 0.00 |  |  |  | 0.00 |  |  | 0.00 |  |  |  | 0.00 |  |  | 0.00 |  |
| Cumulative |  | 300,000 |  |  | 1,300,000 |  | 2,300,000 |  |  |  |  | 3,000,000 |  |  | 0.00 |  | 0.00 |  |  |  | 0.00 |  |  | 0.00 |  |  |  | 0.00 |  |  | 0.00 |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institutional Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Practice Area (Lead) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment & Natural Resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contributing Practice Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cross Cutting Topics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [] | Climate Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [ ] | Fragile, Conflict & Violence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [ ] | Gender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [ ] | Jobs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [ ] | Public Private Partnership |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sectors / Climate Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sector (Maximum 5 and total % must equal 100) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Major Sector |  |  |  |  |  |  |  |  |  | Sector |  |  |  |  |  |  |  |  | % |  |  |  | Adaptation Co-benefits % |  |  |  |  |  | Mitigation Co-benefits % |  |  |  |
| Agriculture, fishing, and forestry |  |  |  |  |  |  |  |  |  | Forestry |  |  |  |  |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  | 100 |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| I certify that there is no Adaptation and Mitigation Climate Change Co-benefits information applicable to this project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Themes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Theme (Maximum 5 and total % must equal 100) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Major theme |  |  |  |  |  |  |  |  |  |  | Theme |  |  |  |  |  |  |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |
| Environment and natural resources management |  |  |  |  |  |  |  |  |  |  | Biodiversity |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50 |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50 |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed Global Environmental Objective(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The proposed project’s Project Development Objective (PDO) and its Global Environmental Objective (GEO) is to help create the ecological conditions for recovery of threatened biodiversity in priority ecological landscapes in the far northeast of China(Heilongjiang and Jilin), using the Amur Tiger as a flagship species. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cost (USD Millions) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institutional Coordination to Mainstream Wildlife Conservation across Sectors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.73 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conservation of Priority Ecosystems and Increased Effectiveness of Habitat Protection in the Changbaishan Landscape |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 9.18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reducing Human Wildlife Conflict in Priority Forest Landscapes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 9.01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management and Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.66 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compliance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Does the project depart from the CAS in content or in other significant respects? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  |  | No |  | [ X ] |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Does the project require any waivers of Bank policies? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  |  | No |  | [ X ] |
| Have these been approved by Bank management? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  |  | No |  | [ ] |
| Is approval for any policy waiver sought from the Board? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  |  | No |  | [ X ] |
| Does the project meet the Regional criteria for readiness for implementation? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  |  | No |  | [ ] |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Safeguard Policies Triggered by the Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  | No |  |  |  |
| Environmental Assessment OP/BP 4.01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Natural Habitats OP/BP 4.04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Forests OP/BP 4.36 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Pest Management OP 4.09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Physical Cultural Resources OP/BP 4.11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Indigenous Peoples OP/BP 4.10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Involuntary Resettlement OP/BP 4.12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Safety of Dams OP/BP 4.37 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Projects on International Waterways OP/BP 7.50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Projects in Disputed Areas OP/BP 7.60 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Composition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bank Staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  | Role |  |  |  |  |  |  |  | Title |  |  |  |  |  |  |  |  |  | Unit |  |  |  |  |  |  |  |  |
| Garo J. Batmanian |  |  |  |  |  | Team Leader (ADM Responsible) |  |  |  |  |  |  |  | Lead Environmental Specialist |  |  |  |  |  |  |  |  |  | GENDR |  |  |  |  |  |  |  |  |
| Jingrong He |  |  |  |  |  | Procurement Specialist |  |  |  |  |  |  |  | Procurement Specialist |  |  |  |  |  |  |  |  |  | GGODR |  |  |  |  |  |  |  |  |
| Fang Zhang |  |  |  |  |  | Financial Management Specialist |  |  |  |  |  |  |  | Financial Management Specialist |  |  |  |  |  |  |  |  |  | GGODR |  |  |  |  |  |  |  |  |
| Jin Liu |  |  |  |  |  | Team Member |  |  |  |  |  |  |  | Senior Rural Development Specialist |  |  |  |  |  |  |  |  |  | GENDR |  |  |  |  |  |  |  |  |
| Songling Yao |  |  |  |  |  | Safeguards Specialist |  |  |  |  |  |  |  | Senior Social Development Specialist |  |  |  |  |  |  |  |  |  | GSURR |  |  |  |  |  |  |  |  |
| Xieli Bai |  |  |  |  |  | Team Member |  |  |  |  |  |  |  | Program Assistant |  |  |  |  |  |  |  |  |  | EACCF |  |  |  |  |  |  |  |  |
| Yiren Feng |  |  |  |  |  | Safeguards Specialist |  |  |  |  |  |  |  | Senior Environmental Specialist |  |  |  |  |  |  |  |  |  | GENDR |  |  |  |  |  |  |  |  |
| Extended Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  | Title |  |  |  |  |  |  |  | Office Phone |  |  |  |  |  |  |  |  |  | Location |  |  |  |  |  |  |  |  |
| Random Dubois |  |  |  |  |  | Senior Environmental Specialist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weisheng Wang |  |  |  |  |  | Director |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Locations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Country |  |  | First Administrative Division |  |  |  |  | Location |  |  |  |  |  |  |  | Planned |  |  |  | Actual |  |  |  | Comments |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultants (Will be disclosed in the Monthly Operational Summary) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultants Required? |  |  |  |  |  | Consultants will be required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

STRATEGIC CONTEXT

## Country Context

- China’s rapid growth is now a driving force in the global economy and is achieving unprecedented rates of poverty reduction. However, ever increasing economic expansion and diversification is also seriously impacting the natural resource base and generating major environmental liabilities. Human activities have led to increasing fragmentation of remaining natural forests, and the wildlife they support.

- Systematic poaching of wildlife, and encroachment and degradation of habitat have led to severe losses in biodiversity, altering food webs and ecosystem functions. According to the Ministry of Environmental Protection, the endangered status of wild animals continues to worsen - 233 vertebrate species face extinction and 44 percent wildlife species are declining.

- Up to the late 1990s logging and timber production was widespread throughout China based on State and provincial forestry farms. Following the national ban on logging declared in 2000, many of these forest farms were converted into provincial nature reserves and often included the retention of former farm staff. In parallel, the State government established a number of programs designed to restore ecosystem services with a focus on soil and water conservation, of which the Natural Forest Protection Program (NFPP) and the Grain to Green Program (GTGP) were and remain the most significant. These programs also generate additional ecological benefits including the restoration of critical habitat and conservation of biodiversity. More recently as China has continued to make substantial progress in the reduction of poverty and reaching economic standards comparable to the West, but has also made a notable shift towards addressing other priorities including the improvement of environmental quality.  This is supported by China’s current 12th, Five-Year Plan (FYP) which proposed the creation of new and strengthening of existing reserves to enhance biodiversity conservation. These factors are contributing to a favorable enabling environment to make a significant impact on biodiversity conservation in China.

## Sectoral and Institutional Context

- China, with its more than 9.5 million km2, has a wide range of ecosystems ranging from tropical forests to pine forests, and from wetlands to deserts. Thus it has a vast biodiversity, including many species of global importance such as the Amur tiger (Panthera tigris altaica), the Amur leopard (Panthera pardus orientalis), the Asian elephant (Elephas maximus), the panda (Ailuropoda melanoleuca), and the Nujiang golden monkey (Rhinopithecus strykeri).

- China has been occupied by human populations for thousands of years, which through time have led to natural habitat fragmentation, and with a population of over 1.3 billion people it is not feasible to set aside large tracks of land for habitat restoration or natural areas for protection. Thus, in order to protect its biodiversity, China needs to use a landscape approach through the establishment of ecological corridors connecting nature reserves to provide habitat for the conservation of viable size populations of key biodiversity while decreasing human-wildlife conflict.

- China is transitioning from forest management practices that previously focused on wood biomass and productivity of fast growing species in plantations, to a more multi-dimensional approach that recognizes the role of natural forest ecosystems in providing a multitude of goods and services including timber, water, carbon sequestration, and biodiversity. However, it has yet to mainstream a landscape approach into land use planning and biodiversity conservation at provincial and local levels.

- The landscape approach for biodiversity conservation is the recommended alternative to creating a series of large and connected protected areas. It enables the co-existence of multiple land uses, from biodiversity conservation, to economic activities such as farming and forestry. Thus, this approach also focuses not only one land use (e.g. nature reserves) but also on the inter-relationship between land uses.

- This is an innovative approach in China where the work in biodiversity conservation has been focusing on creation of nature reserves and actions to curb poaching.  The few efforts to date in landscape planning and management for biodiversity conservation objectives have focused primarily on non-migratory species with relatively small home ranges such as the panda.  It has not focused on species top of the food chain, such as tigers, which have far larger home ranges and more potential for human-wildlife conflict.

- One priority area for biodiversity conservation is the forests of the Changbaishan Landscape found in northeastern China in proximity to the Russian border.  The Landscape includes the Jilin Municipality and the Yanbian Korean Autonomous Prefecture in Jilin Province, and the southern part of the Mudanjiang Prefecture in Heilongjiang Province.

- The region is characterized by a low montane and hilly landscape and is home to the largest remaining tracts of natural temperate forest in China, with a diverse flora and fauna and a significant amount of endemism.  Forests cover about 55% of the region. Coniferous-broadleaf mixed forests is the primary forest cover with Korean pine and Manchurian Fir the dominant species intermixed with over 600 species of plants. It also provides habitat for more than 300 species of wildlife, among them are 44 species of China’s national protected wildlife, including the Amur tiger, Amur leopard, Siberian musk deer (Moschus moschiferus), Sika deer (Cervus nippon), the Japanese sable (Martes zibellina), Asiatic black bear (Ursus thibetanus), and Red deer (Cervus elaphus).

- As a result of long-time logging, the original forest is almost completely gone, replaced by secondary growth, with remnant patches scattered along the Heilongjiang and Jilin border. The remaining forest is in good condition after years of protection and restoration.

- Forestry and agriculture are the dominant sectors in the local economy, followed by much smaller contributions from animal husbandry, mining and tourism sectors, making it one of the least developed regions in the NE China.

- This region is also home to the few remaining individuals of the iconic Amur Tigers in the wild in China. It is the largest of the six existing sub-species of tigers with males reaching 300 kg and 2.3 m. The total population in the wild (Russia and China) is estimated to be only 400 individuals. The tiger population in China is estimated to vary in number from 18-22 individuals, which wander back and forth across the boundary with Russia, in Primorskye Krai where the main population resides. Recovering the  Tiger—and as a first step, doubling the number of individuals in the wild by 2022—is the goal of the People’s Republic of China under the National Tiger Recovery Program (NTRP), to which Premier Wen Jiabao committed in a special forum of Heads of State at the St. Petersburg Tiger Summit in November 2010.

- At present, the habitat for Amur tiger, leopard and many other species of wildlife in the Changbaishan Landscape is fragmented into a series of national and provincial nature reserves with little to no shared connectivity. The results from a recent study supported by China’s Feline Research Center (FRC) identified habitat limiting factors affecting tiger populations (e.g., elevation, habitat integrity, human settlements, road density etc.).  The findings of the study were used to identify priorities that if addressed could lead to the restoration of wildlife habitat in the Changbaishan Landscape. These were first to consolidate the existing corridor with Russia along a north-south axis followed by interventions designed to facilitate wildlife migration further “inland” into China along an east-west axis as habitat is made more “wildlife-friendly” and becomes increasingly suitable to support growing populations. If properly managed, the area of forests remaining in the Changbaishan Landscape should be able to support an increasingly complex biota that ultimately could sustain viable populations of higher order predators, like the Amur Tiger and leopard, and their prey, as well as other species.

- Baseline activities in the project area depend on the province, partner and status of nature reserve participating in the project.  Generally, Jilin Forestry Department (JFD) has progressed the furthest in support of tiger conservation activities.  In addition to Jilin’s existing tiger habitat and conservation and restoration management plan which has already been accepted by the provincial Development and Reform Committee (DRC), they have pioneered some snare removal activities, human-wildlife compensation measures, prey re-introduction activities and have a strong bi-lateral program with their Russian counterparts.  Heilongjiang Forestry Department (HFD) lags behind JFD in having yet to prepare and submit a tiger conservation plan to the DRC and putting into place human-wildlife conflict legislation but have their respective conservation program with their Russian counterparts.   Heilongjiang Forestry Corporation (HFC) is new to tiger conservation and has previously been involved with production forestry so there are few baseline relevant activities at present beyond providing support for basic operations costs in the various forestry farms.  Hunchun and Wangqing National Nature Reserves (NNRs) in Jilin and Mulin NNR in Heilongjiang are large, recognized national reserves and receive significant support from SFA. Said support not only covers adequately operational costs but support new investments including the establishment of the use of a system of camera traps to film tigers and other wildlife (in particular in Hunchun NNR).  In both provinces, many of the other existing and proposed new reserves, in particular at the county-level (including the forestry farms), are poorly developed with budgets that only cover routine operations with little to no investment in conservation activities.  Baseline activities under the project directed at ecological restoration and promotion of tiger-friendly habitat come through a number of State programs designed to restore ecosystem services, in particular focusing on soil and water conservation, of which the Natural Forest Protection Program (NFPP) and the Grain to Green Program (GTGP) were and remain potentially the most significant to generate additional ecological benefits including the restoration of critical habitat and conservation of biodiversity.

## Higher Level Objectives to which the Project Contributes

- The Project is fully consistent with the World Bank’s current FY 2013 – FY 2016 Country Partnership Strategy in supporting Strategic Theme 1: Supporting Greener Growth, in particular through demonstrating sustainable Natural Resource Management approaches (Outcome 1.5).  The Project will demonstrate ways to better manage ecosystems and conserve biodiversity including supporting forestry approaches that maximize ecosystem health and use concessional funding to promote globally important biodiversity. Finally, the Project supports the Bank’s “knowledge through investments” core principle through assisting China to secure incremental GEF funding.

- China is one of the 13 Tiger Range Countries members of the Global Tiger Initiative (GTI) which have pledged their support for tiger recovery under the GTI. The Global Tiger Initiative is a global alliance of governments, international organizations (including the World Bank, civil society, the scientific community, and the private sector) committed to working together to save wild tigers from extinction.

PROJECT DEVELOPMENT OBJECTIVE

- The proposed project’s Project Development Objective (PDO) and its Global Environmental Objective (GEO) is to help create the ecological conditions for recovery of threatened biodiversity in priority ecological landscapes in the far northeast of China (Heilongjiang and Jilin), using the Amur Tiger as a flagship species.

- The Project will do this through: (a) integrating wildlife conservation considerations into economic development planning and sectoral policies and planning frameworks in targeted landscapes; (b) enhancing the effectiveness of protected area/network management; (c) increasing wildlife carrying capacity through restoration, expansion and connectivity of critical habitats, including the expansion of biodiversity-friendly landscapes adjacent to protected areas; (d) promoting more effective patrolling and monitoring in both protected areas and the greater landscape to reduce mortality of flagship species; and (e) reducing human/wildlife conflict by increasing benefits to and buy-in from local communities for wildlife conservation.

## Project Beneficiaries

- Key beneficiaries include the rural population that live in the project area, the Department of Wildlife Conservation and Natural Reserve Management (DWCNRM) of China’s State Forestry Administration (SFA), Jilin Forestry Department, Heilongjiang Forestry Department, Heilongjiang Forestry Corporation, World Wide Fund for Nature (WWF), and the Northeast Forestry University (NFU). The local population would benefit from activities to reduce human-wildlife conflicts, while the agencies will benefit from the training and increase capacity to manage protected areas and conserve biodiversity.

- All have been consulted in the identification of this operation and are very supportive of the activities proposed. Discussions with leaders from local communities living in former production forests indicated their interest in alternative employment linked to conservation.

## PDO Level Results Indicators

- The proposed PDO level results indicators are: (a) Area brought under enhanced biodiversity protection in existing and new nature reserves; and (b)   Area outside of nature reserves managed in a biodiversity friendly manner.

PROJECT DESCRIPTION

## Project Components

- Component 1: Institutional Coordination to Mainstream Wildlife Conservation Across Sectors (Total: USD 1.73 million: GEF USD 0.72 million)

- This component will support a series of activities designed to contribute to the establishment of an enabling policy, institutional and planning framework to facilitate and sustain increased cooperation and collaboration among provincial, national and international institutions in their respective efforts to conserve wildlife and habitat in Northeast China.  This component consists of the following two sub-components:

- Sub-Component 1a: Policy and Planning. Under this sub-component the Project will support the updating of Jilin’s existing tiger habitat and conservation and restoration management plan which has already been accepted by the provincial Development and Reform Committee (DRC) and the preparation of Heilongjiang’s first such plan to be submitted to the DRC. Other activities will support the development of new and updating of existing provincial policies and regulations to reduce human-tiger conflicts.  Specifically this will consist of: (a) the formulation of local regulations to facilitate the management and conservation of wildlife in Dongning County (site for the proposed Niaoqingshan PNR to be created in Heilongjiang Province); (b) formulation of provincial-wide legislation in Heilongjiang Province to promote management measures that include paying compensation for wildlife-associated conflicts that will be submitted to the Provincial People’s Congress for approval before the end of the project; (this legislation already exists in Jilin Province); (c) local compensation regulatory measures that cover HFD and HFC forestry farms included under the project; and (d) the formulation of regulations needed to implement existing wildlife conservation measures specified in the management plans for Mulin and Laolin NNRs and their accompanying buffer zones (Heilongjiang Province);  Finally under this sub-component, the project will support the identification of and planning for priority habitat areas for tiger protection.  Specifically this will include plans that cover existing forest farms managed by the HFD and HFC respectively that will identify suitable areas to be converted to nature reserves in the future for the purposes of expanding the province’s existing NR area network.

- Sub-Component 1b: Institutional Arrangements. Under this sub-component the Project will contribute to the creation of a NE China Advisory Tiger Landscape Committee composed of recognized national experts to provide technical advice to project stakeholders for consideration in the preparation of their annual work plans. This will serve as a source of technical inputs reflecting the latest scientific data on tigers and other wildlife and their habitat and provide a basis to determine how best the Project can adapt to reflect the latest thinking in a cost-effective manner while achieving the GEO.  The Committee would also be available for consultation on an ad hoc basis when necessary.  The institutional composition of the Committee will be composed of representatives from the NE Forestry University, Jilin Academy of Forestry, Wildlife Institute of Heilongjiang Province and all project partners. In addition to internationally recognized experts in wildlife ecology (including Amur tiger and leopard), the Committee will be multi-disciplinary in nature and include a natural resource economist and planner. Its administrative office will be based in FRC at China’s Northeast Forestry University located in Harbin, Heilongjiang Province.  The Committee is expected to meet at minimum 8 times over the 4 year life of project with the first and last meetings hosted by the NPMO and the remaining 6 meetings hosted equally between the three partners. A second set of critical activities supported under this sub-component will lead to increased cooperation between the project’s three main stakeholders and their respective Russian counterparts under an existing Protocol for Conservation of Tigers and their Habitats signed in 1997 and more recent agreements signed in 2010. Participants will include scientists, managers from the three partners’ respective nature reserves, representatives from FRC, SFA, WWF and other relevant institutions and their Russian counterparts.  The project will support four annual meetings.  These will be hosted by JFD (project years 2and 3) and HFD (project years 1 and 4).  It is expected that the thematic issues to be discussed in these meetings and which should lead to on-the-ground actions that would include but not be limited to promoting joint anti-pouching activities, staff training, developing a standard monitoring protocol and the consolidation of statistics into a unified data base. These “regional” meetings are expected to be complemented by bi-lateral meetings between the individual partners and their Russian counterparts.

- The expected Intermediate Results are: (a) an update and new province-wide tiger conservation management plans submitted to the DRC for Jilin and Heilongjiang Provinces, respectively; (b) establishment of a NE China Advisory Tiger Landscape Conservation Committee; and (c) closer cross-provincial collaboration with Russian counterparts.

- Component 2: Conservation of Priority Ecosystems and Increased Effectiveness of Habitat Protection in the Changbaishan Landscape (Total: USD 9.18 million: GEF USD1.57million)

- This component will support the consolidation and strengthening of the Sino - Russian corridor through the strengthening of existing and creation of new Chinese nature reserves, improvement of wildlife habitat in the project’s core zone and provision of support for an integrated wildlife-monitoring program.  This will be achieved through the following four sub-components:

- Sub-component 2a: Increased Management Effectiveness in 4 Existing NRs.  The existing nature reserves proposed for project support occurs in a cluster along a north-south corridor paralleling the Sino-Russian border are Hunchun and Wangqing NNRs (Jilin Province) and Laoyoling NNR (Heilongjiang Province).  Two of these reserves (Hunchun and Laoyoling NNR) share a boundary with the Land of the Leopard NP in Russia. A fourth reserve to be supported under the Project, Mulin NNR (Heilongjiang Province), will serve to expand this cluster of reserves further to the west. Under this sub-component the Project will provide support primarily for training, equipment, updating of existing management plans and development of NR-specific implementation regulations required to facilitate the legal application of existing management plans.    Project support for development and implementation of NR management plans, training and equipment is estimated to lead to an average increase in management effectiveness of the four nature reserves of 27 percent over the life of project as measured by the METT.  This will be applied at the end of the project 2nd and 4th years.

- Sub-component 2b: Creation of 3 New NRs. To strengthen the cluster described under Sub-component 2a and support a more contiguous corridor following a north-south axis parallel to the Sino-Russian border the Project will support the creation of two new reserves, Lanjia “mini-reserve” and Niaoqingshan PNR in Jilin and Heilongjiang Provinces, respectively. A third reserve, Tianqiaoling (Jilin) to be created under the Project will support an expansion along an East-West corridor extending further into China.  The creation of three new NRs will result in 866 km2 of new protected area for tiger and other wildlife.  Under this sub-component the Project will provide support primarily for the necessary field studies, consultations, follow-up preparation and application materials leading to reserve creation followed by limited investment.

- Sub-component 2c: Habitat Restoration. Under this sub-component the Project will support a series of activities on forest lands in proximity to project-supported nature reserves for the purpose of the creation of tiger (and other wildlife)-friendly habitat to promote the expansion of the range of existing populations and gradual increase in carrying capacity.  The total estimated area included under this activity covers 2,252km2.  Support will be provided for increasing the population of local prey species, habitat improvement primarily through reforestation of diverse range of local broad leaf and conifer species, thinning, reduction of understory (shrub cover) and thinning of existing forest stands in areas external to the NRs and the removal of snares; actions that together will contribute to the creation of corridors connecting existing and the newly proposed NRs.  Government financing will include support for increasing existing populations of prey species (mostly ungulates), provision of feed and feeding stations, in particular for the winter periods and habitat improvement activities.  “Biodiversity friendly” in the context of the present project consists of landscapes that meet the following criteria: (a) tree diversity ranging between 50-60%: broad leaf: 50%-40% conifers; (ii) crown cover of 40 % or greater, (iii) understory (i.e., shrub cover) not greater than 10 – 20 % and (iv) cleared of snares.

- Sub-component 2d: Technical Monitoring. A cross-provincial, integrated technical monitoring program under the responsibility of the Feline Research Center (FRC) will be supported under this sub-component that will monitor tiger and other key wildlife populations and their prey, associated habitat and other key environmental indicators including the potential effects of climate change.  This program will also include the monitoring of nature-reserve specific species as indicators of biodiversity “richness” to be identified in project year 1.  Under this sub-component the project will provide support primarily for the purchase of monitoring equipment, training, field studies, data processing and publication and dissemination. The field dimension of the monitoring program will be comprised of two elements: (a) 2 surveys conducted in project years 1 and 4 and led by FRC; and (b) a series of fixed, automatic camera traps run for three month periods twice per year for 4 years.  Both elements will collect data on Amur tiger and associated prey species and habitat both in the reserves and adjacent areas where project will be supporting activities directed at habitat improvement.

- The expected Intermediate Results under this component are: (a) increased management effectiveness among project supported NRs measured by NR specific METT scorecards, (b) 3 new NRs established creating 866 km2 of new protected area for tiger and other wildlife, (c) 296 NR staff trained, (d) decreased incidence of snares in project area and (e) an integrated cross-provincial ecological monitoring program established.

- Component 3: Reducing Human Wildlife Conflict in Priority Forest Landscapes (Total: USD 9.01 million: GEF USD 0.56 million)

- This component will support a series of activities designed to reduce human-tiger conflicts in a buffer zone in proximity to the assemblage of existing and new nature reserves to be supported under component 2.  This component consists of the following three sub-components:

- Sub-Component 3a: Improved Patrolling and Enforcement.  Under this sub-component the Project will support : (i) the restoration of 26 existing and construction of two new forestry protection stations,  (ii) purchase of equipment and small infrastructure ( such as vehicles for patrolling, GPS, snow motorcycle, walkie talkies, binoculars, infrared digital cameras), (iii) training of forestry staff and local farmers  with emphasis on improving capacity in the implementation of SMART patrolling techniques for wildlife conservation, (iv)  and training on promoting increased adoption of tiger friendly land use practices among local communities in priority areas on forest lands in proximity to project-supported NRs.

- Sub-Component 3b: Pilot Mitigation Measures. This sub-component will support measures that would lead to the development and adoption of tiger - friendly land use practices in local communities living in proximity to project-supported nature reserves.  Pilot activities that would be supported under this sub-component include provision of technical assistance, evaluation of past and testing of new approaches to provision of compensation to mitigate human-wildlife conflicts, identification and implementation of alternative livelihoods (e.g., black fungus, medicinal plants, bee-keeping etc.).

- Sub-Component 3c: Increased Public Awareness. This sub-component will support a series of activities to increase public awareness of the global importance of tigers and other wildlife in NE China and the efforts designed for their conservation including the reduction of human – wildlife conflicts.  The Project would provide support primarily for the production of film, printing and distribution of informative material and the construction and placement of boundary markers and informative signs in critical areas in selected areas in proximity to project supported nature reserves.

- The expected Intermediate Results under this component are: (a) 26 Construction and equipping of new and upgrading and equipping of existing wildlife monitoring stations outside of project supported nature reserves; (b) 274 forestry staff trained and (c) 75,000 people participation in public awareness events and other related activities over LOP.

- Component 4: Project Management and Monitoring and Evaluation (Total: USD 0.66 million: GEF: USD 0.15 million)

- This component will support project management activities to be carried out by the implementing agency and coordination between provinces and across international boundaries. Three provincial project management units (PPMUs) will be set up at the provincial level in Jilin (1) and Heilongjiang Provinces (2); two in the latter province due to participation of two partners, the Provincial Forestry Bureau and the Forestry Corporation in the Project.  Support from the NGO and research communities, including in particular the WWF and the Feline Management Center (FMC) located in China’s Northeastern Forestry University will also be provided. The PPMUs will also coordinate with tiger conservation programs across the border in the Russian Far East, and sustainable forest management initiatives within the two provinces. A project coordination unit (NPMO) will be established within the State Forest Administration to ensure fiduciary and procurement standards are met in project implementation, coordinate cross-provincial and cross-international boundary project activities, M&E and facilitate reporting to the World Bank.

## Project Financing

- The lending instrument is Investment Project Financing. The project will be financed by a GEF grant of USD 3 million. In addition, a total of USD 17.58 million in co-financing has been committed from the following sources: (a) USD 8.76 million from Jilin Province, (b) USD 6.07 million from Heilongjiang Province, (c) USD 0.75 million from SFA and (d) USD 2 million from WWF to fund costs directly associated with project implementation. The contribution from the two provinces would be made by governments at provincial and lower levels and both in cash and in kind.

- The GEF grant will be used primarily for covering the costs of technical assistance, training and purchase of equipment for: (a) developing legal and planning frameworks to facilitate the achievement of the PDO/GEO, (b) increasing management effectiveness in existing nature reserves, (c) supporting the creation of new nature reserves, and (d) public awareness campaigns. Government of China will provide co-financing primarily to support the costs of: (a) human resources, equipment and infrastructure in the nature reserves and adjacent buffer zones and (b) interventions leading to improvement in habitat in support of wildlife conservation, and (c) mitigating identified social impacts  FRC will provide support to the project through design and implementation of the integrated monitoring program and participation in the Advisory Committee on Conservation of Tigers in NE China. WWF will provide support for: (a) updating  Jilin’s Conservation and Restoration Plan; (b) overseas study tours to observe examples of how to reduce adverse environmental impact on tiger habitat associated with development activities through visiting SMART infrastructure demonstration projects; (c) an international conference in support of greater collaboration in international tiger conservation activities under the existing Sino-Russian Agreement; and (d) equipment and TA in support of specific nature reserves.

- Table 1.  Project Cost and Financing

(In USD million)

| Project Components | Project Cost | GEF Financing | % Financing |
| --- | --- | --- | --- |
| 1. Institutional Coordination to Mainstream Wildlife Conservation across Sectors 2. Conservation of Priority Ecosystems and Increased Effectiveness of Habitat Protection in the Changbaishan Landscape 3. Reducing Human Wildlife Conflict in Priority Forest Landscapes 4. Project Management, Monitoring and Evaluation Total Financing Required | 1.73 9.18 9.01 0.66 20.58 | 0.72 1.57 0.56 0.15 3.00 | 41.7 17.1 6.2 22.5 14.6 |

IMPLEMENTATION

## Institutional and Implementation Arrangements

- The management structure of the project has been set up. The project implementation arrangements, in particular the role and responsibilities of government agencies and project implementation entities have been clearly defined and assessed by the Bank.

- At the national level, Department of Wildlife Conservation of State Forestry Administration (SFA) will provide the leadership for project implementation, coordinate the involved project agencies, and oversee the project management. It will hold meetings on a semi-annual basis or when requested by the provincial project agencies with relevant project agencies, review project working and budget plans, and monitor the overall project implementation.  A National Project Management Office (NPMO) was set in the SFA’s Planning and Design Institution of Forest Products Industry (PDIFPI) to be responsible for day-to-day project management at national level. The NPMO will be mainly responsible for: (a) coordinating project supported activities involving more than one province (e.g., integrated monitoring) and activities under the Sino-Russian cooperation agreement; (b) reviewing and integrating all needed inputs from the provinces to meet the reporting requirements of the Bank including providing English translations; and (c) monitoring and evaluating project implementation progress and quality to ensure they are in line with the project design.

- At the provincial level, three project management units (PPMUs) have been established in the two participating provinces, Jilin and Heilongjiang.  In Jilin Province the PPMU has been established in the Jilin Forestry Department (JFD).  In Heilongjiang Province, PPMUs has been established in the Heilongjiang Forestry Department (HFD) and Forestry Corporation (HFC), respectively.

- The PPMUs will be responsible for: (a) preparing provincial annual work and annual plans; (b) organizing procurement activities and project disbursement processes; (c) conducting quality check for the project activities that will be conducted by project entities to ensure that they are in compliance with the design and the Bank safeguard policies; (d) organizing professional institutions or expert team conducting project social, environmental; and (e) biodiversity monitoring. They will also coordinate with the expert team to provide technical assistance to the project entities through technical services, training and dissemination. The PPMUs are staffed with personnel with specialization in biodiversity conservation, project management including financial management and procurement as well as the project monitoring.

- At the local level, ten Project Entities (PEs) exist that will be responsible for the execution of project activities at the field level.  Specifically, the responsibilities of the PEs will be undertaking the project activities in the field including small-scale civil works, training to local staff, forest restoration and management, wildlife protection activities and other day-by-day field work. The project entities are listed in below Table 2:

Table 2. Local Project Entities

| Province | Forestry Management System | PE Names | Location (county) |
| --- | --- | --- | --- |
| Heilongjiang | FHD | Dongning Niaoqingshan Nature Reserve | Dongning |
|  | HFC | Suiyang Forestry Bureau | Dongning |
|  |  | Heilongjiang Laoyeling Amur Tiger Nature Reseve | Dongning |
|  |  | Muling Forestry Bureau | Muling |
|  |  | Muling Northeast Hongdousha Nature Reserve | Muling |
| Jilin | JFD | Hunchun Forestry Bureau | Hunchun |
|  |  | Jilin Hunchun Amur Tiger Nature Reserve | Hunchun |
|  |  | Wangqing Forestry Bureau | Wangqing |
|  |  | Jilin Wangqing Amur Tiger Nature Reserve | Wangqing |
|  |  | Tianqiaoling Forestry Bureau | Wangqing |

- Technical Expert Panel. As part of capacity building activities, an Advisory Tiger Landscape Committee in northeast of China will be established.  It would be composed of recognized national and provincial experts to provide the technical support to the project implementation, which include a series of activities (e.g., promoting joint anti-pouching activities, staff training, developing a standard monitoring protocol, and the consolidation of statistics), leading to increased cooperation between the project’s three main stakeholders and their respective Russian counterparts under the existing Sino-Russian cooperative agreement.

- The Committee will serve as a source of technical inputs reflecting the latest scientific data on tigers and other wildlife and their habitat, and it will provide a basis to determine how best the Project can adapt to the latest thinking in a cost-effective manner while achieving the GEO.  The Committee would also be available for consultation on an ad hoc basis when necessary.  The Committee will meet at least 8 times over the 4 year life of project with the first and last meetings hosted by the NPMO and the remaining 6 meetings hosted equally between the three partners.

- During project implementation the Ministry of Finance (MOF) will channel project funds directly to the respective provincial Bureaus of Finance (BOF) who will be responsible for supervising all financial management issues related to project implementation while the PPMUs and PEs will be responsible for managing of project operations.

## Results Monitoring and Evaluation

- The Project will support the establishment of a Monitoring & Evaluation (M&E) system.  The M&E system includes: (a) monitoring project implementation progress and quality; (b) evaluating the achievement of the PDO; and (c) assessing environmental and social impacts. The execution of most project-supported field activities will be the responsibility of the project entities. The responsibility for M&E however will be divided between the PPMUs and the NPMO.

- At the provincial/partner level, the M&E tasks and responsibilities of the PPMU will be achieved through: (a) day-to-day project performance monitoring; (b) technical monitoring of biodiversity and ecosystem “status”, including the integrated technical monitoring plan led by the FRC (including NR-specific indicators for biodiversity “richness” and their respective targets to be defined in project year 1); (c) monitoring the implementation of the EMP by coordinating with NPMO, respectively; and (d) midterm and final evaluations, with the METTs used to evaluate effectiveness of each of the project nature reserves.

- At the national level, the responsibilities of the NPMO for M&E will be primarily on providing leadership and guidance to the overall project monitoring, oversight and consolidation of information provided from the three partners.  At the initiation of project implementation the NPMO through the M&E specialist will set up a project progress monitoring system coordinated with counterpart systems in each of the three project-supported PPMUs. Participatory mechanisms and methodologies for systematic data collection and recording will be developed in support of outcome and output indicator monitoring and evaluation.

- The Project’s Results Framework (Annex 1) includes expected PDO and intermediate results indicators and it will be the main tool for assessing project implementation progress and whether project results are being achieved. The GEF monitoring and evaluation tracking tools (METTs) will be applied at the end of the second and fourth years of this four year project as part of the mid-term review (MTR) and implementation completion reviews (ICR). The Bank will monitor the project implementation through supervision missions as well as day-to-day work.

- Reporting.  Every year on July 15 and January 15, the PPMUs will submit semi-annual progress reports to the NPMO. The NPMO will consolidate these subproject reports into a semi-annual project report and furnish it to the Bank by February 15, commencing on 2016 and an annual project monitoring report on August 15 of each year, commencing on 2016. These reports will include an updated results monitoring table (Annex 1) indicating the progress made by the project towards achieving its outputs and outcome indicators.

- In addition to the semi-annual reports, the NPMO will submit the following reports to the Bank: (a) a project annual work and budget plan for the next calendar year by December 15 of each year, commencing on December 15, 2015; (b); a mid-term review report on June 30, 2017; and (c) a project ICR on June 30, 2019. The project monitoring progress and results report could be part of the project progress reports, as well as the mid-term review report and the ICR.

## Financial Management and Disbursements

- The Financial Management (FM) capacity assessment concluded that the Project FM arrangements satisfy Bank requirements and identified the following principal risk: PPMUs’ financial staff lack experience in managing Bank operations.

- Mitigation measures to address the above risk that have been agreed to are: (a) preparation and issuance of a Financial Management Manual (FMMs) acceptable to the Bank to standardize project FM procedures; (b) in addition to extensive FM training from the Bank, the PFBs who have experience with the Bank operations will arrange more extensive workshops and experience sharing; and (c) NPMO strengthening FM guidance and supervision to PPMUs.

- Overall, the residual project FM risk after mitigation is assessed as Moderate.

- The three PPMUs will be responsible for day-to-day project FM work including project accounting and financial reporting. Financial staffs with segregation of duties are in place in each PPMU. Through observation and review of educational background and work experience of the staffs identified for financial and accounting positions in the PPMUs, the task team noted that they are qualified and appropriate to conduct the work they are expected to assume.

- Budgeting. The counterpart funds will come from local government appropriations and donation from relevant organizations, such as the World Wide Fund for Nature (WWF). The PPMUs will prepare the annual project implementation plan, including the funding resources and budget and submission to the relevant finance bureaus and donors to arrange counterpart funds. All counterpart funds committed by local governments will be reviewed and approved by local People's Congress and be included in their sectoral budget. Budget variance analysis will be conducted semi-annually by PPMUs to inform management of significant variances from plan that may need corrective actions.

- Funds flow. Two project DAs will be opened in USD and managed by Heilongjiang Provincial Finance Bureau (HPFB) and Jilin Provincial Finance Bureau (JPFB). The GEF grant will be: (a) directly paid from the Bank to contractors or reimbursed from the Bank to PPMUs for the portion financed by the Bank paid by PPMUs first or (b) reimbursed from DAs to PPMUs or directly paid from DAs to contractors.

- Accounting and financial reporting. The administration, accounting and reporting of the project will be set up in accordance with Circular #13: “Accounting Regulations for World Bank Financed Projects” issued in January 2000 by the MOF. The standard set of project financial statements has been agreed between the World Bank and MOF. The PPMUs will be responsible for daily project FM work including project accounting and financial reporting. Original accounting documents for project activities will be retained by the PPMUs. Three unaudited semi-annual project interim financial reports (IFRs) by province will be prepared and furnished to the Bank through the NPMO  no later than 45 days following each semester (the due dates will be February 15th and August15th), in form and substance satisfactory to the Bank.

- Adequate project accounting staff with educational background and work experience commensurate with the work they are expected to perform is one of the factors critical to successful implementation of project financial management. Based on discussions, observation and review of educational background and work experience of the staff identified for financial and accounting positions in each PPMU, the task team noted that they need more well-designed training, peer learning, and closer guidance throughout implementation period.

- The task team will monitor the accounting process, including the adequacy of the financial management system and staff training, especially during the initial stage to ensure complete and accurate financial information are provided in a timely manner.

- Internal control. Accounting policy, procedures and regulations for Bank projects were issued by MOF and the FMMs that align the financial management and disbursement requirements among various implementing agencies. Besides, NPMO  will provide guidance and supervision to local PPMUs covering: (a) compliance of Circular #13 for project accounting and financial reporting; (b) examination of usage of DAs and the eligibility of project expenditures as well as efficiency of withdrawal procedures and funds flow; (c) contract management; and (d) budget preparation and variation analysis. The supervision results will be documented in a report and filed.

- Audit. Heilongjiang Provincial Audit Office (HPAO) and Jilin Provincial Audit Office (JPAO) have been identified as the auditor for the project. Two annual audit reports will be issued by HPAO and JPAO and will be due to the World Bank within six months after the end of each calendar year. HPAO and GPAO have extensive experience with auditing the Bank financed operations. According to the World Bank Policy on Access to Information, the audit report for all investment lending operations for which the invitation to negotiate was issued on or after July 1, 2010, need to be made publicly available in a timely fashion and in a manner acceptable to the Bank. Audit reports will be made publicly available on the website of the provincial auditor. Following the World Bank's formal receipt of the audited financial statements from the borrower, the World Bank will also make them available to the public in accordance with the World Bank Policy on Access to Information.

- Three disbursement methods are all available for the project:  advance, reimbursement and direct payment. Supporting documents required for Bank disbursement under different disbursement methods will be documented in the Disbursement Letter issued by the Bank.

- Two segregated DAs in US dollar will be opened at a commercial bank acceptable to the Bank and will be managed by HPFB and JPFB. The ceiling of the DAs will be determined and documented in the Disbursement Letter.

- The GEF grant would be disbursed against eligible expenditures (taxes inclusive) as in the table 4.

Table 4:  Allocation of GEF grant resources by category of disbursements

| Category* | Amount of the Grant Allocated (expressed in USD) | Percentage of Expenditures to be Financed (inclusive of Taxes) |
| --- | --- | --- |
| Jilin Province |  |  |
| Works and Goods | 704,000 | 100 |
| Services | 826,000 | 100 |
| Incremental Operating Costs | 70,000 | 100 |
| Heilongjiang Province |  |  |
| Heilongjiang Forestry Bureau |  |  |
| Works and Goods | 282,000 | 100 |
| Services | 418,000 | 100 |
| Incremental Operating Costs | 50,000 | 100 |
| Longjiang Forestry Corporation |  |  |
| Works and Goods | 431,000 | 100 |
| Services | 189,000 | 100 |
| Incremental Operating Costs | 30,000 | 100 |
| TOTAL AMOUNT | 3,000,000 |  |

* “Incremental operating cost” means the operating costs of the Project incurred by Jilin and Heilongjiang on the basis of the annual work plans and budgets for purposes of Project management, implementation, and monitoring and evaluation, on account of office supplies and consumables, utilities, bank charges, communications, mass media and printing services, vehicle rental, operation, maintenance, and insurance, building and equipment maintenance, domestic travel, lodging, and subsistence allowances, and salaries of contractual and temporary staff, but excluding salaries and any salary supplements of members of the civil service.

- Supervision Plan. The supervision approach for this project is based on its FM risk rating, which will be evaluated on regular basis by the FMS in line with the FMSB’s FM Manual and in consultation with relevant task team leader. The initial FM supervision will focus on: (a) setup of project accounts, (b) compliance of Circular #13 of project accounting and financial reporting and (c) management on further advances

## Procurement

- Procurement Assessment.   The NPMO at central level will be responsible for overall procurement management and supervision under the project. All procurement activities will be carried out by three PPMUs at provincial level. A procurement capacity and risk assessment of the NPMO and PPMUs found that lack of coordination among three PPMUs from the central level and weak procurement capacity at PPMU level are the two main risks which may negatively impact project implementation. The NPMO, which should play the coordinating role to provide support to three PPMUs, was not functioning well at pre-appraisal stage. Each PPMU was working on its own with little support and coordination from NPMO. In addition, the PPMU procurement staff lack Bank procurement experience. To mitigate these risks, the following actions were agreed:  (a) the NPMO  to assign/appoint procurement staff with public procurement experience to be responsible for overall procurement coordination, guidance and monitoring of the project; and (b) a procurement and contract management learning plan has been prepared and is under implementation. PPMU and NPMO staff responsible for processing, reviewing and approving procurement under the project will actively take part in Bank procurement training and communications between the NPMO and the PPMUs will be strengthened. The overall procurement risk for the project is assessed as Substantial.

- Applicable Guidelines. Procurement will be carried out in accordance with the “Guidelines: Procurement of Goods, Works and Non-Consulting Services under IBRD Loans & IDA Credits & Grants by World Bank Borrowers” dated January 2011, revised July 2014; and “Guidelines: Selection and Employment of Consultants under IBRD Loans and IDA Credits & Grants by World Bank Borrowers” dated January 2011, revised July 2014; and the provisions stipulated in the Grant Agreement. National Competitive Bidding (NCB) will be carried out in accordance with the Law on Tendering and Bidding of the People’s Republic of China promulgated by the Order of the President of the People’s Republic of China on August 30, 1999 subject to the modifications stipulated in the Grant Agreement in order to ensure broad consistency with World Bank Procurement Guidelines.

- Procurement of Works. There are no large value works contracts to be procured through International Competitive Bidding under the project. No works procurement is included in the current procurement plan. For works procurement which may be added to the procurement plan in the future, it will be conducted using National Model Bidding Documents agreed with or satisfactory to the Bank for all National Competitive Bidding (NCB) and Enquiry Document agreed with or satisfactory to the Bank for all Shopping contracts.

- Procurement of Goods and Non-consulting Services. Small value goods contracts covering procurement of patrol equipment, office equipment, pickups, motorcycles, etc. will be procured. Procurement will be done using the relevant Bank’s Standard Bidding Documents for all ICB contracts, National Model Bidding Documents agreed with or satisfactory to the Bank for all NCB contracts and Enquiry Documents agreed with or satisfactory to the Bank for all Shopping contracts.

- Selection of Consultants. Consultants for Amur tiger protection planning, protection zone scientific research report preparation, etc. will be hired. The Bank’s Standard Request for Proposals will be used for all QCBS and QBS. Universities and research institutes may be included in shortlists as a source of consultants, provided they possess the relevant qualifications and they are not in a conflict of interest situation.  In such cases, QBS or CQS (for small assignments) would be used, if the shortlist also includes consulting firms which operate as commercial entities.  The shortlist may comprise entirely national consultants (firms registered or incorporated in the country), if the assignment is below 500,000.

- Training and Workshops. Plans for training and workshops will be developed by the PMO and PPMUs together, and included in the project annual work plan for Bank review. Expenditures incurred in accordance with the approved plans for training and workshops organized by the NPMO and PPMUs will be the basis for reimbursement. For trainings, workshop and study tours to be organized by third party service providers, the Bank Guidance Note on Planning, Budgeting, Implementing, Reporting and Accounting for Expenditures related to Training & Workshops in Bank-financed Projects in China & Mongolia would apply.

- Procurement Plan. A Procurement Plan for the first 18 months of project implementation, acceptable to the Bank, has been prepared by the NPMO. It will be made available on the Bank’s external website.  The Procurement Plan will be updated annually or as required to reflect implementation needs and improvements in institutional capacity.

- Procurement Thresholds. The Indicative thresholds for procurement methods and Bank prior review are presented below:

Table 5: Thresholds for Procurement Methods and Prior Review

| Expenditure Category | Contract Value Threshold (USD thousands) | Procurement Method | Prior Review Threshold (USD thousands) 1/2/ |
| --- | --- | --- | --- |
| 1. Goods and Non-Consulting Services | ≥10,000 <10,000 <300 -- | ICB NCB Shopping Direct Contracting | All The first NCB contract of each PPMU regardless of value and all contracts valued ≥1,000 The first Shopping contract of each PPMU regardless of value. >=200 |
| 2. Works and Supply and Installation of Plant and Equipment | ≥40,000 <40,000 <500 | ICB NCB Shopping | ALL The first NCB contract of each PPMU regardless of value. The first Shopping contract of each PPMU regardless of value. |
| 3. Consultants Services | ≥300 <300 -- -- -- | QCBS/QBS CQS Individual Consultant Single-Source Selection (firm) Single-Source Selection (individual) | The first contract for each selection method of each PPMU regardless of value and all contracts valued >=500 The first CQS contract of each PPMU regardless of value. Only in exceptional cases. >=USD100 >=50 |

    - All contracts to be financed through retroactive financing will be subject to prior review.  A contract whose cost estimate was below the Bank prior review threshold is subject to prior review if the price of the lowest evaluated responsive bid (or, in the case of consulting services, the financial offer of the selected firm) exceeds such threshold at the bid/proposal evaluation stage.

    - Procurement post review may be carried out by the Bank, its consultants/auditors.

- Direct Contracting. The Jilin PPMU proposed to contract suppliers for making protection area signs (JFD-G-005 and JFD-G-006) valued about USD14, 000 and USD10, 500 respectively through Direct Contracting with the previous suppliers at market price; the Heilongjiang Forestry Corporation PPMU proposed to contract authorized supplier for 15 sets of fire-fighting equipment (SG006) valued about USD3,000.  Given the small value of the contract, the Bank has no objection to the proposal.

## Social Safeguards

- The proposed activities trigger Indigenous People OP 4.10 and Involuntary Resettlement OP 4.12, and will have various impacts on local communities, such as strengthening restriction of access into the RAs, land reclamation, and wildlife-human conflicts. To address these impacts, a social assessment (SA), a resettlement policy framework (RPF), an Ethnic Minority Development Plan (EMDP) and a Process Framework (PF) were prepared by SFA. These documents were reviewed and found satisfactory and in compliance with the World Bank policies. The costs associated with the mitigation of social safeguards will be covered with counterpart funds provided by the World Wide Fund for Nature and the governments of the project provinces.

- Social Assessment. One hundred and twenty nine households in 14 villages and 330 households in 25 forest farms, and staff from relevant authorities, were investigated via meetings, interviews, and questionnaires. The investigation also identified vulnerable households, including 17 village households and 8 worker households. The project will generate ecological benefits in the region, at the same time could cause adverse impacts on local communities, including three ethnic minority communities, mainly on use of farmland and forestry as well as income decrease. The SA stated that villagers are farming 10 mu farmland per capita; plus 40 mu village forest land per capita to obtain CNY 8,000 to 25,000 income per capita; worker families are using 4 mu farmland per capita to get CNY 8,000 to 40,000 income per capita, and that the project will not affect their assets, but may affect less than 10% of the total income due to activities related to the access restrictions to forests. At present, financial loss from the logging ban due to establishment of the new NR or the expansion of existed NRs would cause income loss related to forest farms with highest of 43% and lowest of 10%. Financial losses for local villagers are also roughly estimated, mainly due to, restriction of access to NRs and decreased chances for collecting NTFPs . In addition, some households that keep cattle would be affected by wild animal-caused accidents or consumption of agricultural assets by wildlife and the transformation of forest farms to reserves. The SA proposed relevant measures to handle the potential impacts, which have been integrated into the detailed project design and implementation. The loss from banning logging will be compensated by SFA with the Natural Conservation Forest Funds. The implementation of the mitigation instruments costs are budgeted as part of the counterpart funds under Sub-component 3b on “Pilot Mitigation Measures”. Local forestry authorities and NRs administrations will be responsible for implementation of the plans and frameworks.

- Involuntary Resettlement: The impact analysis identified and investigated possible impacts by the proposed activities in the project area in both provinces, and found that 8903 persons in 39 communities and farms, including 4559 persons in 14 villages and 4344 persons in 25 forest farms, will be affected. The impacts are from strengthening the restriction of access to the NRs.  No land acquisition and resettlement was identified, but potential land acquisition could not be excluded during the implementation stage, so a RPF was prepared.

- Based on extensive consultation among affected villages, forest farms, and forest bureaus, the PF forecasted possible impacts by the planned strengthening restriction of access to the protected areas in the two provinces, and concluded that the above mentioned persons would face other uncertain income decrease as a result of strengthening access restrictions. The PF established a framework to further identify the affected villagers/individuals, as well as potential impacts and possible measures in the project implementation stage. Further the PF recommended to prepare Protected Area Co-management Plans together by village and forest authority, as well as Village Development Plan in four pilot villages defined in the implementation stage, to achieve the win-win between the communities and authorities. The total cost is estimated at USD313,000 during the lifetime of the project.

- Ethnic Minority: The EMDP identified three ethnic minority villages, two are Korean villages and one is Korean and Manchu village. All the 3 villages are in the surrounding areas of Hunchun NR and part of their livelihood rely on cattle grazing and NTFP collection. With project implementation, wildlife consumption of domestic agricultural assets could affect grazing and NTFP collection. In order to guarantee the free, prior and informed consultations with ethnic minorities, a series of consultation campaigns were carried out.  The campaigns included six consultations with JFD and its branches at city and county levels, four key informant interviews and three focus group interviews at county level. In addition two key informant interviews and 82 household questionnaires were carried out in the 3 villages. The potential impacts and their measures were separately identified and explored with participatory planning.  A series of consultation campaigns found that the three villages broadly supported the project. The critical impacts related to the strengthening of access restriction which results to prohibiting grazing, collection, cutting, etc. in the protected areas, and their proposed mitigation measures to address these restrictions mainly rely on: alternative income-generation training, such as greenhouse production or ecotourism training.   This could include study tours to learn from other successful models. The total cost of addressing these issues is estimated at USD 395,000.

- Monitoring Arrangement. Internal and external monitoring on implementing the RP/PF/EMDP were designed and agreed in the relevant documents, including institutional and financial measures to ensure the proper implementation of the documents. Experienced external monitors will be contractually engaged by the PPMOs to conduct semiannual monitoring in the project areas and the report should be submitted to the Bank periodically.

- Consultation and Participation. Apart from information distribution in the provinces and the relevant communities by local governments and forest authorities, the project preparation team also conducted extensive consultation among the 39 project affected villages/communities and farms as part of the process of impact investigation and to measure development. A total of 129 households in 14 villages and 330 households in 25 forest farms, as well as staff from relevant authorities, participated in the consultation process through interviews, meetings, and questionnaire survey (table 6). Further consultation with and participation of the affected communities will be continuously implemented in the implementation of the RPF/PF/EMDP, as well as in the development and implementation of the Protected Area Co-management Plan, and Village Development Plan. Farmer representatives (including women) from the neighboring communities around the NRs will be organized, join training activities and be facilitated to participate in the process of developing VDPs, the Co-management Plans and the livelihood restoration plans. During implementation an effective communication mechanism will be established between affected communities and the NR authorities on protection, livelihood development, resource sharing, and community development, among others.

Table  6.  Consultation with Stakeholders

| Stakeholders | Methods | Quantity | Location |
| --- | --- | --- | --- |
| HFC | Meeting Key informant interview Focus group interview | 6 4 3 | Beijing, Harbin |
| HFD | Meeting Key informant interview Focus group interview | 6 4 3 | Beijing, Harbin |
| JFD | Meeting Key informant interview Focus group interview | 6 4 3 | Beijing, Changchun |
| Forest workers, Heilongjiang NRs | Questionnaire Focus group interview | 65 1 | Muling City |
| Farmers, Heilongjiang NRs | Questionnaire Focus group interview Key informant interview | 123 2 2 | Muling City, Doning County |
| Forest workers, Jilin NRs | Key informant interview Questionnaire | 2 89 | Wangqing County, Muling City |
| Farmers, Jilin NRs | Key informant interview Questionnaire Focus group interview | 3 56 2 | Wangqing County, Hunchun City |

## Environmental  Safeguards

- The project is classified as Category B as per OP 4.01 Environmental Assessment because the identified impacts on natural habitats and social issues such as potential access restrictions to protection and conservation areas are deemed to be site-specific and reversible. Based on the environmental screening and assessment, the following Bank Environmental safeguards policies are triggered: (1) OP4.01 Environmental Assessment; (2) OP4.04 Natural Habitats; (3) OP4.36 Forests; and (4) Pest Management OP 4.09.

- Accordingly, a partial environmental assessment was conducted by Planning and Design Institute of Forest Products Industry of the State Forestry Administration. The draft environmental safeguards documents have been reviewed and commented on by Bank task team environmental specialists, and final environmental assessment documents—including an Environmental Impact Assessment (EIA) Report and Environmental Management Plan (EMP) were found to be in compliance with the Bank’s Safeguard policy requirements.

- The EIA adequately addressed the key environmental issues, specifically impacts on human and livestock security, restriction of livelihood activities for farmers, impacts of vegetation and biodiversity, pest management, and small scale construction impacts. A stand-alone EMP has been developed based on the findings of the EIA report. It contains Environmental Protection Guidelines (EPG) for plantation to be followed during preparation and implementation of forests related interventions, a Pest Management Plan (PMP), and Environmental Code of Practice (ECOP) for small civil works. The EMP detailed the environmental management and supervision organizations and responsibilities, mitigation measures, training plan, monitoring plan, and budget estimates of EMP implementation. The costs of these environmental and social monitoring and training will be covered with counterpart funds provided by the World Wide Fund for Nature and the governments of the project provinces.

- Main Environmental Impacts and Mitigation Measures. The EA identified and assessed the project benefits and impacts to the natural and social environment and concluded the project will generate significant net positive environmental and ecological benefits in the project area. Through tiger-friendly forest tending activities, the habitat quality of the Siberian tiger in the project area should be significantly recovered and improved, and population of main prey (wild boar, red deer, roe deer and sika deer) should rebound significantly. Key habitats should be recovered and expanded, and the establishment of new nature reserves should increase the reserve area. All these should increase the suitable habitat areas of the Siberian tiger and its prey population. Thus, the current isolated distributional areas of the Siberian tiger should be connected with each other, extended and expanded in stretches to the deep forest of China.

- Meanwhile, the project will have the potential to have impacts on the livelihoods of the forest workers and villagers nearby, impacts of human and livestock security, impacts of vegetation and biodiversity, impacts of pests, and some small scale construction related impacts such as loss of vegetation and soil erosion, noise and dust. These potential adverse impacts have been appropriately assessed and can be adequately avoided, eliminated, minimized and/or mitigated with measures developed either in project design or included in the project’s EMP.

- Environmental Management Plan (EMP). A stand-alone EMP has been developed based on the findings of the EIA report. It contains Environmental Protection Guidelines (EPG) for plantation to be followed during preparation and implementation of forests related interventions, Pest Management Plan (PMP), and Environmental Code of Practice (ECOP) for small civil works. The EMP detailed the environmental management and supervision organizations and responsibilities, mitigation measures, training plan, monitoring plan, and budget estimates of EMP implementation. EPG, PMP, and ECOP were prepared as a standalone annex to the EMP. Environmental mitigation measures developed in EMP will be fully incorporated into the bidding documents and contracts of Contractors.

- Natural Habitats OP4.04. The project includes the improvement of the management effectiveness of existing protected areas, and creation of new protection areas, which are both critical natural habitats as defined under the policy. The project also includes the potential impacts and measures of increasing existing prey population on the ecology/ecological balance of the protected areas.

- Forests OP4.36. The project will include limited reforestation with local, indigenous species.  It will not entail conversion of natural forests, commercial harvesting operation and the introduction of any invasive species. However, the project has the potential to have impacts on the rights and welfare of people and their level of dependence upon or interaction with forests, the policy is therefore triggered. Given the very limited relocation/access restriction proposed the adverse impacts are minor. The social aspects with the relevant context have been incorporated into the EMP accordingly. In addition, the alternative livelihood will be designed and implemented outside of the protected areas, as part of the project activities.

- Pest Management OP 4.09. The project will include critical areas of vegetation restoration, artificial tending, and nursery management etc. A Pest Management Plan (PMP) was prepared to guide the application of pesticides for the forest activities. The PMP covers preface, major pest issues, pesticides management methods and their scope of application, and provided recommendations for different situations. It summarizes the IPM approaches adopted by the project, and lists all chemicals that might be potentially needed for the project, which fulfill the Bank’s requirement and within the World Health Organization’s recommended categories. It describes pesticides management organizations in project areas and their respective responsibilities. It includes a training program, monitoring program and cost estimation for project implementation.

- Safeguard Document Disclosure.  Public consultations and information disclosure have been carried out during the preparation of the environmental assessment and social assessment processes. A combination of expert consultations, questionnaires, and interviews in the project area of influence has been implemented during EA and SA preparation. The EIA/EMP, RPF, PF, EMDP and SA were first disclosed locally on March 30, 2015 and on Infoshop on April 1, 2015. Final version were disclosed at The World Bank Infoshop on June 10, 2015.

## Role of Partners

- Other project partners are World Wide Fund for Nature (WWF) and the Feline Research Center (FRC).  WWF has been active in China since 1960’s and was the first international NGO to work on nature conservation in the country. WWF has more than 120 staff working in China in support of a broad range of conservation programs which includes such project relevant experience as its support in the establishment of 62 giant panda nature reserves.  As one of the project’s co-financiers the WWF will support activities to be implemented in the Jilin portion of the project area.  Specifically, WWF  will provide support for: (a) updating  Jilin’s Conservation and Restoration Plan; (b) overseas study tours to observe examples of how to reduce adverse environmental impact on tiger habitat associated with development activities through visiting SMART infrastructure demonstration projects; (c) an international conference in support of greater collaboration in international tiger conservation activities under the existing Sino-Russian Agreement; and (d) equipment and TA in support of specific nature reserves.

- The SFA’s Feline Research Center was founded in 2011 and is presently housed in Heilongjiang’s Northeast Forestry University located in Harbin.  Its main objective is to provide an international center for technology and information exchange in feline conservation research in China. Among its main objectives are to: (a) integrate the information of experts and set up a platform for the technology and information exchange in the feline conservation research in China; (b) promote the implementation of action strategies and projects in support of the conservation of endangered felines such as Amur tigers and Amur leopards; and (c) explore how best to implement an ecosystem-based approach with big cats as the flagship species. As China’s center of excellence in this field they will be providing support to the project through design and implementation of the integrated monitoring program and participation in the Advisory Committee on Conservation of Tigers in NE China.

## Overall Risk Rating and Explanation of Key Risks

|  | Rating |
| --- | --- |
| Stakeholder Risk | M |
| Implementing Agency Risk |  |
| - Capacity | M |
| - Governance | M |
| Project Risk |  |
| - Design | M |
| - Social and Environmental | M |
| - Delivery Monitoring and Sustainability | M |
| Overall Implementation Risk | M |

- Key risks identified in the Project Concept Note have been fully evaluated and mitigated as much as feasible during project preparation. The keys issues were: (i) The project implementing agencies are new to Bank operations, and (ii) potential impact on the livelihood of local population. Mitigation measures to address these challenges have been incorporated into project design. The residual overall risk of the project with the adoption of the mitigation measures is rated as Moderate.  The implementation of the mitigation measures will be closely monitored for their effectiveness and, if needed, they will be adjusted accordingly.

# Annex 1: Results Framework and Monitoring

China: Landscape Approach to Wildlife Conservation in Northeast China (P122383)

| Global Environment Objective (GEO): The project’s global environment objective is to help create the ecological conditions for recovery of threatened biodiversity in priority ecological landscapes in the far northeast of China (Heilongjiang and Jilin), using the Amur Tiger as a flagship species. |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator Name | Core | Unit of Measure | Baseline | Annual Target Values |  |  |  | Frequency | Data Source/ Methodology |  | Responsibility for Data Collection |
|  |  |  |  | YR1 | YR2 | YR3 | End Target |  |  |  |  |
| Area brought under enhanced biodiversity protection in existing and new nature reserves | x | km2 | 0 | 2,830 | 3,521 | 3,697 | 3,697 | Semi-annually | Progress reports; output verification reports |  | NPMO/PPMUs |
| Area outside of nature reserves managed in a biodiversity friendly manner. | x | km2 | 0 | 720 | 1,408 | 2,000 | 2,252 | Semi-annually | Progress reports; output verification reports |  | NPMO/PPMUs |
| Intermediate Results Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Indicator Name | Core | Unit of Measure | Baseline | Annual Target Values |  |  |  | Frequency |  | Data Source/ Methodology | Responsibility for Data Collection |
|  |  |  |  | YR1 | YR2 | YR3 | End Target |  |  |  |  |
| Component 1 Institutional coordination to mainstream wildlife conservation across sectors |  |  |  |  |  |  |  |  |  |  |  |
| Updated Jilin Conservation and Restoration Plan presented to Provincial Development and Reform Committee (DRC) Provincial-wide tiger conservation management plan submitted for approval by Provincial DRC in Heilongjiang Province | ☐ ☐ | % % | 0 0 | 50% - hire consultants - public consultation and consultation with key stakeholders - preparation of draft plan 30% - hire consultants - public consultation and consultation with key stakeholders | 100% - JFD internal review and comment - external review and comment - incorporate changes - submit to DRC 70% - preparation of draft plan - HFD internal review and comment - external review and comment -incorporate changes | 100% 100% -submit to DRC | 100% 100% | Semi-annually Semi-annually |  | Progress reports; output verification reports; draft plan Progress reports; output verification reports; draft plan | NPMO/PPMU NPMO/PPMU |
| NE China advisory tiger landscape conservation committee established | ☐ | # | 0 | 1 | 1 | 1 | 1 | Semi-annually |  | Progress reports; declaration of creation; minutes of meetings | NPMO/PPMUs |
| Cross-provincial collaboration with Russian counterparts | ☐ | # | 0 | 1 | 2 | 3 | 4 | Semi-annually |  | Progress reports | NPMO/PPMUs |
| Component 2 Conservation of priority ecosystems and increased effectiveness of habitat protection in the Changbaishan Landscape |  |  |  |  |  |  |  |  |  |  |  |
| Increased average management effectiveness achieved in 4 existing NRs Hunchun NNR Wangqing NNR Mulin NNR Laoyoling NNR | ☐ ☐ | # # # # # | 38 49 35 42 27 | - - - - - | 49 60 51 48 36 | - - - - - | 60 71 63 57 47 | In 2nd and 4th years |  | METT | NPMO/PPMUs/ external evaluators |
| Three new NRs (866 km2) of new protected area for tiger and other wildlife established. | ☐ ☐ | # km2 | 0 0 | 0 0 | 2 691 | 3 866 | 3 866 | Semi-annually |  | Progress reports; output verification reports; legal declarations of establishment | NPMO/PPMUs |
| NR staff trained (disaggregated by gender) | ☐ | # | 0 | 67 | 140 | 202 | 296 | Annually |  | attendance records; certificates of training awarded | NPMO/PPMUs |
| Decrease in incidence of snares in defined sampling sites in project area (both inside and outside of nature reserves) | ☐ | % | TBD in PY 1 | - | (- 10) | (- 18) | (- 24) | Semi-annually |  | Progress reports; output verification reports; site visits and field monitoring records | NPMO/PPMUs |
| Integrated cross-provincial ecological monitoring program | ☐ | % | discrete monitoring programs exist among the 3 partners | 100 % - develop a common methodology - design data base - define sampling area/sites - complete common training program | 100% | 100% | 100% | Semi-annually |  | Progress reports; output verification reports; technical monitoring reports | NPMO/PPMUs |
| Component 3 Reducing human wildlife conflict in priority forest landscapes |  |  |  |  |  |  |  |  |  |  |  |
| Construction and equipping of 2 new and upgrading and equipping of 26 existing wildlife monitoring stations outside of project supported nature reserves. | ☐ ☐ | # # | 0 0 | 1 19 | 2 26 | 2 26 | 2 26 | Semi-annually |  | Progress reports; output verification reports; site visits | NPMO/PPMUs |
| Forestry staff trained disaggregated by gender) | ☐ | # | 0 | 63 | 129 | 186 | 274 | Annually |  | attendance records; certificates of training awarded | NPMO/PPMUs |
| Farmers receiving benefits derived from project-supported alternative livelihood activities | ☐ ☐ | # | 0 | 0 | 1,000 | 2,000 | 3,000 | Semi-annually |  | Progress reports; output verification reports; site visits | NPMO/PPMUs |
| People participate in public awareness activities over LOP disaggregated by gender) | ☐ | per time | 0 | 25,000 | 50,000 | 75,000 | 75,000 | Semi-annually |  | Progress reports; output verification reports | NPMO/PPMUs |

# ANNEX 2: EXPECTED Outputs by Partner

China: Landscape Approach to Wildlife Conservation in Northeast China (P122383)

| PDO Indicators | Partner Institutions |  |  | Totals |
| --- | --- | --- | --- | --- |
|  | JFD | HFD | HFC |  |
| Area brought under enhanced biodiversity protection in existing and new nature reserves (km2) | 2,452 | 176 | 1,069 | 3,697 |
| Area outside of nature reserves managed in a biodiversity friendly manner (km2) | 1,103 | 406 | 743 | 2,252 |
| Intermediate Results |  |  |  |  |
| Component 1 |  |  |  |  |
| Updated Jilin Conservation and Restoration Plan presented to Provincial Development and Reform Committee (DRC) | 1 | - | - | 1 |
| Provincial-wide tiger conservation management plan submitted for approval by Provincial DRC in Heilongjiang Province | - | 1 | - | 1 |
| Local regulations/management measures (non – NR-specific) | - | 2 | 3 | 5 |
| Local plans (non – NR-specific) | - | 1 | 1 | 2 |
| NE China advisory tiger landscape conservation committee established | - | - | - | 1 |
| Cross-provincial collaboration with Russian counterparts (bi-national meetings) | 2 | 2 | - | 4 |
| Component 2 |  |  |  |  |
| Increased management effectiveness achieved in 4 existing NRs (METT score) Hunchun NNR Wangqing NNR Mulin NNR Laoyoling NNR | 49 (baseline) 35 (baseline) - - | - - - - | - - 42 (baseline) 27 (baseline) | 71 (end of project) 63 (end of project) 57 (end of project) 47 (end of project) |
| Three new NRs (866 km2) of new protected area for tiger and other wildlife established. | 2 691 km2 | 1 175 km2 | - - | 3 866 km2 |
| NR staff trained | 176 | 20 | 100 | 296 |
| Decrease in incidence of snares in defined sampling sites in project area (both inside and outside of nature reserves) | TBD | TBD | TBD | - 24 % (from baseline) |
| Integrated cross-provincial ecological monitoring program implemented. | - | - | - | 1 |
| Component 3 |  |  |  |  |
| Construction and equipping of 2 new and upgrading and equipping of 26 existing wildlife monitoring stations outside of project supported nature reserves. | - 14 | 2 - | - 12 | 2 26 |
| Forestry staff trained | 94 | 100 | 80 | 274 |
| People participate in public awareness activities over LOP | 60,000 9 | 5,000 2 | 10,000 4 | 75,000 15 |

“Biodiversity friendly” in the context of the present project consists of landscapes that meet the following criteria: (i) tree diversity ranging between 50-60%:50%-40% broad leaf: 50%-40% conifers; (ii) crown cover of 40 % or greater, (iii) understory (i.e., shrub cover) not greater than 10 – 20 % and (iv) cleared of snares.

Integrated planning and “mainstreaming environment including biodiversity” in China falls in the remit of the National Development and Reform Commission (NDRC) situated directly under the Chinese State Council with broad administrative and planning control over the Chinese economy. Provincial level DRC’s are part of provincial government and receive policy and technical guidance from upper level DRCs (i.e., national and city levels).  The submission and approval of provincial tiger habitat conservation plans to the DRC represents a critical step in the “mainstreaming” of these environmental considerations in sector plans.

“Biodiversity friendly”  in the context of the present project consists of landscapes that meet the following criteria: (i) tree diversity ranging between 50-60%:50%-40% broad leaf: conifers; (ii) crown cover 40 % or greater, (iii) understory (i.e., shrub cover) not greater than 10 – 20 % and (iv) cleared of snares.

There is no current baseline on number of snares nor a single, common methodology employed to remove snares.  The methodology, sampling area and baseline will be established in the first snare removal campaign implemented in project year 1.