Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

# PART I: Project Identification

| Project Title: | Developing and Implementing the National Framework on Access and Benefit Sharing of Genetic Resources and Associated Traditional Knowledge |  |  |
| --- | --- | --- | --- |
| Country(ies): | China | GEF Project ID: | 5533 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 5310 |
| Other Executing Partner(s): | Ministry of Environmental Protection | Submission Date: Resubmission Date: | August 13, 2013 August 29, 2013 |
| GEFP Focal Area (s): | Biodiversity | Project Duration (months): | 60 |
| Name of parent programme: | N/A | Agency Fee: | 421,440 |

- focal Area  strategy Framework

| ### Focal Area Objectives | Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Indicative Grant Amount ($) | Indicative co-financing ($) |
| --- | --- | --- | --- | --- | --- |
| BD-4: Build Capacity on Access to Genetic Resources and Benefit Sharing | Outcome 4.1: Legal and regulatory frameworks, and administrative procedures established that enable access to genetic resources and benefit sharing in accordance with the CBD provisions | Output 4.1. Access and benefit-sharing agreements (4) that recognize the core ABS principles of Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) including the fair and equitable sharing of benefits. | GEF TF | 4,226,210 | 21,036,000 |
| Project management cost |  |  | GEF TF | 210,000 | 1,200,000 |
| Total project costs |  |  |  | 4,436,210 | 22,236,000 |

B. Project framework

| # -Project Objective: To develop and implement China’s national framework on access to and benefit sharing (ABS) of genetic resources and associated traditional knowledge in accordance with provisions of the Convention on Biological Diversity (CBD) and the Nagoya Protocol (NP) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant type | Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative Grant Amount ($) | Indicative co-financing ($) |
| 1. Establish-ment of the National Regulatory and Institutional Framework on ABS | TA | - Nagoya Protocol ratified - National ABS regulatory framework established and operational at a national and provincial level in compliance with the Nagoya Protocol | 1.1 Nagoya Protocol approved by the State Council of China for ratification 1.2 National law and implementing regulations, including NP compliant PIC and community protocols, model contracts, codes of conduct, and certificates of compliance/origin on ABS developed with stakeholder participation in compliance with the Nagoya Protocol | GEF TF | 826,210 | 6,864,000 |
|  |  | - Implementation framework under the national ABS law fully operational | 1.3 ABS Framework implementation plans formulated and operational, including: (1) Implementation plan for access to and benefit sharing of genetic resources and derivatives for commercial purposes; (2) Implementation plan for access to and benefit sharing of traditional knowledge associated with genetic resources and derivatives used for commercial purposes including application of PIC and community protocol; and (3)Implementation plan for academic/non-commercial research protocol 1.4 Institutional framework including national (MEP, MoA, SFA, MOFCOM, SIPO, MOST, State Administration of Traditional Chinese Medicine, Ministry of Culture etc.) and provincial competent authorities and supporting measures, designation of checkpoints, procedures, standards and guidelines established in 5 provinces to enable implementation of the national ABS law at national and provincial levels. 1.5 A financing mechanism developed to channel and reinvest proceeds from ABS agreements towards the conservation of biological diversity and sustainable use of its components. |  |  |  |
| 2. ABS capacity building and awareness-raising | TA | - Capacities of national and provincial agencies to implement the National ABS framework improved by at least 20% as measured by UNDP’s ABS Capacity Development Scorecard. - Enhanced understanding of the ABS regime and the value of traditional knowledge associated with genetic and biological resources for improved policy making and on the ground implementation of biodiversity conservation, sustainable use and fair and equitable sharing of benefits among the stakeholders (Baseline is to be established during the PPG). | 2.1 Enhanced capacity and awareness of implementation of the national ABS regime at the national and provincial levels. This will include capacity building and awareness-raising of: (i) management institutions including MEP, SFA, MoA and MoFCOM, SIPO, MOST, State Administration of Traditional Chinese Medicine, Ministry of Culture at the national level and their subsidiary organisation at the provincial level targeting estimated 800 people for ABS framework implementation; (ii) Capacity building of research and development (R&D) activities by academic institutions and private sector partners (through co-financing) targeting estimated 120 individuals; (iii) local communities; and the media and general public targeting estimated 4,000 individuals. 2.2 Training programme and modules on bio-prospecting and research procedures developed and made available to national and provincial research institutions. 2.3 A platform for technology and resources sharing developed, including the ABS clearing-house established. | GEF TF | 900,000 | 4,466,000 |
| 3. Pilot demonstra-tions on ABS | TA | - National ABS framework under implementation through up to 6 pilots in 3- 5 provinces (to be selected from the potential 8 pilots during the PPG), achieving the following outcomes : (i) 3 leading agents for new drug production; (ii) at least 3 ABS agreements negotiated between users and providers of genetic resources/derivatives from potential pilots 1-3 (see table below) ; (iii) at least 3 ABS agreements negotiated for products already commercialized (see potential pilots 4-8 below) ; (iv) at least 4 PIC process with ILCs implemented in accordance with the PIC/community protocol supported under component 1; and (v) direct financial community benefits derived from utilisation of their local genetic resources and traditional knowledge. | 3.1 Improved documentation on genetic resources and associated traditional knowledge in Guizhou, Hunan and Yunnan, Guangxi, and/or Inner Mongolia Provinces. 3.2. ABS cases of pharmaceuticals, and cosmetics, industry demonstrated through the 4 pilots in Yunnan and Guizhou provinces. In these 4 pilots: 3 leading agents for new drugs will be discovered, and at least 4 new ABS agreements established with national and international companies including traditional knowledge associated with biological resources. The agreements will be negotiated between the users (companies), and providers (the government and communities) of the genetic resources and traditional knowledge. 3.3 Lessons and experiences in implementing local ABS regime are documented and disseminated for replication, based on the project’s replication plan. | GEF TF | 2,500,000 | 9,706,000 |
| Sub-total |  |  |  |  | 4,226,210 | 21,036,000 |
| Project management cost |  |  |  | GEF TF | 210,000 | 1,200,000 |
| Total project costs |  |  |  |  | 4,436,210 | 22,236,000 |

C.  Indicative  Co-financing for the project by source and by name, ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | Ministry of Environmental Protection | Grant | 15,136,000 |
| Local Government | Provincial Government of Yunnan, Guizhou, Hunan, Guangxi, Inner Mongolia | Grant | 7,100,000 |
| Total Co-financing |  |  | 22,236,000 |

# d.  GEF fund Requested by Agency (ies), FOCAL Area(s) and Country(ies)1

| GEF Agency | Type of Trust Funds | Focal Area | Country Name | In US$ |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Project amount (a) | Agency Fee (b) | Total c=a+b |
| UNDP | GEF TF | Biodiversity | China | 4,436,210 | 421,440 | 4,857,650 |
| Total GEF Resources: |  |  |  | 4,436,210 | 421,440 | 4,857,650 |

- Project preparation grant (ppg)

Amount Requested ($)	Agency Fee for PPG ($)

$150k for projects up to & including $6 million      		___130,000___________   12,350_____

- PPG  Amount requested by agency(ies), focal area(s) and country(ies) for MFA and/or MTF Project only

| Trust Fund | GEF Agency | Focal Area | Country Name | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| GEF | UNDP | Biodiversity | China | 130,000 | 12,350 | 142,350 |
| Total PPG Amount |  |  |  | 130,000 | 12,350 | 142,350 |

PArt ii:  project JustiFication

A. Project Overview

A.1. Project Description.

China is listed as one of the world’s 17 megadiverse countries, with 60% of all species occurring in just 1.5% of the world’s land area. China is home to some 10% of all plant species and 14 per cent of the Earth’s faunal assemblage. China has 34,984 known species of higher plants of which 50% are endemic species, ranking the third in the world, 6,445 vertebrate animal species, accounting for 13.7% of the world’s total and more than 10,000 fungi species, making up 14% of the global total. Some 11,000 species of plants and 2,800 species of fauna found in China have identified medicinal properties. China boasts a long agricultural history that spans a period of over 5,000 years. During the agricultural system development process, rich genetic diversity emerged through natural selection and artificial selection. At present, China preserves more than 400,000 varieties of crops and 576 identified breeds of livestock and poultry. China is one of the eight global centres of origin for crops, and harbours important agricultural crops such as rice and soybean, as well as serving as a key centre of origin of wild and cultivated fruit trees. Over 1,339 species of cultivated crops and 1,930 species of wild relatives occur in China, and the number of fruit tree species ranks top in the world. China is also a country with multiple ethnic minorities. The distribution of ethnic groups in varied geographic areas enables people to create diverse yet unique traditional knowledge in the process of conserving and sustainably using biodiversity. Such traditional knowledge includes: (i) biological resources of crops, livestock, poultry and fish breeds with unique characters; (ii) traditional medicine, processing techniques, prescriptions and therapies; (iii) traditional farming methods and production models that facilitate comprehensive and recycled utilization of biological resources; (iv) traditional culture, folklore and protocols in favour of biodiversity conservation and sustainable use; and (v) traditional biological products with geographic indications that promote local economic development. Problem: With rapid economic development and globalisation of economy, the globally significant genetic diversity of China is under increasing threat. Habitat loss and fragmentation due to urbanisation, infrastructure and farmland development, have been posing severe pressures on wild fauna and flora including the wild relatives of crops. Excessive exploitation and utilization of wild species for subsistence and commercial use has resulted in the decreased abundance of many medicinal plants and wild animals. In addition, traditional knowledge of local communities that is associated with genetic resources is disappearing rapidly, due to fast the change of traditional lifestyles. A large volume of traditional knowledge, such as of medicinal use of biological resources, farming methods and techniques and cultures closely related with nature and biodiversity, is being replaced by modern technology.

Long-term vision and barriers to achieving it:  The genetic resources in the country must generate tangible local and national economic benefits if they are to be safeguarded.  The benefits will be in the form of business, employment and capacity building opportunities, through the development of a national ABS framework and the discovery and development of new medicines or agrochemicals, thereby providing a rationale for the preservation of the biological resources that contain the genetic material. This will represent a paradigm shift from the situation described above, to one in which biodiversity-rich nations such as China are fully and equitably involved in this lucrative research process with the primary goal of promoting people-centric conservation and sustainable use. The long term vision is therefore to establish and operationalise a robust legal and institutional framework for implementing the national and provincial ABS regime in China, ensuring equitable distribution of benefits to the holders of the traditional knowledge as prescribed in the Nagoya Protocol (NP).  However, three barriers currently hamper the realisation of this vision.

| Barrier | Description |
| --- | --- |
| 1. Weak Enabling Framework and institutional set-up for ABS implementation | Although China is preparing to ratify the NP, development of the national legislation on ABS as well as the establishment of an institutional framework have been lagging behind. This is partially due to the enormous size of the country as well as the vast number of biological and genetic resources the country harbours. It was only in 2005 that the concept of benefit sharing was introduced through the Animal Husbandry Law. However, concrete and operational mechanisms are still insufficient and regulations on protection of traditional knowledge are non-existent. Even traditional Chinese medicine, which is widely regarded as a national treasure, does not receive adequate legal protection for its medical resources and traditional knowledge. In 2011, China promulgated the Intangible Cultural Heritage Law, however the legislation doesn’t include access to and benefit sharing of intangible cultural heritage and associated traditional knowledge. In terms of intellectual property rights protection, the Patent Law revised in 2008 has touched upon the issue in Article 5, which reads “inventions created on the genetic resources illegally acquired or utilised will not be granted a patent right”, and in Article 26 which reads “for inventions and creations made on genetic resources to apply patents, the applicant shall clarify the direct resources and origin of the genetic resources”. Yet, difficulties remain in enforcing these two articles due to lack of national legislation and management mechanisms for access and benefit sharing. Therefore, it is an urgent priority for China to develop legislative and administrative frameworks that specifically deal with genetic resources and associated traditional knowledge based on national conditions and in accordance with the CBD and the NP provisions. Such a regime will include concrete procedures to ensure an approval process for granting access to genetic resources, clear duties and obligations of competent authorities, and fair and transparent mechanisms for benefit sharing. |
| 2. Weak institutional capacity and awareness for ABS | Government institutions have limited capacity to develop and implement national and local ABS norms. Although the State Council has designated MEP to take the lead in establishing a multisectoral and participatory coordination mechanism on ABS, lack of relevant legislation and insufficient capacity makes it difficult to establish an effective forum. The operational capacities of the national competent agencies and their subsidiary departments need to be developed significantly to be able to operationalize the ABS framework, playing a role in various processes. Capacity for sound research and development activities by academic and private sector partners is also lacking. In addition, a major barrier to stakeholder capacity development is insufficient awareness on the issues of ABS. It is necessary to build up awareness within governmental agencies and competent authorities in charge, as well as other stakeholder groups, such as local residents and communities that hold genetic resources and traditional knowledge, scientific staff and research institutions, businesses and the private sector, public and media through training and education. Lack of a platform for technology and resource sharing is also hampering awareness raising and application of the ABS concept in research and development and commercialisation activities. |
| 3. Limited capacity and know-how on bioprospecting and negotiation of viable ABS mechanisms | Chinese genetic resources and traditional knowledge have already contributed to an important number of commercialised products and local research companies continue to harness the economic potential of these resources and knowledge. Chinese government organizations need capacity to regulate the use of genetic resources for the development of pharmaceutical, agricultural, and food products. Similarly, bioprospecting companies and research organizations need capacity to interpret and implement ABS norms and regulations. ABS concepts and their implications on economic development are particularly complex. These issues are compounded by the intricacies of ABS agreement development and implementation in the context of multiple industries that use genetic resources and traditional knowledge (e.g., pharmaceutical, agriculture, crop-protection, cosmetics, food and manufacturing. In addition, local governments, institutions and research companies have limited scientific capacity to carry out bioprospecting, obtain PICs and facilitate equitable benefit sharing. Without model agreements and the realisation of actual benefits to the country and concerned communities, the ABS agenda for meeting the Aichi Target in the country will remain slow. The government also needs support to address bio-piracy cases and ensure that local communities receive their right share of benefits. In addition, the Chinese government is unaware of how genetic resources and traditional knowledge is been used by on-going bioprospecting activities seeking to identify lead compounds for new drugs and skin care products. |

Baseline: The Chinese Government has been making major efforts to safeguard its genetic biodiversity through implementation of the China National Biodiversity Conservation Strategy and Action Plan (CNBSAP) for 2011-2030, under the leadership of the MEP as the responsible agency for the Convention on Biological Diversity (CBD).  CNBSAP identifies priority actions and projects that are relevant to ABS, including:

- Action 8 on the survey and cataloguing of genetic resources and related traditional knowledge, which especially emphasizes surveying traditional knowledge, innovation and practices related to genetic resources in the ethnic minority-inhabited areas, establishing databases and undertaking studies and demonstration projects concerning benefit sharing.

- Action 21 on establishing a regime and mechanisms of conservation, access to, and benefit sharing of, genetic resources and related traditional knowledge, including activities to (a) develop policies of and regulations on access to and benefit sharing of genetic resources and related traditional knowledge; (b) improving regulations on disclosure of origins of genetic resources in patent applications, establishing procedures of mutually agreed terms and prior informed consent for access to and benefit sharing of genetic resources and related traditional knowledge, and ensuring that inspection of the import and export of biological resources will be operated effectively; and (c) establishing administration mechanisms, administrative agencies and technical supporting systems for access to and benefit sharing of genetic resources and improving related information exchange mechanisms.

The MEP is in the process of ratifying the Nagoya Protocol (NP) and is preparing the necessary conditions for implementation of NP.   MEP has so far budgeted US$ 3 million for developing the national ABS framework including drafting of the Regulation on Management of Access and Benefit Sharing of Genetic Resources (ABS Regulations) and for establishment of the National Clearing-house mechanisms for ABS. Planning activities are on-going for this investment.  ABS-related issues have been integrated in various official plans including China’s National Biodiversity Conservation Strategy and Action Plan. Training courses have been organised since 2010 targeting decision makers.

The MoA has in recent years enhanced its capacity for conservation of wild relatives of crops to safeguard the vast genetic diversity the country harbours.  It has conducted a systematic survey and prepared a catalogue of wild varieties of crops and has developed 116 in situ conservation sites.  It has also established a significant ex-situ collection of wild plants, preserving nearly 400,000 plant genetic resource specimens.  It is planning to invest an estimated US$8 million in establishment of over 500 germplasm conservation projects.

In terms of protecting the intellectual properties of the country, the State Council released The Outline of the National Intellectual Property Strategy, which incorporates “effective protection and rational utilization of genetic resources, traditional knowledge, and folklores” as a strategic goal. The identified strategic tasks include: (i) to strengthen systems on  protection, development and utilisation of genetic resources to prevent loss and irrational use; (ii) to balance the interests among protection, development and utilisation of genetic resources, and develop an appropriate regime on access to and benefit sharing of genetic resources; and to guarantee the right of prior informed consent enjoyed by providers of genetic resources; (iii) to establish a sound protection system for traditional knowledge; (iv) to support collation and passing down of traditional knowledge to promote its development; and (v) to improve coordination mechanism for management, protection and utilisation of intellectual property rights for traditional medicine, and strengthen protection, development and utilization of traditional technics.  The patent law was also revised in 2006 to include provisions for genetic resources.

The State Forestry Administration (SFA) is preparing the national report on forest genetic resources and has conducted a national survey and catalogue of oil-tea camellia genetic resources in 2012. The three agencies of industry and commerce, quality supervision, inspection and quarantine, and agriculture are working on the programme National Products of Geographic Indication. The programme aims to identify natural, agricultural or manufactures products that have a specific geographical origin and possess qualities, reputation or characteristics that are essentially attributable to that place of origin, and will link ABS regime with protection of national product of geographic indication.

The Ministry of Commerce (MOFCOM) is strengthening the regulation of the import and export trade of the traditional Chinese medicine extracts and derivatives to enhance monitoring of exports of genetic resources.  The Ministry of Science and Technology is funding scientific research institutions to undertake  a number of research activities pertaining to conservation and sustainable utilization of genetic resources and related traditional knowledge.

# The State Administration of Chinese Traditional Medicine is strengthening the management of the traditional Chinese medicine resources and related traditional knowledge, and promoting benefit sharing from the industry to the holders of traditional knowledge. In 2012, it conducted a national census of traditional medicinal resources.  With the results, it is in the process of establishing a traditional medicine database. It is planning to invest US$ 2 million establish a research centre specialising in traditional knowledge of the Chinese medicine. The programme on national intangible cultural heritage protection by the Ministry of Culture aims to promote conservation and benefit sharing of intangible traditional knowledge.

There are a number of baseline activities for the potential pilots that are identified under Component 3 in the table below.  The economic value of these baseline activities will be estimated during the PPG phase.

| Pilot | Baseline activities |
| --- | --- |
| 1. Traditional medicine (Guizhou) | A vast number of research activities are conducted in the traditional Chinese medicine industry. MEP researchers in collaboration with local research institutions have collected the prescriptions with the prior informed consent of the TK holders. A local researcher from the Chinese Academy of Sciences, and the pharmaceutical company Yibai Pharmaceutical Co. Ltd is identifying genetic resources for heart disease and empyrosis treatments. Legislation and administrative measures, in accordance with CBD and its NP, on traditional medicinal knowledge exploitation are being taken at the provincial level. Capacity training related to ABS is on offer to stakeholders and users of traditional medicinal knowledge and relevant genetic resources, e.g. healers, institutes, pharmaceutical companies, and competent local government units. |
| 2. Jinyinhua Lonicera spp.Honey-suckle (Inner Mongolia) | A major French cosmetic company is planning to develop new skin care products using the medical value of jinyinhua. The company is also willing to pilot ABS demonstration related to the particular genetic resources and associated traditional knowledge. Preparation is on-going for the R&D phase. Provincial level ABS regulations on Jinyinhua and associated traditional medicinal knowledge will be established. And ABS guidelines for cooperation mode of native institutes and multinational companies will be published, too. |
| 3. Pu Erh Tea (Yunnan) | Yunnan province government has issued a provincial level biodiversity conservation strategy and action plans (2012-2030) in April 2013. One of its aims is to develop an ABS system for conservation and utilisation of genetic resources and traditional knowledge, and improve international communication and cooperation on ABS issues of transboundary genetic resources and traditional knowledge in Asia. The Yunnan provincial government will continue in its research on valuable economic plants. Source of plants of Pu Erh tea and its wild relatives will be recorded, collected, and ex-situ cultivation will be promoted. Bioactive chemical constituents will be further researched and developed for new drugs or cosmetics. Provincial level regulations on genetic resources and associated traditional knowledge of Pu Erh tea will be developed. Education and communication activities and capacity training on ABS issues of Pu Erh tea will be served to farmers in the origin area, tea companies, tea institutes, and competent government units. |
| 4. Duyun Maojian Tea (Guizhou) | Research that has been conducted on the special hereditary features of the tea and associated local knowledge for tea preparation. Provincial level ABS regulations on Duyun Maojian tea will be developed. Some education and communication activities about ABS issues of the tea are to be completed at local community level on its area of origin. Capacity training on ABS will be served to farmers, local biotech companies, and tea institutes. |
| 5. Luohanguo Siraitia grosvenorii (Guangxi) | Work is ongoing to collect information on the industry chain of luohanguo, as well as development of local level ABS regulations to make the pilot viable. At the end of 2012, Guangxi province government launched the Implementation Programme of Establishment of Academy of Engineering for Luohanguo Industrialization. The academy consists of enterprise groups, institutes, universities, and farmers. It aims to transfer associated technology for commercial development of Luohanguo and relevant products, e.g., beverages, health care products and drugs. Furthermore, Guangxi province government is developing provincial level biodiversity strategy and actions plans, which are expected to be promulgated at the end of this year. Development of an ABS system on genetic resources and traditional knowledge is also one of the goals of the strategy and action plans. Various education and communication activities about ABS issues of Luohanguo will be carried out when the strategy and action plans enter into force. Various education and communication activities about ABS issues of luohanguo will be developed for local biotech companies, farmers and competent officials. |
| 6. Bajiao Huixiang – Star anise (Guangxi) | A number of local biotechnology companies are isolating and providing the shikimic acid and its derivatives form star anise to international companies for pharmaceutical and cosmetic use. Provincial level legislative or administrative measures will be taken to formulate the utilization and exploitation of Bajiao Huixiang and/or its derivatives. Capacity training on ABS will be served to local biotech and pharmaceutical companies and farmers. |
| 7. Xiangxi Black Pig (Hunan) | Genetic resources for commercialization are being identified and work has started for developing provincial level ABS regulations. ABS regulations on genetic resource of the pig are planning to be issued by the provincial government. Legal education and communication will be held for people who live in the origin area, local biotech companies, and competent officials. |
| 8. Baojing Golden Tea (Hunan) | Genetic resources for commercialization are being identified and work has started to develop provincial-level ABS regulations on Baojing Golden Tea. Legal education and communication activities will be held for people who live in the origin area, local biotech companies, and competent officials. |

Alternative Scenario: The project objective is to: develop and implement China’s national framework on access to and benefit sharing (ABS) of genetic resources and associated traditional knowledge, in accordance with the provisions of the  CBD  and its NP. The project will remove the aforementioned barriers and enable the country to ratify and implement the NP.

Component 1- Establishment of the National Regulatory and Institutional Framework on ABS

This component will support the establishment of the national ABS regulatory framework in compliance with the NP and provide support for timely ratification of the Protocol by the State Council through awareness raising and the provision of necessary information targeting the legislature.  The project will ensure that the national law, the Regulations on Management of Access and Benefit Sharing of Genetic Resources, will be developed with full stakeholder participation and  include clear implementing regulations and processes for, inter alia, prior informed consent (PIC) with clear and NP compliant community protocol, and certificates of compliance/origin on ABS provisions. The project will also support the establishment and operationalization of the implementation framework under the national ABS law at both national and provincial levels. An institutional framework for handling the ABS process will be defined with standard procedures and measures.  This framework will include a number of national competent authorities, for example MEP, MoA, SFA, SIPO, MOST, State Administration of Traditional Chinese Medicine and Ministry of Culture.  At the provincial level, at least 5 provinces will be targeted to implement and operationalize the national ABS law at local levels.  In order to support the process ABS framework implementation plans will be formulated and operationalized.  The plans include implementation plans for: (i) access to, and benefit sharing of, genetic resources and derivatives for commercial purposes including application of NP compliant PIC and community protocol; (ii) access to, and benefit sharing of, traditional knowledge associated with genetic resources and derivatives used for commercial purposes; and (iii) academic/non-commercial research protocol. A financing mechanism will be developed to channel and reinvest proceeds from ABS agreements towards the conservation of biological diversity and sustainable use of its components.

Component 2 – ABS Capacity Building and Awareness Raising

This component will focus on building the capacity of the national and provincial management authorities and stakeholders for implementing the NP and national ABS regime. Capacity improvement will be gauged using the UNDP ABS Capacity Scorecard which has been developed specifically for ABS projects. Emphasis will be placed upon monitoring of bio-prospecting projects, strengthening negotiation and facilitation capacity for the development of NP compliant agreements, tackling of bio-piracy cases, development of certificate of origin and PIC certificate.  Enhanced understanding of the ABS regime and the value of traditional knowledge associated with genetic and biological resources will also be supported. The target agencies will include: (i) management institutions including MEP, SFA, MoA and MoFCOM,  SIPO, MOST, State Administration of Traditional Chinese Medicine, Ministry of Culture at the national level and their subsidiary organisations at the provincial level targeting estimated 800 people for ABS framework implementation; (ii) Capacity building of research and development (R&D) activities by academic institutions and private sector partners (through co-financing) targeting an estimated 120 individuals; (iii) local communities; and the media and general public targeting estimated 4,000 individuals. Training programme and modules on bio-prospecting and research procedures will also be developed and made available to national and provincial research institutions.  Furthermore, the ABS clearing house mechanism will be established for facilitating exchange of information and data related to ABS, in support of the ABS framework implementation.

Component 3 – Pilot Demonstrations on ABS

This largest component will provide targeted support in piloting ABS agreements in a manner that is compliant with the NP.  The project will support up to 6 such pilots focusing on genetic resources and associated traditional knowledge in Guizhou, Hunan, Yunnan, Inner Mongolia and/or Guangxi Provinces.  So far, 8 possible pilots have been identified, as indicated in the table below, in the pharmaceutical, agriculture and food and beverage industries.   They include exploration of new drug development within the 5,000-year-old traditional Chinese medicine industry with its 20 billion Yuan gross turnover in Guizhou alone, aiming to identify potential leading compounds for empyrosis treatment drugs and for heart disease medicine from ingredients that are found in Guizhou province and associated traditional knowledge of the Dong people.  Other bioprospecting potentials within the Chinese traditional medicine will be further investigated during the PPG. Up to 6 pilots will be selected during the PPG phase.

The following table indicates 8 potential pilots so far identified to be further investigated during the PPG phase.

| Potential Pilot | Industry Sector | Organism (genetic resources) under Study | Providers of Genetic Resources | Users of Genetic Resources and Derivatives | Final Products / Existing use of genetic resources | Demonstration Feature |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Traditional medicine (Guizhou) | Pharmaceuti-cals and cosmetics | Huangshan Xintongshu plant | Local healers on Dong ethnic group | Institute e.g., Chinese Academy of Sciences, and pharmaceutical company e.g. Yibai Pharmaceutical Co. Ltd | Potential leading compounds for empyrosis treatment drug and heart disease. | Material collection agreement, TMK prospecting contract and PIC certificate; output transfer agreement on derivatives for commercialization, actual sharing of benefits |
| 2. Jinyinhua Lonicera spp. - Honeysuckle (Inner Mongolia) | Pharmaceuticals & Cosmetics | Flavons derived from Lonicera spp. plants | Chinese citizens represented by the National government | L'OREAL Paris | Flavons and/or its derivatives for skin care products – tissue culture, species, cultivation, extraction, and derivatives of Lonicera spp. plants | Establishment of NP compliant ABS agreement for R&D phase as well as the commercialisation phase. |
| 3. Pu Erh Tea (Yunnan) | Pharmaceuticals | Landrace of Camellia sinensis | Local people (Thai, Jinuo, Lahu and Hani people) | Companies e.g. Dayi Co. and Tiansili Co., and institutes e.g. Tsinghua University, Jilin University and Chinese Academy of Sciences | Landrace of tea; Potential leading compounds or new drugs for reducing blood glucose and lipid, removing NO and other oxidants, and resisting viruses and bacteria. | NP compliant ABS agreement on genetic resources and derivatives of Pu Erh tea tree, with provincial level regulations on genetic resources of Pu Erh tea. |
| 4. Duyun Maojian Tea (Guizhou) | Agriculture | Landrace of tea | Local people in Tuanshan, Shaojiao and Dacao villages | Companies e.g. Guizhou Dunyun Maojian Tea Group | New varieties of tea with genetic resource of Duyun Maojian tea with excellent features e.g. durable fragrance, delicious taste, bright tea water, as well as richness of essential amino acids and rare chemical elements. | Establishment of NP compliant ABS mechanism on special genetic resources of the local tea, with enactment of local level ABS regulations specifically on Baojing Golden Tea. |
| 5.Luohanguo Siraitia grosvenorii (Guangxi) | Food and beverage | Mogroside. This is is a chemical compound, found in certain plants, such as the fruit of the gourd vine luohanguo | Local people (Zhuang and Yao People). Local biotechnology companies | Multinational beverage and sweet companies. Chinese biotechnology companies that provide isolates of luohanguo. | Sweetener for beverages’ flavor; and developing new beverages – tissue culture, cultivation, extraction and derivatives isolation of mongroside | Establishment of NP compliant ABS agreements between local people and local biotechnology companies, as well as between local and international corporations. |
| 6. Bajiao Huixiang – Star anise (Guangxi) | Pharmaceuticals & Cosmetics | Shikimic acid Volatile oil derived from plants of genus Illicium | Chinese citizens represented by the National Government | International pharmaceuticals; Roche: perfume manufacturers; Guilin Layn Natural Ingredients Co. | Shikimic acid and its derivatives, and other anti-flu compounds of the plants of genus Illicium | Establishment of NP compliant ABS agreements between local people and local biotechnology companies, as well as between local and international corporations, with enactment of local level ABS regulations |
| 7. Xiangxi Black Pig (Hunan) | Agriculture | Local breeds of pig | Local people (Miao and Tujia people) | Biotechnology companies e.g. Niujiaoshan Eco-farming Corp. Ltd | New breeds with certain genetic resources features, e.g. high reproductive capacity, resistance to crude feed, high yield of fresh meat and good taste. | Establishment of NP compliant ABS agreements between local people and local biotechnology companies, with enactment of local level ABS regulations |
| 8. Baojing Golden Tea (Hunan) | Agriculture | Landrace of tea | Local people | Biotechnology companies e.g. Hunan Xiangfeng Tea Co. Ltd., and institutes e.g. Hunan Provincial Tea Institute | New tea varieties with certain genetic resources features, e.g. stronger resistance, earlier sprouting, higher production yield, higher amino acid content, and lower phenol ammonia ratio. | Establishment of NP compliant ABS agreements between local people and local biotechnology companies, with enactment of local level ABS regulations |

The project aims to facilitate discovery of 3 leading agents for new drug production, and negotiate at least 3 ABS agreements between national and international companies, which will be negotiated between the companies and the government and/or communities in accordance with the National ABS framework. The project will pilot at least 4 PIC process with ILCs implemented in accordance with the planned PIC/community protocol, and facilitate realisation of direct financial community benefits derived from utilisation of their local genetic resources and traditional knowledge. The project will provide a range of support measures including capacity building of communities and relevant local government units; provision of technical assistance for negotiation and legal drafting; and consolidation of the TK registry.  Improved documentation on genetic resources and associated traditional knowledge in the target areas is also supported. Successful experience and best practices derived from local ABS framework development will be used to inform national ABS framework development. Lessons and experiences derived from local ABS framework development and implementation efforts will be documented and disseminated for replication, based on the project replication strategy and plan to be produced.

| Current Baseline | Alternative | Global Biodiversity benefits |
| --- | --- | --- |
| - Although the government plans to develop the national ABS framework, insufficient technical expertise and experiences will hinder the progress. Harmonisation of the existing laws which touch upon some ABS elements alone will take many years. The MEP will have difficulties driving the ABS agenda for China, coordinating various line ministries and other stakeholders in absence of the project. - R&D activities for use of genetic resources for new medical, cosmetic and other products will continue. However, without GEF financing, the R&D and commercialisation processes will not be NP compliant, without PIC process, MAT practices and mechanism for equitable benefit sharing arrangements. Ad-hoc agreements may be developed however without clear standards and no monitoring mechanisms for implementation of such agreements. - Many more products will be produced using China’s genetic resources and traditional knowledge in absence of the national and local ABS framework, with enormous cost to the country and people, missing the opportunities for ABS to meaningfully contribute to biodiversity conservation. - Local populations will continue to be unaware of the significance of the genetic resources they utilize and associated traditional knowledge. This will perpetuate exploitation of resources by outsiders without accruing any benefits to the custodian of the resources and holders of the traditional knowledge. | - Necessary framework and capacity will be emplaced for operationalising ABS regimes at the national and local levels, including ABS legislation, institutional arrangements and processes. This will make the ABS regime a viable tool for achieving biodiversity conservation goals of the country as stipulated in the NBSAP. - Various regulations and guidelines under sector laws that have relevance to ABS will be harmonized under the national and local ABS framework, with streamlined process for handling the ABS issues. Awareness and capacity of relevant agencies will be increased and better inter-agency coordination will be achieved. - NP compliant ABS agreements will be developed through the pilots at different stage of product development – material collection, R&D, commercialization. Implementation of the agreements will also be demonstrated. This will provide replicable good examples for wider application in the country. - Pilots will also provide opportunities for local communities to increase income through benefit sharing, contributing to improvement of local livelihoods. - More private sector enterprises will be aware of the ABS issue and willing to formulate benefit sharing agreements and participate in biodiversity conservation actions. | - Promotion of CBD and Nagoya Protocol implementation worldwide. - Conservation and sustainable management of China’s outstanding genetic and biological diversity. - Safeguarding of China’s genetic resources and milliard of traditional knowledge of China for the benefits of future generation of the world and as global heritage. - Facilitation of sustainable and the most cost-effective use of biological resources, ensuring that the benefits will accrue to the nation and its people; thus further incentivising conservation of globally significant biodiversity. - Demonstration of ABS framework establishment and operationalization, contributing to the global knowledge and experience. |

Innovativeness, sustainability and scale-up potential: China with its long history of civilisation and vast territory has a wealth of traditional culture and knowledge that has made use of a large number of genetic resources of wild fauna and flora as well as the cultivated crops and livestock.  However, the concept of fair and equitable benefit sharing is new to many of the genetic resource providers and users.  There is, therefore, tremendous potential for the ABS agreements piloted in the project and trial products that are produced to be scaled up under provincial and national programmes after the ratification of the NP.  Many of the project outputs, such as regulations including NP compliant PIC and community protocols, model contracts, codes of conduct, and certificates of compliance/origin on ABS developed with stakeholder participation in compliance with the Nagoya Protocol, will provide tools for replication activities. The project will develop a replication plan to incorporate concrete mechanisms for replication.  The plan will include a clear strategy, methodology, and target for replication. The project will systematically document experiences from different components, in particular from the pilot activities, and codify lessons and disseminate widely.   The project is sustainable as it focuses on establishing the systemic and institutional capacity of the government, which also makes the successful replication highly likely.  In addition to the legal framework, the government’s institutional arrangements and a financing mechanism for ABS will be examined in the project to create a firm foundation for sustaining capacity built by the project.

# A.2  Stakeholders. Identify key stakeholders (including civil society organizations, indigenous people, gender groups, and others as relevant) and describe how they will be engaged in project preparation:

The following stakeholders have been identified. The stakeholder involvement plan will be developed during the PPG.

| Stakeholders | Relevant roles in the project |
| --- | --- |
| Ministry of Environmental Protection (MEP) | Through its Foreign Economic Corporation Office (FECO), MEP is the national executing agency for this project providing a national project director and ensuring quality and timely results monitoring and reporting of the project. MEP is the overall National Competent Authority for implementation of the ABS regime, and is also responsible for reporting entity for the Convention of the Biological Diversity (CBD). It also coordinates implementation of the National Biodiversity Strategy and Framework (NBSAP) as well as the China Biodiversity Partnerships and Framework (CBPF). |
| UNDP | At the request of the Government, UNDP will serve as the GEF Implementing Agency (IA) for the project. In this role, UNDP will ensure project execution on time, on scope and within budget and draw on technical services provided by its regional offices and headquarter to provide technical quality assurance. The project assurance and support functions will be provided by the UNDP China Country Office as well as UNDP Asia-Pacific Regional Centre which houses technical advisors for these projects. |
| Ministry of Agriculture (MoA) | National competent authority, responsible for the examination and approval of collection, import and export of agricultural wild plant, validation of new varieties of plants, regulation production, operation, imports and exports of crop seeds, grass seeds, and fungus seeds, examination and approval for import and export of aquatic seedlings and genetic resources of livestock and poultry. It is a key technical ministry for enacting of the Regulations on the Management of Access and Benefit Sharing of Genetic Resources and eestablishing National Clearing-house mechanisms with MEP. |
| Ministry of Finance | GEF Operational Focal Point. Coordination and implementation of GEF projects. |
| ## Ministry of Culture | National competent authority, responsible for promoting public cultural service, guiding the cultural development at a grass-roots level, and for protecting “non-material (or intangible)” cultural heritage including traditional knowledge. The declaration, examination and approval and protection intangible cultural heritage are being carried out by The Ministry according to the 2011 non-material cultural heritage protection law. It is also responsible for evaluation of the application of intangible cultural heritages for national recognition. |
| State Council | Responsible for the approving legislation including the Regulations on the Management of Access and Benefit Sharing of Genetic Resources. |
| ## State Intellectual Property Office (SIPO) | National competent authority, responsible for It is responsible for patent work and comprehensively coordination of the foreign related affairs in the field of intellectual property. It is also responsible for ensuring the implementation of the article regarding source disclosure requirement in the Law of Intellectual Property Rights and the audit of the patent. A potential check point at the national level. Key entity for promotion and implementation of the Regulations on the Management of Access and Benefit Sharing of Genetic Resources, as well as provisions relating to disclosure of origin in the patent law. |
| State Forestry Administration | National competent authority, responsible for the examination and approval of forest genetic resources, seed, seedlings, terrestrial wild animals or animal products for import and export approval, capture, specimen collection, domestication and trade of wildlife under special state protection, the examination and approval of new varieties of plants etc. Key technical ministry for Regulations on the Management of Access and Benefit Sharing of Genetic Resources enactment. |
| Ministry of Commerce (MOFCOM) | National competent authority responsible for formulating the strategies, guidelines and policies of developing domestic and foreign trade and international economic cooperation. It is also responsible for regulating import and export commodities and technologies. |
| State Administration of Traditional Chinese Medicine | National competent authority and a bureau under the jurisdiction of Ministry of Health, responsible for regulation of the Chinese medicine industry. It is also responsible for promoting development of the science of Traditional Chinese Medicine and Pharmacology (TCMP) as well as safeguarding associated traditional knowledge. It organizes resources census of the Chinese medicine, promote protection, and development and rational utilisation of the resources of the Chinese medicine and contributes to protection of intangible cultural heritage of traditional Chinese medicine. |
| ## General Administration of Quality Supervision, Inspection and Quarantine (AQSIQ) | National competent authority and one of the potential check point at national level. Responsible for inspection of import/export biological resources. AQSIQ is expected to play a key role in ensuring sound inspection of entry and exit biological resources. |
| Ministry of Science and Technology (MOST) | National competent authority and responsible for ensuring scientific and technology development. It is responsible supervision of scientific researches relevant to genetic resources. |
| National People’s Congress - Committee of Environment and Resource Protection | of, and Legislative Affairs Office of the State Council will provide guidance and advice regarding ABS laws and regulations and play a leading role in promoting ABS legislation. |
| National People’s Congress - Committee of Environment and Resource Protection | Legislative Affairs Office of the State Council is a key entity for providing guidance to enactment of the ABS laws and regulations and play a leading role in promoting ABS legislation. |
| Local Governments | Provincial, prefectural and county governments, through subsidiary agencies of the national competent authorities, will play an important role in establishing and implementing local ABS regime, as regulators and administrators. |
| Local communities | Providers of genetic resources and holders of traditional knowledge associated with the resources. Local communities of selected counties and townships will directly participate in ABS regime demonstration and benefit sharing practices as a key stakeholder under component 3. Many of the local communities which are expected to be involved in pilots are ethnic minority communities. These include the Dong people who live mostly in the mountainous areas in the eastern Guizhou, western Hunan, and northern Guangxi provinces in China. They are known for their unique cultural and musical traditions and Dong traditional medicine. Many of the other potential pilots are likely to also involve ethnic minorities, such as Thai, Jinuo, Lahu and Hani in Yunnan Province who possess Pu Erh Tea and associated TK, Zhuang and Yao people in Guangxi Autonomous Region hold Luohanguo. During the PPG, a thorough local level socioeconomic assessment and consultation will be conducted to obtain the consent of the ethnic groups to participate in the project pilots. This is noted in the Environmental and Social Prescreening for the PIF, and will be implemented during the PPG. Full environmental and Social Screening will also be conducted during the PPG phase. |
| Research institutions | Institutions mandated to undertake survey and collection of biological resources (e.g. Institute of Botany and Institute of Zoology under Chinese Academy of Sciences; biology schools in colleges and universities; research academies of agriculture, forestry, environmental sciences, and medical sciences; local research institutions, etc.) will participate in project activities as needed and provide technical support to ABS regime implementation. For instance, taxonomists can provide technical support to survey and identify genetic resources and to the settlement of benefit sharing issues in relation to species that are not endemic and distributed across national boundaries. |
| Private Sector | Businesses and enterprises in bio-prospecting, bio-technology and bio-industries are key stakeholders to the project, in establishing the ABS regime and in implementing the pilot component in particular. Private sectors include: (i) biotechnology companies that culture tissues, extract and isolate derivatives to provide genetic products, e.g. Dayi Group; (ii) users of the genetic resources and derivatives such as pharmaceutical, cosmetic, agrochemical and manufacturing industries, e.g. the French company L'OREAL Paris; (iii) manufacturing and retail sectors for traditional Chinese medicine and agricultural products, such as Guizhou Yibai Co. Ltd. and Yunnan Baiyao Group. |
| NGO and Civil Society | NGOs and civil society working on relevant issues with communities and institution are potential stakeholders. They could participate in public awareness raising and training activities targeting communities. In addition, through close cooperation with local communities, they may serve as agents and voice of local communities and assist them to gain more reasonable benefits from commercialisation of their genetic resources. ICIMOD will be an important partner for the project given its ABS regional programme. |

# A.3  Risk. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable):

# The following risks have been identified.  The risk table will be reviewed and updated during the PPG.

| ## Risks | ## Rating | ## Preventive Measures |
| --- | --- | --- |
| Legislative reform in China is a complicated and time-consuming process with cumbersome procedures. A delay may put the success of the project at risk. | High | The project will be designed so that the national level legislation delay will not delay the pilot and other components. A general guiding structure and principles of the legislation will be developed during the PPG phase, and the drafting of the legislation will be completed at the on-set of the project, drawing from best practices of other countries in their legislation, institutional setup, procedural development and other concrete measures in accordance with the requirement of the Nagoya Protocol. This is to accelerate the full development of the ABS legislation and associated institutional arrangements during the implementation phase. In addition, the project will support development of local ABS regulations within the autonomous legal and legislative framework in selected provinces and ethnic minority-inhabited regions which have certain autonomy, to facilitate pilot implementation. |
| Some national and international partners may prove to be uncommitted to work under the new ABS framework | Medium | A thorough situation analysis will be conducted during the PPG to mitigate this risk. Under the new Patent Law of China, information on sources of genetic resources is required for patent application. The project will support development of robust national and local laws and regulations on management of ABS, ensuring their compatibility with other existing laws which may conflict with the new ABS law. The project will also support capacity development of various institutions in order to ensure strict enforcement of the new laws to avoid any problems arising during the actual biodiscovery and product development processes. The project will further sensitise both providers and users of genetic resources including international and national companies about the new law and the procedures put in place for ABS. |
| Commercial confidentiality restrictions may limit information sharing on development process | Medium | During the PPG and implementation phase, the project will conduct extensive consultation and advocacy campaigns targeting commercial stakeholders to create awareness and political will to take up the proposed ABS regulatory framework. The MEP with support from the project will conduct seminars targeting legislators to advocate for their support to the new ABS regulatory framework. |

# A.4  Coordination. Outline the coordination with other relevant GEF financed and other initiatives:

The proposed project will fully coordinate with the on-going GEF-UNDP China Biodiversity Partnership and Framework for Action (CBPF) Project executed by MEP, and create co-benefits and synergies through data and information sharing. CBPF is designed to enhance CBD implementation in China in which access to and benefit sharing of genetic resources and traditional knowledge pertinent to biodiversity is treated as an integral and crucial component. The project will also provide technical support where appropriate to other existing and emerging GEF financed projects in China, for possible pilots of ABS at the local level as a means for realising the benefits from conservation of biodiversity by the communities and local authorities. Coordination and collaboration between projects can avoid duplication and improve cost effectiveness of the projects. As appropriate, the project will adopt measures such as hiring shared experts, introducing external outputs, and conducting joint research to enhance coordination and collaboration among different initiatives.

The proposed project will also coordinate with other ABS related projects nationally and internationally.  These include ICIMOD’s ABS Programme, a regional programme launched in 2004 with 13 countries including China.  The thrust of the programme has been to raise awareness on ABS with reference to the various marginalised segments of society in the Eastern Himalayan region. The programme has conducted a series of awareness raising activities targeting policy makers, civil society groups, local communities and media, through regional, provincial, and local level workshops.  A regional ABS framework has also been drafted, which will provide an overarching framework for development of the national and provincial legislation. ICIMOD’s emphasis on assessing the status of gendered knowledge on the medical plant will be particularly useful for the pilot in this project. The programme has also initiated a process of developing policy-based research through a set of consultations and field assessments of traditional knowledge and customary arrangements in their pilot project sites in collaboration with its partners. These policy-based research documents are expected to influence the long-term implementation of ABS regimes at the national level, through the creation of an empirical foundation for the rights of marginalised communities to genetic resources and associated traditional knowledge. Several Chinese institutions including the Chinese Academy of Sciences (CAS) and Kunming Institute of Botany are collaborating partners for the programme.  During the PPG phase, details for further collaboration will be explored based on close examination of the ICIMOD programme achievements and future plans.

Description of the consistency of the project with:

B.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSAs, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.

The proposed project is fully in line with the country’s national strategies and plans. The project is in high conformity with China’s policies and strategic goals and its components are highly relevant to priority domains and actions for the next five years clarified by the Chinese Government, revealing its close linkage with sectoral plans and programs of the government. Implementation of this project is expected to receive strong support from the Chinese Government, associated competent authorities, and local governments, which will contribute to its success and maximize its impacts in China

The Government has integrated biodiversity conservation, its sustainable use and access to and benefit-sharing of genetic resources and associated traditional knowledge into key national strategic plans, planning and programmes. In October 2011, the National People’s Congress (NPC) reviewed and adopted The Outline of the Twelfth Five-Year Plan for National Economic and Social Development of People’s Republic of China (the “Outline”, 2011 – 2015). Chapter 25 of the Outline is on Promoting Ecological Conservation and Restoration reiterates the need for conserving biodiversity, improving species resources conservation and management, and effectively preventing genetic resources from loss and bio-piracy.

In December 2011, the State Council issued the National Twelfth Five-Year Plan for Environmental Protection in which biodiversity conservation is identified as an outstanding environmental problem that needs to be effectively addressed. The plan also requires the continuous implementation of CNBSAP, enhanced efforts to develop germplasm banks and gene pools for key areas and sectors, strengthened supervision and management of genetic resources (species) import and export, and establishment of regime on access to and benefit sharing of genetic resources.

The project directly implements the State Council adopted China National Biodiversity Conservation Strategy and Action Plan (CNBSAP) for 2011 – 2030. The CNBSAP defines the basic principles as “conservation first”, “sustainable use”, “public participation”, and “benefit sharing” and reiterates the need to “ensure benefit sharing of genetic resources and associated traditional knowledge” which is one of the 8 strategic tasks. It includes: (i) to draw on advanced international experience and carry out pilot demonstrations; (ii) to strengthen studies on valuation of biodiversity and systems for management of biological and genetic resources; (iii) to rescue and pass on associated traditional knowledge by improving its protection system; and (iv) to explore the establishment of a regime for access to, and benefit sharing of, genetic resources and associated traditional knowledge and coordinate the interests among protectors, developers and users of genetic resources and associated traditional knowledge to ensure that the interests of all stakeholders will be protected.

# B.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities:

# The project addresses the GEF 5 BD4 Focal Area objective – Build capacity on access to genetic resources and benefit sharing, contributing directly towards Outcome 4.1 Legal and regulatory frameworks, and administrative procedures established that enable access to genetic resources and benefit sharing in accordance with the CBD provisions and Output 4.1 Access and benefit-sharing agreements (number) that recognize the core ABS principles of Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) including the fair and equitable sharing of benefits.  The project will establish the national legal and regulatory framework for ABS, build capacity for its implementation through a range of training, awareness and supportive information management and guidance outputs, and demonstrate best practice ABS processes recognizing the principles of Prior Informed Consent (PIC) and Mutually Agreed Terms (MAT) including the fair and equitable sharing of benefits.  The project will also directly implement Aichi Target 16 to operationalize the NP by 2015 and ensure consistence with national legislation.

B.3 The GEF Agency’s comparative advantage for implementing this project:

UNDP has been supporting natural resource management, biodiversity and ecosystem management in China for over three decades.  UNDP implemented/is implementing a number of GEF supported projects that are complementary to this project.  Of particular relevance is the Priority Institutional Strengthening and Capacity Development to Implement the China Biodiversity Partnerships and Framework for Action, which aims to operationalise the CBPF.  The United Nations Development Assistance Framework (UNDAF) for 2011 to 2015 provides the framework for the UN-China partnership over the coming five years, coinciding with the period of China’s 12th Five Year Plan. One of the three priority areas, or UNDAF Outcomes, is Outcome 1: Government and other stakeholders ensure environmental sustainability, address climate change, and promote a green, low carbon economy. This project will contribute to the achievement of this outcome, in particular directly contributing to Output 1.1. Policies and regulations are strengthened to create a green economy; Output 1.2. Policy and implementation mechanisms to manage natural resources are strengthened, with special attention to poor and vulnerable groups. Corresponding to the UNDAF, the UNDP Country Programme (2011 to 2015) seeks to conserve biodiversity and build ecosystem resilience, which is the fundamental building block of the ecosystems’ provisioning, regulating and support services that are essential for China’s social and economic development.  The UNDP Country Office will assign an experienced biodiversity conservation programme manager within the Energy and Environment Team, guided by the head of the team and supported by additional staff, an administrative assistant, and the UNDP finance office.  The UNDP Regional Technical Adviser based in Bangkok and the Senior Technical Adviser on ABS based in Panama will provide technical support to the CO for implementation, monitoring and evaluation of the project.

part iii: approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S):

| Name | Position | Ministry | Date (MM/DD/YYYY) |
| --- | --- | --- | --- |
| Jiandi Ye GEF Operational Focal Point | Director: International Financial institution Division III, International Department | Ministry of Finance | August 12, 2013 |

B. GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date | Project Contact Person | Telephone | Email Address |
| Adriana Dinu, UNDP-GEF Officer-in-Charge and Deputy Executive Coordinator |  | August 29, 2013 | Midori Paxton, Regional Technical Advisor – EBD, UNDP | +66-818787510 | midori.paxton@ undp.org |

It is intended that private sector co-financing will be mobilsied during the PPG phase

On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the GEF Project Grant amount requested.

Part II should not be longer than 5 pages.