request for

Project Type: Full-sized project

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Connect: Mainstreaming biodiversity into the heart of government decision making |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Global | GEF Project ID: | 5730 |
| GEF Agency(ies): | UNEP | GEF Agency Project ID: | 01268 |
| Other Executing Partner(s): | UNEP-WCMC | Submission Date: | 24/02/2016 |
| GEF Focal Area (s): | Biodiversity | Project Duration(Months) | 48 |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP | NA | Project Agency Fee ($): | 475,000 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
| BD-2 | Outcome 2.2: Measures to conserve and sustainably use biodiversity incorporated into policy and regulatory framework practices. | Polices and regulations governing sectoral activities that integrate biodiversity conservation at national level |  | 5,000,000 | 19,799,779 |
| Total project costs |  |  |  | 5,000,000 | 19,799,779 |

- Project Framework

| Project Objective: To ensure biodiversity is taken into account in decision making across government sectors by improving end-users’ access to and use of biodiversity information and embedding biodiversity information within national development decision making processes. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| 1. Mainstreaming entry points and response strategies | TA | Decision points or processes across government sectors are identified where biodiversity information can be influential, and response strategies devised. | 1.1 Political Economy Analysis and assessment of user needs for biodiversity information. 1.2 User groups at national level established to advise on, review and validate project outputs. 1.3 An innovative strategy to mainstream biodiversity information into identified decision processes is devised in each demonstration country. 1.4 Targeted interventions devised to neutralise or address identified barriers to biodiversity data sharing in each demonstration country. 1.5 Up-scaling approach devised and implemented including improved identification of entry points / response strategies achieved by sharing experiences, lessons, good practices, tools, etc. between countries and globally. |  | 980,000 | 1,365,000 |
| 2. Capacity to respond (using appropriate information) | TA | Technical stakeholders are more easily able to acquire and share relevant data, and use this to communicate effectively, for current and future information needs. | 2.1 Biodiversity information products and processes utilising innovative mechanisms and technologies are developed/strengthened and trialled to respond to the demands for biodiversity information identified under Outcome 1. 2.2 Public sector capacity to respond to future requests or opportunities for biodiversity information (including data standards, data management, technologies, reporting systems, etc.) is built/enhanced. 2.3 Establishment or formalisation of partnerships necessary for the acquisition, sharing and delivery of biodiversity information, and catalyzing the further development of national biodiversity monitoring networks. 2.4 Up-scaling approach devised to replicate and transfer these innovative mechanisms and technology between countries and globally. |  | 2,640,000 | 11,003,500 |
| 3. Embed/ integrate necessary information into national development systems | TA | Policy frameworks, including accounting and reporting systems across a range of sectors are incorporating biodiversity decisions | 3.1 Strategies and measures for integrating biodiversity information into decision-making recommended by national user boards, based on iterative review and assessment of results, are identified and implemented. 3.2 Up-scaling approach devised and implemented, including that capacity for embedding biodiversity information into national systems planning, and reporting processes is enhanced iteratively by sharing experiences, lessons, good practices, tools etc. between countries and globally. |  | 855,000 | 6,601,279 |
| 4. Project monitoring and evaluation | TA | Project implementation based on results based management and application of project lessons learned in future operations facilitated. | 4.1 Project monitoring system operating providing systematic information on progress in meeting project outcome and output targets. 4.2 Midterm and final evaluation conducted. |  | 225,000 | 305,000 |  |
| Subtotal |  |  |  |  | 4,700,000 | 19,274,779 |
| Project Management |  |  |  |  | 300,000 | 525,000 |
| Total project costs |  |  |  |  | 5,000,000 | 19,799,779 |

sources of confirmed Co-financing for the project by source and by name ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | National Environment Management Authority (Uganda) | Cash | 100,000 |
| National Government | National Environment Management Authority (Uganda) | In-kind | 1,000,000 |
| National Government | Ministry of Environment, Science, Technology and Innovation (Ghana) | Cash | 600,000 |
| National Government | Ministry of Environment, Science, Technology and Innovation (Ghana) | In-kind | 750,000 |
| National Government | Ministry of Land, Environment and Rural Development (Mozambique) | In-kind | 350,000 |
| Multilateral Agency | Convention on Biological Diversity | Cash | 200,000 |
| Multilateral Agency | Convention on Biological Diversity | In-kind | 600,000 |
| National Government | Instituto de Investigação Científica Tropical (IICT) | Cash | 104,500 |
| National Government | Instituto de Investigação Científica Tropical (IICT) | In-kind | 22,000 |
| International Organization | International Institute for Environment and Development | Cash | 2,369,279 |
| International Organization | BioPAMA | In-kind | 5,200,000 |
| International Organization | BirdLife International | In-kind | 500,000 |
| International Organization | Global Biodiversity Information Facility | In-kind | 3,250,000 |
| International Organization | GEO BON | Cash | 1,150,000 |
| International Organization | GEO BON | In-kind | 1,300,000 |
| International Organization | WCMC | Cash | 1,154,000 |
| International Organization | WCMC | In-kind | 1,150,000 |
| Total Co-financing |  |  | 19,799,779 |

- trust fund Resources Requested by agency, Focal Area  and country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b) | Total c=a+b |
| UNEP | GEFTF | Biodiversity | Global | 5,000,000 | 475,000 | 5,475,000 |
| Total Grant Resources |  |  |  | 5,000,000 | 475,000 | 5,475,000 |

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Co-financing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants | 380,000 | 782,000 | 1162,000 |
| ### National/Local Consultants | 0 | 0 | 0 |

- Does the project include a “non-grant” instrument?

No

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.

The original PIF outlined a number of the national plans and strategies in the project pilot countries to which the project would be aligned. Further details are provided under Section 3.6 of the Project Document. As stated in the PIF this project will improve the ability of governments and the international community to report progress against Aichi Target 2 and 19:

| CBD Aichi 2020 Targets which the project will contribute to | How the project will support the achievement of each target |
| --- | --- |
| Target 2 (By 2020, at the latest, biodiversity values have been integrated into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems) | Mainstreaming strategies and initiatives to remove data sharing barriers; Policy frameworks modified to “pull”/demand biodiversity information for development decisions |
| Target 19: By 2020, knowledge, the science base and technologies relating to biodiversity, its values, functioning, status and trends, and the consequences of its loss, are improved, widely shared and transferred, and applied. | Technical staff in governments and supportive institutions have improved ability to develop and deliver information products that support decision making with respect to biodiversity) |

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities.

No change

A.3 The GEF Agency’s comparative advantage:

No change

A.4. The baseline project and the problem that it seeks to address:

- The baseline situation and the barriers described in the PIF were maintained. In summary the baseline is that biodiversity information is not being used sufficiently within government decision making to halt biodiversity loss. As described in the  Section 2.7 of the Project Document, there are many initiatives at the international, regional, and national level that are trying to tackle the issue that this project will learn lessons from, build upon and leverage in order to sustainably embed biodiversity information within national level decision making.

The design of the Full Project Proposal is in line with the content of the original PIF document and the original project components remain unvaried. However, outcomes and outputs under each technical component have been extensively reviewed to avoid potential overlaps and increase effectiveness and measurability. Particularly, changes made from the PIF include revision and refinement of Output 1.1 title.

In preparing a detailed version of the results framework for the full Project Document, it was observed that Outcome 1 and Output 1.1 had been expressed in similar language that did not fully reflect the difference between a project outcome and a project output:
Outcome 1 original text: "Decision points or processes across government sectors are identified where biodiversity information can be influential, and response strategies devised"
Output 1.1 original text: "Multi-sectoral development decisions and/or processes identified that have an unmet demand for / potential to be influenced by relevant biodiversity information"
Output 1.1 has therefore been changed to: " Political Economy Analysis and assessment of user needs for biodiversity information."

This reflected more accurately the proposed focus of activity under Component 1 as described in  Project Document Section 3.4 Intervention logic.

A. 5. Incremental /Additional cost reasoning: describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

The principal presented in the PIF is maintained. Further details are provided in Section 3.7: Incremental cost reasoning of the Project document.

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks:

A more in depth risk analysis and corresponding mitigation options has been carried out and added since the PIF. Please refer to the table below and Section 3.5 in the Project Document. Assumptions and Risks related specifically to the achievement of the project Outcomes are also addressed in the Project Results Framework (see Annex A to this document).

| Risk | Impact | Likelihood | Mitigation measure | Ongoing measure(s) |
| --- | --- | --- | --- | --- |
| National and international partners in the project have insufficient resources to implement the project | High Lack of or loss of resources e.g. through budget changes, anticipated funding not realised etc. | Low | Qualitative capacity assessment carried out at during the PPG phase. | Full capacity assessment carried out at inception stage and then periodically through the project lifespan Seeking out additional resources / leveraged co-financing through the project |
| Political, economic and security situation becomes unstable | High National crises pull decision making attention away from longer-term development planning processes; priorities in government change rapidly due to external events (e.g. currency fluctuations, trade agreements, natural disasters) | Low | Selected demonstration countries have sufficient level of stability and good prospects as executing partners within the project timeframe (see Selection criteria Section 3.1) | Periodic monitoring through open communications will enable the national User Board to recognise and respond to the dynamism of real-world decision making and priority-setting and be responsible to emerging development decision points. If a national crisis or other significant external event occurs, the User Board will be tasked with considering how such events can be responded to through the project approach. For example, what is the relevance of biodiversity and ecosystem services to the crisis (e.g. forest intactness / flood risk), and are there any new entry points for biodiversity information that present themselves? |
| The inception phase of the project fails to provide sufficient background knowledge of the situation within the demonstration countries in a timely fashion | High Adequate steerage is not given to the project implementation plan Implementation plan delayed with knock-on effects for project outputs | Low | Demonstration country selection criteria (see Section 3.1) designed to address this risk Strong stakeholder engagement through the National User Boards Activities such as Political Economy Analysis and Capacity assessments to be conducted (see Workplan; Appendix 4) | Strong continued stakeholder engagement and partnerships with other projects Project Steering Committee to provide guidance and oversight to maintain momentum towards planned mid-term and final milestones and targets |
| There is tension between mainstreaming and other biodiversity efforts at national level | Medium Mainstreaming can be a long-term process; governments might redirect efforts to issues where they feel immediate gains can be made (e.g. Protected Areas) | Low / Medium | Project identifies key stakeholders during the PPG phase and inception phase in order to build relationships and synergies with ongoing biodiversity efforts in each demonstration country | Project communications emphasise value of mainstreaming to biodiversity over the long-term; emphasise that it doesn’t replace other biodiversity management approaches |
| Individual project partner priorities are redirected away from the project | Medium Specific project activities are not delivered satisfactorily | Low | International partners are identified that are already committed to similar work, can’t shift priorities in project lifespan | Regular project meetings and other communications with project partners to ensure priorities remain aligned |
| Development decision makers/ other end-users are inaccessible to the project | High Incorrect entry points identified Tools/information products are not used in decision making processes | Low | Key audience groups such as environment, development and finance ministries are engaging with during the PPG phase and inception phase to secure buy-in from project outset | The national User Board to be co-chaired by an influential development leader / decision maker from the target audience |
| That the wrong entry points are identified in Component 1 (see workplan Appendix 4) | High Component 2 of the project fails to improve decision making outcomes | Low / Medium | User group is tasked with ensuring the strategy – should be a high-level and influential group with sufficient knowledge of the national context to reach the best-possible outcome | Strategies developed within Component 1 are heavily vetted by national and international partners to ensure the project entry points and intervention strategies are designed for best possible impact (before proceeding to Component 2 at national level) |
| The products and services re-packaged through the Connect project are not used by end users | High There is insufficient use of the tools to have an impact or influence on decision making outcomes | Low | Peer review, vetting of project specifications by National User Boards and ITAUG | Tracking the products and services built into Component 3 (see Appendix 3: Results Framework) |
| Identified national User Board members are not representative and/or ineffective | Medium The advice of the User Boards is irrelevant and leads to the production of ineffective tools | Low | Members of the User Board will be selected to ensure that they are senior enough in their governments to be influential | Continued project monitoring to ensure that the national User Boards and project partners are being as influential as possible The nominated User Board would be jointly chaired by the CBD focal point with another eminent person from the development sector (e.g. head of national planning agency). |
|  |  |  | Project partners are involved in the vetting of members of the national User Boards to ensure that this is an effective body with sufficient seniority and respect to lead the national work effectively. | Advice of peers through the regional groups and ITAUG |
| The required data or information is unavailable and/or cannot be accessed | High There are problems of accessibility of data, including time lags Data quality issues, i.e. resolution not good enough | Low | Qualitative feasibility study during PPG phase to ensure that the demonstration countries there are existing available data (see Annex 2) Clear commitment from data provider project partners to respond to end user feedback on their data and information (quality, availability, validity, salience, etc.) | Share feedback with data providers on quality and usefulness of the data and if necessary, additional analysis brought to bear to translate the information bringing it to a useful state Leveraging co-financing if opportunities to improve data or information are identified through the project (e.g. from bilateral/other donors at national level already investing in those sectors, private sector partners, etc.) Close partnering with credible, peer reviewed data sources and partners |
| Entrenched power relationships may not be amenable to influence e.g. corruption, collusion between actors, other factors outside project influence | Medium Identified entry points are inaccessible – tools/information products are relevant but still not integrated into decision making processes | Low | Carry out a political economy analysis in the inception stage of the project, within each demonstration country | Continued project monitoring and communication between national project teams and the global Project Management Unit |
| Turnover / attrition of institutional knowledge | Medium That capacity cannot be built to successfully access entry points beyond project lifespan | Low | Project designed to have multiple participants at national level in order to spread risk of increased staff turnover | Sub-regional and global sharing of lessons learned Long term partnerships in place with MOUs ensuring continued collaboration |

A.7. Coordination with other relevant GEF financed initiatives

Coordination has advanced during preparation phase and will be further developed during implementation to ensure that synergies are maximized, redundancy avoided and lessons learned find continued application. For the status at present refer to section 2.7 in the Project Document.

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation.

- An extensive landscape of international, regional and national stakeholders and initiatives are focused on providing and using biodiversity information. During the Project preparation phase, those major stakeholders and their potential roles in the project were identified (please refer to the Table below). Extensive engagement with these stakeholders was then undertaken in order to correctly identify the key issues and barriers they are facing and making sure that the objectives of this project address these. Stakeholders that we engaged with during the PPG phase included both international and national data providers and end-users in order to gain a complete picture of the landscape.

- During the project preparation phase the project team has involved a professional stakeholder engagement company because stakeholder engagement underpins this project. This company will continue to be engaged during the full project execution.  The project has been designed with an initial inception phase which focuses on in-depth engagement with stakeholders, understanding their specific needs, and planning the following phases of the project to specifically address these needs. However, it will be an iterative process throughout the lifetime of the project rather than a one-off exercise, thereby ensuring that the project outputs are salient, credible and legitimate. The engagement of these stakeholders across geographical scales will contribute to effective implementation of project activities  and dissemination of project results (see Project document Section 3.10).  A more detailed stakeholder analysis for each of the demonstration countries is included in Annex 2 of the Project document.

Key stakeholders and their involvement in the Connect project

| Stakeholders | Type of involvement |
| --- | --- |
| Implementing and Executing Partners |  |
| United Nations Environment Programme (UNEP) UNEP-World Conservation Monitoring Centre (UNEP-WCMC) Secretariat to the Convention on Biological Diversity (sCBD) International Institute for Environment and Development (IIED) Ministry of Environment, Science, Technology and Innovation (MESTI), Ghana Ministry of Land, Environment and Rural Development (MITADER), Mozambique National Environment Management Authority (NEMA), Uganda | - Lead/ co-lead respective project work packages (See Section 4) - Provide project oversight through the Project Steering Committee (see Section 4) - Responsibility for project deliverables (see Appendix 6) |
| Global organisations and initiatives |  |
| United Nations Development Programme (UNDP) Global Biodiversity Information Facility (GBIF) Group on Earth Observations Biodiversity Observation Network (GEO BON) BirdLife International World Wide Fund for Nature (WWF) International Union for Conservation of Nature (IUCN) Organisation for Economic Co-operation and Development (OECD) Biodiversity Indicator Partnership (BIP) members | - Provide opportunities for collaboration with respective ongoing projects (see Section 2.6 and 2.7) - Potential data providers / information product providers to address decision points identified in Component 1 (see Section 3) - Learning from the approach and outcomes of the project and seeking to replicate the approach in improving their information products (see Upscaling Strategy Section 3.1) |
| Regional organisations and initiatives |  |
| Regional Centre for Mapping of Resources for Development Central African Forest Commission (COMIFAC) Intergovernmental Authority on Development (IGAD) Conservation Alliance South African Development Community (SADC) East African Community (EAC) Economic Community of West African States (ECOWAS) African Union Association of Southeast Asian Nations (ASEAN) South Asian Association for Regional Cooperation (SAARC) Organisation of American States (OAS) Caribbean Community (CARICOM) | - Provide opportunities for collaboration with respective ongoing projects (see Section 2.6 and 2.7) - Potential data providers / information product providers to address decision points identified in Component 1 (see Section 3) - Learn from and adopt similar practices for mainstreaming as those showcased by the project within their respective groups of countries - Provide a platform for regional dissemination of project results |
| Demonstration country organisations and initiatives (see also Annex 2) |  |
| National government bodies/departments (e.g. Ministry of Environment, Forestry Commission, National Development Planning Commission, Agriculture, National Statistics Offices) Private companies Academic/research institutes Non-governmental Organisations Civil Society Organisations Women’s Groups and Organisations | - Undertaking/Target of project interventions - Members of National User Boards - Recipients of capacity building - Potential data providers / information product providers to address decision points identified in Component 1 (see Section 3) - Ensure the equitable representation of diverse value systems within the project interventions |
| Other national organisations and initiatives |  |
| National Geomatics Centre (China) National Commission of Biodiversity Use and Knowledge (CONABIO; Mexico) National Institute of Biodiversity (INBio; Costa Rica) Instituto Humboldt (Colombia) South African National Biodiversity Institute (SANBI; South Africa) | - Potential data providers / information product providers to address decision points identified in Component 1 (see Section 3) - Share best practice and lessons learned for mainstreaming biodiversity information to the demonstration countries - Learn from the approach and outcomes of the project and seek to replicate the approach in improving their information products - Learn from and adopt similar practices for mainstreaming as those showcased by the project |

The Connect project will work collaboratively at the national, regional and global level with those stakeholders identified during the PPG phase (see Project document Section 2.5). This will be followed up with a detailed stakeholder analysis during the project inception phase to ensure that the members of the national User Boards and the ITAUG are best placed to provide sound technical advice and oversight of the project activities and outputs.

The implementation plan for the project has been checked and validated at the PPG phase by the project key partners. This will be further elaborated and validated collaboratively during the lifespan of the project  in order to guarantee continued relevance of the project. Flexibility will be key to enable new stakeholders to be integrated into the project groups as deemed appropriate. The project communication plan will focus on maximizing stakeholder engagement within, and dissemination outside of, the focused project teams.

The Project Steering Committee (see Project document Section 4) will be responsible for ensuring the fair representation of a broad range of stakeholders within the International Technical Advisory Group (ITAUG) and national User Boards. Engaging these groups early on will allow for buy-in at the national level and the provision of sound advice at the global level.

There will be annual ‘all-hands’ project meetings to bring together project stakeholders across levels, immediately following the annual face-to-face ITAUG meetings (see Project document Appendix 4). These meetings will take place in each of the demonstration countries in turn, encouraging the sharing of project experiences between participants, as well as fostering discussions around lessons learned and future implementation strategies. Regular project meetings and communication via online tools such as Skype and Gotomeeting will be held in the interim period.

Through engagement with the CBD, IPBES and other MEA Secretariats, national level MEA focal points will be kept informed of project progress and outputs. The upscaling strategy (see Project document Section 3.1) will include the availability of funds for project replication within countries outside of the demonstration countries, providing further benefits to a broader range of stakeholders than identified during the inception phase. Existing regional assemblies such as GBIF regional groups, the African Leadership Forum (NBSAP 2.0: Mainstreaming Biodiversity and Development project – see Project document Section 2.6), IGAD, SADC etc. will be engaged with in order to build upon these networks for project dissemination.

The national User Boards will meet face-to-face at four national workshops per demonstration country. Bilateral engagement, both face-to-face and virtually will be essential for building and maintaining the required project momentum to enable the successful realization of project objectives. One of the major barriers to data and information sharing is issues around data mis-use and mis-trust between data providers and end users (see Project document Section 2.3). Fostering an atmosphere whereby stakeholders feel comfortable in the sharing of their data for common gains will be vital. The project will therefore draw on the collective experience of key project partners such as IIED and Prospex to build the necessary relationships between national level stakeholders. End-users will be called upon to review and validate the tools and information products produced, and the data providers will be required to maintain flexibility in the application of those tools. This will be critical to the success of the demonstration country interventions and the subsequent provision of robust lessons to be upscaled.

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF):

- The Connect project poses few environmental or social risks. The project focuses on the mobilisation of currently available biodiversity information and re-packaging of existing tools and knowledge products to feed into government decision making processes. As government decision making processes are generally long term activities, with impacts seen over a longer time period than the project lifetime, the need for environmental and social safeguards is limited. The proposed project will ensure environmental social safeguards are provided, and that that social and economic issues are adequately addressed. National User Board and ITAUG recruitment processes will include the engagement of experts in social and economic issues.

- The project will fully be in compliance with all applicable domestic and international law.

- Women play a large enabling role in the management of natural resources in Africa. The distinctive roles, responsibilities and knowledge of men and women are highly differentiated and therefore it is critical to understand how these variables affect processes of ecological change, viable livelihoods and the prospects for sustainable development. Many descriptions of gender roles are simplified and do not capture the fact that the gendered division of labor is constantly renegotiated in response to new situations and economic necessity. Women have also taken on new tasks and responsibilities, and more rights exist at least on paper than at any time before. It’s difficult to capture here various possible scenarios or contexts that gender relations can take place; we try to handle gender issues throughout the Project document.

- The project is designed and implemented in such a way that both women and men (a) are able to participate fully and equally; (b) receive comparable social and economic benefits; and (c) do not suffer disproportionate adverse effects during the development process. Any interventions as a sub-national level will utilize good practices in participation and use a ‘gender-transformative’ approach.  The inequitable distribution of rights, resources and access to social goods – as well as some cultural rules and norms – result in highly asymmetrical relationships of power between men and women. This constrains the ability of many women to take action on biodiversity. However, poor and marginalized men often contend with similar constraints vis-à-vis other relationships of power. Therefore, more recent approaches to ‘empowering’ both women and men to challenge and change deeply rooted inequalities; such approaches have been advanced in the sphere of climate change adaptation, less so in biodiversity management but inspiration can be drawn from their lessons. Such efforts are characterized as ‘gender-transformative activities’, which strive to examine, question and change rigid gender norms and imbalances in power relationships in order to increase people’s resilience. Gender transformative activities encourage critical awareness among men and women of gender roles and norms; promote the position of women; challenge the distribution of resources and allocation of duties between men and women; and/or address power relationships between women and others in the community, such as service providers or traditional leaders. Gender specific indicators have been included as part of the Connect project results framework (see Appendix 3 to the Project Document).

- The project team will ensure to be flexible in its activities, strategies, and objectives so that both women and men can influence, participate in, and benefit from the project. We will take a gender-targeted approach to ensure that:

- When targeting women for certain activities as decision makers and/or participants, the project team will ensure men are sensitised on the rationale behind.

- Context-based gender analysis is conducted. On the understanding that gender issues vary from context to context and can change over time.

Gender mainstreaming

- Efforts to promote gender equality will be integrated in all aspects of project activities and management, through conscious integration of gender-based groups in project activities. The project will fully comply with UNEP gender guidelines, which are incorporated into the various parts of the project design, project framework activities, the budget, and the monitoring framework. IP-related and gender disaggregated data will be collected to monitor project impacts following GEF and UNEP guidelines on Social and Environmental Safeguards, which include specific guidelines for the involvement of Indigenous Peoples.

- Applicable items and response to UNEP checklist for environmental and social issues

| Description |  |
| --- | --- |
| Environmental impacts |  |
| The Connect project would not cause any losses to precious ecology, ecological, and economic functions due to construction of infrastructure, as it does not include components on infrastructure development. |
| Ecosystems related to the Connect project are envisaged to be somewhat degraded. However, it is an objective of the project to strengthen management of these ecosystems to support their sustainability. |
| The Connect project is not likely to cause any impairment of ecological opportunities within the demonstration landscape or at the national level. |
| The Connect project does not involve issues that would directly or indirectly cause increase in peak and flood flows, including from temporary or permanent wastewaters. |
| The Connect project will not cause air, soil, or water pollution, soil erosion and siltation, increase of waste production, hazardous waste production, use pesticides, or cause excessive noise or traffic. |
| The Connect project will not cause a threat to local ecosystems due to invasive species |
| The Connect project will not cause Greenhouse Gas Emissions except for those of normal transportation and use of facilities, in these circumstances emissions will be minimised. |
| At all stages, as applicable, The Connect project will encourage the use of environmentally friendly technologies at the local levels with government, organization, and community stakeholders |

Social impacts

The Connect project will, on all of its implementation, respect internationally proclaimed human rights including dignity, cultural property, and uniqueness and rights of indigenous people.

The Connect project is unlikely to cause social problems or conflicts related to land tenure and access to resources

In its design, The Connect project incorporates measures to allow affected stakeholders’ information and consultation. At the demonstration site the project will be heavy on stakeholder engagement.

The Connect project does not contain implementation aspects that would cause change to legal beneficial uses of land or resources.

The Connect project will not include technologies that would cause land use modification that may change present social and economic activities.

The Connect project will not cause dislocation or involuntary resettlement of local communities, or cause uncontrolled in-migration to possibly overload social infrastructure.

The Connect project will include transparency measures to avoid corruption and promote adequate and equitable use of project financial and otherwise resources.

- The Connect project will take into full consideration the need for gender equality in all project workings, including the process of assessing the implications for women and men of planned action in all areas and at all levels. The project will ensure that the concerns and experiences of stakeholder women and men are an integral dimension of the design, implementation, monitoring, and evaluation of project resulting policies and programs, with the purpose of ultimately achieving gender equality. The project will assess the implications for women and men of any planned action, including legislation, policies or programs, in any area and at all levels. As indicated the project will ensure gender is incorporated in the necessary operations, monitoring and reporting, such as: Training, Workshops, Meetings and Monitoring.

Elements of gender mainstreaming to be incorporated into the Connect project implementation

| Criteria | The Connect project planned aspects during implementation |
| --- | --- |
| Awareness | Steps will be put into place to increase the awareness of gender mainstreaming issues and benefits in all project measures, and in particular those entailing action planning and implementation and policy strategies. |
| Participation | Processes will be put into place to encourage and ensure meaningful participation of women in decision-making processes and policy development, at the project demonstration levels. |
| Assessment | During the project inception period, initial assessments will be conducted to identify gender mainstreaming needs and opportunities, and to establish a baseline with regards to gender issues and initial conditions, particularly for implementation and action planning |
| Strategy | In line with the initial assessments, the project will develop strategies and ensure that its action plans are gender-sensitive, promote gender equality, and engage both women and men in interventions and the necessary decision-making processes |

- The Connect project will address within its implementation strategy the following actions to ensure gender considerations:

- Ensure that sufficient staff time and financial resources are made available for gender mainstreaming

- Use gender-sensitive language

- Implement participatory methods that include women and women’s organizations

- Include gender mainstreaming in monitoring and reporting

- Ensure gender equality in human resources elements of strategy development and implementation

- Ensure that the organizations involved in strategy development have a gender strategy or policy

- Require that staff involved in strategy development report on gender aspects of their work

B.3. Explain how cost-effectiveness is reflected in the project design:

- The Connect project is built on collaborative partnerships, sharing of project outputs and alignment with ongoing current work at both the national and international level. During the PPG phase every effort was made to identify, contact and collaborate with all relevant projects, both within the demonstration countries (see Box 1 below and  Annex 2 of the project document) and at the regional and international level. These efforts will continue throughout the project implementation via continued monitoring by project teams and horizon-scanning by the ITAUG (see Appendix 8 of the Project document).

Box 1. The Clearing House Mechanism and BIOFUND projects in Mozambique The Mozambique Ministry of Land, Environment and Rural Development have received funding to develop a national Clearing House Mechanism (CHM), as required under the CBD. However, the information required is currently scattered in different organisations, including universities. During consultations during the PPG phase, Ministry staff highlighted that they are looking to integrate biodiversity into their green economy work yet require the necessary information to do so. BIOFUND Mozambique aims to support the conservation of aquatic and terrestrial biodiversity and the sustainable use of natural resources, including the consolidation of the national system of conservation areas. During consultations in the PPG phase, BIOFUND reiterated that the main barrier to information sharing in Mozambique is the fact that information is inconsistently collected and stored. BIOFUND have recently funded projects to create a national biodiversity database and have produced habitat maps primarily to inform biodiversity offset schemes. It appears that these initiatives are not well linked. For example BIOFUND were not aware of the Ministry’s attempts to develop a CHM portal and vice versa. The Connect project could usefully build on the work of these initiatives and to provide quick wins in terms of connecting these data providers and end users.

- This is a global project, designed to provide lessons on a global scale through an upscaling strategy (see Project document, Section 3.1). However, in order to produce relevant and useable lessons which can be replicated across the globe, the project will work deeply in three demonstration countries. This number was chosen to allow the necessary focus for project activities that may not be achieved if funds were spread further across four or more demonstration countries; however focusing on only one or two countries may not allow for the necessary variation between demonstrations. The demonstration selection criteria (Project document Section 3.1 and Section 3.5) was developed in order to ensure cost effectiveness and mitigate against risks. Indeed, point seven in the criteria states “Cost-effectiveness: building on existing work in the countries so to maximise project impact and ensure that the GEF investment brings added value”.

- During the PPG phase, a ‘twinning’ approach was considered. This would entail the pairing of a ‘leading’ nation with an ‘advancing’ nation across three distinct geographic regions. However, this strategy was rejected in order to provide the best value for project funds and to allow for dynamic sharing of project experiences between peers in the Sub Saharan region. In order to still allow for a regional element, the project will engage stakeholders through the identification of existing regional groups and the ITAUG (see Project Document Section 3.1).

- The Connect project is not facilitating the collection of new data, but maximizing the potential of existing data and information available at the national level (see Box 2 and Project document Annex 2). The identification, mobilization and re-packaging of existing data and information into a useable and accessible format for end-users will maximize the potential of these data and build on the significant efforts already made.

Box 2. National Biodiversity Data Bank, Uganda The Ugandan National Biodiversity Databank (NBDB) is currently housed at Makerere University in Kampala. The database holds mostly species occurrence data with some additional associated information such as breeding status. Some funding has been identified to support the development of a national biodiversity database within National Environment Management Authority (NEMA). This could potentially be used to support the NBDB at the university with a duplicate, automatically up-dated database sitting in NEMA. National NGO Nature Uganda and the NBDB have a data sharing agreement in place where Nature Uganda pledges not to set up their own database but rather use the NBDB. This illustrates the desire for the long-term sustainability of the NBDB within Uganda. However there is currently a disconnect between the data providers in Uganda (such as the NBDB, Nature Uganda, etc.) and government end users (NEMA, Uganda Bureau of Statistics (UBoS)). This is where the Connect project could add significant value to ongoing initiatives at the national level.

- Linked to this, existing biodiversity groups or forums within each demonstration have been identified (Box 3, Project document Annex 2). Re-convening and/or reinvigorating these networks, as opposed to the formulation of new groups, will lead to cost effectiveness in the coordination of the national User Boards. Integrating new members into an existing group will streamline the initial trust building phase necessary to create meaningful networks of individuals.

Box 3. National Biodiversity Committee, Ghana Previous efforts have been made in Ghana to bring together the various biodiversity data and information that is currently ‘scattered’ across different government ministries, organizations and individuals. A National Biodiversity Committee (NBC) was convened by a consultant from the Centre for African Wetlands for this purpose, but has been dormant for some time. Discussions with partners in Ghana uncovered a need for the Connect project to reconvene the NBC to address issues of data management and provision to serve current national requirements.

- The forging of long term associations between data providers and end users is the cornerstone of the Connect project. These partnerships will be built to last beyond the project lifespan and serve as real world examples of how identified barriers can be removed to provide mutual benefits and sustain the cost effectiveness of the project.

C.  describe the budgeted m &e plan:

- The Project will follow UNEP standard monitoring, reporting and evaluation processes and procedures. Substantive and financial project reporting requirements are summarized in Appendix 6 of the Project Document. Reporting requirements and templates are an integral part of the UNEP legal instrument to be signed by WCMC- UNEP and DEPI. A costed project M&E Plan is presented in Appendix 6.  Costs mentioned in this tool are fully integrated in the project budget, presented in Appendix 1 of the Project Document.

- The project M&E plan is consistent with GEF Monitoring and Evaluation policy. The Project Results Framework presented in Appendix 4 includes SMART indicators for each expected outcome as well as mid-term and end-of-project targets. These indicators along with the key deliverables and benchmarks included in Appendix 6 will be the main tools for assessing project implementation progress and whether project results are being achieved. The means of verification and the costs associated with obtaining the information to track the indicators are also summarized in Appendix 6. Other M&E related costs are also presented in the Costed M&E Plan and are fully integrated in the overall project budget.

- UNEP will be responsible for managing the mid-term review/evaluation and the terminal evaluation. The Project Manager and partners will participate actively in the process. The purpose of the Mid-Term Review (MTR) or Mid-Term Evaluation (MTE) is to provide an independent assessment of project performance at mid-term, to analyze whether the project is on track, what problems and challenges the project is encountering, and which corrective actions are required so that the project can achieve its intended outcomes by project completion in the most efficient and sustainable way. In addition, it will verify information gathered through the GEF tracking tools .

- The GEF tracking tools are attached as Appendix 13. These will be updated at mid-term and at the end of the project and will be made available to the GEF Secretariat along with the project PIR report. The mid-term review/evaluation and terminal evaluations will verify the information of the tracking tool.

- The project Steering Committee will participate in the MTR or MTE and develop a management response to the evaluation recommendations along with an implementation plan. It is the responsibility of the UNEP Task Manager to monitor whether the agreed recommendations are being implemented. An MTR is managed by the UNEP Task Manager. An MTE is managed by the Evaluation Office (EO) of UNEP. The EO will determine whether an MTE is required or an MTR is sufficient.

- An independent terminal evaluation (TE) will take place at the end of project implementation. The EO will be responsible for the TE and liaise with the UNEP/DEPI Task Manager throughout the process. The TE will provide an independent assessment of project performance (in terms of relevance, effectiveness and efficiency), and determine the likelihood of impact and sustainability. It will have two primary purposes:

- to provide evidence of results to meet accountability requirements, and

-      to promote learning, feedback, and knowledge sharing through results and lessons learned among UNEP      and executing partners.

- While a TE should review use of project funds against budget, it would be the role of a financial audit to assess probity (i.e. correctness, integrity etc.) of expenditure and transactions.

- The TE report will be sent to project stakeholders for comments. Formal comments on the report will be shared by the EO in an open and transparent manner. The project performance will be assessed against standard evaluation criteria using a six point rating scheme. The final determination of project ratings will be made by the EO when the report is finalised. The evaluation report will be publically disclosed and will be followed by a recommendation compliance process.

- The direct costs of reviews and evaluations will be charged against the project evaluation budget.

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- A.  Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s):  (Please attach the Operational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Fredua Agyeman | GEF Operational Focal Point | Ministry of Environment, Science technology and innovation, Ghana | 17 /06/ 2015 |
| Patrick Ocailap | Executive Director, NEMA, GEF Operational Focal Point | NEMA, Uganda | 27/07/2015 |
| Marilia Telma Antonio Manjate | GEF Operational Focal Point | Ministry of Land, Environment and Rural Development. Mozambique | 9/10/2015 |

- B. GEF agency(ies) certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| Brennan Vandyke, Director, GEF Coordination Office, UNEP |  | February 24, 2016 | Marieta Sakalian, UNEP Senior Programme Management /Liaison Officer (CGIAR/FAO), Biodiversity | +39 06570 55969 | Marieta.Sakalian@unep.org |

ANNEX A.  PROJECT RESULTS FRAMEWORK

| Project Objective | Objectively verifiable Indicators | Baseline | Mid-term target | End of project target | Means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| To ensure biodiversity is taken into account in decision making across government sectors by improving end-users’ access to and use of biodiversity information and embedding biodiversity information within national development decision making processes. | Number of new or existing information products used by end-users per demonstration country within their decision making processes; Number of cross-ministerial fora where gender is a discussion topic and where there is a gender balance among the participants. | Data providers are not developing biodiversity information products in a timely manner or in appropriate formats for end-users; End-users are not aware of how biodiversity information can be used to inform key development decision points or processes; | At least 1 x information product per demonstration country identified to address needs of end-users; At least one demonstration country has proposed a cross- Ministerial forum. | At least 1 x information product developed, implemented and used by end-users in each demonstration country; All three demonstration counties have proposed a cross- Ministerial forum and at least one demonstration country has established such a forum. | Project Management Unit monitoring against baseline, project reports and project files. Documented case studies in demonstration countries. | There are some existing biodiversity data and information products that could meet/be adapted to end-users requirements; If legitimate, credible, salient and relevant information products are made available to end users, they will utilise them within their decision-making; Demonstration countries maintain economic and political stability and remain committed; Partners (including governments) maintain relevant budget commitments; Project outputs relevant to non-demonstration countries who have resources/capacity to adopt findings. |
|  | Number of new collaborative agreements in place between data providers and end-users per demonstration country. | There is a disconnect and lack of collaboration between data providers and end-users. | Data providers and end-users are working together on information products that meet end-users’ needs. | At least 1 longer-term collaborative agreement between data providers and end-users per demonstration country: inc. MoUs, web services, APIs, etc. | Formal agreements in place. |  |
|  | Number of global/regional events at which project learning is disseminated. | There is limited global understanding about how biodiversity information fits into the mainstreaming equation. | 3 proof of oncepts designed using best-available expertise on biodiversity information and mainstreaming. | A tested and revised theory of change through practice and applied research. | A published theory of change and associated published paper on how biodiversity information fits into the mainstreaming equation. |  |

| Component 1. Mainstreaming entry points, and response strategies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME |  |  | Outputs | Objectively verifiable Indicators |  | Baseline |  | Mid-term target |  | End of project target |  | Means of verification |  | Assumptions |  |  |
| Decision points or processes across government sectors are identified where biodiversity information can be influential, and response strategies devised. |  |  |  | Number of in-country mainstreaming initiatives involving data sharing. |  | Data providers are not aware of/not able to access entry points to influence decision making; No baseline information exists on end-users perception of salient, credible and legitimate biodiversity information; Strategies to influence decision making with biodiversity information in the 3 demonstration cases (if they exist) are not fully effective. |  | 1 response strategy in each demonstration country developed and validated by male and female stakeholders at the national level. |  | Implementation activity from each response strategy per demonstration country underway and yielding initial results and lessons. |  | Documented case studies; Response strategy documents. |  | The correct entry points can be identified during the inception phase; Basic project theory of change is a sound starting point; The relevant stakeholders can be identified in order to influence decision making processes. |  |  |
|  |  |  | Output 1.1 Political Economy Analysis and assessment of user needs for biodiversity information. | Number of sectors related to natural resource management participating in /responding to calls for information to inform these user needs assessments |  | Limited understanding of decision-making processes and user needs exists. |  | 1 PEA and assessment of user needs per demonstration country. |  | 1 PEA and assessment of user needs per demonstration country. |  |  |  | Project has sufficient access to all relevant stakeholders. |  |  |
|  |  |  | Output 1.2 User groups at national level which advise on review and validate project outputs. | Number of different sectors represented on User Board membership; User Board formed of a balance between males and females. |  | 0 User Boards prior to project implementation; There is limited interaction between different government sectors and between data providers and end-users. |  | User Boards established and operational in each demonstration country; National User Board in each demonstration country has a gender balanced membership. |  | User Boards remain operational in each demonstration country until end of project to validate final outputs; National User Board in each demonstration country has gender balanced membership throughout its life. |  | Reports, collaboration agreements. |  | User Board participants successfully selected; senior enough with appropriate influence and commitment and with appropriate balance of male and female members. |  |  |
|  |  |  | Output 1.3 An innovative strategy to mainstream biodiversity information into identified decision processes is devised in each demonstration country. | Number of untried or tested new activities to access entry points included in emerging strategies. |  | 0 prior to project implementation. |  | 3 x innovative country Strategies to access entry points developed and validated by peers. |  | 3 x innovative strategies to access entry points implemented and yielding lessons on how biodiversity information can be used by end-users. |  | Project Documents, Reports. |  | Sound proof-of-concept strategies can be developed through facilitation, peer review and ITAG validation. |  |  |
|  |  |  | Output 1.4 Targeted interventions devised to neutralise or address identified barriers to biodiversity data sharing in each demonstration country. | Number of countries that have undertaken analyses of barriers to sharing of biodiversity data and who have implemented actions to address. |  | In demonstration countries no barrier removal strategies have yet been devised and successfully implemented. |  | 1 national barrier removal strategy per demonstration country (total of 3) developed and peer reviewed by a gender balanced group. |  | 1 barrier removal strategy per demonstration country implemented (total of 3) including any gender-related barriers, lessons collected; 1x summary of common lessons learned in overcoming barriers biodiversity data sharing. |  | Project documents, reports. |  | Data sharing barriers will be common enough between countries / similar to those faced in other countries. |  |  |
|  |  |  | Output 1.5 Up-scaling approach devised and implemented including improved identification of entry points / response strategies achieved by sharing experiences, lessons, good practices, tools, etc. between countries and globally. | Proportion of co-authors for products within the upscaling approach who derive from other sectors |  | No upscaling approach currently exists; Limited peer reviewed literature on lessons learned has been produced by mainstreaming projects. |  | First Component of upscaling approach i.e. 1 x review of previous mainstreaming projects using information as a mechanism for change, made publically available; 1 x global upscaling approach devised and validated. |  | A tested and revised theory of change in the public domain, one of the proposed products of an upscaling approach; 1- 3 peer-reviewed research papers developed on use of biodiversity information in decision making processes, including a balance of male and female authors; Global lessons from this project adopted by dissemination through established global communities of practice e.g. BIP, SGA, NBSAPs Forum etc. |  | Reports of ITAG, Project documents; Use of project website. |  | Relevance of lessons from countries can be drawn to inform other countries; Motivation of project participants remains high throughout project. |  |  |
| Component 2. Capacity to respond (using appropriate information) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 2 |  | Outputs |  | Objectively verifiable indicators |  | Baseline |  | Mid-term target |  | End of Project targets |  | Means of verification |  | Assumptions |  |  |
| Technical stakeholders are more easily able to acquire and share relevant data, and use this to communicate effectively, for current and future information needs. |  |  |  | Positive shift in capacity and capability of male and female technical stakeholders as assessed by a capacity assessment tool at key points in project. |  | Data providers report limited ability to develop and deliver information products that support decision making. |  | Technical stakeholders including data providers understand what makes biodiversity data salient, credible and legitimate developed. . |  | Technical stakeholders including data providers regularly sharing data which is salient, credible and legitimate in response to stated information needs. |  | Follow-up survey on guidance use; Training reports / post-training survey; Capacity Assessment Tool; Stakeholder interviews. |  | Data providers are able to dedicate time amidst multiple demands and staff resourcing levels to training and enhancing their technical capacity. |  |  |
|  |  | Output 2.1 Biodiversity information products and processes utilising innovative mechanisms and technologies are developed/strengthened and trialled to respond to the demands for biodiversity information identified under Outcome 1. |  | Number of new information products developed and existing products strengthened |  | No integrated knowledge sharing system exists in any of the three demonstration countries; Global information products not deemed useful or used routinely at the national level. |  | At least one case per country identified where biodiversity information products and processes can be developed using innovative mechanisms and technologies |  | At least 1 x information product developed, implemented and used by end-users in each demonstration country. |  | Annual reports of partners; Progress reports. |  | That data exist and are available; There is scope to re-package information products; There are adequate technical skills at national-level. |  |  |
|  |  | Output 2.2 Public sector capacity to respond to future requests or opportunities for biodiversity information (including data standards, data management, technologies, reporting systems, etc.) is built/enhanced. |  | Number of technical staff applying good practice guidance for delivering biodiversity information to end-users. |  | Limited awareness by data providers of good practices to deliver biodiversity information and ability to apply them. |  | Training/guidance on enhancing technical capacity to acquire, share and communicate biodiversity data delivered to a balance of male and female participants. |  | Enhanced capacity demonstrated by tried and tested examples in each country of how innovative technologies and mechanisms have responded to national biodiversity data needs. |  | Training reports, follow-up survey; Project reports; User surveys. |  | Basic level of public sector capacity to build on; Sufficient continuity in operations during the project lifespan. |  |  |
|  |  | Output 2.3 Establishment or formalisation of partnerships necessary for the acquisition, sharing and delivery of biodiversity information, and catalyzing the further development of national biodiversity monitoring networks. |  | Number of partnerships linking data providers with end-users. |  | No or limited number of partnerships and/or existing partnerships ineffective. |  | At least 2 potential partnerships between data providers and end-users identified in each demonstration country. |  | Collaboration agreements in place, as above. |  | Collaboration agreements in place, as above. |  | Willingness of partners to collaborate; Capacity and resourcing of partners remains steady or increased during project lifespan. |  |  |
|  |  | Output 2.4 Up-scaling approach devised to replicate and transfer these innovative mechanisms and technology between countries and globally. |  | Number of views/ downloads of materials generated via project by information providers/technical stakeholders through global biodiversity communities of practice and platforms for debate e.g. BIP, SGAN, NBSAPS Forum, CoPs, SBSTAs etc. |  | No upscaling approach currently exists; Limited peer reviewed literature on lessons learned has been produced by mainstreaming projects. |  | First element of upscaling approach i.e. 1 x review of previous mainstreaming projects using information as a mechanism for change, made publically available; 1 x global upscaling approach devised and validated. |  | A tested and revised theory of change; in the public domain one of the proposed products of an upscaling approach; 1- 3 peer-reviewed research papers developed on use of biodiversity information in decision making processes, including a balance of male and female authors; Global lessons from this project adopted by disseminated through established global communities of practice e.g. BIP, SGA, NBSAPs Forum etc. |  | Reports of ITAG, Project documents; Use of project website. |  | Relevance of lessons from countries can be drawn to inform other countries; Motivation of project participants remains high throughout project. |  |  |
| Component 3. Embed/integrate necessary information into national development systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3 | Outputs |  |  |  | Objectively verifiable indicators |  | Baseline |  | Mid-term target |  | End of Project targets |  | Means of verification |  | Assumptions |
| Policy frameworks, including accounting and reporting systems across a range of sectors are incorporating biodiversity decisions |  |  |  |  | Number of verified case studies where policies, frameworks or regulations governing sectoral activities integrate biodiversity conservation considerations |  | End-users in other sectors not using biodiversity information effectively in development focused decision making; not demanding information about biodiversity. |  | At least 1 substantive development decision explicitly informed by biodiversity information per demonstration country. |  | At least one example per demonstration country where biodiversity considerations have been incorporated into policies, frameworks or regulations governing sectoral activities |  | Government, NGO and Private Sector annual reports; Documented case studies. |  | Partnerships and dialogue between different sectors and biodiversity interests will prove valuable and flourish; Policy/practice will change as a consequence of the dbeing established. |
|  | Output 3.1 Strategies and measures for integrating biodiversity information into decision-making recommended by national user boards, based on iterative review and assessment of results, are identified and implemented. |  |  |  | Number of strategies and measures for integrating biodiversity into decision-making recommended by national user boards identified and implemented. |  | Mainstreaming strategies are currently not identified or being implemented. |  | At least 1 user board recommendation adopted per demonstration country. |  | 1 user group recommendation adopted and implemented per demonstration country. |  | Project reports. |  | Recommendations can be sufficiently convincing to ensure longer-term financial allocations. |
|  | Output 3.2 Capacity of decision makers across government sectors to respond (supported by biodiversity knowledge products) is enhanced |  |  |  | Positive shift in capacity of decision makers as measured by a capacity assessment tool at specific times during project. |  | Capacity of decision makers to make decision informed by biodiversity considerations currently low. |  | At least 1 sector across the three demonstration countries show improved capacity to use biodiversity knowledge. |  | At least 2 sectors across the three demonstration countries show improved capacity to use biodiversity knowledge. |  | Capacity survey. Capacity Assessment Tool. |  | Attitude and motivation of decision makers amenable. |
|  | Output 3.3 Up-scaling approach devised and implemented, including that capacity for embedding biodiversity information into national systems planning, and reporting processes is enhanced iteratively by sharing experiences, lessons, good practices, tools etc. between countries and globally |  |  |  | Number of countries beyond the 3 demonstration countries who are accessing/downloading downloads of materials generated via project through global biodiversity communities of practice and platforms for debate e.g. BIP, SGAN, NBSAPS Forum, CoPs, SBSSTAs etc . |  | No global impact and sharing of lessons learned. |  | Experience in three demonstration countries of using information as a mechanism for change encapsulated ready to feed into upscaling approach. |  | Upscaling approach being tested out in countries across all regions. |  | Reports of ITAG, Project documents; Use of project website. |  | Relevance of lessons from countries can be drawn to inform other countries; Motivation of project participants remains high throughout project. |

ANNEX B.  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

Response to GEF Secretariat Review

| Items to consider at CEO endorsement/approval. (FSP) | Response |
| --- | --- |
| 6. Is (are) the baseline project(s), including problem(s) that the baseline project(s) seek/s to address, sufficiently described and based on sound data and assumptions? Yes. This project describes the current problems and the status of efforts well. At CEO endorsement narrow this down to the three countries. | The global baseline project is now described in more detail in the project document Section 2.6. Baseline analysis and gaps and in Appendix 3 Results Framework. The baseline project in the three demonstration countries is specifically described in Annexe 2 on Demonstration Country Information. The status quo, baseline and future scenarios that will be benefit from biodiversity data inclusion in decision-making processes in Ghana are described in pp14-17 section 2.3; for Mozambique on pp36-38 section 3.3; and for Uganda pp66-67 section 4.3. These sections describe the main sectors which would benefit from biodiversity data inclusion in their forward planning but which currently do not do so. This content was generated from visits and meetings with partner organisations and key players in all three countries. |
| 8. (a) Are global environmental/ adaptation benefits identified? (b) Is the description of the incremental/additional reasoning sound and appropriate? For now this is adequate. However once the three countries are identified in the design stage, please describe the global benefits more clearly for each circumstance and link the reduction of drivers of BD loss to the biodiversity context of each country and the measurable global environmental benefits that will ensure. | The global environmental benefits are now described in more detail in Section 3.1. Project rationale, policy conformity and expected global environmental benefits, beginning at p44. This describes how the national experiences gained through the three demonstration countries in embedding consideration of biodiversity related information in decisions made by sectors which could be acting counter to biodiversity conservation will be upscaled to both a sub-regional and national level. This is also described in section 3.9 Replication since acting on lessons learnt in national demonstrations and disseminating them regional and globally is a critical part of delivering global environmental benefits. The status quo, baseline and future scenarios sections in Annexe 2, which gives information on the three demonstration countries, describes the current drivers of biodiversity loss in the three countries. Pressures on current land use in the three demonstration countries originate from development sectors including oil and gas, agricultural transformation/expansion and intensification, mineral resource extraction; the presence of invasive alien species, the persistence of illegal wildlife trade and emerging climate change impacts. These are described in some detail in the sections for each country. Reducing the pressures on biodiversity caused by ill informed development decisions will contribute to national and global biodiversity goals. In sections 2.4,3.4 and 4.4. headed Intervention Strategy, details are provided about how the project demonstrates consistency with national and international efforts. This section shows how the delivery of project benefits at the national level link to both national and global efforts to reduce biodiversity loss. |
| 10. Is the role of public participation, including CSOs, and indigenous peoples where relevant, identified and explicit means for their engagement explained? At CEO endorsement describe in detail engagement with CSO at national level. | The Project Document describes in Section 2.5 Stakeholder mapping and analysis and in Section 3.10 Public awareness, communications and mainstreaming strategy the range of partners and their involvement in the project, and the approach to engaging and communicating with partner organizations at a global level. At national level a number of specific CSOs have been identified as potential data partners and potential facilitators of regional engagement; these are described in sections 2.2, 3.2 and 4.2 on the country nstitutional arrangements. For Ghana (see p13,14 and Table 4) the specific CSOs are Ghana Wildlife Society, A Rocha and Conservation Alliance; for Mozambique (see p34 Table 9) this would mainly be national offices of international NGOs and for Uganda (see p61 and Table 15) this would mainly be NatureUganda and the Uganda Biodiversity Information Facility, though as the information shows there is a rich assemblage of CSOs in the country. |
| 11. Does the project take into account potential major risks, including the consequences of climate change, and describes sufficient risk mitigation measures? (e.g., measures to enhance climate resilience) Full strategy should be evident in the CEO endorsement document | A more in depth risk analysis and corresponding mitigation options has been carried out and added since the PIF. Please refer to the table in Section A6 and Section 3.5 in the Project Document. Assumptions and Risks related specifically to the achievement of the project Outcomes are also addressed in the Project Results Framework (see Annex A to this document). |
| 12. Is the project consistent and properly coordinated with other related initiatives in the country or in the region? Once countries are selected, please amplify this in the CEO endorsement document | The Project has been designed to ensure coherence with national obligations under the Strategic Plan for Biodiversity and to directly support ongoing biodiversity conservation initiatives in the three demonstration countries. Section 3.6. of the Project Document – Consistency with national priorities or plans describes this alignment for Ghana (paragraph) 139, Mozambique (paragraph 140) and Uganda (paragraph 141). |

Response to STAP Review

| Guidance from STAP | Response |
| --- | --- |
| STAP Advisory Response: Based on this PIF screening, STAP’s advisory response to the GEF Secretariat and GEF Agency(ies): Consent STAP welcomes the submission of this concept for an ambitious and innovative project intending to remove identified barriers to acquiring and using biodiversity information so as to influence national development decision-making in at least three demonstration countries (to be identified â€“ although indicative countries have been noted). | The STAP review was taken fully into consideration during project preparation. |
| Comment 1: The structure of the project framework is logical and coherent and clearly demonstrates the links between the identified problem, barriers, and planned Outcomes and Outputs required. Indicators at the Outcome level will obviously require further definition and refinement moving forward. Designing meaningful and actually measurable indicators for the three Outcomes will undoubtedly be challenging particularly because they will invariably be difficult to quantify and also due to the general incompatibility between the timeframe of the proposed project (4 years) and the considerably longer time it will take to potentially see the effects of the interventions. Another key assumption and challenge that the project is making is that better information will result in better decision-making from the perspective of biodiversity. Evidence of changes in outcomes for biodiversity is essential in order to determine long term success and value for money. It would be useful to ensure a follow up assessment of the project's impact 5-10 years following its final evaluation. | It is acknowledged that developing outcome level indicators for the project has been challenging and these have gone through several iterations during the PPG phase. The results of these deliberations have been informed by participation in a UNEP organized Results Based Management Training Course and UNEP-WCMC’s considerable experience in supporting the development of biodiversity indicators. The project strives for long term sustainability of impact beyond the immediate timeframe of the project by ensuring that the project outputs are embedded within decision-making processes, both national and globally. Indeed Component 3 is all about seeking to achieve this. Section 3.8 on Sustainability discusses this approach. UNEP-WCMC has a long term interest in and commitment to the area of mainstreaming of biodiversity information which is a central part of its organizational strategy. It is highly conceivable that as its portfolio of activity in mainstreaming grows over the years, it will (subject to funding) revisit this project and other related mainstreaming projects to assess the long term impact of mainstreaming biodiversity information interventions from both the user and data providers perspectives. |
| Comment 2: Further refinement of the stakeholders will of course be required once the pilot countries are selected. The risks are identified in a generic manner which is adequate at this stage, but will also require revisiting later on in the project's development. Their assessment and proposed mitigation measures are realistic and appropriate. Considerable coordination with other initiatives and processes will be a challenge and thus the specific nature of the mechanism(s) and processes to be employed to ensure effective coordination will require considerable attention â€“ as noted in the document. | Refinement of stakeholders has taken place during the PPG phase. In Annexe 2 on Demonstration Country Information, the principal stakeholders have been tabulated (Tables 4,9 and 15) based on visits to and meetings in the three chosen demonstration countries. This has moved the stakeholder analysis on to be much more specific. Furthermore, it is also proposed that during the inception phase of the project, using a combination of political economy analysis and the National User Boards, further detailed stakeholder analysis focusing particularly on mainstreaming entry points in each country will be developed. This approach is outlined in Section 3.4 Intervention logic (paras 111,112) |
| Comment 3: Finally, the proposal notes the importance of open, transparent access to biodiversity data and information as a prerequisite to development decision making that takes fully into account impacts to biodiversity. However, the proposal does not make explicit the importance of ensuring that any new biodiversity data and/or information assets generated through this effort are themselves available to other actors and potential users beyond government“ in order to improve decision making in other domains such as the civil society and private sectors as well as to build on and add value to these assets wherever possible. STAP strongly proposes that a clear open access commitment on the part of eventual government partners be made an obligation of funding, and also that clear commitments are made by these partners to ensure stable, openly accessible data repositories beyond the life of the project. | Section 3.4. on Intervention Logic in the Project Document which describes Component 2 (focusing on data supply) discusses the value and importance of partnerships (see p.52 Output 2.3) The description in this paragraph of the nature of formalized partnerships includes reference to the need for sharing of information. This would be necessary for both government and non-governmental partners. UNEP-WCMC strongly supports the principle of openly accessible data and when constructing relevant partnership agreements and contracts with partners of all kinds will ensure that this principle is included. |

Annex C.  status of implementation of project preparation activities and the use of funds

| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
| --- | --- | --- | --- |
|  | Budgeted Amount | Amount Spent To date | Amount Committed in co-finance |
| 1: Stakeholder consultations and consensus building at regional and global levels | 45,000 | 45,000 | 15,000 |
| 2: Initial review of barriers to biodiversity data sharing, existing partnerships at national, regional and global scales and existing relevant biodiversity knowledge products | 20,000 | 20,000 | 10,000 |
| 3: Preparation of comprehensive implementation plans for all pilot activities | 20,000 | 20,000 | 10,000 |
| 4: Feasibility analysis and budget preparation | 35,000 | 35,000 | 10,000 |
| Total | 120,000 | 120,000 | 45,000 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF Trust Fund or to your Agency (and/or revolving fund that will be set up)

N/A

GEF_CEOENDR_52

http://www.thegef.org/gef/sites/thegef.org/files/Docs/PL.SD_.03.Policy_on_Environmental_and_Social_Safeguards.Update_09_12_2013.pdf

Aguilar L (2009). Training Manual on Gender and Climate Change, IUCN, UNDP and GGCA, Gland, Switzerland. CARE (2010). Adaptation, gender and women’s empowerment. CARE International Climate Change Brief. Available from: [Link] (Accessed November 2013.)