Project Identification Form (PIF)

Project Type:  		Medium Size Project

Type of Trust Fund:	GEF Trust Fund

PART I: Project INFORMATION

| Project Title: | Supply Change: Securing Food, Sustaining Forests |  |  |
| --- | --- | --- | --- |
| Country(ies): | Global | GEF Project ID: | 5776 |
| GEF Agency(ies): | UNEP | GEF Agency Project ID: | 01267 |
| Other Executing Partner(s): | Forest Trends | Resubmission Date: | 02 April 2014 |
| GEF Focal Area (s): | BD | Project Duration(Months) | 24 |
| Name of parent programme (if applicable): |  | Agency Fee (US$): | 180,500 |

- Indicative Focal Area  strategy Framework:

| ### Focal Area Objectives | ### Trust Fund | ### Indicative Grant Financing ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- |
| BD-2 | GEFTF | 1,900,000 | 2,725,000 |
| Total project costs |  | 1,900,000 | 2,725,000 |

- Indicative Project Framework

| Project Objective: To inform the integration of public policies and private finance to mainstream biodiversity and ecosystem conservation in production landscapes |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative Grant Amount ### ($) | ### Indicative ### Co-financing ### ($) |
| Component 1. State of the art, objective information and analysis to support decisions that favor sustainable commodity sourcing and/or production | TA | 1.1 Increased awareness of corporate sustainability commitments to low- or zero-deforestation in sectors with intensive land area impacts 1.2: Increased transparency and accountability for corporate commitments to sustainable forestry and land use 1.3: Illuminate intersection of commitments to certification of low-deforestation ag/forest products, and regional REDD+ certification of and financing for reduced deforestation in production landscapes (Evidenced by tracking of declarations and adoption of sustainability commitments by corporations. This outcome will contribute to achieving Acihi Target 1, 3, 4, 5, 18 and 19) | 1.1.1: A global assessment of commodities/ crops that derive value from assuring their positive environmental footprint, focusing on commodity sectors with an unarguably significant forest footprint – palm oil, cattle, paper/pulp and soy – and investigating associated corporate commitments to low or zero deforestation/ degradation/ conversion, social conflict mitigation and other sustainability indicators in these sectors; 1.1.2: For commodities under review, build a robust primary data set (tracking >75% of relevant programs and proportion of commodity volume comparable to other tracking initiative results [25-45%]) with support from existing tracking and industry initiatives; 1.2.1: Secure corporate commitments to annually disclose performance data and/or support Forest Trends in development of research product(s); 1.2.2: Develop mutually informative relationships with relevant supply chain actors and regional governments, measured in # of data providers; # of actors engaged in research steering group; quality of industry insights contributed to research process and narrative; and private sector and policy citations of report findings; 1.3.1: Rigorous data collection tracking REDD+ finance flows to and implementation of jurisdiction-scale programs in relevant regions (piloting in Latin American states), identifying opportunities for optimizing jurisdictional REDD+ activities/finance, corproate deforestation targets and on-farm certifications (also informing Project Component 2); findings made publicly available; | GEFTF | 1,000,000 | 1,310,000 |
| Component 2. Mainstreaming Biodiversity and Ecosystem Conservation in Supply Chains | TA | 2.1 Uptake of financing mechanisms that encourage/ support sustainable agriculture production 2.2 Availability of models that mainstream biodiversity and ecosystem values in public and private sectors 2.3. Public sector and investor awareness of regulatory frameworks or policies that account for biodiversity in financial systems (Evidenced by tracking of financial flows to sustainable agriculture produciton and commodity supplly chains. This outcome will contribute to achieving Acihi Target 1, 3, 4,5, 18 and 19) | 2.1.1 Produce three case studies of existing financing mechanisms that encourage agricultural sustainability, including successes and lessons learned that can be applied in the development of new financial mechanisms; 2.1.2 Design two new financial mechanisms that can address agricultural sector barriers to sustainability while incentivizing improved practices and biodiversity conservation; 2.1.3 Conduct consultations on financing mechanisms with tropical forest country institutions (2+), donor governments (3-4), development finance institutions (2), commodity roundtables/ supply chain actors (4+), and private finance actors; 2.2.1 Development and proposal of one or more new sustainable funding models to support jurisdiction-scale sustainable production landscapes for individual /multiple states and nations; 2.2.2 Conduct four stakeholder consultations on potential sustainable funding models among UNEP FI financial institution network; 2.2.3 Conduct in-depth consultations on funding models with donor governments (3-4), development finance institutions (2), tropical forest country institutions (3+), commodity roundtables/ supply chain actors (2+), and institutional investors (2+) 2.3.1 Develop guidance for regulatory framework(s) and/or policy(ies) that effectively account for environmental and social risks in commodity supply chains 2.3.2 Conduct consultations on frameworks and policies with development financial institutions, private finance actors, and institutional investors. | GEF TF | 571,429 | 835,000 |
| Component 3 Enhancing Effective Dialogue in the Commodities Sectors | TA | 3.1: New conservation policies and decisions in the public and agricultural sectors. 3.2: Increased visibility and incentives for voluntary public reporting and sharing of best practice. (Outcome 3 indicator added: Evidenced by tracking of new conservation policies in public and agricuture sectors as well as increased awareness parameters. This outcome will contribute to achieving Acihi Target 1,3, 4, 5, 18 and 19) | 3.1.1: Forward-looking report outlining actionable steps for new conservation policies and decisions by producers, processors, policy-makers and practitioners. 3.1.2: At least three “Katoomba-like” events focused on the theme of sustainable commodities to build impetus and awareness. 3.2.1: At least 6-8 articles/year; and mainstream media coverage, with a target of 2-3 articles (or the equivalent)/year. 3.2.2: Reporting system to publicize achievements/ commitments 3.2.3: Dissemination of peer-reviewed findings via Katoomba events, and commitment relvant official gatherings. Host additional 2-3 annually educational and inclusive report/research launch events engaging public/private sector and producer community stakeholders in order to inform, involve, and incentivize high-profile stakeholder buy-in. | GEFTF | 238,095 | 430,000 |
| Sub-Total |  |  |  |  | 1,809,524 | 2,575,000 |
| Project management cost (5%) |  |  |  | GEF TF | 90,476 | 150,000 |
| Total project costs |  |  |  |  | 1,900,000 | 2,725,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| Sources of C-financing | Name of Co-financer | Type | Amount |
| Multi-lateral | World Bank Programme on Forests | Cash | $500,000 |
| Multi-lateral | UNEP DEPI | In kind | $300,000 |
| Bilateral | GIZ | Cash | $690,000 |
| Bilateral | NORAD | Cash | $600,000 |
| Foundation | Climate and Land Use Alliance | Cash | $245,000 |
| Foundation | Moore Foundation | Cash | $330,000 |
| Foundation | Bloomberg Foundation | Cash | $25,000 |
| NGOs | The Nature Conservancy | Cash | $35,000 |
| Total Co-financing |  |  | $2,725,000 |

- Indicative Trust Fund Resources ($) Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal area | Country Name/Global | Grant amount ($) (a) | Agency Fee ($) (b) | Total ($) (a + b) |
| --- | --- | --- | --- | --- | --- | --- |
| UNEP | GEF TF | BD | Global | 1,900,000 | 180,500 | 2,080,500 |
| Total Grant Resources |  |  |  | 1,900,000 | 180,500 | 2,080,500 |

- Project Preparation Grant (PPG)

PPG amount Requested by Agency(ies), Focal Area(s) and Country(ies) for MFA and/or MTF

| GEF Agency | Type of Trust Fund | Focal area | Country Name/Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNEP | GEF TF | BD | Global | $100,000 | $9,500 | 109,500 |
| Total PPG Amount |  |  |  | $100,000 | $9,500 | $109,500 |

PART II: Project Justification

- Project Overview

A.1.Project Description

- Global challenges to biodiversity conservation, primary drivers and barriers.

The economic rationale for forest protection – for the value of the local and global ecosystem services that forests provide, including carbon sequestration, watershed protection, biodiversity conservation, fertile soil, and resilient food production systems – is well understood. Yet, while there has been some progress in identifying and addressing the drivers of deforestation, many regions, donors and agri-business actors encounter challenges to valuing environmental externalities sufficiently to overcome the short-term opportunity costs of preserving forests at scale.

But in an effort to counteract big agriculture’s contribution to global deforestation, private buyers’ commitments to sustainably-sourced commodities may be a powerful catalyst for conservation, most often driven by 1) consumers, investors and policy-makers who are ever more conscious of supply chain impacts from grower to grocer; 2) corporates’ desire for security of supply and sound producer relationships; and 3) the international community’s intensifying action at the intersection of communities, commodities, climate and the functioning of ecosystems.

Compared to the fragmenting global carbon market – valued at US$176 billion in 2011 (World Bank, 2012) – the turnover value of land-based commodities easily exceeded US$10 trillion in 2010-2011. The associated volume of agriculture production presents enormous threats to ecosystems the world over, as well as opportunities for significant interventions favoring responsible, sustainable production (i.e. low/zero deforestation and climate-smart) and sourcing.

Forest practitioner and policy communities have historically suffered from siloed approaches to natural resource management and biodiversity conservation on one hand, and agricultural production and food security issues on the other. Such efforts have also been hampered by focusing on small-scale pilot projects, farm-level certification schemes, and individual carbon/REDD+ projects rather than broader, more holistic approaches to mainstreaming biodiversity and ecosystem conservation into public and private sector operations and financing.

Successfully mainstreaming biodiversity and ecosystem conservation at the scale of landscapes and regions represents no small task, however – it requires an integrated approach across all parts of the value chain and understanding of the links between producers, buyers, governments and financial institutions, to help generate a large-scale, resilient “supply side” productive landscapes for sustainable commodities, as well as the market “demand side” driven by regulation and/or consumer preference.

Over the years, initiatives like Forest Trends’ Ecosystem Marketplace and some World Bank-led programs and funds have provided some level of market certainty and transparency to other environmental markets; for example, tracking the evolving structure and performance of carbon price mechanisms – including certification types, average pricing and market value. By comparison, information about the drivers, impacts, costs, and infrastructure of sustainable commodity production and sourcing is incomplete. For instance, very little primary data exists on: monetary and other benefits to producers and buyers; market and/or environmental performance for commodities that are governed by corporate commitments to low or zero net deforestation/ degradation/ conversion; social conflict mitigation; biodiversity conservation; and other sustainability indicators.

In order to fill this information gap that is present from the local to global levels, Washington DC-based NGO Forest Trends – with its significant experience in various market tracking and advisory initiatives – aims to apply its  market-tracking methodologies and expertise in structuring public and private finance to support sustainable landscapes to informing and positively influencing these developments.

This work is extremely important and relevant in order to create confidence for commodity buyers to more readily commit to low- or zero-deforestation supply chains in response to more efficient (e.g. jurisdiction-scale) land area certification; for commodity producers and supply chains to change practices in favor of sustainable production; for local governments to support regional policies and petition for a restructuring of existing agriculture expenditures; and for donor governments to commit to REDD+ funding against a trajectory of performance-based payments for biodiversity and forest conservation, the co-benefits of which include rural development and private sector finance engagement.

- The baseline scenario and any associated baseline projects

The Project Components described in Table B address the multifaceted challenge of mainstreaming conservation finance as discrete activities targeting different baseline problems, each of which are nevertheless heavily dependent on the success and quality of the project and deliverables as a whole. Specific baseline problems to be targeted by the proposed Project Components include:

Project Component 1: State of the art, objective information and analysis to support decisions that favor sustainable commodity sourcing and/or production

Changes in production practices are commonly influenced by consumers – in this case, by the world’s major commodity buyers (and, indirectly, by their product end users’ preferences). Some corporate reporting programs have identified buyers such as Nestle, Marks & Spencer, Sainsbury’s, Unilever, McDonald’s and several other buyers/retailers as major influencers in the up-scaling of commodities with a significant, sustainable forest footprint. Broad participation in these voluntary reporting initiatives demonstrates the efficacy of transparency initiatives in driving corporate accountability and in some cases, positive practice change.

These programs are primarily focused on the “buyer link” at the end of the commodity value chain. While such companies can be significant influencers within their sectors, they are nonetheless the last link in a very long and often untraceable chain of producers and intermediaries.

Meanwhile, some organizations serving as conveners like the Consumer Goods Forum (CGF), NGOs such as IDH and WWF, and various roundtables collect some data about their corporate stakeholders. Additionally, researchers and consultants like KPMG, Price Waterhouse Coopers, the Carbon Disclosure Project (CDP) and the International Institute for Sustainable Development (IISD) and the State of Sustainability Initiative (SSI) collect and provide information about voluntary commitments and mechanisms for achieving sustainable production and sourcing. Primary data collected by these programs is largely “top-down” – i.e. obtained from downstream commodity buyers and certifiers. This has produced an inherently limited and fragmented market picture. Some of the most actionable data obtained by or through these organizations must remain confidential. A partial list of currently available resources includes:

The Carbon Disclosure Project’s annual Global Forests Report: Formerly a collaboration between CDP and the Global Canopy Programme, this report documents corporates’ willingness to disclose their “forest footprint”; the nature of corporate commitments to low-, zero- or zero net deforestation; and net value of companies making commitments and participating in the CDP survey. The project does not provide financial data on the cost or value of commitments; geographic or land-area impacts of commitments; or supply- or demand-side drivers; though some effort is being made to tie CDP’s forest survey findings to its supply chain-level survey.

The State of Sustainability Initiative’s semi-annual State of Sustainability Initiatives report: This report tracks a broader suite of impacts related to corporate sustainability commitments through the lens of third-party certifications such as FSC or the Rainforest Alliance. While the project itself is a massive multi-year undertaking, its non-anecdotal primary data is sourced from these and other certifications programs and roundtable secretariats rather than from sample or population surveys of producers, processors or corporates. Because third-party certifications represent a relatively small volume of any commodity sector, this report misses purchasing and trade activities that occur outside of these programs. Also, due to the large volume of information that is presented with respect to these programs, the report itself is viewed as “academic” rather than commercially influential (at >300 pages in length).

The World Wildlife Fund’s corporate commodity scorecards/database: The information collected by WWF, as presented online in its Palm Oil Industry Scorecard, compares corporate commitment types, associated and overall trade and purchase volumes and certification use obtained and reported at the levels of commodity buyers (not consumers) and traders. While WWF maintains and continues to grow this valuable data collection, much of the information is divulged to WWF on a strictly confidential basis and is thus publically unusable even in aggregate. In contrast, Ecosystem Marketplace commits to protect the confidentiality of sensitive business information, but will nonetheless present findings publically, in aggregate, to support the identification and selection of opportunities for action by public and private sector movers.

These examples demonstrate a very significant gap and clear need for additional research that contributes global, aggregated, publically-available information about the supply of and demand for commodities with a low-, zero-, or net zero-deforestation footprint. This conclusion is supported by many of the initiatives themselves and other committed members of various multi-stakeholder initiatives. For instance, very little primary data exists on premiums (if any) and their drivers, market and/or environmental performance for commodities that are governed by corporate commitments to low or zero deforestation, social conflict mitigation and other sustainability indicators. Also important is fostering greater transparency around which companies are making commitments; the impacts associated with those commitments; which companies are not actively greening their supply chains but should be – and why; and which “links” in the supply chain have the most direct influence on both buyer and producer uptake of sustainable practices; all of which may inform policy-makers and consumers about where and how to direct their scrutiny to drive practice change.

Likewise, very little has yet been tracked evaluating land-area impacts on biodiversity and hectares under commitment and management, as well as the relationship or overlap between certified production landscapes and land areas governed by and accounted for under a jurisdiction-scale REDD+ program. Acknowledging that REDD+ interventions commonly target agricultural expansion as a deforestation driver – and are slated for implementation in some of the world’s most threatened and productive ecosystems – Forest Trends expects that emerging programs in these regions will significantly contribute to our understanding of the potential synergies between public policies and public finance supporting REDD+; and private finance supporting low- or zero-deforestation supply chains.

Project Component 2:  Mainstreaming Biodiversity and Ecosystem Conservation in Supply Chains

A number of actors in agricultural commodity value chains (including producers and agri-businesses) have been addressing the need for greater productivity while also conserving forests. For example, the Roundtable for Sustainable Palm Oil and the Roundtable for Responsible Soy have each developed international certification systems that include forest conservation. The Forests, Farms and Finance Initiative (FFFI) has brought together a wide range of actors to better link sustainably produced, Roundtable-certified commodities with increased access to markets and various sources of finance in order to move a range of agricultural commodities to “no forest loss.”

The Consumer Goods Forum (CGF) – a collaboration of 400 retailers, manufacturers, and service providers with combined annual sales of over USD3 trillion – has announced a commitment to move toward a goal of zero net deforestation in its supply chains by 2020. Additionally, individual companies including Unilever and Nestle have ambitious targets for zero deforestation sourcing of raw materials.

While CGF companies have committed to eliminating deforestation from their supply chain, they are just now grappling with how to trace, monitor and evaluate their global supply chains to demonstrate zero-deforestation. And producers in Brazil and other areas have increased production while decreasing deforestation but are also demanding compensation for the higher costs of sustainable production (including opportunity costs of leaving ecosystems intact).

Meanwhile, required annual investments in agriculture just to meet projected demand in 2050 are estimated to be about US$209 billion, which would be even higher if taking into account the costs of implementing sustainable agriculture systems. And reducing deforestation by 50 percent by 2030 via REDD+ implementation will require between US$15 and $33 billion/year. Thus, Forest Trends intends to track and inform the private sector’s independent and roundtable commitments and their contributions as described in Component 1, but also acknowledges that voluntary, market-based approaches will not by themselves overcome the environmental impact of near- to medium-term growth in food production and consumption – and that the costs of producer practice change cannot be met solely by voluntary corporate commitments to greener supply chains.

There is, however, a great opportunity to integrate private and public finance to 1) better support sustainable production and supply chains, 2) to scale up sustainability efforts from the farm to jurisdiction, and 3) to mainstream biodiversity/ecosystem conservation in the global financial system.

First, increasing agricultural sustainability is costly, but financial flows to the agriculture sector are large: average annual investment by domestic private sector actors into just a portion of low- and middle-income countries (76 countries) is US$168 billion, and government expenditures on agriculture in a subsection of these countries (54 countries) is US$160 billion. It is therefore important to harness these larger pools of capital to support sustainable commodity production that reduces deforestation and on-farm emissions. To do so, we must find the intersection of interests between agriculture and biodiversity/REDD+/ecosystem services so that their associated pools of capital can be better integrated to support complementary goals of enhanced agricultural productivity, security of supply, biodiversity protection and rural economic development. Furthermore, while the funding available for climate change and REDD+ is limited, these funds can be critical and catalytic if used to support innovations in agricultural finance to create new financial products, pioneering polices and advanced models that demonstrate or enhance this alignment of interests – which could then unlock additional financing from the private sector, and potentially public funds.

Second, an ambition to operate at scale might allow the development of transformational and financially sustainable funding models. This would include utilizing limited donor funds to leverage both the international capital markets and existing pools of investment (e.g., domestic public agriculture or commodity supply chain finance), to support financing products and regulation on the ground that align sustainable agriculture with environmental conservation. International climate finance (GEF funding, donor country or Green Climate Fund commitments to REDD+ Results-Based Financing) could be utilized to pay for meeting Greenhouse Gas (GHG) emission reduction targets versus an agreed jurisdictional baseline. Financing instruments such as Jurisdictional REDD+ Bonds could leverage private capital from institutional investors in order to help overcome the upfront investment costs and financing requirements of protecting biodiversity and improving agriculture practices.

Capital raised from financing instruments could, at a local level, be ring-fenced for investment in Low-Emission Rural Development and ecosystem protection, helping to send existing agriculture finance programs down a more sustainable path. Financing to achieve jurisdictional GHG reduction targets would result in the creation of landscape-level sustainable timber and low/zero-deforestation agriculture commodity supply chains. And financing Instruments could be sufficiently large to attract investment from institutional investors if structured in the right way and would thus help to mainstream biodiversity values in capital markets.

Third, as financial investment is not currently required to consider the biodiversity/ecosystem/forestry impacts of investment decisions, there is an opportunity to develop guidance for possible regulatory framework(s) and/or policy(ies) that would effectively account for environmental and resource costs and risks in global financial systems such that long-term financing for such conservation would be increased. This will further leverage action through UNEP’s Finance Initiative (FI), whose formal membership network comprises over 230 financial institutions internationally including banks, investors and insurers and with a strong network/operational footprint in commodity producer countries and initiatives (e.g. 6 out of 7 banks in the RSPO ‘Finance Task Force’ are UNEP FI members).

Project Component 3: Enhancing Effective Dialogue in the Commodities Sectors

In response to the growing recognition of soy and cattle expansion as major drivers of land conversion in the Amazon and beyond, producers, agribusinesses, traders and others in agricultural commodity value chains have begun to explore ways of reducing their footprints. Several private sector initiatives have emerged to address this challenge. In addition to the efforts of corporate initiatives such as the CGF and FFFI (see Project Component 2 on previous page), some organizations and companies have formed roundtables to coordinate efforts around specific commodities. And recent initiatives focused on building jurisdictional approaches (national, subnational, and municipal) could bring integrated, large-scale transformation to commodity supply chains.

Initiatives like these are critical, but they are in early stages of development. If the challenge of increased agricultural production and zero-deforestation is to be met in the next few years, new relationships, creative approaches, and new sources of finance will be required to help companies and their supply chains achieve long-term sustainability while still remaining competitive in the marketplace and meeting their bottom line.

At such a critical juncture in the development of sustainable commodity markets, it is more important than ever to provide these actors with a platform to convene, to share experience, showcase new programs, make public commitments, and influence and achieve consensus about industry best practice – as well as to generate positive international exposure for companies taking early action. For 15 years, this kind of open communication and collaboration around biodiversity conservation has been at the crux of Forest Trends’ “Katoomba” events, where hundreds of the most relevant and influential actors in any space converge to catalyze new solutions to environmental finance. We intend to similarly apply this model for incubating innovation to the issues addressed by this project.

- The proposed alternative scenario, with a brief decription of expected outcomes and components of the project.

Project Component 1: State of the art, objective information and analysis to support decision-making around sustainable commodity sourcing and/or production

Planned activities: In order to achieve the outcomes described in the previous paragraph and in Table B, we will increase the level of relevant information and analysis available to the international community as we:

1.1.1: Publish a global assessment of commodities/crops that derive value from assuring their positive environmental footprint, leveraging Ecosystem Marketplace’s nine years of experience with environmental market tracking and value estimation. We will initially focus on commodity sectors with an unarguably significant forest footprint – palm oil, cattle, paper/pulp and soy – and will investigate associated corporate commitments to low or zero deforestation/degradation/conversion, social conflict mitigation and other sustainability indicators in these sectors.

1.1.2: Develop a robust, representative primary data set to inform the report described in Output 1.1.1, as well as advisory and analytical activities detailed in Project Component 2. We aim to track >75% of relevant programs (n both mature and emerging markets) and a proportion of commodity volume that is comparable to other tracking initiative results (25-45%) with support from existing tracking and industry initiatives. This data will be updated annually or as possible/appropriate, and Forest Trends will retain all corporate disclosures as confidential.

1.2.1: As necessary, secure commitments from relevant businesses, regional governments, producers and corporations to annually disclose  performance data and/or support Forest Trends in the development and interpretation of research as defined in this Project Component. This includes utilizing Katoomba event(s) and project partnerships to secure corporates' consent to participation.

1.2.2: Establish strong relationships with relevant supply chain actors and regional governments, measured in the number of data providers contributing to Component 1 research products; number of actors engaged in research steering group; quality of industry insights contributed to research process and narrative; and private sector and policy citations of report findings.

1.3.1: Apply Forest Trends’ REDD Expenditures Tracking Initiative methodology to follow finance flows from donor to recipient institutions at the subnational (i.e. jurisdictional) level, exploring and reporting on sub-national awards, anticipated performance and relevance to regional private sector actors. This research activity will not only investigate the emerging relationship between commodity-based sustainability initiatives and the world’s growing interest in jurisdiction-scale (i.e. regional) conservation incentives and monitoring – it will also provide data to directly inform analysis and guidance developed under Project Component 2. Forest Trends will select a pilot country for analysis based on the strength of our partner relationships and significance to both conservation objectives and international commodities markets. Brazilian states are key candidates.

Project Component 2: Mainstreaming Biodiversity and Ecosystem Conservation in Supply Chains

Planned Activities: In order to achieve the outcomes described in the previous section and in Table B, we will assess opportunities to support the development of sustainable agricultural production via interventions that incentivize and scale up improved production practices alongside direct conservation as we:

2.1.1: Publish three case studies of existing financial mechanisms that encourage agricultural sustainability, including successes and lessons learned that can be applied in the development of new financial mechanisms (e.g., the Low Carbon Agriculture [ABC] financing in Brazil; credit unions in Kenya that offer finance with group guarantees or structured with buyer contracts as collateral; etc.).

2.1.2: Design two opportunities for new financial products that can address agricultural sector barriers to sustainability while incentivizing improved practices and biodiversity conservation. In particular, we will develop a set of specific recommendations around one or more financial products/credit lines that Colombian or other developing countries’ agriculture institutions could design or launch to support access to credit for smallholders or to incentivize/support sustainable production by larger agriculture producers/processers.

2.1.3: Consult with key stakeholders: tropical forest country national and jurisdictional institutions, donor governments, development finance institutions, commodity roundtables/ supply chain actors.

2.2.1: Produce three briefing papers examining one or more sustainable funding models that support jurisdiction-scale sustainable production landscapes and link production landscapes with both voluntary corporate demand for sustainable commodities and legislative ‘demand-side' measures.

2.2.2: Conduct at least four stakeholder consultations on interventions and financial instruments (including focused side events at Katoomba convenings) and among UNEP FI financial institution network; measured as number of participating stakeholders and quality and use of feedback; for example consulting with donors on utilizing REDD+ PFP to leverage capital markets and create funding models for individual/multiple states and nations, under bilateral, multilateral or Green Climate Fund initiatives. This will build on and develop UNEP FI’s work on landscape PFP models that commenced in February 2014 with UN-REDD funding.

2.2.3:  Funding models (e.g. ‘Jurisdictional REDD+ Bonds’) could utilize international results-based financing for ecosystem service values to overcome externalities and drive investment from mainstream institutions. Papers will include one or more case studies evaluating programs in Acre and/or Mato Grosso (Brazil), Colombia, and/or Peru.

2.3.1: Provide guidance for regulatory framework(s) and/or policy(ies) that more effectively account for environmental and resource risks in global financial systems. We also intend to build on the foundations of the UNEP Inquiry which was launched in January 2014, to identify, develop and recommend reforms to the policy and regulatory arrangements governing financial flows relevant to the sustainable production and processing of selected commodities in countries such as Colombia.

2.3.2: Consultations on frameworks and policies with development financial institutions and institutional investors, leveraging UNEP FI’s global network.

Project Component 3: Convene key sustainable supply chain influencers to capture, communicate progress

Planned activities: In order to achieve the outcomes described in the previous section and in Table B, we will convene relevant actors through a series of awareness enhancing activities and through Katoomba events resulting in publicly available outcomes reports focusing on sustainable commodities as we:

3.1.1: Create a report describing pathway forward from recent Katoomba Brazil event: Scaling up Sustainable Commodity Supply Chains (held March 2014, Iguazu Falls, Brazil). The report will capture the event’s significant conclusions developed by attendee producers, processors, policy-makers and practitioners to inform future events and early policy actions.

3.1.2: Explore community progress by hosting additional “Katoomba-like” events focused on the theme of sustainable commodities including palm oil and pulp/paper as well as the soy and beef sectors, in other Latin America countries such as Colombia or other key consumer/buyer geographies such as China, India, Europe or US. These convenings will bring together major private influencers in target industries (significance determined by hectare area and proportion of domestic industry value their operations represent), policy makers, financial institutions, deforestation experts, and civil society organizations to identify challenges and solutions to shift toward sustainable, zero deforestation commodities production. The Katoomba events will build on outcomes from Forest Trends’ Katoomba XIX held in Brazil in March 2014, to be detailed in a summary report described in Activity 3.1.1. Subsequent events supported under this grant will similarly result in report(s)/brief(s) communicating outcomes, progress and messages intended to educate the broader community about the work of Katoombas’ influential attendees and contributors.

3.2.1: Regularly publish original articles related to the topic and associated Forest Trends activities. Thus the project will benefit from Ecosystem Marketplace’s diverse readers and partners (>1 million web hits to date, average report download rate of 35k/year) that already include influencers that are key to bringing both transparency and attention to this effort. Success will be measured as the number of articles published on the Ecosystem Marketplace website, with a target of 6-8 articles/year; and mainstream media coverage, with a target of 2-3 articles (or the equivalent)/year. We will also track reader uptake relative to other topic areas, to identify any greater reader interest in this topic compared to other environmental finance topics.

3.2.2: Publicly report achievements/ commitments, including high-impact media coverage of events, and research and policy outcomes associated with this project. Forest Trends will engage with Burness Communications to guide and ensure desirable coverage of event proceedings that relates real-time event outcomes to deliverables executed under this project.

3.2.3: Disseminate early and (later) peer-reviewed findings via Katoomba events, as well as the Fifth GEF Assembly (Cancun, mid-2014), UN Climate Summit (NYC, September 2014), UNFCCC 20th Conference of Parties (Peru, November 2014), and other public events as relevant and described in the Component 1 Rationale section. As relevant, host additional educational and inclusive report/research launch events engaging public/private sector and producer community stakeholders in order to inform, involve, and incentivize high-profile stakeholder buy-in.

ACROSS ALL COMPONENTS: The project team will work closely with the private sector, relevant international and local NGOs, agricultural research and extension personnel, and major co-financers.  A representative Steering Committee will be defined during the project development phase to provide guidance and facilitate cross-sector coordination.  The Project Manager will report to the Steering Committee, which will have regular meetings throughout the project and will supervise all project activities and decisions.

- Incremental cost reasoning and expected contributions from the baseline, GEFTF and co-financing

Forest Trends identifies a timely opportunity to address a critical gap in and opportunity to provide information and services that aim to up-scale biodiversity conservation incentives at the landscape level.  The activities proposed will opportunistically build on, enhance and coordinate the private sector’s growing interest in sustainable, secure production landscapes with international climate finance under REDD+, as well as developing countries’ domestic investment in agriculture and ecosystem services.  The proposal will incrementally build on the limited available data sources to generate and make publicly available aggregated and robust information on the global commodities supply chain.

The proposal leverages the GEF’s critical institutional role, unique global network of governments and civil society, and ability to take a broad view of the potential for synergistic links between biodiversity conservation, climate change mitigation and adaptation in order to build on efforts described in the baseline, to:  1) increase the level of relevant information and analysis available to the international community; 2) in particular, to foster transparency in the early stages of jurisdiction-scale conservation program finance and development that illuminates any mutual interests between public REDD+ finance and programs, and private finance and supply chain commitments; 3) incubate interventions that support global to local policy and financing mechanisms integrating biodiversity values into economic decision-making; and 4) convene relevant actors to foster new relationships, creative approaches, and new sources of finance necessary to help public and private decision-makers achieve long-term sustainability.

With respect to the scale of both the problem and solution, significantly-sized multilateral funders – particularly the GEF – are well-placed as leaders in this space to observe the full spectrum of eco-agricultural challenges and to support initiatives such as this one led by Forest Trends to provide transparent and reliable information that can guide their clients and stakeholders toward the most effective climate interventions.

GEF’s objective to increase attention to the socio-economic and gender elements of GEF projects, as important drivers and incentives for achieving global environmental benefits, echoes Forest Trends’ view that creating opportunities for forest and indigenous communities should be central to any policy or other intervention. Because of this – and recognizing that women and low-income communities bear the greatest risks associated with extreme climate change – both gender and community-facing indicators are included in the criteria by which we will evaluate corporate commitments to sustainable production landscapes.

In particular, it is well understood that women are disproportionately affected by decisions related to procurement of agricultural/pastoral products, and so are vulnerable to corporate decision-making and thus well-positioned to inform and implement alternative production strategies. In the research design process, we will consult with experts in the field of gender mainstreaming to determine the best methods to account for women’s inclusion in sustainable agriculture solutions. To the extent that it applies to our research product, we will explore means to collect gender-disaggregated data and to highlight the extent of gender considerations in the parameters of corporate commitments and targets. Emphasizing women’s critical role in implementing practice changes – and highlighting programs that successfully deliver on both gender and related adaptation benefits – will promote awareness of the topic and incentivize such considerations as standard to agricultural sustainability initiatives.

Likewise, Forest Trends’ REDD+ Expenditures Tracking Initiative includes parameters for tracking country performance in local community engagement in REDD+ activities. This same socio-economic data will be tracked at the sub-national level through this project – which may produce even more granular information about the extent to which public REDD+ finance and programs directly target agricultural deforestation drivers and thus influence forest community livelihoods, women’s participation and practice change.

Many agricultural sustainability initiatives operate under the assumption that improved agricultural techniques will result in additional community benefits, like more resilient local economies, poverty alleviation, and mitigation of social conflicts. Tracking the extent to which socio-economic indicators are considered – and delivered upon and measured – is a key element of Forest Trends’ market tracking and advisory services. Promoting better understanding of the current extent of and need for local community and gender inclusion will necessarily improve the efficacy and sustainability of the corporate initiatives. To some extent, this may also result from the more transparent alignment of private sector decision-making and investments with national policies and development priorities.

- Global environmental benefits (GEBs)

This project addresses a critical gap in information available to decision-makers involved in land-use and agriculture policies and forest-intensive commodity sectors for which global supply chains between producers and buyers are complex and interconnected, and vulnerable to deviations in economic and environmental conditions. Freely available, broad-based information about public and private policies influencing the state of sustainable commodity investment and sourcing, with a focus on positive forest and land-use impacts, is key to promote clear, strategic decisions expanding conservation in critical sectors (GEB 1).

Experts acknowledge that markets have a role to play; that many companies have ambition; that governments have the resources to support widespread innovation in forest-intensive commodity sectors; and that market confidence and partnerships are the primary elements that would tip the balance in favor of more sustainable, resilient agricultural approaches. This project design is based on the assumption that communicating pilot activity uptake, positive business outcomes, and early policy-driven successes helps to de-risk sustainable practice change (GEB 2). This project will provide unprecedentedly comprehensive market information that will endow otherwise fragmented actors with momentum, capacity and confidence to act (GEB 3), which in turn will inform innovative policy recommendations and investment incentives that favor sustainable commodities (GEB 4). Its proposed in-person convenings will be the connective tissue binding the relationships necessary to make such improvements systemic to policy and investment decisions (GEB 5).

This project will thus endow decision-makers with a broader view of opportunities that will bring agility and appropriate incentives to sustainable producers, investors, shareholders, and ultimately to consumers (GEB 6) – while uniquely tracking its own outcomes including the expanded awareness of and demand for low-, zero-, or net zero-deforestation commodities (GEB 7).

Forest Trends’ primary contribution to this space, through these proposed activities, is as a proven and neutral information provider and trusted ally of key businesses, governments, and civil society. Thus, many of these benefits will not be the result of systems changed implemented directly by Forest Trends, but instead as a result of the unique, decision-critical support provided to those best-placed to limit or reverse agriculture’s forest footprint (GEB 8).

The project is furthermore consistent with the prioritization of GEF-5 global focal area set aside funds to address supra-national strategic priorities to make substantive changes in the state of biodiversity at the global level.  The project specifically is: (i) relevant to the objectives of GEF’s biodiversity strategy; (ii) in support of priorities identified by the COP of  the CBD; (iii) high likely to have a broad and positive impact on biodiversity; (iv) targeting potential for replication; (v) delivering global demonstration value; and (vi) contributing to global conservation knowledge.

| Baseline Practices | Alternative | GEBs |
| --- | --- | --- |
| Component 1. Significant gap and clear need for additional research that contributes global, aggregated, publically-available information about the supply of, and demand and traceability for commodities with a low-, zero-, or net zero-deforestation footprint. | Increased awareness of corporate sustainability commitments to low- or zero-deforestation in sectors with intensive land area impacts; Increased transparency and accountability for corporate commitments to sustainable forestry and land use. | Reduce the development drivers affecting loss of biodiversity; Worldwide results through up-scaling strategy; Changes in policies and sustainability commitments will be monitored, verified through the project lifespan in conjunction with the completion of corresponding BD-2 GEF Tracking Tool. |
| Component 2. Un-integrated, fragmented financing opportunities supporting global supply chain achievement of low-, zero- or net zero-deforestation. | Increased integration of private and public finance to 1) better support sustainable production and supply chains; 2) to scale up sustainability efforts from the farm to jurisdiction; and 3) to mainstream biodiversity/ecosystem conservation in the global financial system. |  |
| Component 3. Companies at very early stages of addressing sustainability in supply chains are challenged by the need to remain competitive in the marketplace. | Avail of this critical juncture to to share experience, showcase new programs, make public commitments, and influence and achieve consensus about industry best practice – as well as to generate positive international exposure for companies taking early action -- with resulting new conservation policies and decisions, as well as increased visibility and incentives for voluntary public reporting and sharing of best practice. |  |

- Innovativeness, sustainability and potential for scaling up

Efforts to quantify the impacts of corporate sustainability initiatives, track REDD+ finance supporting jurisdiction-scale sustainable landscapes, and influence reprioritization of public finance toward sustainable outcomes are topics that Forest Trends and/or its implementing partners have tackled in recent years. This project is innovative in its recognition of the interrelated nature of these policies and potential efficiencies that could be achieved by their convergence. This, in turn, may increase their likelihood of mainstream uptake. The project is also unique in that several Forest Trends initiatives have already worked independently on these various topics – each respected in its own right – and are well-positioned to implement this project collaboratively. This combination of ideas and in-house cross-disciplinary approaches is unique to Forest Trends and will result in new thinking and catalysis.

In addition to internal enthusiasm for the subject matter, Forest Trends’ external research relationships, coalition-building and co-financing arrangements lend to the project’s sustainability. To this end, we will assemble a Steering Committee to guide project development and implementation, monitor funding allocation and reporting, and maintain regular dialog between this project and other related efforts, including those that will arise from GEF6. Members of the Steering Committee will include representatives of organizations like IDH, the Moore Foundation and private sector actors from the Consumer Goods Forum, which will fund or have expressed an interest in providing additional multi-year support to this project. Due to the sustainability business case and increasingly finite natural resources for producing (and thus sourcing) the commodities under review, we anticipate continued interest in this topic that will sustain research to achieve significant and measurable impacts.

With respect to potential up-scaling and future applications, the three Project Components outlined here are designed with the express purpose of replicating both our methodologies and recommended strategies. Project Component 1, tracking global commitments to and outcomes from sustainable commodity production/sourcing tracks select aspects of corporate sustainability initiatives in forest-intensive sectors. Meanwhile topics of air quality, improved health outcomes, increased access to education opportunities, reduction of drudgery, and non-forest-intensive sectors are not the subject of this project. Even so, any lessons, challenges incurred or efficiencies uncovered will be shared with others in the field. Collaborative industry research programs such as IDH’s State of Sustainability in Agro-commodities, which will track several commodity types and indicators beyond the purview of this project, is one opportunity to combine and share our findings with other researchers focusing on different aspects of the same market.

Tracking of jurisdiction-scale REDD+ finance, program development, private sector incentives and land-area outcomes builds upon Forest Trends’ existing methodology of tracking REDD+ expenditures and outcomes at the national level. It was developed with the goal of being universally applicable to any region and implementable by partner organizations, in order to track and report on a topic of this large scope. In this way, Forest Trends has partnered with well over a dozen local partners in the 14 forest countries so far tracked, and will apply the same approach when we drill down to the next level of decision-making.

Project Component 2 consists of proposing, supporting and – if successful – replicating public-private collaborative finance models in various jurisdictions. The purpose of the research is to identify effective models for integrated forest finance, with the intention of making that information freely available to other governments that wish to pilot such models, and to policy-makers developing forest finance incentives that are generic and globally applicable despite regional discrepancies.

With regard to Project Component 3, Katoomba events have been convened on every continent and in response to a multiplicity of emerging trends in the field. Likewise, the themes, discussions and outcomes of Katoomba Brazil (March 2014) will be continued at the next Katoomba(s) in this series (location TBD). As of this spring, Forest Trends has hosted 20 Katoomba events in this manner.

A.2. Stakeholders -  Please review and assign appropriate role…

| Stakeholders | Role |
| --- | --- |
| Forest Trends | Lead overall Executing Agency |
| UNEP’s Finance Initiative (FI) & Network | Partner executing agency |
| CDP | Consultative partner |
| Dutch Sustainable Trade Initiative (IDH) | Consultative partner |
| Consumer Goods Forum | Consultative partner |
| Roundtable + REDD+ Consortium | Consultative partner |
| IPAM Brazil | Consultative partner |
| The Nature Conservancy | Consultative partner |
| International Trade Center (ITC) | Consultative partner |
| Rainforest Alliance | Consultative partner |
| Tropical Forest Alliance | Consultative partner |
| IFC | Consultative partner |
| Food and Agriculture Organization (FAO) | Consultative partner |
| Center for International Forestry Research (CIFOR) | Consultative partner |
| State of Sustainability Initiatives Programme | Consultative partner |
| Sustainability Standards Transparency Initiative | Consultative partner |
| Forest Stewardship Council | Consultative partner |
| Relevant forest and agri-commodity roundtables | Consultative partner |
| PROFOR | Consultative partners and co-financiers |
| World Bank BioCarbon Fund’s Initiative for Sustainable Forest Landscapes and Forest Carbon Partnership Facility | Consultative partners and co-financiers |
| Climate and Land Use Alliance (CLUA) | Consultative partners and co-financiers |
| Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH | Consultative partners and co-financiers |
| Moore Foundation | Co-financiers |
| Bloomberg Foundation/New Energy Finance | Consultative partners and co-financiers |
| Verified Carbon Standard & Climate, Community and Biodiversity Alliance (VCS & CCBA) | Consultative partners |
| Various private sector stakeholders (e.g. Unilever, Bunge) | Consultative partners |
| Earth Innovation Institute (EII) | Consultative partners |
| World Resources Institute (WRI) | Consultative partners |
| World Wildlife Fund (WWF) | Consultative partners |

A.3. Risks

| RISK | Low, Moderate or High Risk | Risk Mitigation Strategy |
| --- | --- | --- |
| Scope creep: due to complexity of topic, inability to narrow research focus in order to determine and deliver findings; | M | Given the massive size and scope of the global commodity markets, as well as the broad application of sustainability certifications, this project will be challenged to identify and stick to the most relevant market segments and questions. This will require us to dedicate significant resources at the front end of the research process to clearly define our research agenda, strategy, milestones, variables and exclusions. |
| Business-sensitive data collection topics may deter corporates with visible international brands from contributing data at a meaningful depth; | M | Because this research project aims to provide market data based on cost and profit variables, we anticipate that companies may be reticent to share such sensitive business information with a third party. This will require us to: 1) Execute non-disclosure agreements with data contributors upon request, and factor the time required of any associated bureaucracy into our project timeline; 2) communicate our reputation and procedures for protecting confidential business information; and 3) establish rapport with significant data contributors early in the research project in order to maximize their level of comfort with our research parameters. |
| Survey/Research fatigue among relevant entities; | L | Many of the organizations we intend to survey and gain insight from are already the target of several research organizations’ efforts. Thus, they may be reticent to provide additional information to another research organization, as doing so is perceived as a sometimes significant time-cost. This will require us to: 1) establish the critical and unique nature of our data collection and anticipated report; 2) the report’s relevance to their sustainability initiative and information needs; 3) engage significant players directly and early in the development of the research product; and 4) as often as possible, partner with existing data collection efforts to minimize research duplication. |
| With respect to the proposed REDD+ Bond, lack of continuity at the ministerial level | M | Forest Trends has worked to establish strong relationships with policy leaders in multiple jurisdictions. While a change in leadership could potentially jeopardize the viability of a REDD+ Bond launch in one jurisdiction, we have made a significant effort to mitigate this risk by developing redundant relationships with political leaders in other candidate jurisdictions. |
| With respect to the proposed REDD+ Bond, failure to align international donors, national and sub-national finance ministries, and private investors to implement the mechanism | M | Again, we attempt to mitigate this risk by building “redundancy” into our project design – in this case, by remaining flexible with respect to the design of the REDD+ Bond or other potential finance model. We will adjust recommendations in step with changing policy and business ecosystems. |

A.4. Coordination

This project targets the core of Forest Trends’ mission, to expand the incorporation of ecosystem services’ value into business, policy and personal decision-making. As such, it will not result in the creation of a new research program, but will cut across and leverage the work, contacts and resources of several existing Forest Trends initiatives – most significantly impacting Ecosystem Marketplace, but also engaging the Public-Private Co-finance Initiative, the Forest Trade and Finance Initiative, the Katoomba Incubator and the Communities and Markets Initiative, in particular.

Externally, and as described throughout previous sections, “strengthening relationships with key stakeholders” is a primary deliverable of this project – recognizing that research and data partnerships and government relationships are absolutely necessary to deliver on other aspects of the project. In particular, this includes collaboration with other tracking and analytical initiatives led by organizations like IDH, the Earth Innovation Institute, WRI, WWF, CDP, and SSI, to identify knowledge gaps, needs, and best practice. Additionally, the content of this project will require collaboration with certification organizations that track their own projects and associated corporate commitments (when known), including Rainforest Alliance, Fairtrade, the Programme for the Endorsement of Forest Certification, and various commodity roundtables. In order to access relevant market actors – in particular, corporate producers/buyers – we will engage with business-facing programs like the Consumer Goods Forum and/or the Tropical Forest Alliance. Each of these programs is independent and well-established, and has agreed to support this research.

Select representatives of private sector, indigenous communities, relevant international and local NGOs and major co-financers will be invited to participate in a Steering Committee and/or Advisory Body to provide guidance and facilitate cross-sector coordination.  The GEF Implementing Agency (UNEP) will be part of the project Steering Committee and will also contribute to ensuring that appropriate linkages and coordination is maintained with relevant programs of all other relevant UN agencies, the UN REDD programs, the UN Finance Initiative, as well as with global environmental conventions and particularly with UNFCCC, CBD and UNCCD as well as the newly formed IPBES.

Description of the consistency of the project with:

B.1.National strategies and plans or reports and assessments under relevant 
conventions, if applicable, i.e. NAPAs, NAPs, NBSAPs, National Communications, TNAs, NCSAs, NIPs, PRSPs, NPFE, Biennial Update Reports, etc: (1)

N/A

B.2. GEF Focal area and/or fund(s) strategies, eligibility criteria and priorities:

Forest Trends’ proposal for work under the GEF-5 Biodiversity Strategy focuses on the goals of conservation, the sustainable use of biodiversity, and the maintenance of ecosystems’ goods and services – in particular, the 2nd GEF-5 strategic objective of “Mainstreaming biodiversity conservation and sustainable use into production landscapes and sectors” – through the design of activities which will result in impacts in the first and second outcome areas of this objective. Our proposal leverages the GEF’s critical global institutional role and ability to take a broad view of the potential for synergistic links between biodiversity conservation, climate change mitigation and adaptation in order to achieve these outcomes and also align with select Aichi Biodiversity Targets:

GEF BD Outcome 2.1: Increase in sustainably managed landscapes that integrate biodiversity conservation by 1: increasing the level of relevant information and analysis available to the international community, driving “race to the top” among decision-makers with regard to the quality and scope of sustainable forestry targets, and as a function of heightened consumer and investor attention (measured in ongoing increase in buyer participation in reporting processes and producer/processor-level data contributions, which in aggregate reflect greater stringency of supply chain transparency and governance; and in mainstream media coverage and otherwise broad dissemination of research results that reinforces corproate participation, attracts new report readers,and exhibits uptake within public-sector and investment decisions); and 2: fostering transparency in the early stages of regional conservation program finance and development that may lend scale and efficiencies to pursuit of both public and corporate sustainability targets (measured in ongoing increase of regional government contributions of forest conservation finance data, according to number of participating jurisdictions, quality and quantity of data collected, mainstream media and decision-maker use of findings, and any instances of public program development/change/additions attributed to enhanced policy transparency).

See also Aichi Target 1: People are aware of the values of biodiversity and the steps they can take to conserve and use it sustainably; Target 19: Knowledge, the science base and technologies relating to biodiversity, its values, functioning, status and trends, and the consequences of its loss, are improved, widely shared and transferred, and applied; and Target 5: The rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced.

In pusuit of these targets, this proposal includes measures to track and broadly disseminate information regarding corporate and regulatory progress in slowing or eradicating deforestation within agricultural supply chains (measured in quality, quantity, and reader uptake of related market tracking); fills a gap in global knowledge regarding public and private measures to combat forest loss (measured in quality, quantity, and reader uptake of proposed publications and advisory activities); and illuminates (thus helping eliminate) barriers to achievement of targets, enabling technical and financing conditions, and sectoral progress and contribution(s) to Target 5 (measured in ecosystem impacts of public and private programs as tracked according to indicators to be developed in early research phases [including but not limited to annual change in hectares measured according to corporate commitments of various stringencies]) .

and

GEF BD Outcome 2.2: Measures to conserve and sustainably use biodiversity incorporated in policy and regulatory frameworks by 3: incubating interventions that support global to local policy and financing mechanisms integrating biodiversity values into economic decision-making (measured in quality, quantity and public sector reference or contribution to, or uptake of, related reccomendations/publications); and 4: convening relevant actors to foster new relationships, creative approaches, and new sources of finance necessary to help public and private decision-makers achieve long-term sustainability of biodiverse landscapes (Measured in quantity and representativeness of event participants; quality, breadth and diversity of viewpoints and content presented; influence/uptake of any resulting accords or attendee-driven reccomendations; and any transactions, decisions or other related developments that are furthered by event outcomes).

See also Aichi Target 3: …Positive incentives for the conservation and sustainable use of biodiversity are developed and applied, consistent and in harmony with the Convention and other relevant international obligations, taking into account national socio economic conditions; Target 4: Governments, business and stakeholders at all levels have taken steps to achieve or have implemented plans for sustainable production and consumption and have kept the impacts of use of natural resources well within safe ecological limits; and Target 18: Traditional knowledge, innovations and practices of indigenous and local communities relevant for the conservation and sustainable use of biodiversity, and their customary use of biological resources, are respected, subject to national legislation and relevant international obligations, and fully integrated and reflected in the implementation of the Convention with the full and effective participation of indigenous and local communities, at all relevant levels.

In pusuit of these targets, this proposal includes measures to analyze and support public actors to harness the larger financing flows associated with public or private investment in agriculture in order to bring about transformational change in reducing deforestation at a landscape level; and leverage investment from private actors not only in the supply chain but also from investment institutions and the capital markets to address the significant upfront costs and financing requirements for increasing food production and improving livelihoods while preserving forests and ecosystem services (measured in quality, quantity and public sector reference or contribution to, or uptake of, related reccomendations/publications). In keeping with Forest Trends’ mission to “to enhance the livelihoods of local communities living in and around those forests”, any agendas, Katoomba events, outreach and research associated with this project will account for the role of indigenous peoples and communities in the pursuit of sustainable production landscapes and livelihoods (measured in proportion of data contributions, findings insights, event attendance, publication contents and reccomendations [as relevant] stemming from or relating to indigenous and other communities).

The project intervention strategy is consistent with several recommendations outlined in Decision X/21taken at the Conference of Parties (COP 10) in October 2010 at Nagoya. Project Components outlined above are particularly aligned with the Decision’s call to governments and businesses to:

Relevant to project Component 1: “Use clear and measurable criteria or indicators as a means to track implementation of these commitments in a transparent manner, by means of voluntary declaration”; and “Compile information on existing tools that can further facilitate the engagement of businesses in integrating biodiversity concerns into corporate strategies and decision-making”; and “Encourage businesses that endorse the objectives of the Convention and its Strategic Plan for Biodiversity 2011-2020 in communicating their biodiversity-relevant activities to their consumers, customers, and other stakeholders”.

Relevant to project Component 2: “Promote a public policy environment that enables private sector engagement and the mainstreaming of biodiversity into corporate strategies and decision-making in a manner that contributes to the achievement of the three objectives of the Convention”; and “Identify a range of options for incorporating biodiversity into business practices that take into account existing developments under various forums”.

Relevant to project Component 3: “Share and adopt lessons learned between and among business and enterprises, including small and medium-sized enterprises”; and “Survey available best practice within relevant industries, and to consider how specific skills, expertise and influence can be mobilized and shared in order to minimize and avoid negative impacts on biodiversity”; and “Develop and maintain an ongoing dialogue with Governments on how best to contribute to the achievement of the three objectives of the Convention”; and “Publicly report on biodiversity conservation and sustainable use of ecosystem services related activities”.

B.3. The GEF Agency’s comparative advantage for implementing this project:

The project is fully in line with the UNEP role of catalyzing the development of scientific and technical analysis and advancing environmental management in GEF-financed activities. UNEP provides guidance on relating the GEF financed activities to global, regional and national environmental assessments, policy frameworks and plans, and to international environmental agreements. More specifically, the project lies within the following areas recognized by GEF as areas where UNEP has a comparative advantage:

- Sound science for national, regional and global decision-makers, notably by strengthening science-to-policy linkages and by strengthening environmental monitoring and assessment;

- Technical assistance and capacity building at country level, notably by strengthening technology assessment, by demonstration and through innovation, and also by directly developing capacity;

- Knowledge management, including through awareness raising and advocacy.

The project is consistent with UNEP’s Programme of Work for 2014-2017, particularly the Ecosystem Management (EM), Resource Efficiency (RE) Programme Frameworks.  Specific objectives and supporting activities under Programme Frameworks include: Collaboration with the private sector through partnerships and pilot projects to integrate the ecosystem approach into sector strategies and operations is enhanced (EM); The 10 Year Framework of Programmes on Sustainable Consumption and Production and UNEP’s delivery on Green economy in the context of sustainable development (RE).

UNEP will be the “Implementing Agency” of the project and will contribute its experience in managing complex multi-country conservation-themed initiatives.  UNEP will be responsible for overall project supervision to ensure consistency with GEF and UNEP policies and procedures, and will provide guidance on linkages with related UNEP- and GEF-funded activities as well as technical guidance on specific issues. UNEP will also have the responsibility for regular liaison with the project Executing Agency (Forest Trends) on substantive technical and administrative matters and participating in meetings and workshops as appropriate.  The UNEP/GEF will be responsible for clearance and transmission of financial and progress reports on the relevant portions of the project to the Global Environment Facility Secretariat. UNEP/GEF retains responsibility for review and approval of the substantive and technical reports and products produced in accordance with the schedule of work.  Technical backstopping from the Sustainable Consumption and Production Branch, Division of Technology Industry and Energy (DTIE) in Paris, France.

As an executing partner, UNEP through its Finance Initiative (FI) is well positioned to deliver on the proposal due to a range of attributes including:

- Strong fit with current work areas: all proposed activities extend, focus and deepen current UNEP FI activities and will leverage an existing multi-million dollar existing budget already focused on these areas

- A formal membership network-  through UNEP’s Finance Initiative - of over 230 financial institutions internationally including banks, investors and insurers and with a strong network/operational footprint in commodity producer countries and initiatives (e.g. 6 out of 7 banks in the RSPO ‘Finance Task Force’ are UNEP FI members)

- Established relationships with ministries of finance, central banks and financial regulators in key commodity producing and purchasing countries

- Deep internal expertise within UNEP FI in all pertinent areas of environmental finance including investment, banking and insurance.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

N/A

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Brennan van Dyke, Director, GEF Coordinator Office, UNEP, Nairobi |  | April 2, 2014 | Kristin Mclaughlin, Task Manager | 202-974-1312 | Kristin.mclaughlin@unep.org |

See: Jurisdictional REDD+ Bonds, Sustainable Supply Chains, Finance and Development. Forest Trends paper forthcoming)