request for project preparation grant (PPG)

Project Type:

the GEF Trust Fund

Submission date:  February 9, 2010

GEF Project ID: 4191

GEF Agency  Project ID: 3374

Country(ies): Guatemala

Project Title: Promoting ecotourism to strengthen the financial sustainability of the Guatemalan Protected Areas System (SIGAP).

GEF Agency(ies):

Other Executing partner(s): National Protected Areas Council - CONAP

GEF Focal Area(s):

GEF-4 Strategic program(s): BD-SP1Financing; BD-SP3 PA Networks

name of parent/program/umbrella project (if applicable):  N/A

a.   Project preparation Timeframe

| Start date of PPG | June 2010 |
| --- | --- |
| Completion date of PPG | May 2011 |

- Past project preparation activities ($): N/A

| ### List of Past Project Preparation Activities | ### Output of the Activities | Project Preparation Amount (a) | Co-financing (b) | Total c = a + b |
| --- | --- | --- | --- | --- |
| Total Project Preparation Financing |  | 0 | 0 | 0 |

C.  proposed project preparation activities ($)

| Describe the PPG activities and justifications: - Assessment of laws and policies for implementing ecotourism within the SIGAP. PPG funds will be used to review selected legislation and policies in order to make an initial assessment of the changes needed to promote biodiversity conservation through the implementation of ecotourism in protected areas (PAs). Specifically, the following activities will be funded: i) identification of existing laws and policies related to tourism in PAs; ii) review of existing laws and policies for the collection and reinvestment of gate /concession fees in PAs; iii) review of existing taxation laws and preliminary identification of fiscal barriers that limit private sector investment in PA infrastructure and operations; and iv) institutional analysis to identify critical steps for incorporation of needed changes and updates into laws and policies. The information gathered through these activities will be instrumental for the development of the legal/policy and institutional context of the Project Document (ProDoc). - Final PA selection for the implementation of ecotourism activities. PPG funds will also be used to select the PAs that will be piloted within new tourism routes in three Western Highlands landscapes: RUMCLA (Lake Atitlán, 122,900 hectares [ha]), Todos Santos Cuchumatán (7,255 ha), and Tacaná (2,964 ha) and Tajumulco Volcanoes (13,032 ha). Pilot PAs will be selected from among national parks and smaller PAs such as the Chicabal Volcano, Los Altos de San Miguel Totonicapán Municipal Regional Park, San Pedro Sacatepequez Municipal Regional Parks/Forests 1 and 2, San Marcos Municipal Regional Park, Canjulá-Tocapote-Los Maijones Municipal Regional Park, El Caracol-Los Espinos-Mirasol-Tizate Municipal Regional Park, and the Corazón del Bosque Community Natural Reserve. In addition, target PAs may include several reserves within RUMCLA, such as San Pedro La Laguna and Santa Clara La Laguna, which are in the process of being incorporated into the SIGAP. Once the final selection of PAs is completed, the management effectiveness baseline will be established using UNDP/GEF’s Management Effectiveness Tracking Tool (METT). An initial assessment of the socioeconomic aspects of the target PAs will also be carried out and will allow the following to be achieved: i) identification of local- and regional-level stakeholders related to ecotourism implementation in PAs; and ii) the early involvement of stakeholders in ecotourism implementation decision making processes. - Biological and ecosystem baseline for ecologically sensitive areas. PPG funds will be used to identify ecologically sensitive areas within the target PAs to ensure that ecotourism activities are implemented within the acceptable limits of change in the pilot landscapes. Baseline studies will result in the definition of biodiversity impact indicators and their baseline values and conservation targets for sensitive species and ecosystems. Specifically, the following activities will be funded: i) detailed review of secondary information on sensitive species and ecosystems in the target PAs; ii) quantification of the status (baseline) of sensitive species and ecosystems; and iii) definition of indicators and conservation targets. - Income and financial gap assessment for pilot PAs. During the PPG a baseline study will be performed to assess the financial status of the target PAs. Specific issues to be addressed include current and projected management costs and financial sources, including revenue generated from ecotourism, financial gaps, existing revenue allocation mechanisms and their limitations, and an assessment of the management and business plans’ status for the target PAs. - Capacity needs assessment to strengthen CONAP and PA managers for ecotourism implementation in PAs. PPG funds will also be used to assess the training needs of CONAP’s officials and other PA managers to: a) manage visitors (including the development of skills for determining the visitor-carrying capacity of PAs and the collection and disposal of wastes that result from the increased numbers of visitors and activities, among other needs) and b) monitor the impacts of ecotourism. Training targets will also be defined. - Monitoring and evaluation (M&E) strategy. PPG funds will be used to develop the M&E strategy to track the project’s impacts and measure biodiversity conservation and financial performance trends over the long term. Activities will include the following: (i) evaluation of participating institutions’ current M&E systems - to measure conservation impacts and the financial sustainability of PAs; (ii) development of key biodiversity and financial indicators at the PA level; (iii) evaluation of how partner institutions account for financial sustainability and biodiversity impacts and benefits in decision making and project implementation; (iv) formulation of project M&E strategies including baseline levels, indicators, methodologies, and targets to track project progress and effectiveness; and (v) development of a cost-effectiveness analysis protocol to identify optimal interventions, assess lessons learned, and outline replication strategies. |  |  |  |  |
| --- | --- | --- | --- | --- |
| ### List of Proposed Project Preparation Activities | ### Output of the PPG Activities | Project Preparation Amount (a) | Co-financing (b) | Total c = a + b |
| 1. Assessment of legislation and policies for implementing ecotourism within the SIGAP. | - Review of laws and policies related to ecotourism in PAs finalized. - Institutional/stake-holder analysis and legal/policy reform implementation scenarios (including institutional bottlenecks). | $6,711 | $11,163 | $17,874 |
| 2. Final PA selection for the implementation of ecotourism activities. | - Project’s target PAs within pilot landscapes selected. - METTs baseline scores for target PAs. - Stakeholder analyses for target PAs. | $7,211 | $16,428 | $23,639 |
| 3. Biological and ecosystem baseline for ecologically sensitive areas. | - Baseline values and conservation targets for sensitive species and ecosystems defined. - Project indicators defined. | $7,880 | $11,164 | $19,044 |
| 4. Income and financial gap assessment for pilot PAs. | - Income and financial gap assessment, including revenues from ecoturism in place. - Assessment of the management and business plans’ status for the target PAs. | $4,370 | $11,164 | $15,534 |
| 5. Capacity needs assessment to strengthen CONAP and PA managers for ecotourism implementation in PAs. | - Capacity needs assessment to implement environmental and social safeguards for ecotourism in place. - Training targets for CONAP officials to manage visitors and monitor the impacts of ecotourism are determined. | $3,785 | $7,069 | $10,854 |
| 6. Monitoring and evaluation (M&E) strategy. | - M&E strategy is developed. - ProDoc and CEO Endorsement Request are submitted. | $38,225 | $11,194 | $49,419 |
| Total Project Preparation Financing |  | $68,182 | $68,182 | $136,364 |

D.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| GEF financing | 68,182 | 6,818 |
| Co-financing | 68,182 |  |
| Total | 136,364 | 6,818 |

E.  PPG requested by agency(ies), focal area(s) and country(ies) : N/A

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| Total PPG Requested |  |  | 0 | 0 | 0 |

F.   PPG Budget Request

| ### Cost Items | ### Total Estimated Person Weeks for GEF Grant (PW) | GEF ($) | ### Co-financing ($) | ### Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants | 48 | 29,080 | 62,670 | 91,750 |
| ### International consultants | 12 | 30,000 | 0 | 30,000 |
| Travel & Miscellaneous |  | 9,102 | 5,512 | 14,614 |
| Total PPG Budget |  | 68,182 | 68,182 | 136,364 |

G.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec UNDP/GEF Executive Coordinator |  | February 9, 2010 | Santiago Carrizosa, Regional Technical Advisor | +507 302-4510 | Santiago.carrizosa@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Position / Titles | $/ Person Week | Estimated PWs | Tasks to be performed |
| --- | --- | --- | --- |
| Local Operational specialist | 685 | 10 (GEF) 30 (Cof) | - Define operational strategies and resource needs for effective project implementation. - Organize stakeholder consultations (threats analysis, logical framework, financial baseline information, institutional and participation arrangements). - Define needs for implementation and participation mechanisms. - Negotiate implementation and participation mechanisms with institutions and local stakeholders. - Support drafting of PRODOC and CEO Endorsement Request. |
| Environmental/tourism law and policy expert | 585 | 10 (GEF) 14 (Cof) | - Review and analyze the existing legal and policy framework related to ecotourism within the SIGAP. - Perform stakeholder analysis for the implementation of legal and policy reforms. - Develop guidelines for the procedures required for effective institutional coordination for legal/policy reform at the local, regional, and national levels. |
| PA specialist | 585 | 16 (Cof) | - Hold consultations and meetings with PA authorities and managers (e.g., CONAP, INGUAT, municipalities) for the final selection of the target PAs. - In coordination with the operational specialist and the environmental M&E specialist apply the METT for the target PAs. |
| Biodiversity expert/ecologist | 585 | 12 (GEF) 14 (Cof) | - Hold consultations and meetings with managers and selected staff from target PAs to identify sensitive species and ecosystems. - Define biodiversity impact indicators for sensitive species and ecosystems to be monitored during project implementation. - Define baseline values and targets for sensitive species and ecosystems. |
| Socioeconomic expert | 585 | 10 (GEF) 14 (Cof) | - Develop preliminary socioeconomic analyses of target PAs. - Perform stakeholder analyses for target PAs. - Assess training needs and targets for CONAP and PA managers to implement environmental and social safeguards for ecotourism. - Assess training needs and targets for PA administrators managing visitors and providing them with the appropriate services. |
| PA finance specialist | 585 | 6 (GEF) 14 (Cof) | - Assess target PAs’ financial status, including management costs and financial needs and gaps. - Assess income generation and allocation mechanisms, particularly those related to revenue from ecotourism (i.e., gate and concession fees collection and allocation). - Evaluate the status of the management and business plans for each of the existing PAs, identifying the needs and limitations based on their ecotourism potential and conservation goals. |
| Subtotal local consultants |  | 48 (GEF) 102 (Cof) |  |
| International Environmental M&E specialist | 2,500 | 12 (GEF) | - Review and structure existing data and methodologies for development of key outputs. - Develop an M&E plan, including baseline analysis, project indicators, methodologies, and protocols for the collection and systematization of information. - Develop a monitoring strategy for financial sustainability of the PAs. - Determine whether databases and technical analyses can be appropriately adapted to the scope, scale, and needs of project stakeholders and the implementer. - Provide overall orientation to PPG team in relation to GEF logic and information requirements. - Develop incremental cost matrices. - Perform final review and definition of strategic work plan and cost-efficiency analysis. |

Project ID number will be assigned by GEFSEC.  If PIF has already been submitted, please use the same ID number as PIF.