## Workplan
Project Components | Project Outcomes | Project Outputs | Activities |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1. Strengthening of institutional capacity for GMO surveillance, monitoring and detection. | 1.1 National laboratories strengthened to provide GMO detection support and related post approval monitoring activities. | 1.1.1 Diagnosis of the installed capacity and of trained human resources in detection of GMOs. | 1.1.1.1 Consultancy analysis of lab capacities in terms of personnel and equipment. | NPC | bar: Year 1 Q1 to Year 1 Q2
[7 empty] | x | x
|  | 1.1.2 Based on the evaluation of results of 1.1.1, at least two national laboratories selected and strengthened to play the role of national reference laboratory. | 1.1.2.1 Definition of evaluation criteria that will orient the selection of two national labs, and conduct such evaluation through the NCAs. (to be done under 1.1.1.1 consultancy) | bar: Year 1 Q3 to Year 1 Q4
1.1.2.2 Stregthen the select labs in terms of technical capacities (purchase of equipment). | bar: Year 2 Q1 to Year 2 Q3
|  | 1.1.3 Harmonized Toolkits/ Guidelines/ Protocols/ Standard Operating Procedures (SOPs) on GMO detection developed and/or adapted to suit Guatemala´s reality. | 1.1.3.1 Checking of procedures already used in other international GMOs detection labs. | bar: Year 1 Q4 to Year 2 Q1
1.1.3.2 Identification of sampling and detection methods seeking to respond to already agreed presence umbral levels. | bar: Year 2 Q1 to Year 2 Q3
1.1.3.3 Homologation and adaptation of procedures in national labs. | bar: Year 2 Q2 to Year 2 Q4
|  | 1.1.4 Training programme on GMO detection established (e.g. workshops and manuals). | 1.1.4.1 (3) development of workshops including, schedules and programme, and manuals. | bar: Year 2 Q3 to Year 2 Q4
[13 empty] | x | x
| 1.2 Agreements for collaborative networking established between national and international labs. | 1.2.1 Inter-Laboratory cooperation MoUs developed and signed (to facilitate interaction and promote a cost-benefit approach between national and regional laboratories). | 1.2.1.1 Consultancy development of interinstitutional cooperation memorandums among national and international labs. | NPC | bar: Year 2 Q4 to Year 3 Q2
1.2.1.2 Signing of cooperation agreements among national and international labs for tackling special GMOs detection cases. | bar: Year 3 Q3 to Year 4 Q1
| 1.3 Country able to implement biosafety monitoring and surveillance measures. | 1.3.1 Operative guidelines and clear roles and responsibilities for a monitoring and surveillance system developed (using as a base the early developments done during the implementation projects). | 1.3.1.1 Development of operative guidelines in monitoring and surveillance and revision of the definition of roles and responsibilities. | bar: Year 1 Q3 to Year 2 Q1
1.3.1.2 Submission of the revised monitoring and surveillance system to the competent authorities for its final approval. | bar: Year 2 Q2 to Year 2 Q3
1.3.1.3 Support the implementation of the national monitoring system. | bar: Year 2 Q4 to Year 4 Q4
|  | 1.3.2 Strategy for field detection (screening procedure) developed. | 1.3.2.1 Develop the strategy for field detection. Evaluating biotechnological events approved in surrounding countries. | bar: Year 1 Q3 to Year 2 Q1
1.3.2.2 Acquisition of tools (strips) for field detection. | bar: Year 2 Q1 to Year 2 Q2
1.3.2.3 Training in field detection techniques for inspectors. | bar: Year 2 Q3 to Year 2 Q4
|  | 1.3.3 Administrative and technical guides designed for each institution involved in the National Custom System. | 1.3.3.1 Review and update the baseline on the current situation of customs regarding their role on CP. | bar: Year 1 Q3 to Year 2 Q1
1.3.3.2 Develop technical and administrative guidelines for each institution. | bar: Year 2 Q1 to Year 2 Q3
|  | 1.3.4 Workshops (4) for custom officers on monitoring and surveillance. | 1.3.4.1 Conduct workshops according to the needs identified in the diagnostic 1.3.3. | bar: Year 2 Q4 to Year 3 Q2
Component 2. Strengthening of administrative and technical biosafety system of the National Competent Authorities (NCAs) in line with article 2.1 of the CPB. | 2.1 System in place for handling of requests, for GMOs in place (including digital system connecting all competent authorities). | 2.1.1 Sectorial regulations and their respective implementation tools for biosafety regulation, developed during the previous Implementation Project, tested and submitted for approval. | 2.1.1.1 Socialize through workshops with each competent authorities, individualized and interinstitutional where appropriate. | bar: Year 1 Q2 to Year 1 Q4
|  |  | 2.1.1.2 Conduct a practical exercise in each NCA. | NPC | bar: Year 2 Q1 to Year 3 Q4
2.1.1.3 Legalization of procedures in each of the authorities. | bar: Year 2 Q3 to Year 2 Q4
2.1.1.4 Institutionalization of the system components. | bar: Year 2 Q4 to Year 3 Q2
|  | 2.1.2 Digital system for managing GMO applications in place and connecting all competent authorities as a single window for processing applications. | 2.1.2.1 Design and creation of a comprehensive platform inter institutional linked and under the BCH umbrella. | bar: Year 1 Q4 to Year 2 Q4
2.1.2.2 Test of the platform through mock excersise. | bar: Year 2 Q4 to Year 3 Q2
2.1.2.3 Launch of the platform. | bar: Year 3 Q3
|  | 2.1.3 Hands on training for the NCA´s personnel (2 mock exercises on how to process dossiers using the new digital system system). | 2.1.3.1 Conduct technical workshops with the main stakeholders. | bar: Year 3 Q4 to Year 4 Q2
2.1.3.2 Conduct mock request seeking to test the administrative and technical system. | bar: Year 2 Q4; Year 3 Q2; Year 4 Q3
2.1.2.3 Participation of technical personnel on international forums, fellowships and training opportunities. | bar: Year 2 Q4; Year 3 Q4; Year 4 Q3
Component 3. Developing capacities on liability and redress (Article 27) and socioeconomic considerations (Article 26). | 3.1 Guatemala moved towards ratification of the Nagoya - Kuala Lumpur Protocol. | 3.1.1 Draft NKLP ratification document for ratification by the relevant authority. | 3.1.1.1 Development of draft proposal of ratification. | bar: Year 1 Q4 to Year 2 Q1
3.1.1.2 Consensus-building and integration of observations of the proposal for ratification. | bar: Year 2 Q1 to Year 2 Q3
|  | 3.1.2 Proposal on how to include and manage liability and redress (L&R) issues in the current biosafety administrative system. | 3.1.2.1 Submission to NCAs for further discussion and future adoption. | bar: Year 2 Q3 to Year 2 Q4
3.1.2.2 Presentation and lobbying to the Presidency and Congress seeking to get final approval. | bar: Year 3 Q1 to Year 3 Q2
| 3.2 Guatemala takes into account socio economic considerations in GMO decision-making. | 3.2.1 Study of the existing national and regional approaches related to the use of socioeconomic consideration in decision making. | 3.2.1.1 Generation of databases at national and international level relating to costs of production, and profitability, both conventional crops and GM crops; possible social effects by shifting from conventional crops to GM crop. | bar: Year 1 Q1 to Year 1 Q2
3.2.1.2 Studies based on the collected statistics (incidence in yields, costs, improvements, among others) to forecast the probable effects of using the new technologies. | bar: Year 1 Q3 to Year 1 Q4
3.2.1.3 Study of existing national and regional laws and regulations related to the use of socio-economic considerations in the decision making. | bar: Year 2 Q1 to Year 2 Q2
|  | 3.2.2 Analysis of the technical and legal implications of the implementation of article 26 of the CPB. | 4.3.2.1 Workshops with personnel from NCAs and other relevant stakeholders to know and discuss technical and methodological aspects regarding socioeconomic considerations. | bar: Year 2 Q1; Year 2 Q4; Year 3 Q3; Year 4 Q2
|  |  | 4.3.2.2 Hypothetical case study: maize. | NPC | bar: Year 2 Q4
4.3.2.3 Socialization of the results of the studies with policy makers and national authorities. | bar: Year 2 Q4 to Year 3 Q1
4.3.2.4 Public awareness between the decision-makers and other actors (technical workshops and regional meetings). | bar: Year 3 Q2 to Year 3 Q3
Component 4. Conservation of native biodiversity in support of biosafety related activities. | 4.1 Protection of native genetic resources of agricultural importance (e.g. maize) is increased through the application of biosafety measures. | 4.1.1 Maize baseline data (morphologic, genetic, socioeconomic and distribution of wild maize) is strengthened through support of ongoing research initiatives and data gathering activities. | 4.1.1.1 Identification of research projects planned or in development, related to the subject. | NPC partially | bar: Year 1 Q3 to Year 1 Q4
4.1.1.2 Establishment of agreements with the research institutions in charge of the projects. | bar: Year 1 Q4 to Year 2 Q1
4.1.1.3 Implementation of the research projects jointly with partner institutions. | bar: Year 2 Q1 to Year 3 Q4; Year 4 Q3
4.1.1.4 Report of key findings to the national competent authorities. | bar: Year 3 Q4 to Year 4 Q1
|  | 4.1.2 Normative framework, defining GMO´s free zones, is drafted. | 4.1.2.1 Two workshops to discuss scientific methodology to define center of origin and diversity. | bar: Year 2 Q1; Year 3 Q1
4.1.2.2 Consultation with local communities. | bar: Year 2 Q2 to Year 3 Q1
4.1.2.3 Drafting of the strategy on GMO free zones. | bar: Year 3 Q2 to Year 3 Q3
| 4.2 There is a clear link between biodiversity protection and biosafety actions. | 4.2.1 A maize genetic reserve is established in Huehetenango region based on systematization of information from 4.1.1 and land use regulations. | 4.2.1.1 Analysis of available information regarding distribution of wild maize, genetic diversity, land use regulation. | NPC partially | bar: Year 1 Q2 to Year 1 Q4
4.2.1.2 Characterization of the socio-economic aspects of the population in the distribution area of wild maize based on information already gathered by other institutions as a key element to be included in the new in situ reserve. | bar: Year 1 Q3 to Year 2 Q1
4.2.1.3 Development of the proposal for the establishment of an in situ maize reserve. | bar: Year 2 Q1 to Year 2 Q3
4.2.1.3 Lobbying activities with competent authorities and stakeholders to promote the establishment of the genetic reserve. | bar: Year 2 Q2 to Year 3 Q4
Component 5. Project Monitoring and Evaluation | 5.1 Effective project management, coordination, and delivery with project impacts and global benefits assessed. | 5.1.1 Establishing the Project Team. | 5.1.1.1 Hiring of project personnel. | bar: Year 1 Q1
5.1.1.2 Establishment of project offices. | bar: Year 1 Q1
|  | 5.1.2 Project M&E measures implemented. | 5.1.2.1 Task Force meetings. | bar: Year 1 Q2; Year 1 Q4; Year 2 Q2; Year 2 Q4; Year 3 Q2; Year 3 Q4; Year 4 Q2; Year 4 Q4
5.1.2.2 Elaboration of expenditure and progress reprots, and finacial audits. | bar: Year 1 Q3 to Year 1 Q4; Year 2 Q3 to Year 2 Q4; Year 3 Q3 to Year 3 Q4; Year 4 Q3 to Year 4 Q4
|  | 5.1.3 Meetings of the Steering Committee. | 5.1.3.1 Bi-annual SC meetings. | bar: Year 1 Q1; Year 1 Q4; Year 2 Q2; Year 2 Q4; Year 3 Q2; Year 3 Q4; Year 4 Q2; Year 4 Q4
|  | Mid-Term and Terminal evaluation of project. | 5.1.3.2 Carry out independent evaluations. | bar: Year 2 Q4; Year 4 Q4

## Supervision plan
Project Title: Strengthening and expansion of capacities in biosafety that lead to a full implementation of the Cartagena Protocol on Biosafety in Guatemala
Project number:
Project implementation period (add additional years as required): 4 yrs
|  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
| Month | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d
| Mth no | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
Executing partner
UNEP/DEPI | bar: Month
Joint responsibility
Activity/Task/Output
Project Management, Coordination & Sustainability
Inception meeting and report of meeting | bar: Year 1 j to Year 1 f
Progress report - Dec 31 + 30 days | bar: Year 1 j; Year 1 d; Year 2 a; Year 2 d; Year 3 j; Year 3 d; Year 4 j; Year 4 d
Annual audit report - Dec 31 + 180 days | bar: Year 1 d; Year 2 d; Year 3 d; Year 4 d
Expenditure reports (including co-finance reprot) - Dec 31, March,31, June 30, Sep 30 (+ 30 days) | [49 empty] | x | bar: Year 1 a; Year 1 j; Year 1 o; Year 2 j; Year 2 a; Year 2 j; Year 2 o; Year 3 j; Year 3 a; Year 3 j; Year 3 o; Year 4 j; Year 4 a; Year 4 j; Year 4 o
Establish M&E system | bar: Year 1 j to Year 1 f
Annual non-expendable equipment inventory - update 31 Dec (+ 30 days) | bar: Year 1 j; Year 2 j; Year 3 j; Year 4 j
Review of project workplan (annual) | bar: Year 1 j; Year 2 j; Year 3 j; Year 4 j
Mid-term review/evaluation | bar: Month; Year 2 j to Year 2 m
Training workshops/seminars (*)
Procurement of equipment & hiring of consultants (**)
Progress reports to co-financiers (**)
Project brochure/newsletter/banner | bar: Year 1 j to Year 1 f
Project Implementation Review | [49 empty] | x | bar: Year 1 j; Year 2 j; Year 3 j; Year 4 j; Year 4 d
PSC/PMC meetings + minutes of meetings (*)
GEFSEC communications (Inception, midterm & completion) | [49 empty] | x | bar: Month to Year 1 f; Year 2 d to Year 3 j
Site visits + mission reports (**) | bar: Month
Technical substantive completition | [49 empty] | x
Final report + outputs | [49 empty] | x
Completition revision | [49 empty] | x | bar: Month
Terminal evaluation | [49 empty] | x
Final audit report for project | [49 empty] | x
* Will be adjusted according to annual workplan, starting at inception
** as required