Project Document

Government of Guinea-Bissau and UNDP

Executing Agency / Implementing Partner: Institute for Biodiversity and Protected Areas (IBAP) of the State Secretariat for Environment (SEA); Directorate General for Forests and Fauna (DGFF) of the Ministry of Agriculture and Rural Development (MARD)

United Nations Development Programme

UNDP Project ID PIMS 5177 / GEF Project ID PMIS 5368

Strengthening the financial and operational framework of the national PA system in Guinea-Bissau

Brief description

The objective of this project is to strengthen the financial sustainability and management effectiveness of the national protected areas system (SNAP) in Guinea-Bissau. Building upon the results of previous GEF interventions, baseline programs, and projects, and coordinating with ongoing and other donor-funded projects, the project will pursue two interlinked approaches: (i) increasing revenue generation for the SNAP by lifting barriers that impede full functioning of the BioGuinea Foundation (FBG), achieving short-term endowment capitalization targets with project co-financiers and putting in place the foundations for the achievement of medium- and long-term targets; and (ii) strengthening effective protected area (PA) management by the Institute for Biodiversity and Protected Areas (IBAP) to a critically threatened priority PA (Cantanhez National Park, CNP), while developing new operational frameworks that entail enhanced efficiencies through the involvement of the Directorate General for Forests and Fauna (DGFF) and local stakeholders. The project will contribute to the conservation of 952,172 hectares (ha) of critical natural habitats through the long-term financial sustainability of Guinea-Bissau’s national network of PAs, which will cover 26% of the country. The extensive and highly productive mangrove ecosystems are critical contributors to the sub-region’s marine productivity as they support globally endangered and threatened species and a variety of migratory birds, as well as sequestering significant carbon stocks. The woodland savannah, semi-dry tropical forest, and the critically endangered primary tall sub-humid tropical forests are home to threatened and endangered species of global importance that are typical of the Guinea Savannah Forest Mosaic and play critical roles as biological corridors and migration routes for large mammals. Other global environmental benefits will be derived from achieving strengthened management capacity coupled with financial sustainability at the PA system level. More specifically, by project end the initial capitalization of the endowment of the FBG with USD 7,365,248 will increase the sustainability of the SNAP by providing a flow of stable and sustainable financing equivalent to approximately 30% of the overall annual recurrent funding needs, and by so doing will contribute to the consolidation of the terrestrial PAs of Guinea-Bissau. In addition, collaborative cost-effective management of the critically threatened priority PA, the CNP and its related forest areas and buffer zones, will improve management effectiveness by 20% and will reduce the loss of threatened West African forest habitats across 105,800 ha.

SIGNATURE PAGE	Country: GUINEA BISSAU

Project Title: Strengthening the financial and operational framework

of the national PA system in Guinea-Bissau

2008-2012 UN Development Assistance Framework Outcome (s)/Indicator (s):

Effet UNDAF 1: les institutions gouvernent dans le respect des Droits Humains, pour la consolidation de l’Etat de droit et selon les principes de gestion transparente et efficiente des  ressources du pays.

Effet Programme 2 : la société civile est renforcée et la modernisation de l’administration publique amorcée en vue d’une gestion transparente et efficace des ressources du pays.

Produit 2.2 : les capacités de l’administration publique sont renforcées en vue d’une gestion efficiente et transparente des ressources du pays.

Effet UNDAF 2 : Les populations, les institutions et les organisations développent le secteur privé et la création d’emplois par l’amélioration des systèmes de production, la diversification des activités, contribuent à la réduction de la pauvreté et gèrent de façon durable l’environnement

Effet Programme 3 : Les capacités des institutions nationales des OCB et des entreprises pour l’application des principes et des normes de gestion des ressources naturelles et de l’environnement sont renforcées

Produit 1.3 : les capacités des Institutions nationales, les entreprises et les OCB du secteur de l’environnement sont renforcées en matière d’élaboration, d’application et de surveillance de la législation et des normes pour prévenir les dégradations de l’environnement et des ressources naturelles.

Expected Country Programme Outcome(s) (2008-2012; extended to be effective until end 2015):

PRIORITE NATIONALE: favoriser la croissance économique et la création d’emplois

Effet recherché 3: les ménages, surtout les plus pauvres et les organisations communautaires de base (OCB) adoptent des systèmes de production respectant les normes de gestion des ressources naturelles et de l’environnement.

Produit 10. Sensibiliser davantage la population et les OCB et actualiser et appliquer la législation prévenant les dégradations volontaires sur l'environnement et les ressources.

Produit 11. Renforcer les capacités de surveillance des structures nationales de coordination du secteur de l'environnement.

Expected UNDP IIRF Output(s)/Indicator(s) to be monitored by UNDP including UNDP Country Office:

Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem  services, chemicals and waste

Indicator 1.3.1:  Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or sub-national level

Sub-indicator 1.3.1.A.1.1.  Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or sub-national level

Output 2.5: Legal and regulatory frameworks, policies and institutions enabled  to ensure the  conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation

Indicator 2.5.1. Extent to which legal, policy and institutional frameworks are in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems

Sub-indicator 2.5.1.C.1.1: Extent to which institutional frameworks are in place for conservation, sustainable use, and/or access and benefit sharing of natural resources, biodiversity and ecosystems

Executing Entity/Implementing Partner: Institute for Biodiversity and Protected Areas (IBAP)

| Project duration | 48 months |  | Total Project Resources: | $18,989,677 |
| --- | --- | --- | --- | --- |
| ATLAS Award ID: | 00087219 |  | Total resources in TBW: | $2,674,429 |
| ATLAS Project ID: | 00094321 |  | GEF | $2,304,429 |
| GEF PMIS #: | 5368 |  | UNDP (TRAC) | $370,000 |
| UNDP PIMS #: | 5177 |  | Others: |  |
| Mgt Arrangement: | NIM |  | Government of Guinea Bissau | $4,645,760 |
| PAC Meeting Date: |  |  | European Union | $9,360,000 |
|  |  |  | MAVA Foundation | $1,619,488 |
|  |  |  | The World Bank Group | $690,000 |

| Agreed by (Government): | Date/Month/Year: |
| --- | --- |
| NAME: | Signature |

| Agreed by (Executing Entity/Implementing Partner): | Date/Month/Year: |
| --- | --- |
| NAME: | Signature |

| Agreed by UNDP: | Date/Month/Year: |
| --- | --- |
| NAME: | Signature |

Table of Contents

SECTION I: Elaboration of the Narrative	7

PART I: Situation Analysis	7

I.1. Context and global significance	7

I.2. Threats, root causes, and impacts	15

I.3. Long-term solution and the barriers to achieving this solution	19

I.4. Stakeholder analysis	21

I.5. Baseline analysis	23

PART II: Strategy	27

II.1. Project Rationale and Policy Conformity	27

II.2. Project Goal, Objective, Outcomes, and Outputs/activities	28

II.3. Project Risks	40

II.4. Cost-effectiveness	42

II.5. Project consistency with national priorities/plans:	44

II.6. Country ownership: Country eligibility and Country Drivenness	45

II.7. Sustainability and Replicability	45

PART III: Management Arrangements	48

III. 1. Project implementation arrangement	48

III. 2. Financial and other procedures	49

PART IV: Monitoring Framework and Evaluation	50

IV.1. Monitoring and reporting	50

IV.2. Audit Clause	53

PART V: Legal Context	53

SECTION II: Strategic Results Framework (SRF) and GEF Increment	55

PART I: Strategic Results Framework Analysis	55

I.1. Programmatic Links	55

I.2. Indicator framework as part of the SRF	56

PART II: Incremental Reasoning and Cost Analysis	60

SECTION III: Total Budget and Work Plan	63

SECTION IV: Additional Information	67

PART I: Letters of co-financing commitment	67

PART II: Stakeholder Involvement Plan and Coordination with other Related Initiatives	76

PART III. Terms of References for key project staff	79

SECTION V: PROJECT ANNEXES	81

Annex 1: Capacity Assessment	81

Annex 2. UNDP Social and Environmental Screening	83

Annex 3. Example for CF Guiding Principles	84

Annex 4. Rapid Assessment Result of BioGuinea Foundation (Fundação Bioguine) to Inform the Design of Component 1 of GEF/UNDP GEF 5 Project	86

Annex 5. Project Risk Analysis	102

Annex 6. BD-1 Tracking Tools: METTs and Financial Sustainability Scorecard	106

Acronyms

ACAP-Cantanhez 	Associação dos camponeses da Area Protegida de Cantanhez

AD 	Ação Para O Desenvolvimento

APAMIC 	Association des producteurs de mangues et ananas d’Iemberem et Cambèque

AWP	Annual Work Plan

°C	Degrees Celsius

CAIA 	Unit for the Evaluation of Environmental Impacts

CBD	Convention on Biological Diversity

CBMP	Coastal and Biodiversity Management Project

CBO	Community-Based Organization

BCP 	Biodiversity Conservation Project

CAFÉ	Consortium of African Funds for the Environment

CFA 	Conservation Finance Alliance

CNP 	Cantanhez Forest National Park

CO	(UNDP) Country Office

CODECECAS 	Cooperativo, Centro Para o Desenvolvimento dos camponeses do Sul

COP	Conference of Parties

CPAP	Country Programme Action Plan

CR	Critically Endangered

CSO	Civil Society Organization

CTF 	Conservation Trust Fund

DGA	Directorate General for the Environment

DGFF 	Directorate General for Forests and Fauna

DIVUTEC 	Associação Guineense de Estudos e Divulgação das Tecnologias Apropriadas

EC 	European Commission

EEZ	Exclusive Economic Zone

EIA 	Environmental Impact Assessment

EN	Endangered

ERC	(UNDP) Evaluation Resource Centre

ESSP	(UNDP) Environmental and social screening procedure

EU	European Union

EUR 	Euros

FBG	BioGuinea Foundation

FFEM 	Fonds français pour l'environnement mondial

FIAL 	Fund for Local Environmental Initiatives

FUNBIO 	Fundo Brasileiro para a Biodiversidade

GCCA+	Global Climate Change Alliance+

GDP	Gross Domestic Product

GEF	Global Environment Facility

GIS	Geographical Information System

GoGB	Government of Guinea-Bissau

GPC	Office of Coastal Planning

ha	Hectare

HACT 	Harmonized Approach to Cash Transfer

HDI	Human Development Index

IBA	Important Bird Area

IBAP	Institute for Biodiversity and Protected Areas

IDA 	International Development Association

IUCN 	International Union for the Conservation of Nature

km	Kilometre

KPI	Key Performance Indicator

LU/LC	Land Use/Land Cover

M&E	Monitoring and Evaluation

MARD 	Ministry of Agriculture and Rural Development

METT	Management Effectiveness Tracking Tool

mm	Millimetre

NAPA	National Adaptation Plan of Action

NGO	Non-Governmental Organization

NIM	National Implementation Modality

NSPAB	National Strategy for Protected Areas and Biodiversity Conservation

NT 	Near threatened

NTFP	Non-Timber Forest Product

PA 	Protected Area

PIR	Project Implementation Report

POL 	Operational Development Partners

PPG 	Project Preparation Grant

PSC	Project Steering Committee

RCU	(UNDP) Regional Coordinating Unit

REDD 	Reduced Emissions from Deforestation and Forest Degradation

RTA	(UNDP) Regional Technical Adviser

SBAA	Standard Basic Assistance Agreement

SEA 	State Secretariat for Environment

SNAP 	National System of Protected Areas

SRF 	Strategic Results Framework

TRAC 	(UNDP) Target for Resource Assignment from the Core funds

TBW	Total Budget and Work plan

TINIGUENA 	Associação de Promoção do Desenvolvimento Participativo na Base e Gestão Durável dos Recursos Naturais

TORs	Terms of Reference

UNDP	United Nations Development Programme

UNDAF	United Nations Development Assistance Framework

UNESCO	United Nations Educational, Scientific, and Cultural Organization

UNFCCC 	United Nations Framework Convention on Climate Change

UNOPS 	United Nations Office for Project Services

USD	U.S. Dollars

VCS 	Voluntary Carbon Standard

VU	Vulnerable

WAMER 	West African Marine Ecoregion Project

WCMC	World Conservation Monitoring Center

WWF 	Worldwide Fund for Nature / World Wildlife Fund

# SECTION I: Elaboration of the Narrative

## PART I: Situation Analysis

### I.1. Context and global significance

- Introduction

The Government of Guinea-Bissau (GoGB) is seeking the support of the Global Environment Facility (GEF) for a well-funded National System of Protected Areas (SNAP) that conserves biodiversity of global importance in Guinea-Bissau through protected areas (PAs) that are effectively managed and sustainable under nationally mandated standards to meet conservation goals in a cost-effective manner. Building upon the results of previous Global Environment Facility (GEF) interventions and coordinating with ongoing and other donor-funded projects, the project will pursue two interlinked approaches: a) increasing revenue generation for the SNAP by lifting barriers that impede the full functioning of the BioGuinea Foundation (FBG) as an independent conservation trust fund, achieving short-term endowment capitalization targets together with project co-financiers and putting into place the foundations for the achievement of medium- and long term-targets, and thereby providing sustainable financing for biodiversity conservation activities in Guinea-Bissau in perpetuity; and b) strenthening the effective PA management by the Institute for Biodiversity and Protected Areas (IBAP) to a critically threatened priority PA (Cantanhez National Park [CNP]) while developing new operational frameworks entailing enhanced efficiencies through the involvement of the Directorate General for Forests and Fauna (DGFF) and local stakeholders.

- National Context: Socio-economic, Environment, Biodiversity

Guinea-Bissau is a small country in West Africa with a total area of 36,125 square kilometers (km2) and an estimated population of 1,700,000 inhabitants. It is one of the poorest countries in the world (70% of the population live below the national poverty line and 33% live in extreme poverty) and has one of the lowest Human Development Index (HDI) scores (0.396, 2013) as well as the lowest life expectancy (54 years at birth) and literacy rate (57%) indicators. The inequality of income distribution is one of the most extreme in the world and a short and violent civil war in 1998 destroyed most of its productive infrastructure. In recent years, the country has experienced prolonged periods of political and institutional instability. However, successful elections held in April and May 2014 have paved the way for a political renewal and hopefully also economic recovery; the gross domestic product (GDP) is expected to grow by 2.6% in 2014 and 4% in 2015.

Agriculture is the predominant sector of the country’s economy and is the source of occupation for approximately 82% of the population. The agricultural sector contributes approximately 93% of the total value of exports and approximately 50% of the GDP, and is structured around the production of rice, cashews, peanuts, and livestock. The bulk of agricultural exports consists of cashews and peanuts. After cashews, rice is the second most relevant crop and has a crucial role for food security. Livestock raising is practiced throughout the country and integrates all systems of agricultural production. Guinea-Bissau is a country with a vast expanse of coastal area, estimated at 22,235 km² (equivalent to 61% of the country’s area) and where 80% of the country’s population live. The coastline of Guinea-Bissau extends approximately 170 kilometers (km). Fisheries is favored by a low-depth continental shelf, by the extension of the maritime front, and the existence of the Bijagos Archipelago marine delta. The country’s Exclusive Economic Zone (EEZ) has important commercial-value fishery resources in which traditional and industrial fishing are practiced. Fish and shellfish are the primary sources of animal protein at the national level, and these sources are economically important and provide food security for the majority of the poorest rural populations. Fishery resources are also important sources of foreign exchange inflows through licensing and financial compensation resulting from agreements with foreign industrial fishing vessels operating legally in the country’s waters. In 2010, the fisheries sector generated at least 14 million USD of revenue for the GoG, essentially paid by foreign fleets for fishing access. The sector annually contributes between 25-40% of government revenue and 3.9% of exports.

Guinea-Bissau possesses rich cultural diversity with five major ethnic groups as well as a wealth of natural resources. Almost a quarter of the country’s territory is marine and its coastal region is a vast expanse of mangroves, islets, and estuarine environments. Wedged between Senegal to the north and Guinea Conakry to the south and east, Guinea-Bissau constitutes a transition zone between sub-Saharan arid savannah ecosystems and more humid tropical forest ecosystems. The country has a tight mesh of small river basins and associated freshwater ecosystems. Its landscape boasts a great diversity of plant and animal species in its rich coastal and marine ecosystems, the savannahs in the north and northeast, and forests in the south and southeast. Guinea-Bissau’s natural habitats form an ecological bridge that allows species migrations, an ecosystemic feature that is especially critical in the face of changing climate conditions.

The climate in Guinea-Bissau is tropical. Most of the country receives 1,500 to 2,000 millimetres (mm) of rain annually, with the average amount of rainfall in excess of 2,000 mm. Rainfall is highly seasonal, with a 7-month dry season lasting from November to May. The climate is warm year-round with little fluctuation of temperatures (25 degrees Celsius [°C] to 28°C). The terrain of Guinea-Bissau is mostly a low coastal plain in the west rising to a forest-savanna mosaic in the east. Given that Guinea-Bissau phytogeographically lies in the Guineo-Congolesa/Sudanesa Regional Transition Zone, it is home to a great diversity of flora. Existing surveys indicate that there are at least 1,618 species of vascular plants and bryophytes. Similarly, the fauna of Guinea-Bissau, although still relatively little-studied, is extremely rich. Over 1,000 species of vertebrates have been recorded, including 132 species of mammals distributed in 12 orders, and 456 species of birds, including nine globally threatened species (4 Endangered [EN], 5 Vulnerable [VU]).

Guinea-Bissau harbours globally significant biodiversity in two major biomes: the coastal and marine complex and the forest belt. The former is host to exceptional biodiversity, due to its landscape featuring the extensive interpenetration of terrestrial and marine/aquatic environments, including vast estuaries, a large archipelago rising from the continental shelf, and seasonally flooded coastal plains. Guinea-Bissau’s coastal and marine habitats are indeed among West African’s richest in terms of biodiversity and home to one of the most productive remaining fisheries in the world. The country’s waters contain a high level of diversity (fish, crustaceans, mollusks); it was recently estimated that demersal species represent a biomass of 479,000 tons (58% bony fish, 15% skate, 15% shark, 3% crustacean, 6% cephalopod, 1.8% gasteropod, 0.9% echinoderm). Key aquatic species of global importance include the Large-tooth Sawfish (Pristis perotteti, Critically Endangered [CR]), the Common Sawfish (Pristis pristis, CR), the Goliath Grouper (Epinephelus itajara, CR), the Bottlenose Skate (Rostroraja alba, EN), the West African Manatee (Trichechus senegalensis, VU), a unique population of sea-going Hippopotamus (Hippopotamus amphibius, VU), and five species of marine turtles (all globally threatened). The Green Turtle (Chelonia mydas, EN) nesting site in the João Vieira and Poilão Marine PA is recognized as the largest in West and Central Africa and the third largest in the Atlantic. The Bijagos Archipelago, classified as a Biosphere Reserve by the United Nations Educational, Scientific, and Cultural Organization (UNESCO), has recently been proposed also as a World Heritage site. It is one of the foremost locations for migratory water birds in West Africa, and is said to host 1% of the total global bird population during the winter. All of the country’s coastal and marine PAs are identified as Important Bird Areas by Birdlife International. The Cufada Lagoons Natural Park has been designated as a wetland site of international importance under the Ramsar Convention and several other potential sites in Guinea-Bissau are currently being assessed.

In the south and southeast, the continental portion of the country features the Forest Belt region that is equally important in terms of global and regional biodiversity. It is characterized by patches of dense forests and open forests, predominantly intertwined with woodland savannahs that are rich in globally significant plant and animal life and serve as refuge for many migratory species that move across the West African savannahs. The Forest Belt contains or has contained several endemic and rare and threatened species of birds, higher plants, reptiles, and mammals, including the African Wild Dog (Lycaon pictus, EN), African Dwarf Crocodile (Osteolaemus tetraspis, VU), Lion (Panthera leo, VU), and African Elephant (Loxodonta africana, VU); and large ungulates such as the African Buffalo (Syncerus caffer), Hippopotamus (Hyppopotamus amphibious, VU), and Eland (Taurotragus derbianus). Dozens of families of chimpanzees (Pan troglodytes, EN) inhabit that area and as of yet are poorly studied. Other threatened primates include the Sooty Mangabey (Cercocebus atys, VU), the West African Red Colobus (Procolobus badius, EN), and the King Colobus (Colobus polykomos, VU). With habitat fragmentation and pressures on natural resources increasing throughout West Africa, areas such as the Forest Belt of Guinea-Bissau are rapidly becoming critical refuges for emblematic and threatened species that provide important national and transnational biological corridors and migration routes for large mammals in the region.

The country’s ecosystems not only support a wealth of biodiversity but also provide valuable services to the country’s population. The coastal zone, in particular the 338,652 hectares (ha) of mangrove ecosystems—Guinea-Bissau is 12th among countries at the global level with the highest rates of mangrove coverage and second in Africa after Nigeria—serves as nursery and breeding grounds for commercially valuable fish stocks; provides carbon stocks and sequestration capacities that could be sold on the global market; and buffers against potential sea level rise and storm surges resulting from climate change. The terrestrial forest and savannah woodlands also provide a variety of goods and services to local populations, such as food, shelter, traditional medicinal plants, and fuel. For example, a recent study reported 85 species of useful plants in the Canhabaque and João Vieira Poilão Marine National Park.  The terrestrial forest and savannah woodlands also contribute to ensuring supplies of clean water and resilience against climate change. The biological and ethnic diversity that characterize the country have given rise to the emergence of rich cultural traditions, notably in the Bijagós Archipelago, and these biodiversity, ecological and/or cultural characteristics are recognized to be of both national and international significance.

- SNAP: Current status and coverage

The GoGB has made significant advances to address the threats to biodiversity by bringing critical areas under protection through a SNAP. However, the conservation status and associated investments in the coastal and marine biome and the terrestrial biome have been heterogeneous. First efforts were focused on setting up and managing vulnerable marine and coastal PAs. The first national park was established in 1997. IBAP was created in 2004/2005 with the explicit authority and responsibility to protect and manage Guinea-Bissau’s biodiversity endowment through the SNAP. By 2011, six protected areas had been legally decreed, providing protection to 545,615 ha of valuable ecosystems and their species (15.1% of national territory; see Table 1 and Figure 1) in the southeast of the country; this included CNP, established in 2011. With the critical marine and coastal areas under increasing protection and institutional capacity within IBAP on the rise, attention then moved to the terrestrial ecosystems in the country’s south-eastern interior. The process to establish the first purely terrestrial PAs in Guinea-Bissau is led by the ongoing UNDP/GEF project supporting the consolidation of PAs in the Forest Belt (GEF ID 3575, UNDP ID 3650). This project is contributing to correct the skew in the representativeness and connectivity of the SNAP by supporting the establishment of two inland PAs (Boé National Park and Dulombi National Park) and three biological corridors (Tchetche, Cuntabane-Quebo, and Salifo) linking these to each other in the Forest Belt, but also to already-existing coastal PAs including CNP. Through this ongoing UNDP/GEF-supported project an additional 406,557 ha (11.3%) of the country will have come under protective management by 2014/2015. This will bring the total PA coverage to 952,172 ha (26.4%) of the national territory – a significant achievement in less than two decades.

Table 1 – Existing Protected Area Coverage in Guinea-Bissau (Source: IBAP 2014: Estratégia Nacional para as Áreas Protegidas e a Conservação da Biodiversidade na Guiné-Bissau 2014-2020).

| Name of PA (in Portuguese) | Type of PA | International Designation | Area (ha) | % of Territory | Responsible Institution | Legal Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Parque Nacional das Ilhas de Orango | National Park | Biosphere Reserve | 158,200 | 4.4% | IBAP | Decree-Law No. 11/2000 |
| 2. Parque Natural dos Tarrafes de Cacheu | National Park |  | 88,615 | 2.5% | IBAP | Decree-Law No. 12/2000 |
| 3. Parque Natural das Lagoas de Cufada | National Park | RAMSAR site | 89,000 | 2.5% | IBAP | Decree-Law No. 13/2000 |
| 4. Parque Nacional Marinho de João Vieira e Poilão | National Park | Biosphere Reserve | 49,500 | 1.4% | IBAP | Decree-Law No. 6-A/2000 |
| 5. Área Marinha Protegida Comunitária das Ilhas de Urok | Community Marine Protected Area | Biosphere Reserve | 54,500 | 1.5% | IBAP | Decree-Law No. 8/2005 |
| 6. Florestas de Cantanhez | National Park |  | 105,800 | 2.9% | IBAP | Decree No. 14/2011 |
| Subtotal |  |  | 545,615 | 15.1% |  |  |
| 7. Boé | National Park |  | 105,370 | 2.9% | IBAP | To be established |
| 8. Dulombi | National Park |  | 160,100 | 4.4% | IBAP | To be established |
| 9. Tchetche | Biological Corridor |  | 49,922 | 1.4% | IBAP | To be established |
| 10. Cuntabane-Quebo | Biological Corridor |  | 55,003 | 1.5% | IBAP | To be established |
| 11. Salifo | Biological Corridor |  | 36,162 | 1.0% | IBAP | To be established |
| Subtotal |  |  | 406,557 | 11.3% |  |  |
| TOTAL |  |  | 952,172 | 26.4% |  |  |

- Figure 1 – Protected areas of Guinea-Bissau (official protected areas [áreas protegídas oficialzadas], areas to be protected [áreas protegídas por oficializar], and corridors [corredores]. Source: BISSASIG-Célula SIG-INEP/GPC 2011).

Among Guinea-Bissau’s PAs, the CNP is now of particular interest. The CNP is situated in the southeast of the country on the international border with the Republic of Guinea. It covers an area of 105,800 ha and is meant to safeguard the most important remnants of tall semi-humid forest in Guinea-Bissau and the other biodiversity of global importance located therein; these forests are the last vestiges of the great continuum of semi-humid forests that used to stretch across Guinea-Conakry, Sierra Leone, and Liberia i.e. are of exceptional regional/global importance. The Worldwide Fund for Nature (WWF) has identified the Cantanhez Forest as one of the 200 most important ecoregions of the world, since it is one the last remaining fragments of humid forest in West Africa. The CNP is situated in the southeast of the country on the international border with the Republic of Guinea. It covers an area of 105,767 ha and includes river floodplains and mangroves on the northern and western banks of the upper reaches of the Rio Cacine and areas of savanna. Mangroves present in the CNP include the Red Mangrove (Rhizophora mangle and R. racemosa), R. x harrisonii (often considered a hybrid), the White Mangrove (Avicennia germinans), the Black Mangrove (Laguncularia racemosa), and the Gray Mangrove (Conocarpus erectus). Inland forests include the best remaining example of semi-humid forest in the country dominated by Afzelia africana, Alstonia congensis, Antiaris africana, Ceiba pentandra, Dialium guineense, Ficus spp., and Parinari excelsa.,

At least 84 species of mammals are present in CNP. Ten different orders are represented: primates (12 species), carnivores (24 species), pangolins (2 species), Artiodactyla (13 species), Sirenia (1 species), the Proboscidea (1 species), the Tubulidentata (1 species), rodents (at least 8 species), the hyracoids (1 species), and bats (15 species). In addition, 194 species of birds have been reported in the CNP, with estuarine areas along the Rio Cacine supporting considerable numbers of migratory shorebirds (especially waders) and islands in the mouth of the river serving as important breeding areas for water birds; in 2001 the area was designated an Important Bird Area (IBA) by Birdlife International. Several of the species present in the CNP are classified as threatened according to the International Union for Conservation of Nature (IUCN), including the chimpanzee (Pan troglodytes, EN), the Temminck’s Red Colobus (Procolobus badius ssp. Temminckii, EN), the King Colobus (Colobus polykomos, VU), Defassa Waterbuck (Kobus ellipsiprymnus defassa, subspecies NT), the West African Manatee (Trichechus senegalensis, VU), and the Yellow-casqued Hornbill (Ceratogymna elata, VU). African Buffalo, Roan Antelope (Hippotragus equinus, LC), Leopard (Panthera pardus, NT) and African Elephant (Loxodonta africana, VU) are reported to remain, at least on a seasonal basis.

Approximately 24,000 people live in the CNP region (21 inhabitants/km2). The population is spread over more than 100 villages known locally as tabancas, and belongs to several ethnic groups: Nalu (32.4%); Balanta (26.1%); Mandinga (15.3%); Fula (9.0%); Tanda (5.4%); and Sussu (3.6%). The Nalus are the traditional occupants of the area and practice farming; the remaining groups also practice farming, ranching, silviculture, and growing rice on saline soils. Controlled seasonal hunting in the CNP is permitted by law, but only by local people and only certain game can be taken, such as the warthhog (Phacochoerus africanus) and forest duikers (Cephalophus spp., of which there are no globally threatened species in Guinea-Bissau).

Despite the advances—particularly in the marine and coastal regions—significant gaps still remain in the institutional framework underlying the development and future management of the SNAP. This includes most notably the need to secure more and sustainable sources of financial resources to fully develop and protect the SNAP and capitalise on the promising on the growing in-country capacity. The country is now seeking to further strengthen the SNAP and its financial sustainability, to safeguard its biodiversity conservation achievements, and to enable operational efficiencies to reach the management levels needed for long-term threat containment in both the coastal/marine and terrestrial biomes.

In this context, there is an urgent need for the consolidation of operations in CNP and the associated buffer zones, because the area has received only limited attention and resources to date and multiple threats towards development/conversion are on the rise.

- Institutional Context

In Guinea-Bissau, two key institutional players are responsible for the conservation and management of forest-related biodiversity: IBAP and the DGFF. IBAP was established by Decree 2/2005; it is attached institutionally to the State Secretariat for Environment (SEA) and has administrative, financial, and patrimonial autonomy. SEA is charged with promoting environmentally and socially sustainable development in the country as a whole, as well as for ensuring that the Country’s commitments under the international environmental conventions are met. This includes, proposing and coordinating the policy and actions pertaining to biodiversity in Guinea-Bissau.  IBAP is the agency responsible for the implementation of these policies, the management of the SNAP, and the management and monitoring of the key values of biodiversity (species and habitats) in the country. To achieve their mandates, SEA and IBAP foster partnerships with multiple stakeholders, particularly with other public institutions responsible for the management of natural resources, non-governmental organizations (NGO), the private sector, with traditional rulers and grassroots communities as well as scientific institutions, conservation organizations, and cooperation agencies.

The DGFF, which falls under the jurisdiction of the Ministry of Agriculture and Rural Development (MARD), is the authority historically responsible for the management of the nation’s forests—including lands under communal forest regimes—as well as for wildlife management policies and hunting concessions, as detailed in the recently revised Forestry Law (Lei Florestal, Decree-Law No. 5/2011). The agency is directly responsible for forest policies and has responsibilities in the national territory in terms of forest management, allocation of logging concessions, and inspection of extractive and hunting activities. However, within PAs these are the sole responsibility of IBAP.

Other government agencies with mandates which influence biodiversity conservation efforts in the country include, the State Secretariat of Fisheries/Applied Research Center of Fisheries (CIPA), the Unit for the Evaluation of Environmental Impacts (SEA/CAIA), amongst others. The latter was conceived and established with the aim of creating conditions in which environmental and social considerations are taken into account in the political decision-making processes and development activities planned in the country. The unit contributes to the promotion of sustainable development, ensuring economically viable investments that are socially acceptable and ecologically balanced for Guineans in particular, and for humanity in general. In the long term, the CAIA must forecast, determine, evaluate, and help mitigate the potential impacts of a project, program, or strategy on humans, fauna, and flora; as well as on biodiversity and ecosystems services.

- Policy and Legislative Context

In recent years, a variety of environmental laws have been passed in Guinea-Bissau related to biodiversity. The most important for the present project are the Framework Law for Protected Areas, the Basic Environment Law, the Environmental Assessment Act, the revision and update of the Forestry Law, the General Law on Fisheries Act, the Artisanal Fisheries Regulation, and the Decree on Creation of the CNP.

The Framework Law for Protected Areas of 1997 (Lei Quadro das Áreas Protegidas, Decree-Law 22/97) establishes a clear mandate to “protect plant and animal species and their habitat, as well as threatened ecosystems and landscapes of unique quality.” This law regulates the designation and de-gazetting of national or natural parks and other PAs and provides the regulatory framework for IBAP’s plans and actions. One key feature of this law is the provision to establish an “ad hoc commission or council” for PAs as the preferred consultation and consensus-building mechanism in the interaction with local communities on any conservation issues that affect human populations in the country. In 2007 a revision and updating process of this law was initiated and was finalized with the new Decree-Law No. 5-A/2011. Some of the innovations and contributions of this new law include the adoption of the PA definitions published in 1994 by IUCN and the World Conservation and Monitoring Center (WCMC), and of the six categories of PAs defined by IUCN in 2008 (eliminating the category of Natural Parks). The Community Protected Areas, Forests, and Sacred Sites became typified as a PA and opened the possibility of having new categories of PAs in line with scientific development and commitments under conventions, treaties, or agreements. Finally, the competence of the government structure that houses IBAP and its role and mandate was further defined, and provided IBAP with management tools.

The Basic Environment Law was approved under Law No. 1/2011. Proper application of specific principles, such as the prevention and precautionary, polluter-pays, user-pays, international cooperation, recovery, participation and accountability contained in this act for repairing the environmental damage caused by a non-durable activity could bring a highly positive contribution for the country in general and biodiversity in particular.

The Environmental Assessment Act, Law No. 10/2010 was published in the Official Gazette No. 38, regarding the requirements of preparing environmental impact assessment as well as the audit, licensing, and environmental monitoring introduced as policy instruments on environmental management in the framework of the CAIA. IBAP and its PAs must provide an evaluation before any environmental permit is issued, if the project in question resides in the geographic areas under their jurisdiction. This law provides a general framework for the development of environmental and social safeguards to ensure an ecologically, economically, and socially balanced environment.

The Forestry Law of 1991 (Lei Florestal, Decree-Law No. 4-A/91) establishes the need to develop and implement management plans for wildlife and forest concessions under the authority and supervision of the DGFF of the MARD. A revised Forest Law (Decree-Law No. 5/2011) provides further clarification of the role of PAs in the conservation of the country’s forests and recognizes the IBAP as the management organ for patrimony and forestry; when necessary, this institution may also be solicited to become part of the Forestry Technical Council.

Additional forestry-related policies and legislation include: a) Ministerial Decree No. 01/GM, 1996 (of December 1996), which provides the regulatory framework for communal forest management and asserts to DGFF the mandate to regulate all lands under “communal forest regime” in order to effectively assist rural communities in establishing sustainable forest management practices (Regulamento da Gestão da Floresta Comunitária); b) the National Forest Management Plan (1997), aimed at reversing the trends of deforestation and forest degradation; and c) the National Forestry Policy (2010) and the Forestry Master Plan (2010). Finally, with the goal of adopting actions directed toward mitigating the effects of climate change, attracting investment, and promoting the sustainable management of natural resources, the GoGB initiated participation in the Reduced Emissions from Deforestation and Forest Degradation (REDD) initiative (under the United Nations Framework Convention on Climate Change [UNFCCC]) by applying for membership of the UN-REDD program in early 2014).

Two acts of legislation apply to the regulation of fishing practices within the PAs. First, the General Law on Fisheries (Decree-Law No. 10/2011) approves the basic fishing legislation and establishes the requirements to be met in order to perform any activity related to the use of aquatic biological resources within waters under the jurisdiction of Guinea-Bissau. Second, the Artisanal Fisheries Regulation (Decree No. 24/2011) is focused on artisanal fisheries within the inland waters and territorial seas of Guinea-Bissau. In particular, the regulation specifies requirements to be met by fishing vessels, fishing zones, as well as fishing licenses, gear, and methods, according to the sustainable use of aquatic biological resources of the country. It also prescribes inspections, controls, and fines to be paid for illegal artisanal fishing activities. Revision of the General Law on Fisheries and the Artisanal Fisheries Regulation resulted in the following: a) the introduction of the Reserved Fishing Zones concept; this must be created jointly by the General Directors of Artisanal Fisheries, Environment, and IBAP; related regulations and participatory management are to be elaborated by IBAP and its partners; b) prohibition of hunting, capture, and detention of all seabird species, as well as onboard possession, landing, marketing or offering for sale of species of marine mammals, sea turtles and crocodiles, stingrays, and sharks as well as other species considered threatened or endangered that are included in the list of species to be protected; c) prohibition or restriction of the use of mangroves for fish processing, marketing, and construction; and d) the recognition of the Marine Parks Guards as entities for surveillance and for the control of artisanal fishing activities in their areas of jurisdiction.

### I.2. Threats, root causes, and impacts

The rich diversity present in Guinea-Bissau is under increasing threat. In the coastal and marine areas threats stem from subsistence activities such as itinerant agriculture, rice production, and artisanal fishing, as well as the rapidly growing and weakly regulated industrial fishing sector. In the Forest Belt threats are also increasing and include practices such as shifting agriculture, subsistence hunting, charcoal manufacturing, indiscriminate felling of forest resources and the rapid expansion of cashew plantations. These threats have resulted in the loss of biodiversity and the overall overexploitation of biological resources. In addition, climate change represents an immediate threat to Guinea-Bissau’s biodiversity. These threats are described in detail in the following paragraphs.

Habitat loss / land use change due to expanding and non-sustainable agricultural practices. Deforestation due to the expansion of subsistence agriculture and the emergence of new human settlements associated with the development of new agricultural concessions is among the principal factors for habitat loss in Guinea-Bissau. The total forest area in the country, including mangrove ecosystems, open forests, sub-humid forests, natural palm forests, and tree savannahs amounts to between 1.5 and 2 million ha, or between 44 and 56% of the country’s area—but these have been subjected to deforestation at a rate of 40,000 to 60,000 ha/yr. Subsistence farming has traditionally prevailed in Guinea-Bissau, but since mid-1980s there has been a shift towards commercial agriculture, mainly due to the expansion of cashew cultivation. Cashews grow on small trees cultivated in mono-specific orchards with a closed, mono-layered vegetation structure, and are mostly produced by small farmers in savannahs and in previous shifting cultivation fields, involving to a varying extent about 85% of the country’s population. Cashew cultivation requires only few inputs, low-level technology, and untrained labour. Cashew nuts are Guinea-Bissau’s main export, accounting for 85 to 90 percent of the country’s total exports; cashews have become the most important cash crop and comprise 98% of export earnings and 17% of total fiscal revenue. The expansion of cashew plantations is an increasing threat to the remaining forest stands and biodiversity and a major trigger for local extinctions.

Non-sustainable farming practices based on slash-and-burn agriculture and overgrazing are widespread throughout the country. Unsustainable techniques are generally expanding, compounded by the fact that the fallow period is getting shorter and soils less fertile as a result of demographic pressures. This is due to the displacement of food crops with cash crops (cashews), population growth, and internal migrations spurred by new infrastructure and access to markets. An increased demand for agricultural land for the production of newly introduced upland rice has resulted in brush-clearing of large tracts of forest areas. New settlements (tabancas) are also being established by small groups that take refuge from turmoil and economic deprivation in the region. In addition to the loss of forest cover and other natural habitats and to the loss of valuable forest resources, unsustainable slash-and-burn leads to soil degradation and soil erosion, reduced groundwater and surface water quantity, the siltation of riverbeds, lowered soil fertility, and ultimately causes the loss of biodiversity. Small livestock herding is by and large extensive and is in direct competition in some areas with wildlife for fodder and access to water resources.

Fire also poses a significant direct threat to biodiversity in the country. Fire is the preferred land-clearing method for preparing land for agriculture. In addition, hunting with the aid of fire is also common as well as fires of other various origins (exploitation of honey, carelessness, and arson). Practices that use fire are particularly destructive if they are not managed appropriately. It is estimated that each year between 50,000 to 80,000 ha of forest in Guinea-Bissau are degraded by fires. Savannahs are also susceptible to fire, especially during the dry season. Burning forests to clear land for cashew production has contributed to the aging and shrinking of the surface covered by the African Fan Palm or “cibe” (Borassus aethiopum), which occurs at low altitudes along rivers and in coastal woodlands.

Timber and firewood use. A progressive disorganization of the forestry sector and an increase  in demand for timber, especially in urban markets, has led to the reduction of relicts of forest stands and the near local extinction of precious timber species like the Afzelia (Afzelia africana), the Barwood (Pterocarpus erinaceus), and the African Mesquite (Prosopis africana), among other species. Also, the demand for building material from the African Fan Palm has been intensifying in recent years with the expansion of towns and cities. Firewood is widely used as a source of domestic energy and the prodution of charcoal. The African Mesquite is the species most in demand for charcoal production; therefore, this species has suffered intense pressure, resulting in its endangerment. Other species used include mangroves trees (Avicennia and Rhizophora spp.), the Kosso (Pterocarpus erinaceus), the Velvet Tambarin (Guinea dialium), Daniella (Daniella oliveri), the African Mahogany (Khaya senegalensis, EN), and the Sasswood (Erithrophleum guinea). In addition to impacting the populations of the tree species used, firewood use and charcoal production affect biodiversity directly through resource removal and indirectly through habitat alteration.

Unsustainable fishing. Traditional artisanal fishing using monofilament nets of small mesh sizes and the technique of closing the mouths of rivers and river stretches “tadja river” are the main pressures on coastal fishery resources. Small mesh nets are used both in open water as well in the small stretches of the sea or river, leading to the capture of immature shrimp and fish in coastal and mangrove areas. In river deltas, nets are spread across the river mouths to catch fish of all sizes, including young immature individuals and other species of aquatic fauna such as manatees (Trichechus senegalensis). These mammals get caught up in nets during the high and low tides while seeking feeding zones. Other species frequently captured and drowned in the nets include sea turtles, dolphins, and crocodiles. In addition, the establishment of commercial artisanal fishing camps usually lead to the following damaging activities: a) cutting of mangroves (and sometimes other types of vegetation) to obtain firewood for fish processing; b) cutting of large trees to build canoe keels and other parts of vessels; c) fishing directed at breeding areas, affecting fish stocks and fisheries in the food chain; d) the accidental capture and/or targeting of protected and rare species; e) capturing African ospreys for meat consumption; and f) collecting sea turtle eggs and adult females at nesting beaches.

Pressures and threats exerted by industrial fishing, which is loosely regulated in the region, include: a) operations and presence of trawlers in areas reserved for artisanal fishing leading to a degradation and alteration of the seabed, coastal ecosystems, and its resources; b) overfishing of species of high commercial value along with threatened species; c) pollution; and d) raids by pirate fishing boats.

Hunting pressure on game species is high on a country-wide scale. It has driven a number of species to the brink of local extinction and severely affected the migratory patterns and survival capacities of others, among them large mammals (elephant, buffalo, eland, etc.), large predators (lion, leopard, etc.), and primates (e.g., Colobus monkeys and baboons). The marketing circuit for bush meat has its main outlets in towns located near PAs. In addition to pressure from professional hunters who enter conservation areas covertly, game species are under threat from military personnel stationed in various provincial army garrisons.

Urban growth and development (mining and tourism). Urbanization and construction of new infrastructure have been made at the expense of different plants and habitat formations of great ecological value. This is the case throughout the downtown area of Bissau, which was formerly a wetland harbouring mangroves and lakes that served as resting sites and feeding area for many birds, as well as a source of protein for the poorest people of Bissau through fish, mollusks, and shellfish. In addition, mangrove areas on the perimeter of cities are used as dumps for waste and wastewater. Unfortunately, many infrastructure projects are being built in proximity of areas rich in biodiversity and fragile ecosystems without proper environmental impact studies.

Over the last 10 years, the GoGB has been seeking to strengthen the emerging mining sector, particularly with regard to offshore oil and minerals (phosphate and bauxite). The development of this sector raises high expectations from the government, local communities, and society in general as a source of employment and wealth. The potentially oil-rich area off the Bijagos Archipelago has already led to oil prospection along the boundaries of the Bolama-Bijagós Biosphere Reserve. Deposits of phosphates in Farim are estimated at approximately 100 million tons with 30% phosphate content, while for bauxite there is an estimation of 113 million tons with 44.9% aluminum content.  For the cases of bauxite and phosphate, concession areas are respectively in Boe and Farim (i.e., in the vicinity of Boe NP, Cacheu NP, Corubal River, Farim River, and Cacheu River). A deep-water port in the Rio Grande de Buba was constructed to allow the export of bauxite. The site of the future port of Buba is located in the central area of the Cufada Lagoons NP. All sites that have been identified for mining have a high level of biodiversity, which may be threatened by pollution, ecosystem degradation, and loss of important habitat and species, as well as uncertainty regarding food security and the economy of the local people that depend on natural resources.

The Bijagós Archipelago is widely recognized as the principal tourist hub of the Guinean coastal zone, with the focus mainly on sport fishing. The Bijagós Archipelago includes the João Viera and Poilão Marine Protected Areas, where the largest green turtle nesting site (the third-largest in the Atlantic) in West and Central Africa are found. The installation of tourist infrastructure in these areas has not considered the ecological fragility and vulnerability of the small islands, nor their local economic and social importance.

Climate change. The effects of climate change in Guinea-Bissau are already quite discernible. Precipitation has become more irregular, less abundant, and less evenly distributed in spatiotemporal terms, thus contributing to the salinization and acidification of floodplain soils. In the Bijagós Archipelago, the islets of sedimentary origin (and the second-most important area in West Africa for migratory water birds) are being affected by increase in erosion, rising sea levels, and even the disappearance of some more exposed islets and shoals. In other areas, rice farming in wetland depressions (bolanhas) is gradually dying out. As the valley bottoms and floodplains are abandoned as farming areas, pressure increases on forest and savannah areas, which become the site of subsistence farming, thus threatening hill and plateau forest ecosystems. During preparation of the GEF-funded project Support to the Consolidation of a Protected Area System in Guinea-Bissau’s Forest Belt an initial analysis of climate change scenarios for Guinea-Bissau was performed. The PPG study showed dramatic impacts on land, water, and forest resources, all affecting the survival capacity of local communities across the entire Forest Belt region. The study was largely based on existing data and modelling carried out towards the National Adaptation Plan of Action (NAPA), which was finalized in 2008. It concluded that over the next few decades the impacts of climate change on water, land for food crops, and on biodiversity will be catastrophic, compounded by the fact that cross-border migrations from the north and south will exacerbate the problem and make subsistence and survival in the region very difficult.

The root causes for the loss of biodiversity in Guinea-Bissau lie in three main areas, which are described in the following paragraphs.

Poverty in rural areas. Threats to biodiversity are often associated with rural poverty (75.6%, 2010), leading to the non-sustainable exploitation of the country’s natural capital, including coastal and terrestrial biodiversity and forest resources. The HDI of Guinea-Bissau (0.396) is one of the lowest in the world; the country has one of the highest maternal death rates in the world, a life expectancy at birth of only 54 years, and considerable disparity in income distribution. Agriculture generates 80% of employment and 90% of exports, primarily through cashews. However, although the exploitation of non-renewable resources such as bauxite, phosphate, and petroleum may become important drivers of future economic growth, the country still has poor infrastructure and weak social indicators, and more than two-thirds of the population live below the poverty line. Natural resources are still the basis of the livelihood strategies for the majority of the population. In terrestrial ecosystems, subsistence livelihoods have led to deforestation and land degradation, which continues to be one of the critical environmental problems confronting Guinea-Bissau. A time-series analysis derived from the use of remote sensing in selected portions of the Forest Belt has documented that over a period of 17 years dense forest cover has decreased by an estimated 50% in the Boé area and by 20% in the Dulombi area. Affected landscapes are subject to shifting cultivation, overgrazing, reduced groundwater and surface water quantity, erosion, lowered soil fertility, and ultimately the loss of biodiversity.

Institutional weakness and lack of coordination among authorities. Traditionally, poor governance together with a lack of technical capacities has rendered the implementation of long-term policies and programs for the conservation of biodiversity through effectively managed PAs and sustainable forest and land management ineffective. The  lack of coordination among public agencies that are directly responsible for the management and conservation of forests and biodiversity (i.e., IBAP and DGFF), has created inefficiencies and lost opportunities for developing synergies across government agencies, including enforcement of law and regulations,  and stakeholder groups at both the national and local levels. This deficiency becomes aggravated by the lack of technical capacities and lack of staff that are adequately trained to manage environmental issues and the effective conservation of biodiversity; even if IBAP has developed positively and provides good basic capacity on relevant matters; and within PAs mechanims exist that allow consultation and participation of local stakeholders, NGOs, and other government agencies in PA management.

Insufficient and unpredictable financing for biodiversity. One of the largest barriers to adequate and effective biodiversity and PA conservation and management is the lack of continued financial support towards the SNAP. The existing PA-funding model is based on a set of parallel and sequential short-term donor/externally funded projects and needs to be replaced, or complemented, by sustainable financial flows. In response to these needs, the FBG, a conservation trust fund, was conceived and created under English law in 2011 under the GEF/World Bank-supported Guinea-Bissau Biodiversity Conservation Trust Fund project. The role of the FBG is to manage endowment, sinking, and revolving funds, generating long-term constant returns which can then be used for the conservation and management of Guinea-Bissau’s biodiversity and ecosystems, including the SNAP. However, the endowment of the FBG has not been capitalized and PA management in Guinea-Bissau still relies almost exclusively on external project-based funding sources, which are generally unpredictable, insufficient and directed at particular sites or issues of donor interest. As a result, the SNAP continues to be underfunded, which limits the ability of PA officials to reduce current threats to biodiversity and PAs, for effective community engagement and for control and patrolling.

Globalization and regionalization of economies. More recently, the increasing globalization and regionalization of economies has forced local communities to exert further pressure on the coastal and terrestrial ecosystems. Market-oriented productions systems (i.e., agriculture, timber forest exploitation, and fisheries) have contributed to an increase in the “savannahization” of the country’s higher lands and the loss and degradation of the coastal mangroves. The expansion of cashew monocultures has been replacing the traditional techniques of conservation land under fallow and agriculture geared towards individual and household consumption. The cycle of cultivation and fallow tends to be interrupted and the lands under natural regeneration while deforestation and the degradation of ecosystems across the country increases. Dry and semi-dry forests and palm tree groves are the most affected in this regard. Finally, market-oriented agriculture is contributing to the gradual decrease of the diversity of traditional foods with known nutritional values and to the loss global genetic diversity (in situ) as there are many local varieties that are probably being lost, as well as the country’s ecosystems and their associated services.

### I.3. Long-term solution and the barriers to achieving this solution

The long-term solution is to have a well-funded SNAP that conserves Guinea-Bissau’s highest biodiversity value ecosystems through PAs that are effectively managed under nationally mandated standards to meet conservation goals in a cost-effective manner, and working towards sustainable development in stakeholder communities. Despite the rapid advances of the last two decades in which Guinea-Bissau with the support of GEF and other donors has put into place the first building blocks towards a SNAP, the achievement of this long-term solution is impeded by continued financial and operational barriers, as described below.

Barrier 1: Revenue generation constraints:

Lack of government funding for PAs: The financial analysis of the SNAP (Financial Sustainability Scorecard) completed during the PPG indicates that almost a 100% of PA funding in Guinea-Bissau comes from external sources. Government funds are limited to tax exemption, which while useful for improving the cost-effectiveness of external interventions, do not provide the ready cash needed to develop and manage the SNAP.

Limited capacity during conservation trust fund start-up phase: Over the last years major advances have been made in setting up the FBG according to international standards through projects supported by the GEF and World Bank. The FBG has been designed as a sustainable financing mechanism to shield the management of the SNAP from the chronic public budget shortages and reduce the reliance on unpredictable donor financing. The minimum operational and management capacity has been established, and a founding Board and Executive Secretariat are in place. According to annual workplans, the Secretariat is developing the required foundations tools for the day-to-day operations of the FBG. However, political instability in Guinea-Bissau during past years has led to delays in investment and performance. Further dedicated support is required to ensure the fledgling fund will become fully operational and further equipped with sound management, communications and financing tools and strategies. With a new stable government in place, support from various sources is available for developing key operational tools and processes, but it is still essential that procedures are verified and formalized auditing and reporting protocols finalized, and that management arrangements are completed to increase confidence levels to catalyze capitalization. Furthermore, new approaches are needed to complete capitalization over the longer term, and a creative fund raising strategy is required that would explore alternative mechanisms rather than traditional donors. While first steps have been made via a national PA financing strategy that lays out the need for revenue generation and fee levels across PAs, these measures have yet to be implemented and the scope of analysis needs to expanded. The prioritization of funding allocations to specific PAs, financial flows to sites and relevant organisations such as IBAP, as well as grant making procedures still need to be developed in detail. The FBG Operational Manual must be reviewed and updated and underpinned with additional specialist policies, guidance, and operalizationtiona to ensure that the conservation trust fund can grow into full operations.

Limited capital-donor confidence during conservation trust fund start-up phase and lack of initial endowment capitalization: In addition, building donor/ investor confidence and achieving the first level of capitalization has been a huge challenge. The initial fundraising target for the FBG endowment was USD 5 million, at the time deemed sufficient to guarantee the recurrent operating costs of at least two key PAs as well as of the FBG itself. However, prior to the Project Preparation Grant (PPG) phase of this project, no tangible results could be obtained due to various issues associated with eligibility criteria, and unmet matching provisions that The World Bank and other partners encountered in the past. Capitalization has been hampered in the past by political instability and also by an initial caution in donor confidence in governance and operational capacity of the newly established FBG. In consequence, the endowment of the FBG has not yet been capitalized and PA management in Guinea-Bissau still relies almost exclusively on external project-based funding sources. Unless the foundation is rendered fully functional and urgently capitalized, there is a real risk that conservation activities in Guinea-Bissau are eventually halted and that significant conservation gains accrued over the last decade end up being reversed. An in-depth assessment undertaken by the Fundo Brasileiro para a Biodiversidade (FUNBIO), a well-established Brazilian conservation trust fund, estimated that an FBG endowment of 24 to 46 million USD (19.1 to 37.1 million EUR), with a 5.9% return, would be sufficient to sustainably finance the recurrent costs of the country’s existing protected areas and biodiversity conservation efforts in perpetuity, using four different scenarios – minimalist, realistic, strategic and priority.

Barrier 2: Incomplete coverage and operational deficiencies of PA management:

The abovementioned funding limitations are exacerbated by a yet incomplete coverage of effective PA management by the government (IBAP) due to weak presence in selected areas and specific operational deficiencies. For instance, PA management plans are in some cases outdated (e.g., CNP) and PAs do not have business plans, or are in the preliminary stages of development of business plans, which consider the full extent of management needs of the PAs. Furthermore, procedures for expenditure reporting are weak and are not linked to conservation benefits with the result that even with increased resource allocations to sites these would not necessarily be commensurate with contributions to conservation goals. Management capacity and long-term financial planning for the SNAP are still limited and most existing field-level personnel still lack the full complement of skills and equipment required for efficient PA management in a context of low funding levels while being faced with multiple pressures from within and around the PA boundaries. Nor do they have the administrative and financial experience to manage the sparse resources or to link budgets to strategic and long-term management goals. The absence of financial skills also limits access to non-budgetary funding opportunities.

Operational deficiencies are further compounded by a weak collaborative framework among institutions responsible for biodiversity conservation and forest management. IBAP manages biodiversity and the SNAP, as detailed in the recently revised Law on Protected Areas (Lei-Quadro das AP, Decree-Law No. 5a/2011). The DGFF in contrast is responsible for the management of the nation’s forests, including lands under communal forest regimes, wildlife management policies, and hunting concessions, as detailed in the Forestry Law, also recently revised (Lei Florestal, Decree-Law No. 5/2011). This mandate thus covers key land uses and practices that are exerting major pressures on PAs. The two institutions have so far had little scope for collaboration, particularly since IBAP until recently focused on the coastal regions of Guinea-Bissau. There have been significant incidences highlighting the differing approaches of the two institutions, such as exploitation permits being issued by DGFF in the buffer zone, which were inconsistent with PA and community-based forest management goals defined by IBAP and other stakeholders. This restricts the reduction of threats at the source and the subsequent reduction in threat mitigation costs, and limits the potential of sharing of costs across institutions. The lack of cooperation between the the two different government agencies has been identified as a key issue to be addressed to achieve a more effective management and protection of forest-related biodiversity in Guinea-Bissau. In fact, the effective establishment and management of PAs in the continental Forest Belt region of the country requires the creation of a functional collaborative framework involving the two institutions, leading to a shared vision and the alignment of key policy objectives.

Most PAs in Guinea-Bissau have significant human populations within or around their boundaries exerting mounting pressure on biodiversity resources and resulting in increased PA management costs. The potential for stakeholders near PAs to contribute—in conjunction with government (IBAP)—to the effectiveness and cost-efficiency of PA management is not sufficiently harnessed. Although the national forestry policy and legal framework allows for stakeholder participation through delegation of functions, co-management arrangements, and advisory boards and councils, respectively, local stakeholders have limited capacities to fulfill this projected role. Similarly, although there are policies that PA budgets should include funds for the livelihoods of communities living in and around the PAs as part of threat reduction strategies, these have so far had limited application or have been dependent on external funding that is not sustainble, thereby creating funding gaps that generate distrust among local communities intended to benefit from these activities. Consequently, local stakeholders obtain few direct benefits from PAs, and therefore view them principally as potential sources of natural resources from which income can be derived through extraction.

### I.4. Stakeholder analysis

During the project preparation stage, a stakeholder analysis was undertaken in order to identify key stakeholders and assess their roles and responsibilities in the context of the proposed project. Table 2 describes the major categories of stakeholders identified, the individual stakeholder institutions/organizations within each of these categories, and a brief summary of their specific roles and responsibilities in supporting or facilitating the implementation of project activities.

- Table 2 - Summary of key stakeholders.

| # | Stakeholder | Indicative roles and responsibilities |
| --- | --- | --- |
| 1 | Institute for Biodiversity and Protected Areas in Guinea-Bissau (IBAP) | IBAP will be the project’s lead executing agency. IBAP is a semi-autonomous government agency with the mandate to manage biodiversity and the SNAP of Guinea-Bissau, as detailed in the recently revised Law on Protected Areas (Lei-Quadro des AP, Decree-Law No. 5a/2011). As such, IBAP will be responsible for overseeing the implementation of project activities in accordance with its work plan, procurement plan and agreed budget. IBAP will lead the Project Steering Committee (PSC) on behalf of the State Secretariat for Environment/SEA. |
| 2 | State Secretariat for Environment and Development (SEA) | The Secretariat depends directly from the Prime Minister and has the specific mandate to coordinate environmental policies and ensure their mainstreaming in the wider decision-making processes. It hosts the focal points for the GEF, Convention on Biological Diversity (CBD) and UNFCCC. Of particular importance to the project is SEA’s CAIA, mandated to ensure environmental impact assessment (EIA) functions within Guinea-Bissau. It is anticipated that CAIA will play a crucial role in improving the implementation of government EIA policies and the licensing and monitoring of activities such as logging in and around PAs. |
| 3 | Directorate General for Forestry and Fauna (DGFF) of Ministry of Agriculture and Rural Development (MARD) | DGFF will play an active role in the management of CNP’s buffer zones and connected biological corridors and related community engagement activities. The effective collaboration of IBAP and the DGFF will be critical in tackling the complex socioeconomic reality prevailing in and around CNP. The two institutions will coordinate closely for the identification and prioritisation of management activities and the allocation of funds for investments in biodiversity conservation, forestry, and land use planning in CNP and at the wider landscape level. DGFF will be a member of the PSC. |
| 4 | BioGuinea Foundation (FBG) | Physically housed at IBAP, the FBG has been designed and set up as an autonomous sustainable financing mechanism that has as a priority safeguarding the management of the SNAP. With support from The World Bank-International Development Association (IDA) and West African Marine Ecoregion Project (WAMER) projects, the FBG will benefit from and co-lead the implementation of activities planned under Component 1 of the project, and receive and manage the resources mobilised for its endowment capital. FBG will be a member of the PSC. |
| 5 | Local Communities (Cantanhez NP and buffer areas) | Approximately 23,000 people reside in the CNP and are distributed across various villages known as tabancas. The CNP population is divided among six ethnic groups: Balantas, Nalus, Tandas, Djacancas, Fulas, and Sussos. Local communities (both women and men) will be important beneficiaries of all project interventions. Community institutions will participate directly in every level of planning and management, particularly in ecologically sensitive areas such as buffer zones and biological corridors. They will be involved in the negotiation, implementation and monitoring of collaborative management agreements in the CNP and buffer areas (including their participation in the CNP’s Management Council), and in the piloting of innovative biodiversity-friendly economic activities, promoting sustainable livelihoods with reduced impact on biodiversity resources and ecosystem services. Additionally they will be beneficiaries of training awareness-raising activities regarding conservation and sustainable use of biodiversity, and technical assistance for the implementation of biodiversity-friendly practices. |
| 6 | Domestic NGOs / CBOs | Local NGOs that are active in the CNP and adjacent areas have played and will continue to play a fundamental role in facilitating community engagement, building local capacities, mobilizing community policing groups in the CNP, protecting natural resources and the environment and encouraging their sustainable use, and implementing livelihood activities including the piloting of biodiversity-friendly economic activities. The local NGOs in the CNP and adjacent areas include: Cooperativo, Centro Para o Desenvolvimento dos camponeses do Sul (CODECECAS), Associação Guineense de Estudos e Divulgação das Tecnologias Apropriadas (DIVUTEC), Ação Para O Desenvolvimento (AD), Associação de Promoção do Desenvolvimento Participativo na Base e Gestão Durável dos Recursos Naturais (TINIGUENA), Associação dos camponeses da Area Protegida de Cantanhez (ACAP-Cantanhez), and Association des producteurs de mangues et ananas d’Iemberem et Cambèque (APAMIC), among others. Additionally, several local organizations provide support for the development of income-generating activities for women (palm oil, confection of baskets, and horticulture) to strengthen the food and nutrition security of their families. |
| 7 | International funding and implementation partners | The international funding and implementation partners have been, and will continue to be, instrumental in the operationalization of the FBG and the capitalization of the FBG endowment. In addition, they will contribute through different investments to enhance the management effectiveness of the CNP and its buffer zones. IUCN, WWF, and other international NGOs have been critical partners in the early establishment of IBAP and the SNAP. The World Bank has played a key role in the setup of IBAP and provides continued support for its consolidation as Guinea-Bissau’s SNAP administrator. Additionally, through the Biodiversity Conservation Project (BCP) and the closely related World Bank-GEF Biodiversity Conservation Trust Fund project, the World Bank has been providing support to the set up and pilot operation of the FBG. It also supported the GoGB in the conduct of the necessary field work and accreditation processes towards the mobilizing of REDD+ carbon credits from Cantanhez NP, eventually thereby catalyzing the expected contribution by the GoGB towards the FBG capital using these carbon sales revenues. The MAVA Foundation works for the conservation and sustainable management of the coastal and marine environments in West Africa in close collaboration with the communities and states that depend on them, including Guinea-Bissau. The MAVA Foundation will serve as a project co-financier, providing critical support for the capitalization of the FBG endowment. The EU is another a project co-financier; it will oversee the projects it finances in Guinea-Bissau, including a Global Climate Change Alliance+ project (GCCA+) contributing to the consolidation of the CNP. The FFEM (Fonds français pour l’environnement mondial) is expected to become a project co-financier over the course of 2015, eventually contributing EUR 1,000,000 (c. USD 1,245,760) towards the capital of the FBG. 1st and 2nd stage proposals were submitted by the PPG/FBG to the FFEM in December 20014 and February 2015, respectively; a decision on the 2nd stage proposal is expected for March, after which a validation mission will take place to justify and trigger the release of funds to FBG, still expected for 2015. All the partners will continue to play a key role in the project and directly for IBAP and FBG. The World Bank, the MAVA Foundation, the EU, and other project co-financiers will form part of the PSC. The donors towards the FBG capital and operationalisation have also expressed their interest in establishing a monitoring mechanism under the FBG, in the form of a Donor Contact Group, to structure the dialogue between these donors and the FBG governance system in order to harmonise their positions and expectations towards the FBG. Furthermore, the FFEM if it so desires can as all FBG donors request a seat on the FBG’s Governing Board, on the basis of the existing membership stipulations. All partners will in addition gather at the annual donor roundtable. |
| 8 | Conservation Finance Alliance (CFA) and the Consortium of African Funds for the Environment (CAFE) | CFA is an international network of conservation finance specialists and conservation trust fuds (CTF) around the world. The FBG is already part of this network and will not only benefit as a member, but actively contribute to international best practices and experiences by formally interacting with the regional and global community-of-practice. The objective of the CAFE is the development of innovative finance mechanisms to foster conservation, environmental management, and sustainable development in Africa. The FBG liaise with the subset of United-Kingdom-based CAFE CTFs, and will be a fully paid member in the near future benefitting from mechanisms for sharing best practices and financing. |

### I.5. Baseline analysis

Baseline protected area and forest use management system: In Guinea-Bissau, two key institutional players are responsible for the conservation and management of forest-related biodiversity. IBAP is attached institutionally to the SEA and has administrative, financial and patrimonial autonomy. Through support from the World Bank-GEF-EU-IUCN Coastal and Biodiversity Management Project (CBMP), the ensuing World Bank-GEF Biodiversity Conservation Trust Fund Project, and the ongoing World Bank-IDA BCP, IBAP was established and supported through legal, physical, and capacity building programs. The PA Framework Law and other existing legislation was amended to reflect IBAP’s roles and responsibilities, the identification and establishment of IBAP’s Board and the design of its institutional and governance structures. Internal administrative and financial operating procedures have been established, as well as the recruitment of qualified staff. As a result, IBAP has grown into a fully functioning institution, coordinating the day-to-day management of the SNAP.

The World Bank-GEF Biodiversity Conservation Trust Fund Project also supported the design and legal establishment of the FBG. The ongoing World Bank-IDA BCP currently supports the operationalisation of the FBG, until approximately May 2016 (see co-financing). In late 2007 a national ad hoc working group, drawing on representatives from government, private sector, NGOs, and civil society was set up, which laid the ground work for establishing this independent conservation trust fund which over the long term would provide sustainable financing for biodiversity conservation activities in Guinea-Bissau. The FBG was officially registered in 2011 as a “private foundation for public utility” under English and Welsh law – the legal registration of the foundation as such an offshore private entity with public utility status was chosen to maximise its accountability and mitigate any risks arising from institutional or political changes. An independent and mixed Board of Directors is being put in place to oversee the Fondation, in which the government will be represented but not have a majority. In early 2012, charity status was secured for the FBG, granted by the UK Charity Commission, and a protocol was formalized with the GoGB, recognizing its legal statute and granting the foundation tax exempt status also in Guinea Bissa. The overarching objective of the FBG during its first of operations is to leverage resources for, and manage, endowment, sinking and revolving funds, with a view to securing stable and sustainable financing for the maintenance of the SNAP and the biodiversity it supports over the long term. The legal basis and governance structure of the foundation have been carefully designed to comply with the key recommendations identified by the GEF for the effective establishment of trust funds. Further achievements by the previous World Bank-GEF support entail the provision of relevant technical assistance to IBAP and other key players on the modus operandi of the charity. However, the World Bank-GEF project faced significant challenges linked to government changes in Guinea-Bissau and was therefore not able to fully deliver on various aspects originally expected under the project. This includes the fact that the FBG has not been capitalized to date.

This is why the follow-up World Bank-IDA BCP was conceived to further advance the operationalisation of the FBG. Under this ongoing project the FBG Executive Secretariat has been set up and an (interim) international Executive Secretary and a Finance Officer are on staff. An initial workplan addressing key priorities for the further operationalisation of the fund has been developed, and will be implemented as co-financing commitment to the here-proposed UNDP-GEF project. The World Bank-IDA support will run in parallel for at least one year to the UNDP-GEF project.

A preliminary assessment undertaken by FUNBIO in 2014, estimated that an FBG endowment of 24 to 46 million USD (19.1 to 37.1 million EUR), with a 5.9% return, would be sufficient to sustainably finance the recurrent costs of the country’s existing PAs and biodiversity conservation efforts in perpetuity. This analysis considered four different scenarios – minimalist, realistic, strategic, and priority (Table 3; see Annex 4 for details).

- Table 3 – Estimated finance gaps according to four different scenarios (minimalist, realist, strategic, and priority) (all figures are inclued in EUR; Source: FUNBIO 2014):

|  | Gap total in EUR | Average yearly in M€ | Average Size of Endowment @ 5.9% in M€ | Yearly Min (after 2017) in M€ | Yearly Max (after 2017) in M€ | Endow F Min in M€ | Endow F Max in M€ |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Minimalist | -20,459,109 | 1.6 | 27.1 | 1.5 | 1.6 | 25.4 | 27.1 |
| Realist | -24,299,828 | 2 | 33.8 | 1.5 | 2.2 | 25.4 | 37 |
| Strategic | -21,330,386 | 1.8 | 30.5 | 1.5 | 1.8 | 25.4 | 30.5 |
| Priority | -11,966,762 | 1 | 17 | 1 | 1.1 | 17 | 18.6 |

The above figures give the approximate endowment value that would be needed to sustainably run the operations of the SNAP and its support organizations (i.e., IBAP and FBG; Table 4). Given the complexities behind the FUNBIO scenarios, an “in between” figure of EUR 28 million (USD 34.88 million) is being used throughout the proposal as the endowment investment projected to be leveraged in the medium to long-term, including the initial capitalization to be leveraged through this project.

- Table 4 – Structure of the costs required for operating the SNAP and its support organizations (Source: FUNBIO, 2014).

| Cost category | % range | Institutions | % range |
| --- | --- | --- | --- |
| Investment cost | 11 % – 13% | Protected Areas | 62% – 72% |
| Personnel cost | 33% – 36% | IBAP | 16% – 21% |
| Operations & Activities | 52% – 56% | FBG | 12% – 17% |

A further institution is critically relevant to this project—the DGFF, which falls under the jurisdiction of the MARD. The DGFF is the authority historically responsible for the management of the nation’s forests—including lands under communal forest regimes—as well as for wildlife management policies and hunting concessions, as detailed in the recently revised Forestry Law (Lei Florestal, Decree-Law No. 5/2011). It has direct responsibility for forest policies and the management of forest resources, and is specifically tasked with the issuance of forest concessions. The DGFF has a similar mandate to manage and enforce wildlife management policies as part of its oversight of game and hunting concessions outside of PAs. In this sense, there is no formal overlap of mandates between DGFF and IBAP; however, missing coordination between the two institutions have in some cases led to misaligned action, including significant incidences such as exploitation permits being issued by DGFF that were inconsistent with PA and community-based forest management goals defined by IBAP and other stakeholders.

- Baseline projects and resources

Approximately USD 13,540,000 will be invested between 2015 and 2018 in biodiversity conservation in Guinea-Bissau. This will provide resources for the overall operational costs of IBAP’s central office and the management of existing PAs. Approximately USD 45,000 will be invested from revenue generated by PAs through tourism entrance fees. An estimated USD 1,115,000 is being invested in Guinea-Bissau by the EU-UNDP-WWF regional WAMER project, which in Guinea-Bissau aims inter alia to improve governance and institutional capacity in the country’s coastal and marine PAs; however, this project also entails specific support for fundraising and communication activities by FBG (leveraged in co-financing of USD 400,000, see below). In a similar fashion the above-mentioned ongoing World Bank-IDA project provides USD 1,270,000 for the further consolidation and strengthening of capacity for the management of coastal and marine PAs and biodiversity in Guinea-Bissau, in addition to supporting the FBG (of which USD 690,000 are project co-financing). The ongoing UNDP-GEF Forest Belt PA project mentioned previously is directly contributing USD 1,700,000 (USD 950,000 of GEF and USD 760,000 of UNDP grants) to the creation and management of Dulombi and Boe National Parks and three related corridors. While this project will end in 2016 and does not include CNP (which also has been almost entirely excluded from marine and coastal PA/biodiversity projects), it is building experience within IBAP on the management of forest PAs and some lessons on forestry and agro-forestry, fire management, and landscape zoning. The EU-funded MONTE project (which has a budget of USD 3,100,000) supports the sustainable management of forest resources in the Cacheu Mangrove National Park in the north-west, which could provide lessons on PA functions that are relevant for the effective management of terrestrial PAs; in doing so it will also work on systemic forest management issues at the national level that will immediately link to the project proposed herein, working most notably towards its REDD+ financing objectives. A further contribution to baseline investment is given by the IBAP/IUCN project promoting sustainable tourism in Guinea-Bissau with a focus on PAs – this project includes an allocation of around USD 200,000 towards CNP of its total budget of USD 770,000, which is commited as co-financing to this UNDP-GEF project. Baseline investmentsts will also inlude a GCCA+ project in Guinea-Bissau, with a total investment of USD 4.98 million (EUR 4 million); a portion of this amount will be directed towards the effort to reduce deforestation in CNP and Cacheu NP.

Over the four-year period under consideration, the DGFF will invest approximately USD 2,800,000 (for salaries, operations, and training) of which an estimated 50% and 20% will be earmarked for operational and forest management costs in the Forest Belt region and the areas around CNP, respectively. Enhanced coordination between DGFF and IBAP at the systemic level, and at the site-specific level piloted under the project in CNP, therefore provides important opportunities for: a) reducing pressures on biodiversity assets inside and adjacent to PAs through improved management of forest resources and wildlife (e.g., with regard to the issuance and enforcement of logging and hunting licenses/concessions); and b) cost-efficiency.

With a view to increasing the financial sustainability of the SNAP, the abovementioned World Bank/IDA BCP and WAMER projects have begun operationalizing the FBG through the recruitment of key staff, the establishment of financial systems, and the initiation of fund-raising activities. The present project has developed a closely linked workplan (see design of  Component 1) with these two initiatives, and their related respective contributions of USD 390,000 and USD 300,000 are critical co-finance for securing the institutional background against which capitalization of the FBG can take place.

Without investing in a sustainable financing mechanism, the SNAP will remain almost entirely dependent on external project finance. This leaves significant achievements of the past decades vulnerable as, in the event that this external financing is halted, SNAP activities will be forced to stop and the conservation gains are likely to be reversed. Thus, the PA system would continue to lag behind in terms of connectivity and overall management effectiveness, including the consolidation of the terrestrial PA estate, leaving especially CNP and associated buffer zones and ecological corridors unprotected and susceptible to a variety of threats. Finally, under the business-as-usual scenario, funds and efforts would not be sufficient to address current gaps in the institutional framework, particularly the emergence of a functional collaborative framework involving IBAP, DGFF, and other key stakeholders aimed at enhancing the management of forest-related biodiversity in Guinea-Bissau.

In conclusion, the country is set to benefit from a significant project baseline directed at the management of biodiversity and the SNAP in Guinea-Bissau. However, under the business-as-usual scenario the country is not expected to leverage or use relevant domestic budget allocations for biodiversity, and will remain almost exclusively reliant on such external project-based funding, which is generally unpredictable, insufficient and directed at particular sites or issues of donor interest – already some donors have expressed their hesitation to continue financing at the current level. Under the business-as-usual scenario, there are no concrete perspectives for leveraging capital into the FBG endowment meeting the minimum threshold required for it to become operational and eventually effective. At this point there are no other plans to operationalise other more innovative revenue sources. In fact under the business-as-usual scenario the already-made progress towards setting up a functional FBG will likely be reversed and previously made investments will be lost once the current projects draw to a close. Moreover, under the business-as-usual scenario important gaps would remain in PA management coverage and operational effectiveness, most especially with regard to CNP.

## PART II: Strategy

### II.1. Project Rationale and Policy Conformity

- Fit with the GEF Focal Area Strategy and Strategic Programme

The project is designed to strengthen the financial and operational framework of the SNAP in Guinea-Bissau and in doing so to contribute to its financial sustainability and management effectiveness. This is in line with the first Biodiversity Focal Area Objective (BD-1: Improving Sustainability of Protected Area Systems). Component 1 of the project will contribute to Biodiversity Focal Area Outcome 1.2: Increased revenue for PA systems to meet total expenditures required for management. This will be achieved by supporting the initial capitalization of the FBG, which has been designed and set up in compliance with the key recommendations identified by the GEF for the effective establishment of trust funds—the latter having been achieved through prior interventions by a World Bank-GEF project. Component 2 of the project will contribute to Biodiversity Focal Area Outcome 1.1: Improved management effectiveness of existing and new PAs. By operationalizing and enhancing the management of CNP and of connected buffer zones, the project will contribute to the expansion and improved management effectiveness of Guinea-Bissau’s SNAP.

- Rationale and summary of the GEF Alternative

The GoGB is seeking GEF support to remove the above-mentioned barriers that prevent the country from having a financially sustainable and effectivelly managed SNAP. Building upon the results of previous GEF interventions and coordinating with ongoing and other donor-funded projects (see Section IV, Part II), the project will pursue two interlinked approaches: a) increasing revenue generation for the SNAP by lifting barriers that impede full functioning of the FBG, achieving short-term endowment capitalization targets with project co-financiers and putting in place the foundations for the achievement of medium- and long-term targets; and (ii) strengthening effective PA management by IBAP to a critically threatened priority PA (CNP), while developing new operational frameworks that entail enhanced efficiencies through the involvement of the DGFF and local stakeholders. This will be an important next step towards a well-funded SNAP that conserves Guinea-Bissau’s highest biodiversity value ecosystems through PAs that are managed in a cost-effective manner.

As part of the first approach, with dedicated co-financing from the World Bank/IDA and EU-WAMER projects, the project proposed herein will lead to completion of management systems, due diligence, and compliance procedures triggering the direct capitalization of the FBG. GEF project funding will initiate the capitalization of the FBG endowment and thereby catalyze the long-awaited leveraging of funds from other already-committed co-financiers as a first crucial step towards the development of financial sustainability for the SNAP. During the PPG phase, negotiations for co-funding this capitalisation reached USD 6,065,248, bringing the total capitalization to USD 7,365,248, with USD 1,300,000 from the GEF.

The second approach would pilot new operational efficiencies in a pilot site by improving PA management capacity and effectiveness in the CNP. In doing so, the project will support the collaborative management of vital buffer zones and adjacent areas in close coordination with DGFF and other key stakeholders including the EU-GCCA+ project for reducing deforestation. This would also lead to strengthened institutions and enhanced institutional coordination between IBAP and DGFF, aimed at gradually reaching a consensus on conservation approaches, including their social and economic dimensions. Finally, systems and tools successfully demonstrated by the project in the CNP, especially for the management of forest biodiversity, will be generalized to support the ongoing and planned expansion of the forest PA reserve in Guinea-Bissau.

The CNP will be targeted by this project for a number of reasons. The CNP is critically important for the safeguarding of the most important remnants of tall semi-humid forest in Guinea-Bissau, which occur in 14 patches within the PA. With a human population estimated at around 24,000 residents living within the PA, pressure on biodiversity and forest resources in the PA and its periphery is inevitably high and continues to rise. Encroachment through shifting cultivation is the main driver of deforestation, while hunting reduces the populations of larger mammals with the partial exception of primates. CNP has therefore been identified by IBAP as the topmost priority for further strengthening the country’s PA network, in line with the 2007-2011 National Strategy for Protected Areas and Biodiversity Conservation (NSPAB). While the PA was legally declared in 2011, almost no financial resources have yet been mobilized for the government (IBAP) to intervene on the site, due to the systemic funding limitations affecting the SNAP. However, in view of past work through local NGOs (i.e., AD) and efforts such as the Fund for Local Environmental Initiatives (FIAL), among others initiatives, it is a potentially suitable demonstration site to develop and test a new model aimed at an efficient establishment of at least basic PA operations under the severe funding limitations prevailing in Guinea-Bissau (while ensuring at least minimal levels of sustainability through the activation of the FBG endowment). At the same time, the intervention is necessary to start consolidating dispersed activities under a structured management system and clearly defined goals. In addition, the World Bank (USD 500,000 budget) has worked in the area since 2007 to assess the potential of its forests to qualify for REDD carbon funding. The project proposed herein will prepare the ground by supporting improved PA management in order to achieve the avoided deforestation targets and will support the verification process on behalf of the Voluntary Carbon Standard (VCS). The REDD project – which is a unique pilot for the whole of Africa – can thus help catalyze the generation of carbon credits to be marketed, linking back to the issue of sustainable financing – a part of the expected revenues expected under the REDD project (altogether estimated to USD 15 million over 10 years) will start financing on-the-ground forest management actions in the CNP including both via IBAP and community benefit sharing, and another be channelled – as project co-finance – into the endowment capital of the FBG to generate sustainable finance for the SNAP.

The overall project goal is thus to strengthen the financial and operational frameworks of the SNAP. To achieve this, the project has two components that directly address the main barriers identified (see Section I.3).

### II.2. Project Goal, Objective, Outcomes, and Outputs/activities

The project objective is to strengthen the financial sustainability and management effectiveness of the SNAP in Guinea-Bissau. The project’s incremental approach consists of two components designed to deliver multiple global environmental benefits: Component 1 will strengthen the financial framework of the SNAP and Component 2 will strengthen the management effectiveness of the CNP and its buffer zone. The project components and the expected outcomes and outputs are described below.

- Component 1 – Strengthening the financial framework of the national PA system

This component will spearhead the capitalization of the FBG. While the full capitalization of the FBG endowment with over 28 million EUR (USD 34.88 million) explained above is realistically a long-term process, the project is designed to make a fundamental contribution by kick-starting and catalyzing this endeavour, presently considered by all key stakeholders as the most critical element for the future of biodiversity conservation and PA management in Guinea-Bissau. By investing USD 1,300,000 of GEF resources as initial capital, the intervention proposed under this component provides a unique opportunity to leverage funds towards the FBG and its endowment. During the PPG, commitments for the capitalization of the endowment were obtained from the GoGB and the MAVA Foundation, totalling USD 6,065,248. The MAVA Foundation pledged EUR 1,300,000 (c. USD 1,619,488). The GoGB commitments stem from two sources: firstly, from the GoGB-EU Fisheries Agreement (currently under negotiation) that is dedicated to the endowment for conservation actions, contributing USD 1,245,760. And secondly, from the pilot REDD programme being developed with support from the World Bank, the intended revenue of which will partially be made available to both the Endowment Fund and to support IBAP and community conservation measures on the ground; the GoGB commited an initial USD 3,200,000 from these REDD carbon revenues to the endowment capital.

The allocation of the GEF and already-committed co-financing resources to the endowment capital and to the accompanying activities of Component 1, respectively, is as follows:

| Source of funding | Component 1: Endowment capital (USD) | Component 1: Activities (USD) |
| --- | --- | --- |
| GEF | $1,300,000 | $ 500,000 |
| GoGB: EU-Guinea-Bissau fisheries agreement | $1,245,760 |  |
| GoGB/SEA: avoided-carbon revenues generated through REDD work in Guinea-Bissau | $3,200,000 |  |
| MAVA Foundation | $1,619,488 |  |
| World Bank: IDA Project |  | $374,400 |
| EU: WAMER Project |  | $384,000 |
| Subtotals | $7,365,248 | $1,258,400 |
| Total Component 1 | $8,623,648 |  |

The PPG moreover secured a good likelihood of obtaining an additional EUR 1,000,000 (c. USD 1,245,760) from the Fonds français pour l'environnement mondial (FFEM) for the FBG endowment; even if no co-financing letter could be secured because final processes and decisions are still pending. A decision is expected in mid-2015. With this additional amount, the FBG endowment would be capitalised with USD 8,611,008. The project will also aim to leverage further FBG income over the project’s duration, keeping the long-term endowment target of approximately 28 million EURO (USD 34.88 million) in view.

At an average return of 5.9% on the already-committed capital (USD 7,365,248), the annual financial contribution towards the management of the Guinea-Bissau’s PA estate is estimated to be approximately USD 434,550 by the end of the project (the revenue will evolve as the fund is capitalized during the life of the project). The FBG administrative costs are being covered mainly under the World Bank/IDA BCP until 2016; with project support from this GEF investment and its cofinancing partners, these costs will continue to be covered during the life of the project. The revenues generated from the endowment fund will be directed to the SNAP, contributing up to 30% of the overall annual recurrent funding needs. This strategy will also be designed to allow the FBG to pilot its grant-giving mechanisms during the life of the project. Development and implementation of a successful grant-giving mechanism that is directly linked to demonstratable conservation results will help to attract future financing contributions.

The full operationalization of the FBG will be a significant milestone for biodiversity conservation and PA management in Guinea-Bissau, while representing a model for the rest of the sub-region of what long-term and internationally collaborative efforts can achieve. In close coordination with other partners, activities under this component of the project would ensure that asset management is optimized in compliance with GEF best practices for trust funds. Investment guidelines will be developed to reflect a conservative risk strategy, the balanced diversification of FBG’s investment portfolio, the competitive selection of professional asset managers and the regular oversight of investment performance in relation to standard benchmarks; the investment guidelines will equally provide clear instructions and rules on the type of investment that the endowment fund will make, ensuring these are socially and environmentally responsible. Transparent and internationally recognized auditing and reporting protocols will be implemented to monitor and evaluate FBG’s achievements against time-bound targets and the effectiveness, efficiency and impact in the use of endowment, sinking and revolving funds at its disposal. On this basis, support from the project will enable the FBG and IBAP in briefing and providing information to annual donor meetings on progress and operational efficiencies of the FBG and on the needs and opportunities for further aid programmes. This will be coupled with targeted assessments of alternative revenue generation mechanism’s for Guinea-Bissau’s PA system including further work on REDD revenues and compensation schemes such as mining and timber concessions, fines, tourism fees, etc.

The allocation of resources generated by the FBG endowment will be governed by the FBG Board and guided by Guinea-Bissau’s national PA strategy. Detailed analyses will be undertaken of the predictability and sufficiency of revenue sources, and of the cost-effectiveness and efficiency in the use of available funding. This will be based on the assessment of capacity in the different PAs of the national network and the careful consolidation of site-specific data sets. Lessons learned from these experiences will assist in defining management and budgetary requirements for individual PAs in the national PA network. With support from the project (GEF and confinancing), IBAP and the FBG will quantify their intended impacts on biodiversity conservation and sustainable use, develop performance indicators and simple monitoring and evaluation (M&E) systems to measure progress and channel feedback into programme improvements and management decisions.

After 4 years, the Project’s outcomes will include:

1.1. – Initial capitalization of the endowment of the FBG with USD 7,365,248 increasing sustainability of PA system and consolidating terrestrial PAs of Guinea-Bissau by:

a) USD 434,550 of annual endowment revenues achieved by end of project, equivalent to around 30% of the overall annual recurrent funding needs , reducing vulnerability from over-dependence on donor funding;

b) Increase from 33% to 50% in the number and variety of funding sources to further capitalise the FBG and its endowment, increases the flow of recurrent revenues and the financial sustainability of the PA system, as measured  the UNDP/GEF Sustainability Scorecard (Component 3, Element 1).

c) Increase from 34% to 40% in the overall financial sustainability of the SNAP as measured by the Financial Sustainability Scorecard.

Output 1.1 – FBG Board and Executive Secretariat operating effectively and efficiently (including fiduciary and management systems)

The project will allow to strengthen the setup and operation of the FBG governance and management structures (Board and Executive Secretariat), such that they are operating effectively and efficiently in line with the Memorandum and Articles of Association, Operational Manual and other relevant legal and planning documents. Specifically, the project will support: a) the recruitment of additional Members to the General Assembly and Directors to the Board; b) General Assembly and Board operations, including Annual General Meetings and regular Board meetings; c) the establishment of specialized committees to oversee and guide implementation of specific aspects of the FBG mandate (e.g., investment committee, technical committee); d) reinforce the Executive Secretariat staff as required (e.g., grant officer, communications specialist, support staff), currently comprised of Executive Secretary and Financial Officer; e) day-to-day operation of the Foundation (e.g., planning, budgeting, accounting, banking); f) develop and implement capacity-building plan targeting specific themes (e.g., operation and grant-making procedures, fund-raising; and of budget development and control) for General Assembly Members, Board Directors, and foundation staff; g) annual donor meetings to inform them on progress and operational efficiencies; h) participation in international conservation trust fund-related meetings, to promote knowledge exchange and lesson sharing; i) support South-South cooperation and mentoring arrangements (currently with FUNBIO); and j) properly equip FBG’s office and staff and support operating costs.

The Foundation is in the process of putting in place the operational tools and systems necessary for its full operation. It is critical that FBG adopts internationally accepted and high-standard due diligence and compliance procedures. The project will ensure that these are developed in line with the reporting standards and requirements set out in its Articles as well as with International Best Practice, including the GEF’s 1998 “Evaluation of Experience with Conservation Trust Funds” and the recently approved CFA “Practice Standards for Conservation Trust Funds”. More specifically, the project will support a) the preparation/update of and development of key administrative and operational guidelines, including the Operational Manual, By-laws; Conflict of Interest Policy; and other instruments as required; b) the design and adoption of a fiduciary/financial system; c) the preparation of a multi-annual Strategic Business Plan for the Foundation with short- and medium-term financial projections and corresponding annual work plans, including yearly budgets; and d) a formal assessment of existing Governance, Operations, and Administration arrangements against CFA and other relevant standards and integrate these into ongoing monitoring program (see Output 1.2).

Output 1.2 – Transparent and internationally recognized auditing and reporting standards/protocols to monitor and evaluate the FBG’s achievements against time-bound targets and the use of endowment, sinking, and revolving funds at its disposal

This project output operationalizes the reporting standards and requirements set out in the Articles for the FBG and sets out a stringent performance monitoring plan and agreement. Whilst a part of the monitoring will focus on financial and institutional performance of the FBG, the monitoring plan will set targets in line with measurements of on-the-ground conservation achievements and impacts developed and feed by IBAP. Based on the initial FUNBIO “SNAP” analysis, priorities for investments and associated performance targets will be set, linked to the individual PA business plans, which are partially already developed. Priorities to be supported in a first phase will be decided by Board, based on IBAP’s strategy/priorities, and in consultation with stakeholders. Although the FBG Secretariat is housed within IBAP, it will retains a healthy degree of independence to be able to preserve oversight powers. The Activities under these outputs entail the following: a) develop a detailed M&E plan for different purposes and for different target groups, including FBG donors, Governments of Fund registration and operations, and against national and international conservation targets (including the Aichi Targets), using a participatory and  multi-stakeholder approach  for its development; b) in line with CFA and other relevant standards develop reporting, monitoring, and evaluation standards and plan (including M&E templates, reporting schedules, and assessments for grant recipients from FBG-managed funds), integrating relevant standards from all other outputs under this component; c) set up banking arrangements in the United Kingdom and Guinea-Bissau, in line with Articles and Operational Manual; d) continue support for accounting and legal agencies registered in the United Kingdom, for ensuring that documentation is prepared and filed in line with UK legal requirements on an ongoing basis, including Charity Commission, Companies House and Tax Authorities, and conduct yearly audits and as seen suitable; internal audits to be conducted if needed; and e) identify any other instruments needed to deliver to this output, including the development and implementation of a Policy on Conflict of Interest (national/international – applying international best practice), linked to Output 1.1 and other outputs under this component.

Finally, independent auditors will be recruited to conduct annual audits to confirm independence, assess management and performance, and provide feedback to FBG management, Board, financing partners and the public. Audited and approved documents will be submitted to CFA for resource sharing and set up a benchmarking system to monitor own performance among peers.

Output 1.3 – Pre-requisite due diligence and compliance procedures verified and formalised, and the FBG endowment capitalised with an initial investment of USD 7,365,248 through direct investment by the project and its co-financiers, and further enriched in a staggered approach in line with fundraising strategy

Internationally accepted and high-standard due diligence and compliance procedures will be adopted by FBG. Already existing standards and procedures for other conservation trust funds, United Nations Office for Project Services (UNOPS), or available through international audit firms can be applied. It is important to realize that the initial capitalization of the Endowment is just a first step in setting out and testing the setup of the fund, and that the further implementation of the fund-raising and capitalization strategy under Output 1.5 will follow suit. The main activities under this output include: a) procure consultants/firm to conduct a due diligence on compliance standards, processes and procedures etc., to ensure that best standards and safeguard are adopted; b) ensure that interest, investment income, and capital are not taxed either in the United Kingdom where fund is registered nor Guinea-Bissau, where it operates; and c) apply to endowment.

Output 1.4 – FBG’s assets management capacity is optimized to reflect the regular oversight of investment performance, as well as an appropriate risk strategy and balanced diversification of its investments portfolio, ensuring the latter is socially and environmentally responsible (details to be defined by the FBG Board)

Essential services will be recruited to support the FBG Executive Secretariat and the Board to make it fully operational. This will includee the competitive recruitment of an investment manager, responsible for managing the FBG’s investment portfolio, and an investment advisor who will provide oversight and guidance. In the future the option of pooling funds with other African UK based conservation trust funds will be explored, as a cost efficiency strategy. It is intended that activities of the investment manager would be guided and overseen by a Financial Committee (working in conjunction with the investment advisor), which in turn would report to the Board. Relevant capacities may be drawn from the established CFA pool of experts. The specific activities under this output include: a) procure experienced investment firm (or individuals) in the field of conservation finance (i.e., CTFs) through competitive processes to develop investment strategy; b) judicious investment of funds, according to the principle of lowest risk and highest return procedures by tapping into various level of financial expertise (i.e., Financial Committee/Board, FBG staff, and investment advisor); c) define optimal Financial Structure of the fund over time and risk strategy for the investment portfolio; reports developed and supervised on a regular basis on fund performance; d) develop social and environmental safeguards, in line with international best practice; and e) undertake formal assessment of existing Assets Management arrangements against CFA and other relevant standards and integrate into ongoing monitoring program (see Output 1.2).

Output 1.5 – Comprehensive fundraising/ capitalisation strategy in place involving FBG and other key stakeholders, and including inter alia (i) finely-tuned communications/ advocacy plans; (ii) annual donor meetings informed on progress and operational efficiencies of FBG; (iii) targeted in-depth assessments of potential revenue generation mechanisms (e.g., compensation schemes from mining and timber concessions, fines, tourism fees, REDD) and related enabling/ institutional needs

As part of the FBG’s first phase of fundraising, the project seeks to secure the initial seed capital for the FBG endowment, which, at an interest rate of 5.9%, is expected to cover up to 30% of the current system’s basic recurrent costs. The project will also support the participatory preparation and implementation of a capitalization strategy for the second phase of fund raising. This strategy will not only seek to increase the capital contributions to the endowment fund, but will also explore complementary sinking and/or revolving fund options. To this end, linked to the above-mentioned update/ refinement of the financial strategy for the SNAP and the FBG, the project will facilitate: a) development of financial projections with varying scenarios, including the further update and refine analysis undertaken by FUNBIO, and improve the Financial Sustainability Scorecard (BD-1 Tracking Tool); b) develop a detailed, standardized, and realistic framework for determining the demand and projections (with varying scenarios) of finance fund management, IBAP, and the SNAP, including planned and actual expense sheets; c) promote multi-stakeholder brainstorming meetings to solicit guidance and to inform the fund-raising/capitalization strategy; d) preparation and implementation of a detailed multi-year fundraising strategy and action plan, as well as annual work plans and budgets; e) conduct of regular gap analyses to inform investment planning and, subsequently, the adaption of the fundraising strategy; f) training of FBG staff and Board members in fundraising, as needed; g) implementation of fundraising events, publications, public relations, and other and marketing activities; h) formal assessment of existing resource mobilization arrangements against CFA “Practice Standards for Conservation Trust Funds” and relevantr other standards, integrating this into the ongoing monitoring program (see Output 1.2); and h) establish a donor committee/group to support fundraising and supervision.

Given the country’s extreme poverty and limited economic opportunities, and the competing demands for scarce government budgetary resources, it is likely that identification and setup of alternative financing mechanisms will take time. Nevertheless, if these are to be realized, the process of identification, assessment of feasibility, design and negotiation of related enabling/institutional needs to be launched now with the interested parties. To this end the project will support the identification and exploration of potential options, as well as efforts to sensitize and launch a dialogue amongst key stakeholders for at least two of the identified options with the most immediate potential.  Potential options identified by the preliminary financing strategy as meriting further exploration in the near term include: REDD, debt for nature swaps, fines for environmental damage and/or pollution, compensation for mining, forestry or petroleum concessions. Other possibly more medium term options include: tourism taxes, visitation fees, and green lotteries. It is moreover recommended that the project consults the UNDP Biodiversity Finance Initiative for additional guidance.

Output 1.6 – Strong communication and public relations strategy implemented, ensuring ongoing conversations with national and international partners (GoGB, donors, and private sector) and minimizing risk of government interference while creating ownership

Although the FBG has the full blessing of the GoGB, the risk remains that political interference may hamper its performance and actual existence under extraordinary circumstances. Experiences from other conservation trust funds around the world point to the importance of developing and implementing well-targeted communication and public relation strategies to ensure that all relevant stakeholders within country and internationally understand the full intention as well as performance of a conservation trust fund. In order to develop a strong communication plan and promote good public relations the activities to be supported include: a) identification of key target groups and communication needs; (ii) stakeholder consultations; (iii) design and implement a communication strategy and action plan (iv) provide relevant communications training for all FBG (and relevant IBAP) staff, including the Board, to reach different stakeholder groups and manage conflict that may arise.

- Component 2 – PA and buffer zone management in Cantanhez NP

This component will provide basic management effectiveness to CNP, thereby closing the top-most priority gap in the overall SNAP of Guinea-Bissau. In doing so it will further improve the representativeness, connectivity and management capacity of the terrestrial portion of the Guinea-Bissau SNAP. This will involve the piloting in CNP of a shared vision and training programs between IBAP and DGFF, spearheading the alignment of policy objectives and the creation of a functional collaborative framework. Improved coordination between the two institutions will also be critically important to catalyze the engagement of local communities and other key stakeholders in a better aligned management of biodiversity and ecosystem services in PA buffer zones and adjacent areas, with the aim to reduce the pressures exerted by resource users on the PA and thereby additionally rendering PA management more cost-effective. While addressing the main barriers identified, this component will focus on several related and parallel activity streams:

After 4 years, the project’s outcomes will include:

a. Collaborative cost-effective management of CNP and related buffer zones and forest areas improves management effectiveness at 19.6% over baseline levels as measured by the Management Effectiveness Tracking Tool (METT).

b. Improved management effectiveness reduces threats as measured by: (i) the reduction in the illegal utilization of woody vegetation and deforestation rates; (ii) reduction in the recorded levels of poaching.

c. Reduced the loss of critically threatened West African forest habitats across c. 105,800 ha of PAs and surrounding zones and improved protection to globally significant species and other key biodiversity resources in the Forest Belt biome.

d. Level of satisfaction of local community members (differentiated by gender) collaborating with PA and forest management (Indicative assessment categories: Highly Unsatisfactory, Unsatisfactory, Moderately Unsatisfactory, Moderately Satisfactory, Satisfactory, and Highly Satisfactory) (baseline and target will be established during the first year of project implementation).

e. Increase in cash or in-kind benefits returned to local  communities (beneficiaries differentiated by gender) as a result of biodiversity-friendly economic activities (baseline and target will be established during the first year of project implementation)

Output 2.1 – Operational capacities of CNP consolidated to permit compliance with at least basic functions through (i) primary operational logistics and equipment; (ii) training programmes for IBAP staff (involving DGFF and other PA management council members) with special emphasis on PA planning and management, community engagement and conflict resolution techniques, forest management challenges and approaches; iii) underpinning support to IBAP headquarters

The CNP (105,800 ha), including its vital buffer zones (44,713 ha), will be made operational and reinforced to permit compliance at least with basic management functions. The project will allow IBAP to reassess short-term needs using initially the existing business plan (2013) for the CNP in order to identify the primary operational logistics and equipment for specific staff positions, and training needs of staff needed to ensure that the implementation of project activities are initiated on a timely manner and with the basic needed operational resources in place. This will include the development of a precise and realistic immediate (1-year) operational plan and will include functional office facilities and the provision of basic equipment and logistics, including communication, transport, and research, as well as staff costs. Once the CNP management plan is updated (see Output 2.4) operational programing will be adjusted to respond to medium- and long-term needs identified as part the new planning process.

In addition, the project will facilitate the strengthening of management capacity of IBAP and DGFF staff, as well as local stakeholders (e.g., PA management council members) with responsibilities in public and community forest management and PA management, with a particular focus on the CNP and its periphery. A capacity development plan will be developed, which will include a capacity needs assessment focusing on strengthening PA management, biodiversity conservation and forest management functions and specific skills required by the two institutions, including law enforcement, policing and control, biodiversity and forest surveying and monitoring, community engagement, conflict resolution techniques, and reporting, among other topics. Training modules and materials will be designed and at least 50 IBAP and DGFF officials, PA and field staff, as local stakeholders (including women), who will be trained by the end of the project through workshops, seminars, and short thematic courses, as well as field visits to the CNP and its buffer zones to engage in the sharing of knowledge and experiences, and to strengthened coordination and mutual cooperation between the two institutions. The impact of the training and capacity building will be assessed through interviews and follow-up, including the use of project capacity development indicators (Capacity Development Scorecard). The scorecard will be applied initially during the first 6 months of project implementation to stablish a baseline, and twice more during the life of the project: at the mid-point and finalization.

Capacity-building will be maintained throughout the four years of the project; the project team, in close collaboration with IBAP officials will be responsible for coordinating the implementation of all training activities. Strengthened capacities for biodiversity and forest surveying and monitoring will serve as a basis for measuring related indicators included in the Strategic Results Framework (see Section 3.2 of this Project Document) to assess the overall impact of the project and the delivery of global environmental benefits, and will include the development monitoring and surveying protocols. Training will be delivered through the government, universities, and/or private agencies (i.e., public-private partnerships). In addition, it will include South-South exchanges on best practices in PA and buffer zone management in West Africa. Finally, close coordination and partnership will be established with EU-funded project GCCA+ in Guinea Bissau: building resilience to climate change through enhanced institutional and mitigation capacities, which will also contribute to the consolidation of the CNP and will provide support to IBAP through co-financing.

Output 2.2 – Strengthened institutional capacity of DGFF and IBAP for effective oversight of land use and threat reduction in PA buffer zones and related forest areas through (i) joint DGFF-IBAP planning and collaboration programming in priority high risk areas; (ii) joint DGFF-IBAP training programmes with emphasis on EIAs, law enforcement, licensing and monitoring of economic activities in and around PAs, PA management challenges and approaches.

A strengthened and better aligned enabling environment involving IBAP, DGFF, and other key stakeholders will be supported by the project in order to promote the effective management of viable buffer zones and adjacent areas. The effective collaboration of IBAP and DGFF will be critical in tackling the complex socio-economic reality prevailing in and around CNP; for example, this should ensure that use permits issued by DGFF are consistent with PA and community-based forest management goals defined by IBAP and other key stakeholders.

Enforcement and control plans will be developed jointly between IBAP and DGFF and implemented in a coordinated manner. Enforcement and control plans will serve as critical tools to provide operational guidance for IBAP and DGFF staff in the field and will focus on reducing existing threats to biodiversity in PA buffer zones and related forest areas targeting illegal logging, uncontrolled slash-and-burn/forest fires, and poaching, among other threats. These plans will include a detailed assessment of the threats and stakeholders/sectors exerting pressure on the CNP and buffer zones, placing special emphasis on EIA and the licensing and monitoring of related activities in and around PAs, given the high level of logging pressure currently experienced throughout the Forest Belt region, including such exerted from foreign companies. This will include the participation of CAIA, the unit within the SEA that is mandated to ensure EIA functions within Guinea-Bissau. Additionally, the plans will include: a) objectives and threat reduction targets; b) zoning, identifying high risk and ecological sensitive areas, including biological corridors and hotspots for biodiversity of global importance; c) prevention and control activities (i.e., patrolling, boundary enforcement, reporting of violations, and reporting of illegal activities, and instructions on how to proceed when confiscations of biodiversity, timber, and/or related products); d) timeline of activities; e) budget assessment and resource allocation, including the allocation of funds by IBAP, DGFF and other institutions with responsibilities for biodiversity conservation, forestry and land-use planning in CNP and buffer zones; f) and implementation and evaluation of the plan. Enforcement and control plans will be in line with the management plan of the CNP and connected buffer zones and ecological corridors (Output 2.4) and will be implemented as part of annual management activities. In addition it will include the participatory monitoring of biodiversity and forest resources in line with the project’s Strategic Results Framework (see Section 3.2 of this Project Document) to assess the overall impact of the project and the delivery of global environmental benefits and focusing on critical areas as define by the zoning exercise.

IBAP and DGFF staff will be equipped and trained so that they can carry out planning and enforcement activities more effectively. Training will emphasize EIA, law enforcement, licensing and monitoring of economic activities in and around PAs, PA management needs, and approaches. In addition, the project will strengthen DGFF and IBAP ability to monitor land use/land cover (LU/LC) change in PA buffer zones and related forest areas using remote monitoring to assess threats from the expansion of agriculture, cattle-ranching, aquaculture, and other land uses. Remote monitoring will include the use of satellite imagery with field verification with the participation of local communities to assess LU/LC change and the incorporation of results into PA and buffer zone planning and management. Training will be articulated with related capacity events of Outcome 2.1 to maximize effective inter-institutional cooperation and coordination between IBAP and DGFF, and will include project capacity development indicators (Capacity Development Scorecard) to assess the impact of training.

Enforcement and control plans will also include an awareness-raising campaign so that the different stakeholders (e.g., local communities, civil society organizations [CSOs], NGOs, and the private sectors) are aware of the permitted activities and restrictions, including knowledge about the existing norms and rules (including sanctions), regarding natural resources use in the PA and buffer zones. Protection and control plans will be developed through coordination meetings by field staff, with the support of technical personnel, and will be approved jointly by IBAP and DGFF top officials. Periodic meetings (at least four per year) will be held with the participation of IBAP, DGFF, and other key stakeholders (e.g., CNP Management Council, local CSO, etc.) to present results, and discuss and update the protection and control plans as required.

Output 2.3 – Local community involvement in and collaboration with PA and forest management  improved by (i) strengthening PA management council and related public participation and institutional arrangements for negotiating, implementing and monitoring management and collaborative agreements; (ii) training programme including conflict resolution mechanisms, and community surveillance and enforcement; (iii) the development of biodiversity-friendly economic activities

Local community involvement and collaboration with PA and forest management will be improved by strengthening the Management Council of the CNP, which has been operating since the establishment of the PA in 2008 and that includes the Director of the CNP, representatives of communities living in the national park; representatives of government agencies, representatives of CSOs (grassroots) associated with the CNP, and representatives of operational development partners (POLs). The existing CNP management plan resulted from a participatory process and its implementation is being overseen by the CNP Management Council. The CNP management plan will be updated (Output 2.4) and the CNP Management Council capacity will be strengthened to better fulfill its role and contribute to overcoming the threats to biodiversity and the CNP that still persist.

The project will strengthen the ability of local communities and CSOs within and around the CNP to establish and participate in collaborative agreements with IBAP, DGFF, other government agencies, and NGOs for the management of the CNP and the protection and sustainable use of forest-related biodiversity, including compliance with the sustainable use of forest products and the use of biodiversity-friendly production methods. To this end, the project will map all key stakeholders in PA forest resource protection and management within and around the CNP that need to be involved in collaborative agreements jointly with the local communities and CSOs. Additionally, the project will implement activities to raise awareness among these local communities and CSOs about the importance of collaborative management for: a) achieving biodiversity conservation goals; b) evaluating and monitoring the implementation of sustainable economic activities and specific actions in and around CNP for the reduction of threats; and c) for resolving potential conflicts regarding resource use and conservation actions.

As part of the strategy to strengthen local community involvement and collaboration with PA and forest management, a training program will be implemented to improve existing conflict resolution mechanisms and participation of local communities in monitoring, surveillance, and enforcement activities. The training program will consist of: a) a participatory assessment of existing mechanisms of conflict resolution and local participation in surveillance and control activities to identify gaps and needs, including establishing a baseline using capacity development indicators; b) the design of training modules and materials jointly with PA and forestry authorities and management council members, and training a least 50 local community members through hands-on workshops and field-based activities (e.g., patrolling, monitoring, boundary enforcement, management of wildlife and local land use conflicts, reporting of  conflicts and of violations, and procedures for the sanction of infractions) and by providing information and raising awareness about existing PA and forest management laws and regulations; and c) a participatory assessment of the impact of the training program through interviews and follow-up conducted in the field regarding what was learned and the perceived effectiveness of the participatory enforcement and control system, as well as the reapplication capacity development indicators.

In the past the CNP has benefited from local-level actions by resident communities living within and adjacent to the CNP. This has also involved local and national NGOs (including AD, TINIGUENA, and DIVUTEC) with support from international organizations and donors such as IUCN, the World Bank and the EU. The project will continue to engage these and other relevant local communities and NGOs through public participation in project implementation (i.e., PA management under the leadership of IBAP), with a view towards effective delivery and cost-efficiency.

Sustainable development activities in the CNP have focused on the sustainable use of natural resources through strengthening the socio-economic development of the local stakeholders present in the PA. From 2005 to 2011, the World Bank, the GEF, the EU and IUCN provided support to the GoGB to protect large areas of coastal mangroves and forests through the Coastal and Biodiversity Management Project (CBMP; GEF ID 1221). The CBMP efforts led to the establishment of FIAL, a benefit-sharing mechanism aimed at alleviating pressure on biodiversity and ecosystems while simultaneously helping local communities improve their well-being. Through FIAL, environmentally-friendly community development initiatives (i.e., micro-projects) in PAs were funded, including initiatives such as the rehabilitation of rice fields, bee-keeping, palm oil extraction, fish processing, constructing wells, and building schools. FIAL-funded local initiatives were evaluated as a cost-effective way to achieve conservation and local development goals. The FIAL model is highly participatory as local communities determine their own developmental needs and the funding is approved by a committee consisting of PA authorities, community representatives, and Management Councils, ensuring that these are compatible with conservation goals. The project will follow the FIAL model for implementing biodiversity-friendly economic activities, which may include traditional low-impact and low-input rice production (using lowland bolanhas and pluvial rice), sustainable fruit and horticulture production, agro-forestry and silvo-pastoral systems, bee-keeping, and sustainable small-scale fisheries, among other activities.

Mechanisms for financing biodiversity-friendly economic activities to be implemented by local communities will include improved CNP management for the achievement of avoided deforestation targets under the REDD project Community-Based Avoided Deforestation Project in Guinea-Bissau; the validation of the REDD project is being implemented by IBAP with the support of the World Bank. The related reductions in deforestation rates in and around CNP will be a result of the improved forest and PA management supported under this project (including the EU-GCCA+ co-financing activities). The project will also provide support for verifying actual emission reductions on behalf of the VCS. This independent auditing process will ensure compliance with VCS requirements for environmental integrity, a necessary step to be taken prior to the sale of carbon credits. The expected revenues from the REDD project will provide a sustainable and stable flow of funds to IBAP that will be used to cover CNP management costs, and for the SNAP as whole, and to support biodiversity-friendly economic activities that will be implemented by the local communities. IBAP will provide technical support in implementation and monitoring of biodiversity-friendly economic activities, and will operate the micro-finance mechanism with support from the UNDP Country Office (CO) to ensure that the communities in and around the parks realize direct and tangible benefits from forest and mangrove protection. In addition, the project will deliver additional mechanisms for financing biodiversity-friendly economic activities through grants and incentives.

Output 2.4 – Management and business plans for CNP and connected buffer zones and ecological corridors updated/produced, allowing the coordinated identification, prioritisation of management activities and allocation of funds by IBAP, DGFF, and other institutions with responsibilities for biodiversity conservation, land use planning, and forestry

The project will support the updating of the management plan for the CNP, which will constitute the governing document for conservation, land use planning, management, and the administration of the protected area. The existing management plan was developed in 2008 for a 5-year period and is now outdated. The existing management plan has as its main objective the implementation of a long-term strategy for the sustainability of the existing natural resources based on the conservation of humid forest patches and their associated biodiversity. This objective will be revised considering conservation progress to date, as well current land uses, threats, and public/local participation in management. More specifically, the updating of the management plan will include: a) integration of the planning team, which will consist of IBAP staff ( headquarters and PA staff), representatives from other government agencies, (e.g., CAIA, DGFF), representatives from the CNP Management Council (i.e., communities living in the CNP, CSOs associated with the NP, local authorities, etc.), and technical experts in various disciplines; b) establishment of the methodology for management update emphasizing the participative nature of the planning process; and c) structuring of the management plan into specific components to facilitate its implementation, including: i) Descriptive Component: describes and assigns value to the NP’s environmental and cultural attributes; ii) Management Considerations Component: identifies the NP’s primary conservation objectives, determines threats and conflicts, establishes the uses of the area, and agrees the zoning of the PA and its buffer zones; iii) Operational Component: establishes the management actions based on an assessment of existing gaps and needs regarding conservation of habitats and species, research, sustainable development (i.e., sustainable use of natural resources and biodiversity-friendly economic activities), training and capacity development, awareness and communication, basic social infrastructure, financing, and conservation and rational use of natural resources of specific importance for local communities; iv) Regulatory Component: defines the regulatory aspects of the CNP, including internal regulations (daily operational guidelines and rules for the PAs agreed with the stakeholders), participatory patrolling and surveillance, reporting and sanctioning of illegal activities, and resources use conflict resolution; and v) Follow-up and Evaluation Component: participatory evaluation mechanisms and tools to assess the effectiveness of implementation of management measures and facilitate decision making (i.e., corrective measures and adaptative management), including use of impact indicators to assess biodiversity and socioeconomic benefits.

The updating of the management plan for CNP will rely on stakeholder participation, particularly in the local communities and resource users that live in and around the NP and depend upon them for their livelihoods. In addition, the management plan will be science-based, including designs to strengthen ecological/wildlife corridors between CNP and other PAs (e.g., Dulombi NP and Cufada Lagoons NP) and following accepted guidelines (e.g. IUCN, CBD and others). Once the updated management plan is drafted, meetings and workshops will be held with CNP and buffer zone stakeholders for their final input, as well as to raise awareness and to establish organizational arrangements for its implementation. Final approval of the updated management plan will be made by IBAP and will be published and made available nationally and locally (local communications materials will include posters/pamphlets/radio shows for dissemination in different local languages). The CNP management plan will be updated during the first 18 months of project implementation under the supervision of the CNP Management Council and with broad representation of local stakeholders. The new management plan will be valid for 5 years and will be implemented through annual work plans.

In addition, the project will develop a detailed business plan for CNP. The business plan will be developed simultaneously with the management plan during the first and second years of the project and will be responding to the management financial needs for its implementation. The business plan will include: a) evaluation of the specific financial needs and gaps (i.e., basic and optimum cost analyses) using as reference the management plan; b) evaluation of viable government and private funding sources (e.g., incentives, grants, loans) including by sectors (fishing, forestry, ecotourism, agriculture, and NTFP) and potential revenue generation mechanisms (e.g., ecotourism/visitors fees, fines, and REDD revenues expected for forest/biodiversity conservation and local communities); c) cost vs. revenue analysis; d) developing financial scenarios (short-, medium-, and long-term) to respond to immediate operational needs (one year) and multi-year financing need to achieve medium-term and broader management and conservation objectives, including indicators to assess progress (secured funding) and maximize performance (achievement of conservation goals); and e) fundraising strategy to better engage donors, the private sector, and the government, and taking full advantage of available funding opportunities, including the allocation of funds by IBAP, DGFF, FBG and other institutions with responsibilities for biodiversity conservation, land use planning, and forest management.

The business plan for the CNP will be developed in coordination with IBAP officials and the CNP’s Management Council and drafting and approval of the business plans by IBAP. Efforts for securing new financial resources for PA management will begin by year 2 of project implementation and will continue until project completion, under the guidance of the project team, IBAP, and with the support of a financial/fundraising expert and in close coordination with the FBG (Output 1.5).

### II.3. Project Risks

Project risks and risk mitigation measures are presented in Table 4. Refer to Annex 6 for the Guiding Risk Assessment Matrix.

Table 4 – Risks facing the project and the risk mitigation strategy

| Risks | Level | Mitigation |
| --- | --- | --- |
| 1. The capital invested in the FBG endowment and the revenue generated are diverted from their purpose, (i.e., not used for the conservation of biodiversity and management of PAs) | Low | The governance of the FBG and its setup as a charity under English and Welsh law will guarantee institutional independence and accountability towards the donors over the long term. The FBG is set up in compliance with benchmark trust fund requirements (GEF, World Bank, UNDP, CFA). |
| 2. The global economic and financial crisis leads to reduced funds from international donors, and causes consistently lower returns on the endowment over the long term | Low-Medium | The initial capitalization of the FBG endowment fund with USD 7,365,248 through the current project is one of the best mitigation responses to Guinea-Bissau’s high vulnerability to unpredictable and declining donor funding. In addition, the FBG will engage in more proactive promotional activities that involve some key players and institutions involved in the conservation of Guinea-Bissau’s biodiversity (including IBAP, UNDP and others) to leverage further contributions. The project will conduct an in-depth analysis of more general financing mechanisms that can be applied in the country to broaden the spectrum of income sources – for the endowment but also for sinking and revolving funds. Although interest rates and investment returns have been relatively low in recent years, historical data suggest that it is reasonable to assume an average 5.9% return on the FBG investments over the long term, which is the rate reflected in the proposal, following the FUNBIO study. Possible fluctuations in future returns will be taken into account in the design of the investment and grant-making strategies. |
| 3. Institutional agreements involving IBAP, DGFF and other key stakeholders do not function properly, undermining the effective governance and management of CNP and the forests in its periphery | High | This is a critical element of the project. An effective collaborative framework between the two lead institutions has not yet been put into place and tested, and misaligned approaches prevail. Hence, based on the precautionary principle, the risk is presently flagged as high. Great attention will be paid during the project preparation phase to coordinate closely with IBAP, DGFF, and other key stakeholders at the national, regional, and local levels. Practical tools and formal protocols will be established to ensure the effective co-execution of the project by the two leading partner institutions. Joint training and capacity-building are envisioned as well as a review of policy and legislative frameworks and of institutional mandates, proposing amendments where appropriate and in the clear interest of improved PA management and forest biodiversity conservation. |
| 4. Political interference disempowers the FBG and leads to its collapse | Medium | The careful setup of the FBG and its legal arrangements may secure investments abroad and instil donor confidence; however, it may also disenfranchise national stakeholders. Donors may be seen to manipulate national affairs, and competition for revenue generated from the endowment may erupt – although the careful setup has taken all possible legal issues and actions under consideration. It is critical that the FBG invests in dedicated communications, information-sharing and public relations on an ongoing basis to ensure that any potential misconceptions be addressed systematically. Output 1.6 has been included in the project design to address this risk specifically. |
| 5. The impacts of large-scale enterprises in sectors such as logging or mining reduce the viability for biodiversity conservation of the CNP and its connected buffer areas and biological corridors. | Medium | This risk is precisely why this project in CNP is so critically important, and the enhanced PA management and law enforcement in conjunction with already sensitized communities is the best response. Specific training and capacity-building measures for EIAs and the licensing and monitoring of economic activities will target PA staff and personnel from IBAP and DGFF at the regional and national levels. In addition, the participation of the CAIA, which is attached to the SEA, was actively sought during project preparation and will continue throughout the implementation phase. |
| 6. Political and institutional instability disrupts minimal governance conditions necessary for project implementation | Medium-High | The political and governance situation in the country has recently seen significant improvements, yet a degree of instability and governance challenges remain that may affect the enforcement of existing PAs. However, IBAP has effectively operated under similar conditions in the past, even if minor disruptions may occur that cannot be prevented; wherefore the risk appears manageable. |
| 7. Climate change could have a negative impact on key biodiversity and ecosystems in Guinea-Bissau in general and in the CNP and adjacent areas in particular, undermining project achievements. | Low-Medium | Some of the climate change trends that have been observed, or can reasonably be expected, are related to increasing sea level and wave energy causing coastal-zone erosion and salt water intrusion, increased variability in rainfall/rainy season, more frequent uncontrolled fires, and changes in ecological communities and ecosystem functionality. However, the SNAP that the GoGB has established, the management of which is ensured through IBAP, besides covering an important portion of the country’s territory, also makes ample provisions for ecological corridors between individual PAs that are expected to increase the resilience of the ecological systems and its constituent species. The extensive mangrove areas remaining in the country (and which are well covered in the SNAP) mitigate the impact in terms of coastal erosion. In the CNP specifically, the PA management plan in its updated version will integrate climate change considerations in terms of adaptive management of biodiversity and natural resources in the PA and adjacent areas, to the best possible degree given knowledge constraints. The project will contribute to consolidating corridors between CNP and other PAs, enhancing the resilience of ecosystems and key species to climate variability and change. Over the longer term, sustainable recurrent revenues from FBG will allow IBAP and its PA/biodiversity management partners to strengthen monitoring efforts, generating more information and allowing enhanced adaptation of management and conservation strategies in response to climate change-induced trends. |

### II.4. Cost-effectiveness

This project has been developed using cost-effectiveness criteria and focuses on removing the institutional, financial, and technical barriers that prevent a financially sustainable and effectively managed SNAP in Guinea-Bissau and the reduction of threats to coastal-marine and terrestrial biodiversity of global importance. The project proposes a strategy consisting of two complementary components. First, the project leverages a catalytic investment in securing the long-term financial sustainability of the SNAP in Guinea-Bissau. Second, the project implements a collaborative-cost effective strategy for improving the PA and buffer zone management in the CNP.

Component 1 of the project focuses on securing a minimum investment in an endowment fund that will be managed by an already established foundation (FBG); however, this foundation is as of yet only marginally operational. Leveraged co-financing and project management allocations will initially support the FBG to further establish its operations and secure management and fiduciary standards of the highest international standards to ensure the endowment investments are securely and profitably managed. It is envisaged that the FBG will be self-sufficient after the project intervention absorbing between 12-17% depending on the scenario of yearly funding, and will focus on increasing the endowment capital as well as diversifying financial revenue through implementing a targeted fund-raising strategy during the project’s lifetime.

The project is considered cost-effective for the following reasons:

- Supporting the operationalisation of a sustainable financing mechanism is arguably the best and most cost-effective solution over the long term to support Guinea-Bissau’s SNAP, given that the likelihood of obtaining stable funding flows from public sources is minimal due to the country’s extreme poverty, and because flows from external donors are unpredictable and sometimes skewed to particular actions or regions/PAs.

- The independence of the particular mechanism (the endowment of a conservation trust fund, the FBG) is vital to guarantee continued SNAP support in the event of further/renewed instability (political, governance, institutional) in the country. CTFs have been recommended as an effective financing mechanism especially in countries with a certain degree of instability and uncertainty; justifying the assignation of the available resources into the FBG’s capital. The overall cost-effectiveness of conservation investments in the country could be seriously undermined if existing achievements were lost due to such instability and the loss of any conservation action; the sustainable revenue generated by the FBG’s endowment capital is expected to impede this scenario.

- A modest investment in the continued and well-founded existing efforts for the operationalization of the already-existing FBG over the next four years will leverage the institutional capacities for mobilizing a sustainable financial mechanism that contributes significantly to increasing, diversifying, and stabilizing the financial flows to PAs in Guinea-Bissau. As a result of the project investments, it is anticipated that by the end of the project the PA financing gap will be reduced by around 30%. Over the long term (>20 years), it is envisaged that the SNAP, with support from the FBG’s sustainable financing mechanism, will continue to reduce its dependence on external donor funding support to up to 50% of its operating costs.

- In addition to the initial capitalization to be achieved over the lifetime of the project, support for the initial ongoing operating costs of the FBG are expected to help leverage a much greater capitalization of the endowment fund, aiming at the target EUR 28 million (USD 34.88 million) in the medium to long term.

- The average anticipated cost for FBG lies at USD 236,695-352,550 (EUR 190,000-283,000) per year, which would require an endowment of at least USD 4-6 million (EUR 3.2-4.8 million), respectively, just to cover the FBG operational costs alone. The SNAP/FBG financing strategy proposes an average operating cost for the FBG on the order of 12% to 17% of the anticipated endowment revenue flows over the long term, once capitalization targets are met. During the project’s lifetime the operational costs of the FBG will be covered, wherefore the revenue generated over the capital are fully available for SNAP action. After project end, in the short term, FBG will need to be covered by a blend of project financing and a share of the capital interest revenue generated; this indicates that further capitalisation of the FBG endowment should be secured as fast as possible to generate. Once the capital target is achieved however, the FBG running cost of 12-17% of revenue from capital are well below other “overhead” charges, which according to GEF often range between 20-25%.

The project’s cost-effectiveness is based on improving revenue from a range of existing and new financial products through the exploitation of scale and scope economies, improving the cost-effectiveness of operational management costs of FBG, and supporting the financial planning and management capacity of PA institutions and communities.

Alternative approaches could include the use of the available resources for a standalone GEF investment into several PAs, without investing in the already established FBG. That scenario would presumably achieve an immediate and strong effect in the targeted PAs, but sustainability considerations would potentially fare poorly. And as indicated in the cost-effectiveness summary above, conservation investments in the country could be seriously undermined if existing achievements were lost due to renewed political instability, and the decision to assign a substantial part of the available resources to the FBG endowment capital counters that risk.

Component 2 improves the participatory and collaborative management effectiveness of CNP and its buffer zones, thereby reducing threats to and the loss of critically threatened wildlife, at the same time benefiting local communities through strengthened local governance, capacity-building, and implementation of biodiversity-friendly economic activities. Under the GEF scenario, basic PA operations will be funded while simultaneously the FBG endowment is operationalized so that it can start to generate economic returns that will provide some level of financial sustainability to the CNP and the SNAP, overcoming its operation under limited management budgets and dependency on external funding. The GEF scenario will also help to consolidate dispersed activities under a structured management system and clearly define goals for the CNP and its buffer zones, contributing to effective biodiversity conservation and forest management. In addition, the GEF scenario will improve PA management in order to support the achievement of avoided deforestation targets under a REDD project that is underway in the CNP, as well as the verification process on behalf of the VCS; these actions will facilitate the generation of expected revenues from the REDD project (sale of carbon credits) and will be cost-effective as REDD revenues will finance on-the-ground sustainable forest management actions in the CNP and its buffer areas. Finally, the GEF scenario will improve local governance for sustainable natural resource use and will raise awareness among local communities about the importance of biodiversity and ecosystem services conservation. The GEF scenario will support the implementation of biodiversity-friendly production practices by replicating micro-project type models successfully tested under a past GEF intervention (GEF ID 1221), responding to PA management and local community needs. These activities will be cost-effective as they will promote a behavioral change with a low investment that will largely pay itself once REDD revenues, together with other leveraged resources (e.g., grants and incentives), start flowing towards local communities to support biodiversity-friendly production practices.

The alternative management scenario is one in which limited skills and funding and the lack of collaborative efforts between PA managers (IBAP) and forest managers in buffer zones (DGFF) will prevail, putting them in a disadvantageous position to face the current threats to the PA and biodiversity. This will prove costly over time as future actions will require larger investments when it is not possible to act on them in a timely manner. In addition, the CNP and its buffer zones have outdated management plans that must be updated to consider the conservation needs of the wider landscape in order to reduce the increasing pressures on biodiversity from other land uses. The CNP’s management financial needs are currently addressed by following a business plan that responds to short-term needs rather than to strategic planning that considers basic and optimal scenarios, short- and long-term investments, and facilitates adaptive management. Finally, under the alternative management scenario participatory PA management will continue to be weak as there will be limited incentives for local communities living within and around the CNP to reduce pressure on forests, mangroves, and coastal resources.

### II.5. Project consistency with national priorities/plans:

The project is consistent and fully in line with national plans, priorities and policies. The 2014-2020 National Strategy for Protected Areas and Biodiversity Conservation (NSPAB), under strategic objective N.1 for institutional strengthening, calls for the implementation of a sustainable financial mechanism supporting the PA system and the operationalization of the FBG. Under strategic objective N.2, the NSPAB calls for the strengthening of the management effectiveness of PAs and for sustainable development within PAs with the active participation of PA stakeholders, including local communities. The project is also in line with the National Forestry Policy (2010), the Forestry Master Plan (2010), and the recently revised Forestry Law (Lei Florestal, Decree-Law No. 5/2011). Collectively, these texts set out a new vision for the preservation of forest resources in Guinea-Bissau, acknowledging the vital role of PAs and the necessity of establishing a collaborative framework involving local communities and other key stakeholders such as IBAP. The Forestry Master Plan specifically indicates the need to improve the institutional alignment and coordination between IBAP and DGFF – which the project proposes to pilot in the CNP with implications for forest management in PA buffer zones at the national level. Finally, the project is also consistent with the National Adaptation Plan of Action (NAPA 2007) which, based on the negative influence of climate variability, recognizes the need to enhance the sustainable management of ecosystem services as an important adaptation option.

### II.6. Country ownership: Country eligibility and Country Drivenness

The GoGB is a party member of the CBD (October 27, 1995) by ratification. As a party to the CBD, Guinea-Bissau is committed to implement the Programme of Work on Protected Areas (PoWPA) (COP 7, Decision VII/28). The project will specifically contribute to addressing the following PoWPA activities: Activities 1.1.4/ 2.1.5/ 2.2.1/ 2.2.2/ 2.2.4/3.5.4 (encouraging participation of indigenous and local communities); Activity 1.4.1 (site-based participatory planning); Activity 1.4.6 (effective management); Activity 1.5.5 (assess key threats and develop and implement strategies to address threats); and Activity 3.2.1 (capacity needs assessment and capacity-building).

The project will help Guinea-Bissau contribute to achieving the global Aichi Targets through national action, most importantly in relation to the following:

- Targets 5 and 12, by reducing the rate of loss and degradation of natural habitats and forests in Guinea-Bissau, improving the conservation status of globally threatened species, and preventing their extinction: directly through the project intervention inside and adjacent to the CNP, and more generally by providing a sustainable flow of funding for biodiversity conservation and PA management in the country as a whole.

- Target 7, by promoting a more biodiversity-friendly management of forest resources in areas around the CNP and more generally, through a pilot enhancing coordination between IBAP and DGFF

- Target 11, by adding the long-gazetted CNP to the cohort of effectively managed PAs in Guinea-Bissau.

- Target 15, by preparing the ground for REDD initiatives in the CNP and working towards the maintenance of its significant threatened forest carbon stock.

- Target 20, by providing a sustainable long-term flow of financial resources for biodiversity conservation and PA management covering about 30% of the recurrent costs of managing the SNAP; this is a good start and key leverage for further increasing resource availability in the future / by 2020.

### II.7. Sustainability and Replicability

The project has been carefully designed to optimize prospects for improving the sustainability of the SNAP in the following areas:

Ecological sustainability: Ecological sustainability of the project relies on the effective coordination and mutual cooperation between IBAP, DGFF, and local stakeholders in the implementation of actions directed to improve the management effectiveness of the CNP, where IBAP has jurisdiction, and its buffer zones, where DGFF operates. This includes the development and implementation of enforcement and control plan jointly between IBAP and DGFF, with local participation, which will emphasize EIA and the licensing and monitoring of logging activities in and around PAs, as well as identifying and providing increased protection of high-risk and ecologically sensitive areas, including biological corridors and hot spots for biodiversity of global importance. In addition it includes updating the CNP management plan, which will be effective for 5 years, with active local participation, including considerations and designs to strengthen ecological corridors (e.g., wildlife corridors) within the CNP, and between the CNP and other PAs and its buffer zones. This approach will allow the management of landscape components (larger contiguous areas of habitat) that are critical for the long-term conservation of multiple wildlife species. The participation of local communities living within and around the CNP will provide inputs and perspectives regarding the conservation and the sustainable use of biodiversity, which is a fundamental aspect for the long-term viability of the PA. Finally, the development of a business plan as a means to increase funding for the implementation of management activities (Component 2) as well as the operationalization of the FBG endowment (Component 1) will provide medium- and long-term funds for the sustainable use and conservation of biodiversity and the reduction of threats in the CNP and other PAs of the SNAP.

Institutional sustainability: The basis for institutional sustainability lies in the strengthening of the capacity of IBAP, DGFF, and the FBG to effectively carry out their institutional mandates in a harmonized manner. This includes building a lasting inter-institutional cooperation framework for IBAP that DGFF to overcome weak collaboration and past cases of misaligned action related to biodiversity conservation and forest management. To this end, through Component 2 the project will develop actions that will allow IBAP and DGFF to plan and implement activities in a coordinated manner in the CNP and its buffer zones. This will include joint DGFF-IBAP planning and collaboration in priority risk areas, including biological corridors and water sources for key wildlife species, and joint DGFF-IBAP training programs that will strengthen capacities to enforce conservation and forest management regulations, and that will facilitate the reduction and monitoring of threats in and around the CNP, including strengthening EIA and licensing processes. Institutional sustainability will also be achieved by strengthening the skills of IBAP’s staff both at its headquarters and at the PA level (CNP) in PA planning and management, community engagement and conflict resolution techniques, and biodiversity monitoring, among other topics. Improved capacity for stakeholder engagement will boost the interaction between IBAP and local communities, including the role of the Management Council of the CNP, and will facilitate communication and coordination to improve decision-making, thereby contributing to the institutional sustainability of the project at the PA level. Capacity-building will include the use of capacity development indicators that will allow assessing the impact of training over time so that capacity development is delivered in a more a systematic manner and with long-lasting impacts. Additionally, the consolidation of the FBG endowment (Component 1) will provide a sustainable flow of financial resources that will contribute to strengthening IBAP’s role as the national administrator of the SNAP.

Financial sustainability: Financial stability is an integral part of the project design, especially with regard to Component 1. The project specifically seeks to promote the financial sustainability of GB’s SNAP and biodiversity conservation initiatives by: a) securing/leveraging sufficient seed capital for an endowment fund, the revenue of which will provide stable, predictable funding for these activities in perpetuity; and b) strengthening the fiduciary capacity of the institituion which manages it, the FBG. Well-designed project activities under Outputs 1.1 to 1.6 are geared to further develop the institutional capacity of the FBG to effectively secure and administer funds for PA management in Guinea-Bissau. It will do this by developing and implementing relevant operational and fiscal guidelines and tools, as well as a dedicated fund-raising strategy. Critical capacities such as those of investment specialists will be solicited. Support to the further operationalization of FBG will generate more stable and predictable income flows for PAs over the longer term. The financial sustainability of project benefits to be delivered through Component 2 will also depend of the implementation of a business plan for the CNP that will allow the implementation of its management plan, including buffer zones. The business plan involves a blend of grants, incentives and REDD contributions (sale of carbon credits) that will allow the implementation of conservation and sustainable use measures beyond project completion.

Social sustainability: The social sustainability of the project will be achieved through the direct engagement of local stakeholders (e.g., local communities, CSOs, and members of the CNP Management Council) in the planning and implementation of conservation and forest management activities. This will enable local stakeholders to participate actively in the sustainable management and use of the coastal and terrestrial ecosystems which provide goods and services upon which the communities depend, such as food, flood protection, and timber and NTFP, among others. Participation in planning and implementation processes (e.g., management plans and enforcement and control plans) will empower local men and women and will enhance their ability to interact with multiple stakeholders beyond project completion. Capacity-building activities will strengthen their skills to negotiate and participate in collaborative agreements, and in the management, monitoring, and control of biodiversity and forest resource use, including the incorporation of their knowledge about biodiversity and forest management and the strengthening of relationships with IBAP, DGFF, and other stakeholders. Through the economic and social benefits that will result from the project, including the implementation of sustainable initiatives (e.g. biodiversity-friendly agriculture and silvo-pastoral and agro-forestry systems) that are expected to contribute to food security for farmers and their families (including women) as well as generate additional household income, local communities will perceive further benefits that will contribute to a lasting commitment to conservation and the sustainable use of biodiversity and forest resources. The project will provide technical assistance for the implementation of biodiversity-friendly production systems so that once the project finalizes local farmers can continue their implementation with limited outside assistance.

Replication. Strengthening the financial and operational framework of the SNAP in Guinea-Bissau will have an impact on various levels. At the local and national levels, a set of actions will be piloted in the CNP that will allow replication in other PAs around the country. The project will instill better coordination and mutual cooperation, as well as joint training and vision-building between IBAP and DGFF, through the planning and management of biological and forest resources in CNP and adjacent areas. This pilot is meant to locally reduce the pressures on the PA, enhance cost-efficiency of PA management, and more generally trigger a better conservation of forest biodiversity in the target area to be replicated across Guinea-Bissau. At the farm level, actions for the implementation of biodiversity-friendly activities have the potential to be replicated to the extent that they generate environmental and economic benefits for farmers through biodiversity-friendly production activities and other activities. The improved institutional and individual capacity of IBAP staff will benefit other PAs around the country, as their knowledge and management skills that are gained through this GEF initiative (e.g., PA planning and management, stakeholder engagement and conflict resolution techniques, biodiversity monitoring, etc.) can be applied throughout the entire PA system.

The project also has the potential to be replicated at the international level. Firstly, the long-term dividends from biodiversity conservation interventions in Guinea-Bissau would be strengthened and by engendering a potentially virtuous cycle, the possibility for their further up-scaling improved accordingly. Already IBAP is often considered a model biodiversity and PA institution in the region, in terms of capacity and setup and in terms of what long-term international collaborative efforts can achieve through coordinated planning and investment; this could be further strengthened through the project. And secondly, the REDD work in CNP is a pilot for the region, and the experience on the groundwork and the carbno credits sale via voluntary markets will inform similar attemps in other interested countries. The project will use available tools from the UNDP and the GEF (e.g., information network, discussion groups, documents and publications, etc.) to disseminate best practices and lessons learned so that they may be used to design and implement similar projects in Guinea-Bissau, the Western Africa region, and elsewhere. The indicative cost to disseminate best practices and lessons learned will be USD 4,000 (an average of USD 1,000 per year) and has been incorporated into the project monitoring and evaluation plan.

## PART III: Management Arrangements

### III. 1. Project implementation arrangement

The project will be implemented over a period of four years. UNDP will have responsibility for overseeing the implementation of the project. The project will be nationally implemented (in line with National Implementation Modality - NIM) by the Institute for Biodiversity and Protected Areas (IBAP), in line with the Standard Basic Assistance Agreement (signed by the parties on May 28, 1975) and the UNDP Country Programme Action Plan (2008-2015) signed between the UNDP and the Government of Guinea-Bissau. A micro-assessment was carried out in May 2011 to determine whether the procedures in the Harmonized Approach to Cash Transfer (HACT) can be applied for IBAP (see Annex 1).

The UNDP CO will monitor the project’s implementation and achievement of the project outputs, and ensure the proper use of UNDP/GEF funds. Working in close cooperation with IBAP,  the UNDP CO will be responsible for: a) providing financial backstopping and audit services to the project; b) recruitment and contracting of project consultants funded by GEF and UNDP Target for Resource Assignment from the Core (TRAC) funds; c) overseeing financial expenditures against project budgets approved by the PSC; d) appointment of independent financial auditors; e) recruitment and contracting external evaluators; and f) ensuring that all activities, including procurement and financial services, are carried out in strict compliance with UNDP-GEF procedures.

IBAP will have the overall responsibility for achieving the project goal and objectives. IBAP will designate a senior official to act as the National Project Director. The National Project Director will provide the strategic oversight and guidance to project implementation.

The day-to-day administration of the project will be carried out by a full time National Project Coordinator (funded by GEF and by UNDP as part of its co-financing contribution, and recruited jointly with IBAP). The project will benefit from the technical, management, and strategic support of a project team (refer to Overview of Project Consultants). The project team will be based in IBAP’s headquarters in Bissau. The project staff will be recruited using standard UNDP recruitment procedures. The National Project Coordinator has the authority to administer the project on a day-to-day basis on behalf of IBAP, within the constraints laid down by the PSC. The National Project Coordinator’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The National Project Coordinator will liaise and work closely with all partner institutions to link the project with complementary national programs and initiatives. The National Project Coordinator is accountable to the National Project Director for the quality, timeliness, and effectiveness of the activities carried out, as well as for the use of funds.

The Project Coordinator will be technically supported by contracted national and international service providers, including biodiversity, PA and forest management, and financial experts, among others. Recruitment of specialist support services and procurement of any equipment and materials for the project will be done by the Project Coordinator with support from IBAP, in consultation with the National Project Director and in accordance with national rules and regulations. The terms of reference for key project staff/consultants are detailed in Section IV, Part III.

To deliver Component 1 as outlined in the project’s results framework, IBAP will delegate responsibilities to FBG. FBG will be contracted as a Responsible Party through appropriate modalities, as advised by UNDP; the corresponding Letter of Agreement (LoA) will be annexed to the project document that will be signed between UNDP and the IBAP once the GEF project document has been endorsed. IBAP will bear responsibility for the delivery of the related Outputs and put in place adequate measures to oversee such work by FBG.

A Project Steering Committee (PSC) will be constituted to serve as the Project Board, which is its highest coordination and decision-making body. The PSC will ensure that the project remains on course to deliver the desired outcomes of the required quality. It will also ensure strategic coordination among different projects. The PSC will be chaired by IBAP and will include representation from DGFF, FBG, the World Bank, UNDP, the MAVA Foundation and other co-financiers and relevant entities. The Committee’s constitution will be reviewed and recommended for approval during the Local Project Appraisal Committee (LPAC) meeting. Representatives of other stakeholder groups may be included in the PSC, as considered appropriate and necessary. The PSC will meet at least twice per annum (more often if required).

The Project Coordinator will produce Annual Work Plans (AWP, to include annual budget) with support from his/her team and IBAP, FBG staff and UNDP CO. These plans will provide the basis for allocating resources to planned activities. A consolidated AWP, endorsed by the PSC, will be sent to the GEF Regional Coordinating Unit (RCU; which hosts the UNDP Regional Technical Advisor [RTA] for Biodiversity) for clearance with respect to GEF and UNDP funds. Once the Annual Working Plan and Budget is cleared by the RCU/RTA, GEF funds will be released. The Project Coordinator and his team will produce quarterly progress reports, as well as annual Project Implementation Reports (PIR) for review by the PSC and submission to UNDP/GEF. The Project Coordinator and his team will further produce any other reports at the request of the PSC. These reports will summarize the progress made by the project versus the expected results, explain any significant variances, detail the necessary adjustments, and be the main reporting mechanism for monitoring project activities.

### III. 2. Financial and other procedures

The financial arrangements and procedures for the project are governed by the UNDP rules and regulations for National Implementation Modality (NIM).  Some financial transactions may be conducted through direct payment requests made by IBAP (as opposed to drawing on funds advance). These requests will originate from the project, to UNDP, to transfer funds to beneficiaries. All procurement and financial transactions will be governed by applicable UNDP regulations under NIM.

[Paragraph deleted].

## PART IV: Monitoring Framework and Evaluation

### IV.1. Monitoring and reporting

The project will be monitored through the following monitoring and evaluation (M&E) activities. The M& E budget is provided in Table 5.

Key M& E Activities

Project start-up: A Project Inception Workshop will be held within the first 2 months of project start with those with assigned roles in the project organization structure, UNDP (CO and preferably RTA) as well as other stakeholders. The Inception Workshop is crucial to building ownership for the project results and to plan the first year annual work plan.

The Inception Workshop should address a number of key issues including:

- Assist all partners to fully understand and take ownership of the project. Detail the roles, support services and complementary responsibilities of UNDP CO and RCU staff vis à vis the project team. Discuss the roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms. The Terms of Reference for project staff will be discussed and finalised if needed.

- Based on the project’s strategic results framework and the relevant GEF Tracking Tool if appropriate, finalize the first annual work plan. Review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks.

- Provide a detailed overview of reporting and M&E requirements. The M&E work plan and budget should be agreed and scheduled.

- Discuss financial reporting procedures and obligations, and arrangements for annual audit.

- Plan and schedule PSC meetings. Roles and responsibilities of all project organization structures should be clarified and meetings planned. The first PSC meeting should be held within the first 12 months following the inception workshop.

The resulting Inception Workshop Report is a key reference document and must be prepared and shared with participants to formalize various agreements and plans decided during the meeting. The Inception Report must be submitted to UNDP-GEF RCU.

Quarterly: Progress made shall be monitored in the UNDP Enhanced Results Based Management Platform. Short Quarterly Progress Reports (QPRs) must be prepared and uploaded.

Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS. Risks become critical when the impact and probability are high.

Based on the information recorded in ATLAS, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

Other ATLAS logs can be used to monitor issues, lessons learned, etc. The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Annually: Annual Project Implementation Reports (PIRs):  This key report is prepared to monitor progress made since project start and in particular for the previous reporting period. The PIR combines both UNDP and GEF reporting requirements.

The PIR includes, but is not limited to, reporting on the following:

- Progress made toward project objective and project outcomes - each with indicators, baseline data and end-of-project targets (cumulative)

- Project outputs delivered per project outcome (annual).

- Lessons learned/good practice.

- AWP and other expenditure reports

- Risk and adaptive management

- ATLAS Quarterly Progress Report (QPR)

- Portfolio level indicators (i.e. GEF focal area tracking tools) are used by most focal areas on an annual basis as well.

Periodic Monitoring through site visits: UNDP CO and the UNDP RCU will conduct visits to project sites based on the agreed schedule in the project's Inception Report/Annual Work Plan to assess first hand project progress. Other members of the PSC may also join these visits. A Field Visit Report/BTOR will be prepared by the CO and UNDP RCU and will be circulated no less than one month after the visit to the project team and PSC members.

Mid-term of project cycle: The project will undergo an independent Mid-Term Evaluation at the mid-point of project implementation (estimated June 2017). The Mid-Term Evaluation will determine progress being made toward the achievement of outcomes and will identify course corrections if needed. It will focus on the effectiveness, efficiency, and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation, and management. The findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term. The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document. The Terms of Reference for this mid-term evaluation will be prepared by the UNDP CO based on guidance from the RCU and UNDP-GEF. The management response and the evaluation will be uploaded to UNDP corporate systems, in particular the UNDP Evaluation Office’s Evaluation Resource Center (ERC).

The relevant GEF Focal Area Tracking Tools will also be completed during the mid-term evaluation cycle.

End of Project: An independent Final Evaluation will take place three months prior to the final PSC meeting and will be undertaken in accordance with UNDP and GEF guidance. The final evaluation will focus on the delivery of the project’s results as initially planned (and as corrected after the mid-term evaluation, if any such correction took place). The final evaluation will look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental benefits/goals. The Terms of Reference for this evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.

The Terminal Evaluation should also provide recommendations for follow-up activities and requires a management response which should be uploaded to PIMS and to the UNDP ERC.

The relevant GEF Focal Area Tracking Tools will also be completed during the final evaluation.

During the last three months, the project team will prepare the Project Terminal Report. This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved. It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Table 5 – M&E work plan and budget

| Type of M&E activity | Responsible Parties | Budget USD Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Coordinator - UNDP CO, UNDP GEF | Indicative cost: 4,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Coordinator will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Coordinator - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to PIR and to the definition of annual work plans |
| PIR | - Project Coordinator and team - UNDP CO - UNDP RTA - UNDP GEF | None | Annually |
| Periodic status/ progress reports | - Project Coordinator and team | None | Quarterly |
| Mid-term Review | - Project Coordinator and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Indicative cost: 27,400 | At the mid-point of project implementation. |
| Terminal Evaluation | - Project Coordinator and team, - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Indicative cost: 27,400 | At least three months before the end of project implementation |
| Lessons learned | - Project Coordinator and Team - GEF RCU (suggested formats for documenting best practices, etc.) | Indicative cost: 4,000 (1,000/year) | Yearly |
| Technical reports | - Project Coordinator and Team - Hired consultants as needed | Indicative cost: 4,000 | To be determined by Project Team and UNDP-CO |
| Project Terminal Report | - Project Coordinator and team - UNDP CO | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project Coordinator and team | Indicative cost per year: 3,750 (Total: 15,000) | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU and PSC (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | USD 81,800 |  |

Learning and knowledge sharing

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based, and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Communications and visibility requirements

Full compliance is required with UNDP’s Branding Guidelines. These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects need to be used. For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo. The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo. The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”). The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf. Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies, and other project equipment. The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Where other agencies and project partners have provided support through co-financing, their branding policies, and requirements should be similarly applied.

### IV.2. Audit Clause

Audit will be conducted according to UNDP Financial Regulations and Rules and applicable Audit policies.

## PART V: Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA [or other appropriate governing agreement] and all CPAP provisions apply to this document.

Consistent with the Article III of the SBAA, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- Put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- Assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# SECTION II: Strategic Results Framework (SRF) and GEF Increment

## PART I: Strategic Results Framework Analysis

### I.1. Programmatic Links

Link to UNDP Strategic Plan (2014-2017) [Link]: Output 1.3. Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste Output 2.5. Legal and regulatory frameworks, policies and institutions enabled to ensure the conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation

Contribution to 2008-2012 UN Development Assistance Framework / UNDAF Outcomes: Effet UNDAF 1: les institutions gouvernent dans le respect des Droits Humains, pour la consolidation de l’Etat de droit et selon les principes de gestion transparente et efficiente des ressources du pays. Effet Programme 2 : la société civile est renforcée et la modernisation de l’administration publique amorcée en vue d’une gestion transparente et efficace des ressources du pays. Produit 2.2 les capacités de l’administration publique sont renforcées en vue d’une gestion efficiente et transparente des ressources du pays. Effet UNDAF 2 : Les populations, les institutions et les organisations développent le secteur privé et la création d’emplois par l’amélioration des systèmes de production, la diversification des activités, contribuent à la réduction de la pauvreté et gèrent de façon durable l’environnement Effet Programme 3 : Les capacités des institutions nationales des OCB et des entreprises pour l’application des principes et des normes de gestion des ressources naturelles et de l’environnement sont renforcées Produit 1.3: les capacités des Institutions nationales, les entreprises et les OCB du secteur de l’environnement sont renforcées en matière d’élaboration, d’application et de surveillance de la législation et des normes pour prévenir les dégradations de l’environnement et des ressources naturelles. Effet UNDAF 2 : Les populations, les institutions et les organisations développent le secteur privé et la création d’emplois par l’amélioration des systèmes de production, la diversification des activités, contribuent à la réduction de la pauvreté et gèrent de façon durable l’environnement Effet Programme 3 : Les capacités des institutions nationales des OCB et des entreprises pour l’application des principes et des normes de gestion des ressources naturelles et de l’environnement sont renforcées Produit 1.3 les capacités des institutions nationales, les entreprises et les OCB du secteur de l’environnement sont renforcées en matière d’élaboration d’application et de surveillance de la législation et des normes pour prévenir les dégradations de l’environnement et des ressources naturelles

Expected Country Programme Outcome(s) (2008-2012; extended to be effective until end 2015): PRIORITE NATIONALE: favoriser la croissance économique et la création d’emplois Effet recherché 3: les ménages, surtout les plus pauvres et les organisations communautaires de base (OCB) adoptent des systèmes de production respectant les normes de gestion des ressources naturelles et de l’environnement. Produit 10. Sensibiliser davantage la population et les OCB et actualiser et appliquer la législation prévenant les dégradations volontaires sur l'environnement et les ressources. Produit 11. Renforcer les capacités de surveillance des structures nationales de coordination du secteur de l'environnement.

Applicable GEF Strategic Objective and Program: BD1: Improve Sustainability of Protected Area System

Applicable GEF Expected Outcomes: 1.1: Improved management effectiveness of existing and new protected areas

Applicable GEF Outcome Indicators: Increased coverage of threatened ecosystems and threatened species: 1. New protected areas and coverage of unprotected ecosystems: - Extent of the network of protected areas: 545,615 ha (officially established) - Coverage of vegetation types in the protected area network: 482,502 ha (as per Tracking Tool) 2. METT score for the CNP will improve from a baseline of 57 to 77

### I.2. Indicator framework as part of the SRF

|  |  | Indicator | Baseline | Target/s (End of Project) | Source of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective Strengthening financial sustainability and management effectiveness of the national PA system in Guinea-Bissau | 0 | UNDP IRRF 1.3.1.A.1.1. Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or sub-national level | FBG partly operational and without endowment capital or other income | FBG fully operational, capitalised with at least USD 7,365,248, using also the national financing mechanism – the EU Fisheries Agreement and the REDD carbon sales from CNP | - FBG annual financial reports - Capitalization/ funding agreements - Auditing reports - Project reports |  |
|  | 1 | UNDP IRRF 2.5.1.C.1.1: Extent to which institutional frameworks are in place for conservation, sustainable use, and/or access and benefit sharing of natural resources, biodiversity and ecosystems | 0 | Missing institutional frameworks established | Government institutional decrees, regulations, FBG annual reports and rules & regulations, project reports |  |
|  | 2 | Change in the financial sustainability of the SNAP according to that established through the total average score in the UNDP/GEF Sustainability Scorecard | 34% | 50% | - Updated Financial Sustainability Scorecard (Tracking Tool for BD-1) - Updated METT scorecards (Tracking Tool for BD-1) - Annual project evaluation reports - Mid-term and final evaluation reports | - The GoGB, the civil sector, and the private sector working jointly for the financial sustainability and management effectiveness of the SNAP - Stable national and international economic conditions |
|  | 3 | Change in the management effectiveness of the CNP as measured through the METT scorecard | 57 | 77 (19.6% increase) |  |  |
| Outcome 1 Strengthening the financial framework of the national PA system | 4 | Capitalization of the endowment of the FBG after 4 years | 0 USD | At least USD 7,365,248 (21% of overall Endowment of USD 34.88 million [EUR 28 million] envisaged). | - FBG annual financial reports - Capitalization/ funding agreements - Auditing reports - Project reports | - Stable national and international economic conditions allow a sustained flow of new financial resources - Fundraising efforts are optimal |
|  | 5 | Change in the percentage of SNAP recurrent costs supported by endowment revenues | 0 | 30% | - Updated Financial Sustainability Scorecard - SNAP annual financial reports - Project monitoring and evaluation reports: PIR, mid-term and final evaluation reports |  |
|  | 6 | Change in the number and variety of revenue sources used across the PA system as measured the UNDP/GEF Sustainability Scorecard (Component 3, Element 1) | 33% | 50% |  |  |
| Outputs: 1.1. FBG Board and Executive Secretariat operating effectively and efficiently (including fiduciary and management systems). 1.2. Transparent and internationally recognized auditing and reporting standards/protocols to monitor and evaluate the FBG’s achievements against time-bound targets and the use of endowment, sinking, and revolving funds at its disposal.. 1.3 – Pre-requisite due diligence and compliance procedures verified and formalised, and the FBG endowment capitalised with an initial investment of USD 7,365,248 through direct investment by the project and its co-financiers, and further enriched in a staggered approach in line with fundraising strategy 1.4. FBG’s assets management capacity is optimized to reflect the regular oversight of investment performance, as well as an appropriate risk strategy and balanced diversification of its investments portfolio, ensuring the latter is socially and environmentally responsible (details to be defined by the FBG Board). 1.5. Comprehensive fundraising/ capitalisation strategy in place involving FBG and other key stakeholders, and including inter alia (i) finely-tuned communications/ advocacy plans; (ii) annual donor meetings informed on progress and operational efficiencies of FBG; (iii) targeted in-depth assessments of potential revenue generation mechanisms (e.g., compensation schemes from mining and timber concessions, fines, tourism fees, REDD) and related enabling/ institutional needs. 1.6. Strong communication and public relations strategy implemented, ensuring ongoing conversations with national and international partners (GoGB, donors, and private sector) and minimizing risk of government interference while creating ownership. |  |  |  |  |  |  |
| Outcome 2 PA and buffer zone management in Cantanhez NP | 7 | Existence of PA headquarters with functional office facilities and basic equipment and logistics | No functional office facilities | PA headquarter has functional office facilities | - NP annual reports - Project monitoring and evaluation reports: PIR, mid-term and final evaluation reports | - NP boundaries are suitably demarcated and regularly patrolled - Strict controls over illegal activities and land use in the NP are more actively enforced by NP authorities - Wildlife sampling efforts are optimal - Environmental variability (including climate change) is within the normal range |
|  | 8 | Degree of illegal utilisation of key plant species of commercial value as recorded in CNP and its buffer zones per year, to include at least - Red mangrove or “Mangal/Tarafe” (Rhizophora mangle) - “Pó de sangue” (Pterocarpus erinaceus) - African fan palm or “Cibe” (Borassus aethiopium) - African mahogany or “Bissilão” (Khaya senegalensis) - “Poilão” (Ceiba pendandra) | The final list of species to be considered and the baseline values will be established during the first year of project implementation | Target values will be established during the first year of project implementation | - PA monitoring, control, and surveillance reports - Databases on confiscations, forfeitures and sanctions |  |
|  | 10 | Level of poaching recorded in CNP and its buffer zones per year, using as proxy indicators - Campbell's mona monkey or “Macaco Mona” (Cercopithecus (mona) campbelli ) - Bay duiker or “Cabra de mato” (Cephalophus dorsalis) - Bushbuck or “Gazela” (Tragelaphus scriptus) - Crested porcupine or “Porco espinho (Hystrix cristata) - Warthogs or “Porco de Mato” (Phacochoerus africanus) | The final list of species to be considered and the baseline values will be established during the first year of project implementation | Target values will be established during the first year of project implementation | - PA Monitoring, control, and surveillance reports - Databases on seizures, forfeitures and sanctions, |  |
|  | 11 | Number (or size) of wildlife populations recorded in CNP, to include at least - Leopard (Panthera pardus) - West African Manatee or “Pis-Bus/Manatim” (Trichechus senegalensis) - West African Red Colobus or “Macaco Fidalgo vermelho” (Piliocolobus badius temminckii) - Chimpanzee (Pan troglodytes) - Hippopotamus (Hippopotamus amphibius) - Buffalo (Syncerus caffer) | The final list of species to be considered and the baseline values will be established during the first year of project implementation | Target values will be established during the first year of project implementation | - Robust wildlife census data - NP annual reports |  |
|  | 12 | Number of staff (including women) from IBAP, DGFF, local community members trained for effective oversight of land use and threat reduction in PA buffer zones | 0 | At least 50 | - Data bases with records of the training events - Project monitoring and evaluation reports: technical reports, PIR, mid-term and final evaluation reports | - Effective coordination and agreement among national and local government officials (IBAP and DGF) for the development of strategies for the effective management of viable PA buffer zones and adjacent areas. - Local communities living within an adjacent to the NP willing to implementing innovative biodiversity-friendly economic activities. |
|  | 13 | Existence of PA and buffer zone management bodies which involve key stakeholders: IBAP, DGFF, and local stakeholders (community councils, CSOs, NGOs) | No (Existence of CNP management council but does not address management in buffers zones) | Yes | - Agreements/memorandum of understanding - Data bases with records of the training events - Field/technical verification reports - Socio economic surveys - Project monitoring and evaluation reports: technical reports, PIR, mid-term and final evaluation reports |  |
|  | 14 | Level of satisfaction of local community members (differentiated by gender) collaborating with PA and forest management. Indicative assessment categories: - Highly Unsatisfactory - Unsatisfactory - Moderately Unsatisfactory - Moderately Satisfactory - Satisfactory - Highly Satisfactory | Baseline will be established during the first year of project implementation | Target will be established during the first year of project implementation |  |  |
|  | 15 | Increase in cash or in-kind benefits returned to local communities (beneficiaries differentiated by gender) as a result of biodiversity-friendly economic activities | Baseline will be established during the first year of project implementation | Target will be established during the first year of project implementation |  |  |
|  | 15 | Management and business plan for CNP and buffer zones updated and under implementation | - Management plan: Outdated - Business plan: Preliminary | - Management plan: Updated - Business plan: Yes | - Approved CNP Management and Business Plans - CNP annual management/business plan implementation reports - Project monitoring and evaluation reports: PIR, mid-term and final evaluation reports | - Effective interinstitutional coordination and local stakeholder participation allows the implementation of the CNP management plan |
| Outputs: 2.1. Operational capacities of CNP consolidated to permit compliance with at least basic functions through (i) primary operational logistics and equipment; (ii) training programmes for IBAP staff (involving DGFF and other PA management council members) with special emphasis on PA planning and management, community engagement and conflict resolution techniques, forest management challenges and approaches; iii) underpinning support to IBAP headquarters. 2.2. Strengthened institutional capacity of DGFF and IBAP for effective oversight of land use and threat reduction in PA buffer zones and related forest areas through (i) joint DGFF-IBAP planning and collaboration programming in priority high risk areas; (ii) joint DGFF-IBAP training programmes with emphasis on Environmental Impact Assessment (EIA), law enforcement, licensing and monitoring of economic activities in and around PAs, PA management challenges and approaches. 2.3. Local community involvement in and collaboration with PA and forest management improved by: (i) strengthening PA management council and related public participation and institutional arrangements for negotiating, implementing and monitoring management and collaborative agreements; (ii) training programme including conflict resolution mechanisms, and community surveillance and enforcement; (iii) the development of biodiversity-friendly economic activities. 2.4. Management and business plans for CNP and connected buffer zones and ecological corridors updated/produced, allowing the coordinated identification, prioritisation of management activities and allocation of funds by IBAP, DGFF, and other institutions with responsibilities for biodiversity conservation, land use planning, and forestry. |  |  |  |  |  |  |

## PART II: Incremental Reasoning and Cost Analysis

Expected Global, National and Local Benefits

Table 6 – Incremental Cost Matrix

| Cost/Benefit | Baseline (B) | Alternative (A) | Increment (A-B) |
| --- | --- | --- | --- |
| BENEFITS |  |  |  |
| Global benefits | Although Guinea-Bissau is set to benefit from a significant project baseline directed at the management of biodiversity and the SNAP in Guinea-Bissau, under the ‘business-as-usual’ scenario funds and efforts would not be sufficient to address current gaps in the institutional framework, particularly the emergence of a functional collaborative framework involving IBAP, DGFF, and other key stakeholders aimed at enhancing the management of forest-related biodiversity in Guinea-Bissau. Additionally, the country would remain reliant almost exclusively on external project-based funding, which is generally unpredictable, insufficient, and directed at particular sites or issues of donor interest – some donors have already expressed hesitation at continuing financing at the current level. There are no concrete perspectives for leveraging capital into the FBG endowment that would surpass the minimum threshold required for it to become operational and effective, and there are no other plans to operationalize other more innovative revenue sources. Moreover, under the business-as-usual scenario important gaps would remain in PA management coverage and operational effectiveness (especially in relation to CNP). | The GEF Alternative will remove the barriers that prevent Guinea-Bissau from having a strengthened financial and operational framework for the SNAP. Building on the results of previous GEF interventions, baseline programs, and projects, and coordinating with ongoing and other donor-funded projects, the project will pursue two interlinked approaches: a) increasing revenue generation for the SNAP by removing barriers that impede the full functioning of the FBG, achieving short-term endowment capitalization targets together with project co-financiers and putting into place the foundations for the achievement of medium- and long-term targets; and b) extending the coverage of effective PA management by IBAP to a critically threatened priority PA (i.e., CNP) while developing new operational frameworks that promote enhanced efficiencies through the involvement of DGFF and local stakeholders. This will be an important next step towards a well-funded SNAP that conserves Guinea-Bissau’s highest biodiversity value ecosystems through PAs that are effectively managed in a cost-effective manner. The project will generate important global biodiversity benefits. It will contribute to the long-term financial sustainability of 952,172 ha of critical natural habitat via Guinea-Bissau’s national network of PAs, covering some 26% of the country. The extensive and highly productive mangrove ecosystems are critical contributors to the sub-region’s marine productivity, supporting globally endangered and threatened species and a variety of migratory birds. The project pays special attention to the urgent operationalization of a critical PA containing ecosystems such as woodland savannah, semi-dry tropical forest, and especially the critically endangered primary tall sub-humid tropical forests. These ecosystems contain threatened and endangered species of global importance that are typical of the Guinea Savannah Forest Mosaic and play a critical role as biological corridors and migration routes for large mammals. Other global environmental benefits will be derived from achieving strengthened management capacity coupled with financial sustainability at the SNAP level. | With dedicated co-financing from the World Bank/IDA, WAMER, and UNDP projects, this project will lead to the completion of management systems, due diligence, and compliance procedures triggering the direct capitalization of the FBG. GEF project funding will initiate the capitalization of the FBG endowment and thereby catalyse the long-awaited leveraging of funds from the other committed co-financiers as a first crucial step towards the development of financial sustainability for Guinea-Bissau’s SNAP, which protects some of the most biodiverse and threatened ecosystems in West Africa. During the preparation of the PIF, negotiations for co-funding this capitalization to as much as USD 5,550,000 have advanced beyond that number, bringing the total capitalization through the project to USD 7,365,248, with USD 1,300,000 funding from the GEF. An additional EUR 1,000,000 (c. USD 1,245,760) cash co-financing are in the process of being secured from FFEM, yet not confirmed; these would bring the FBG endowment capital to USD 8,611,008. The project will pilot new operational efficiencies in a pilot site by improving PA management capacity and effectiveness in the CNP. In parallel, the project will support the collaborative management of vital buffer zones and adjacent areas in close coordination with DGFF and other key stakeholders – including through links with a REDD project expected to generate revenue for forest/biodiversity conservation and local communities. This would also lead to strengthened institutions gradually reaching consensus on conservation approaches, including their social and economic dimensions. Finally, systems and tools successfully demonstrated by the project in the CNP, especially with regard to the management of forest biodiversity, will be generalized to support the ongoing and planned expansion of the forest PA estate in Guinea-Bissau. This GEF incremental investment will contribute to the conservation of globally significant ecosystems and biodiversity including river floodplains, mangroves, forests, and savannahs; forest species such as Afzelia africana (VU), Alstonia congensis, Antiaris africana, Ceiba pentandra, Dialium guineense, Ficus spp., and Parinari excelsa; and fauna species including the West African Manatee (Trichechus senegalensis, VU), chimpanzee (Pan troglodytes, EN); the West African Red Colobus (Procolobus badius EN), the King Colobus (Colobus polykomos VU), the Guinea Baboon (Papio papio, NT), the leopard (Panthera pardus, NT), the African Elephant (Loxodonta africana, VU), and a considerable numbers of migratory shorebirds and water birds. |
| National and local benefits | Under the “business-as-usual” scenario, local-level benefits will be limited because the lack of skills, funding, and collaborative efforts (IBAP, DGFF, NGOs, and local communities) for effective PA management (CNP) will not allow facing the current threats to the PA and related biodiversity. In addition, the CNP and its buffer zones will continue operations with an outdated management plan that lacks strategic conservation strategies (i.e., wider landscape) to reduce the increasing pressures on biodiversity from other land uses. Similarly, the CNP will continue operating with a business plan that does not address the strategic long-term financial needs for effective management. Finally, under the “business-as-usual” scenario, effective participatory management of the PA will continue to be weak as there will be limited incentives for local communities living within and around the CNP to reduce pressure on forests, mangroves, and coastal resources. | The project will engage a variety of stakeholders in supporting the conservation of biodiversity and the management of the CNP and its buffer zones. Through strengthened governance for biodiversity and forest conservation, enhanced participatory PA and forest management, targeted capacity-building programs, and biodiversity-friendly economic activities for local communities, the GEF Alternative will deliver sustainable environmental and socioeconomic benefits at the local level. This strategy will reduce pressure on the PA, enhance cost-efficiency of PA management, and more generally trigger the improved conservation of forest biodiversity in the target area, which will then be replicated across Guinea-Bissau. | The GEF incremental investment will contribute to the effective conservation and management of the CNP and its buffer zones, which are home to biodiversity and forest resources of local and national importance. The project will consolidate the basic operation of the CNP by providing primary logistics and equipment. In addition, the CNP’s Management Council, which was established upon the creation of the PA in 2008, will be strengthened through a process of building a collaborative and cooperative relationship between PA and forest management authorities (i.e., IBAP and DGFF) and local communities. Targeted training will enable key government and local stakeholders to improve their skills for improved PA and forest management. Through a blend of FBG endowment returns, REDD contributions (sale of carbon credits), and grants and incentives, sustainable financial resources will be available for the long-term conservation and management of biodiversity and forests. The project is expected to yield local benefits through an improvement in the living conditions of communities living in and around CNP. Through the implementation of sustainable biodiversity-friendly production activities, the project will contribute to food security for farmers and their families (including women) and will generate additional household income. Through the IBAP, the project will provide technical assistance for the implementation of biodiversity-friendly production systems so that once the project is finalized, local communities may continue production with limited outside assistance. By project end, the management effectiveness of the CNP will have increased by 20% as measured through the METT scorecard (from 57 to 77). |
| COSTS |  |  | GEF + mobilised co-financing beyond the baseline |
| Outcome 1: Strengthening the financial framework of the national PA system | Baseline: USD 1,195,000 Sources: IBAP (revenue from tourism fees), WB-IDA, IBAP-IUCN. | Alternative: USD 9,818,648 A critical mass of donors committed to the capitalization of the endowment fund is identified, bringing the FBG above the targeted minimum threshold of USD 5,000,000. At least USD 7,365,248 will be injected into the FBG endowment over the course of the project, with an additional approximately USD 1,300,000 currently being negotiated at project submission (no co-financing letter has been secured yet) and additional opportunities being pursued. This capitalization of the Fund will provide around 30% of PA management costs at the end of this project, significantly reducing donor dependence. In addition to the Endowment capitalization, a carefully designed suite of outputs and associated activities are being supported in addition to the Endowment, ensuring that the fund management capacity of the FBG is strengthened. The focus is on the following on six outputs: - Operationalization of FBG management - Internationally recognized auditing and reporting standards/protocols - Due diligence and compliance procedures - FBG assets management capacity - Fundraising/capitalization strategy - Communication and public relations strategy | Increment: USD 8,623,648 GEF; 1,800,000. Co-financing (GoGB, EU, WB, MAVA); 6,823,648. TOTAL; 8,623,648. |
| Outcome 2: PA and buffer zone management in CNP | Baseline: USD 2,260,000 Sources: UNDP-GEF, DGFF | Alternative: USD 11,721,694 | Increment: USD 9,461,694 GEF; 394,694. Co-financing (EU, WB, IBAP):; 9,067,000. TOTAL; 9,461,694. |
| Project Management | n/a | Alternative: USD 904,335 | Increment: USD 904,335 GEF; 109,735. Co-financing (UNDP, EU, WB); 794,600. TOTAL; 904,335. |
| TOTAL | Baseline: USD 3,455,000 | Alternative: USD 22,444,677 | TOTAL Increment: USD 18,989,677 GEF; 2,304,429. Co-financing; 16,685,248. TOTAL; 18,989,677. |

# SECTION III: Total Budget and Work Plan

| ATLAS Award ID: | 00087219 |
| --- | --- |
| ATLAS Project ID: | 00094321 |
| ATLAS Award Title: | Expansion and Strengthening of Guinea-Bissau’s Protected Area system |
| Project Title: | Strengthening the financial and operational framework of the national PA system in Guinea-Bissau |
| UNDP Project ID: | 5177 |
| GEF Project ID: | 5368 |
| Implementing Agency: | Institute for Biodiversity and Protected Areas (IBAP) |

| Project Component / Atlas Activity | Implem. Agent | Fund ID | Donor Name | ATLAS Budget Code | Atlas Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | TOTAL | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Strengthening the financial framework of the national PA system | NIM | 62000 | GEF | 71400 | Contractual Services - Individ |  | 50,000 | 45,000 | 30,000 | 125,000 | 1 |
|  |  |  |  | 71600 | Travel |  | 35,000 | 35,000 | 25,000 | 95,000 | 2 |
|  |  |  |  | 72400 | Communic. & Audio Visual Equip |  | 5,000 | 5,000 | 5,000 | 15,000 | 3 |
|  |  |  |  | 72500 | Supplies |  | 4,000 | 4,000 | 2,000 | 10,000 | 4a |
|  |  |  |  | 73100 | Rental & Maintenance-Premises |  | 6,000 | 6,000 | 3,000 | 15,000 | 4b |
|  |  |  |  | 74100 | Professional Services | 40,000 | 70,000 | 50,000 | 20,000 | 180,000 | 5a |
|  |  |  |  | 75700 | Trainings, workshops and conferences | 10,000 | 20,000 | 20,000 | 10,000 | 60,000 | 5b |
|  |  |  |  | 72600 | Grants | 1,300,000 |  |  |  | 1,300,000 | 6 |
|  | Total - Component 1 / Atlas Activity 1 |  |  |  |  | 1,350,000 | 190,000 | 165,000 | 95,000 | 1,800,000 |  |
| 2. PA and Buffer zone management in CNP | NIM | 62000 | GEF | 71300 | Local consultants | 27,900 | 31,500 | 21,600 | 21,600 | 102,600 | 7 |
|  |  |  |  | 71600 | Travel | 6,500 | 9,500 | 7,000 | 7,000 | 30,000 | 8 |
|  |  |  |  | 72100 | Contractual Services-Companies | 25,000 |  |  |  | 25,000 | 9 |
|  |  |  |  | 72200 | Equipment and Furniture | 24,500 | 3,500 | 3,500 | 3,500 | 35,000 | 10 |
|  |  |  |  | 72300 | Materials & Goods | 4,000 |  | 4,000 | 4,000 | 12,000 | 11 |
|  |  |  |  | 72500 | Supplies | 1,150 | 1,150 | 1,150 | 1,144 | 4,594 | 12 |
|  |  |  |  | 72600 | Grants | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 | 13 |
|  |  |  |  | 74200 | Audio Visual&Print Prod Costs | 7,000 | 5,000 | 2,000 |  | 14,000 | 14 |
|  |  |  |  | 75700 | Training, Workshops and Confers | 29,875 | 29,875 | 22,375 | 9,375 | 91,500 | 15 |
|  | Total - Component 2 / Atlas Activity 2 |  |  |  |  | 145,925 | 100,525 | 81,625 | 66,619 | 394,694 |  |
| 3. Project Management | NIM | 62000 | GEF | 71200 | International consultants |  |  | 7,000 | 7,000 | 14,000 | 16 |
|  |  |  |  | 71300 | Local consultants | 2,000 | 2,000 | 4,000 | 4,000 | 12,000 | 17 |
|  |  |  |  | 71400 | Contractual Services - Individ | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 18 |
|  |  |  |  | 71600 | Travel |  |  | 7,800 | 7,800 | 15,600 | 19 |
|  |  |  |  | 72200 | Equipment and Furniture | 6,150 | 500 | 500 | 500 | 7,650 | 20 |
|  |  |  |  | 72400 | Communic. & Audio Visual Equip | 1,800 | 1,800 | 1,800 | 1,800 | 7,200 | 21 |
|  |  |  |  | 72500 | Supplies | 650 | 650 | 650 | 650 | 2,600 | 22 |
|  |  |  |  | 73100 | Rental & Maintenance-Premises | 1,800 | 1,800 | 1,800 | 1,800 | 7,200 | 23 |
|  |  |  |  | 74500 | Miscellaneous Expenses | 875 | 870 | 870 | 870 | 3,485 | 24 |
|  | Subtotal GEF - Project Management / Atlas Activity 3 |  |  |  |  | 23,275 | 17,620 | 34,420 | 34,420 | 109,735 |  |
|  | NIM | 04000 | UNDP TRAC | 71200 | International consultants |  |  | 7,000 | 7,000 | 14,000 | 25 |
|  |  |  | UNDP TRAC | 71300 | Local consultants |  |  | 2,000 | 2,000 | 4,000 | 26 |
|  |  |  | UNDP TRAC | 71400 | Contractual Services - Individ | 64,000 | 64,000 | 64,000 | 64,000 | 256,000 | 27 |
|  |  |  | UNDP TRAC | 71600 | Travel | 3,750 | 3,750 | 3,750 | 3,750 | 15,000 | 28 |
|  |  |  | UNDP TRAC | 72200 | Equipment and Furniture | 30,000 |  |  |  | 30,000 | 29 |
|  |  |  | UNDP TRAC | 73400 | Rental & Maint of Other Equip | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 30 |
|  |  |  | UNDP TRAC | 74100 | Professional Services | 4,750 | 4,750 | 4,750 | 4,750 | 19,000 | 31 |
|  |  |  | UNDP TRAC | 74500 | Miscellaneous Expenses | 1,250 | 1,250 | 1,250 | 1,250 | 5,000 | 32 |
|  |  |  | UNDP TRAC | 75700 | Training, Workshops and Confers | 4,000 |  | 1,500 | 1,500 | 7,000 | 33 |
|  | Subtotal UNDP TRAC - Project Management / Atlas Activity 3 |  |  |  |  | 112,750 | 78,750 | 89,250 | 89,250 | 370,000 |  |
|  | Total - Project Management / Atlas Activity 3 |  |  |  |  | 136,025 | 96,370 | 123,670 | 123,670 | 479,735 |  |
|  | SUB-TOTAL GEF |  |  |  |  | 1,519,200 | 308,145 | 281,045 | 196,039 | 2,304,429 |  |
|  | SUB-TOTAL UNDP TRAC |  |  |  |  | 112,750 | 78,750 | 89,250 | 89,250 | 370,000 |  |
|  | GRAND TOTAL (in cash) |  |  |  |  | 1,631,950 | 386,895 | 370,295 | 285,289 | 2,674,429 |  |

BUDGET ASSUMPTION: The budget contribution to Component 1 activities is split between the Word Bank/IDA’s BCP, the WAMER project, and the GEF 5 project for the four years of GEF support. It is estimated that one year after the endowment payments have been paid into the account, a first revenue payment of approximately USD 434,550 will be generated by project end, which will be used to cover some of the ongoing FBG costs, as well as on-the-ground SNAP management activities. Component 1 activities are covered by a suite of co-financing partners.

| Budget Notes |  |
| --- | --- |
| 1 | Support for FBG operational staff costs, backup to revenue from Endowment Fund. Project budget support for this activity is assumed to diminish as soon as the Endowment Fund generates first revenue. A minimum staff complement required to drive the effective functioning of the FBG is covered by the GEF support. |
| 2 | Travel includes meetings of the Boards and other statutory committees, as well as for car km usage, staff travel to international CTF conferences, and for the organization of an investment committee workshop. |
| 3 | From the communications strategy emerging priority communication products such as brochures, printed and audio visual media, as set out in a communications strategy. |
| 4a | Supplies include office supplies, printing, and car maintenance and supplies |
| 4b | Rental fee for office usage. |
| 5a | Professional Services: a number of professional expert services will be financed that will further advance technical support work that will provide a rigorous operational foundation for the FBG. As such, professional services for the following are covered: Fundraising and Investment Strategy; investment professional; M&E tools; Legal Services within and outside of Guinea-Bissau and United Kingdom; selected TA continued by FUNBIO. |
| 5b | Training of FBG staff on themes covered in Note 5a. |
| 6 | Grants: the Endowment fund is capitalized with USD 1,300,000. |
| 7 | National short-term consultants: a) Experts for management plan update (3) @ USD 900/week during 10 weeks (USD 27,600); b) Biodiversity and forest monitoring experts (2) @ USD 900/week during 6 weeks per year each during a 4-year period (USD 43,200); c) Financial expert: Support to business plan development and fundraising @ USD 900/week during 24 weeks (USD 21,600); d) GIS expert for LU/LC change assessments, including field verification @ USD 900/week during 12 weeks (USD 10,800). |
| 8 | a) Travel costs related to management plan update (USD 7,000); b) Domestic and international travel costs for fundraising (USD 12,000); c) Travel costs for diversity and forest monitoring in CNP and buffer zones (USD 8,000); d) Travel costs for field verification of LU/LC change (USD 3,000). |
| 9 | Verification of avoided deforestation targets under a REDD project for CNP (USD 25,000). |
| 10 | Basic equipment for PA operation: patrolling and surveillance, biodiversity monitoring (e.g., radios VHF, motorbikes, binoculars, computers, printer, software, etc.). |
| 11 | Satellite imagery and materials to assess LU/LC change in CNP and buffer zones. |
| 12 | Field supplies and materials for basic PA operations. |
| 13 | Grants to local communities for the biodiversity friendly economic activities (costs of development, implementation, and M&E) (USD 80,000 over a 4-year period). |
| 14 | a) Biodiversity monitoring and surveying protocols (USD 5,000): b) Materials for awareness-raising campaign: CNP biodiversity values, permitted activities and restrictions, and the importance of collaborative CNP and buffer zones management (USD 6,000); c) Publication of CNP and buffers zones management plan (USD 3,000). |
| 15 | a) Training program for enhance operational capacities of CNP (IBAP, DGFF, and other PA management council members) (USD 24,000); b) Joint DGF-IBAP training program for EIA, law enforcement, licensing, and monitoring (USD 15,000); c) Workshops and meetings for joint IBAP & DGFF planning and programing (USD 7,500); d) Training of local communities for surveillance and enforcement (USD 20,000); e) Workshops and meetings for negotiating, implementing, and monitoring collaborative agreements (USD 10,000); d) Workshops and meeting for participatory management plan update and business plan development (USD 15,000); |
| 16 | 50% of the costs for an international short-term consultant (at USD 3,500 per week): Evaluator (USD 14,000 for the mid-term evaluation and USD 14,000 for the final evaluation to be split 50/50 between UNDP and GEF). |
| 17 | a) 50% of the cost of a national short-term consultant (at USD 1,000 per week): Evaluator (USD 4,000 for the mid-term evaluation and USD 4,000 for the final evaluation to be split 50/50 between UNDP and GEF); b) Review and systematization of lessons learned and best practices (USD 4,000 @ USD 1,000/yr.); c) Technical reports on specific issues or areas of project activity (USD 4,000 @ USD 1,000/yr.). |
| 18 | 25% of the costs of the National Project Coordinator: project planning, day-to-day management of project activities, project reporting, maintaining key relationships with stakeholders. (USD 40,000 per year /costs over a 4-year period to be split 75/25 between UNDP and the GEF). |
| 19 | Domestic and international travel costs for mid-term evaluation (USD 7,800) and final evaluation (USD 7,800) |
| 20 | a) Digital camera (USD 400, USD 200/unit); b) two (2) computers (USD 3,000, USD 1,500/unit); c) One (1) printer (USD 750); d) IT supplies & maintenance (USD 2,000 @ USD 500/year during 4 years); e) Video beam (500); f) Office furniture: 2 sets of desks and chairs (USD 1,000; USD 500/set) |
| 21 | Communications related to project management (USD 7,200 @ USD 1,800/year for a 4-year period). |
| 22 | a) Office supplies related to project management (USD 2,400 @ USD 600/year for a 4-year period); b) Supplies for mid-term (USD 100) and final (USD 100) evaluations. |
| 23 | Office utilities related to project management (USD 7,200 @ USD 1,800/year during a 4-year period). |
| 24 | Insurance, bank charges, and other sundries related to project management (USD 3,485 over a 4-year period). |
| 25 | 50% of the costs of an international short-term consultant (at USD 3,500 per week): Evaluator (USD 14,000 for the mid-term evaluation and USD 14,000 for the final evaluation to be split 50/50 between UNDP and GEF). |
| 26 | 50% of the cost of a national short-term consultant (at USD 1,000 per week): Evaluator (USD 4,000 for the mid-term evaluation and USD 4,000 for the final evaluation to be split 50/50 between UNDP and GEF) |
| 27 | a) 75% of the costs of the National Project Coordinator: project planning, day-to-day management of project activities, project reporting, maintaining key relationships with stakeholders (USD 40,000 per year /costs over a 4-year period to be split 75/25 between UNDP and GEF); b) Full cost of a driver (USD 9,000 per year /costs over a 4-year period); c) Linked to Budget note 1; support to ongoing FGB operational and staff costs, until the Endowment Fund generates sustainable financing (USD 100,000 @ 25,000/year during for year). |
| 28 | Domestic travel costs of the National Project Coordinator and driver (USD 15,000 @ USD 3,750/year over a 4-year period). |
| 29 | One all-terrain project vehicle (at USD 30,000). |
| 30 | a) Gas for project vehicle (USD 8,000 @ USD 2,000/year during a 4-year period); b) Maintenance & Insurance of project vehicle (USD 12,000 @ USD 3,000/year during a 4-year period) |
| 31 | a) External audit (4) (USD 15,000 @ USD 3,750/yr.); b) Translations as needed (USD 4,000 @ 1,000/ year over a 4-year period) |
| 32 | Insurance, bank charges, and other sundries related to project management (USD 5,000 @ 1,250/year over a 4-year period) |
| 33 | Project Inception Workshop (USD 4,000), and Mid-Term (USD 1,500) and Final Evaluation (USD 1,500) related workshops. |

# SECTION IV: Additional Information

## PART I: Letters of co-financing commitment

- [See separate folder for all co-financing letters]

|  | Name of Co-financier | Date | Amounts | of which into FBG capital |
| --- | --- | --- | --- | --- |
| 1 | MAVA Foundation | 23/12/2014 | USD 1,619,488 (EUR 1,300,000) | USD 1,619,488 (EUR 1,300,000) |
| 2 | Government of Guinea Bissau/ Secretario de Estado do Ambiente: REDD revenue | 27/11/2014 | USD 3,200,000 | USD 3,200,000 |
| 3 | Government of Guinea Bissau: EU Fisheries Agreement | 24/12/2014 | USD 1,245,760 (EUR 1,000,000) | USD 1,245,760 (EUR 1,000,000) |
| 4 | UNDP | 26/11/2014 | USD 370,000 |  |
| 5 | World Bank | 02/12/2014 | USD 690,000 |  |
| 6 | European Union | 09/12/2014 | USD 9,360,000 (EUR 7,500,000) |  |
| 7 | Government of Guinea Bissau: IBAP | 01/12/2014 | USD 200,000 |  |
|  | Total |  | USD 16,685,248 | USD 6,065,248 |

## PART II: Stakeholder Involvement Plan and Coordination with other Related Initiatives

Stakeholder identification

During the project preparation stage, a stakeholder analysis was performed to identify key stakeholders at the national and local levels, assess stakeholders’ interests in the project, and define their roles and responsibilities for project implementation. Refer to Table 2 in Section I.4, which describes the major categories of stakeholders identified and the level of their involvement envisioned for the project.

Table 2 indicates that IBAP will be the main institution responsible for different components of project implementation. IBAP will work closely with other participating public institutions, in particular DGFF. IBAP participated in all aspects of project development.

The participation of FBG in project implementation will be instrumental for the success of activities planned under Component 1 of the project; the FBG has well-established stakeholder consultation processes, and the project preparation has been an integral part of its ongoing activities. The FBG’s Board was involved at all stages of project development.

IBAP and DGFF, local communites, other members of CNP’s Management Council, and NGOs will be the principal stakeholders participating in the joint planning and implementation of biodiversity and forest conservation and sustainable management in the CNP and its buffer zones.

Information dissemination, consultation, and similar activities that took place during the PPG

Throughout project development, close contact was maintained with the national and local stakeholders. National institutions and key donor agencies were directly involved in the development of the project. Numerous consultations occurred with all of the stakeholders to discuss the various aspects of project design. These consultations are described in the following paragraphs.

Component 1: For this project component consultations were performed with FBG, IBAP, and the World Bank to evaluate the status quo of activities that have already been implemented as well as ongoing activities, and identify priorities for implementation of activities under the GEF project to strengthen the FBG. Numerous conference calls were conducted during the consultation with these agencies and a joint analysis of activities to be implemented over the next four years was performed. Consultations with co-financing institutions were conducted to ensure that a well-orchestrated support package is designed for the SNAP of Guinea-Bissau.

Component 2: For this project component, consultations were made with IBAP and the World Bank, as well as co-financing agencies such as the EU (through the GCCA+ project).

3. Approach to stakeholder participation

The project’s approach for stakeholder involvement and participation is based on the principles outlined in the following table.

| Principle | Stakeholder participation will: |
| --- | --- |
| Adding Value | Be an essential means of adding value to the project. |
| Inclusivity | Include all relevant stakeholders. |
| Accessibility and Access | Be accessible and promote access to the process. |
| Transparency | Be based on transparency and fair access to information. |
| Fairness | Ensure that all stakeholders are treated in a fair and unbiased way. |
| Accountability | Be based on a commitment to accountability by all stakeholders. |
| Constructive | Seek to manage conflict and promote the public interest. |
| Redressing | Seek to redress inequity and injustice. |
| Capacitating | Seek to develop the capacity of all stakeholders. |
| Needs-Based | Be based on the needs of all stakeholders. |
| Flexible | Be designed and implemented in a flexible manner. |
| Rational and Coordinated | Be rationally planned and coordinated, rather than ad hoc. |
| Excellence | Be subject to ongoing reflection and improvement. |

Stakeholder involvement plan

The project’s design incorporates several features to ensure ongoing and effective stakeholder participation in its implementation. The mechanisms to facilitate the involvement and active participation of different stakeholders in project implementation will comprise a number of different elements:

a) Project inception workshop to enable stakeholder awareness of the start of project implementation

The project will be launched by a multi-stakeholder workshop. This workshop will provide an opportunity to provide all stakeholders with the most updated information on the project and the project work plan. It will also establish a basis for further consultation as the project’s implementation commences.

b) Formation of Project Steering Committee to ensure representation of stakeholder interests in project

A Project Steering Committee (PSC) will be formed to ensure broad representation of all key interests throughout the project’s implementation. The representation and broad terms of reference of the PSC are further described in Section I, Part III (Management Arrangements) of this Project Document.

c) Establishment of a Project Management team to oversee stakeholder engagement processes during project

The Project Management team will take direct operational and administrative responsibility for facilitating stakeholder involvement and ensuring increased local ownership of the project and its results. At the local level, particularly in the management of the CNP and buffer zones, stakeholder engagement will include the Management Council of the CNP, which has been operating since the establishment of the PA in 2008 and includes the Director of the CNP, representatives of communities living in the national parks, representatives of government agencies, representatives of CSOs (grassroots) associated with the CNP, and representatives of POLs.

d) Project communications to facilitate ongoing awareness of the project

Component 1 entails a specific output on communications to ensure that all stakeholders are critically aware of the functions of the FBG and that its governance is transparently managed.

Component 2 will be implemented in close coordination with the CNP Management Council, and collaborative agreements for biodiversity and forest conservation and management will be established between key government and local stakeholders, both of whom will facilitate communication for ongoing awareness of the project.

e) Direct involvement of local stakeholders in project implementation

Local stakeholders will be directly involved in the implementation of the project, in particular through project Component 2, by means of the following: a) participatory planning, management, monitoring, and control of biodiversity and forest resource use in the CNP and its buffer zones; and b) implementation of biodiversity-friendly production practices. IBAP considers local community participation as a central aspect of its operation principles; the project will adhere to this principle during implementation.

f) Establishing cooperative governance structures to formalize stakeholder involvement in the project

The project will strengthen the CNP Management Council and establish collaborative agreements to create governance structures for formalizing stakeholder involvement at the local level. In addition, through collaborative efforts between the DGFF and IBAP, biodiversity conservation and forest management plans will established for the CNP and its buffer zones.

g) Capacity-building

Project activities are strategically designed to build capacity of the institutional and community stakeholder groups – at the systemic, institutional, and individual levels – to ensure the sustainability of project outcomes. Investments are directed at building the capacities of IBAP and DGFF at the institutional level and at the level of the CNP and its buffer zones (i.e., park managers, rangers, and forestry field staff). At the community level, the project will strengthen the capacity of the CNP Management Council to negotiate, implement, and monitor collaborative agreements; to effectively engage in conflict resolution; and to work with the local communities in surveillance and enforcement activities. IBAP will provide technical assistance for the implementation of biodiversity-friendly practices and the local communities will be the beneficiaries of activities to raise awareness about biodiversity and ecosystem services conservation and PA and forest management laws and regulations.

Coordination with other related initiatives

Project design and implementation will build upon the achievements and investments of several closely related interventions and coordinate regularly with the following ongoing and planned projects. By investing in the CNP – a priority PA site in the Forest Belt region of Guinea-Bissau – the project will contribute to the process begun by the UNDP-GEF project to consolidate the SNAP (GEF ID 3575: Support for the Consolidation of a Protected Area System in Guinea-Bissau's Forest Belt) and correct the imbalance in the representativeness, connectivity, and operational management capacity of the terrestrial component of Guinea-Bissau’s SNAP. This ongoing project in turn provides a foundation for having improved systemic and institutional capacities as well as demonstrated community sustainable approaches that can be replicated in the CNP.

The project will also build upon the results of the World Bank-GEF Mid-size project (MSP) that was put into place by the FBG (GEF ID 3817 Guinea Bissau Biodiversity Conservation Trust Fund Project), while providing short-term, stopgap financing for the basic operating costs of the PA network and IBAP as more sustainable financing arrives. At the same time, the World Bank is implementing the Biodiversity Conservation Project (International Development Association-IDA Credit H6700), which builds upon the GEF MSP by reinforcing support to Guinea-Bissau related to the following: a) continuing to manage and conserve Guinea-Bissau’s existing network of five national PAs and their associated biodiversity; and b) piloting the operationalization of the FBG. Active collaboration and support was provided by the World Bank during the final design of the project proposed herein, ensuring harmonization and complementarity between these projects. In addition, the World Bank will be a member of the Project’s Board, which will ensure further collaboration during implementation.

In addition, the project proposed herein will build upon and coordinate closely with a World Bank-supported project (Community-based Avoided Deforestation project in Guinea-Bissau) in assessing and preparing the forests of the CNP (and Cacheu NP) with regard to their eligibility for avoided-deforestation REDD revenues. Once validated, the project will generate tradable emission reductions, creating a sustainable flow of revenue to local communities, PA management, and the FBG, thereby leveraging long-term protection of forests and related biodiversity.

The project will also coordinate closely with the EU-UNDP-WWF-funded West African Marine Ecoregion project (Gouvernance, politiques de gestion des ressources marines et réduction de la pauvreté dans l'Écorégion WAMER) which aims, inter alia, to improve governance and institutional capacity in Guinea-Bissau’s coastal and marine PAs and institutional support for the initial capitalization of the biodiversity trust fund/FBG. Similarly, the project will establish and maintain a close working relationship with the EU-funded project GCCA+ in Guinea Bissau: building resilience to climate change through enhanced institutional and mitigation capacities, particularly with regard to complementary initiatives for reducing deforestation in the CNP and its buffer zones. This project, which is currently in the final design stage, will be implemented simultaneously with the project proposed herein; during the PPG phase synergy was developed between the two projects and activities were planned to ensure complementarity and avoid duplication of efforts for the CNP. A third project, Gestão Sustentável dos Recursos Florestais no Parque Natural dos Tarrafes de Cacheu, which is funded by the EU, will provide lessons learned regarding community-based approaches for the sustainable development of PAs as well as collecting and processing data related to REDD.

Finally, the project will also coordinate actions with the two MAVA/IUCN projects Renforcement des dynamiques de conservation de l'environnement en Guinée Bissau and Promotion d’un tourisme écologique et durable en Guinée-Bissau, the latter of which will generate opportunities for biodiversity conservation and will benefit the resident populations of the PAs by promoting sustainable tourism in Guinea-Bissau with a focus on the PAs (it will end in March 2016).

## PART III. Terms of References for key project staff

The following are the indicative ToR for the project management staff. The project will be supervised by the Project Director and will be staffed by a full-time National Project Coordinator, which will be nationally-recruited position. The ToR for this position will be further discussed with UNDP´s CO and will be fine-tuned during the Inception Workshop so that roles and responsibilities and UNDP GEF reporting procedures are clearly defined and understood. Also, during the Inception Workshop the ToR for specific consultants and sub-contractors will be fully discussed and, for those consultancies to be undertaken during the first six months of the project, full ToR will be drafted and selection and hiring procedures will be defined.

Duties and Responsibilities

- Coordinate the production of project outputs, as per the project document.

- Mobilize all project inputs, in accordance with UNDP procedures for nationally implemented projects.

- Supervise and coordinate the work of all project staff, consultants and sub-contractors;

- Liaise with IBAP’s management, UNDP, relevant government agencies, and all project partners, including donor organizations and NGOs for effective coordination of all project activities.

- Ensure the timely submission of the Inception Report, the Combined UNDP-GEF report ‘Project Implementation Review/Annual Project Report’ (PIR), technical reports, quarterly financial and progress reports, terminal report, and any other reports as may be required by UNDP, GEF, IBAP and other oversight agencies.

- Disseminate project reports and respond to queries from interested stakeholders.

- Report progress in implementation and achievement of results to the steering committees, and ensure the fulfilment of directives from the committees.

- Work closely with the UNDP’s RTA and CO in ensuring exchange and sharing of experiences and lessons learned with relevant community based integrated conservation and development projects nationally and internationally.

- Assist local community groups, NGOs, PA and forestry staff, and others with development of essential skills through training workshops and on the job training thereby upgrading their institutional capabilities.

- Carry regular, announced and unannounced inspections of all sites and the activities of the project site management units.

# SECTION V: PROJECT ANNEXES

## Annex 1: Capacity Assessment

Pursuant to the UN General Assembly Resolution 56/201 on the triennial policy review of operational activities for development of the United Nations system, UNDP, UNICEF, UNFPA and WFP (UNDG ExCom Agencies) adopted a common operational framework for transferring cash to government and non-government Implementing Partners. Its implementation will significantly reduce transaction costs and lessen the burden that the multiplicity of UN procedures and rules creates for its partners.

Financial regulation 27.02 (Definitions) of the UNDP Financial Regulations and Rules (FRR) defines National Implementation Modality (NIM) as: "The overall management of UNDP programme activities in a specific programme country carried out by an eligible national entity of that country.” National implementation is used when there is adequate capacity in the national authorities to undertake the functions and activities of the programme or project.

National implementation is considered to be the norm since it is expected to contribute most effectively to:

- Greater national self-reliance by effective use and strengthening of the management capabilities, and technical expertise of national institutions and individuals, through learning by doing;

- Enhanced sustainability of development programmes and projects by increasing national ownership of, and commitment to development activities;

- Reduced workload and integration with national programmes through greater use of appropriate national systems and procedures.

The Agencies will assess the risks associated with transactions to an Implementing Partner, before initiating cash transfers under the harmonized procedures. Two types of assessments are required:

- Macro Assessment: In order to ensure adequate awareness of the Public Financial Management (PFM) environment within which Agencies will provide cash transfers to Implementing Partners, a review of existing assessments of the PFM system will be conducted. This review is expected to be undertaken once per programme cycle, preferably during Common Country Assessment (CCA) preparation, and may be updated whenever significant changes in the country’s governance system are noticed. The Macro Assessment findings provide information on the national context that is useful for each Micro Assessment. The findings related to the national audit system establish whether the audit system can be relied on to conduct the required audits of Implementing Partners who receive cash transfers. The Macro Assessment does not include an overall risk rating.

- Micro Assessment: This assesses the risks related to cash transfers to the partner and is done once every programme cycle, or whenever a significant change in the Implementing Partner’s organizational management is noticed. Assessments should be done for partners (government or NGO) that receive or are expected to receive cash transfers above an annual amount (usually USD 100,000 combined from all Agencies. The micro assessment reviews the Implementing Partner’s system of accounting, reporting, auditing, and internal controls.

The Macro and Micro Assessments serve two objectives:

- Development objective: The assessments help Agencies and the Government to identify strengths and weaknesses in the PFM system and the financial management practices of individual Implementing Partners, and identify areas for capacity development.

- Financial management objective:  The assessments help Agencies identify the most suitable resource transfer modality and procedures, and scale of assurance activities to be used with each Implementing Partner.

After assessing the national procurement and financial systems and the capacity of implementing partners, UNDP will adopt a risk management approach and select the most suitable funds transfer modality. In addition, UNDP will define steps to ensure the proper use of the funds provided. This will approach will ensure greater convergence between the assistance provided and the priorities and needs of each country.

Micro Assessment: IBAP

Based on the operating guidelines provided above, a micro assessment was performed in May 2011 to evaluate IBAP’s financial management capacity. The evaluation included a visit to IBAP’s headquarters to assess supporting financial documentation (e.g., decree of creation of IBAP, rules of procedure, handbook of financial, administrative, and accounting procedures, staff files, reports, and management tools) and interviews with key personnel.

IBAP’s micro assessment, as extracted from the micro assessment report, concluded that: “from all what precedes, we can say that IBAP disposes of an administrative and financial technical organisation for the management of donor funds, and is in position to manage UNDP funds on the condition that their capacity is strengthened in terms of human resources and training of implementation stakeholders, so they become familiar with the tools and procedures of UNDP (translated from French, YdS).

## Annex 2. UNDP Social and Environmental Screening

[To be completed for UNDP:LPAC]

## Annex 3. Example for CF Guiding Principles

Excerpts from Mozambique Feasibility Study/PPG: Set of Guiding Principles for CTF. It is proposed that these should be adopted to guide the CTF implementation.

Guiding Principles

It is recommended that the CTF be structured to achieve the following basic principles:

Government Support but not Control: Worldwide experience makes it abundantly clear that those CTFs that succeed are those that receive strong government support, but which are not controlled by government. Thus, the governance structure should have a slight nongovernmental majority while involving government at each step of the development and operation process.

Government Counterpart Funding: Since most potential international donors require government counterpart funding, priority will be given to seeking a decision by the Council of Ministers to develop an Environmental Compensation Scheme that would capitalize a CTF, or if this is not feasible, the development and passage of an Environmental Compensation Law that will institute a 0.5% tax on all development projects. This tax will be Government's contribution to the CTF.

Accountability: Funds administered by the CTF are understood to be managed in trust for the people of Mozambique, and for the donor agencies and their stakeholders. As such, the CTF should be fully accountable to donors, stakeholders, and the Government and people of Mozambique.

Participation: Priorities for grant making by the CTF will need to be established through participatory processes at the national and CA levels, and should include representatives of major stakeholder groups. Donors will be encouraged to respect these priorities, and grants will be made accordingly. Stakeholders should also be involved in participatory evaluations of the grant making process to identify weaknesses, and propose any amendments that may be required in functions and/or procedures.

Transparency: Important decisions on the grant making process will be communicated to stakeholders, including the Government and partners, on a regular basis, and all aspects of the process should be open to public inspection, except confidential information about individuals or grantees.

Rigorous oversight and review: Operations should be characterized by a rigorous system of regular technical and financial monitoring and evaluation with review by independent consultants and auditors which are tendered internationally.

Quality assurance: Results-based management should be used to establish the efficiency and effectiveness of the grant making process, identify bottlenecks and gaps, and provide the basis for timely solutions.

Adaptive management: The CTF should be a learning institution that not only monitors and evaluates each step of the grant making process for effectiveness and efficiency, but also acts quickly to revise procedures and improve performance when weaknesses are identified. Recommendations made by stakeholders (in the broadest sense) for revised procedures will need to be carefully considered and a dialogue undertaken to find the best solutions. As learning takes place, and new funding opportunities are identified, the CTF should evolve to deal effectively with new potential opportunities.

Institutional Diversity: It is understood that, just as with natural systems, institutional and financial diversity leads to stability. Thus, the CTF should see it as being in the interest of biodiversity conservation to support the existence, growth, and well-being of a diverse set of institutions related to biodiversity management, including financial intermediaries such as government-based environmental (FUNAB) and tourism (FUTUR) funds. It also should recognize the need to diversify sources of income, and to that end actively seek, experiment with, and bring on stream new sources, such as through payment for environmental services from CAs, individual donors, and partnerships with the private sector.

Good governance: The governing body and staff of the CTF should be held to the highest standards of ethical conduct, and conflicts of interest, or the appearance of conflict of interest, should be scrupulously avoided. Stakeholders should be encouraged to hold the CTF to the principles listed above at each stage of the development of the CTF, and of the grant making process.

## Annex 4. Rapid Assessment Result of BioGuinea Foundation (Fundação Bioguine) to Inform the Design of Component 1 of GEF/UNDP GEF 5 Project

The Rapid Assessment was undertaken by Integrated Environmental Consultants Namibia (IECN) in conjunction with MZ Nyeleti Consulting - Inclusive Financial and Rural Markets, November 2014

Section I: Background

Various financial mechanisms exist to support Protected Areas (PA) and PA systems. Among them are Conservation Trust Funds (CTFs). CTFs are institutions that can manage various financial products including, but not limited to, endowment funds, sinking funds, revolving funds, or debt for nature swaps. The traditional donor project support as well as government budget allocations, taxes and park revenues etc. are the other classical option to support the PAs. All these financial mechanisms can strategically complement each other and should act in synergy within the framework of a comprehensive financial strategy.

The Conservation Finance Alliance (CFA) in its most recent publication “Practice Standards for Conservation Trust Funds” (October 2014) defines a Conservation Trust fund as follows: “CTFs are private, legally independent institutions that provide sustainable grant-funding for biodiversity conservation. They often finance part of the long-term management costs of a country’s PA and/or PA system as well as conservation and sustainable development initiatives outside PA. CTFs raise and invest funds to make grants to NGOs or CBOs and governmental agencies (such as national park management authorities). A CTF usually manages one or several Funds, but most certainly an Endowment Fund where capital is invested in perpetuity and only interest or investment income is used to support conservation activities.

Guinea Bissau with its international partners had already at the end of the 1990’ties, when the Institute for Biodiversity and Protected Areas (IBAP) was conceived, decided to solve its persistent problem with predictable protected area financing through the establishment of Fundação BioGuine a CTF. Preparation to set-up the fund was financially supported mainly by the World Bank , GEF, EU and IUCN with its local partners IBAP, Government, Local and international NGOs and civil society, which took nearly a decade. This is nothing out of the extraordinary as establishing endowment funds simply takes a long time, as sound groundwork and strong buy-in from all stakeholders is of utmost importance for the smooth functioning of the mechanism. In GB additionally phases of political instability have induced a longer time lag in establishing a functional mechanism. Now the FUNDAÇÃO BIOGUINE is in its capitalisation phase and a manager (Executive Secretary) was recently employed, both significant milestones. However, there is still some ground to be covered before the Fund can start operating fully. The checklist included in in section 3 provides some guidance on what still needs to be done to fully operationalise the Fund, and the final section of this paper highlights critical areas which need to be taken care of as matter of priority. For example, additional members need to be recruited, the Board of Directors need to be elected and they all need to be familiarised with the Rules that will govern the Fund. Operations need to be run based on a 3 volumes strong Operation Manual determining the FBG’s processes and procedure to be followed.

As the WB‘s IDA funded Biodiversity Conservation Project (BCP) is coming to an end, and after previous GEF WB support, GEF/UNDP was asked to give the project continuity and support in form of technical assistance as well as a capital injection into FUNDAÇÃO BIOGUINE . Component 1 of the proposed GEF 5 project, namely “Strengthening the financial and operational framework of the national protected area system in Guinea-Bissau,” deals directly with the FBG.

This rapid assessment of the BioGuinea Foundation was conducted on 3 levels:

- Firstly, based on the Checklist for Environmental Funds elaborated by GEF and UNDP, it looked on whether all steps have been followed by establishing best practice CTFs and identified gaps which still need to be finalised in order to be compliant with GEF/UNDP standards on supporting Conservation Fund set-up processes and procedures.

- Secondly, the rapid assessment outlines Best Practices Principles and Standards in the Design and Set up of similar Funds implemented throughout the World in the last 20 years and compares these benchmarks with the design of the FUNDAÇÃO BIOGUINE.

- In a 3rd step the financial gap analysis and funding strategy prepared by FUNBIO in 2013/14 was analysed as it plays a key role in the funds capitalisation and respective endowment return.

Summarising the assessment results in form of a SWOT matrix and providing concluding remarks, ends the paper. Results of this rapid assessment updated the main project document of Component 1’s design.

Section II. Status quo of the set up process of FUNDAÇÃO BIOGUINE against pre-defined UNDP/GEF Milestones

Following the internal guidelines of UNDP/GEF the following checklist for the design and set-up of environmental funds gives an overview on where this process stands with the FBG. Whereas in theory the set-up should follow a certain sequencing of steps, this in reality is something not possible. The following table presents an overview of current implementation status, the sub-tables following provide an additional layer of information on: a) Legal Framework provisions; b) GEF Minimum Eligibility Criteria to be checked in feasibility study; c) Precondition check for capitalisation of fund during project preparation; and d) Due Diligence.

|  |  | Activities/Stages | Requirements | Status of Fundação BioGuine |
| --- | --- | --- | --- | --- |
| 1. |  | Project Concept |  |  |
|  | 1.1. | General Objectives of Fund in place? (conservation objectives and activities defined, various finance mechanisms evaluated) | Conservation objectives and related activities be clearly defined and an analysis on why this particular financial product was chosen and not any other. The design has to aim at reaching the desired objective and equally important be accountable. | The general objectives are defined in the Memorandum of Association of the BioGuinea Foundation prepared by Bates, Wells and Braithwaite dated 22.3.2011. The objectives of the Charity are: 1. To promote for the benefit of the public, the conservation, protection and improvement of the physical and natural environment and biodiversity of Guinea-Bissau, with priority focus on Guinea-Bissau’s national system of protected areas. 2. To promote, for the benefit of the public, sustainable development that supports the conservation of biodiversity in Guinea-Bissau in particular the protected areas and/or other areas of significant ecological conservation and/or biological importance including: (a) The preservation, conservation and the protection of the environment and the sustainable use of natural resources; and (b) The relief of poverty and the improvement of the conditions of life for the benefit of populations living in and around protected areas and other areas of significant ecological conservation and/or biological importance. and 3. To advance the education of the public on environmental issues including the biodiversity, conservation, sustainability and management of Guinea-Bissau’s protected areas and/or other areas of significant ecological conservation and/or biological importance. |
|  | 1.2 | Funding needs and gaps determined and quantified? | In general trust funds produce a steady long-term but modest income flow therefore this instruments might not be appropriate for big funding gaps identified which would require a big capital injection. Therefore the entire funding gap needs to be elaborated and the part identified suitable for fund finance. | In February 2014 a funding needs assessment had been conducted by FUNBIO for FBG. They distinguish between 4 scenarios dependent on how much the endowment fund is envisaged to contribute. Funding needs over the next 14 years vary between 12 and 24 Million Euros. Funding Gap total in Euros Minimalist -20.459.109 Realist -24.299.828 Strategic -21.330.386 Priority -11.966.762 Figures are reported in lump sum amounts and do not allow for a cost structure analysis. The underlying assumptions of the financial model are not easily accessible and a section in the report to describe the underlying assumptions and the data would be useful. It makes it difficult to judge whether figures are realistic or not and whether they are based on past financial performance or based on planned future spending. |
|  | 1.3 | Assess cofinancing options and document | Environmental funds should be capitalised by various sources. First because an endowment funds requires large amount of capital to produce a sizeable income stream and one investor might not be willing to take a risk on his own, but also a diversity of investors reduces the vulnerability of the fund per se and diminishes dependency. | The fund has made contacts with the MAVA Foundation, FFEM, KfW, EU, World Bank, GEF, UNDP, and others (no commitment as yet). Interest has been shown though no formal commitment has been obtained so far, Government indicated that I case REDD money is forthcoming, they intent to contribute to the capitalisation of FBG. The financial needs assessments list a number of potential funding sources but it is a rather vague list without concrete names, e.g. international NGOs, private sector. All contacts and options should be documented and archived for future use as new investors could be attracted for futures tranches when the fund can show off some actual performance indicators whether financial or impact related. At this stage the capital raised will be only for the endowment fund not yet also for sinking and revolving fund options as this would attract different funders/investors. Local investors, whether from the private or public sector, would strengthen ownership as at this point in time all substantial investors come from outside Guinea-Bissau |
| 2. |  | Project preparation |  |  |
|  | 2.1 | Analyses available legal structures requiring the establishment of a trust fund and document choices | A scoping study on suitable legal form should be conducted by experts on whom institutional options are available for trust funds and identify the most suitable legal forms for trust funds as well as documenting all legal provisions governing the fund, e.g. scope of allowable activities, governance structure, processes and procedures, dissolution. This should be done in a way that also non-legal experts can easily understand the rules and its implications. | Whether a similar legal form to the now registered British charity form exists in Guinea Bissau or not was most probably not the question but rather which form gives the funds the most credibility in an unstable political country as GB is. The legal form chosen is probably the less risky option in the view of attracting investors to the fund. To establish the Fund in country was not acceptable to donors, Therefore option overseas were explored and the UK framework was judged the most suitable |
|  | 2.2 | Define type of fund, e.g. endowment, sinking, revolving fund and document | It should be clearly stated which type or any mixture of it will be established. Therefore it is important to quantity and quality demand of financial resources and match it with the different types of financial instruments, for some chunk of expenses an endowment fund might be the matching instruments for other activities a sinking fund or revolving fund. Does the feasibility study clearly distinguish between these types? | The endowment option is the most advanced and the main reason to establish the fund. Though there is not exclusivity for this instrument as a fund can administer several business lines which diversify risk and investors and can respond to various funding needs requiring different products. So far neither sinking fund capital nor revolving fund demand has been quantified. It is not clear whether the fund per se has the purpose of overall donor/government coordination or not. |
|  | 2.3 | Conduct Feasibility study including viability analysis addressing eligibility, asset management, cofinancing | The feasibility study for the establishment of a new or existing fund is to be conducted by an experienced expert and should ascertain that GEF eligibility criteria (see below), are fulfilled, adequate operational and administrative requirements are satisfied as well as a functioning and effective governance structure in place. The design of asset management needs to ensure security of the assets from invasion, currency devaluation and other investment risk The study should establish cofinancing targets based on the previously established capital targets. | No complete feasibility study has been conducted, but bits and pieces separately. The fund handbook for example defines the operational and financial procedures, the Memorandum of the association defines the governance structures, the financial needs assessment the financial requirements. Asset management has not been addressed so far and this needs to be done as a selling point for investors. As said before cofinancing targeting has to be done as transparently as possible because it is not expected that professional investors buy in into "lump sum" figures not knowing where they were derived from. |
|  | 2.4 | Development of Fundraising strategy | Based on the realistically evaluated co financing needs, a clear strategy should be developed for the funds cofinancing requirements. Matching funds at least for the first tranche of capitalisation of funds have to be secured by donors/investors BEFORE project submission. (Fundraising costs needs to be included in budget=7-10% of capital to be raised). | The financial needs assessments touches on the sources of prospective capital. What is needed in a next step is to elaborate a specific fundraising strategy supplemented by detailed activities. Fundraising costs should not be underestimated and incorporated in the fund's budget as well as financial analysis. |
|  | 2.5 | Capacity building plan for management structure of the fund | A capacity building plan needs to be elaborated and budgeted for, e.g. board members, coop with other funds, seconding of expert to Board or similar. UNDP orders mentoring support and res rep or deputy sits in board on personal capacity. | Some TA costs have been set aside but it is not clear whether this includes the systematic mentoring/coaching of board members too. FUNBIO will assume some mentoring arrangement to support FBG’s operationalization. Board members should be familiarised with the foundation concept in comparison to for profit boards. |
|  | 2.6 | Set up a timeline for capitalisation in tranches | Ensure that tranching arrangements are in place, not too many not too few. This serves not only that capacities are built up before capital is fully committed and provides donor leverage, but funds are subject to economies of scale which reaps the most benefits if a substantial amount is applied and not withheld. Though tranching arrangements give some bargaining powers to enforce performance indicators to be fulfilled. | No detailed tranching has been planned so far and still needs to be elaborated. Phase I’s goal is to raise 10 Million US as Seed capital. This is extremely ambitious and often these funds live from the principle of early adapters and the herd followers. Also time line considerations should include the phasing in of new products as the introduction of revolving or sinking funds, or swaps. There is not yet a performance monitoring system in place linked to further capitalisation requirements. |
| 3. |  | Project Brief |  |  |
|  | 3.1 | An annex that provides the basis for justifying the creation of at the fund and how it will contribute to the conversation objective is prepared. | Included are analysis of funding deficits, objectives and activities, assumptions, key GEF requirements, legal, governance and operational structure, capitalisation steps, capacity building mechanisms, description of operation cost.= summary into main text | A summary pamphlet as well as a video clip has been produced to raise interest of potential investors but also for other publicity exercises. This should continue and be done in a simple understandable way for non-finance people and linked to impacts as opposed to a purely financial viewpoint. |
| 4. |  | Project Document |  |  |
|  | 4.1 | Prepare work plan with activities | A detailed schedule for operationalising the Fund should be in place. | This is currently in preparation and a joint document should be established to bring the implementing agency on the same page. |
|  | 4.2 | Precondition checks on capitalisation of Fund for first and subsequent tranches concluded | see below for preconditions to be checked during project preparation | In preparation |
|  | 4 | Harmonisation of procedures among investors/donors/implementers/government etc. | A fund lives and its impact maximised if they exploit their huge potential of scale economies. If a notorious difficult field of donor harmonisation can be achieved that would benefit everyone involved. | To be addressed and negotiated |
| 5. |  | Implementation: capitalisation |  |  |
|  | 5.1 | Due Diligence to be conducted to ensure that conditions have been met before capitalisation | A final professional due diligence evaluation has to be conducted to ensure that the minimum conditions specified precedent to capitalisation are satisfied along the lines provided in part V. | This should be done by professional experts in the field and not done in-house as this requires a different skill sets from the usual project associates. |
| 6. |  | Implementation: Supervision |  |  |
|  | 6.1 | Undertake independent audit of funds regularly | n/a | The Memorandum of Association prescribes yearly audits. One has to draft terms on what the audit should include; whether only the financial or also the operational procedures etc. |
|  | 6.2 | Design and implement annual M&E Programmes to assess impact on Fund |  | Ideally this should be done jointly also against impact assessment for conservation objective. For a financial person the functioning and profitability of the funds’ performance tops the agenda. The environmentalist is most interested what the fund achieves on implementation level. To match the two necessities and setup the fund as a two prong mechanisms is the challenge. For both aspects a proper M&E framework has to be in place hopefully harmonised among all stakeholders. |

Legal Framework provisions

| 1 | Registration requirement | Yes, registered under British Company's Act No.6 |
| --- | --- | --- |
| 2 | Scope of allowed activities | As per Memorandum of Association |
| 3 | Governance arrangements | As per Memorandum of Association |
| 4 | Processes and procedures for receipt of funds | Hand Book I-III |
| 5 | Limitation on investment activities | As per defined objectives/fund manager |
| 6 | Taxation requirement, incl. regulations governing taxation of assets outside of the country | In the UK as well as in GB (Memorandum of Understanding) should be tax exempted. |
| 7 | Arrangements of dissolution of the Fund | As per Memorandum of Association |

GEF Minimum Eligibility Criteria to be checked in feasibility study

| 1 | The fund can be established as a public-private mechanism outside of the direct government control | Done |
| --- | --- | --- |
| 2 | The fund has clear goals and objectives, which can be satisfied with the income generated from the proposed capital targets | FBG has clear general goals and overall objectives. These need to be broken down to more specific and detailed goals. The underlying financing study determining the proposed capital targets needs to be updated over time as the assumptions and underlying data is too general to conclude accurate fund requirements. |
| 3 | Existence of basic fabric of legal and financial practices and supporting institutions (including banking, auditing and contracting) in which the international community has confidence. | Yes |
| 4 | The fund may operate cost effectively , with operating costs within a range of 20-25% of the available annual income | An initial capitalisation of the fund of 6.8 Mio Euros is committed, and with planned expenses of Euro 259,000 in the first years of operations, the ratio far exceeds GEF's set target of up to 75%. Surely this will diminish if more funds can be mobilised. It should also be taken into account that start-up costs are higher and decrease over time not only proportionally but also in real terms. |
| 5 | The fund may be legally domiciled in the recipient country | Not wished for |

Precondition check for capitalisation of fund during project preparation

| before 1st tranche |  |
| --- | --- |
| Deed of Foundation for the Fund is notarised and legally registered | Yes |
| Bylaws contain legal provision against allocation of income towards baseline activities. | Defined in general, but allocation process needs to be refined, clearly structured and transparently communicated. |
| An independent, internationally reputable and experienced Asset Manager has been contracted, and an asset management strategy is agreed upon that assures the safety of assets | Not yet |
| An Operational Manual for the Fund is completed | Yes |
| A grant agreement is negotiated between UNDP and the Fund | In process |
| Parallel funding has been secured. | Partially |
| Prior to the Release of the Second, and subsequent tranches: | Not sure whether envisaged as yet |
| Parallel funding has been committed | n/a |
| Certification by independent evaluation that the fund is operating effectively and in accordance with best practices | n/a |
| Full disclosure and independent authentication of grant making criteria and procedures. | n/a |

Due Diligence

| 1 | Preparation and Signature of a Trust Fund Grant Agreement between UNDP and the Trust Fund | Next step |
| --- | --- | --- |
| 2 | Evidence that the Trust Fund has been legally registered in the country of domicile | Next step |
| 3 | Selection of an internationally recognized and credible Asset Manager through competitive tendering (a signed copy of the Contract is required) | Next step |
| 4 | Preparation of an asset management strategy (detailing how the corpus of the fund will be invested) | Next step |
| 5 | Evidence that the Trust Fund will be exempt from tax (where assets are being managed offshore, evidence that tax exemptions have been provided at the locus of asset management is needed) | Next step |
| 6 | Evidence that challenge grants have been raised | Next step |

Additional requirements include:

- Copy of the Operations Manual (Minutes of the Board Meeting approving the Operations manual should be attached)

- Letter from the Chairman of the Trust Fund requesting the transfer of funds, providing details of the  bank account to which funds would be transferred, and stating that  all conditions for disbursement established in the donor agreement have been met.

Section III. Design Principles and Best Practice Standards

There are certain core principles and practice standards which have evolved over the last years which are supposed to guide the design of conversation funds. A brief overview of key guiding principles and standards will follow below to enable the reader to relate to the following SWOT summary table. A more detailed description with explanation of core design principles is provided in the annexes and Practice Standards including and its explanations can be found in CFA’s most recent publications in this field of expertise.

The following basic principles are seen to be cornerstones in structuring successful CTFs starting with the ones, which need to be set straight at the beginning followed by the ones which will be set up during operations.

Almost always on top of the list when practitioners are ask what is/was the biggest threat to their CTFs is the political inference by Government regardless in what country or continent a fund operates. But without any Government involvement also not much seems to take off on its own. Government should support the FUNDAÇÃO BIOGUINE but not controlling it is on criterion specified in best practice guidance from Mozambique (Annex in ProDoc). Closely related to this criteria is that Government should provide counterpart funding or any other form of monetary contributions such as passing  of some Environmental Compensation Law which proceeds will be channeled to the CTF. The highest standard of good Governance governing the fund and that included accountability, transparency, quality assurance and rigorous oversight and review practices will apply. Statutes, regulation and bylaws and process and procedures need already be defined beforehand and transmitted to all involved stakeholders to cement in these principles right at the beginning. Adaptive management and institutional diversity should be developed throughout the lifetime of the fund to make success a possibility.

Closely related are the international Best Practice Standards on Conservation Trust Funds which are setting the bar on priority areas of funds in the areas of:  governance, operations, administration, reporting and M&E as well as asset management and resource mobilisation levels.

Surely these are often meant to function in an ideal World but reality often forces to make 2nd or even 3rd best choices especially in a challenging country set up as Guinea Bissau, which, realistically, would make the endowment fund and its management vulnerable. But it is useful to point these areas out before they become a problem so that risk mitigating mechanism can be put in place beforehand.

Section IV. Financial Implications from the Fundraising Strategy prepared by FUNBIO

A gap analysis was conducted by FUNBIO, a Brazilian CTF, in 2013/14, as part of a TA agreement they have with FUNDAÇÃO BIOGUINE, under the BCP. It is necessary to present the methodology applied and the underlying assumptions of the study, to interpret the results correctly. The objective of the study was to quantify the gap between the estimated demand and actual supply of financial resources towards PA funding in Guinea Bissau to derive the amount of capital needed to capitalise the FBG. The mismatch between demand and supply constitutes the gap of finance which has to be raised somewhere else, in the FBG case from the interest earned on the endowment fund and other more traditional sources of funding in order not to restrict implementation of planned activities. The time horizon of the study is 15 years.

These types of long-term financial projections are by nature a rough approximation only, especially when the estimates are based on planned subjective business plan figures and not on past real expense and income data. As no past income and expense data was available, all numbers determined were provided by untested estimates of expenses. For the supply side the data is a bit more realistic as actual available funds for projects available and still not expired were used.

The projections include PA cost estimates for each protected area, costs of IBAP- as PA Head Office and the cost of FBG. Summed up they present the demand for finance. Business plans were developed for most PAs plus IBAP, in two types of scenarios, (1) minimalist (operational costs and some project costs), and (2) realistic (= minimalist plus some more project activities), whereas the latter is by definition always higher as more activities are foreseen. Where business plans we not available estimated costs were used.

Costs types where lumped into 3 cost categories:  investment, staff and admin costs.

Investment cost: buildings, furniture, office, scientific equipment, cars, tourism material etc.

Staff cost: Salaries, taxes, bonuses

Admin costs: office costs, communication cost, transport

The study builds four different scenarios, namely a minimalist, a realistic, a priority, and a strategic option. By definition this includes:

Minimalist Scenario: All protected areas can implement the minimalist version of their developed business plans.

Realistic Scenario:  Minimalist option plus more activities/projects can be implemented by the PA.

Strategic Scenario: In this scenario the three “main” parks Parque Orango, João Vieira and Cantanhez will be able to implement the realistic version of their business plan, all other parks only their minimalist versions

Priority Scenario: The lightest version of all includes that only the 3 of the above mentioned parks receive investments according to the minimalist approach and the rest will just be functioning around the minimalist scenario but minus the investment costs.

Despite the fact that business volumes of the FBG will vary, it was decided to keep the cost for FBG and IBAP constant for the purposes of this analysis; it is however important to recognise that in reality these costs will evolve over time.

For the two “overhead” institutions IBAP and FBG, only for first had a business plan and budget available. FUNBIO’s suggested costs of FBG vary between 269.500 Euro in the long term when operation are expected to be more diverse and 159.800 Euros at start-up. These figures were reported as a lump sum and no more detailed budget information was available at time of this review.

It has to be noted that the business plans of IBAP were not reviewed or adapted in the FUNBIO National System for Protected Areas (SNAP) study, so no assessment was undertaken on whether they are realistic or not.. It should be also noted, as expenses are pure estimates with no basis and experience from previous operation that the financial projections need to be adapted as soon as more realistic figures become available. It needs to be ensured that a simple book keeping at PA level needs to take place to make future financial projection exercises less guestimates.

The supply side of the FUNBIO study lists available funds by current donor projects, which are earmarked for predefined activities. Altogether there are about Euro  8.5 Million not yet expensed thereof 4.2 Million Euro which can be deducted from the overall gap calculations as they are earmarked for IBAP, FUNDAÇÃO BIOGUINE  and a small government contribution. All of these commitments have phased out by 2017 latest.

DPA+FUNDAÇÃO BIOGUINE  = Demand for finance for Protected area system and FBG

SPA = Supply of contractual committed resources (current project commitment and public budget contribution)

rinv = Interest rate on investments (in Fin Bio fixed @ 5.9% )

CEndow Fund= Capital of endowment fund to break even

DPA+FBG-SPA= ∆Fin Gap

CEndow Fund =  ∆Fin Gap×1+rinv

For the calculation of the Finance gap and subsequently the value of the endowment fund needed the following simple model was used, where

Key results from the FUNBIO study with regard to the structure of the costs are reflected in the following table, showing the composition of the cost in terms of cost categories and institutions in total:

| Cost category | % range | Institutions | % range |
| --- | --- | --- | --- |
| Investment cost | 11 % – 13% | Protected Areas | 62% – 72% |
| Personnel cost | 33% – 36% | IBAP | 16% – 21% |
| Operations & Activities | 52% – 56% | FUNDAÇÃO BIOGUINE | 12% – 17% |

Looking at the composition, they look like in a healthy relation to each other as well as the cost allocation by beneficiary institution. It is assumed that the majority of the cost goes into activities and not staff cost, as well as most of the costs are incurred at PA operational level. How this will look in reality, when the first actual cost figures come in, needs to be re-analysed and if necessary adapted. A 12 – 17% overhead for FUNDAÇÃO BIOGUINE is in line with most donor overhead rates, GEF recommends anything below the margin of 20% - 25%.

As it is envisaged that FUNBIO will more continuously provide technical assistance to FBG, the importance of realistic financial modelling should be addressed and in turn capacity built until protected area and park management. FUNBIO should have clear terms of reference linked to a performance based contract.

The FUNBIO study estimated the finance gaps according to the different scenarios as follows:

|  | Gap total in Euro | Average yearly in Million (Mio) | Size of Endowment @ 5.9% in Mio | Min (after 2017) | Max (after 2017) | Endow F Min | Endow F Max |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Minimalist | -20.459.109 | 1.6 | 27.1 | 1.5 | 1.6 | 25.4 | 27.1 |
| Realist | -24.299.828 | 2 | 33.8 | 1.5 | 2.2 | 25.4 | 37 |
| Strategic | -21.330.386 | 1.8 | 30.5 | 1.5 | 1.8 | 25.4 | 30.5 |
| Priority | -11.966.762 | 1 | 17 | 1 | 1.1 | 17 | 18.6 |

On the assumption that interest earned is expensed in each year the average of endowments on hand are valued between 17 Mio for the priority scenario and up  to 33.8 Mio up to the realistic scenario based on elaborated business plans. In the most costly year the endowment needs to rise to 37 Mio to cover all the cost of GB’s SNAP.

Average cost for FBG rounded are between 190,000 Euro per year and 283,000 per year which would require an endowment of at least 3.2 Mio and 4.8 Mio respectively just to cover the FBG operational cost alone.

According to the study, funding for the financing of FBG operations is available at least partially until 2017. This needs to be confirmed as information received from different sources differ.

A question which needs answering is how the proceeds of the funds will be distributed if the endowment is not capitalised to earn as much as to cover all the demand of funding. This opens doors for conflict. This will be decided at Board level, but it is clear if firstly the FBG costs are not paid, the financial instrument will collapse. This will surely not go well with protected area objectives and donors, if they can’t mobilise direct project funding.

It is already seen at this early stage that the appetite for investors into the FBG is not as strong as was initially envisaged. But this is quite normal as to commit investors before a fund has a performance history is always a difficult undertaking, especially with a country like GB which is only known by most of political coups and not of their beauty and rareness of nature among the rest of the World.

The study would benefit for the sake of transparency and easier understanding from a paragraph describing the data used for the projections and its assumptions to give the readers an opportunity to place the projections.

A lot of emphasis has to be placed on fundraising which normally takes 7-10% of CFT costs.  A detailed strategy with a specific action plan has to be developed and immediately implemented. Long-term funding needs - on average – take far longer to be negotiated than short term funds.

The costs indicated for individual PA management seem to be reasonable at least to going concern and will not allow for really fancy expenses, but it should be taken into account that prefabricated budgets invite for inefficiencies and should be linked to cost saving / income generating incentive systems or linked to performances. It is not clear in how far the individual parks and civil society were consulted when defining yearly activities and related budgets. Ensuring consultation on this level would create some useful ownership of the national system of PA management and the FBG.

FUNBIO indicates in their report that the initial study was a first attempt of quantification, but that a more detailed study would need to be undertaken at a later stage, including revisiting the underlying assumptions business plans etc. What would be very important to do, is to prepare a different interest rate scenario as a steady 5.9% interest rate is not very realistic. Despite the reputation that most CTF endowments are well managed and indeed have produced on average about 5-7% return, it is difficult to predict how international financial markets develop as they can be very volatile at times. Calculating different interest rate scenarios might prepare FBG for rate changes and have a strategy in place how to deal with unexpected changes.

Section V. SWOT Analysis for planned FBG and conclusions

This rapid assessment has not been a detailed due diligence exercise or audit, analysing each single article of the operations handbook or bylaws for example, but rather checked whether key steps in setting up of FUNDAÇÃO BIOGUINE  have been followed and whether best practice design criteria were taken into account.

The following table is not complete but provides a summary of the rapid assessment and highlights FBG’s strength, weaknesses, opportunities and threats (SWOT).

| Strength | Weakness |
| --- | --- |
| - Existing structures and operations; previous investments - Long term sustainability - Solid institutional framework according to Best Practices - Able to use for operational costs for parks etc. - No direct Government control but participation - Conflict robust financing instruments - Product champion in place - Pragmatic approach to get something off the ground - Flexibility in spending - Fund management now in place - Initial Financing strategy in place | - Unstable ownership from GB especially on the lively Government side. How strong civil society is in GB and whether it was involved is unknown. - Donor driven - IBAP plays very dominant role in parks management, how participatory they operate is unknown but World Bank says it is good. - High overheads to be funded by the endowment fund, so little goes to the parks straight, non-transparent in terms of available financial data in the first place; vague projections based on weak data base - Detailed financial projections are missing - Basis and assumptions section of financing gap study weak - Design tailored entirely for IBAP - IBAP is a donor construct which has mainly driven the establishment - Various and more diverse entities involved in PA management not known and identified, and level of buy-in to concept not known - National HR resources limited - No incentives based performance system in place - “Cookie cutter” approach to establishing a CTF |
| Opportunities | Threats |
| - Product diversification - Exploitation scale and scope economies - Secure resources for PA in GB - Coordinate Government activities - Increase efficiency - Transparency of PA funding - Coordinate donor activities - Decentralisation and participation of PA management | - Political interference, to a large extent because of lacking ownership and also for competition (to be analysed in more detail) - Various Government structures involved in PA management may lead to internal quarrelling. - Political insecurity - Capitalisation of fund not achieved as high as needed so expectation might not be fulfilled and will cause drop outs - Foreseen Income generating no projects e.g. REDD’s carbon credits, etc. will not materialise. - Outbreak of Ebola |

The FBG is, in general, designed along best practice lines and follows standard conservation trust procedures. For a country like Guinea Bissau it might be good financial instrument for protected area financing as it is easier to control one big investment as in comparison to many smaller and less reliable projects. The following examines four key areas:

- Governance

- Operation/Administration

- Resource Mobilization:

- Reporting, Monitoring & Evaluation

GOVERNANCE:  With the design and the decision to incorporate the fund outside Guinea Bissau, it was tried to minimise the risk of direct government access. Also the Governance structure is planned that Government in theory might not be able to control the fund but participate. Whether these safeguarding mechanisms hold in practice, one will only know at a later stage. Among all threats to the smooth functioning of a CTF, government inference is still cited as the biggest threat among practitioners’ even when appropriate rules and regulation were put in place.

What seems as an advantage may simultaneously be a disadvantage. With the Fund outside the country, Government has no ownership, and also does not contribute (yet) to the capitalization of the Fund, although co-financing has been committed through REDD and the EU Fisheries Agreement for the GEF 5 project. It is asserted that ownership is important, as operating in a country without a supporting Government can be troublesome. FBG should invest into strengthening its relationship with Government and channel Government to play a constructive role. Relevant ongoing and targeted communication to ensure that the intentions of the Fund are well understood and supported will become even more important as the Fund is receiving endowment investments.

Though IBAP, one of the key players in the management of the protected area system, is an independent legal entity, the relation to the government is there. It is located under the State Secretariat of Environment and Tourism. It was recently considered for staff to be paid via the public budget. There is a real risk that IBAP, in time of crises, would potentially lean towards government support, should there be a conflict.

Another concern for FBG with respect to IBAP is its overdependence on the institution. IBAP is FBG’s main driver for their establishment, and the FBG is physically hosted at IBAP. This might bring along an entire different set of potential issues and problem areas. Assessed “independently” from an outside view, it is not clear in how far IBAP’s operations are fully participatory and collaborative with the individual parks and civil society. Additionally, often these types of “donor darling institutions” develop high cost structures, which are difficult to reverse and sadly often prove unstable in the long-term, as they consume an over-proportional amount of investment e.g. earned through an endowment fund. Through the formulation of incentive systems based on conservative spending or increasing other revenues, this risk can be reduced.

As in Guinea Bissau’s various government institutions are involved in environment relevant fields, like forestry and fishery, inter-ministerial bickering might occur when these government institutions are obliged to contribute to the capitalisation of the fund, but do not feature on the recipient list of the endowment proceeds. It is a great achievement to have solicited co-financing letters from Guinea Bissau’s REDD revenue and the EU Fisheries Agreement, but it is clear that ongoing relationship building is needed to address real threats of potential risks associated.

Clear guidelines of “to whom” and “how” returns of the FBG will be distributed among the various stakeholders needs to be developed urgently and relevant information needs to be transparently communicated to various target groups. If FBG consumes already 80% or so of interest earned on the endowment, soon other prospective beneficiaries will complain as they feel that they are not benefitting equally. This is a particularly high risk in the early days of the endowment, when the returns from the investment will still be relatively low. The GEF 5 project is designed to provide project support to the FBG for some time to help overcome such a risk, but it is clear that well thought through and realistic cost estimates are needed. The FUNBIO study was a first attempt into this direction, however, still needs to be strengthened. It is clear that a consensus on the “to whom” and “how” has to be reached and a dedicated communication strategy needs to be in place to reduce potential conflict, disagreement and misinterpretation take off.

OPERATION/ADMINISTRATION: Although it is foreseen to keep overall staffing of the FBG “light,” it seems that with its various “Boards” it is a heavy headed and slow construct. With trustees classified in numerous categories and regulation to have them in certain proportion will make the management cumbersome. Everything seems to be decided at the top. The need to regulate as much as possible is understandable from the viewpoint to protect the capital put into the fund, but it may make operations slow as Board members have limited time, and they often do not participate as actively as desired. The Fund management team and the beneficiaries might become frustrated about slow decision making. One way to speed up things could be through the delegation of operational task to committees, which are in a way more flexible and often can have a more specific skills set or a certain task on hand, speeding up operations.

So far only two appointed founding trustees are on the Board-of FBG. This seems by far too little at time of starting full operations. Normally when members are recruited the Board of Directors is elected according to the election law. It is not clear whether relevant by-laws for such aspects have already been elaborated. It seems important to regulate for some sort of diversity among board members.

An operational handbook with 3 volumes defining processes and procedures to be followed by fund managements is quite “scary.” The administrative guidance seems a bit blown out of proportion at a time when the Fund does not yet employ more than 2 people. Normally op manuals are carefully and gradually elaborated to match the needs of the institution in varying development stages. Often it is better to develop these over time to make them a relevant management instrument fully attuned to the “development stage” of the institution. At the same time one needs to be cautious not to make the Fund Management top heavy. In the end the Fund Management team just assumes administrative duties. It is planned that a separate investment banker will be employed, most probably situated abroad. There is a risk that if FBG fulfils too many technical roles, it can start being seen as a threat to IBAP.

Marketing/Communication of the fund and its rules and procedures will need to be one of the main activities in the first years. This includes training board members, members, staff, NGOs and other stakeholders on the functioning of the Fund. The rules of the game have to be clear and transparent otherwise the fund becomes a big black box look and is regarded as suspicious by non-insiders.

RESOURCE MOBILIZATION: It seems that delays in capitalization of the Fund during the past years, some of the strong momentum build up before has been lost. Efforts of convincing traditional (and non-traditional) institutions willing to capitalise the CTF need to be strengthened and a strong strategy needs to be pursued. It is hoped that by demonstrating some positive outcomes from the Fund at an early stage, it will be easier to solicit support from additional donor, international and national, and all stakeholders for this instrument in the future.

Looking at figures provided in the FUNBIO study, looking at an initial endowment value of between 21- 28 million EURO (USD 34.88 million), is in comparison to other younger funds a norm. Only few of the longer established and really well performing CTFs managed to capitalise above the 100 Mio Euros hurdle.

As already elaborated in section IV, IBAP needs a more detailed financing strategy preferably prepared in a participatory way involving communities, NGOs, individual park management and head office. The concept of business plans/work plans and budget is newly introduced concept in park management and likely needs some support effort in the beginning. Development of these plans must follow a bottom up approach and not top down, otherwise it is difficult to reach commitment from the implementers. People have to be trained using these plans and monitor their financial performance of budget versus actual costs and income, as well as demonstrating conservation impacts on the ground. This would help address transparency issues, increase efficiency, and improve much needed national ownership.

REPORTING, MONITORING & EVALUATION: The other task on hand is to develop a result oriented monitoring system. This will be a complex exercise as tracking environmental impacts in a short period of time and link this to the establishment of an endowment fund might be a challenge. A clear effort has to be made to develop a practical and effective system that can help ownership building, performance monitoring and communication on hopefully great conservation successes.

## Annex 5. Project Risk Analysis

| # | Description | Date Identified | Type | Probability and Impact | Countermeasures/ Management Response | Owner | Submitted, Updated By | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The capital invested in the FBG endowment and the revenue generated are diverted from their purpose, i.e. not used for the conservation of biodiversity and management of PAs | 12 Apr 2013 (at PIF) | Financial | Enter probability on a scale from 1 (low) to 5 (high) P = 2 Enter impact on a scale from 1 (low) to 5 (high) I = 2 | The governance of the FBG and its setup as a charity under English and Welsh law will guarantee institutional independence and accountability towards the donors over the long term. The FBG is set up in compliance with benchmark trust fund requirements (GEF, World Bank, UNDP, CFA). | FBG, UNDP | UNDP | Dec 2014 (during PPG) | Risk continues to persist |
| 2 | The global economic and financial crisis leads to reduced funds from international donors, and causes consistently lower returns on the endowment over the long term | 12 Apr 2013 (at PIF) | Financial | Enter probability on a scale from 1 (low) to 5 (high) P = 2 Enter impact on a scale from 1 (low) to 5 (high) I = 3 | The initial capitalization of the FBG endowment fund with USD 7,365,248 through the current project is one of the best mitigation responses to Guinea-Bissau’s high vulnerability to unpredictable and declining donor funding. In addition, the FBG will engage in more proactive promotional activities that involve some key players and institutions involved in the conservation of Guinea-Bissau’s biodiversity (including IBAP, UNDP and others) to leverage further contributions. The project will conduct an in-depth analysis of more general financing mechanisms that can be applied in the country to broaden the spectrum of income sources – for the endowment but also for sinking and revolving funds. Although interest rates and investment returns have been relatively low in recent years, historical data suggest that it is reasonable to assume an average 5.9% return on the FBG investments over the long term, which is the rate reflected in the proposal, following the FUNBIO study. Possible fluctuations in future returns will be taken into account in the design of the investment and grant-making strategies. | FBG, UNDP | UNDP | Dec 2014 (during PPG) | Risk continues to persist |
| 3 | Institutional agreements involving IBAP, DGFF and other key stakeholders do not function properly, undermining the effective governance and management of CNP and of forests in its periphery. | 12 Apr 2013 (at PIF) | Institutional | Enter probability on a scale from 1 (low) to 5 (high) P = 4 Enter impact on a scale from 1 (low) to 5 (high) I = 4 | This is a critical element of the project. An effective collaborative framework between the two lead institutions has not yet been put into place and tested, and misaligned approaches prevail. Hence, based on the precautionary principle, the risk is presently flagged as high. Great attention will be paid during the project preparation phase to coordinate closely with IBAP, DGFF, and other key stakeholders at the national, regional, and local levels. Practical tools and formal protocols will be established to ensure the effective co-execution of the project by the two leading partner institutions. Joint training and capacity building are envisioned as well as a review of policy and legislative frameworks and of institutional mandates, proposing amendments where appropriate and in the clear interest of improved PA management and forest biodiversity conservation. | IBAP, DGFF, UNDP | IBAP, UNDP | Dec 2014 (during PPG) | Risk continues to persist |
| 4 | Political interference disempowers the FBG and leads to its collapse | Dec 2014 (during PPG) | Political | Enter probability on a scale from 1 (low) to 5 (high) P = 3 Enter impact on a scale from 1 (low) to 5 (high) I = 3 | The careful setup of the FBG and its legal arrangements may secure investments abroad and instil donor confidence; however, it may also disenfranchise national stakeholders. Donors may be seen to manipulate national affairs, and competition for revenue generated from the endowment may erupt – although the careful setup has taken all possible legal issues and actions under consideration. It is critical that the FBG invests in dedicated communications, information sharing and public relations on an ongoing basis to ensure that any potential misconceptions be addressed systematically. Output 1.6 has been included in the project design to address this risk specifically. | IBAP, UNDP | IBAP, UNDP | Dec 2014 (during PPG) | Risk continues to persist |
| 5 | The impacts of large-scale enterprises in sectors such as logging or mining reduce the viability for biodiversity conservation of CNP and of connected buffer areas and biological corridors. | 12 Apr 2013 (at PIF) | Developmental/ Institutional | Enter probability on a scale from 1 (low) to 5 (high) P = 3 Enter impact on a scale from 1 (low) to 5 (high) I = 3 | This risk is precisely why this project in CNP is so critically important, and the enhanced PA management and law enforcement in conjunction with already sensitized communities is the best response. Specific training and capacity-building measures for EIAs and the licensing and monitoring of economic activities will target PA staff and personnel from IBAP and DGFF at the regional and national levels. In addition, the participation of the CAIA, which is attached to the SEA, was actively sought during project preparation and will continue throughout the implementation phase. | IBAP, DGFF | IBAP, DGFF | Dec 2014 (during PPG) | Risk continues to persist |
| 6 | Political and institutional instability disrupts minimal governance conditions necessary for project implementation | 12 Apr 2013 (at PIF) | Political/ institutional | Enter probability on a scale from 1 (low) to 5 (high) P = 3 Enter impact on a scale from 1 (low) to 5 (high) I = 4 | The political and governance situation in the country has recently seen significant improvements, yet a degree of instability and governance challenges remain that may affect the enforcement of existing PAs. However, IBAP has effectively operated under similar conditions in the past, even if minor disruptions may occur that cannot be prevented; wherefore the risk appears manageable. | IBAP UNDP | IBAP, UNDP | Oct 2014 (during PPG) | Risk continues to persist |
| 67 | Climate change could have a negative impact upon key biodiversity and ecosystems in Guinea-Bissau in general and in CNP and adjacent areas in particular, undermining project achievements. | 12 Apr 2013 (at PIF) | Environmental | Enter probability on a scale from 1 (low) to 5 (high) P = 2 Enter impact on a scale from 1 (low) to 5 (high) I = 2 | Some of the climate change trends that have been observed, or can reasonably be expected, are related to increasing sea level and wave energy causing coastal-zone erosion and salt water intrusion, increased variability in rainfall/rainy season, more frequent uncontrolled fires, and changes in ecological communities and ecosystem functionality. However, the SNAP that the GoGB has established, the management of which is ensured through IBAP, besides covering an important portion of the country’s territory, also makes ample provisions for ecological corridors between individual PAs that are expected to increase the resilience of the ecological systems and its constituent species. The extensive mangrove areas remaining in the country (and which are well covered in the SNAP) mitigate the impact in terms of coastal erosion. In the CNP specifically, the PA management plan in its updated version will integrate climate change considerations in terms of adaptive management of biodiversity and natural resources in the PA and adjacent areas, to the best possible degree given knowledge constraints. The project will contribute to consolidating corridors between CNP and other PAs, enhancing the resilience of ecosystems and key species to climate variability and change. Over the longer term, sustainable recurrent revenues from FBG will allow IBAP and its PA/biodiversity management partners to strengthen monitoring efforts, generating more information and allowing enhanced adaptation of management and conservation strategies in response to climate change-induced trends. | IBAP, UNDP | IBAP, UNDP | oct 2014 (during PPG) | Risk continues to persist |

## Annex 6. BD-1 Tracking Tools: METTs and Financial Sustainability Scorecard

| Tracking Tool for Biodiversity Projects in GEF-3, GEF-4, and GEF-5. |
| --- |
| Objective 1: Catalyzing Sustainability of Protected Area Systems |  |  |
| SECTION I |  |  |
| Objective: To measure progress in achieving the impacts and outcomes established at the portfolio level under the biodiversity focal area. Rationale: Project data from the GEF-3, GEF-4, and GEF-5 project cohort will be aggregated for analysis of directional trends and patterns at a portfolio-wide level to inform the development of future GEF strategies and to report to GEF Council on portfolio-level performance in the biodiversity focal area. Structure of Tracking Tool: Each tracking tool requests background and coverage information on the project and specific information required to track portfolio level indicators in the GEF-3, GEF-4, and GEF-5 strategy. Guidance in Applying GEF Tracking Tools: GEF tracking tools are applied three times: at CEO endorsement, at project mid-term, and at project completion. Submission: The finalized tracking tool will be cleared by the GEF Agencies as being correctly completed. |  |  |
| Important: Please read the Guidelines posted on the GEF website before entering your data |  |  |
| I. General Data | Please indicate your answer here | Notes |
| Project Title | Strengthening the financial and operational framework of the national PA system in Guinea-Bissau |  |
| GEF Project ID | 5368 |  |
| Agency Project ID | 5177 |  |
| Implementing Agency | UNDP |  |
| Project Type | FSP | FSP or MSP |
| Country | Guinea-Bissau |  |
| Region | AFR |  |
| Date of submission of the tracking tool |  | To be determined |
| Name of reviewers completing tracking tool and completion date |  | Completion Date: 01/15/2015 |
| Planned project duration | 4 | years |
| Actual project duration |  | years |
| Lead Project Executing Agency (ies) |  | Institute for Biodiversity and Protected Areas (IBAP) |
| Date of Council/CEO Approval |  | To be determined |
| GEF Grant (US$) | 2,304,429 |  |
| Cofinancing expected (US$) | 16,685,248 |  |
| II. Total Extent in hectares of protected areas targeted by the project by biome type | Please indicate your answer here |  |
| Please use the following biomes provided below and place the coverage data within these biomes |  |  |
| Terrestrial (insert total hectares for terrestrial coverage and then provide coverage for each of the terrestrial biomes below) |  |  |
| Total hectares | 482,502 | ha |
| Tropical and subtropical moist broadleaf forests (tropical and subtropical, humid) |  | ha |
| Tropical and subtropical dry broadleaf forests (tropical and subtropical, semi-humid) |  | ha |
| Tropical and subtropical coniferous forests (tropical and subtropical, semi-humid) |  | ha |
| Temperate broadleaf and mixed forests (temperate, humid) |  | ha |
| Temperate coniferous forests (temperate, humid to semi-humid) |  | ha |
| Boreal forests/taiga (subarctic, humid) |  | ha |
| Tropical and subtropical grasslands, savannas, and shrublands (tropical and subtropical, semi-arid) |  | ha |
| Temperate grasslands, savannas, and shrublands (temperate, semi-arid) |  | ha |
| Flooded grasslands and savannas (temperate to tropical, fresh or brackish water inundated) |  | ha |
| Mangroves |  | ha |
| Montane grasslands and shrublands (alpine or montane climate) |  | ha |
| Tundra (Arctic) |  | ha |
| Mediterranean forests, woodlands, and scrub or Sclerophyll forests (temperate warm, semi-humid to semi-arid with winter rainfall) |  | ha |
| Deserts and xeric shrublands (temperate to tropical, arid) |  | ha |
| Mangrove (subtropical and tropical, salt water inundated) |  | ha |
| Freshwater (insert total hectares for freshwater coverage and then provide coverage for each of the freshwater biomes below) |  |  |
| Total hectares |  | ha |
| Large lakes |  | ha |
| Large river deltas |  | ha |
| Polar freshwaters |  | ha |
| Montane freshwaters |  | ha |
| Temperate coastal rivers |  | ha |
| Temperate floodplain rivers and wetlands |  | ha |
| Temperate upland rivers |  | ha |
| Tropical and subtropical coastal rivers |  | ha |
| Tropical and subtropical floodplain rivers and wetlands |  | ha |
| Tropical and subtropical upland rivers |  | ha |
| Xeric freshwaters and endorheic basins |  | ha |
| Oceanic islands |  | ha |
| Marine (insert total hectares for marine and then distinguish coverage between each of the following zones) |  |  |
| Total hectares |  | ha |
| Coral reefs |  | ha |
| Estuaries |  | ha |
| Ocean (beyond EEZ) |  | ha |
| III. Please complete the table below for the protected areas that are the target of the GEF intervention and add new sections for each protected area if the project extends beyond four Pas. Use NA for not applicable. | Please indicate your answer here |  |
| 1. Protected Area |  |  |
| Name of Protected Area | Cantanhez National Park (CNP) |  |
| Is this a new protected area? | 0 | Yes = 1, No = 0 |
| Area in Hectares | 105,800 | ha, Please specify biome type |
| Global designation or priority lists | WWF Global 2000 | (E.g., Biosphere Reserve, World Heritage site, Ramsar site, WWF Global 2000, etc.) |
| Local Designation of Protected Area | National Park | (E.g, indigenous reserve, private reserve, etc.) |
| IUCN Category | 2 | 1: Strict Nature Reserve/Wilderness Area: managed mainly for science or wilderness protection 2: National Park: managed mainly for ecosystem protection and recreation 3: Natural Monument: managed mainly for conservation of specific natural features 4: Habitat/Species Management Area: managed mainly for conservation through management intervention 5: Protected Landscape/Seascape: managed mainly for landscape/seascape protection and recreation 6: Managed Resource Protected Area: managed mainly for the sustainable use of natural ecosystems |
| 2. Protected Area |  |  |
| Name of Protected Area | Lagoa de Cufada National Park (LCNP) |  |
| Is this a new protected area? | 0 | Yes = 1, No = 0 |
| Area in Hectares | 89,000 | Please specify biome type |
| Global designation or priority lists | Ramsar site | (E.g., Biosphere Reserve, World Heritage site, Ramsar site, WWF Global 2000, etc.) |
| Local Designation of Protected Area | National Park | (E.g, indigenous reserve, private reserve, etc.) |
| IUCN Category | 4 | 1: Strict Nature Reserve/Wilderness Area: managed mainly for science or wilderness protection 2: National Park: managed mainly for ecosystem protection and recreation 3: Natural Monument: managed mainly for conservation of specific natural features 4: Habitat/Species Management Area: managed mainly for conservation through management intervention 5: Protected Landscape/Seascape: managed mainly for landscape/seascape protection and recreation 6: Managed Resource Protected Area: managed mainly for the sustainable use of natural ecosystems |
| 3. Protected Area |  |  |
| Name of Protected Area | Tarafes do Rio Cacheu National Park (TCNP) |  |
| Is this a new protected area? | 0 | Yes = 1, No = 0 |
| Area in Hectares | 80,000 | Please specify biome type |
| Global designation or priority lists | WWF Global | (E.g., Biosphere Reserve, World Heritage site, Ramsar site, WWF Global 2000, etc.) |
| Local Designation of Protected Area | Estatal | (E.g, indigenous reserve, private reserve, etc.) |
| IUCN Category | 2 | 1: Strict Nature Reserve/Wilderness Area: managed mainly for science or wilderness protection 2: National Park: managed mainly for ecosystem protection and recreation 3: Natural Monument: managed mainly for conservation of specific natural features 4: Habitat/Species Management Area: managed mainly for conservation through management intervention 5: Protected Landscape/Seascape: managed mainly for landscape/seascape protection and recreation 6: Managed Resource Protected Area: managed mainly for the sustainable use of natural ecosystems |
| 4. Protected Area |  |  |
| Name of Protected Area | Orango National Park (ONP) |  |
| Is this a new protected area? | 0 | Yes = 1, No = 0 |
| Area in Hectares | 158,235 | Please specify biome type |
| Global designation or priority lists | Biosphere Reserve | (E.g., Biosphere Reserve, World Heritage site, Ramsar site, WWF Global 2000, etc.) |
| Local Designation of Protected Area | National Park | (E.g, indigenous reserve, private reserve, etc.) |
| IUCN Category | 2 | 1: Strict Nature Reserve/Wilderness Area: managed mainly for science or wilderness protection 2: National Park: managed mainly for ecosystem protection and recreation 3: Natural Monument: managed mainly for conservation of specific natural features 4: Habitat/Species Management Area: managed mainly for conservation through management intervention 5: Protected Landscape/Seascape: managed mainly for landscape/seascape protection and recreation 6: Managed Resource Protected Area: managed mainly for the sustainable use of natural ecosystems |
| 5. Protected Area |  |  |
| Name of Protected Area | Joao Vieira e Poilão Marine Protected Area |  |
| Is this a new protected area? | 0 | Yes = 1, No = 0 |
| Area in Hectares | 49,500 | Please specify biome type |
| Global designation or priority lists | Reserva Biosfera | (E.g., Biosphere Reserve, World Heritage site, Ramsar site, WWF Global 2000, etc.) |
| Local Designation of Protected Area | Marine Protected Area and Community Reserve | (E.g, indigenous reserve, private reserve, etc.) |
| IUCN Category | 2 | 1: Strict Nature Reserve/Wilderness Area: managed mainly for science or wilderness protection 2: National Park: managed mainly for ecosystem protection and recreation 3: Natural Monument: managed mainly for conservation of specific natural features 4: Habitat/Species Management Area: managed mainly for conservation through management intervention 5: Protected Landscape/Seascape: managed mainly for landscape/seascape protection and recreation 6: Managed Resource Protected Area: managed mainly for the sustainable use of natural ecosystems |

| Tracking Tool for Biodiversity Projects in GEF-3, GEF-4, and GEF-5. |
| --- |
| Objective 1: Catalyzing Sustainability of Protected Area Systems |  |  |
| SECTION II: Management Effectiveness Tracking Tool for Protected Areas |  |  |
| Note: Please complete the management effectiveness tracking tool for EACH protected area that is the target of the GEF intervention and create a new worksheet for each. Structure and content of the Tracking Tool - Objective 1. Section II: The Tracking Tool has two main sections: datasheets and assessment form. Both sections should be completed. 1. Datasheets: the data sheet comprises of two separate sections: ü Data sheet 1: records details of the assessment and some basic information about the site, such as name, size and location etc. ü Data sheet 2: provides a generic list of threats which protected areas can face. On this data sheet the assessors are asked to identify threats and rank their impact on the protected area. 2. Assessment Form: the assessment is structured around 30 questions presented in table format which includes three columns for recording details of the assessment, all of which should be completed. |  |  |
| Important: Please read the Guidelines posted on the GEF website before entering your data |  |  |
| Data Sheet 1: Reporting Progress at Protected Area Sites | Please indicate your answer here | Notes |
| Name, affiliation and contact details for person responsible for completing the METT (email etc.) | Queba Quecuta (quecutaqueba@hotmail.com) |  |
| Date assessment carried out | December 3rd, 2014 | Month DD, YYYY (e.g., May 12, 2010) |
| Name of protected area | Cantanhez National Park (CNP) |  |
| WDPA site code (these codes can be found on www.unep-wcmc.org/wdpa/) | 351088 |  |
| Designations(please choose 1-3) | 2 | 1: National 2: IUCN Category 3: International (please complete lines 35-69 as necessary ) |
| Country | Guinea-Bissau |  |
| Location of protected area (province and if possible map reference) | Regiäo de Tombali 11°15′53″N 15°01′45″W﻿ / ﻿11.26461°N 15.02930°W﻿ / 11.26461; -15.02930 |  |
| Date of establishment | October 1st, 2007 |  |
| Ownership details (please choose 1-4) | 1 | 1: State 2: Private 3: Community 4: Other |
| Management Authority | Institute for Biodiversity and Protected Areas (IBAP) |  |
| Size of protected area (ha) | 105,800 |  |
| Number of Permanent staff | 2 |  |
| Number of Temporary staff | 16 |  |
| Annual budget (US$) for recurrent (operational) funds – excluding staff salary costs | Not specified |  |
| Annual budget (US$) for project or other supplementary funds – excluding staff salary costs | Not specified |  |
| What are the main values for which the area is designated | Greatest extension of sub humid forest in Guinea-Bissau |  |
| List the two primary protected area management objectives in below: |  |  |
| Management objective 1 | Preserve, conserve, and defend the last vestige of the northernmost sub-humid forest of West Africa |  |
| Management objective 2 | Promote ecotourism and enhance economic activities in order to improve the livelihoods of local residents |  |
| No. of people involved in completing assessment |  |  |
| Including: (please choose 1-8) | 3 | 1: PA manager 2: PA staff 3: Other PA agency staff 4: Donors 5: NGOs 6: External experts 7: Local community 8: Other |
| Information on International Designations | Please indicate your answer here |  |
| UNESCO World Heritage site (see: http://whc.unesco.org/en/list) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical co-ordinates |  |  |
| Criteria for designation |  | (i.e. criteria i to x) |
| Statement of Outstanding Universal Value |  |  |
| Ramsar site (see: http://ramsar.wetlands.org) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical number |  |  |
| Reason for Designation (see Ramsar Information Sheet) |  |  |
| UNESCO Man and Biosphere Reserves (see: http://www.unesco.org/new/en/natural-sciences/environment/ecological-sciences/man-and-biosphere-programme/ | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  | Total, Core, Buffe, and Transition |
| Geographical co-ordinates |  |  |
| Criteria for designation |  |  |
| Fulfilment of three functions of MAB |  | conservation, development and logistic support |
| Please list other designations (i.e. ASEAN Heritage, Natura 2000) and any supporting information below | X |  |
|  | WWF Global 2000 | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
| Data Sheet 2: Protected Areas Threats (please complete a Data Sheet of threats and assessment for each protected area of the project). |  |  |
| Please choose all relevant existing threats as either of high, medium or low significance. Threats ranked as of high significance are those which are seriously degrading values; medium are those threats having some negative impact and those characterised as low are threats which are present but not seriously impacting values or N/A where the threat is not present or not applicable in the protected area. |  |  |
| 1. Residential and commercial development within a protected area |  |  |
| Threats from human settlements or other non-agricultural land uses with a substantial footprint |  |  |
| 1.1 Housing and settlement | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 1.2 Commercial and industrial areas | - | 0: N/A 1: Low 2: Medium 3: High |
| 1.3 Tourism and recreation infrastructure | - | 0: N/A 1: Low 2: Medium 3: High |
| 2. Agriculture and aquaculture within a protected area |  |  |
| Threats from farming and grazing as a result of agricultural expansion and intensification, including silviculture, mariculture and aquaculture |  |  |
| 2.1 Annual and perennial non-timber crop cultivation | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 2.1a Drug cultivation | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.2 Wood and pulp plantations | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.3 Livestock farming and grazing | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2.4 Marine and freshwater aquaculture | - | 0: N/A 1: Low 2: Medium 3: High |
| 3. Energy production and mining within a protected area |  |  |
| Threats from production of non-biological resources |  |  |
| 3.1 Oil and gas drilling | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.2 Mining and quarrying | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.3 Energy generation, including from hydropower dams | - | 0: N/A 1: Low 2: Medium 3: High |
| 4. Transportation and service corridors within a protected area |  |  |
| Threats from long narrow transport corridors and the vehicles that use them including associated wildlife mortality |  |  |
| 4.1 Roads and railroads (include road-killed animals) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.2 Utility and service lines (e.g. electricity cables, telephone lines,) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.3 Shipping lanes and canals | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.4 Flight paths | - | 0: N/A 1: Low 2: Medium 3: High |
| 5. Biological resource use and harm within a protected area |  |  |
| Threats from consumptive use of "wild" biological resources including both deliberate and unintentional harvesting effects; also persecution or control of specific species (note this includes hunting and killing of animals) |  |  |
| 5.1 Hunting, killing and collecting terrestrial animals (including killing of animals as a result of human/wildlife conflict) | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 5.2 Gathering terrestrial plants or plant products (non-timber) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.3 Logging and wood harvesting | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.4 Fishing, killing and harvesting aquatic resources | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 6. Human intrusions and disturbance within a protected area |  |  |
| Threats from human activities that alter, destroy or disturb habitats and species associated with non-consumptive uses of biological resources |  |  |
| 6.1 Recreational activities and tourism | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.2 War, civil unrest and military exercises | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.3 Research, education and other work-related activities in protected areas | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.4 Activities of protected area managers (e.g. construction or vehicle use, artificial watering points and dams) | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.5 Deliberate vandalism, destructive activities or threats to protected area staff and visitors | - | 0: N/A 1: Low 2: Medium 3: High |
| 7. Natural system modifications |  |  |
| Threats from other actions that convert or degrade habitat or change the way the ecosystem functions |  |  |
| 7.1 Fire and fire suppression (including arson) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.2 Dams, hydrological modification and water management/use | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3a Increased fragmentation within protected area | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3b Isolation from other natural habitat (e.g. deforestation, dams without effective aquatic wildlife passages) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3c Other ‘edge effects’ on park values | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3d Loss of keystone species (e.g. top predators, pollinators etc) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 8. Invasive and other problematic species and genes |  |  |
| Threats from terrestrial and aquatic non-native and native plants, animals, pathogens/microbes or genetic materials that have or are predicted to have harmful effects on biodiversity following introduction, spread and/or increase |  |  |
| 8.1 Invasive non-native/alien plants (weeds) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1a Invasive non-native/alien animals | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1b Pathogens (non-native or native but creating new/increased problems) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.2 Introduced genetic material (e.g. genetically modified organisms) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9. Pollution entering or generated within protected area |  |  |
| Threats from introduction of exotic and/or excess materials or energy from point and non-point sources |  |  |
| 9.1 Household sewage and urban waste water | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.1a Sewage and waste water from protected area facilities (e.g. toilets, hotels etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.2 Industrial, mining and military effluents and discharges (e.g. poor water quality discharge from dams, e.g. unnatural temperatures, de-oxygenated, other pollution) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.3 Agricultural and forestry effluents (e.g. excess fertilizers or pesticides) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.4 Garbage and solid waste | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 9.5 Air-borne pollutants | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 9.6 Excess energy (e.g. heat pollution, lights etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 10. Geological events |  |  |
| Geological events may be part of natural disturbance regimes in many ecosystems. But they can be a threat if a species or habitat is damaged and has lost its resilience and is vulnerable to disturbance. Management capacity to respond to some of these changes may be limited. |  |  |
| 10.1 Volcanoes | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.2 Earthquakes/Tsunamis | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.3 Avalanches/ Landslides | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.4 Erosion and siltation/ deposition (e.g. shoreline or riverbed changes) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 11. Climate change and severe weather |  |  |
| Threats from long-term climatic changes which may be linked to global warming and other severe climatic/weather events outside of the natural range of variation |  |  |
| 11.1 Habitat shifting and alteration | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 11.2 Droughts | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 11.3 Temperature extremes | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 11.4 Storms and flooding | - | 0: N/A 1: Low 2: Medium 3: High |
| 12. Specific cultural and social threats |  |  |
| 12.1 Loss of cultural links, traditional knowledge and/or management practices | - | 0: N/A 1: Low 2: Medium 3: High |
| 12.2 Natural deterioration of important cultural site values | - | 0: N/A 1: Low 2: Medium 3: High |
| 12.3 Destruction of cultural heritage buildings, gardens, sites etc | - | 0: N/A 1: Low 2: Medium 3: High |
| Assessment Form |  |  |
| 1. Legal status: Does the protected area have legal status (or in the case of private reserves is covered by a covenant or similar)? | 3 | 0: The protected area is not gazetted/covenanted 1: There is agreement that the protected area should be gazetted/covenanted but the process has not yet begun 2: The protected area is in the process of being gazetted/covenanted but the process is still incomplete (includes sites designated under international conventions, such as Ramsar, or local/traditional law such as community conserved areas, which do not yet have national legal status or covenant) 3: The protected area has been formally gazetted/covenanted |
| Comments and Next Steps |  |  |
| 2. Protected area regulations: Are appropriate regulations in place to control land use and activities (e.g. hunting)? | 1 | 0: There are no regulations for controlling land use and activities in the protected area 1: Some regulations for controlling land use and activities in the protected area exist but these are major weaknesses 2: Regulations for controlling land use and activities in the protected area exist but there are some weaknesses or gaps 3: Regulations for controlling inappropriate land use and activities in the protected area exist and provide an excellent basis for management |
| Comments and Next Steps |  |  |
| 3. Law Enforcement: Can staff (i.e. those with responsibility for managing the site) enforce protected area rules well enough? | 1 | 0: The staff have no effective capacity/resources to enforce protected area legislation and regulations 1: There are major deficiencies in staff capacity/resources to enforce protected area legislation and regulations (e.g. lack of skills, no patrol budget, lack of institutional support) 2: The staff have acceptable capacity/resources to enforce protected area legislation and regulations but some deficiencies remain 3: The staff have excellent capacity/resources to enforce protected area legislation and regulations |
| Comments and Next Steps |  |  |
| 4. Protected area objectives: Is management undertaken according to agreed objectives? | 3 | 0: No firm objectives have been agreed for the protected area 1: The protected area has agreed objectives, but is not managed according to these objectives 2: The protected area has agreed objectives, but is only partially managed according to these objectives 3: The protected area has agreed objectives and is managed to meet these objectives |
| Comments and Next Steps |  |  |
| 5. Protected area design: Is the protected area the right size and shape to protect species, habitats, ecological processes and water catchments of key conservation concern? | 2 | 0: Inadequacies in protected area design mean achieving the major objectives of the protected area is very difficult 1: Inadequacies in protected area design mean that achievement of major objectives is difficult but some mitigating actions are being taken (e.g. agreements with adjacent land owners for wildlife corridors or introduction of appropriate catchment management) 2: Protected area design is not significantly constraining achievement of objectives, but could be improved (e.g. with respect to larger scale ecological processes) 3: Protected area design helps achievement of objectives; it is appropriate for species and habitat conservation; and maintains ecological processes such as surface and groundwater flows at a catchment scale, natural disturbance patterns etc |
| Comments and Next Steps |  |  |
| 6. Protected area boundary demarcation: Is the boundary known and demarcated? | 1 | 0: The boundary of the protected area is not known by the management authority or local residents/neighbouring land users 1: The boundary of the protected area is known by the management authority but is not known by local residents/neighbouring land users 2: The boundary of the protected area is known by both the management authority and local residents/neighbouring land users but is not appropriately demarcated 3: The boundary of the protected area is known by the management authority and local residents/neighbouring land users and is appropriately demarcated |
| Comments and Next Steps |  |  |
| 7. Management plan: Is there a management plan and is it being implemented? | 2 | 0: There is no management plan for the protected area 1: A management plan is being prepared or has been prepared but is not being implemented 2: A management plan exists but it is only being partially implemented because of funding constraints or other problems 3: A management plan exists and is being implemented |
| Comments and Next Steps |  |  |
| 7.a Planning process: The planning process allows adequate opportunity for key stakeholders to influence the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.b Planning process: There is an established schedule and process for periodic review and updating of the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.c Planning process: The results of monitoring, research and evaluation are routinely incorporated into planning | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 8. Regular work plan: Is there a regular work plan and is it being implemented | 1 | 0: No regular work plan exists 1: A regular work plan exists but few of the activities are implemented 2: A regular work plan exists and many activities are implemented 3: A regular work plan exists and all activities are implemented |
| Comments and Next Steps |  |  |
| 9. Resource inventory: Do you have enough information to manage the area? | 1 | 0: There is little or no information available on the critical habitats, species and cultural values of the protected area 1: Information on the critical habitats, species, ecological processes and cultural values of the protected area is not sufficient to support planning and decision making 2: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient for most key areas of planning and decision making 3: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient to support all areas of planning and decision making |
| Comments and Next Steps |  |  |
| 10. Protection systems: Are systems in place to control access/resource use in the protected area? | 2 | 0: Protection systems (patrols, permits etc) do not exist or are not effective in controlling access/resource use 1: Protection systems are only partially effective in controlling access/resource use 2: Protection systems are moderately effective in controlling access/resource use 3: Protection systems are largely or wholly effective in controlling access/ resource use |
| Comments and Next Steps |  |  |
| 11. Research: Is there a programme of management-orientated survey and research work? | 3 | 0: There is no survey or research work taking place in the protected area 1: There is a small amount of survey and research work but it is not directed towards the needs of protected area management 2: There is considerable survey and research work but it is not directed towards the needs of protected area management 3:There is a comprehensive, integrated programme of survey and research work, which is relevant to management needs |
| Comments and Next Steps |  |  |
| 12. Resource management: Is active resource management being undertaken? | 2 | 0: Active resource management is not being undertaken 1: Very few of the requirements for active management of critical habitats, species, ecological processes and cultural values are being implemented 2: Many of the requirements for active management of critical habitats, species, ecological processes and, cultural values are being implemented but some key issues are not being addressed 3: Requirements for active management of critical habitats, species, ecological processes and, cultural values are being substantially or fully implemented |
| Comments and Next Steps |  |  |
| 13. Staff numbers: Are there enough people employed to manage the protected area? | 1 | 0: There are no staff 1: Staff numbers are inadequate for critical management activities 2: Staff numbers are below optimum level for critical management activities 3: Staff numbers are adequate for the management needs of the protected area |
| Comments and Next Steps |  |  |
| 14. Staff training: Are staff adequately trained to fulfill management objectives? | 1 | 0: Staff lack the skills needed for protected area management 1: Staff training and skills are low relative to the needs of the protected area 2: Staff training and skills are adequate, but could be further improved to fully achieve the objectives of management 3: Staff training and skills are aligned with the management needs of the protected area |
| Comments and Next Steps |  |  |
| 15. Current budget: Is the current budget sufficient? | 1 | 0: There is no budget for management of the protected area 1: The available budget is inadequate for basic management needs and presents a serious constraint to the capacity to manage 2: The available budget is acceptable but could be further improved to fully achieve effective management 3: The available budget is sufficient and meets the full management needs of the protected area |
| Comments and Next Steps |  |  |
| 16. Security of budget: Is the budget secure? | - | 0: There is no secure budget for the protected area and management is wholly reliant on outside or highly variable funding 1: There is very little secure budget and the protected area could not function adequately without outside funding 2: There is a reasonably secure core budget for regular operation of the protected area but many innovations and initiatives are reliant on outside funding 3: There is a secure budget for the protected area and its management needs |
| Comments and Next Steps |  |  |
| 17. Management of budget: Is the budget managed to meet critical management needs? | 1 | 0: Budget management is very poor and significantly undermines effectiveness (e.g. late release of budget in financial year) 1: Budget management is poor and constrains effectiveness 2: Budget management is adequate but could be improved 3: Budget management is excellent and meets management needs |
| Comments and Next Steps |  |  |
| 18. Equipment: Is equipment sufficient for management needs? | - | 0: There are little or no equipment and facilities for management needs 1: There are some equipment and facilities but these are inadequate for most management needs 2: There are equipment and facilities, but still some gaps that constrain management 3: There are adequate equipment and facilities |
| Comments and Next Steps |  |  |
| 19. Maintenance of equipment: Is equipment adequately maintained? | - | 0: There is little or no maintenance of equipment and facilities 1: There is some ad hoc maintenance of equipment and facilities 2: There is basic maintenance of equipment and facilities 3: Equipment and facilities are well maintained |
| Comments and Next Steps |  |  |
| 20. Education and awareness: Is there a planned education programme linked to the objectives and needs? | 2 | 0: There is no education and awareness programme 1: There is a limited and ad hoc education and awareness programme 2: There is an education and awareness programme but it only partly meets needs and could be improved 3: There is an appropriate and fully implemented education and awareness programme |
| Comments and Next Steps |  |  |
| 21. Planning for land and water use: Does land and water use planning recognise the protected area and aid the achievement of objectives? | 2 | 0: Adjacent land and water use planning does not take into account the needs of the protected area and activities/policies are detrimental to the survival of the area 1: Adjacent land and water use planning does not takes into account the long term needs of the protected area, but activities are not detrimental the area 2: Adjacent land and water use planning partially takes into account the long term needs of the protected area 3: Adjacent land and water use planning fully takes into account the long term needs of the protected area |
| Comments and Next Steps |  |  |
| 21a. Land and water planning for habitat conservation: Planning and management in the catchment or landscape containing the protected area incorporates provision for adequate environmental conditions (e.g. volume, quality and timing of water flow, air pollution levels etc) to sustain relevant habitats. | - | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21b. Land and water planning for habitat conservation: Management of corridors linking the protected area provides for wildlife passage to key habitats outside the protected area (e.g. to allow migratory fish to travel between freshwater spawning sites and the sea, or to allow animal migration). | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21c. Land and water planning for habitat conservation: "Planning adresses ecosystem-specific needs and/or the needs of particular species of concern at an ecosystem scale (e.g. volume, quality and timing of freshwater flow to sustain particular species, fire management to maintain savannah habitats etc.)" | - | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 22. State and commercial neighbours:Is there co-operation with adjacent land and water users? | - | 0: There is no contact between managers and neighbouring official or corporate land and water users 1: There is contact between managers and neighbouring official or corporate land and water users but little or no cooperation 2: There is contact between managers and neighbouring official or corporate land and water users, but only some co-operation 3: There is regular contact between managers and neighbouring official or corporate land and water users, and substantial co-operation on management |
| Comments and Next Steps |  |  |
| 23. Indigenous people: Do indigenous and traditional peoples resident or regularly using the protected area have input to management decisions? | 2 | 0: Indigenous and traditional peoples have no input into decisions relating to the management of the protected area 1: Indigenous and traditional peoples have some input into discussions relating to management but no direct role in management 2: Indigenous and traditional peoples directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Indigenous and traditional peoples directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24. Local communities: Do local communities resident or near the protected area have input to management decisions? | 3 | 0: Local communities have no input into decisions relating to the management of the protected area 1: Local communities have some input into discussions relating to management but no direct role in management 2: Local communities directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Local communities directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24 a. Impact on communities: There is open communication and trust between local and/or indigenous people, stakeholders and protected area managers | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 b. Impact on communities: Programmes to enhance community welfare, while conserving protected area resources, are being implemented | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 c. Impact on communities: Local and/or indigenous people actively support the protected area | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 25. Economic benefit: Is the protected area providing economic benefits to local communities, e.g. income, employment, payment for environmental services? | 2 | 0: The protected area does not deliver any economic benefits to local communities 1: Potential economic benefits are recognised and plans to realise these are being developed 2: There is some flow of economic benefits to local communities 3: There is a major flow of economic benefits to local communities from activities associated with the protected area |
| Comments and Next Steps |  |  |
| 26. Monitoring and evaluation: Are management activities monitored against performance? | 2 | 0: There is no monitoring and evaluation in the protected area 1: There is some ad hoc monitoring and evaluation, but no overall strategy and/or no regular collection of results 2: There is an agreed and implemented monitoring and evaluation system but results do not feed back into management 3: A good monitoring and evaluation system exists, is well implemented and used in adaptive management |
| Comments and Next Steps |  |  |
| 27. Visitor facilities: Are visitor facilities adequate? | 2 | 0: There are no visitor facilities and services despite an identified need 1: Visitor facilities and services are inappropriate for current levels of visitation 2: Visitor facilities and services are adequate for current levels of visitation but could be improved 3: Visitor facilities and services are excellent for current levels of visitation |
| Comments and Next Steps |  |  |
| 28. Commercial tourism operators: Do commercial tour operators contribute to protected area management? | 2 | 0: There is little or no contact between managers and tourism operators using the protected area 1: There is contact between managers and tourism operators but this is largely confined to administrative or regulatory matters 2: There is limited co-operation between managers and tourism operators to enhance visitor experiences and maintain protected area values 3: There is good co-operation between managers and tourism operators to enhance visitor experiences, and maintain protected area values |
| Comments and Next Steps |  |  |
| 29. Fees: If fees (i.e. entry fees or fines) are applied, do they help protected area management? | 2 | 0: Although fees are theoretically applied, they are not collected 1: Fees are collected, but make no contribution to the protected area or its environs 2: Fees are collected, and make some contribution to the protected area and its environs 3: Fees are collected and make a substantial contribution to the protected area and its environs |
| Comments and Next Steps |  |  |
| 30. Condition of values: What is the condition of the important values of the protected area as compared to when it was first designated? | 2 | 0: Many important biodiversity, ecological or cultural values are being severely degraded 1: Some biodiversity, ecological or cultural values are being severely degraded 2: Some biodiversity, ecological and cultural values are being partially degraded but the most important values have not been significantly impacted 3: Biodiversity, ecological and cultural values are predominantly intact |
| Comments and Next Steps |  |  |
| 30a: Condition of values: The assessment of the condition of values is based on research and/or monitoring | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30b: Condition of values Specific management programmes are being implemented to address threats to biodiversity, ecological and cultural values | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30c: Condition of values: Activities to maintain key biodiversity, ecological and cultural values are a routine part of park management | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| TOTAL SCORE | 57 | Pls add up numbers from assessment form (questions 1 to 30) |

| Tracking Tool for Biodiversity Projects in GEF-3, GEF-4, and GEF-5. |
| --- |
| Objective 1: Catalyzing Sustainability of Protected Area Systems |  |  |
| SECTION II: Management Effectiveness Tracking Tool for Protected Areas |  |  |
| Note: Please complete the management effectiveness tracking tool for EACH protected area that is the target of the GEF intervention and create a new worksheet for each. Structure and content of the Tracking Tool - Objective 1. Section II: The Tracking Tool has two main sections: datasheets and assessment form. Both sections should be completed. 1. Datasheets: the data sheet comprises of two separate sections: ü Data sheet 1: records details of the assessment and some basic information about the site, such as name, size and location etc. ü Data sheet 2: provides a generic list of threats which protected areas can face. On this data sheet the assessors are asked to identify threats and rank their impact on the protected area. 2. Assessment Form: the assessment is structured around 30 questions presented in table format which includes three columns for recording details of the assessment, all of which should be completed. |  |  |
| Important: Please read the Guidelines posted on the GEF website before entering your data |  |  |
| Data Sheet 1: Reporting Progress at Protected Area Sites | Please indicate your answer here | Notes |
| Name, affiliation and contact details for person responsible for completing the METT (email etc.) | Honorio Fernandes Pereira | Director do PNLC utomb60@yahoo.com.br |
| Date assessment carried out | 06/15/2012 | Month DD, YYYY (e.g., May 12, 2010) |
| Name of protected area | Lagoa de Cufada National Park (LCNP) |  |
| WDPA site code (these codes can be found on www.unep-wcmc.org/wdpa/) | 33048 |  |
| Designations(please choose 1-3) | 2 | 1: National 2: IUCN Category 3: International (please complete lines 35-69 as necessary ) |
| Country | Guinea-Bissau |  |
| Location of protected area (province and if possible map reference) | 11º 34´00 - 11º 55´06 N /14º 49´00 - 15º 16´00 W |  |
| Date of establishment | December 12th, 2007 |  |
| Ownership details (please choose 1-4) | 1 | 1: State 2: Private 3: Community 4: Other |
| Management Authority | Institute for Biodiversity and Protected Areas (IBAP) |  |
| Size of protected area (ha) | 89,000 |  |
| Number of Permanent staff | 13 |  |
| Number of Temporary staff | 2 |  |
| Annual budget (US$) for recurrent (operational) funds – excluding staff salary costs | Not specified |  |
| Annual budget (US$) for project or other supplementary funds – excluding staff salary costs | Not specified |  |
| What are the main values for which the area is designated | Integrate the largest basin for the retention of freshwater in the country |  |
| List the two primary protected area management objectives in below: |  |  |
| Management objective 1 | Preserve, conserve, and defend the marginal living systems of the Corubal, Great Buba, and Fulacunda rivers and ecosystems associated with dense sub-humid forest and the dry and semi-dry forest |  |
| Management objective 2 | Defend, enhance, and maintain the activities and traditional ways of life to protect the ecological heritage |  |
| No. of people involved in completing assessment | 15 |  |
| Including: (please choose 1-8) | 3 | 1: PA manager 2: PA staff 3: Other PA agency staff 4: Donors 5: NGOs 6: External experts 7: Local community 8: Other |
| Information on International Designations | Please indicate your answer here |  |
| UNESCO World Heritage site (see: http://whc.unesco.org/en/list) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical co-ordinates |  |  |
| Criteria for designation |  | (i.e. criteria i to x) |
| Statement of Outstanding Universal Value |  |  |
| Ramsar site (see: http://ramsar.wetlands.org) | RAMSAR 469 |  |
| Date Listed | 14/05 /90 |  |
| Site name | Lagoa de Cufada |  |
| Site area | 39,098 ha |  |
| Geographical number | 11°43'N 015°02'W |  |
| Reason for Designation (see Ramsar Information Sheet) | A large, permanent, freshwater lake, with abundant aquatic vegetation and adjoining river floodplain. Includes two smaller lakes, seasonally flooded marshes, fringing mangroves, and extensive mudflats. |  |
| UNESCO Man and Biosphere Reserves (see: http://www.unesco.org/new/en/natural-sciences/environment/ecological-sciences/man-and-biosphere-programme/ | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  | Total, Core, Buffe, and Transition |
| Geographical co-ordinates |  |  |
| Criteria for designation |  |  |
| Fulfilment of three functions of MAB |  | conservation, development and logistic support |
| Please list other designations (i.e. ASEAN Heritage, Natura 2000) and any supporting information below | NA |  |
|  |  | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
| Data Sheet 2: Protected Areas Threats (please complete a Data Sheet of threats and assessment for each protected area of the project). |  |  |
| Please choose all relevant existing threats as either of high, medium or low significance. Threats ranked as of high significance are those which are seriously degrading values; medium are those threats having some negative impact and those characterised as low are threats which are present but not seriously impacting values or N/A where the threat is not present or not applicable in the protected area. |  |  |
| 1. Residential and commercial development within a protected area |  |  |
| Threats from human settlements or other non-agricultural land uses with a substantial footprint |  |  |
| 1.1 Housing and settlement | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 1.2 Commercial and industrial areas | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 1.3 Tourism and recreation infrastructure | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2. Agriculture and aquaculture within a protected area |  |  |
| Threats from farming and grazing as a result of agricultural expansion and intensification, including silviculture, mariculture and aquaculture |  |  |
| 2.1 Annual and perennial non-timber crop cultivation | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 2.1a Drug cultivation | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.2 Wood and pulp plantations | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 2.3 Livestock farming and grazing | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2.4 Marine and freshwater aquaculture | - | 0: N/A 1: Low 2: Medium 3: High |
| 3. Energy production and mining within a protected area |  |  |
| Threats from production of non-biological resources |  |  |
| 3.1 Oil and gas drilling | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.2 Mining and quarrying | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.3 Energy generation, including from hydropower dams | - | 0: N/A 1: Low 2: Medium 3: High |
| 4. Transportation and service corridors within a protected area |  |  |
| Threats from long narrow transport corridors and the vehicles that use them including associated wildlife mortality |  |  |
| 4.1 Roads and railroads (include road-killed animals) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 4.2 Utility and service lines (e.g. electricity cables, telephone lines,) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.3 Shipping lanes and canals | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 4.4 Flight paths | - | 0: N/A 1: Low 2: Medium 3: High |
| 5. Biological resource use and harm within a protected area |  |  |
| Threats from consumptive use of "wild" biological resources including both deliberate and unintentional harvesting effects; also persecution or control of specific species (note this includes hunting and killing of animals) |  |  |
| 5.1 Hunting, killing and collecting terrestrial animals (including killing of animals as a result of human/wildlife conflict) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.2 Gathering terrestrial plants or plant products (non-timber) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.3 Logging and wood harvesting | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.4 Fishing, killing and harvesting aquatic resources | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6. Human intrusions and disturbance within a protected area |  |  |
| Threats from human activities that alter, destroy or disturb habitats and species associated with non-consumptive uses of biological resources |  |  |
| 6.1 Recreational activities and tourism | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6.2 War, civil unrest and military exercises | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.3 Research, education and other work-related activities in protected areas | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.4 Activities of protected area managers (e.g. construction or vehicle use, artificial watering points and dams) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6.5 Deliberate vandalism, destructive activities or threats to protected area staff and visitors | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7. Natural system modifications |  |  |
| Threats from other actions that convert or degrade habitat or change the way the ecosystem functions |  |  |
| 7.1 Fire and fire suppression (including arson) | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 7.2 Dams, hydrological modification and water management/use | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3a Increased fragmentation within protected area | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3b Isolation from other natural habitat (e.g. deforestation, dams without effective aquatic wildlife passages) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.3c Other ‘edge effects’ on park values | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3d Loss of keystone species (e.g. top predators, pollinators etc) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 8. Invasive and other problematic species and genes |  |  |
| Threats from terrestrial and aquatic non-native and native plants, animals, pathogens/microbes or genetic materials that have or are predicted to have harmful effects on biodiversity following introduction, spread and/or increase |  |  |
| 8.1 Invasive non-native/alien plants (weeds) | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 8.1a Invasive non-native/alien animals | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1b Pathogens (non-native or native but creating new/increased problems) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.2 Introduced genetic material (e.g. genetically modified organisms) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9. Pollution entering or generated within protected area |  |  |
| Threats from introduction of exotic and/or excess materials or energy from point and non-point sources |  |  |
| 9.1 Household sewage and urban waste water | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.1a Sewage and waste water from protected area facilities (e.g. toilets, hotels etc) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 9.2 Industrial, mining and military effluents and discharges (e.g. poor water quality discharge from dams, e.g. unnatural temperatures, de-oxygenated, other pollution) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.3 Agricultural and forestry effluents (e.g. excess fertilizers or pesticides) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.4 Garbage and solid waste | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.5 Air-borne pollutants | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.6 Excess energy (e.g. heat pollution, lights etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 10. Geological events |  |  |
| Geological events may be part of natural disturbance regimes in many ecosystems. But they can be a threat if a species or habitat is damaged and has lost its resilience and is vulnerable to disturbance. Management capacity to respond to some of these changes may be limited. |  |  |
| 10.1 Volcanoes | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.2 Earthquakes/Tsunamis | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.3 Avalanches/ Landslides | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.4 Erosion and siltation/ deposition (e.g. shoreline or riverbed changes) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 11. Climate change and severe weather |  |  |
| Threats from long-term climatic changes which may be linked to global warming and other severe climatic/weather events outside of the natural range of variation |  |  |
| 11.1 Habitat shifting and alteration | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.2 Droughts | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.3 Temperature extremes | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.4 Storms and flooding | - | 0: N/A 1: Low 2: Medium 3: High |
| 12. Specific cultural and social threats |  |  |
| 12.1 Loss of cultural links, traditional knowledge and/or management practices | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 12.2 Natural deterioration of important cultural site values | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 12.3 Destruction of cultural heritage buildings, gardens, sites etc | 1 | 0: N/A 1: Low 2: Medium 3: High |
| Assessment Form |  |  |
| 1. Legal status: Does the protected area have legal status (or in the case of private reserves is covered by a covenant or similar)? | 3 | 0: The protected area is not gazetted/covenanted 1: There is agreement that the protected area should be gazetted/covenanted but the process has not yet begun 2: The protected area is in the process of being gazetted/covenanted but the process is still incomplete (includes sites designated under international conventions, such as Ramsar, or local/traditional law such as community conserved areas, which do not yet have national legal status or covenant) 3: The protected area has been formally gazetted/covenanted |
| Comments and Next Steps |  |  |
| 2. Protected area regulations: Are appropriate regulations in place to control land use and activities (e.g. hunting)? | 3 | 0: There are no regulations for controlling land use and activities in the protected area 1: Some regulations for controlling land use and activities in the protected area exist but these are major weaknesses 2: Regulations for controlling land use and activities in the protected area exist but there are some weaknesses or gaps 3: Regulations for controlling inappropriate land use and activities in the protected area exist and provide an excellent basis for management |
| Comments and Next Steps |  |  |
| 3. Law Enforcement: Can staff (i.e. those with responsibility for managing the site) enforce protected area rules well enough? | 3 | 0: The staff have no effective capacity/resources to enforce protected area legislation and regulations 1: There are major deficiencies in staff capacity/resources to enforce protected area legislation and regulations (e.g. lack of skills, no patrol budget, lack of institutional support) 2: The staff have acceptable capacity/resources to enforce protected area legislation and regulations but some deficiencies remain 3: The staff have excellent capacity/resources to enforce protected area legislation and regulations |
| Comments and Next Steps |  |  |
| 4. Protected area objectives: Is management undertaken according to agreed objectives? | 2 | 0: No firm objectives have been agreed for the protected area 1: The protected area has agreed objectives, but is not managed according to these objectives 2: The protected area has agreed objectives, but is only partially managed according to these objectives 3: The protected area has agreed objectives and is managed to meet these objectives |
| Comments and Next Steps |  |  |
| 5. Protected area design: Is the protected area the right size and shape to protect species, habitats, ecological processes and water catchments of key conservation concern? | 2 | 0: Inadequacies in protected area design mean achieving the major objectives of the protected area is very difficult 1: Inadequacies in protected area design mean that achievement of major objectives is difficult but some mitigating actions are being taken (e.g. agreements with adjacent land owners for wildlife corridors or introduction of appropriate catchment management) 2: Protected area design is not significantly constraining achievement of objectives, but could be improved (e.g. with respect to larger scale ecological processes) 3: Protected area design helps achievement of objectives; it is appropriate for species and habitat conservation; and maintains ecological processes such as surface and groundwater flows at a catchment scale, natural disturbance patterns etc |
| Comments and Next Steps |  |  |
| 6. Protected area boundary demarcation: Is the boundary known and demarcated? | 2 | 0: The boundary of the protected area is not known by the management authority or local residents/neighbouring land users 1: The boundary of the protected area is known by the management authority but is not known by local residents/neighbouring land users 2: The boundary of the protected area is known by both the management authority and local residents/neighbouring land users but is not appropriately demarcated 3: The boundary of the protected area is known by the management authority and local residents/neighbouring land users and is appropriately demarcated |
| Comments and Next Steps |  |  |
| 7. Management plan: Is there a management plan and is it being implemented? | 3 | 0: There is no management plan for the protected area 1: A management plan is being prepared or has been prepared but is not being implemented 2: A management plan exists but it is only being partially implemented because of funding constraints or other problems 3: A management plan exists and is being implemented |
| Comments and Next Steps |  |  |
| 7.a Planning process: The planning process allows adequate opportunity for key stakeholders to influence the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.b Planning process: There is an established schedule and process for periodic review and updating of the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.c Planning process: The results of monitoring, research and evaluation are routinely incorporated into planning | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 8. Regular work plan: Is there a regular work plan and is it being implemented | 2 | 0: No regular work plan exists 1: A regular work plan exists but few of the activities are implemented 2: A regular work plan exists and many activities are implemented 3: A regular work plan exists and all activities are implemented |
| Comments and Next Steps |  |  |
| 9. Resource inventory: Do you have enough information to manage the area? | 2 | 0: There is little or no information available on the critical habitats, species and cultural values of the protected area 1: Information on the critical habitats, species, ecological processes and cultural values of the protected area is not sufficient to support planning and decision making 2: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient for most key areas of planning and decision making 3: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient to support all areas of planning and decision making |
| Comments and Next Steps |  |  |
| 10. Protection systems: Are systems in place to control access/resource use in the protected area? | 2 | 0: Protection systems (patrols, permits etc) do not exist or are not effective in controlling access/resource use 1: Protection systems are only partially effective in controlling access/resource use 2: Protection systems are moderately effective in controlling access/resource use 3: Protection systems are largely or wholly effective in controlling access/ resource use |
| Comments and Next Steps |  |  |
| 11. Research: Is there a programme of management-orientated survey and research work? | 2 | 0: There is no survey or research work taking place in the protected area 1: There is a small amount of survey and research work but it is not directed towards the needs of protected area management 2: There is considerable survey and research work but it is not directed towards the needs of protected area management 3:There is a comprehensive, integrated programme of survey and research work, which is relevant to management needs |
| Comments and Next Steps |  |  |
| 12. Resource management: Is active resource management being undertaken? | 2 | 0: Active resource management is not being undertaken 1: Very few of the requirements for active management of critical habitats, species, ecological processes and cultural values are being implemented 2: Many of the requirements for active management of critical habitats, species, ecological processes and, cultural values are being implemented but some key issues are not being addressed 3: Requirements for active management of critical habitats, species, ecological processes and, cultural values are being substantially or fully implemented |
| Comments and Next Steps |  |  |
| 13. Staff numbers: Are there enough people employed to manage the protected area? | 2 | 0: There are no staff 1: Staff numbers are inadequate for critical management activities 2: Staff numbers are below optimum level for critical management activities 3: Staff numbers are adequate for the management needs of the protected area |
| Comments and Next Steps |  |  |
| 14. Staff training: Are staff adequately trained to fulfill management objectives? | 2 | 0: Staff lack the skills needed for protected area management 1: Staff training and skills are low relative to the needs of the protected area 2: Staff training and skills are adequate, but could be further improved to fully achieve the objectives of management 3: Staff training and skills are aligned with the management needs of the protected area |
| Comments and Next Steps |  |  |
| 15. Current budget: Is the current budget sufficient? | 2 | 0: There is no budget for management of the protected area 1: The available budget is inadequate for basic management needs and presents a serious constraint to the capacity to manage 2: The available budget is acceptable but could be further improved to fully achieve effective management 3: The available budget is sufficient and meets the full management needs of the protected area |
| Comments and Next Steps |  |  |
| 16. Security of budget: Is the budget secure? | 2 | 0: There is no secure budget for the protected area and management is wholly reliant on outside or highly variable funding 1: There is very little secure budget and the protected area could not function adequately without outside funding 2: There is a reasonably secure core budget for regular operation of the protected area but many innovations and initiatives are reliant on outside funding 3: There is a secure budget for the protected area and its management needs |
| Comments and Next Steps |  |  |
| 17. Management of budget: Is the budget managed to meet critical management needs? | 2 | 0: Budget management is very poor and significantly undermines effectiveness (e.g. late release of budget in financial year) 1: Budget management is poor and constrains effectiveness 2: Budget management is adequate but could be improved 3: Budget management is excellent and meets management needs |
| Comments and Next Steps |  |  |
| 18. Equipment: Is equipment sufficient for management needs? | 2 | 0: There are little or no equipment and facilities for management needs 1: There are some equipment and facilities but these are inadequate for most management needs 2: There are equipment and facilities, but still some gaps that constrain management 3: There are adequate equipment and facilities |
| Comments and Next Steps |  |  |
| 19. Maintenance of equipment: Is equipment adequately maintained? | 2 | 0: There is little or no maintenance of equipment and facilities 1: There is some ad hoc maintenance of equipment and facilities 2: There is basic maintenance of equipment and facilities 3: Equipment and facilities are well maintained |
| Comments and Next Steps |  |  |
| 20. Education and awareness: Is there a planned education programme linked to the objectives and needs? | 2 | 0: There is no education and awareness programme 1: There is a limited and ad hoc education and awareness programme 2: There is an education and awareness programme but it only partly meets needs and could be improved 3: There is an appropriate and fully implemented education and awareness programme |
| Comments and Next Steps |  |  |
| 21. Planning for land and water use: Does land and water use planning recognise the protected area and aid the achievement of objectives? | 2 | 0: Adjacent land and water use planning does not take into account the needs of the protected area and activities/policies are detrimental to the survival of the area 1: Adjacent land and water use planning does not takes into account the long term needs of the protected area, but activities are not detrimental the area 2: Adjacent land and water use planning partially takes into account the long term needs of the protected area 3: Adjacent land and water use planning fully takes into account the long term needs of the protected area |
| Comments and Next Steps |  |  |
| 21a. Land and water planning for habitat conservation: Planning and management in the catchment or landscape containing the protected area incorporates provision for adequate environmental conditions (e.g. volume, quality and timing of water flow, air pollution levels etc) to sustain relevant habitats. | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21b. Land and water planning for habitat conservation: Management of corridors linking the protected area provides for wildlife passage to key habitats outside the protected area (e.g. to allow migratory fish to travel between freshwater spawning sites and the sea, or to allow animal migration). | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21c. Land and water planning for habitat conservation: "Planning adresses ecosystem-specific needs and/or the needs of particular species of concern at an ecosystem scale (e.g. volume, quality and timing of freshwater flow to sustain particular species, fire management to maintain savannah habitats etc.)" | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 22. State and commercial neighbours:Is there co-operation with adjacent land and water users? | 2 | 0: There is no contact between managers and neighbouring official or corporate land and water users 1: There is contact between managers and neighbouring official or corporate land and water users but little or no cooperation 2: There is contact between managers and neighbouring official or corporate land and water users, but only some co-operation 3: There is regular contact between managers and neighbouring official or corporate land and water users, and substantial co-operation on management |
| Comments and Next Steps |  |  |
| 23. Indigenous people: Do indigenous and traditional peoples resident or regularly using the protected area have input to management decisions? | 3 | 0: Indigenous and traditional peoples have no input into decisions relating to the management of the protected area 1: Indigenous and traditional peoples have some input into discussions relating to management but no direct role in management 2: Indigenous and traditional peoples directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Indigenous and traditional peoples directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24. Local communities: Do local communities resident or near the protected area have input to management decisions? | 3 | 0: Local communities have no input into decisions relating to the management of the protected area 1: Local communities have some input into discussions relating to management but no direct role in management 2: Local communities directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Local communities directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24 a. Impact on communities: There is open communication and trust between local and/or indigenous people, stakeholders and protected area managers | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 b. Impact on communities: Programmes to enhance community welfare, while conserving protected area resources, are being implemented | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 c. Impact on communities: Local and/or indigenous people actively support the protected area | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 25. Economic benefit: Is the protected area providing economic benefits to local communities, e.g. income, employment, payment for environmental services? | 3 | 0: The protected area does not deliver any economic benefits to local communities 1: Potential economic benefits are recognised and plans to realise these are being developed 2: There is some flow of economic benefits to local communities 3: There is a major flow of economic benefits to local communities from activities associated with the protected area |
| Comments and Next Steps |  |  |
| 26. Monitoring and evaluation: Are management activities monitored against performance? | 2 | 0: There is no monitoring and evaluation in the protected area 1: There is some ad hoc monitoring and evaluation, but no overall strategy and/or no regular collection of results 2: There is an agreed and implemented monitoring and evaluation system but results do not feed back into management 3: A good monitoring and evaluation system exists, is well implemented and used in adaptive management |
| Comments and Next Steps |  |  |
| 27. Visitor facilities: Are visitor facilities adequate? | 1 | 0: There are no visitor facilities and services despite an identified need 1: Visitor facilities and services are inappropriate for current levels of visitation 2: Visitor facilities and services are adequate for current levels of visitation but could be improved 3: Visitor facilities and services are excellent for current levels of visitation |
| Comments and Next Steps |  |  |
| 28. Commercial tourism operators: Do commercial tour operators contribute to protected area management? | - | 0: There is little or no contact between managers and tourism operators using the protected area 1: There is contact between managers and tourism operators but this is largely confined to administrative or regulatory matters 2: There is limited co-operation between managers and tourism operators to enhance visitor experiences and maintain protected area values 3: There is good co-operation between managers and tourism operators to enhance visitor experiences, and maintain protected area values |
| Comments and Next Steps |  |  |
| 29. Fees: If fees (i.e. entry fees or fines) are applied, do they help protected area management? | 3 | 0: Although fees are theoretically applied, they are not collected 1: Fees are collected, but make no contribution to the protected area or its environs 2: Fees are collected, and make some contribution to the protected area and its environs 3: Fees are collected and make a substantial contribution to the protected area and its environs |
| Comments and Next Steps |  |  |
| 30. Condition of values: What is the condition of the important values of the protected area as compared to when it was first designated? | 2 | 0: Many important biodiversity, ecological or cultural values are being severely degraded 1: Some biodiversity, ecological or cultural values are being severely degraded 2: Some biodiversity, ecological and cultural values are being partially degraded but the most important values have not been significantly impacted 3: Biodiversity, ecological and cultural values are predominantly intact |
| Comments and Next Steps |  |  |
| 30a: Condition of values: The assessment of the condition of values is based on research and/or monitoring | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30b: Condition of values Specific management programmes are being implemented to address threats to biodiversity, ecological and cultural values | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30c: Condition of values: Activities to maintain key biodiversity, ecological and cultural values are a routine part of park management | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| TOTAL SCORE | 77 | Pls add up numbers from assessment form (questions 1 to 30) |

| Tracking Tool for Biodiversity Projects in GEF-3, GEF-4, and GEF-5 |  |  |
| --- | --- | --- |
| Objective 1: Catalyzing Sustainability of Protected Area Systems |  |  |
| SECTION II: Management Effectiveness Tracking Tool for Protected Areas |  |  |
| Note: Please complete the management effectiveness tracking tool for EACH protected area that is the target of the GEF intervention and create a new worksheet for each. Structure and content of the Tracking Tool - Objective 1. Section II: The Tracking Tool has two main sections: datasheets and assessment form. Both sections should be completed. 1. Datasheets: the data sheet comprises of two separate sections: ü Data sheet 1: records details of the assessment and some basic information about the site, such as name, size and location etc. ü Data sheet 2: provides a generic list of threats which protected areas can face. On this data sheet the assessors are asked to identify threats and rank their impact on the protected area. 2. Assessment Form: the assessment is structured around 30 questions presented in table format which includes three columns for recording details of the assessment, all of which should be completed. |  |  |
| Important: Please read the Guidelines posted on the GEF website before entering your data |  |  |
| Data Sheet 1: Reporting Progress at Protected Area Sites | Please indicate your answer here | Notes |
| Name, affiliation and contact details for person responsible for completing the METT (email etc.) | Fernando Biag (fernandobiag@hotmail.com) |  |
| Date assessment carried out | Not specified | Month DD, YYYY (e.g., May 12, 2010) |
| Name of protected area | Tarafes do Rio Cacheu National Park (TCNP) |  |
| WDPA site code (these codes can be found on www.unep-wcmc.org/wdpa/) |  |  |
| Designations(please choose 1-3) | 2 | 1: National 2: IUCN Category 3: International (please complete lines 35-69 as necessary ) |
| Country | Guinea-Bissau |  |
| Location of protected area (province and if possible map reference) | 12°10´-12°25´N e 15°55´-16°27´W Regiao Administrativa de Cacheu |  |
| Date of establishment |  |  |
| Ownership details (please choose 1-4) | 1 | 1: State 2: Private 3: Community 4: Other |
| Management Authority | Institute for Biodiversity and Protected Areas (IBAP) |  |
| Size of protected area (ha) | 80,000 |  |
| Number of Permanent staff | 18 |  |
| Number of Temporary staff | 2 |  |
| Annual budget (US$) for recurrent (operational) funds – excluding staff salary costs | Not specified |  |
| Annual budget (US$) for project or other supplementary funds – excluding staff salary costs | Not specified |  |
| What are the main values for which the area is designated | Largest patches of mangroves in West Africa | Fauna amplamente representativa e variada |
| List the two primary protected area management objectives in below: |  |  |
| Management objective 1 | Conservation of mangrove ecosystem |  |
| Management objective 2 | Promotion of community development through BD-related products |  |
| No. of people involved in completing assessment | Not reported |  |
| Including: (please choose 1-8) | 3 | 1: PA manager 2: PA staff 3: Other PA agency staff 4: Donors 5: NGOs 6: External experts 7: Local community 8: Other |
| Information on International Designations | Please indicate your answer here |  |
| UNESCO World Heritage site (see: http://whc.unesco.org/en/list) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical co-ordinates |  |  |
| Criteria for designation |  | (i.e. criteria i to x) |
| Statement of Outstanding Universal Value |  |  |
| Ramsar site (see: http://ramsar.wetlands.org) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical number |  |  |
| Reason for Designation (see Ramsar Information Sheet) |  |  |
| UNESCO Man and Biosphere Reserves (see: http://www.unesco.org/new/en/natural-sciences/environment/ecological-sciences/man-and-biosphere-programme/ | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  | Total, Core, Buffe, and Transition |
| Geographical co-ordinates |  |  |
| Criteria for designation |  |  |
| Fulfilment of three functions of MAB |  | conservation, development and logistic support |
| Please list other designations (i.e. ASEAN Heritage, Natura 2000) and any supporting information below | NA |  |
|  |  | Name: |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
| Data Sheet 2: Protected Areas Threats (please complete a Data Sheet of threats and assessment for each protected area of the project). |  |  |
| Please choose all relevant existing threats as either of high, medium or low significance. Threats ranked as of high significance are those which are seriously degrading values; medium are those threats having some negative impact and those characterised as low are threats which are present but not seriously impacting values or N/A where the threat is not present or not applicable in the protected area. |  |  |
| 1. Residential and commercial development within a protected area |  |  |
| Threats from human settlements or other non-agricultural land uses with a substantial footprint |  |  |
| 1.1 Housing and settlement | 2 | 0: N/A 1: Low 2: Medium 3: High |
| 1.2 Commercial and industrial areas | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 1.3 Tourism and recreation infrastructure | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2. Agriculture and aquaculture within a protected area |  |  |
| Threats from farming and grazing as a result of agricultural expansion and intensification, including silviculture, mariculture and aquaculture |  |  |
| 2.1 Annual and perennial non-timber crop cultivation | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2.1a Drug cultivation | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.2 Wood and pulp plantations | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.3 Livestock farming and grazing | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.4 Marine and freshwater aquaculture | - | 0: N/A 1: Low 2: Medium 3: High |
| 3. Energy production and mining within a protected area |  |  |
| Threats from production of non-biological resources |  |  |
| 3.1 Oil and gas drilling | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.2 Mining and quarrying | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 3.3 Energy generation, including from hydropower dams | - | 0: N/A 1: Low 2: Medium 3: High |
| 4. Transportation and service corridors within a protected area |  |  |
| Threats from long narrow transport corridors and the vehicles that use them including associated wildlife mortality |  |  |
| 4.1 Roads and railroads (include road-killed animals) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.2 Utility and service lines (e.g. electricity cables, telephone lines,) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.3 Shipping lanes and canals | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 4.4 Flight paths | - | 0: N/A 1: Low 2: Medium 3: High |
| 5. Biological resource use and harm within a protected area |  |  |
| Threats from consumptive use of "wild" biological resources including both deliberate and unintentional harvesting effects; also persecution or control of specific species (note this includes hunting and killing of animals) |  |  |
| 5.1 Hunting, killing and collecting terrestrial animals (including killing of animals as a result of human/wildlife conflict) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.2 Gathering terrestrial plants or plant products (non-timber) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.3 Logging and wood harvesting | - | 0: N/A 1: Low 2: Medium 3: High |
| 5.4 Fishing, killing and harvesting aquatic resources | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6. Human intrusions and disturbance within a protected area |  |  |
| Threats from human activities that alter, destroy or disturb habitats and species associated with non-consumptive uses of biological resources |  |  |
| 6.1 Recreational activities and tourism | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6.2 War, civil unrest and military exercises | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.3 Research, education and other work-related activities in protected areas | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.4 Activities of protected area managers (e.g. construction or vehicle use, artificial watering points and dams) | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.5 Deliberate vandalism, destructive activities or threats to protected area staff and visitors | - | 0: N/A 1: Low 2: Medium 3: High |
| 7. Natural system modifications |  |  |
| Threats from other actions that convert or degrade habitat or change the way the ecosystem functions |  |  |
| 7.1 Fire and fire suppression (including arson) | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.2 Dams, hydrological modification and water management/use | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3a Increased fragmentation within protected area | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3b Isolation from other natural habitat (e.g. deforestation, dams without effective aquatic wildlife passages) | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3c Other ‘edge effects’ on park values | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3d Loss of keystone species (e.g. top predators, pollinators etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8. Invasive and other problematic species and genes |  |  |
| Threats from terrestrial and aquatic non-native and native plants, animals, pathogens/microbes or genetic materials that have or are predicted to have harmful effects on biodiversity following introduction, spread and/or increase |  |  |
| 8.1 Invasive non-native/alien plants (weeds) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1a Invasive non-native/alien animals | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1b Pathogens (non-native or native but creating new/increased problems) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.2 Introduced genetic material (e.g. genetically modified organisms) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9. Pollution entering or generated within protected area |  |  |
| Threats from introduction of exotic and/or excess materials or energy from point and non-point sources |  |  |
| 9.1 Household sewage and urban waste water | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.1a Sewage and waste water from protected area facilities (e.g. toilets, hotels etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.2 Industrial, mining and military effluents and discharges (e.g. poor water quality discharge from dams, e.g. unnatural temperatures, de-oxygenated, other pollution) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.3 Agricultural and forestry effluents (e.g. excess fertilizers or pesticides) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.4 Garbage and solid waste | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.5 Air-borne pollutants | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.6 Excess energy (e.g. heat pollution, lights etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 10. Geological events |  |  |
| Geological events may be part of natural disturbance regimes in many ecosystems. But they can be a threat if a species or habitat is damaged and has lost its resilience and is vulnerable to disturbance. Management capacity to respond to some of these changes may be limited. |  |  |
| 10.1 Volcanoes | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.2 Earthquakes/Tsunamis | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.3 Avalanches/ Landslides | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.4 Erosion and siltation/ deposition (e.g. shoreline or riverbed changes) | - | 0: N/A 1: Low 2: Medium 3: High |
| 11. Climate change and severe weather |  |  |
| Threats from long-term climatic changes which may be linked to global warming and other severe climatic/weather events outside of the natural range of variation |  |  |
| 11.1 Habitat shifting and alteration | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.2 Droughts | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.3 Temperature extremes | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.4 Storms and flooding | - | 0: N/A 1: Low 2: Medium 3: High |
| 12. Specific cultural and social threats |  |  |
| 12.1 Loss of cultural links, traditional knowledge and/or management practices | - | 0: N/A 1: Low 2: Medium 3: High |
| 12.2 Natural deterioration of important cultural site values | - | 0: N/A 1: Low 2: Medium 3: High |
| 12.3 Destruction of cultural heritage buildings, gardens, sites etc | - | 0: N/A 1: Low 2: Medium 3: High |
| Assessment Form |  |  |
| 1. Legal status: Does the protected area have legal status (or in the case of private reserves is covered by a covenant or similar)? | 3 | 0: The protected area is not gazetted/covenanted 1: There is agreement that the protected area should be gazetted/covenanted but the process has not yet begun 2: The protected area is in the process of being gazetted/covenanted but the process is still incomplete (includes sites designated under international conventions, such as Ramsar, or local/traditional law such as community conserved areas, which do not yet have national legal status or covenant) 3: The protected area has been formally gazetted/covenanted |
| Comments and Next Steps |  |  |
| 2. Protected area regulations: Are appropriate regulations in place to control land use and activities (e.g. hunting)? | 3 | 0: There are no regulations for controlling land use and activities in the protected area 1: Some regulations for controlling land use and activities in the protected area exist but these are major weaknesses 2: Regulations for controlling land use and activities in the protected area exist but there are some weaknesses or gaps 3: Regulations for controlling inappropriate land use and activities in the protected area exist and provide an excellent basis for management |
| Comments and Next Steps |  |  |
| 3. Law Enforcement: Can staff (i.e. those with responsibility for managing the site) enforce protected area rules well enough? | 3 | 0: The staff have no effective capacity/resources to enforce protected area legislation and regulations 1: There are major deficiencies in staff capacity/resources to enforce protected area legislation and regulations (e.g. lack of skills, no patrol budget, lack of institutional support) 2: The staff have acceptable capacity/resources to enforce protected area legislation and regulations but some deficiencies remain 3: The staff have excellent capacity/resources to enforce protected area legislation and regulations |
| Comments and Next Steps |  |  |
| 4. Protected area objectives: Is management undertaken according to agreed objectives? | 3 | 0: No firm objectives have been agreed for the protected area 1: The protected area has agreed objectives, but is not managed according to these objectives 2: The protected area has agreed objectives, but is only partially managed according to these objectives 3: The protected area has agreed objectives and is managed to meet these objectives |
| Comments and Next Steps |  |  |
| 5. Protected area design: Is the protected area the right size and shape to protect species, habitats, ecological processes and water catchments of key conservation concern? | 3 | 0: Inadequacies in protected area design mean achieving the major objectives of the protected area is very difficult 1: Inadequacies in protected area design mean that achievement of major objectives is difficult but some mitigating actions are being taken (e.g. agreements with adjacent land owners for wildlife corridors or introduction of appropriate catchment management) 2: Protected area design is not significantly constraining achievement of objectives, but could be improved (e.g. with respect to larger scale ecological processes) 3: Protected area design helps achievement of objectives; it is appropriate for species and habitat conservation; and maintains ecological processes such as surface and groundwater flows at a catchment scale, natural disturbance patterns etc |
| Comments and Next Steps |  |  |
| 6. Protected area boundary demarcation: Is the boundary known and demarcated? | 2 | 0: The boundary of the protected area is not known by the management authority or local residents/neighbouring land users 1: The boundary of the protected area is known by the management authority but is not known by local residents/neighbouring land users 2: The boundary of the protected area is known by both the management authority and local residents/neighbouring land users but is not appropriately demarcated 3: The boundary of the protected area is known by the management authority and local residents/neighbouring land users and is appropriately demarcated |
| Comments and Next Steps |  |  |
| 7. Management plan: Is there a management plan and is it being implemented? | 2 | 0: There is no management plan for the protected area 1: A management plan is being prepared or has been prepared but is not being implemented 2: A management plan exists but it is only being partially implemented because of funding constraints or other problems 3: A management plan exists and is being implemented |
| Comments and Next Steps |  |  |
| 7.a Planning process: The planning process allows adequate opportunity for key stakeholders to influence the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.b Planning process: There is an established schedule and process for periodic review and updating of the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.c Planning process: The results of monitoring, research and evaluation are routinely incorporated into planning | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 8. Regular work plan: Is there a regular work plan and is it being implemented | 2 | 0: No regular work plan exists 1: A regular work plan exists but few of the activities are implemented 2: A regular work plan exists and many activities are implemented 3: A regular work plan exists and all activities are implemented |
| Comments and Next Steps |  |  |
| 9. Resource inventory: Do you have enough information to manage the area? | 2 | 0: There is little or no information available on the critical habitats, species and cultural values of the protected area 1: Information on the critical habitats, species, ecological processes and cultural values of the protected area is not sufficient to support planning and decision making 2: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient for most key areas of planning and decision making 3: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient to support all areas of planning and decision making |
| Comments and Next Steps |  |  |
| 10. Protection systems: Are systems in place to control access/resource use in the protected area? | 2 | 0: Protection systems (patrols, permits etc) do not exist or are not effective in controlling access/resource use 1: Protection systems are only partially effective in controlling access/resource use 2: Protection systems are moderately effective in controlling access/resource use 3: Protection systems are largely or wholly effective in controlling access/ resource use |
| Comments and Next Steps |  |  |
| 11. Research: Is there a programme of management-orientated survey and research work? | 2 | 0: There is no survey or research work taking place in the protected area 1: There is a small amount of survey and research work but it is not directed towards the needs of protected area management 2: There is considerable survey and research work but it is not directed towards the needs of protected area management 3:There is a comprehensive, integrated programme of survey and research work, which is relevant to management needs |
| Comments and Next Steps |  |  |
| 12. Resource management: Is active resource management being undertaken? | 2 | 0: Active resource management is not being undertaken 1: Very few of the requirements for active management of critical habitats, species, ecological processes and cultural values are being implemented 2: Many of the requirements for active management of critical habitats, species, ecological processes and, cultural values are being implemented but some key issues are not being addressed 3: Requirements for active management of critical habitats, species, ecological processes and, cultural values are being substantially or fully implemented |
| Comments and Next Steps |  |  |
| 13. Staff numbers: Are there enough people employed to manage the protected area? | 2 | 0: There are no staff 1: Staff numbers are inadequate for critical management activities 2: Staff numbers are below optimum level for critical management activities 3: Staff numbers are adequate for the management needs of the protected area |
| Comments and Next Steps |  |  |
| 14. Staff training: Are staff adequately trained to fulfill management objectives? | 3 | 0: Staff lack the skills needed for protected area management 1: Staff training and skills are low relative to the needs of the protected area 2: Staff training and skills are adequate, but could be further improved to fully achieve the objectives of management 3: Staff training and skills are aligned with the management needs of the protected area |
| Comments and Next Steps |  |  |
| 15. Current budget: Is the current budget sufficient? | 2 | 0: There is no budget for management of the protected area 1: The available budget is inadequate for basic management needs and presents a serious constraint to the capacity to manage 2: The available budget is acceptable but could be further improved to fully achieve effective management 3: The available budget is sufficient and meets the full management needs of the protected area |
| Comments and Next Steps |  |  |
| 16. Security of budget: Is the budget secure? | 2 | 0: There is no secure budget for the protected area and management is wholly reliant on outside or highly variable funding 1: There is very little secure budget and the protected area could not function adequately without outside funding 2: There is a reasonably secure core budget for regular operation of the protected area but many innovations and initiatives are reliant on outside funding 3: There is a secure budget for the protected area and its management needs |
| Comments and Next Steps |  |  |
| 17. Management of budget: Is the budget managed to meet critical management needs? | 2 | 0: Budget management is very poor and significantly undermines effectiveness (e.g. late release of budget in financial year) 1: Budget management is poor and constrains effectiveness 2: Budget management is adequate but could be improved 3: Budget management is excellent and meets management needs |
| Comments and Next Steps |  |  |
| 18. Equipment: Is equipment sufficient for management needs? | 2 | 0: There are little or no equipment and facilities for management needs 1: There are some equipment and facilities but these are inadequate for most management needs 2: There are equipment and facilities, but still some gaps that constrain management 3: There are adequate equipment and facilities |
| Comments and Next Steps |  |  |
| 19. Maintenance of equipment: Is equipment adequately maintained? | 2 | 0: There is little or no maintenance of equipment and facilities 1: There is some ad hoc maintenance of equipment and facilities 2: There is basic maintenance of equipment and facilities 3: Equipment and facilities are well maintained |
| Comments and Next Steps |  |  |
| 20. Education and awareness: Is there a planned education programme linked to the objectives and needs? | 2 | 0: There is no education and awareness programme 1: There is a limited and ad hoc education and awareness programme 2: There is an education and awareness programme but it only partly meets needs and could be improved 3: There is an appropriate and fully implemented education and awareness programme |
| Comments and Next Steps |  |  |
| 21. Planning for land and water use: Does land and water use planning recognise the protected area and aid the achievement of objectives? | 2 | 0: Adjacent land and water use planning does not take into account the needs of the protected area and activities/policies are detrimental to the survival of the area 1: Adjacent land and water use planning does not takes into account the long term needs of the protected area, but activities are not detrimental the area 2: Adjacent land and water use planning partially takes into account the long term needs of the protected area 3: Adjacent land and water use planning fully takes into account the long term needs of the protected area |
| Comments and Next Steps |  |  |
| 21a. Land and water planning for habitat conservation: Planning and management in the catchment or landscape containing the protected area incorporates provision for adequate environmental conditions (e.g. volume, quality and timing of water flow, air pollution levels etc) to sustain relevant habitats. | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21b. Land and water planning for habitat conservation: Management of corridors linking the protected area provides for wildlife passage to key habitats outside the protected area (e.g. to allow migratory fish to travel between freshwater spawning sites and the sea, or to allow animal migration). | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21c. Land and water planning for habitat conservation: "Planning adresses ecosystem-specific needs and/or the needs of particular species of concern at an ecosystem scale (e.g. volume, quality and timing of freshwater flow to sustain particular species, fire management to maintain savannah habitats etc.)" | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 22. State and commercial neighbours:Is there co-operation with adjacent land and water users? | 2 | 0: There is no contact between managers and neighbouring official or corporate land and water users 1: There is contact between managers and neighbouring official or corporate land and water users but little or no cooperation 2: There is contact between managers and neighbouring official or corporate land and water users, but only some co-operation 3: There is regular contact between managers and neighbouring official or corporate land and water users, and substantial co-operation on management |
| Comments and Next Steps |  |  |
| 23. Indigenous people: Do indigenous and traditional peoples resident or regularly using the protected area have input to management decisions? | 3 | 0: Indigenous and traditional peoples have no input into decisions relating to the management of the protected area 1: Indigenous and traditional peoples have some input into discussions relating to management but no direct role in management 2: Indigenous and traditional peoples directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Indigenous and traditional peoples directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24. Local communities: Do local communities resident or near the protected area have input to management decisions? | 3 | 0: Local communities have no input into decisions relating to the management of the protected area 1: Local communities have some input into discussions relating to management but no direct role in management 2: Local communities directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Local communities directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24 a. Impact on communities: There is open communication and trust between local and/or indigenous people, stakeholders and protected area managers | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 b. Impact on communities: Programmes to enhance community welfare, while conserving protected area resources, are being implemented | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 c. Impact on communities: Local and/or indigenous people actively support the protected area | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 25. Economic benefit: Is the protected area providing economic benefits to local communities, e.g. income, employment, payment for environmental services? | 3 | 0: The protected area does not deliver any economic benefits to local communities 1: Potential economic benefits are recognised and plans to realise these are being developed 2: There is some flow of economic benefits to local communities 3: There is a major flow of economic benefits to local communities from activities associated with the protected area |
| Comments and Next Steps |  |  |
| 26. Monitoring and evaluation: Are management activities monitored against performance? | 2 | 0: There is no monitoring and evaluation in the protected area 1: There is some ad hoc monitoring and evaluation, but no overall strategy and/or no regular collection of results 2: There is an agreed and implemented monitoring and evaluation system but results do not feed back into management 3: A good monitoring and evaluation system exists, is well implemented and used in adaptive management |
| Comments and Next Steps |  |  |
| 27. Visitor facilities: Are visitor facilities adequate? | 2 | 0: There are no visitor facilities and services despite an identified need 1: Visitor facilities and services are inappropriate for current levels of visitation 2: Visitor facilities and services are adequate for current levels of visitation but could be improved 3: Visitor facilities and services are excellent for current levels of visitation |
| Comments and Next Steps |  |  |
| 28. Commercial tourism operators: Do commercial tour operators contribute to protected area management? | 1 | 0: There is little or no contact between managers and tourism operators using the protected area 1: There is contact between managers and tourism operators but this is largely confined to administrative or regulatory matters 2: There is limited co-operation between managers and tourism operators to enhance visitor experiences and maintain protected area values 3: There is good co-operation between managers and tourism operators to enhance visitor experiences, and maintain protected area values |
| Comments and Next Steps |  |  |
| 29. Fees: If fees (i.e. entry fees or fines) are applied, do they help protected area management? | 3 | 0: Although fees are theoretically applied, they are not collected 1: Fees are collected, but make no contribution to the protected area or its environs 2: Fees are collected, and make some contribution to the protected area and its environs 3: Fees are collected and make a substantial contribution to the protected area and its environs |
| Comments and Next Steps |  |  |
| 30. Condition of values: What is the condition of the important values of the protected area as compared to when it was first designated? | 2 | 0: Many important biodiversity, ecological or cultural values are being severely degraded 1: Some biodiversity, ecological or cultural values are being severely degraded 2: Some biodiversity, ecological and cultural values are being partially degraded but the most important values have not been significantly impacted 3: Biodiversity, ecological and cultural values are predominantly intact |
| Comments and Next Steps |  |  |
| 30a: Condition of values: The assessment of the condition of values is based on research and/or monitoring | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30b: Condition of values Specific management programmes are being implemented to address threats to biodiversity, ecological and cultural values | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30c: Condition of values: Activities to maintain key biodiversity, ecological and cultural values are a routine part of park management | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| TOTAL SCORE | 81 | Pls add up numbers from assessment form (questions 1 to 30) |

| Tracking Tool for Biodiversity Projects in GEF-3, GEF-4, and GEF-5. |
| --- |
| Objective 1: Catalyzing Sustainability of Protected Area Systems |  |  |  |
| SECTION II: Management Effectiveness Tracking Tool for Protected Areas |  |  |  |
| Note: Please complete the management effectiveness tracking tool for EACH protected area that is the target of the GEF intervention and create a new worksheet for each. Structure and content of the Tracking Tool - Objective 1. Section II: The Tracking Tool has two main sections: datasheets and assessment form. Both sections should be completed. 1. Datasheets: the data sheet comprises of two separate sections: ü Data sheet 1: records details of the assessment and some basic information about the site, such as name, size and location etc. ü Data sheet 2: provides a generic list of threats which protected areas can face. On this data sheet the assessors are asked to identify threats and rank their impact on the protected area. 2. Assessment Form: the assessment is structured around 30 questions presented in table format which includes three columns for recording details of the assessment, all of which should be completed. |  |  |  |
| Important: Please read the Guidelines posted on the GEF website before entering your data |  |  |  |
| Data Sheet 1: Reporting Progress at Protected Area Sites | Please indicate your answer here | Notes |  |
| Name, affiliation and contact details for person responsible for completing the METT (email etc.) | Domingos Gomes Betunde (dogomesbetunde62@yahoo.com.br) |  |  |
| Date assessment carried out | Not specified | Month DD, YYYY (e.g., May 12, 2010) |  |
| Name of protected area | Orango National Park (ONP) |  |  |
| WDPA site code (these codes can be found on www.unep-wcmc.org/wdpa/) | 33,047 |  |  |
| Designations(please choose 1-3) | 2 | 1: National 2: IUCN Category 3: International (please complete lines 35-69 as necessary ) |  |
| Country | Guinea-Bissau |  |  |
| Location of protected area (province and if possible map reference) | Arquipelago dos Bijagos 11°07′N 16°03′W﻿ / ﻿11.12°N 16.05°W﻿ / 11.12 |  |  |
| Date of establishment | December 1st, 2000 |  |  |
| Ownership details (please choose 1-4) | 1 | 1: State 2: Private 3: Community 4: Other |  |
| Management Authority | Institute for Biodiversity and Protected Areas (IBAP) |  |  |
| Size of protected area (ha) | 158,235 |  |  |
| Number of Permanent staff | 14 |  |  |
| Number of Temporary staff | - |  |  |
| Annual budget (US$) for recurrent (operational) funds – excluding staff salary costs | Not specified |  |  |
| Annual budget (US$) for project or other supplementary funds – excluding staff salary costs | Not specified |  |  |
| What are the main values for which the area is designated | Biodiversity, cultural, and landscape values |  |  |
| List the two primary protected area management objectives in below: |  |  |  |
| Management objective 1 | Conserve biodiversity and balanced and functional ecosystems |  |  |
| Management objective 2 | Support the govenment institutions in the management of the oceans and the environment in general |  |  |
| No. of people involved in completing assessment |  |  |  |
| Including: (please choose 1-8) | 1 | 1: PA manager 2: PA staff 3: Other PA agency staff 4: Donors 5: NGOs 6: External experts 7: Local community 8: Other |  |
| Information on International Designations | Please indicate your answer here |  |  |
| UNESCO World Heritage site (see: http://whc.unesco.org/en/list) | NA |  |  |
| Date Listed |  |  |  |
| Site name |  |  |  |
| Site area |  |  |  |
| Geographical co-ordinates |  |  |  |
| Criteria for designation |  | (i.e. criteria i to x) |  |
| Statement of Outstanding Universal Value |  |  |  |
| Ramsar site (see: http://ramsar.wetlands.org) | NA |  |  |
| Date Listed |  |  |  |
| Site name |  |  |  |
| Site area |  |  |  |
| Geographical number |  |  |  |
| Reason for Designation (see Ramsar Information Sheet) |  |  |  |
| UNESCO Man and Biosphere Reserves (see: http://www.unesco.org/new/en/natural-sciences/environment/ecological-sciences/man-and-biosphere-programme/ | X |  |  |
| Date Listed | 1,996 |  |  |
| Site name | Boloma Bijagós Biosphere Reserve/Orango National Park |  |  |
| Site area | Total (101,230), Core (24,410), Buffer (23,780), and Transition (53,040) |  |  |
| Geographical co-ordinates | 11°40' to 14°43'N; 15°20' to 17°00'W |  |  |
| Criteria for designation | High diversity of ecosystems: mangroves with intertidal zones, palm forests, dry and semi-dry forests, secondary and degraded forests, coastal savanna, sand banks and aquatic zones. Many rivers discharge nutrient rich freshwater into the sea with resulting in very high productivity; the area is an important feeding and reproduction ground for many species. There is a large ethnic diversity (total population: 27,000). People make their living from rice cultivation stock raising, wild palm tree exploitation, fishing and the collection of molluscs, orchards and horticulture. |  |  |
| Fulfilment of three functions of MAB |  | conservation, development and logistic support |  |
| Please list other designations (i.e. ASEAN Heritage, Natura 2000) and any supporting information below | NA |  |  |
|  |  | Name |  |
|  |  | Detail |  |
|  |  | Name |  |
|  |  | Detail |  |
|  |  | Name |  |
|  |  | Detail |  |
| Data Sheet 2: Protected Areas Threats (please complete a Data Sheet of threats and assessment for each protected area of the project). |  |  |  |
| Please choose all relevant existing threats as either of high, medium or low significance. Threats ranked as of high significance are those which are seriously degrading values; medium are those threats having some negative impact and those characterised as low are threats which are present but not seriously impacting values or N/A where the threat is not present or not applicable in the protected area. |  |  |  |
| 1. Residential and commercial development within a protected area |  |  |  |
| Threats from human settlements or other non-agricultural land uses with a substantial footprint |  |  |  |
| 1.1 Housing and settlement | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 1.2 Commercial and industrial areas | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 1.3 Tourism and recreation infrastructure | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 2. Agriculture and aquaculture within a protected area |  |  |  |
| Threats from farming and grazing as a result of agricultural expansion and intensification, including silviculture, mariculture and aquaculture |  |  |  |
| 2.1 Annual and perennial non-timber crop cultivation | 2 | 0: N/A 1: Low 2: Medium 3: High |  |
| 2.1a Drug cultivation | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 2.2 Wood and pulp plantations | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 2.3 Livestock farming and grazing | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 2.4 Marine and freshwater aquaculture | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 3. Energy production and mining within a protected area |  |  |  |
| Threats from production of non-biological resources |  |  |  |
| 3.1 Oil and gas drilling | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 3.2 Mining and quarrying | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 3.3 Energy generation, including from hydropower dams | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 4. Transportation and service corridors within a protected area |  |  |  |
| Threats from long narrow transport corridors and the vehicles that use them including associated wildlife mortality |  |  |  |
| 4.1 Roads and railroads (include road-killed animals) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 4.2 Utility and service lines (e.g. electricity cables, telephone lines,) | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 4.3 Shipping lanes and canals | 2 | 0: N/A 1: Low 2: Medium 3: High |  |
| 4.4 Flight paths | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 5. Biological resource use and harm within a protected area |  |  |  |
| Threats from consumptive use of "wild" biological resources including both deliberate and unintentional harvesting effects; also persecution or control of specific species (note this includes hunting and killing of animals) |  |  |  |
| 5.1 Hunting, killing and collecting terrestrial animals (including killing of animals as a result of human/wildlife conflict) | 2 | 0: N/A 1: Low 2: Medium 3: High |  |
| 5.2 Gathering terrestrial plants or plant products (non-timber) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 5.3 Logging and wood harvesting | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 5.4 Fishing, killing and harvesting aquatic resources | 2 | 0: N/A 1: Low 2: Medium 3: High |  |
| 6. Human intrusions and disturbance within a protected area |  |  |  |
| Threats from human activities that alter, destroy or disturb habitats and species associated with non-consumptive uses of biological resources |  |  |  |
| 6.1 Recreational activities and tourism | 2 | 0: N/A 1: Low 2: Medium 3: High |  |
| 6.2 War, civil unrest and military exercises | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 6.3 Research, education and other work-related activities in protected areas | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 6.4 Activities of protected area managers (e.g. construction or vehicle use, artificial watering points and dams) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 6.5 Deliberate vandalism, destructive activities or threats to protected area staff and visitors | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 7. Natural system modifications |  |  |  |
| Threats from other actions that convert or degrade habitat or change the way the ecosystem functions |  |  |  |
| 7.1 Fire and fire suppression (including arson) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 7.2 Dams, hydrological modification and water management/use | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 7.3a Increased fragmentation within protected area | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 7.3b Isolation from other natural habitat (e.g. deforestation, dams without effective aquatic wildlife passages) | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 7.3c Other ‘edge effects’ on park values | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 7.3d Loss of keystone species (e.g. top predators, pollinators etc) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 8. Invasive and other problematic species and genes |  |  |  |
| Threats from terrestrial and aquatic non-native and native plants, animals, pathogens/microbes or genetic materials that have or are predicted to have harmful effects on biodiversity following introduction, spread and/or increase |  |  |  |
| 8.1 Invasive non-native/alien plants (weeds) | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 8.1a Invasive non-native/alien animals | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 8.1b Pathogens (non-native or native but creating new/increased problems) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 8.2 Introduced genetic material (e.g. genetically modified organisms) | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 9. Pollution entering or generated within protected area |  |  |  |
| Threats from introduction of exotic and/or excess materials or energy from point and non-point sources |  |  |  |
| 9.1 Household sewage and urban waste water | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 9.1a Sewage and waste water from protected area facilities (e.g. toilets, hotels etc) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 9.2 Industrial, mining and military effluents and discharges (e.g. poor water quality discharge from dams, e.g. unnatural temperatures, de-oxygenated, other pollution) | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 9.3 Agricultural and forestry effluents (e.g. excess fertilizers or pesticides) | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 9.4 Garbage and solid waste | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 9.5 Air-borne pollutants | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 9.6 Excess energy (e.g. heat pollution, lights etc) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 10. Geological events |  |  |  |
| Geological events may be part of natural disturbance regimes in many ecosystems. But they can be a threat if a species or habitat is damaged and has lost its resilience and is vulnerable to disturbance. Management capacity to respond to some of these changes may be limited. |  |  |  |
| 10.1 Volcanoes | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 10.2 Earthquakes/Tsunamis | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 10.3 Avalanches/ Landslides | - | 0: N/A 1: Low 2: Medium 3: High |  |
| 10.4 Erosion and siltation/ deposition (e.g. shoreline or riverbed changes) | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 11. Climate change and severe weather |  |  |  |
| Threats from long-term climatic changes which may be linked to global warming and other severe climatic/weather events outside of the natural range of variation |  |  |  |
| 11.1 Habitat shifting and alteration | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 11.2 Droughts | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 11.3 Temperature extremes | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 11.4 Storms and flooding | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 12. Specific cultural and social threats |  |  |  |
| 12.1 Loss of cultural links, traditional knowledge and/or management practices | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 12.2 Natural deterioration of important cultural site values | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| 12.3 Destruction of cultural heritage buildings, gardens, sites etc | 1 | 0: N/A 1: Low 2: Medium 3: High |  |
| Assessment Form |  |  |  |
| 1. Legal status: Does the protected area have legal status (or in the case of private reserves is covered by a covenant or similar)? | 3 | 0: The protected area is not gazetted/covenanted 1: There is agreement that the protected area should be gazetted/covenanted but the process has not yet begun 2: The protected area is in the process of being gazetted/covenanted but the process is still incomplete (includes sites designated under international conventions, such as Ramsar, or local/traditional law such as community conserved areas, which do not yet have national legal status or covenant) 3: The protected area has been formally gazetted/covenanted |  |
| Comments and Next Steps |  |  |  |
| 2. Protected area regulations: Are appropriate regulations in place to control land use and activities (e.g. hunting)? | 3 | 0: There are no regulations for controlling land use and activities in the protected area 1: Some regulations for controlling land use and activities in the protected area exist but these are major weaknesses 2: Regulations for controlling land use and activities in the protected area exist but there are some weaknesses or gaps 3: Regulations for controlling inappropriate land use and activities in the protected area exist and provide an excellent basis for management |  |
| Comments and Next Steps |  |  |  |
| 3. Law Enforcement: Can staff (i.e. those with responsibility for managing the site) enforce protected area rules well enough? | 3 | 0: The staff have no effective capacity/resources to enforce protected area legislation and regulations 1: There are major deficiencies in staff capacity/resources to enforce protected area legislation and regulations (e.g. lack of skills, no patrol budget, lack of institutional support) 2: The staff have acceptable capacity/resources to enforce protected area legislation and regulations but some deficiencies remain 3: The staff have excellent capacity/resources to enforce protected area legislation and regulations |  |
| Comments and Next Steps |  |  |  |
| 4. Protected area objectives: Is management undertaken according to agreed objectives? | 3 | 0: No firm objectives have been agreed for the protected area 1: The protected area has agreed objectives, but is not managed according to these objectives 2: The protected area has agreed objectives, but is only partially managed according to these objectives 3: The protected area has agreed objectives and is managed to meet these objectives |  |
| Comments and Next Steps |  |  |  |
| 5. Protected area design: Is the protected area the right size and shape to protect species, habitats, ecological processes and water catchments of key conservation concern? | 3 | 0: Inadequacies in protected area design mean achieving the major objectives of the protected area is very difficult 1: Inadequacies in protected area design mean that achievement of major objectives is difficult but some mitigating actions are being taken (e.g. agreements with adjacent land owners for wildlife corridors or introduction of appropriate catchment management) 2: Protected area design is not significantly constraining achievement of objectives, but could be improved (e.g. with respect to larger scale ecological processes) 3: Protected area design helps achievement of objectives; it is appropriate for species and habitat conservation; and maintains ecological processes such as surface and groundwater flows at a catchment scale, natural disturbance patterns etc |  |
| Comments and Next Steps |  |  |  |
| 6. Protected area boundary demarcation: Is the boundary known and demarcated? | 2 | 0: The boundary of the protected area is not known by the management authority or local residents/neighbouring land users 1: The boundary of the protected area is known by the management authority but is not known by local residents/neighbouring land users 2: The boundary of the protected area is known by both the management authority and local residents/neighbouring land users but is not appropriately demarcated 3: The boundary of the protected area is known by the management authority and local residents/neighbouring land users and is appropriately demarcated |  |
| Comments and Next Steps |  |  |  |
| 7. Management plan: Is there a management plan and is it being implemented? | 3 | 0: There is no management plan for the protected area 1: A management plan is being prepared or has been prepared but is not being implemented 2: A management plan exists but it is only being partially implemented because of funding constraints or other problems 3: A management plan exists and is being implemented |  |
| Comments and Next Steps |  |  |  |
| 7.a Planning process: The planning process allows adequate opportunity for key stakeholders to influence the management plan | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 7.b Planning process: There is an established schedule and process for periodic review and updating of the management plan | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 7.c Planning process: The results of monitoring, research and evaluation are routinely incorporated into planning | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 8. Regular work plan: Is there a regular work plan and is it being implemented | 2 | 0: No regular work plan exists 1: A regular work plan exists but few of the activities are implemented 2: A regular work plan exists and many activities are implemented 3: A regular work plan exists and all activities are implemented |  |
| Comments and Next Steps |  |  |  |
| 9. Resource inventory: Do you have enough information to manage the area? | 2 |  | 0: There is little or no information available on the critical habitats, species and cultural values of the protected area 1: Information on the critical habitats, species, ecological processes and cultural values of the protected area is not sufficient to support planning and decision making 2: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient for most key areas of planning and decision making 3: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient to support all areas of planning and decision making |
| Comments and Next Steps |  |  |  |
| 10. Protection systems: Are systems in place to control access/resource use in the protected area? | 2 | 0: Protection systems (patrols, permits etc) do not exist or are not effective in controlling access/resource use 1: Protection systems are only partially effective in controlling access/resource use 2: Protection systems are moderately effective in controlling access/resource use 3: Protection systems are largely or wholly effective in controlling access/ resource use |  |
| Comments and Next Steps |  |  |  |
| 11. Research: Is there a programme of management-orientated survey and research work? | 2 | 0: There is no survey or research work taking place in the protected area 1: There is a small amount of survey and research work but it is not directed towards the needs of protected area management 2: There is considerable survey and research work but it is not directed towards the needs of protected area management 3:There is a comprehensive, integrated programme of survey and research work, which is relevant to management needs |  |
| Comments and Next Steps |  |  |  |
| 12. Resource management: Is active resource management being undertaken? | 2 | 0: Active resource management is not being undertaken 1: Very few of the requirements for active management of critical habitats, species, ecological processes and cultural values are being implemented 2: Many of the requirements for active management of critical habitats, species, ecological processes and, cultural values are being implemented but some key issues are not being addressed 3: Requirements for active management of critical habitats, species, ecological processes and, cultural values are being substantially or fully implemented |  |
| Comments and Next Steps |  |  |  |
| 13. Staff numbers: Are there enough people employed to manage the protected area? | 2 | 0: There are no staff 1: Staff numbers are inadequate for critical management activities 2: Staff numbers are below optimum level for critical management activities 3: Staff numbers are adequate for the management needs of the protected area |  |
| Comments and Next Steps |  |  |  |
| 14. Staff training: Are staff adequately trained to fulfill management objectives? | 3 | 0: Staff lack the skills needed for protected area management 1: Staff training and skills are low relative to the needs of the protected area 2: Staff training and skills are adequate, but could be further improved to fully achieve the objectives of management 3: Staff training and skills are aligned with the management needs of the protected area |  |
| Comments and Next Steps |  |  |  |
| 15. Current budget: Is the current budget sufficient? | 2 | 0: There is no budget for management of the protected area 1: The available budget is inadequate for basic management needs and presents a serious constraint to the capacity to manage 2: The available budget is acceptable but could be further improved to fully achieve effective management 3: The available budget is sufficient and meets the full management needs of the protected area |  |
| Comments and Next Steps |  |  |  |
| 16. Security of budget: Is the budget secure? | 2 | 0: There is no secure budget for the protected area and management is wholly reliant on outside or highly variable funding 1: There is very little secure budget and the protected area could not function adequately without outside funding 2: There is a reasonably secure core budget for regular operation of the protected area but many innovations and initiatives are reliant on outside funding 3: There is a secure budget for the protected area and its management needs |  |
| Comments and Next Steps |  |  |  |
| 17. Management of budget: Is the budget managed to meet critical management needs? | 2 | 0: Budget management is very poor and significantly undermines effectiveness (e.g. late release of budget in financial year) 1: Budget management is poor and constrains effectiveness 2: Budget management is adequate but could be improved 3: Budget management is excellent and meets management needs |  |
| Comments and Next Steps |  |  |  |
| 18. Equipment: Is equipment sufficient for management needs? | 2 | 0: There are little or no equipment and facilities for management needs 1: There are some equipment and facilities but these are inadequate for most management needs 2: There are equipment and facilities, but still some gaps that constrain management 3: There are adequate equipment and facilities |  |
| Comments and Next Steps |  |  |  |
| 19. Maintenance of equipment: Is equipment adequately maintained? | 2 | 0: There is little or no maintenance of equipment and facilities 1: There is some ad hoc maintenance of equipment and facilities 2: There is basic maintenance of equipment and facilities 3: Equipment and facilities are well maintained |  |
| Comments and Next Steps |  |  |  |
| 20. Education and awareness: Is there a planned education programme linked to the objectives and needs? | 2 | 0: There is no education and awareness programme 1: There is a limited and ad hoc education and awareness programme 2: There is an education and awareness programme but it only partly meets needs and could be improved 3: There is an appropriate and fully implemented education and awareness programme |  |
| Comments and Next Steps |  |  |  |
| 21. Planning for land and water use: Does land and water use planning recognise the protected area and aid the achievement of objectives? | 2 | 0: Adjacent land and water use planning does not take into account the needs of the protected area and activities/policies are detrimental to the survival of the area 1: Adjacent land and water use planning does not takes into account the long term needs of the protected area, but activities are not detrimental the area 2: Adjacent land and water use planning partially takes into account the long term needs of the protected area 3: Adjacent land and water use planning fully takes into account the long term needs of the protected area |  |
| Comments and Next Steps |  |  |  |
| 21a. Land and water planning for habitat conservation: Planning and management in the catchment or landscape containing the protected area incorporates provision for adequate environmental conditions (e.g. volume, quality and timing of water flow, air pollution levels etc) to sustain relevant habitats. | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 21b. Land and water planning for habitat conservation: Management of corridors linking the protected area provides for wildlife passage to key habitats outside the protected area (e.g. to allow migratory fish to travel between freshwater spawning sites and the sea, or to allow animal migration). | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 21c. Land and water planning for habitat conservation: "Planning adresses ecosystem-specific needs and/or the needs of particular species of concern at an ecosystem scale (e.g. volume, quality and timing of freshwater flow to sustain particular species, fire management to maintain savannah habitats etc.)" | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 22. State and commercial neighbours:Is there co-operation with adjacent land and water users? | 2 | 0: There is no contact between managers and neighbouring official or corporate land and water users 1: There is contact between managers and neighbouring official or corporate land and water users but little or no cooperation 2: There is contact between managers and neighbouring official or corporate land and water users, but only some co-operation 3: There is regular contact between managers and neighbouring official or corporate land and water users, and substantial co-operation on management |  |
| Comments and Next Steps |  |  |  |
| 23. Indigenous people: Do indigenous and traditional peoples resident or regularly using the protected area have input to management decisions? | 3 | 0: Indigenous and traditional peoples have no input into decisions relating to the management of the protected area 1: Indigenous and traditional peoples have some input into discussions relating to management but no direct role in management 2: Indigenous and traditional peoples directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Indigenous and traditional peoples directly participate in all relevant decisions relating to management, e.g. co-management |  |
| Comments and Next Steps |  |  |  |
| 24. Local communities: Do local communities resident or near the protected area have input to management decisions? | 3 | 0: Local communities have no input into decisions relating to the management of the protected area 1: Local communities have some input into discussions relating to management but no direct role in management 2: Local communities directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Local communities directly participate in all relevant decisions relating to management, e.g. co-management |  |
| Comments and Next Steps |  |  |  |
| 24 a. Impact on communities: There is open communication and trust between local and/or indigenous people, stakeholders and protected area managers | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 24 b. Impact on communities: Programmes to enhance community welfare, while conserving protected area resources, are being implemented | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 24 c. Impact on communities: Local and/or indigenous people actively support the protected area | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 25. Economic benefit: Is the protected area providing economic benefits to local communities, e.g. income, employment, payment for environmental services? | 3 | 0: The protected area does not deliver any economic benefits to local communities 1: Potential economic benefits are recognised and plans to realise these are being developed 2: There is some flow of economic benefits to local communities 3: There is a major flow of economic benefits to local communities from activities associated with the protected area |  |
| Comments and Next Steps |  |  |  |
| 26. Monitoring and evaluation: Are management activities monitored against performance? | 2 | 0: There is no monitoring and evaluation in the protected area 1: There is some ad hoc monitoring and evaluation, but no overall strategy and/or no regular collection of results 2: There is an agreed and implemented monitoring and evaluation system but results do not feed back into management 3: A good monitoring and evaluation system exists, is well implemented and used in adaptive management |  |
| Comments and Next Steps |  |  |  |
| 27. Visitor facilities: Are visitor facilities adequate? | 3 | 0: There are no visitor facilities and services despite an identified need 1: Visitor facilities and services are inappropriate for current levels of visitation 2: Visitor facilities and services are adequate for current levels of visitation but could be improved 3: Visitor facilities and services are excellent for current levels of visitation |  |
| Comments and Next Steps |  |  |  |
| 28. Commercial tourism operators: Do commercial tour operators contribute to protected area management? | 2 | 0: There is little or no contact between managers and tourism operators using the protected area 1: There is contact between managers and tourism operators but this is largely confined to administrative or regulatory matters 2: There is limited co-operation between managers and tourism operators to enhance visitor experiences and maintain protected area values 3: There is good co-operation between managers and tourism operators to enhance visitor experiences, and maintain protected area values |  |
| Comments and Next Steps |  |  |  |
| 29. Fees: If fees (i.e. entry fees or fines) are applied, do they help protected area management? | 3 | 0: Although fees are theoretically applied, they are not collected 1: Fees are collected, but make no contribution to the protected area or its environs 2: Fees are collected, and make some contribution to the protected area and its environs 3: Fees are collected and make a substantial contribution to the protected area and its environs |  |
| Comments and Next Steps |  |  |  |
| 30. Condition of values: What is the condition of the important values of the protected area as compared to when it was first designated? | 2 | 0: Many important biodiversity, ecological or cultural values are being severely degraded 1: Some biodiversity, ecological or cultural values are being severely degraded 2: Some biodiversity, ecological and cultural values are being partially degraded but the most important values have not been significantly impacted 3: Biodiversity, ecological and cultural values are predominantly intact |  |
| Comments and Next Steps |  |  |  |
| 30a: Condition of values: The assessment of the condition of values is based on research and/or monitoring | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 30b: Condition of values Specific management programmes are being implemented to address threats to biodiversity, ecological and cultural values | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| 30c: Condition of values: Activities to maintain key biodiversity, ecological and cultural values are a routine part of park management | 1 | 0: No 1: Yes |  |
| Comments and Next Steps |  |  |  |
| TOTAL SCORE | 84 | Pls add up numbers from assessment form (questions 1 to 30) |  |

| Tracking Tool for Biodiversity Projects in GEF-3, GEF-4, and GEF-5 |  |  |
| --- | --- | --- |
| Objective 1: Catalyzing Sustainability of Protected Area Systems |  |  |
| SECTION II: Management Effectiveness Tracking Tool for Protected Areas |  |  |
| Note: Please complete the management effectiveness tracking tool for EACH protected area that is the target of the GEF intervention and create a new worksheet for each. Structure and content of the Tracking Tool - Objective 1. Section II: The Tracking Tool has two main sections: datasheets and assessment form. Both sections should be completed. 1. Datasheets: the data sheet comprises of two separate sections: ü Data sheet 1: records details of the assessment and some basic information about the site, such as name, size and location etc. ü Data sheet 2: provides a generic list of threats which protected areas can face. On this data sheet the assessors are asked to identify threats and rank their impact on the protected area. 2. Assessment Form: the assessment is structured around 30 questions presented in table format which includes three columns for recording details of the assessment, all of which should be completed. |  |  |
| Important: Please read the Guidelines posted on the GEF website before entering your data |  |  |
| Data Sheet 1: Reporting Progress at Protected Area Sites | Please indicate your answer here | Notes |
| Name, affiliation and contact details for person responsible for completing the METT (email etc.) | Castro Barbosa (castrobarbosa2002@gmail.com) |  |
| Date assessment carried out | Not specified | Month DD, YYYY (e.g., May 12, 2010) |
| Name of protected area | Joao Vieira e Poilão Marine Protected Area |  |
| WDPA site code (these codes can be found on www.unep-wcmc.org/wdpa/) | 317052 |  |
| Designations(please choose 1-3) | 2 | 1: National 2: IUCN Category 3: International (please complete lines 35-69 as necessary ) |
| Country | Guinea-Bissau |  |
| Location of protected area (province and if possible map reference) | 10°57′02″N 15°42′43″W﻿ / ﻿10.95063°N 15.71182°W﻿ / 10.95063 |  |
| Date of establishment | August 1st, 2000 |  |
| Ownership details (please choose 1-4) | 1 | 1: State 2: Private 3: Community 4: Other |
| Management Authority | Institute for Biodiversity and Protected Areas (IBAP) |  |
| Size of protected area (ha) | 49 500 |  |
| Number of Permanent staff | 6 |  |
| Number of Temporary staff | - |  |
| Annual budget (US$) for recurrent (operational) funds – excluding staff salary costs | Not specified |  |
| Annual budget (US$) for project or other supplementary funds – excluding staff salary costs | Not specified |  |
| What are the main values for which the area is designated | Biodiversity, cultural, and landscape values |  |
| List the two primary protected area management objectives in below: |  |  |
| Management objective 1 | Conserve biodiversity and balanced and functional ecosystems |  |
| Management objective 2 | Support the govenment institutions in the management of the oceans and the environment in general |  |
| No. of people involved in completing assessment |  |  |
| Including: (please choose 1-8) | 3 | 1: PA manager 2: PA staff 3: Other PA agency staff 4: Donors 5: NGOs 6: External experts 7: Local community 8: Other |
| Information on International Designations | Please indicate your answer here |  |
| UNESCO World Heritage site (see: http://whc.unesco.org/en/list) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical co-ordinates |  |  |
| Criteria for designation |  | (i.e. criteria i to x) |
| Statement of Outstanding Universal Value |  |  |
| Ramsar site (see: http://ramsar.wetlands.org) | NA |  |
| Date Listed |  |  |
| Site name |  |  |
| Site area |  |  |
| Geographical number |  |  |
| Reason for Designation (see Ramsar Information Sheet) |  |  |
| UNESCO Man and Biosphere Reserves (see: http://www.unesco.org/new/en/natural-sciences/environment/ecological-sciences/man-and-biosphere-programme/ | X |  |
| Date Listed | 1,996 |  |
| Site name | Boloma Bijagós Biosphere Reserve/Joao Vieira e Poilão Marine Protected Area |  |
| Site area | Total (101,230), Core (24,410), Buffer (23,780), and Transition (53,040) | Total, Core, Buffe, and Transition |
| Geographical co-ordinates | 11°40' to 14°43'N; 15°20' to 17°00'W |  |
| Criteria for designation | ########################## |  |
| Fulfilment of three functions of MAB |  | conservation, development and logistic support |
| Please list other designations (i.e. ASEAN Heritage, Natura 2000) and any supporting information below | NA |  |
|  |  | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
|  |  | Name |
|  |  | Detail |
| Data Sheet 2: Protected Areas Threats (please complete a Data Sheet of threats and assessment for each protected area of the project). |  |  |
| Please choose all relevant existing threats as either of high, medium or low significance. Threats ranked as of high significance are those which are seriously degrading values; medium are those threats having some negative impact and those characterised as low are threats which are present but not seriously impacting values or N/A where the threat is not present or not applicable in the protected area. |  |  |
| 1. Residential and commercial development within a protected area |  |  |
| Threats from human settlements or other non-agricultural land uses with a substantial footprint |  |  |
| 1.1 Housing and settlement | - | 0: N/A 1: Low 2: Medium 3: High |
| 1.2 Commercial and industrial areas | - | 0: N/A 1: Low 2: Medium 3: High |
| 1.3 Tourism and recreation infrastructure | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2. Agriculture and aquaculture within a protected area |  |  |
| Threats from farming and grazing as a result of agricultural expansion and intensification, including silviculture, mariculture and aquaculture |  |  |
| 2.1 Annual and perennial non-timber crop cultivation | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 2.1a Drug cultivation | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.2 Wood and pulp plantations | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.3 Livestock farming and grazing | - | 0: N/A 1: Low 2: Medium 3: High |
| 2.4 Marine and freshwater aquaculture | - | 0: N/A 1: Low 2: Medium 3: High |
| 3. Energy production and mining within a protected area |  |  |
| Threats from production of non-biological resources |  |  |
| 3.1 Oil and gas drilling | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.2 Mining and quarrying | - | 0: N/A 1: Low 2: Medium 3: High |
| 3.3 Energy generation, including from hydropower dams | - | 0: N/A 1: Low 2: Medium 3: High |
| 4. Transportation and service corridors within a protected area |  |  |
| Threats from long narrow transport corridors and the vehicles that use them including associated wildlife mortality |  |  |
| 4.1 Roads and railroads (include road-killed animals) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.2 Utility and service lines (e.g. electricity cables, telephone lines,) | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.3 Shipping lanes and canals | - | 0: N/A 1: Low 2: Medium 3: High |
| 4.4 Flight paths | - | 0: N/A 1: Low 2: Medium 3: High |
| 5. Biological resource use and harm within a protected area |  |  |
| Threats from consumptive use of "wild" biological resources including both deliberate and unintentional harvesting effects; also persecution or control of specific species (note this includes hunting and killing of animals) |  |  |
| 5.1 Hunting, killing and collecting terrestrial animals (including killing of animals as a result of human/wildlife conflict) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 5.2 Gathering terrestrial plants or plant products (non-timber) | - | 0: N/A 1: Low 2: Medium 3: High |
| 5.3 Logging and wood harvesting | - | 0: N/A 1: Low 2: Medium 3: High |
| 5.4 Fishing, killing and harvesting aquatic resources | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6. Human intrusions and disturbance within a protected area |  |  |
| Threats from human activities that alter, destroy or disturb habitats and species associated with non-consumptive uses of biological resources |  |  |
| 6.1 Recreational activities and tourism | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 6.2 War, civil unrest and military exercises | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.3 Research, education and other work-related activities in protected areas | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.4 Activities of protected area managers (e.g. construction or vehicle use, artificial watering points and dams) | - | 0: N/A 1: Low 2: Medium 3: High |
| 6.5 Deliberate vandalism, destructive activities or threats to protected area staff and visitors | - | 0: N/A 1: Low 2: Medium 3: High |
| 7. Natural system modifications |  |  |
| Threats from other actions that convert or degrade habitat or change the way the ecosystem functions |  |  |
| 7.1 Fire and fire suppression (including arson) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 7.2 Dams, hydrological modification and water management/use | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3a Increased fragmentation within protected area | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3b Isolation from other natural habitat (e.g. deforestation, dams without effective aquatic wildlife passages) | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3c Other ‘edge effects’ on park values | - | 0: N/A 1: Low 2: Medium 3: High |
| 7.3d Loss of keystone species (e.g. top predators, pollinators etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8. Invasive and other problematic species and genes |  |  |
| Threats from terrestrial and aquatic non-native and native plants, animals, pathogens/microbes or genetic materials that have or are predicted to have harmful effects on biodiversity following introduction, spread and/or increase |  |  |
| 8.1 Invasive non-native/alien plants (weeds) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1a Invasive non-native/alien animals | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.1b Pathogens (non-native or native but creating new/increased problems) | - | 0: N/A 1: Low 2: Medium 3: High |
| 8.2 Introduced genetic material (e.g. genetically modified organisms) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9. Pollution entering or generated within protected area |  |  |
| Threats from introduction of exotic and/or excess materials or energy from point and non-point sources |  |  |
| 9.1 Household sewage and urban waste water | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.1a Sewage and waste water from protected area facilities (e.g. toilets, hotels etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.2 Industrial, mining and military effluents and discharges (e.g. poor water quality discharge from dams, e.g. unnatural temperatures, de-oxygenated, other pollution) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.3 Agricultural and forestry effluents (e.g. excess fertilizers or pesticides) | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.4 Garbage and solid waste | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.5 Air-borne pollutants | - | 0: N/A 1: Low 2: Medium 3: High |
| 9.6 Excess energy (e.g. heat pollution, lights etc) | - | 0: N/A 1: Low 2: Medium 3: High |
| 10. Geological events |  |  |
| Geological events may be part of natural disturbance regimes in many ecosystems. But they can be a threat if a species or habitat is damaged and has lost its resilience and is vulnerable to disturbance. Management capacity to respond to some of these changes may be limited. |  |  |
| 10.1 Volcanoes | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.2 Earthquakes/Tsunamis | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.3 Avalanches/ Landslides | - | 0: N/A 1: Low 2: Medium 3: High |
| 10.4 Erosion and siltation/ deposition (e.g. shoreline or riverbed changes) | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 11. Climate change and severe weather |  |  |
| Threats from long-term climatic changes which may be linked to global warming and other severe climatic/weather events outside of the natural range of variation |  |  |
| 11.1 Habitat shifting and alteration | 1 | 0: N/A 1: Low 2: Medium 3: High |
| 11.2 Droughts | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.3 Temperature extremes | - | 0: N/A 1: Low 2: Medium 3: High |
| 11.4 Storms and flooding | - | 0: N/A 1: Low 2: Medium 3: High |
| 12. Specific cultural and social threats |  |  |
| 12.1 Loss of cultural links, traditional knowledge and/or management practices | - | 0: N/A 1: Low 2: Medium 3: High |
| 12.2 Natural deterioration of important cultural site values | - | 0: N/A 1: Low 2: Medium 3: High |
| 12.3 Destruction of cultural heritage buildings, gardens, sites etc | - | 0: N/A 1: Low 2: Medium 3: High |
| Assessment Form |  |  |
| 1. Legal status: Does the protected area have legal status (or in the case of private reserves is covered by a covenant or similar)? | 3 | 0: The protected area is not gazetted/covenanted 1: There is agreement that the protected area should be gazetted/covenanted but the process has not yet begun 2: The protected area is in the process of being gazetted/covenanted but the process is still incomplete (includes sites designated under international conventions, such as Ramsar, or local/traditional law such as community conserved areas, which do not yet have national legal status or covenant) 3: The protected area has been formally gazetted/covenanted |
| Comments and Next Steps |  |  |
| 2. Protected area regulations: Are appropriate regulations in place to control land use and activities (e.g. hunting)? | 3 | 0: There are no regulations for controlling land use and activities in the protected area 1: Some regulations for controlling land use and activities in the protected area exist but these are major weaknesses 2: Regulations for controlling land use and activities in the protected area exist but there are some weaknesses or gaps 3: Regulations for controlling inappropriate land use and activities in the protected area exist and provide an excellent basis for management |
| Comments and Next Steps |  |  |
| 3. Law Enforcement: Can staff (i.e. those with responsibility for managing the site) enforce protected area rules well enough? | 3 | 0: The staff have no effective capacity/resources to enforce protected area legislation and regulations 1: There are major deficiencies in staff capacity/resources to enforce protected area legislation and regulations (e.g. lack of skills, no patrol budget, lack of institutional support) 2: The staff have acceptable capacity/resources to enforce protected area legislation and regulations but some deficiencies remain 3: The staff have excellent capacity/resources to enforce protected area legislation and regulations |
| Comments and Next Steps |  |  |
| 4. Protected area objectives: Is management undertaken according to agreed objectives? | 3 | 0: No firm objectives have been agreed for the protected area 1: The protected area has agreed objectives, but is not managed according to these objectives 2: The protected area has agreed objectives, but is only partially managed according to these objectives 3: The protected area has agreed objectives and is managed to meet these objectives |
| Comments and Next Steps |  |  |
| 5. Protected area design: Is the protected area the right size and shape to protect species, habitats, ecological processes and water catchments of key conservation concern? | 3 | 0: Inadequacies in protected area design mean achieving the major objectives of the protected area is very difficult 1: Inadequacies in protected area design mean that achievement of major objectives is difficult but some mitigating actions are being taken (e.g. agreements with adjacent land owners for wildlife corridors or introduction of appropriate catchment management) 2: Protected area design is not significantly constraining achievement of objectives, but could be improved (e.g. with respect to larger scale ecological processes) 3: Protected area design helps achievement of objectives; it is appropriate for species and habitat conservation; and maintains ecological processes such as surface and groundwater flows at a catchment scale, natural disturbance patterns etc |
| Comments and Next Steps |  |  |
| 6. Protected area boundary demarcation: Is the boundary known and demarcated? | 2 | 0: The boundary of the protected area is not known by the management authority or local residents/neighbouring land users 1: The boundary of the protected area is known by the management authority but is not known by local residents/neighbouring land users 2: The boundary of the protected area is known by both the management authority and local residents/neighbouring land users but is not appropriately demarcated 3: The boundary of the protected area is known by the management authority and local residents/neighbouring land users and is appropriately demarcated |
| Comments and Next Steps |  |  |
| 7. Management plan: Is there a management plan and is it being implemented? | 3 | 0: There is no management plan for the protected area 1: A management plan is being prepared or has been prepared but is not being implemented 2: A management plan exists but it is only being partially implemented because of funding constraints or other problems 3: A management plan exists and is being implemented |
| Comments and Next Steps |  |  |
| 7.a Planning process: The planning process allows adequate opportunity for key stakeholders to influence the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.b Planning process: There is an established schedule and process for periodic review and updating of the management plan | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 7.c Planning process: The results of monitoring, research and evaluation are routinely incorporated into planning | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 8. Regular work plan: Is there a regular work plan and is it being implemented | 2 | 0: No regular work plan exists 1: A regular work plan exists but few of the activities are implemented 2: A regular work plan exists and many activities are implemented 3: A regular work plan exists and all activities are implemented |
| Comments and Next Steps |  |  |
| 9. Resource inventory: Do you have enough information to manage the area? | 2 | 0: There is little or no information available on the critical habitats, species and cultural values of the protected area 1: Information on the critical habitats, species, ecological processes and cultural values of the protected area is not sufficient to support planning and decision making 2: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient for most key areas of planning and decision making 3: Information on the critical habitats, species, ecological processes and cultural values of the protected area is sufficient to support all areas of planning and decision making |
| Comments and Next Steps |  |  |
| 10. Protection systems: Are systems in place to control access/resource use in the protected area? | 2 | 0: Protection systems (patrols, permits etc) do not exist or are not effective in controlling access/resource use 1: Protection systems are only partially effective in controlling access/resource use 2: Protection systems are moderately effective in controlling access/resource use 3: Protection systems are largely or wholly effective in controlling access/ resource use |
| Comments and Next Steps |  |  |
| 11. Research: Is there a programme of management-orientated survey and research work? | 2 | 0: There is no survey or research work taking place in the protected area 1: There is a small amount of survey and research work but it is not directed towards the needs of protected area management 2: There is considerable survey and research work but it is not directed towards the needs of protected area management 3:There is a comprehensive, integrated programme of survey and research work, which is relevant to management needs |
| Comments and Next Steps |  |  |
| 12. Resource management: Is active resource management being undertaken? | 2 | 0: Active resource management is not being undertaken 1: Very few of the requirements for active management of critical habitats, species, ecological processes and cultural values are being implemented 2: Many of the requirements for active management of critical habitats, species, ecological processes and, cultural values are being implemented but some key issues are not being addressed 3: Requirements for active management of critical habitats, species, ecological processes and, cultural values are being substantially or fully implemented |
| Comments and Next Steps |  |  |
| 13. Staff numbers: Are there enough people employed to manage the protected area? | 2 | 0: There are no staff 1: Staff numbers are inadequate for critical management activities 2: Staff numbers are below optimum level for critical management activities 3: Staff numbers are adequate for the management needs of the protected area |
| Comments and Next Steps |  |  |
| 14. Staff training: Are staff adequately trained to fulfill management objectives? | 2 | 0: Staff lack the skills needed for protected area management 1: Staff training and skills are low relative to the needs of the protected area 2: Staff training and skills are adequate, but could be further improved to fully achieve the objectives of management 3: Staff training and skills are aligned with the management needs of the protected area |
| Comments and Next Steps |  |  |
| 15. Current budget: Is the current budget sufficient? | 2 | 0: There is no budget for management of the protected area 1: The available budget is inadequate for basic management needs and presents a serious constraint to the capacity to manage 2: The available budget is acceptable but could be further improved to fully achieve effective management 3: The available budget is sufficient and meets the full management needs of the protected area |
| Comments and Next Steps |  |  |
| 16. Security of budget: Is the budget secure? | 1 | 0: There is no secure budget for the protected area and management is wholly reliant on outside or highly variable funding 1: There is very little secure budget and the protected area could not function adequately without outside funding 2: There is a reasonably secure core budget for regular operation of the protected area but many innovations and initiatives are reliant on outside funding 3: There is a secure budget for the protected area and its management needs |
| Comments and Next Steps |  |  |
| 17. Management of budget: Is the budget managed to meet critical management needs? | 2 | 0: Budget management is very poor and significantly undermines effectiveness (e.g. late release of budget in financial year) 1: Budget management is poor and constrains effectiveness 2: Budget management is adequate but could be improved 3: Budget management is excellent and meets management needs |
| Comments and Next Steps |  |  |
| 18. Equipment: Is equipment sufficient for management needs? | 2 | 0: There are little or no equipment and facilities for management needs 1: There are some equipment and facilities but these are inadequate for most management needs 2: There are equipment and facilities, but still some gaps that constrain management 3: There are adequate equipment and facilities |
| Comments and Next Steps |  |  |
| 19. Maintenance of equipment: Is equipment adequately maintained? | 2 | 0: There is little or no maintenance of equipment and facilities 1: There is some ad hoc maintenance of equipment and facilities 2: There is basic maintenance of equipment and facilities 3: Equipment and facilities are well maintained |
| Comments and Next Steps |  |  |
| 20. Education and awareness: Is there a planned education programme linked to the objectives and needs? | 2 | 0: There is no education and awareness programme 1: There is a limited and ad hoc education and awareness programme 2: There is an education and awareness programme but it only partly meets needs and could be improved 3: There is an appropriate and fully implemented education and awareness programme |
| Comments and Next Steps |  |  |
| 21. Planning for land and water use: Does land and water use planning recognise the protected area and aid the achievement of objectives? | 2 | 0: Adjacent land and water use planning does not take into account the needs of the protected area and activities/policies are detrimental to the survival of the area 1: Adjacent land and water use planning does not takes into account the long term needs of the protected area, but activities are not detrimental the area 2: Adjacent land and water use planning partially takes into account the long term needs of the protected area 3: Adjacent land and water use planning fully takes into account the long term needs of the protected area |
| Comments and Next Steps |  |  |
| 21a. Land and water planning for habitat conservation: Planning and management in the catchment or landscape containing the protected area incorporates provision for adequate environmental conditions (e.g. volume, quality and timing of water flow, air pollution levels etc) to sustain relevant habitats. | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21b. Land and water planning for habitat conservation: Management of corridors linking the protected area provides for wildlife passage to key habitats outside the protected area (e.g. to allow migratory fish to travel between freshwater spawning sites and the sea, or to allow animal migration). | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 21c. Land and water planning for habitat conservation: "Planning adresses ecosystem-specific needs and/or the needs of particular species of concern at an ecosystem scale (e.g. volume, quality and timing of freshwater flow to sustain particular species, fire management to maintain savannah habitats etc.)" | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 22. State and commercial neighbours:Is there co-operation with adjacent land and water users? | 2 | 0: There is no contact between managers and neighbouring official or corporate land and water users 1: There is contact between managers and neighbouring official or corporate land and water users but little or no cooperation 2: There is contact between managers and neighbouring official or corporate land and water users, but only some co-operation 3: There is regular contact between managers and neighbouring official or corporate land and water users, and substantial co-operation on management |
| Comments and Next Steps |  |  |
| 23. Indigenous people: Do indigenous and traditional peoples resident or regularly using the protected area have input to management decisions? | 3 | 0: Indigenous and traditional peoples have no input into decisions relating to the management of the protected area 1: Indigenous and traditional peoples have some input into discussions relating to management but no direct role in management 2: Indigenous and traditional peoples directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Indigenous and traditional peoples directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24. Local communities: Do local communities resident or near the protected area have input to management decisions? | 3 | 0: Local communities have no input into decisions relating to the management of the protected area 1: Local communities have some input into discussions relating to management but no direct role in management 2: Local communities directly contribute to some relevant decisions relating to management but their involvement could be improved 3: Local communities directly participate in all relevant decisions relating to management, e.g. co-management |
| Comments and Next Steps |  |  |
| 24 a. Impact on communities: There is open communication and trust between local and/or indigenous people, stakeholders and protected area managers | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 b. Impact on communities: Programmes to enhance community welfare, while conserving protected area resources, are being implemented | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 24 c. Impact on communities: Local and/or indigenous people actively support the protected area | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 25. Economic benefit: Is the protected area providing economic benefits to local communities, e.g. income, employment, payment for environmental services? | 3 | 0: The protected area does not deliver any economic benefits to local communities 1: Potential economic benefits are recognised and plans to realise these are being developed 2: There is some flow of economic benefits to local communities 3: There is a major flow of economic benefits to local communities from activities associated with the protected area |
| Comments and Next Steps |  |  |
| 26. Monitoring and evaluation: Are management activities monitored against performance? | 2 | 0: There is no monitoring and evaluation in the protected area 1: There is some ad hoc monitoring and evaluation, but no overall strategy and/or no regular collection of results 2: There is an agreed and implemented monitoring and evaluation system but results do not feed back into management 3: A good monitoring and evaluation system exists, is well implemented and used in adaptive management |
| Comments and Next Steps |  |  |
| 27. Visitor facilities: Are visitor facilities adequate? | 3 | 0: There are no visitor facilities and services despite an identified need 1: Visitor facilities and services are inappropriate for current levels of visitation 2: Visitor facilities and services are adequate for current levels of visitation but could be improved 3: Visitor facilities and services are excellent for current levels of visitation |
| Comments and Next Steps |  |  |
| 28. Commercial tourism operators: Do commercial tour operators contribute to protected area management? | 3 | 0: There is little or no contact between managers and tourism operators using the protected area 1: There is contact between managers and tourism operators but this is largely confined to administrative or regulatory matters 2: There is limited co-operation between managers and tourism operators to enhance visitor experiences and maintain protected area values 3: There is good co-operation between managers and tourism operators to enhance visitor experiences, and maintain protected area values |
| Comments and Next Steps |  |  |
| 29. Fees: If fees (i.e. entry fees or fines) are applied, do they help protected area management? | 3 | 0: Although fees are theoretically applied, they are not collected 1: Fees are collected, but make no contribution to the protected area or its environs 2: Fees are collected, and make some contribution to the protected area and its environs 3: Fees are collected and make a substantial contribution to the protected area and its environs |
| Comments and Next Steps |  |  |
| 30. Condition of values: What is the condition of the important values of the protected area as compared to when it was first designated? | 2 | 0: Many important biodiversity, ecological or cultural values are being severely degraded 1: Some biodiversity, ecological or cultural values are being severely degraded 2: Some biodiversity, ecological and cultural values are being partially degraded but the most important values have not been significantly impacted 3: Biodiversity, ecological and cultural values are predominantly intact |
| Comments and Next Steps |  |  |
| 30a: Condition of values: The assessment of the condition of values is based on research and/or monitoring | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30b: Condition of values Specific management programmes are being implemented to address threats to biodiversity, ecological and cultural values | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| 30c: Condition of values: Activities to maintain key biodiversity, ecological and cultural values are a routine part of park management | 1 | 0: No 1: Yes |
| Comments and Next Steps |  |  |
| TOTAL SCORE | 83 | Pls add up numbers from assessment form (questions 1 to 30) |

In early 2012, charity status was secured for the FBG in the United Kingdom and a protocol was formalized with the GoBG, recognizing its legal statute and granting the foundation tax exempt status within the country.

United Nations Development Programme. 2014 Human Development Report Summary. 28 pp.

Gini coefficient is 47.0 as of HDR 2007/2008.

http://www.worldbank.org/en/country/guineabissau/overview. Accessed 11/2014.

Second National Communication on Climate Changes in Guinea-Bissau Final Report. 2011. Republic of Guinea-Bissau Secretary of State for Environment and Sustainable Development Environment Directoriat. UNDP & GEF. 83 pp.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Idem.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

www.cbd.int/countries. Accessed, November 2014.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Also part of the Ilhas de Bijagós Biosphere Reserve.

Rainho, A., et al. 2007. Inventário da fauna de morcegos e aves das florestas de Cantanhez e Cacine. UBAP, ICN, Centro de Biologia Ambiental. 34 pp.

Bout, N. and A. Ghiurghi. 2013. Guide des Mammifères du Parc National de Cantanhez, Guinée-Bissau. Acção para o Desenvolvimento, Guinée-Bissau Associazione Interpreti Naturalistici ONLUS, Italie. Première édition.

Bird Life International. 2014. Important Bird Area factsheet: Cantanhez forests. Downloaded from http://www.birdlife.org on 11/2014.

Instituto de Biodiversidade e Areas Protegidas de Guinea Bissau. Plano de Gestão do Parque Nacional Cantanhez. 34 pp.

Bout, N. and A. Ghiurghi. 2013. Guide des Mammiferes du Parc National de Cantanhez, Guinée-Bissau. Acção para o Desenvolvimento, Guinée-Bissau Associazione Interpreti Naturalistici ONLUS, Italie. Première edition.

Instituto de Biodiversidade e Areas Protegidas de Guinea Bissau. Plano de Gestão do Parque Nacional Cantanhez. 34 pp.

Hockings, K.J., and C Sousa. 2013. Human-Chimpanzee Sympatry and Interactions in Cantanhez National Park, Guinea-Bissau: Current Research and Future Directions. Primate Conservation 26: 57–65.

IBAP 2014: Estratégia Nacional para as Áreas Protegidas e a Conservação da Biodiversidade na Guiné-Bissau 2014-2020.

The Hunting Regulations (Regulamento da Caça) D.4/80 regulates extraction of wildlife outside game concessions and thus could apply to protected areas and their buffer zones as well. This decree establishes areas and periods where hunting is permitted under certain conditions and others where and when it is not allowed. It establishes fees and sanctions associated to hunting activities, reinforced by the Código Penal DL no.4/93 and Código de Proceso penal DL no.5/93.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Implementing regulation D. 26/91 and D. 27/91 of the Forestry Law No.4-A/91 establish a “forest resources fund” to collect fees from forest and game concessions as well as fines from improper exploitation and for igniting forest and brush fires. The fund exists but is not operational.

Boubacar-Sid Barry, et al. 2007. Conflict, livelihoods, and poverty in Guinea-Bissau. Washington, D.C: The World Bank.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp

Institute for Biodiversity and Protected Areas (IBAP). 2006. Managing biodiversity for sustainable development. 20 pp.

Project Phase Proposal: Promotion de la démocratie et Gestion transparente des industries extractives, phase III. Groupe de Travail sur le Pétrole et autres Industries Extractives - GTP-IE. SwissAid. 26 pp.

Catry, P., et al. 2002. First census of the green turtle at Poilão, Bijagós Archipelago, Guinea-Bissau: the most important nesting colony on the Atlantic coast of Africa. Oryx 36(4): 400-403.

Robertson, P. Important Bird Areas in Africa and associated islands – Guinea-Bissau. 8 pp. Available at: http://www.birdlife.org/datazone/userfiles/file/IBAs/AfricaCntryPDFs/GuineaBissau.pdf. Accessed, 11/2014.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Idem.

Viriato Soares Cassamá, 2009: Análise da Biodiversidade no Complexo Dulombi-Boé-Tchetche. Relatório Final. Projecto – Apoio à Cosolidaçao do Sistema de Áreas Protegidas Terrestres na Faixa de Floresta da Guiné-Bissau. PPG-3650, PNUD-GEF.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

Idem.

FUNBIO. 2014. Ambiente Financeiro e Estratégia Financeira para o Sistema Nacional de Áreas Protegidas de Guiné-Bissau. 95 pp.

This would approximately translate to a range of 21,000,000 to 41,800,000 US$.

Document de Politique de Développement Forestier. Version finale, 2010. República da Guinée-Bissau Ministério da Agricultura e Desenvolvimento Rural.

Fifth National Report to the Convention on Biological Diversity. 2014. Republic of Guinea Bissau.74 pp.

GEF evaluation of experience with conservation trust funds. GEF Council, Washington DC, 1998.

FUNBIO. 2014. Ambiente Financeiro e Estratégia Financeira para o Sistema Nacional de Áreas Protegidas de Guiné-Bissau. 95 pp.

1 USD = 1.24576 EURO.

a) Minimalist Scenario: All protected areas can implement the minimalist version of their developed business plans; b) Realistic Scenario:  Minimalist option plus more activity/project can be implemented by the PA; c) Strategic Scenario: In this scenario the three “main” national parks (Orango, João Vieira, and Cantanhez) will be able to implement the realistic version of their business plan, all other parks only their minimalist versions; d) Priority Scenario: The lightest version of all includes that only the 3 of the above mentioned national parks receive investments according to the minimalist approach and the rest will just be functioning around the minimalist scenario but minus the investment costs.

As per FUNBIO table 8. P 40 (financial needs minus funds available = finance gap)

The following columns are all calculated from FNBIO Study tables in in Annexes 1 and 2.

Calculated as: average yearly financial gap (column 3) equals 5.9% and column 4 equals 100% to determine the average endowment needed to cover the average yearly financial gap.

See FUNBIO study annex 1.

Estimated based on the Financial Sustainability Scorecard (baseline data for 2014).

Approximate amount remaining to be raised after initial capitalization through GEF 5 project, approximating an “intermediate” funding scenario from the four scenarios investigated by Funbio.

Estimated based on the current (2014; see Financial Score Card) and 2014-2018 projected funding gap – as described in the Draft Multi-Year Workplan of IBAP.

In early 2012, charity status was secured for the FBG in the United Kingdom and a protocol was formalized with the Guinea-Bissau Government, recognizing its legal statute and granting the foundation tax exempt status within the country.

Established terrestrial PAs and related biological corridors in Guinea Bissau: Boé NP (95,280 ha), Cacheu NP (88,615 ha), Cantanhez NP (105,800 ha), Cufada NP (89,000 ha), Dulombi NP (98,951 ha), Cheché Corridor (36,604 ha), Cutabande-Quebo Corridor (55, 003 ha), Salifo Corridor (56,162 ha).

Ibid

Ibid

www.biodiversityfinance.net

The most recent application of the METT for Cantanhez NP was conducted during the PPG phase of the project, yielding a total score of 57.

21,352 ha conservation zone, 44,712 ha buffer zone, 39,702 ha development zone.

Bellamy, Jean-Joseph and Kevin Hill (2010), “Monitoring Guidelines of Capacity Development in Global Environment Facility Projects,” Global Support Programme Bureau for Development Policy, United Nations Development Programme, New York, USA.

a) IUCN. Connectivity Conservation: International Experience in Planning, Establishment and Management of Biodiversity Corridors. Background paper, 18 pages. Available at: http://cmsdata.iucn.org/downloads/070723_bci_international_report_final.pdf; b) Bennett, G., and Mulongoy, K.J. (2006). Review of Experience with Ecological Networks, Corridors, and Buffer Zones. Secretariat of the Convention on Biological Diversity, Montreal, Technical Series No. 23, 100 pages; and e) Dewi, S. et al. 2013. Protected areas within multifunctional landscapes: Squeezing out intermediate land use intensities in the tropics? Land Use Policy 30(1): 38–56.

Based on the FUNBIO study, 2014.

Idem.

See Sec. 2.2, Forestry Master Plan (2010) and Sec. 5, Lei Florestal, No. 5/2011 for new vision for the preservation of forest resources; see Sec. 5.3.9 - 5.3.10 of National Forestry Policy (2010) for issues related to PAs and coordination with IBAP.

By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced.

By 2020 the extinction of known threatened species has been prevented and their conservation status, particularly of those most in decline, has been improved and sustained.

By 2020 areas under agriculture, aquaculture, and forestry are managed sustainably, ensuring conservation of biodiversity.

By 2020, at least 17 percent of terrestrial and inland water areas, and 10 percent of coastal and marine areas, especially areas of particular importance for biodiversity and ecosystem services, are conserved through effectively and equitably managed, ecologically representative and well-connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes.

By 2020, ecosystem resilience and the contribution of biodiversity to carbon stocks has been enhanced, through conservation and restoration, including restoration of at least 15 percent of degraded ecosystems, thereby contributing to climate change mitigation and adaptation and to combating desertification.

By 2020, at the latest, the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources, and in accordance with the consolidated and agreed process in the Strategy for Resource Mobilization, should increase substantially from the current levels. This target will be subject to changes contingent to resource needs assessments to be developed and reported by Parties.

Decision 2005/1 of 28 January, 2005 of UNDPs Executive Board approved the new Financial Regulations and Rules and along with them the new definitions of ‘execution’ and ‘implementation’.

The National Project Director will not be paid from the project funds, but will represent a Government in-kind contribution to the Project.

Refers to a UNDP procedural and minuted meeting which allows the Resident Representative to sign off on a Project Document.

There are two scenarios of NIM: (a) Full national implementation, in which national implementing partners directly assume the responsibility for the related output (or outputs) and carry out all activities towards the achievement of these outputs; and (b) National implementation, in which the national implementing partner assumes full responsibility for the related output(s) but where, at the request of the government, UNDP as a responsible party undertakes specific and clearly defined activities for the implementing partner.

As per GEF guidelines, the project will also be using the BD-1 Tracking Tool. New or additional GEF monitoring requirements will be accommodated and adhered to once they are officially launched.

Spergel, Barry and Kathleen Mikitin (2014) Practice Standards for Conservation Trust Funds, CFA.

ibid

IBAP was formally established and commenced operations in 2005.

It is noted that the Operations Manual is currently under review by the newly hired Executive Secretary.

Based on an internal document prepared by NIK Sekhran for UNDP/GEF “Checklist for Environmental Funds”.

Spergel, Barry et al 2014

Pers. Com, Lorenzo Rosenzweig, Fondo Mexicano para la Conservacion de la Naturaleza, November 2014.

See Pims 3938, Sustainable Financing of the Protected Areas System in Mozambique.

Based on an internal document prepared by NIK Sekhran for UNDP/GEF “Checklist for Environmental Funds”.