United Nations Development Programme

Project Document template for nationally implemented projects

financed by the GEF/LDCF/SCCF Trust Funds

| Project title: Combatting illegal and unsustainable trade in endangered species in Indonesia |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Country: Indonesia | Implementing Partner: Ministry of Environment and Forestry (Directorate General of Law Enforcement on Environment and Forestry) |  |  |  | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF/Country Programme Outcome: Outcome 3. By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disasters and other shocks. Output 3.3: National/local governments have improved policies, systems, and partnerships with non-state actors to protect biodiversity and endangered species. |  |  |  |  |  |
| UNDP Strategic Plan Output: Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste. Output 2.5: Legal and regulatory frameworks, policies and institutions enabled to ensure the conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation. |  |  |  |  |  |
| UNDP Social and Environmental Screening Category: Moderate |  |  | UNDP Gender Marker: 2 |  |  |
| Atlas Proposal/Award ID (also known as ‘project’): 00094636 |  |  | Atlas output Project ID (also known as ‘output’): 00098732 |  |  |
| UNDP-GEF PIMS ID: 5391 |  |  | GEF ID: 9150 |  |  |
| Planned start date: this is defined as the expected project document signature date July 2017 (estimated) |  |  | Planned end date: this is defined as the planned date of operational closure. Calculate the planned end date by adding the project duration in months noted on the PIF to the expected project document signature date June 2023 (estimated) |  |  |
| LPAC date: To be determined |  |  |  |  |  |
| Brief project description: The development challenge that this project seeks to address concerns the devastating impact of unsustainable and illegal wildlife trade (IWT) on wildlife populations in Indonesia and SE Asia. The value of the illegal trade in Indonesia alone is estimated at up to US$ 1 billion per year. Factoring in the unsustainable legal trade, the value rockets, representing an enormous economic, environmental, and social loss. This trade has already caused the decline and local extinction of many species across SE Asia. Much of the trade is highly organized, benefits a relatively small criminal fraternity, whilst depriving developing economies of billions of dollars in lost revenues and development opportunities. Within SE Asia, a significant amount of this trade starts from Indonesia, one of the world’s top 10 ‘megadiverse’ countries and the largest supplier of wildlife products in Asia, both ‘legal’ and illegal. The IWT and associated bushmeat trade are an immediate threat to the existence of key endangered species such as the Sumatran and Javan Rhinoceros, Sumatran Tiger, Asian Elephant and Sunda Pangolin amongst a wide range of less prominent species. Indonesia is also becoming an important transit point for IWT from Africa to East Asia, such as African Ivory. The consequence of the unsustainable trade is a massive threat to globally important wildlife. The GEF project alternative aims to remove the barriers to accomplishing the long term solution to this challenge, namely to conserve key wildlife species in Indonesia, by ensuring that the legal wildlife trade is ecologically and economically sustainable, while reducing the scale and impact of illegal wildlife trafficking, both from Indonesia and in transit through the country. Even biodiversity within the PA system is not shielded from poaching to supply the domestic and international IWT. Wildlife is a natural resource that, if exploited well, can fuel development, provide considerable state revenues and provide financial incentives to manage wildlife and ecosystems. The key barriers are: 1) the weak policy and regulatory framework and insufficient information and tools to understand, regulate and combat illegal wildlife trade; 2) suboptimal institutional capacity for compliance monitoring and enforcement; 3) ineffective enforcement at the site and landscape levels; and 4) inadequate information sharing mechanisms to support responses to IWT. These barriers will be removed through the implementation of the project’s four components leading to the following outcomes that in turn will contribute towards achievement of the Project Objective, which is to reduce the volume of unsustainable wildlife trade and the rate of loss of globally significant biodiversity in Indonesia and East and South-East Asia. Outcome 1: Strengthened national policy, legal and institutional framework for regulating legal commercial wildlife trade and combating illegal wildlife trade. This component aims to enhance the legal and policy environment by creating subsidiary regulations and removing loopholes and inconsistencies that prevent enforcement of measures to combat IWT. Appropriate institutional frameworks will be put in place to ensure inter-agency coordination domestically and internationally. Information systems will be established for accurately tracking and sharing legal trade volumes and revenues, enforcement effectiveness, reliable intelligence on illegal trade and its impacts across sectors, and on the in situ status of traded species. Economic valuation of IWT and the feasibility of a cost recovery system from regulation of wildlife trade will be assessed. The project will support establishment of the National Wildlife Crime Taskforce. Outcome 2: Strengthened institutional capacity for regulatory coordination, implementation and enforcement at the national and international levels. Under this component, the project will support key law enforcement institutions to ensure that institutional capacity, including development of tools to support continued effective actions for combatting IWT. Increased capacity will be gauged using the ICCWC Indicator Framework related to wildlife trade control, increased rate of inspections, seizures, arrests and successful prosecution of wildlife crime cases. Increased and more effective enforcement cooperation between Indonesia and other key states (e.g. Vietnam and China) will be developed. Outcome 3: Improved enforcement strategy demonstrated and scaled up at key trade ports and connected subnational regions with key ecosystems. This component will focus on scaling-up on-the-ground implementation of improved enforcement capacity and strategies supported under components 1 and 2, including the Wildlife Crime Unit (WCU) approach for two critically important IWT subnational demonstration regions – northern Sumatra centered on the Leuser ecosystem and northern Sulawesi centered on the Bogani Nani Wartabone ecosystem and their respective seaport and airport. The project will support coordinated intelligence analysis to determine wildlife trade chains across these regions, including source areas, markets and ports, joint enforcement operations, and community awareness raising, engagement in information networks, and livelihood support in source areas. The project will also support systematic assessment and capacity building for enforcement at five key wildlife trade ports. Outcome 4: Implementation and upscaling/replication of project approaches at national and international levels is supported by effective knowledge management and gender mainstreaming. The fourth project component closely links with and underpins the other three, by supporting the sharing of knowledge, experiences and lessons learned through project implementation with project stakeholders, the wider public in Indonesia, and also globally through the GEF Global Wildlife Programme. Finally, this project forms part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and falls under the GEF Programme Global Partnership on Wildlife Conservation and Crime Prevention For Sustainable Development (9071). Under this programmatic framework, with the coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured. |  |  |  |  |  |
| Financing Plan |  |  |  |  |  |
| GEF Trust Fund or LDCF or SCCF or other vertical fund |  |  | USD 6,988,853 |  |  |
| UNDP TRAC resources |  |  | USD -0 |  |  |
| Cash co-financing to be administered by UNDP |  |  | USD -0 |  |  |
| - Total Budget administered by UNDP |  |  | USD 6,988,853 |  |  |
| Parallel co-financing |  |  |  |  |  |
| UNDP |  |  | USD 100,000 |  |  |
| Government (MoEF) |  |  | USD 42,848,742 |  |  |
| Wildlife Conservation Society |  |  | USD 2,000,000 |  |  |
| - Total co-financing |  |  | USD 44,948,742 |  |  |
| - Grand-Total Project Financing (1)+(2) |  |  | USD 51,937,595 |  |  |
| Signatures |  |  |  |  |  |
| Signature: |  | Agreed by Government |  | Date/Month/Year: |  |
| Signature: |  | Agreed by Implementing Partner |  | Date/Month/Year: |  |
| Signature: |  | Agreed by UNDP |  | Date/Month/Year: |  |

# Table of Contents

I.	Table of Contents	4

II.	Development Challenge	8

III.	Strategy	15

IV.	Results and Partnerships	25

V.	Feasibility	50

VI.	Project Results Framework	61

VII.	Monitoring and Evaluation (M&E) Plan	67

VIII.	Governance and Management Arrangements	71

IX.	Financial Planning and Management	77

X.	Total Budget and Work Plan	80

XI.	Legal Context	89

I.	Mandatory Annexes	90

II.	Optional Annexes	90

FIGURES AND TABLES

Figure 1. Conceptual model of the factors influencing the project targets, with project interventions.	14

Figure 2. Theory of Change Diagram for the Project (above)	22

Table 1. Assumptions for Theory of Change Diagram	22

Figure 3. Map showing project demonstration regions and ports (Source: WCS).	24

Figure 4. Detailed project pathways from Outputs to Outcomes and Impacts	37

Table 2. Summary stakeholder analysis indicating main roles and responsibilities	39

Table 3. Proposed gender mainstreaming actions for project implementation	46

Table 4. Description of project risks, impact and probability and mitigation measures	52

Table 5. Mandatory GEF M&E Requirements and M&E Budget	69

Figure 5. Project Organisation Structure	72

Table 6. Key features of the project demonstration regions	75

Acronyms and Abbreviations

AGO	Attorney General’s Office

APR/PIR	Annual Project Review/ Project Implementation Reports

ASEAN-WEN	Association of South East Asian Nations – Wildlife Enforcement Network

BAPPEDA	Badan Perencana Pembangunan Daerah (Regional Body for Planning and Development)

BAPPENAS	Badan Perencanaan Pembangunan Nasional (Body for National Development Planning)

BKSDA		Natural Resources Conservation Agency

BPPS	Bureau for Policy and Programme Support

CBD		Convention on Biological Diversity

CBO	Community Based Organization

CID		Criminal Investigation Division (of the Indonesian National Police)

CITES		Convention on International Trade in Endangered Species

CMS	Convention on the Conservation of Migratory Species of Wild Animals

CO	Country Office

CPAP	Country Programme Action Plan

CSO		Civil Society Organization – used interchangeably with local NGO

DG	Directorate General

Dishut		Dinas Kehutanan (Forestry Agency)

EOP		End of Project

ERC		Evaluation Resource Center (of UNDP Evaluation Office)

E-PASS		UNDP/GEF project - Enhancing the Protected Area System in Sulawesi

FFI		Fauna & Flora International

FGD	Focus Group Discussion

FPIC		Free Prior and Informed Consent

FSP	Full Sized Project

Gakkum	Directorate General of Law Enforcement on Environment and Forest (MoEF)

GDP		Gross Domestic Product

GEF		Global Environment Facility

GEFSEC	Global Environment Facility Secretariat

GoI	Government of Indonesia

GTI		Global Tiger Initiative

Ha		Hectare

HWC	Human wildlife conflict

IBSAP		Indonesian Biodiversity Strategy and Action Plan

ICCWC		International Consortium on Combatting Wildlife Crime

ICITAP	International Criminal Investigative Training Program (US Department of Justice)

IDR		Indonesian Rupiah

INGO		International Non-Governmental Organization

INP		Indonesian National Police

IUCN		International Union for Conservation of Nature (World Conservation Union)

IP		Implementing Partner

IPB	Institute Pertanian Bogor

IW		(Project) Inception Workshop

IWT	Illegal wildlife trade

KSDAE 		Directorate of Conservation of Natural Resources and Ecosystems

KPK		Komisi Pemberantasan Korupsi (Corruption Eradication Commission)

KUHAP		Indonesian Code of Criminal Procedures

LIPI		Indonesian Institute of Science (CITES scientific authority)

LoA	Letter of Agreement

M&E		Monitoring and Evaluation

METT		Management Effectiveness Tracking Tool

MMAF		Ministry of Marine Affairs and Fisheries

MoEF		Ministry of Environment and Forestry

MoHA	 Ministry of Home Affairs

MoU		Memorandum of Understanding

MTR	Mid-Term Review

NGO		Non-Governmental Organization (used interchangeably with CSO)

NIM	National Implementation Modality

NP		National Park

NTRP		National Tiger Recovery Plan

OPDAT	Overseas Prosecutorial Development, Assistance and Training (US Dept of Justice)

PA		Protected Area

PAC	Project Appraisal Committee

PB	Project Board

PD	Project Director

PIF		Project Identification Form (for GEF)

PIMS		Project Information Management System

PIR	GEF Project Implementation Report

PIU	Project Implementation Unit

PM	Project Manager

PMC	Project Management Cost

PMU		Project Management Unit

POLAIR	Directorate of Coast and Sea Guarding Police

POPP		Programme and Operation Policies and Procedures

PortMATE	Port Monitoring & Anti-Trafficking Evaluation tool

PPATK		Pusat Pelaporan dan Analisis Transaksi Keuangan (Indonesian Financial Transaction Reports and Analysis Centre)

PPG		Project Preparation Grant (for GEF)

PPH		Penyidikan dan Pengamanan Hutan (Forest Security and Investigation)

PPNS		Penyidik Pegawai Negeri Sipil (Civil Service Investigator)

PPR		Project Progress Report

PusDikLat	Pusat Pendidikan dan Pelatihan (Training and Education Centre)

RBM		Resort Based Management (for National Parks)

RF		Results Framework

RP	Responsible Party

RTA		Regional Technical Advisor (of UNDP)

SA WEN	Southern Africa Wildlife Enforcement Network

SESP		UNDP Social and Environmental Screening Procedure

SMART 	Spatial Monitoring and Reporting Tool (patrolling and reporting system)

SPORC		Satuan Polhut Reaksi Cepat (Rapid Response Forest Police Unit)

STAP	GEF Scientific Technical Advisory Panel

TE	Terminal Evaluation

TOR	Terms of Reference

TRACE 	Tools and Resources for Applied Conservation and Enforcement – Wildlife Forensics Network

UN		United Nations

UN-REDD	United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation in Developing Countries

UNDAF		United Nations Development Assistance Framework

UNDP		United Nations Development Programme

UNDP-CO	UNDP Country Office

UNEP		United Nations Environment Programme

UNOCD	United Nations Office on Drugs and Crime

UPT		Unit Pelaksanaan Teknis (Technical Implementation Unit)

UPT KKJI	Unit Pelaksanaan Teknis Konservasi Kawasan dan Jenis Ikan (Technical Implementation Unit of Aquatic Species and Area Conservation - of MMAF)

US$		United States Dollar

USAID	US Agency for International Development

USAID-ARREST 	Asia’s Regional Response to Endangered Species Trafficking, 2010-2016

US-DoJ	US Department of Justice International Criminal Investigative Training Program (ICITAP)

WCS		Wildlife Conservation Society

WCO	World Customs Organization

WCU	Wildlife Crimes Unit

WRU	Wildlife Response Unit

WT	Wildlife trade

WWF		World Wide Fund for Nature

ZSL		Zoological Society of London

# Development Challenge

- Threats, Root causes and Impacts: This project specifically addresses the threats posed by the illegal and unsustainable wildlife trade to endangered species in Indonesia. The illegal trade in fauna and flora (other than fisheries and timber) has been estimated by different sources to be worth US$ 7-23 billion dollars annually and US$ 2.5 billion in East Asia and the Pacific alone. Some of the values associated with wildlife products are huge; ivory is being traded at over $2000/kg whilst Rhino horn can fetch over $66,000/kg, Helmeted Hornbill beaks trade for $6400/kg in China, Sun Bear gall bladders up to $2000 each, Tiger canine pairs at $6200-7200 and Pangolin scales $3000/kg.

- This trade has already caused the decline and local extinction of many species across SE Asia, including those inside protected areas. The impacts have been particularly strong in this region, with populations of tigers, Asian elephants and various turtle species showing severe losses . Much of the trade is highly organized, benefits a relatively small criminal fraternity, whilst depriving developing economies of billions of dollars in lost revenues and development opportunities

- Combatting the illegal wildlife trade in Indonesia is hindered by its low domestic political profile, which translates into a lack of interest and poor collaboration between law enforcement agencies. There is also a widespread lack of understanding regarding laws and enforcement procedures at all levels, and regulatory loopholes and inconsistencies that prevent successful prosecutions (see barriers below for further information). For example, inside Indonesia the trade and sale of African ivory and non-native tiger or rhino parts is technically not illegal. Regulatory reform is critical to address these issues.

- Wildlife crime is driven by complex demands from various complex and fluid markets. Opinions on the primary drivers behind wildlife crime (and the corollary responses to address them) differ widely amongst different wildlife experts, partly due to a lack of data and partly due to most workers in the field focusing on a specific species or area with few having a wider view across the supply chain. Many of the variations in wildlife crime can certainly be attributed to variations in markets, and most supply chains displaying high levels of variability in response to changes in supply and demand. Furthermore, increasing economic wealth is thought to be a significant factor behind increasing demand for wildlife products and the trappings of economic growth such as better infrastructure and freer trading markets are also thought to have had significant impact on wildlife crime. One of the key sources of demand for wildlife products has been the Traditional Chinese Medicine industry, which has ancient cultural roots but has been increasing in popularity in recent years in tandem with rapid economic growth in China and countries where Chinese medicine is popular, and new trends are also occurring. However, other sources of demand are also important, including the pet trade, food (for protein intake, and also as delicacies), curios and souvenirs and fur and skins. The few market-based instruments that have been used to address wildlife crime such as certification, taxation and buying agreements – used particularly for timber – do appear to be having some success.

- Without enforcement, laws and sanctions alone do little to deter wildlife criminals. Laws and regulations are generally thought to be a critical part of the framework for addressing wildlife crime. However, the existence of laws and punishments alone do not necessarily have any impact on wildlife crime, with the risk of detection being a key factor for compliance.

- The underlying socio-economic factors contributing to these threats include population growth and poverty in rural and protected area boundary zones, which reduce the ability of local communities to practice sustainable agriculture and natural resource use.  Productive job opportunities – which might provide local residents with an alternative source of livelihood – are limited, driving some to engage in illegal poaching activities. However, middle-men and traders gain significantly more from the trade in wildlife products and are usually based in urban centres. Whilst links between poverty and the wildlife trade evidently exist, particularly with regards to leaving the trade, the relationships appear to be so complex that initiatives to counter wildlife crime through alternative livelihoods or increased incomes do not seem to be very successful. As with the impacts of livelihoods, the relationship between awareness and wildlife crime also appear to be highly complex and relatively poorly understood.

- The economic and social impacts of wildlife crime are far less understood but potentially far more serious. The impacts of wildlife crime are not only environmental. Illegal wildlife trade involves wide, complex markets involving people from wide and various social and economic backgrounds from poor rural villagers to small scale traders to wealthy, politically connected importers and exporters. The impacts of the industry can therefore be far reaching . Firstly, the environmental impacts will have social implications through the loss of ecosystem functionality, the spread of zoonotic diseases, the reduction in available natural assets and through missed taxation revenue. In Asia, this is particularly a risk for poorer communities strongly reliant on natural resources. But there is also plenty of evidence that the social impacts of wildlife trade go even further than that, including direct threats to the lives of people working in the sector, the proliferation of weapons, the fuelling of social conflict and undermining governance, socio-economic stability and even national security. Furthermore, wildlife crime is often associated with other serious, organised criminal activities and/or political rebel groups (particularly in Africa) with shared personnel, trading networks, finances and methods to undermine the rule of law. Much of the world’s wildlife crime is now run by extremely organized and increasingly sophisticated and well-equipped criminal syndicates.

- The direct threats impacting on the project target, populations of key endangered species in Indonesia, and their relationships with a range of indirect factors (root causes) are illustrated in the conceptual diagram below, with the entry points for project intervention strategies indicated (Figure 1).

- Baseline Analysis: A situation analysis has been conducted during project preparation with regard to the policy, legal and regulatory framework, institutional capacity for enforcement and coordination, information sharing, and enforcement at key ports used for wildlife trade, details of which are given in Annexes 11 - 17.

- The CITES Management Authority in Indonesia is the Ministry of Environment and Forestry (MoEF), which was formed by the merging of respective Ministry of Forestry and Ministry of Environment following the election of the new President – Mr. Joko Widodo - in 2014. Within the newly established MoEF, the unit or Directorate which handles matters related to CITES remains the same as before, namely the Directorate of Biodiversity Conservation (c.q. Sub-Directorate Program and Convention), under the Directorate General of Conservation of Natural Resources and Ecosystem (formerly called the Directorate General of Forest Protection and Nature Conservation).  CITES matters only form part of the duty of the Directorate of Biodiversity Conservation, as this Directorate is also responsible for managing matters related to wildlife and plants conservation in the country, monitoring including inter-province and inter-island wildlife trade. The national parks and other conservation areas (excluding protection forest) are managed by the Directorate of Conservation Areas, also under the Directorate General of Conservation of Natural Resources and Ecosystem.

- MoEF has many regional offices called Balai Konservasi Sumber Daya Alam (BKSDA).  Currently there are 31 BKSDAs, spread out all over in Indonesian territory.  In relation to wildlife trade, BKSDAs have roles to proposed number of annual quota for harvestable species and its monitoring, issue a letter of domestic transportation of wildlife specimens (Surat Ijin Angkut Tumbuhan dan Satwa Dalam Negeri, SATS-DN), and as law enforcers against wildlife trafficking in their areas.

- For law enforcement, however, substantial changes have occurred in MoEF’s organizational structure.  In the previous organization, matters related to law enforcement of IWT were managed by the Directorate of Forest Protection and Prevention, also under the Directorate General of Forest Protection and Nature Conservation. When the Ministry of Environment and Forestry was formed, law enforcement became a bigger issue, covering green issues (related to forestry, i.e. land encroachment, illegal timber trade, illegal wildlife trade) and brown issues (related to pollution).  Therefore, the MoEF uplifted the Directorate (of Forest Protection and Prevention) into a Directorate General of Law Enforcement on Environment and Forestry and the organization structure was changed accordingly. Among the four sub-directorates of the Directorate General of Law Enforcement of Environment and Forestry, two Directorates are directly concerned with law enforcement of illegal wildlife trade, namely the Directorate of Forest Prevention and Protection (Pencegahan dan Pengamanan Hutan) and Directorate of Criminal Law Enforcement (Penegakan Hukum Pidana).   Currently the MoEF employs 8,105 forest rangers, PPNS (Civil Investigation Officers) 1,043, and 764 SPORC (Satuan Polisi Kehutanan Reaksi Cepat; Quick Responding Forest Rangers). Rangers do not have powers of arrest, so patrolling is not very effective and there is a need for improving coordination with the police and the army. Much of the enforcement effort is directed towards forestry offences.

- The Criminal Investigation Division (CID, Bareskrim POLRI) of the Indonesian National Police (INP) is a key agency in combatting nationwide illegal wildlife trade. Unit 1 is specifically tasked with targeting environmental crimes, and has 7 staff and an annual budget of $50,000.  It has played a leading role in the majority of high-profile prosecutions brought successfully in Indonesia over the past 5 years, however is hampered by limited staffing, budgets, capacity and the limited importance attached to wildlife crimes by prosecutors, the judiciary and customs. Other relevant Indonesian Law enforcement agencies include the Attorney General’s Office (AGO), the Ministry of Marine Affairs and Fisheries, Customs, Quarantine, the Corruption Eradication Commission (KPK) and the Financial Trans-projects Analysis and Reporting Centre (PPATK).

- The government’s effort has been complemented by investments from bilateral and multilateral agencies, and international NGOs over the past years. Since 2003, the Wildlife Conservation Society (WCS) has pioneered an innovative approach to working with law enforcement agencies across local, regional and national scales to combat illegal wildlife trade in Indonesia, called the “Wildlife Crimes Unit” (WCU). The WCU has supported the Indonesian government to conduct more than 350 arrests in Sumatra, Java, Kalimantan, Sulawesi, Bali, Nusa Tenggara, and Papua. To date, the WCU consists of 6 units to protect both terrestrial and marine protected species. More than 400 wildlife traffickers have been arrested (with a successful prosecution rate of >90%), and thousands of protected animals and tones of animal parts have been seized from sting operations. This is unparalleled in the Asian context, and the WCU is the most successful example of an approach to combat illegal wildlife crime in the region. WCS currently invests c.$250,000/year in work on illegal wildlife trade in Indonesia, including projects on combating trade of sharks and rays, and strengthening institutional frameworks to combat wildlife trafficking in Indonesia.

- Progress in 2015 on strengthening the legal and institutional frameworks for combating the illegal wildlife trade supported by WCS has included a rapid assessment of current knowledge, trends and priority actions for wildlife crime, and a detailed analysis of the policy and legal context with support from USAID, with subsequent support to MoEF to implement report recommendations for legal revisions to improve species protection. This has included significant achievements – government agreement to revise the Conservation Law 5/1990 during 2016, MoEF agreement that the revised Law should always reflect the current and existing CITES list, and progress towards updating the Protected Species List by January 2016. In addition, trainings were conducted for MoEF, the police, customs, and the Financial Transactions Analysis and Reporting Centre (PPATK) to build capacity for handling wildlife crime. These included training of 35 police officials from around the country to detect wildlife crime; training of 50 staff from law enforcement agencies and journalists in use of forensics for species identification, with TRACE Wildlife Forensics Network and the Eijkman Institute; and training for 15 PPATK staff.

- Indonesian law enforcement agencies also carried out at least 26 arrests involving 37 perpetrators during 2015 with the assistance of the WCU, with cases including 5 tons of pangolins from Medan; over 1 ton of manta ray bone and gill plates, 6 tiger cases, 2 ivory cases, over 500kg of oceanic whitetip shark fins, and the conviction of an orang-utan trader. Such cases have been publicised in the Indonesian media through collaboration with the Alliance of Independent Journalists and Indonesian Journalists Association.

- Marine wildlife protection has progressed, with four convictions of traders in manta ray parts reflecting the tough new stance of the MMAF to protect these species, and the WCU and MMAF handled a total of 9 manta and shark test cases in total between November 2014 and October 2015. WCS also worked with MMAF, MoEF, LIPI and other institutions towards preparing a legal framework for shark and ray protection through the development of  National Plans of Action for sharks and rays (NPOA 2015-2019) and for manta rays (NPOA 2016-2020) and associated revision of the Conservation Act 5/1990 and updating of the annex of GR7/1999 to include enhanced protection for shark and ray species in line with CITES through the Protected Species List, with the final updated list expected to be issued through Ministerial Decree at the end of 2015. Training has been conducted for management and enforcement agencies (including MMAF, Customs and PPATK) regarding CITES-listed shark and ray species, relevant legislation for prosecution for related trafficking offences, and identification of species. Training also included 50 provincial and district staff of MMAF’s Technical Implementation Unit of Aquatic Species and Area Conservation on WCU approaches and identification of shark and manta products. WCU has also agreed with the Misool Baseftin Foundation (MBF) to conduct joint sea patrols in Lamakera, Nusa Tenggara province, to protect manta rays and whale sharks from hunting, involving police officers from the Directorate of Coast and Sea Guarding Police (POLAIR) and one WCU staff. Two equipped guard posts will be established in Lamakera to support the patrols and alternative livelihood program for the local community, especially manta hunters.

- At the landscape level, WCS supported Wildlife Response Units (WRUs) in two critical tiger landscapes in Sumatra –Leuser and Bukit Barisan Selatan, which responded to at least 44 human-wildlife conflict cases, 17 involving tigers, with domestic livestock killed in some cases. In responding to such conflicts, the WRUs secure and stabilize the situation, and assist communities to remain safe and to protect their livestock, benefiting both the communities and the tigers.

- Under a 2014 MoU between the Government of Indonesia and the United States Government, US Government agencies are providing capacity-building assistance to law enforcement agencies on environmental crimes (including wildlife trafficking) and are facilitating regional dialogues of action to reduce illegal wildlife trade. These are implemented by US Department of Justice (US-DoJ) International Criminal Investigative Training Program (ICITAP), US-DoJ Office of Overseas Prosecutorial Development, Assistance and Training (OPDAT), and the US Agency for International Development (USAID). Regional initiatives include USAID-ARREST (Asia’s Regional Response to Endangered Species Trafficking, 2010-2016); The Association of Southeast Asian Nations’ Wildlife Enforcement Network (ASEAN-WEN); efforts by the International Consortium for Combatting Wildlife Crimes (ICCWC) partners, including the CITES secretariat, Interpol, World Customs Organisation, United Nations Office on Drugs and Crime and the World Bank. In December 2012 Indonesia and Vietnam also signed a MoU on Wildlife Law Enforcement, which is driving bilateral cooperation within the region.

- Finally, despite a relatively adequate national policy framework and institution, gender equality in performing biodiversity conservation management is still weak. The predominant role of men is primarily due to biophysical, cultural and structural factors. As to date, the majority of Indonesians perceive that particularly forest management activities are not suitable for women to do because they involve physical power, masculinity and extended periods of stay in the field. Examples are hunting of wildlife and harvesting of NTFPs. For reasons of traditional beliefs and values, the majority of households in rural areas still believe that wives’ primary task is to rear children and do domestic chores like cooking and cleaning. Another limiting factor is the established structure of state employees that is dominated by men, thus decision-making on biodiversity conservation management is also male-dominated.

- Overall, in the baseline situation described above, there remain regulatory loopholes, lack of coordination between enforcement agencies, a lack of capacity and resources, and a limited ability to upscale successful models (e.g. the Wildlife Crimes Unit) with the consequence that wildlife trade, both illegal and legal, will substantially increase or, at best, will continue unabated, resulting in local declines and the increased likelihood of extinctions of key Indonesian wildlife species, including elephants, tigers and rhinos. Even biodiversity within the PA system is not shielded from poaching to supply the domestic and international illegal wildlife trade. Illegal wildlife trade will continue to operate as organized crime, while legal wildlife trade will remain poorly regulated, raising few revenues for the state, and acting as a cover behind which illegal trade can flourish. Thus, these baseline activities, although significant, fall short of the proposed long-term solution: to conserve key wildlife species in Indonesia, by ensuring that the legal wildlife trade is ecologically and economically sustainable, while reducing the scale and impact of illegal wildlife trafficking, both from Indonesia and in transit through the country.

- Barriers: Although the legal framework for wildlife protection and regulation of wildlife trade in Indonesia is relatively well developed, it contains a number of significant loopholes, which are facilitating or enabling the continuing illegal trade of legally protected, and otherwise threatened species in Indonesia. In addition, there are a number of significant implementation challenges which hamper the enforcement of the existing legal framework. Thus, while the government has made tremendous efforts to control poaching and illegal wildlife trade as described above, its efforts have been impeded by a number of barriers. These include: (1) Weak policy and regulatory framework and insufficient information and tools to understand, regulate and combat illegal wildlife trade; (2) Sub-optimal institutional capacity for compliance monitoring and enforcement; and (3) Ineffective enforcement at the site and landscape level. A detailed breakdown of these barriers is provided in Annex 13.

- Consistency with national priorities: Indonesia is a member of multilateral agreements on biodiversity conservation including CBD, CITES, the Ramsar Convention on Wetlands and CMS agreements on sharks, dugong, marine turtles and Albatrosses and Petrels (ACAP). The CBD (enacted through Law 5/1999), is expanded in the Indonesian Biodiversity Strategy and Action Plan (IBSAP) 2003-2020 (BAPPENAS 2003). The IBSAP is stated in Medium Term National Development Planning (2004-2009), Presidential Regulation (7/2005), the 6th National Development Target of Environment Conservation and sustainable use of biodiversity according to the IBSAP 2003-2020; and the Program on Protection and Conservation of Natural Resources, through the main activity: Management and Protection of biodiversity to avoid loss biodiversity (terrestrial, marine and coastal).

- The project also addresses objectives and activities under the National Strategy and Action Plan for Sumatran Tiger, Rhino, Orangutan and Asian Elephant (MoEF: P42/Menhut-II/2007, P44/Menhut-II/2007, P43/Menhut-II/2007, P53/Menhut-II/2007) and human-wildlife conflict (P48/Menhut-II/2008), as well as Indonesian commitments under the Convention on International Trade in Endangered Species (CITES; enacted through Presidential Decision 43/1978) through strengthening controls on the illegal wildlife trade.

- The Government of Indonesia signed the St. Petersburg Declaration on Tiger Conservation as adopted by the range states at the Global Tiger Summit in November 2010. This complements the MoEF’s own NTRP, part of the Global Tiger Recovery Program for which the GEF has a financial supporting role.

- In terms of overall national development context, Indonesia’s National Long-Term Development Plan (2005-2025) aims to achieve a “green and ever-lasting Indonesia”.  The vision and mission of the plan is to establish a country that is developed and self-reliant, just and democratic, and peaceful and united, to achieve the development goals as mandated in the Preamble to the Constitution of 1945.

- The project intervention will also contribute directly towards the achievement of key performance indicators for the Implementing Partner, the DG of Law Enforcement on Environment and Forestry (Gakkum), as follows:

| No | Target | Key Performance Indicator | National Target (2015 – 2019) |
| --- | --- | --- | --- |
| 1 | Increased effectiveness on handling and settlement of criminal case on environment and forestry. | Percentage settlement of criminal case with P 21 | 75% from all cases on one year. |
|  |  | Number of verified criminal case on environment and forestry | 200 cases per year |
|  |  | Percentage of handled evidences are in accordance to the number of handled cases | 100% |
|  |  | Number of government staff who are trained and increased their capacity. | 500 staff per year |
| 2 | Forest protection and surveillance on violence and threat in forestry related matters in 34 provinces are undertaken (77 locations particularly at 15 priority watershed areas) | Number of locations where forest protection and surveillance on violence and threat in forestry related matters are undertaken through socialization, patrols and operations. | 77 locations per year |
|  |  | Number of empowered and trained forest rangers (increased capacities) | 2500 personnel/ year |
|  |  | Number of empowered community-based forest rangers (Masyarakat Mitra Polhut/MMP) and forest security officers (Tenaga Pengamanan Hutan Lainnya/TPHL) and other environmental activists. | 34 Unit MMP/TPHL/CSO/ Partner per year |
|  |  | Number of available infrastructure for forest monitoring, surveillance, and law enforcement to meet minimum requirement standard. | 11 Brigade per year |
|  |  | Extent of forest area protected from illegal activities annually | 2015: 3 mil Ha 2016: 5 mil Ha 2017: 8 mil Ha 2018: 11 mil Ha 2019: 13 mil Ha |

- SDGs and Aichi Targets: This project will directly contribute towards the following SDGs: 14 (Life below water), 15 (Life on land) and 16 (Peace, justice and strong institutions). It will also contribute towards 8 (Decent work and economic growth) and 17 (Partnerships for the goals). The project will contribute towards Strategic Goal C of the Aichi Targets: To improve the status of biodiversity by safeguarding ecosystems, species and genetic diversity, specifically Target 12 (By 2020 the extinction of known threatened species has been prevented and their conservation status, particularly of those most in decline, has been improved and sustained).

Figure 1. Conceptual model of the factors influencing the project targets, with project interventions.

Key: Project Targets (green oval), direct factors (pink box), indirect factors (orange box), project intervention strategies (yellow hexagon)

# Strategy

- The project Objective is to reduce the volume of unsustainable wildlife trade and the rate of loss of globally significant biodiversity in Indonesia and East and South-East Asia. To achieve this objective the project will utilize 4 general strategies (Project Components) with intervention pathways described in the theory of change diagram in Figure 2 below. The Components (as the GEF project alternative) aims to remove the barriers to accomplishing the long-term solution (see Fig. 1, Section II, and Annex 13), namely to conserve key wildlife species in Indonesia, by ensuring that the legal wildlife trade is ecologically and economically sustainable, while reducing the scale and impact of illegal wildlife trafficking, both from Indonesia and in transit through the country. The proposed Components are described below:

- Component 1: Effective national framework for managing wildlife trade. This component aims to enhance the legal and policy environment by creating subsidiary regulations and removing loopholes and inconsistencies that prevent enforcement of measures to combat illegal wildlife trade. Appropriate institutional frameworks will be put in place to ensure inter-agency coordination domestically and internationally. The feasibility of a cost recovery system from regulation of wildlife trade will be determined. The project will support establishment of the National Wildlife Crime Taskforce, involving the Indonesian National Police, MoEF and Attorney General’s Office.

- Component 2: Institutional capacity for implementation and enforcement at the national and international levels. Under this component, the project will support key law enforcement institutions to ensure that institutional capacity, including development of tools to support for continued effective actions for combatting illegal wildlife trade. Here, a national information system will be established to accurately track and share IWT information, including intelligence data across sectors. Increased capacity will be gauged using the ICCWC Indicator Framework related to wildlife trade control, increased rate of inspections, seizures, arrests and successful prosecution of wildlife crime cases. Increased and more effective enforcement cooperation between Indonesia and other key states along the wildlife trafficking value chain (e.g. Vietnam and China) is expected, leading to multiple arrests and convictions, disrupting and dismantling significant wildlife crime syndicates.

- Component 3: Scaling-up improved enforcement strategy at key trade ports and connected ecosystems. This component will focus on scaling-up of on-the-ground implementation of improved enforcement capacity and strategies supported under component 1 and 2, including the Wildlife Crime Unit (WCU) approach for two subnational demonstration regions – northern Sumatra (in North Sumatra and Aceh provinces) centered on the Leuser ecosystem; and northern Sulawesi (in Gorontalo and North Sulawesi provinces), centered on the Bogani Nani Wartabone ecosystem. Both are major IWT hubs for domestic and international markets and contain seaports and airports that facilitate this trade. The project will support coordinated intelligence analysis to determine wildlife trade chains across these regions, including source areas, markets and ports, joint enforcement operations, and community awareness raising, engagement in information networks, and livelihood support in source areas. The project will also support systematic assessment and capacity building for five key wildlife trade ports: Jakarta (Tanjung Priok) and Surabaya (Tanjung Perak) ports in Java, Bitung (Sulawesi), and Belawan port and Kualanamu airport in Medan, North Sumatra (see Figure 3 for locations, Table 5 for summary information and Annexes 11 and 17 for details).

- Component 4: Knowledge Management, Monitoring and Evaluation and Gender Mainstreaming. The fourth project component closely links with and underpins the other three, by supporting the sharing of knowledge, experiences and lessons learned through project implementation with project stakeholders, the wider public in Indonesia, and also globally through the UNDP/WB/GEF Global Wildlife Programme.

- Indicators and assumptions for the accomplishment of expected Outcomes under proposed Components are given in the Project Results Framework, and the assumptions indicated in the theory of change diagram (Figure 2) are also described below.

- Significantly, this project is part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and falls under the GEF Programme Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (GWP) (9071). Under this programmatic framework, with the coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured. This includes significant potential for coordination with the Ports of Excellence project in assessing performance and building capacity at the demonstration ports in Indonesia, and subsequent upscaling. The project components will contribute towards the GWP Outcomes as follows:

| Child Project Components | Relevant GWP Components | Relevant GWP Outcome | Relevant GWP GEF Indicators and Targets |
| --- | --- | --- | --- |
| 1. Effective national framework for managing wildlife trade | Component 2. Reduce Wildlife Trafficking | Outcome 4: Enhanced institutional capacity to fight trans-national organized wildlife crime by supporting initiatives that target enforcement along the entire illegal supply chain of threatened wildlife and products | 4.1: Increase in number of dedicated wildlife law enforcement coordination mechanisms at program sites 4.2: Increase in number of multi-disciplinary and/or multi-jurisdictional intelligence-led enforcement operations at program sites 4.3: Increase in the proportion of seizures that result in arrests, prosecutions, and convictions |
| 2. Institutional capacity for implementation and enforcement at the national and international levels | Component 2. Reduce Wildlife Trafficking | Outcome 4: Enhanced institutional capacity to fight trans-national organized wildlife crime by supporting initiatives that target enforcement along the entire illegal supply chain of threatened wildlife and products | 4.3: Increase in the proportion of seizures that result in arrests, prosecutions, and convictions |
| 3. Scaling-up improved enforcement strategy at key trade ports and ecosystems | Component 1. Reduce Poaching and Improve Community Benefits and management Component 2. Reduce Wildlife Trafficking | Outcome 1: Reduction in elephants, rhinos, and big cat poaching rates. Increase in detection/interception of poaching incidents and arrests Outcome 2: Increased community engagement to live with, manage, and benefit from wildlife Outcome 4: Enhanced institutional capacity to fight trans-national organized wildlife crime by supporting initiatives that target enforcement along the entire illegal supply chain of threatened wildlife and products Outcome 5: Reduction of demand from key consumer countries | 1.1: Reduction in poaching rates of target species at program sites. 1.2: Number of poaching-related arrests (increase at first, then decrease over time) 1.3: Number of investigations/patrols at program sites that result in poaching-related arrests (increase at first, then decrease over time) 1.4: Increase in the proportion of poaching-related arrests that result in prosecution 1.6: Increase in law enforcement effectiveness score for program sites 2.1: Benefits received by communities from sustainable (community-based) natural resource management activities and enterprises (increase) 2.2: Human-wildlife conflict (HWC) as measured by incident reports (decrease) 4.1: Increase in number of dedicated wildlife law enforcement coordination mechanisms at program sites 4.2: Increase in number of multi-disciplinary and/or multi-jurisdictional intelligence-led enforcement operations at program sites 4.3: Increase in the proportion of seizures that result in arrests, prosecutions, and convictions 5.1: Measurable positive change in knowledge, attitudes, and practice (KAP) towards consumption of illegal wildlife products (compared to baseline) 5.2: Increased number of awareness campaigns for target groups to educate them on the negative impacts of illegal wildlife trade for global environment, security, and development 5.3: Reduction in the number of markets/shops/on-line retailers selling illegal wildlife products (disaggregated) compared to baseline |
| 4. Knowledge management, M&E and Gender Mainstreaming | Component 4. Knowledge, Policy Dialogue and Coordination | Outcome 6: Improved coordination among program stakeholders and other partners, including donors | 6.2: Program monitoring system successfully developed and deployed 6.3: Establishment of a knowledge exchange platform to support program stakeholders |

- This project will contribute towards the GWP target to maintain globally significant biodiversity and the ecosystem goods and services that it provides to society (25,096,730 ha) through its Component 3 interventions in the two demonstration subnational regions (northern Sumatra and northern Sulawesi) in Component 3 which will strengthen wildlife conservation and law enforcement to suppress illegal wildlife trade chains including source areas, markets and ports over regions totaling 8,978,875 ha. Within these regions, the area of targeted ports, markets and villages is c.45,000 ha. Overall, it will contribute significantly to the reduction of IWT pressures on wildlife populations throughout Indonesia.

- Component 1: By strengthening the legal and regulatory framework pertaining to illegal wildlife trade, Indonesia will block existing legal loopholes that allow CITES listed species to be received in or transit through Indonesia. This will be a major contribution towards controlling international trafficking of wildlife products from Africa to other Asian destinations (GWP Outcome 4). It will also strengthen protection over Indonesian species and increase penalties as a deterrent to poachers and traders using Indonesia as a source country for trade to other Asian nations (eg Vietnam and China) in particular.

- Component 2: By strengthening institutional capacity, inter-agency coordination, inter-agency information sharing, joint operations, and transnational cooperation, the project will support the strengthened legal and regulatory framework in Component 1 with much stronger and more effective intelligence based enforcement. This will act as an increased deterrent to criminals involved in the IWT and contribute significantly to global efforts (GWP Outcome 4).

- Component 3: By strengthening detection and enforcement processes at five key ports and the analysis and interception of trade chains across related demonstration regions, this component will significantly increase the interception of IWT in these regions and deter poachers and traders from using these areas (GWP Outcomes 1 and 4). This component will also support the engagement of communities in IWT source areas and along trade chains through awareness raising, voluntary and contracted assistance to government agencies, alternative livelihoods and mitigation of human-wildlife conflicts (GWP Outcomes 2 and 5).

- In addition, the project will pilot the PortMATE (Port Monitoring & Anti-Trafficking Evaluation) tool developed by and with support from the UNDP/GEF Ports of Excellence project (under the GEF Global Wildlife Programme). This will involve adapting and developing it for use during the assessment of the project demonstration ports. The PortMATE assessment focuses on six sections, namely Management and Administration, Information and Intelligence, Detection, National Investigations, International Cooperation and Criminal Justice. While Customs and Excise is the key government institution partner to be involved in the assessment, the tool has wider applicability and other relevant institution, such as Quarantine, INP and Gakkum, should also participate. Following baseline assessments at the other ports, a review will be conducted to determine the use and usefulness of PortMATE and its potential for replication across Indonesia.  Building on the baseline assessments at each port, the project will support capacity-building programs covering both systems enhancement to improve customs surveillance and training to build staff skills in wildlife law enforcement. The four ports will be invited to participate in joint training on controlled deliveries, strengthening South-South cooperation in combating wildlife crime. The ports will be the first to participate in the innovative Ports of Excellence best practice scheme and network that will be developed by the global UNDP-GEF project.

- The Government of Indonesia will participate in the Ports of Excellence project under the UNDP implemented maritime trafficking component of the GWP coordination project through the inclusion of Tanjung Perak as a key port. This would allow for Tanjung Perak (Surabaya) to become a founding member of the Ports of Excellence network and consequently one of the first ports to strive towards achieving the ‘Port of Excellence’ best practice standard and associated global recognition.  Accordingly, a higher level of intervention is intended for Surabaya port, to be based on a more detailed assessment followed by substantial support for capacity building and monitoring. Importantly, these activities will not only help combat wildlife trafficking, but will increase the efficiency and effectiveness of customs clearance processes through the use of cutting-edge technology that drastically reduces clearance time while simultaneously targeting screening of high-risk containers and improved detection techniques. The support is envisaged to include the installation of a paperless container processing system and a world-leading fully-automated risk analysis engine. These actions should lead to lower operational costs through increased efficiency and reduction in administrative workload, a higher rate of seizures and increased trade resulting from enhanced port operations. In combination, they offer the potential of significantly increased customs revenue.

- Component 4: (on knowledge management, M&E and gender mainstreaming) closely links with and underpins the other three, by supporting the sharing of knowledge, experiences and lessons learned through project implementation with project stakeholders, the wider public in Indonesia, and also globally through the GEF Global Wildlife Programme. This project forms part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and falls under the GEF Programme Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (9071). Under this programmatic framework, with the coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured (contributing to GWP Outcome 6).

- Particularly innovative aspects of this project include scaling-up the Wildlife Crime Unit (WCU) approach and the development of cost recovery mechanisms. The WCU is already one of the most successful approaches to combat illegal wildlife trafficking in Southeast Asia, albeit on a modest scale currently, and key to the success is the partnership of Indonesian law enforcement agencies (MoEF, INP, MMAF, AGO, PPATK, etc.) working together to combat wildlife crimes. Scaling-up this innovative approach has huge potential to serve as a model for other countries in the region. The project will also test cost-recovery mechanisms from illegal trade seizures using money laundering legislation and from legal trade through fiscal regulations to ensure trade is taxed at a level commensurate with the cost of regulating it. These types of approaches have been often discussed with respect to wildlife trade, but have never been trialled in the region.

- Global Environmental Benefits: Indonesia is one of the most biodiverse regions in the world, and supports many mammal and bird species including endemic and endangered species threatened by illegal wildlife trade such as Sumatran tiger, Sumatran and Javan rhinoceros, Bornean and Sumatran orang-utan, Asian elephant, Sunda pangolin, anoa, babirusa, helmeted hornbill, yellow-crested cockatoo and other parrot family species.  The country is located in the biodiversity distribution path of the Asian continent (Java, Sumatra and Kalimantan islands) and Australia (Papua), and is in the transitional zone of the Wallace line (Sulawesi, Maluku and Nusa Tenggara islands), and therefore harbours the biological richness of Asia, Australia and the transitional zone of the two continents. GEF funding will secure populations of globally significant species through dramatically improving the systemic and institutional capacity of the nation to control legal commercial and illegal wildlife trade and associated overexploitation of species. In addition, the GEF finance will significantly reduce the role of Indonesia as a transit and destination country in transnational wildlife trafficking networks, such as for African Ivory.

- National Socio-economic Benefits: In line with the global GEF Program on IWT, this project focuses on disrupting wildlife crime trade routes, especially focusing on the supply and trafficking aspects. In combination with coordinated efforts in other countries, this project’s outcomes will have immediate and longer term socio-economic benefits for local communities, local and national revenues, and international trade. Combating wildlife crime saves species but it also curbs corruption. This directly benefits local people disadvantaged by the wide range of corrupt practices that forestall development and progress. Moreover, combating wildlife crime reduces insecurity and crime in rural areas and strengthens the infrastructure for effective law enforcement that can address both wildlife crime and other crimes that affect rural communities. It will also ensure that species and their habitats are better managed and more resilient, thus creating the conditions for communities to continue to use natural resources as a socio-economic safety net, particularly as climate change uncertainty exacerbates risks to their economic and physical security.

- Local and national economies benefit in two ways: first, increased revenues from legal trade in natural resources are assured as the risk of contraband entering trade chains is reduced, and legal businesses that benefit from reduced corruption and a better and safer business environment, can provide improved tax revenues. Governments and communities can also legally exploit natural resources in a sustainable way rather than suffer the consequences of foregone opportunity as they are depleted and destroyed. International trade benefits from removing illegal contraband from trade flows, which in turn reduces the cost of surveillance and detection. Removing contraband also speeds up trade flows and reduces the risk of shipments being seized or stopped at borders when legal goods as well as contraband can be held up indefinitely.

- At the local level, tangible socioeconomic benefits will be delivered to rural communities in targeted wildlife trade source areas within the demonstration regions, through better managing wildlife and fishery resources, addressing conflicts with wildlife, and indirectly the protection of forests and marine resources in the demonstration regions and the ecosystem services that they provide. The project will provide benefits to these local communities through capacity building, trainings, employment opportunities, revenue and income, etc. These benefits will be generated at the local and community level from wildlife management, sustainable livelihoods and economic development (i.e. tourism and other natural resources management and conservation activities).

- While the above-mentioned socio-economic benefits will undoubtedly apply, there remains a need for economic studies to quantify the actual losses to national and local economies associated with illegal wildlife trade, and the actual benefits that would accrue through legally regulated sustainable trade. This project includes such an economic assessment to quantify the value of legal and illegal wildlife trade including externalities and opportunity costs, as well as the economics of enforcement to provide a disincentive to malpractice and guidance for more effective resource allocation.

- In the component addressing the demonstration regions, gender will be a significant consideration for the successful implementation of a range of activities. Indonesia has a relatively good record at empowering women compared to some countries, but significant barriers to progress still remain. The importance of gender equality will therefore be addressed specifically when management organization is addressed for demonstration region interventions. Gender will also be important during the participation of communities in sustainable / alternative livelihood development including income generating schemes for rural households, firstly because women have different connections and dependencies on their environment to men, influencing the range of development and conservation options they would find beneficial, and secondly because female engagement in implementation is likely to be important for the success of development projects. Overall, the project will seek to establish or strengthen stakeholder participation mechanisms in order to achieve legally recognized, sustainable management of wildlife and fishery products.

Figure 2. Theory of Change Diagram for the Project (above)

Table 1. Assumptions for Theory of Change Diagram

| Code in Fig. 2 | Assumption | Notes and References |
| --- | --- | --- |
| A1 | There is sufficient political will to support revision of key policies, laws and regulations | Progress is already being made towards revising the Conservation Act UU5/1990 and the Protected Species List GR7/1999 through a collaborative review process, which this project will support and inform. See baseline policy assessment by IPB (2016a) and WCS 2015b. |
| A2 | There exists willingness to cooperate between the relevant law enforcement agencies | There are examples of existing collaboration, including the highly successful Wildlife Crime Unit (WCU) established in 2003 and operated by WCS in collaboration with a range of Indonesian government agencies, which this project will upscale. See WCS 2015a. |
| A3 | Provincial and district government agencies and port authorities are motivated to improve monitoring and enforcement of unsustainable and illegal wildlife trade | There are examples of collaborative efforts in Sumatra, including joint patrolling and human wildlife conflict response teams. The WCU has conducted successful sting operations at certain ports in recent years, resulting in successful convictions of illegal wildlife traders. See WCS 2015c, 2015d, IPB 2016c. |
| A4 | Stakeholders responsible for hosting the information system, providing data and information and making use of the information are willing to collaborate and share information and resources openly. | Focus Group Discussion held during the PPG in March 2016 with all relevant stakeholders indicated high interest in collaboration on wildlife enforcement and in sharing data and information (IPB 2016b). The WCU has also made use of information from different agencies to inform its operations. However, such data sharing is currently patchy and unstructured. |
| A5 | Demand from the unsustainable legal and illegal wildlife trade is a key driver for poaching activities | Challender et al. 2016; Bennett 2015; WCS 2015a, Nijman et al. 2012; Lyons et al. 2013, etc. |
| A6 | Poaching is in reality a major negative factor impacting populations of globally threatened species in Indonesia | See WCS 2015a for profiles of key species in wildlife trade in Indonesia; see IUCN Red List for key endangered species impacted by poaching and illegal trade. |

References for Assumptions in Table 1

Bennett E.L. 2015. Legal ivory trade in a corrupt world and its impact on African elephant populations. Conservation Biology 29.1 (2015): 54-60.

Challender et al. 2016. On scaling up pangolin conservation. TRAFFIC Bull. 28(1)19-21.

IUCN Red List. http://www.iucnredlist.org/

Lyons, J. A., D. J. D. Natusch, and C. R. Shepherd. 2013. The harvest of freshwater turtles (Chelidae) from Papua, Indonesia, for the international pet trade. Oryx 47:298–302.

IPB 2016a. Review of the policy, legal and institutional framework for wildlife trade in Indonesia.  Faculty of Forestry, Bogor Agricultural University. Unpublished report to UNDP.

IPB 2016b. Analysis of information-sharing and database systems relating to wildlife trade in Indonesia. Faculty of Forestry, Bogor Agricultural University. Unpublished report to UNDP.

IPB 2016c. Identification of specific trade ports or markets for the intervention and profiling. Faculty of Forestry, Bogor Agricultural University. Unpublished report to UNDP.

Nijman, V., C. R. Shepherd, Mumpuni, and K. L. Sanders. 2012. Over-exploitation and illegal trade of reptiles in Indonesia. Herpetological Journal 22:83–89.

WCS 2015a. Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  Report to USAID. http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

WCS 2015b. Changes for Justice Project - Wildlife Trade, Wildlife Crimes and Species Protection In Indonesia: Policy and Legal Context. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  Report to USAID.

WCS 2015c. Traders of One of Indonesia’s Most Hunted Bird Species Arrested.

https://newsroom.wcs.org/News-Releases/articleType/ArticleView/articleId/6830/Traders-of-One-of-Indonesias-Most-Hunted-Bird-Species-Arrested.aspx

WCS 2015d. Major Illegal Tiger Skin Trader Arrested in Indonesia

https://newsroom.wcs.org/News-Releases/articleType/ArticleView/articleId/8389/Major-Illegal-Tiger-Skin-Trader-Arrested-in-Indonesia.aspx

Figure 3. Map showing project demonstration regions and ports (Source: WCS).

Note: Demonstration ports are shown in red text

# Results and Partnerships

- Expected results (see Fig. 4)

- The project is designed to achieve the following Long-Term Impact or GEB: populations of threatened wildlife in Indonesia are stable or increasing. While this project will have a broad impact across the country through its integrated approach, specific benefits are anticipated for targeted threatened wildlife populations in its two demonstration sub-regions. These include 10% population increases from 2015-2019 for: Sumatran Tiger (baseline of 0.53 tigers/100km2); Sumatran Elephant (baseline of 490-520 individuals); and Sumatran Rhinoceros (baseline of 38 individuals). The project will also target highly threatened and endemic wildlife in northern Sulawesi including Babirusa, Anoa and Black-crested Macaque for which baseline population estimates are not currently available.

- The Long-Term Impact will be achieved through reduction of poaching as the key direct threat for wildlife (Mid-Term Impact). This includes a 40% reduction in poaching of Sumatran Tiger (baseline of 5 poached) and Sumatran Elephant (7 poached), 100% reduction in poaching of Sumatran Rhinoceros (1 poached); and 40% decrease for Anoa (10 poached), Babirusa (12) and Black-crested macaque (TBC).

- Reduction of poaching will be possible via achievement of the following project Objective Outcomes:

- Increased number of inspections/patrols, seizures, arrests and prosecutions of illegal wildlife traders and poachers (>25% increase in seizures/arrests from baseline and >75% cases prosecuted – over baseline of: From mid-2015 to mid-2106: The WCU facilitated law enforcement operations for 31 cases with 55 people arrested and taken to court. Of those with a known outcome, 41 were prosecuted (100% prosecution). This is for terrestrial species in Sumatra and Java).

- Reduced Unsustainable Wildlife Trade, indicated by a stable/declining trend over baseline of 4666 wild animals seized from 34 protected species (DG Law enforcement, 2016)

- Increased number of local people benefiting from wildlife conservation. At least 2100 government staff improved knowledge on IWT (1050m/1050f); and at least 600 local people in project demonstration areas benefit directly from project intervention (300m/300f).

- The GEF funding requested by the MoEF will be used to achieve the Objective Outcomes through achievement of four integrated and complementary Outcomes:

Outcome 1: Strengthened national policy, legal and institutional framework for regulating legal commercial wildlife trade and combating illegal wildlife trade.

Accordingly, the following key legislation gaps will be addressed by improved IWT legislation documents approved by Government:

- Minimum fines and sentences increased to provide deterrent effect

- Non-native endangered species including elephant, rhinoceros, big cat and pangolin species given legal protection

- Indonesian protected species list updated to include all CITES Appendix 1 and globally threatened species

- Authority of forestry civil investigators improved

- Detention/prison evaluation for creating deterrent effect and rehabilitation for criminals

- Online trade regulation to address online wildlife trafficking.

Two policy (UU5 – Biodiversity Conservation Act, PP7 – Protected Species List) revisions legalised; 3 other policy revisions finalised and undergoing final legalisation process.

Support provided for CITES implementation, permitting process/listed species, and regulatory mechanisms (CITES technical training and piloting CITES e-permits).

In addition, an inter-agency taskforce will be put in place to increase coordination and cooperation amongst relevant agencies in their counter-IWT actions.

Outcome 2: Strengthened institutional capacity for regulatory coordination, implementation and enforcement at the national and international levels.

UNDP Capacity Score for law enforcement agency Gakkum (see Annex 18) increased from 60% to 80%.

Official national statistics on seizures/arrests and prosecutions will show a >25% increase in seizures/arrests from baseline and >75% cases prosecuted.

At least three joined up transnational counter-IWT operations will be conducted by the end of the project, reflected by an increased annual number of seizures as a result of these operations.

A Gakkum information system is fully operational to provide intelligence/cybercrime analyses, operated by trained staff, covering all IWT priority species and supported by protocols for information sharing; with technical expertise provided from the WCS-WCU.

Training materials accredited by at least 5 agencies (DG Law Enforcement, INP, AGO, MMAF, Customs, Aviation/Ports authorities, quarantine); At least 200 enforcement staff including judges with improved knowledge on IWT.

At least 2 training courses run for Gakkum on forensic analysis techniques (including securing crime scene, DNA sampling, etc).

Strengthened national implementation of CITES; at least 3 agreements concerning IWT established on bilateral collaboration with key countries and under implementation.

Outcome 3: Improved enforcement strategy demonstrated and scaled up at key trade ports and connected subnational regions with key ecosystems

Increased enforcement effectiveness at 5 key trade ports indicated by a 50% increase in PortMATE assessment tool scores (average score for KSDA, Customs, Port Management Authority at each port).

Effective enforcement of two sub-national regions known to include significant wildlife trade routes, measured by: 25% increase in the annual number of IWT seizures, IWT investigations leading to arrests and successful IWT prosecutions at the project sites.

Gakkum (as a new agency) supported to establish/expand in northern Sumatra and northern Sulawesi demonstration regions.

Increased engagement of local communities in patrolling, market surveillance, local informant networks and HWC reduction, in collaboration with ongoing activities (including GEF Tigers and EPASS projects).

Increased coordination of information through CID, customs, quarantine, immigration, anti-corruption agency and other information systems to combat IWT.

Clear reporting and feedback system established between the sub-national and national level agencies.

Outcome 4: Implementation and upscaling/replication of project approaches at national and international levels is supported by effective knowledge management and gender mainstreaming

At least 5 project lessons used by other national and international projects.

At least 10 national and international organizations participate in the project M&E and adaptive management.

Gender is systematically incorporated into project implementation and M&E according to the project gender mainstreaming strategy.

- The outputs (the project’s products and services) suggested to achieve the Outcomes are described below:

Component 1: Effective national framework for managing wildlife trade.

Total Cost: US$3,048,000; GEF project grant requested: US$1,048,000; Co-financing: US$2,000,000

Outcome 1: Strengthened national policy, legal and institutional framework for regulating legal commercial wildlife trade and combating illegal wildlife trade.

Output 1.1: Amendments and drafts for policies, legislation, regulations and procedures to reduce illegal wildlife trade and improve implementation of CITES in Indonesia are developed and legal adoption processes supported

- Despite a comprehensive framework of laws and subsidiary regulations designed to halt the loss of wildlife to poaching and trafficking, a number of legal loopholes and inconsistencies in rules and practice allow poachers, traders, shippers and buyers of illegal wildlife to evade investigation, arrest and prosecution in Indonesia. A baseline report has been prepared identifying the key weaknesses in the current legal and regulatory framework on wildlife crime in Indonesia (see Annex 15). Key recommendations include the reform of PP7/1999; establishing MMAF as a CITES management authority with necessary implementation regulations that are CITES compliant; reform of UU5/1990 to incorporate the current CITES listed species and stiffen fines and penalties; ensure non-native CITES-listed species are subject to the same legal controls as native species; and mandating conservation measures for protected species outside of conservation areas.

- The MoEF and LIPI, with technical support from WCS, are building upon the findings of this report through updating and amending PP7/1999 and UU5/1990, which includes, for example, stiffer fines and penalties for wildlife crimes. The GEF project has been designed to fully complement these ongoing efforts by facilitating ongoing dialogue through focus group discussions (FGDs) and workshops, engaging with parliament, and supporting subsequent revisions to policy drafts until they reach completion. In parallel, high-quality research that identifies gaps, weaknesses, needs and makes feasible recommendations for revisions of other policies is currently being conducted. The results will be presented in academic policy papers and disseminated and discussed through FGDs and workshops. Thus, in the GEF project, it is envisioned that it will support these efforts through creating expert working groups (POKJA) that partner with key government institutions that discussing and then call for the issuance of a new Ministerial Decrees or other policy reforms, with appropriate technical support provided thereafter. Building on the reforms to PP7/1999, the project will provide MoEF, as the CITES management authority, and likely MMAF, as the intended CITES authority for marine species, with policy studies on Indonesian species being traded at unsustainable levels and therefore in need of stronger CITES regulation and emerging opportunities such as introducing CITES e-permitting as a means of reducing fraudulent documentation and improving administrative efficiency. A successful example exists in the Government of Indonesia’s proposal to list helmeted hornbill as an Appendix I species, which was ratified at COP17. Indicative activities under Output 1.1 include:

- Conduct workshops and follow up discussions on policy revisions, such as,

  - Confirmation of policy, legislative and regulatory needs for key partner agencies through a national workshop

  - Finalization of new/revised Act to replace UU5/1990 and its derivatives (PP7/99, PP8/99, which are associated with wildlife trade) changes to the draft policy (identification of names of species)

  - Protection of non-native species

- Support CITES implementation, permitting process/listed species, and regulatory mechanisms (CITES technical training and piloting CITES e-permits).

Output 1.2: Proposal for a National Wildlife Crime Taskforce for improved collaboration amongst responsible agencies is developed and operationalized during the project

- To improve intersectoral coordination and cooperation at the national level, the project will support the conceptualization, development and operation of an inter-agency National Wildlife Crime Taskforce. This will first involve a review of the organizational options for improving coordination across the range of national agencies involved in fighting wildlife crime, including MoEF (particularly Gakkum), MMAF, Police, Attorney General, Customs, PPATK, KPK. The Taskforce is intended to provide an interface between key government agencies and lead law enforcement actions, as necessary, to share information, interdict and prosecute major illegal wildlife traders and others who operate across provincial and national boundaries where capacity and safety of forest officers and police officers is in question at a landscape level. Once the Taskforce has been established it will hold regular meetings between the key partners to monitor progress against the strategy’s targets and to refine the strategy, as needed. The Taskforce will also be able to provide direct support to the priority landscapes of Leuser and northern Sulawesi, as well as the target ports (in Outcome 3). Indicative activities under Output 1.2 include:

- Develop proposal for a National Wildlife Crime Taskforce, facilitate its establishment and develop national multi-agency strategy for tackling IWT, with phases as follows,

1. Preparation of proposals - meetings, drafting agreement and SOP (including development of inter-agency agreements for information sharing)

2. Facilitate the establishment of a National Wildlife Crime Taskforce

3. Taskforce develops a national (multi-agency) strategy for tackling IWT

4. Capacity building (including workshops on data collection, management and data sharing, procedures).

Output 1.3: Economic assessments conducted to quantify the value of legal and illegal wildlife trade and its impacts on the national economy and to assess the feasibility of cost-recovery mechanisms

- This output represents action to follow up on an important gap in Indonesian policy towards addressing IWT. There are two parts to this output: i) providing evidence that describes the annual economic loss to the GoI from wildlife trade, either through poor management of the legal trade or the loss of protected species and their habitat and the wider impacts that this can have, e.g. loss of ecosystem services; and, ii) investigating whether these values can be used as a reference point in the prosecution of IWT cases, just as fraud cases are linked to economic losses with those convicted having assets seized to the value of the estimated loss. For IWT, this might include seizing a fishing boat used for catching protected species (e.g. manta rays for their gill-rakers) or wildlife trafficking, which would then become the property of the state. At the moment the assets remain the property of the individual, reducing the disincentives to wildlife crime and enabling criminals to carry on once they are out of jail. The policy reform work in Output 1.1 would explore options for cost recovery from successful prosecutions and confiscations that would allow for revenue generated from asset seizures or fines to be invested back into law enforcement.

- The IWT inflicts significant costs on the environment and on society. While these costs are often conceptualised in terms of non-monetary impacts on biodiversity, they can also be quantified and valued.  These include the market values of wildlife, which are particularly notable for high-value species that play important roles in the broader economy, such as for fisheries and timber, where IWT compromises sustainable harvest opportunities and tax revenues. There may also be costs associated with cultural losses to society and with reintroduction or increased conservation efforts, such as additional monitoring and enforcement. Despite these impacts, the true costs of damage are rarely experienced by the perpetrators of IWT. Even when caught and prosecuted, illegal harvesters, intermediaries, vendors and consumers are more often targeted with small fines and jail sentences - even in cases that involve large-scale commercial IWT and egregious environmental harm. Thus, activities in this output will explore ways in which damages from IWT can and/or are measured and used in legal liability suits in Indonesia, particularly in cases common to the highly prized wildlife species prioritized in this project. Once the cost has been quantified, the project will review the mechanisms currently in place that would enable recovery of the loss, including possible modifications, or suggest alternative mechanism to achieve this. Indicative activities under Output 1.3 include:

- Conduct an economic assessment to quantify the value of legal and IWT, loss to national economy, related issues

- Conduct a feasibility study on cost-recovery mechanisms to enable IWT seizures/confiscations etc to support enforcement activities, especially in landscapes

- Consider whether action is needed to follow up on / operationalize these studies.

Component 2: Institutional capacity for implementation and enforcement at the national and international levels

Total Cost: US$12,212,000; GEF project grant requested: US$2,212,000; Co-financing: US$10,000,000

Outcome 2: Strengthened institutional capacity for regulatory coordination, implementation and enforcement at the national and international levels

Output 2.1: Strengthened capacity of Gakkum to tackle IWT

- The WCS Indonesia Program established the WCU in 2003, as part of an innovative partnership designed to combat illegal wildlife trade in Indonesia. The partner base is both strong and diverse including MoEF, MMAF, INP, Attorney General, Customs and excise; PPTAK; civil society and media organisations. Over 290 cases have been prosecuted by law enforcement agencies based upon information from the WCU, including the 10 largest wildlife crime cases in Indonesia, with a success rate of >85%. This is unparalleled in the Southeast Asian context, and the WCU is the most successful example of an approach to combat illegal wildlife crime in the region. In this project, WCS will provide technical assistance to Gakkum and scale-up lessons learned from 10 years of operating the WCU, to address the systemic institutional and capacity barriers that limit effective national-level action on illegal wildlife trade in Indonesia and the region. Under this Output, this will include strengthening Gakkum’s capacity at the national level, including the ongoing development of i2 criminal network mapping and analyses, tackling online trade, and developing high-quality briefing papers. The project would provide the expertise to support Gakkum in establishing its own i2 system because at present strategic planning is not based on reliable intelligence data which limits the effectiveness of subsequent law enforcement operations. This means that the intended targets may not be the most cost-effective ones to invest limited resources in. The i2 system has been demonstrated to address these issues because it maps criminal networks and identifies the central nodes (key actors within the network) to then target for greatest impact on the network.

- To tackle online IWT, the INP’s Cybercrime Division, the WCU and social networking companies, such as Facebook, whose networking platforms are being used by online wildlife traders have begun working together. Despite being still in its infancy, there is a high willingness and commitment by these organisations to work together to identify, monitor and intercept illegal online traders through tracking key words/phrases, testing search algorithms, shutting down errant accounts and arresting illegal traders. In 2016, the Facebook (FB) Head, Trust & Safety for the Asia-Pacific region met with the Indonesian National Police to discuss procedures for reporting illegal material being advertised on FB and separately with WCS to discuss addressing IWT issues. The GEF project would advance these discussions by developing a partnership with FB to tackle IWT in Indonesia. Both of these themes could form part of the GoI’s commitment as stated in the Hanoi Statement on IWT (see more detailed description in Output 2.1). Here, the GoI committed to strengthen institutional and personal capacity to monitor and detect illegal wildlife trafficking by investing in developing and establishing an analytical room for wildlife crimes, particularly for tackling cybercrime.

- The above actions will underpin and support the subnational strengthening of Gakkum’s approach that will be progressed in Output 3.2, which will greatly expand its scope and impact in northern Sumatra and northern Sulawesi. Indicative activities under Output 2.1 include:

- Provide technical assistance to strengthen Gakkum to operate in Sumatra, Java, and Wallacea region, with support from WCS-WCU

- Strengthen DG Gakkum’s national database; Support facilities/equipment for database management in an Operations Room; Provide training on database management to relevant officers; Initiate standardized data collection, with support from the WCS-WCU

- Technical assistance to Gakkum to analyse online marketing information to identify and intercept shipments and domestic trade, support provided by WCS-WCU

- Provide technical assistance to Gakkum to conduct research on wildlife trafficking, producing various peer-reviewed articles, with support from WCS-WCU.

Output 2.2: Training modules and standard operating procedures (SOPs) are developed for integration into government training programmes

- To have an impact, project monitoring and evaluation will feedback into government planning, and existing human resources and financial management practices will be improved towards incentive-based systems that promote motivation by rewarding success. The partnering institutions (in particular MoEF, INP and Customs and Excise) will be supported to identify and introduce appropriate incentive structures to improve staff performance and national/site-level institutional performance. Incentive mechanisms, such as accreditation or career points, for increasing the motivation of field staff will be considered. Overall, improvements in staff capacity here should lead to Key Performance Indicators set by national government being achieved, as well as the GEF targets.

- The project will significantly invest in capacity building of various government institutions to raise awareness of illegal wildlife trade as a serious crime, Indonesian law pertaining to this, the respective institutional mandates for tackling the trade and, ultimately, strengthen the government’s ability to achieve successful detections, arrests, prosecutions and deterrent sanctions. A training syllabus consisting of a set of thematic modules, tailored to each institution, will be developed. Incentive mechanisms, such as accreditation for career points, for increasing the motivation of field staff will be included. The formal adoption of the training syllabus will enable it to be included in annual work plans that are sustainably financed by government. Expert training will be supported by WCS, for which there are past successes with the police, MoEF, Attorney General and others. After this, a Training of Trainers course will be run for government institutions own trainers, who will then go on to run future training courses.

- In late 2016, a training needs assessment (TNA) was conducted for the relevant law enforcement agencies. The aim of the TNA was to identify gaps in the operationalization of regulations on wildlife crime. The TNA draws upon interviews with officials from the Director General of Customs and Excise, INP, Supreme Court, Attorney General’s Office (AGO), PPATK, Quarantine, Corruption Eradication Commission and Gakkum-MoEF. This supplements a desk review of regulations on wildlife, law enforcement and capacity building in each agency that was also conducted by WCS. These two sources of information have been used to determine the type of capacity building that is needed for each agency and how best to deliver it. In summary, this includes:

- Gakkum – i2 database, wildlife law and valuation on environmental damages.

- INP – evidence handling, wildlife forensics, i2 database, wildlife law (including online trading), and valuation on environmental damages.

- AGO - evidence handling, wildlife law (including online trading) and valuation on environmental damages.

- Customs - wildlife identification, evidence handling, coordination mechanism with Quarantine, MMAF and BKSDA on handling wildlife cases at seaports and airports.

- Supreme Court - evidence handling, wildlife law (including online trading), valuation on environmental damages and inserting these issues into pre-existing training modules.

- PPATK - i2 database on wildlife and valuation on environmental damages.

- Quarantine - evidence handling, coordination mechanism with Quarantine, MMAF and BKSDA on handling wildlife cases at airports.

- To support the training, WCS has recently finalised a technical agreement for capacity building of INP through its Police Education Agency (or Lembaga Pendidikan Kepolisian, LEMDIKPOL) and in 2017 will sign a training agreement with the Deputy Attorney General for General Crimes (or Jaksa Agung Muda Tindak Pidana Umum, JAM PIDUM) and Gakkum. Indicative activities under Output 2.2 include:

- Embed wildlife crime arrests/investigations within job descriptions and/or within performance criteria required for achieving promotion

- Develop training modules with various agencies (e.g. detection, species identification, investigators, prosecutors, international conventions/agreements)

- Deliver high quality training in priority topics.

Output 2.3 DG Law Enforcement and other key agencies are trained in wildlife forensics techniques and provided with necessary equipment and expert support

- The project will support the WCU to expand its national partner base to include the Eijkman Institute and TRACE Wildlife Forensics Network to support the Indonesian law enforcement agencies in forensic techniques. The TRACE Wildlife Forensics Network is an international NGO established in 2006 that aims to promote the use of forensic science in biodiversity conservation and the investigation of wildlife crime. TRACE undertakes research and development of new techniques as well as delivering training and capacity building in wildlife DNA forensics. It led the ASEAN-WEN Wildlife Forensics Project and has conducted training for Indonesian forensic scientists. Eijkman Institute is a non-profit, government funded research institute conducting basic research in medical molecular biology and biotechnology, located in Jakarta, with expertise in forensic science. For example, in 2015, a training program to build knowledge sharing and understanding of forensic techniques was held by the Eijkman Institute in collaboration with The Society of Indonesian Science Journalists (SISJ) in Jakarta. The Eijkman Institute is able to identify species from wildlife parts and products using genetic analyses, as part of forensic evidence gathering by government agencies involved in wildlife trade and crime. The training program’s objective was to provide updates on forensic techniques for species identification conducted by the Eijkman Institute in order to support the work of police and civil investigators. This is important for analyzing DNA samples from confiscated species to firstly determine whether it is protected under Indonesian law (so cases can therefore be prosecuted) and to track trends in species being traded, both native and exotic. Thus, training and capacity building will be provided for the relevant government institutions and a partnership developed and maintained to enable the rapid analysis or future DNA samples from wildlife. Indicative activities under Output 2.3 include:

- Preparation for improved investigator training in forensic analysis, in the following phases:

1. training needs assessment

2. training module/SOP design

3. TOT module/SOP

- Training for improved investigator training in forensic analysis (including securing crime scene, DNA sampling

- Collaboration with Eijkman Institute and litbang hut (FORDA) for technical support for laboratories.

Output 2.4: Drafts of International Agreements on IWT control are prepared; collaboration with international agencies is facilitated; participation of Indonesia representatives in ASEAN WEN and CITES is supported

- Regionally, mechanisms such as the ASEAN Wildlife Enforcement Network (WEN) and SA WEN, and intentionally, INTERPOL offer opportunities for collaboration in tackling illegal wildlife trade. The project will ensure that mutual legal assistance treaties are in place and organize annual meetings of frontline enforcement officers from Indonesia (especially Gakkum), Vietnam, and China to facilitate joint planning and intelligence-sharing. This is therefore intended to enhance regional collaborations between Government of Indonesia law enforcement agencies and other Southeast Asian nations (especially Vietnam, a prime destination for Indonesia’s wildlife) and international bodies (such as INTERPOL).

- Previous dialogue between the governments of Vietnam and Indonesia on wildlife law enforcement resulted in a memorandum of understanding (MOU) between the Vietnam Administration of Forestry and the Indonesian Directorate General of Forest Protection and Nature Conservation on cooperation in wildlife law enforcement (December 2012). The objective of the MOU is to promote the cooperation between two countries to eliminate the illicit trafficking of protected wildlife. The area of cooperation includes information sharing, capacity building, enforcement cooperation and awareness. This was followed by the formation of a joint Taskforce for combating transnational trade in pangolins and in 2013 by the signing of a mutual legal assistance treaty (MLAT) on criminal matters related to IWT, which was ratified in Indonesia through Law no. 13/2015. Most recently, representatives from the two government agencies held a side meeting at the Hanoi Conference on IWT (November 2016). Here, an informal lunch meeting between the Deputy Director of the CITES MA of Vietnam and Deputy Director of Forest Crime Prevention and Forest Security (Gakkum, MoEF) was organised to discuss preparations for a formal meeting to revisit the MoU and its implementation. The formal meeting was planned for 23 February 2017 in Hanoi, with the objective to revisit the MoU and promote cooperation on law enforcement to strengthen commitments to jointly dismantle wildlife trafficking networks. This forms part of the GoI commitment, as stated in the Hanoi Statement on IWT, to continue to strengthen law enforcement efforts through existing cooperation agreements with other countries which also aimed to reduce demand of IWT. The GEF funds will be used to support the development of technical briefings and situation analysis documented in preparation of government-to-government meetings. This may also include costs incurred for meetings held prior to the main one to disseminate document information and achieve consensus on a well-understood GoI position. The direct travel and meeting costs for GoI staff to attend official meetings would be covered by GoI co-financing for the project. Indicative activities under Output 2.4 include:

- Provide technical assistance to support the GoI in national agreements/initiatives related to IWT

- Provide technical assistance to support the GoI in participating in international agreements/initiatives related to IWT (international meetings - e.g. CITES, INTERPOL, ASEAN-WEN) and to establish and implement agreements for strengthened bilateral collaboration (Indonesia-China, Indonesia-Vietnam and Indonesia-US).

Output 2.5: Communication Strategy and social marketing campaigns to increase awareness on IWT are implemented at national and regional scales

- WCS will work with government partners to design and test social media campaigns that target a reduction in demand for a specific species, particularly ones that are threatened by domestic consumption (such as wild birds, sharks, babirusa, anoa and elephant). Any investment in demand management will focus on changing prevailing widespread social norms. For example, the common practice of keeping wild-caught birds for pets – rather than focusing on broad information and education campaigns, which do not promote widespread change in behaviors and norms associated with domestic consumption of illegal wildlife. Any such effort will include a credible method of monitoring and measuring the campaign’s impact. WCS programs in China and Vietnam have a lot of practical experience in running demand reduction campaigns and the project can learn from these and other initiatives, such as Save the Shark. Indicative activities under Output 2.5 include:

- Develop and implement project communications strategy to reduce IWT demand and update the strategy annually.

- Develop and support a systematic approach to increase media coverage of IWT cases

- Use social/online media to distribute IWT case information

- Support targeted awareness campaigns.

Component 3: Scaling-up improved enforcement strategy at key trade ports and connected ecosystems

Total Cost: US$32,121,500; GEF project grant requested: US$3,121,500; Co-financing: US$29,000,000

Outcome 3: Improved enforcement strategy demonstrated and scaled up at key trade ports and connected subnational regions with key ecosystems

Output 3.1: Capacity development supported at demonstration ports including training of key agency staff on CITES and IWT control with focused attention on Surabaya port

- The project will pilot the PortMATE (Port Monitoring & Anti-Trafficking Evaluation) tool developed by and with support from the UNDP/GEF Ports of Excellence project (UNDP portion of component 2 under PIMS 9211 Coordinate Action and Learning to Combat Wildlife Crime). This will involve adapting and developing it for use during the assessment of the project demonstration ports. The PortMATE assessment focuses on six sections, namely Management and Administration, Information and Intelligence, Detection, National Investigations, International Cooperation and Criminal Justice. While Customs and Excise is the key government institution partner to be involved in the assessment, the tool has wider applicability and other relevant institution, such as Quarantine, INP and Gakkum, should also participate. Following baseline assessments at the other ports, a review will be conducted to determine the use and usefulness of PortMATE and its potential for replication across Indonesia.

- Building on the baseline assessments at each port, the project will support capacity-building programs covering both systems enhancement to improve customs surveillance and training to build staff skills in wildlife law enforcement. The four ports will be invited to participate in joint training on controlled deliveries, strengthening South-South cooperation in combating wildlife crime. The ports will be the first to participate in the innovative Ports of Excellence best practice scheme and network that will be developed by the global UNDP-GEF project.

- The Government of Indonesia has been invited by UNDP to participate in the Ports of Excellence project through the inclusion of Tanjung Perak (Surabaya) as a key port. This would allow for Tanjung Perak to become a founding member of the Ports of Excellence network and consequently one of the first ports to strive towards achieving the ‘Port of Excellence’ best practice standard and associated global recognition.  Accordingly, a higher level of intervention is intended for Surabaya port, to be based on a more detailed assessment followed by substantial support for capacity building and monitoring. Importantly, these activities will not only help combat wildlife trafficking, but will increase the efficiency and effectiveness of customs clearance processes through the use of cutting-edge technology that drastically reduces clearance time while simultaneously targeting screening of high-risk containers and improved detection techniques. The support provided would include the installation of a paperless container processing system and a world-leading fully-automated risk analysis engine. These actions should lead to lower operational costs, a higher rate of seizures and increased trade resulting from enhanced port operations. In combination, they offer the potential of significantly increased customs revenue.  Indicative activities under Output 3.1 include:

- Use of PortMATE assessment tool to track improvements in enforcement at all five ports in line with the global wildlife trafficking and ports project

- Capacity building / training activities at all target ports (taken from global ports project)

- Higher level capacity development, feasibility assessment and potential piloting of enhanced customs system at Surabaya port as contribution to / with TA from the global wildlife trafficking and ports project

- Information sharing mechanisms (national level forum discussion between relevant agencies)

- Review options for development of wildlife handling facilities for each port, with trained staff, and procedures for how to dispose of confiscated wildlife quickly and efficiently in terms of welfare, supporting conservation efforts, etc., without impacting legal evidence requirements for cases in line with CITES COP17 guidance.

Output 3.2: Inter-agency coordination mechanisms for addressing IWT are developed and introduced for the selected subnational regions and ports

- Further to national level strengthening (see Output 2.1), the WCU technical assistance to Gakkum supported by WCS will continue to enable the operationalization of Gakkum teams in the selected subnational regions (Sumatra and Sulawesi) and target ports. Here, the project aims to improve efficiency and effectiveness within key law enforcement agencies through strengthening the institutional basis for detecting, investigating, arresting/seizing and prosecuting cases of illegal wildlife trade at the subnational level, including ports that have tended to receive little attention. Based on the establishment of a fully functioning multi-agency national taskforce (Output 1.2), the project will socialize its purpose, roles and responsibilities, and action plan/strategy to the subnational agencies. This will provide the opportunity to discuss the implementation of a counter-wildlife trafficking enforcement system that the project will then design for northern Sumatra and northern Sulawesi. Thus, a workshop will be organised to discuss the feasibility, efficiency and usefulness of a subnational forum, as well as raising awareness over illegal wildlife trade and identifying capacity building needs. Workshop participants will include MoEF, INP, Customs and Excise, prosecutors, judges etc. This forum will be used to facilitate the development of interagency counter IWT agreements for database and information sharing. Indicative activities under Output 3.2 include:

- Develop a subnational inter-agency communication forum to facilitate inter-agency coordination for each demo region based on series of stakeholder consultations to detail wildlife trade chains, key species involved, key actors etc.

- Coordinate information through CID, customs, quarantine, immigration, anti-corruption agency and other information systems to combat IWT.

Output 3.3: Gakkum's operations strengthened and key stakeholders effectively engaged in the western and eastern Indonesia demonstration sites including capacity development for SMART patrolling

- Technical assistance will be provided to support Gakkum to expand and intensify its operations in the northern Sumatra and northern Sulawesi demonstration regions and ports. It will build on the inter-agency partnership developed in Output 3.2 but also actively engage NGOs and community groups to collaborate in tackling IWT in these two regions. The actions in this Output will include: i) institutionalization of inter-agency joint action at the site level; ii) establishment and operation of informant networks in forested landscapes and major trade centres gathering evidence for government to prosecute crimes; iii) collaborating with local enforcement agencies, building the understanding of prosecutors and judges to ensure that cases are fully and fairly administered; and, iv) working with media to keep the judicial proceedings transparent.

- The two protected areas within the demonstration regions include the second largest in Sumatra (Gunung Leuser NP) and the largest in Sulawesi (Bogani Nani Wartabone NP) both of which are strongholds for many of the project target species that are heavily traded through the related targeted ports (Belawan, Kuala Namu and Bitung). Much of the SMART patrol work in Gunung Leuser will be covered by the UNDP/GEF Tiger project, whereas the SMART patrols in Bogani Nani are not covered in E-PASS (except for some training) and it is important to have an eastern Indonesia demonstration site. A national MoEF SMART Taskforce was established in 2016, which represents a major milestone in institutionalizing SMART. To support efforts to increase the MoEF allocation of funds for operating SMART systems, it is essential to support the realisation of several successful examples of how SMART can be used to increase PA management effectiveness. There are parallel efforts being conducted to explore sustainable financing options for PAs. Here, the Government with support from WCS is currently conducting a PA funding needs review, using Leuser as a case study, as a means to develop effective arguments for increasing Conservation Area financing and work with government to identify opportunities to filling these gaps from government resources or through different funding schemes. Thus, the GEF IWT project will be used to support Bogani Nani patrols, and will be used to demonstrate its complementary landscape level links with ports in both the Sumatra and Sulawesi demonstration areas, which in combination makes a strong case for it being funded and supported by multiple agencies. Next, local communities will partner with government rangers in conducting SMART patrols, as urban and rural based informants who will monitor and report IWT and as assistants in local market bushmeat surveys. The GEF funds would be used to support community rangers and not government rangers. The funds would also be used to equip the community rangers and to enable WCS to provide technical assistance, such as through SMART training of rangers and limited supervision/support thereafter as the government incrementally takes full responsibility and ownership here.

- Advice on law enforcement training such as SMART-RBM patrolling for PA resort management staff will be provided. A key aspect of reducing illegal poaching and wildlife trafficking is to establish a system which allows patrol rangers within each PA to systematically record and monitor progress on tackling poaching and illegal activities within park boundaries. SMART (Spatial Monitoring and Reporting Tool) is a best practice adaptive management approach, which is supported by software that has been designed based on information derived from wide consultation with governmental and non-governmental conservation practitioners worldwide. SMART combines a ranger-based data collection tool and a suite of best practices to help PA and PA managers better plan, evaluate, and implement conservation activities. WCS is one of the leading proponents of SMART in Indonesia, and has worked alongside KSDAE to institutionalize the use of SMART in 3 national parks in Sumatra. This deliverable will strengthen capacity to monitor and combat poaching that is linked to IWT and bushmeat trade, contribute towards WCS advisory support to EPASS on SMART-RBM development in the 3 focal PAs (SMART training in Bogani Nani Wartabone National Park is already underway in 2 resorts by WCS) and ensure that the database architecture and staff capacity exists for the proper management and analysis of data from patrols. Indicative activities under Output 3.3 include:

- Provide technical assistance to support Gakkum to establish/expand in northern Sumatra and northern Sulawesi demonstration regions, technical assistance provided by WCS-WCU, including training in SMART patrolling for Gakkum and related PA staff

- Engagement of local communities in patrolling, market surveillance, local informant networks, in collaboration with ongoing activities (including GEF Sumatran Tigers and EPASS projects).

Output 3.4: Livelihood options and HWC reduction mechanisms developed and introduced to local communities in wildlife trade source areas

- The project’s activities will respond to the anticipated effects of tackling IWT on women and recognize the gender-differentiated impacts that this may have on men and women and their households. These activities will focus on communities in identified source areas for IWT within the two demonstration landscapes, supported by awareness programmes and efforts to greatly reduce their conflicts and economic losses to problem wildlife. Indicative activities under Output 3.4 include:

- Engage local NGOs/CSOs to conduct awareness programmes in schools, churches, mosques, and community centres and capacity development for communities

- Employment of local people as community rangers, informants and wildlife conflict enumerators

- Targeted support for response to HWC issues in priority IWT source areas including crop and livestock protection (WRUs).

Component 4: Knowledge Management, Monitoring and Evaluation and Gender Mainstreaming

Total Cost: US$976,500; GEF project grant requested: US$276,500; Co-financing: US$700,000

Outcome 4: Implementation and upscaling/replication of project approaches at national and international levels is supported by effective knowledge management and gender mainstreaming

Output 4.1: Knowledge management is coordinated with other GEF projects through the GEF Programmatic Framework to Prevent the Extinction of Known Threatened Species

- This project is part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and also the GEF Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (9439 – Resubmission of 9071). Under this programmatic framework, with coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured. In addition, the design of the project incorporates a number of features related to strengthening the country’s knowledge management system and capacity. This includes publication of project discussion papers, technical briefs and communication pieces, which will form part of a project communication strategy. This also includes compiling and disseminating to decision makers and other key stakeholders publicly available, accurate, and up-to-date information portraying the volume, flows, values and social norms encouraging the illicit wildlife trade. Finally, the project will support the participation of MoEF in international events and supporting the strategic thinking leading up to these events, especially for CITES COP, IUCN congresses and various regional IWT initiatives. Indicative activities under Output 4.1 include:

- Project communications strategy developed and updated annually

- Technical reports, news articles and IWT awareness materials (etc) arising from project activities uploaded to national and project websites, shared with key national stakeholders and provided to GWP Secretariat

- Case studies developed on key issues relating to IWT and published as technical briefs

- Project representatives participate in GWP conference calls and events, and present results at international conferences in coordination with other GWP projects (eg CITES COP side events)

Output 4.2: M&E system incorporating gender mainstreaming developed and implemented for adaptive project management

- The project will ensure that information and knowledge accumulated within the project will be codified and documented for sharing and upscaling efforts. It will do this through annual rigorous project implementation review exercises, mid-term and final project review. The project will strengthen connections with the global illegal wildlife trade program and global project under this, including use of the Global Wildlife Programme Tracking Tool, PortMATE, as well as the project Results Framework. This will enable project performance to be reliably monitored using a shared and quantitative set of indicators. These indicators do not presently exist for the various partnering government institutions, but would contribute towards more effective planning and direction of agency programmes in relation to IWT. Gender will be mainstreamed into project implementation through a gender mainstreaming strategy and monitored as part of the M&E framework for the project. Indicative activities under Output 4.2 include:

- Review and update M&E plan including results framework baselines during project inception phase, including GEF Global Wildlife Program Tracking Tool, ICCWC Indicator Framework and PortMATE assessments

- Conduct Mid Term Review and Terminal Evaluation in line with UNDP/GEF requirements, and incorporate recommendations of MTR into revised project plans (management response) following PSC approval, and monitor their implementation

- Develop national-level indicators for effective enforcement

- Develop a gender mainstreaming strategy and monitor its implementation

Figure 4. Detailed project pathways from Outputs to Outcomes and Impacts

- Partnerships:

- This project is part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and is specifically included in the GEF Programme Global Partnership on Wildlife Conservation and Crime Prevention For Sustainable Development (9071). Under this programmatic framework, with the coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured.

- During the project development stage, collaboration arrangements were discussed with the UNDP/GEF Ports of Excellence project under the GEF Global Wildlife Program, in order to invite Indonesia to participate in this new project supporting sea ports to combat wildlife crime. Four ports are being targeted for initial inclusion, including Surabaya/Tanjung Perak sea port (the fifth project site is an airport). At each port the project will offer a comprehensive assessment of port operations using the PortMATE assessment tool, see Output 3.1.

- The proposed project will directly complement the UNDP-GEF project Enhancing the Protected Area System in Sulawesi (E-PASS) for Biodiversity Conservation (2014-2019) and UNDP-GEF project PIMS No. 4892 Transforming effectiveness of biodiversity conservation in priority Sumatran landscapes (2016-2022). These two projects aim to address the main threats to biodiversity across the islands of Sumatra (home to Indonesia’s remaining Sumatran tiger, Sumatran rhino, Sumatran elephant and Sumatran orangutan populations) and Sulawesi (notable for its high levels of endemism), through interventions including strengthening protected area management and site-level actions to reduce poaching. By targeting the regulatory, institutional and capacity barriers to effective action to combat illegal wildlife trade at the national level and transit/export points (ports) for wildlife illegally exiting Sumatra and Sulawesi, the proposed project will complement these landscape-level GEF initiatives.

- The proposed project will similarly complement other landscape-focused initiatives, including the US Government - Government of Indonesia debt-for-nature swap under the Tropical Forest Conservation Act, USAID’s investments in landscapes through its forestry programme, and the German Government’s investments in landscapes through the International Climate Initiative and bilateral development cooperation.

- The proposed project will coordinate closely with other smaller-scale initiatives to strengthen enforcement capacity and institutional frameworks to address environmental crimes in Indonesia, including ICITAP’s training programs, OPDAT’s work with the AGO, UNODC and Interpol. The GEF project activities are designed to complement and strengthen, rather than duplicate, activities by other bilateral or multilateral donors.

- Regarding partnerships within and between government institutions and NGOs, this project will contribute significantly to bridging the gaps in communication and promote collaboration within and between different entities in government and also keys NGOs. While the MoEF is the lead Implementing Partner, it will work in close collaboration with the following government institutions: INP, MMAF, Customs and Exercise, Quarantine, Avsec/Port Security and LIPI. The MoEF will also work through its NGO partners, which hold an MOU, such as WCS and in particular its WCU, which effectively operates all key government institutions. Linkages and collaboration will be strengthened between these government and non-government agencies at the national level and also landscape level through training, technical advice, information sharing and joint strategic planning and implementation to ensure the delivery and achievement of project goals and objectives. The role of the Project Board and the Project Management Unit in ensuring that the partnerships work and the interactions are kept functional is therefore key. UNDP, in its oversight role, and as both the Implementing Agency for this GEF project and a development partner to the MoEF, will play a central role in ensure that these partnerships work, and will liaise at the highest level with government to ensure that the project fully delivers against its workplan and targets.

- UNDP has a large presence in Indonesia and the project will contribute towards UNPDF/CPD Outcome 3: By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disasters and other shocks, and UNDP Indicative CP Output 3.3: National/local governments have improved policies, systems, and partnerships with non-state actors to protect biodiversity and endangered species.

- Responsible national institutions and relevant stakeholders are more effective in managing environmental resources and addressing environmental pollution by implementing the intended output of Government, private sector and CBO partners to stimulate coherent and effective policy frameworks, action plans, implementing arrangement and funding arrangement to sustainably manage terrestrial ecosystems. Wildlife trade is essentially a governance issue, and herein lies the main strength of UNDP. Aspects of this project relating to the development of sustainable supply chains also lie firmly in UNDP’s field of expertise. Within Indonesia and the region UNDP is also very well placed to implement this project as the leading UN agency assisting the Government of Indonesia in implementing NBSAP towards achievements of the Aichi Targets under the CBD. The UNDP Country Office (CO) will assign an experienced biodiversity conservation programme manager within the Energy and Environment Unit, guided by the head of the Unit and supported by the alternate staff, administrative assistant, and the UNDP finance and quality assurance unit.  The UNDP Regional Technical Adviser based in Bangkok, as well as the global adviser on wildlife trade and enforcement based in Addis Ababa, will provide technical support to the CO for implementation, monitoring and evaluation of the project.

Stakeholder engagement:

- During project preparation, a stakeholder analysis was undertaken to identify key stakeholders, assess their interests in the project and define their roles and responsibilities in its implementation. Overall, support for the project and involvement in it was secured from a diverse group of stakeholders, whose roles are summarised in Table 2. PPG stakeholder meetings were convened on 15 March 2016 (combined with the Focus Group Discussion Meeting on Databases) in Bogor; on 22-23 August 2016 in Bogor; and on 20-21 October 2016 in Bogor. The national consultancy team from the Faculty of Forestry at the Agricultural Institute of Bogor (Institut Pertanian Bogor, IPB) convened a series of Focus Group Discussion (FGD) meetings to consult with key stakeholders on the key themes being reviewed, supported by extensive interviews and field visits (see Annexes 11,14,15,16,17). Further information on the institutional framework for wildlife crime enforcement and implementation is given in the baseline analysis section above, and on the roles of key stakeholders in project implementation in the Management Arrangements section below. The stakeholder engagement strategy in Annex 19 includes details of the key stakeholders in each of the demonstration regions (N Sumatra and N Sulawesi) and key actions to engage them. Further consultations will be conducted in the demonstration regions during project implementation to obtain Free Prior Informed Consent for the communities that are identified for targeted interventions according to further analysis of wildlife trade chains including source areas, transportation routes, markets and ports.

Table 2. Summary stakeholder analysis indicating main roles and responsibilities

| Stakeholder | Main roles and responsibilities |
| --- | --- |
| National level |  |
| Ministry of Environment and Forestry (MoEF) | The CITES Management Authority in Indonesia is the Ministry of Environment and Forestry (MoEF), more specifically the Directorate of Biodiversity Conservation (c.q. Sub-Directorate Program and Convention), under the Directorate General of Conservation of Natural Resources and Ecosystem. MoEF has many regional offices called Balai Konservasi Sumber Daya Alam (BKSDA). Currently there are 31 BKSDAs, spread out all over in Indonesian territory. In relation to wildlife trade, BKSDAs have roles to proposed number of annual quota for harvestable species and its monitoring, issue a letter of domestic transportation of wildlife specimens (Surat Ijin Angkut Tumbuhan dan Satwa Dalam Negeri, SATS-DN), and as law enforcers against wildlife trafficking in their areas. For law enforcement, a new Directorate General of Law Enforcement of Environment and Forestry and the organization structure has been established. Among the four sub-directorates of the Directorate General of Law Enforcement of Environment and Forestry, two Directorates are directly concerned with law enforcement of illegal wildlife trade, namely the Directorate of Forest Prevention and Protection (Pencegahan dan Pengamanan Hutan) and Directorate of Criminal Law Enforcement (Penegakan Hukum Pidana). Currently the MoEF employs 8,105 forest rangers, PPNS (Civil Investigation Officers) 1,043, and 764 SPORC (Satuan Polisi Kehutanan Reaksi Cepat; Rapid Response Forest Rangers). As the national CITES Management Authority, MoEF must coordinate CITES implementation and enforcement with many other agencies, including customs, quarantine, police and other related agencies. Several training manuals, guidelines on species identification and CITES have been produced and training provided. The MoEF has a number of officials who have been trained as civil investigators (PPNS) to investigate particular cases under the authority of their Ministries. Most of the MoEF rangers and investigators are posted in national parks or provincial Nature Conservation Agencies (BKSDA). Only a few of them are posted at the headquarters of the ministry in Jakarta, where they have nationwide jurisdiction. GAKKUM has played a lead role in coordinating with other stakeholders during the project preparation. Subsequently, GAKKUM has been identified as the lead implementing partner from the government/MOEF during the project implementation, and will be responsible in delivering project results. |
| Ministry of Marine Affairs and Fisheries (MMAF) | Among the five Directorates General within MMAF, there are two Directorates General relevant to species conservation and conservation areas: the Directorate General for Marine, Coastal, and Small Islands; and the Directorate General for Supervision/Monitoring of Marine and Fisheries Resources, which is responsible for law enforcement. Similar to the MoEF, the MMAF has civil investigators (PPNS) with responsibility to investigate fisheries offences (including species protected under the Fisheries Law, such as mantas). However, the MMAF has no equivalent to forest rangers and the SPORC (i.e., rapid response units). It does not currently act as a CITES management authority for marine species (only MoEF). Technical Implementation Unit of Aquatic Species and Area Conservation (UPT KKJI). As this project is primarily focused on combatting terrestrial-based IWT, MMAF will be included in consultations on national policy, legislation and institutional issues but will not have direct responsibility for implementation of specific activities (Component 1). |
| Ministry of Justice and Human Rights; Courts | Responsible for the national judiciary amongst other functions. The function of the courts is to adjudicate the cases filed by the law enforcers (criminal cases) or other government entities and the public (civil cases). There are courts at three levels - regency/city (kabupaten/kota), where the lowest court (pengadilan negeri) exists, the province (the high court), and nationally (the supreme court). By January 2015, 103 judges had been trained for certification as environmental judges through collaboration between the Supreme Court and WCS’s WCU. The MoJHR will participate in the project Technical Advisory Committee, and staff will be provided with training and professional development in relation to IWT crime through the project (Components 1, 2). |
| Attorney General’s Office (AGO) | Responsible for the national prosecution service, the AG’s Office is a member of the National Task Force for Wildlife Enforcement Network in Indonesia. It will participate in the project Technical Advisory Committee and staff will participate in training activities in relation to IWT crime through the project (Component 2). |
| Ministry of Trade | Responsible for domestic and international trade policy, development and regulation (Component 1). |
| Ministry of Agriculture | The Quarantine Agency of the Ministry of Agriculture is a member of the National Task Force for Wildlife Enforcement Network in Indonesia. It will participate in the project Technical Advisory Committee and staff will participate in training activities in relation to IWT crime through the project, especially at the demonstration ports in Component 3. |
| Ministry of National Development Planning (BAPPENAS) | National government agency responsible for national economic and development planning, as well as development of strategies and policies in determining financial allocations for the various sectors of the national economy. Bappenas is on the Project Board. |
| Ministry of Transportation | Responsible for the development and regulation of transportation including shipping and air. Will participate through port/airport authorities in Component 3 activities for capacity development at demonstration ports. |
| Ministry of Finance, Customs | The Directorate General of Customs and Excise of the Ministry of Finance plays a key role in the detection and enforcement of the trade in wildlife through Indonesia’s many shipping ports and airports through enforcement of the Customs Law 17/2006. It is a member of the National Task Force for Wildlife Enforcement Network in Indonesia. Project Board member, and customs will be a key department for the project activities at the demonstration ports in Component 3. |
| Corruption Eradication Commission (KPK) | Law No.30/2002 on the Corruption Eradication Commission provided the legal basis for the establishment of the KPK. Its duties include investigating and prosecuting corruption cases and monitoring the governance of the state. It has wide powers for investigation and detention of suspects. Will participate in the Technical Advisory Committee and will be a key project partner in strengthening the multi-door approach to IWT prosecutions in Components 1 and 2. |
| Financial Transactions Analysis and Reporting Centre (PPATK) | Key role as an anti-money laundering agency, involved in wildlife crime trade detection and enforcement through the application of anti-money laundering legislation (2002 Anti-Money Laundering Law and its 2010 amendment). Will participate in the Technical Advisory Committee and will be a key project partner in strengthening the multi-door approach to IWT prosecutions in Components 1 and 2. |
| Indonesian National Police (INP) | Law enforcement in Indonesia. For forestry and wildlife crime issues works under a national-level MoU between the MoEF and the National Police Headquarters. The Criminal Investigation Division (CID, Bareskrim POLRI) is a member of the National Task Force for Wildlife Enforcement Network in Indonesia. Unit 1 is specifically tasked with targeting environmental crimes, and has played a leading role in the majority of high-profile prosecutions brought successfully in Indonesia over the past 5 years. Project Board member and key project partner for support in implementation of all project components. |
| Indonesia Institute of Science (LIPI) | LIPI is the CITES Scientific Authority for Indonesia, supporting MoEF as the CITES Management Authority. Key project partner for Component 1 in particular, in relation to the regulation and institutional framework for species protection and establishment of quotas for legally traded wildlife. |
| Wildlife Conservation Society (WCS) | WCS will act as a project implementation partner, building on their long experience in combatting illegal wildlife trade, advancing species management and in conserving specific landscapes through cofinanced programmes and working in partnership with the MoEF, MMAF and other agencies to build capacity, conduct joint patrolling and monitoring operations and other shared activities. Established and supports the Wildlife Crimes Unit (WCU) that brings together key government agencies for a coordinated response to wildlife crime. |
| Wildlife Crimes Unit (WCU) | Starting in 2003, the WCS Indonesia Program has pioneered an innovative approach towards working with Indonesian law enforcement agencies across local, regional, and national scales to combat illegal wildlife trade. The WCU brings together a partnership including MoEF, MMAF, Police, Attorney General and Customs, and a network of local civil society and media organizations. The WCU approach includes establishing informant networks around key landscapes, and in key markets and transport hubs; using highly-trained investigators to gather evidence correctly; assisting the government with the cases in the criminal courts; building the capacity of investigators, prosecutors and judges for case administration; and collaborating with media organisations to raise awareness about successful prosecutions. The WCU will play a central role in supporting Gakkum in the implementation of the project, especially the inter-agency coordination and joint operation aspects (All Components). |
| Eijkman Institute for Molecular Biology | MoU for collaboration with WCS and TRACE Wildlife Forensics Network for capacity building for forensic testing of species identified in illegal trade in support of prosecutions. Training for police, MoEF investigators and journalists started in April 2015. Eijkman Institute is expected to support capacity development activities in Component 2. |
| TRACE Wildlife Forensics Network | TRACE (Tools and Resources for Applied Conservation and Enforcement) was established in 2006 as a non-profit organisation dedicated to the promotion of forensic science in wildlife conservation and law enforcement. It has a global remit for the development, dissemination and implementation of forensic tools to help tackle wildlife crime. MoU for collaboration with WCS and Eijkman Institute. TRACE is expected to support capacity development activities in Component 2. |
| Other international and local NGOs (TRAFFIC, Fauna & Flora International (FFI), Zoological Society of London (ZSL), WWF-Indonesia, Birdlife/Burung Indonesia, ProFauna, Jakarta Animal Aid Network (JAAN), Conservation Policy Working Group (POJKA Kebijakan) | A number of NGOs have been significantly supporting wildlife conservation and species protection efforts in Indonesia for decades, including anti-poaching measures (e.g. FFI, WWF and ZSL) and action to improve enforcement at markets (e.g. ProFauna, JAAN). TRAFFIC have conducted a number of investigations into the trade of certain species in Indonesia and provided recommendations to government. POJKA Kebijakan (a CSO coalition) is facilitating technical discussions on the review of the Conservation Law 5/1990 in collaboration with MoEF. The Technical Advisory Group provides a mechanism for engagement of CSOs, and additional inputs can be secured through subcontracting as necessary. |
| Landscape and site level (see Annexes 11 and 19 for further details) |  |
| Provincial and District Governments | According to the decentralisation process in Indonesia, including the natural resource management sector, the provincial governments, as well as district governments, at the targeted ports and in the target landscapes are responsible for local development and land use planning, service provision and natural resource management for all areas outside NPs. These government levels will be involved in overseeing the implementation of activities in the demonstration landscapes in northern Sumatra and northern Sulawesi (Component 3). |
| National Park Agencies | Subsidiary units of the MoEF responsible for managing individual national parks. This project will support anti-poaching and awareness raising activities in and around national parks in the demonstration landscapes, and connect park management with wider IWT enforcement operations (Component 3). . |
| Natural Resources Conservation Agencies (BKSDA) | Provincial units of the MoEF responsible for managing wildlife and conservation areas, including nature reserves, wildlife sanctuaries, nature recreation parks and hunting parks. BKSDA will be key partners for implementation of activities in Component 3 in the demonstration landscapes and at the ports. |
| Provincial Forestry Agencies (Dishut) | Agency under the provincial government in charge of planning and management of the production and protection forests. Stakeholders for implementation of activities in Component 3 in the demonstration landscapes. |
| Provincial development and planning agencies (Bappeda) | Agency under the provincial government and responsible for provincial development planning, including spatial plan development. Stakeholders for implementation of activities in Component 3. |
| Port Administrations | Responsible for the management of port facilities. Key partners for implementation of activities in Component 3 at the demonstration ports. |
| Local communities and indigenous people | Key users and beneficiaries of natural resources and associated ecosystem services; may also participate in wildlife trade. Stakeholders for implementation of activities in Component 3, specific communities will receive targeted support in wildlife trade source areas in terms of awareness raising, community engagement and sustainable livelihood support. |
| CBOs | Currently support a range of activities focused on biodiversity conservation and socio-economic development for communities in target landscapes and are key partners for various government agencies and international NGOs. Stakeholders for implementation of activities in Component 3. |
| International and local NGOs | International NGO with qualifications and long-term contribution in combatting illegal wildlife trade and improving the effectiveness of PA management through introduction of a joint agency patrolling model (Wildlife Crimes Unit) will support project implementation at landscape level, including application of the SMART law enforcement monitoring system, and technical assistance for enforcement of trade in terrestrial and marine species. Local NGOs will be also engaged and trained to increase their capacity with regard to illegal wildlife trade during project implementation. |
| Academic institutions | Several local universities provide training in wildlife, forest and marine management to undergraduate and postgraduate students, of which many graduates now work for local and international environmental NGOs. Potential sources of TA for supporting the implementation of Component 3 activities. |
| International level |  |
| Association and South East Asian Nations – Wildlife Enforcement Network (ASEAN-WEN) | ASEAN-WEN was established in 2006 and covers all 10 ASEAN states including Indonesia (where the ASEAN Secretariat is currently based). It aims to provide an inter-governmental law enforcement network to combat wildlife crime, and a mechanism for sharing best practices. It provides a significant means of tackling international illegal wildlife trade routes through collaborative operations and to enhance the regional networking capacity of the CITES and law enforcement authorities in Indonesia. The project will coordinate with ASEAN WEN and seek to increase the level of Indonesian participation in its activities (Component 2). |
| International Consortium on Combating Wildlife Crime (ICCWC) | Established in 2010, the ICCWC brings together the main international governmental organizations responsible for combating wildlife crime (CITES Secretariat, INTERPOL, UNODC, WCO and World Bank) to provide a coordinated response. A key output is the Wildlife and Forest Crime Analytic Toolkit to guide national responses, and the more recent ICCWC Indicator Framework (Components 2 and 3). |
| INTERPOL (International Criminal Police Organization) | The main platform for policing authorities to work across borders to catch wildlife trade criminals through its Wildlife Crime Working Group, which works under the auspices of its Environmental and Compliance Committee. They lead operations to address wildlife crime, develop best practice guidelines and link national environmental agencies. INTERPOL participated in PPG consultation meetings and will be a key project partner at the national level (All Components). |
| TRAFFIC | Formed by an alliance of WWF and IUCN in 1976, TRAFFIC works to ensure that the trade in wild plants and animals is not a threat to nature conservation. It has 7 regional teams and a presence in 30 countries. The SE Asian regional office is located in Malaysia, and has conducted a number of investigations involving Indonesia. TRAFFIC will be kept informed about project progress and its advice and technical assistance sought where necessary (All Components). |
| UNODC (UN Office on Drugs and Crime) | The key UN agency mandated to act on wildlife crime since 2000. UNODC operates a Global Program for Combating Wildlife and Forest Crime/Sustainable Livelihoods Unit (GP/SLU) through which it accesses various UN divisions to provide country support through capacity development to combat wildlife crime. UNODC is a partner in the GWP Ports of Excellence project and will support training activities at ports in Indonesia in Component 3, and potentially other TA. |
| Wildlife Conservation Society | WCS’s Vietnam, China and Tanzania programs are actively engaged in wildlife trade issues and provide capacity to facilitate transnational collaboration. Project activities will be coordinated with these programs through WCS Indonesia and its Wildlife Crimes Unit that operates across the archipelago (All Components). |
| World Customs Organization | Represents the customs authorities of 179 countries; established its environment programme in 2012, with a focus on IWT. Resources for members include ENVIRONET – a real-time communication tool and CLiKC - a learning tool offering courses on environmental crime. Partner for Component 3 activities on ports. |

Mainstreaming gender:

- During the PPG phase, a consultancy study was undertaken to conduct a gender assessment reviewing the roles of men and women in the project development and implementation and potential impacts of the project on each gender group, and to provide guidance on gender mainstreaming for the project.  This aimed to ensure an inclusive approach through which women and men are able to participate actively and benefit equitably, have equitable access to the project resources and receive fair social and economic benefits. The full report of this study is given in Annex 16, while its key findings and recommendations are summarized here, with recommended gender mainstreaming actions given in Table 3 below. A gender mainstreaming strategy will be developed in year 1 as part of the M&E Plan and its implementation monitored by the M&E and Gender Mainstreaming consultant.

Gender analysis

- The situation analysis for the project study area included social economic assessment for the project context, at national level and a case study for Langkat Regency, part of the Leuser Ecosystem in North Sumatra.

- In Indonesia, gender is perceived as the contrast of attitude, role and position of men against women by society and influenced by beliefs or religions, cultural, political and economic system. Therefore, gender as a concept may be changing by time, space and culture. As reported in the Gender Inequality Index (GEI) of 2011, Indonesia ranked 100 out of 146 countries indicating strong gender bias in many areas: women had a lower literacy rate (86 %) than men (94 %); fewer years of schooling (6.5 years) than men (7.6 years); smaller share of income (USD 2,289) than men (USD 4,434) in 2003; and less access to productive resources than men (Hoque, 2015). The policy framework on governance of gender equality in Indonesia consists of:

- Ratified UN Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) in 1984.

- Indonesia’s Basic Constitution of 1945 that treats men and women equally before the law and the government.

- Law No. 10 of 2008 on legislative election reserving a 30 percent quota for women.

- Presidential instruction No. 9 of 2000 on gender mainstreaming in the national development.

- To operationalize the above policies, the Government of Indonesia has established the State Ministry for Women’s Empowerment and Child Protection which has been built on the Ministry originally established in 1978 for the first time. Despite the relatively adequate policy framework and institution, gender equality in performing biodiversity conservation management is still weak. The predominant role of men is primarily due to biophysical, cultural and structural factors. As to date, the majority of Indonesians perceive that particular forest management activities are not proper or taboo for women to do because they involve physical power, masculinity and extended periods of stay in the field. Examples are hunting of wildlife and harvesting of NTFPs. For reasons of traditional beliefs and values, the majority of households in rural areas still believe that wives’ primary task is to rear children and do domestic chores like cooking and cleaning. Another limiting factor is the established structure of state employees that is predominated by men, thus facilitates domination of men in decision-making on different aspects of biodiversity conservation management.

- In Indonesia, gender is an important variable that determines access to and control over forest resources and women play pivotal roles in the resource management and use. While activities vary across the country, women engage in collection of firewood, harvesting of NTFPs and forest protection, to mention only a few. In general, rural women work 13 hours longer than men in a week because they have to combine child rearing and other domestic chores with other activities to fulfill subsistence needs. Access to and control over productive resources such as land is pivotal for women because the resources provide income, can be used as collateral for credit and reflect gendered decision making. Rights over land in Indonesia is formally regulated by the Basic Agrarian Law of 1960 but in practice, traditional patriarchal social norms as well as religious and customary laws create barriers for women to gain equitable access to land and control of productive resources (FAO, 2001). Further details from the gender analysis are available in Annex 11.

- The Social and Environmental Screening Procedure applied to the project has reviewed its potential impacts on women and gender equality through consultations conducted at national and demonstration region levels, with some disaggregated socio-economic information available in the site profiles. Safeguards have been applied to the project design in order to mitigate issues identified in the SESP conclusions (see Annex 6).

- With its focus on strengthening the legal and policy framework and capacity building for wildlife crime law enforcement, this is not a typical development project regarding gender issues. However, there is scope for seeking a gender balance in training activities for national and regional agencies, as is the case for the capacity building program involving WCS, TRACE and the Eijkman Institute, which is being led by several female Indonesian scientists. It is most likely that the project interventions in the two demonstration subnational regions will provide the greatest opportunities to mainstream gender and to empower women in local communities through participation in project activities such as education and awareness programmes, sustainable livelihoods and working groups / committees.

- Consistent with the WB/UNDP/GEF Global Wildlife Programme, this project will focus on gender in developing the pathways out of poaching for local communities, for instance the development of tourism as an alternative livelihood to enhance job opportunities for women. Tourism relies on charismatic species to attract visitors and so is one among several important antidotes to poaching. Moreover, it employs a large segment of the services sector across poor countries, whose ranks are largely peopled by women. Although this project is focused on controlling wildlife trade at source and trafficking, it should be noted that women and women’s groups play a significant role in reducing the demand for wildlife. Many wildlife products are used in the health sector, as spurious catch-all cures. As women are the primary procurers and managers of family healthcare across the developing world, they are an integral constituency to convince in order to reduce demand. Consequently, the awareness programmes planned through this project will have a strong emphasis on targeting women as key proponents of attitudinal change.

Table 3. Proposed gender mainstreaming actions for project implementation

| Outcome/ Output | Responsible | Gender Mainstreaming Actions |
| --- | --- | --- |
| Component 1: Effective national framework for managing wildlife trade |  |  |
| Output 1.1: Amendments and drafts for policies, legislation, regulations and procedures to reduce illegal wildlife trade and improve implementation of CITES in Indonesia are developed and legal adoption processes supported | MOEF, LIPI | - Proactive inclusion of women in working groups and committees involved in policy and regulatory reviews - Consideration of gender disaggregated information on socio-economic aspects of resource use and livelihoods related to IWT and implications for women |
| Output 1.2: Proposal for a Taskforce for improved collaboration amongst responsible agencies is developed and active during the project | MOEF | - Proactive inclusion of women in working groups and committees concerned with IWT |
| Output 1.3: Economic assessments conducted to quantify the value of legal and illegal wildlife trade and its impacts on the national economy and to assess the feasibility of cost-recovery mechanisms | MOEF | - Proactive inclusion of women in working groups and consultancy roles for economic assessments |
| Component 2: Institutional capacity for implementation and enforcement at the national and international levels |  |  |
| Output 2.1: Strengthened capacity of Gakkum to tackle IWT | MOEF, WCS | - Proactive inclusion of women in TA roles and committees on IWT - Proactive inclusion of women participants in related capacity development activities |
| Output 2.2: Training modules and standard operating procedures (SOPs) are developed based on needs assessment for integration into government training programmes |  | - As above - Gender roles to be clearly articulated while undertaking training needs assessment and incorporate in training modules. - Proactive inclusion of women in working groups, committees, new positions - Focus specific incentive mechanisms targeting female law enforcement officers |
| Output 2.3: DG Law Enforcement and other key agencies are trained in wildlife forensics techniques and provided with necessary equipment and expert support |  | - As above |
| Output 2.4: Drafts of National and International Agreements on IWT control are prepared; collaboration between national and international agencies is facilitated; participation of Indonesia representatives in international meetings/initiatives is supported |  | - As above |
| Output 2.5: Communication Strategy and social marketing campaigns to increase awareness on IWT are implemented at national and regional scales |  | - Proactive inclusion of women in TA roles and working groups for awareness raising programme - Requirement for gender disaggregated information to design communications strategy and awareness campaign - Focus on women as a key target group in wildlife trade source areas for fostering attitudinal change - Identification of female champions to participate in awareness efforts |
| Component 3: Scaling-up improved enforcement strategy at key trade ports and ecosystems |  |  |
| Output 3.1: Capacity development supported at demonstration ports including training of key agency staff on CITES and IWT control with focused intervention at Surabaya port | MOEF, WCS | - Proactive inclusion of women in working groups on IWT at ports - Proactive inclusion of women participants in related capacity development activities |
| Output 3.2: Gakkum's operations strengthened and key stakeholders engaged in the selected subnational regions and ports | MOEF, WCS | - Proactive inclusion of women in working groups, committees, new positions and unofficial roles - Proactive inclusion of women participants in related capacity development and field activities - Requirement for gender disaggregated information on wildlife exploitation and trade including demand aspects |
| Output 3.3: Coordination mechanisms of IWT intelligence are developed and introduced to agencies and communities; and local people are trained in IWT monitoring and collaboration with law enforcement | MOEF, WCS, CSOs | - As above - Involvement of women as CBO facilitators for community work |
| Output 3.4: Livelihood options and HWC reduction mechanisms developed and introduced to local communities in wildlife trade source areas | MOEF, WCS, CSOs | - Involvement of women as CBO facilitators for community work - Proactive inclusion of women in working groups, committees, new positions and unofficial roles - Proactive inclusion of women participants in related capacity development and field activities - Requirement for gender disaggregated information on wildlife exploitation and trade including demand aspects |
| Component 4: Knowledge Management, M&E and Gender Mainstreaming |  |  |
| Output 4.1: Knowledge management is coordinated with other GEF projects through the GEF Programmatic Framework to Prevent the Extinction of Known Threatened Species | MOEF, UNDP | - Requirement for gender disaggregated information on wildlife exploitation and trade including demand aspects - Proactive attention to lessons learned regarding gender roles in CBNRM and IWT management |
| Output 4.2: M&E system incorporating gender mainstreaming developed and implemented for adaptive project management | MOEF, UNDP | - Gender mainstreaming strategy developed in year 1 - Requirement for gender-disaggregated information for appropriate indicators in the M&E Plan - Specific monitoring of gender mainstreaming progress during project implementation |

South-South and Triangular Cooperation:

- The project falls under the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and is specifically included as a Phase I child project in the GEF Programme Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (9071). Under this programmatic framework, with the coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured, including African and Asian countries. Beyond this general framework for SS/TrC, the project does aim to engage specifically with other countries in SE Asia on IWT issues through strengthened presence in ASEAN-WEN and bilateral cooperation with key neighbouring countries that are transit or destinations for Indonesian wildlife, such as Vietnam, Thailand, Malaysia, Singapore and China. In addition, efforts will be made to connect with SA WEN in southern Africa in relation to the trade in African ivory. Finally, the engagement with the Ports of Excellence global project under the Global Wildlife Programme for systematic assessment, monitoring and capacity development of key Indonesian ports will provide opportunities for networking, improved tracking and interception of illicit cargoes and global recognition for efforts being undertaken by the Indonesian government to stem IWT. The Ports of Excellence initiative will further facilitate knowledge exchange and adoption of best practices amongst the countries in AP and Africa – Indonesia, Thailand, Kenya, Tanzania, Uganda, Vietnam, Philippines, etc.

# Feasibility

Cost efficiency and effectiveness:

- The weaknesses in the policy and regulatory framework, suboptimal institutional capacity for compliance monitoring and enforcement,  ineffective enforcement at regional and port levels, and inadequate information sharing mechanisms to support responses to IWT are all significant barriers impeding the conservation and sustainable management of Indonesia’s rich and diverse wildlife resources. The proceeds of IWT benefit the individuals and criminal organizations engaged in such trade at the cost of the wider values to society that such wildlife populations would otherwise bring, and denying the country revenue that would be obtained through lawful, sustainable wildlife trade. These losses have not been calculated in the Indonesian context, but their massive scale is apparent through the huge diversity of species in trade, the large volumes in the case of some species and the very high values attached to certain wildlife products. The project intervention will aim to quantify these values and remove these barriers, allowing more effective conservation of Indonesia’s terrestrial and marine biodiversity, more sustainable use of wildlife resources and greater benefits to both the national economy and local communities in wildlife source areas. This approach is cost-effective in that it will address key barriers at natioanal level and also demonstrate the approach towards outrolling more efficient enforcement systems at specific ports and subnational regions with strong potential for future replication and upscaling to other regions of Indonesia.  As such, the project will contribute directly towards national policy, planning, fiscal and communications goals in support of biodiversity conservation.

- In line with the National Implementation Modality (NIM), implementation will be led largely by existing government structures, with TA from the relatively advanced CSO sector. This approach is believed to be particularly cost effective, as it reduces costs that would need to be spent on consultant-driven implementation, and it builds the capacity of the government system for ongoing and more widespread implementation of integrated land and seascape management. At a technical level, the streamlining of progressive approaches into wildlife resource management and the variety of law enforcement agencies for eventual replication across the country will be a cost-effective investment in terms of project impact.

- In order to reduce costs and to avoid duplication, the GEF-financed project will pursue an active partnership strategy with other ongoing and planned initiatives, including the current GEF projects on protected areas management effectiveness in Sumatra and Sulawesi and the diversity of IWT initiatives (see Partnerships section above). Through these collaborations, the project will build on the lessons learned and best practices from past and current projects and ensure that cost effectiveness is included as a selection criteria or in the identification of appropriate adaptation practices and implementation protocols. As part of the GEF Global Wildlife Program “Global Partnership On Wildlife Conservation And Crime Prevention For Sustainable Development” the GEF investment in this project will contribute towards larger scale impact through interconnectivity with other countries participating in the Program, especially through the UNDP/GEF global project component on Ports of Excellence, where standardized assessment, performance recognition and capacity development approaches will be applied for ports related to wildlife trade activities. In general, coordination and outreach through the Program with partners and collaborators can be achieved to bring more efficiency to the investments and avoid duplication of efforts.The lessons learned through this project will also be shared and applied more readily via south-south exchanges through the Program.

- The total GEF investment of US$6,988,853 for this project will leverage a minimum of US$ 42 million in cofinancing, a cost-effective ratio of 6.01 with additional associated financing inputs anticipated during project implementation.

Risk Management:

- The key risks that could threaten the achievement of results though the chosen intervention strategy are shown in Table 4. As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log.  Risks will be reported as critical when the impact and probability are high (i.e. when impact is rated as 5, and when impact is rated as 4 and probability is rated at 3 or higher).  Management responses to critical risks will also be reported to the GEF in the annual PIR.

Table 4. Description of project risks, impact and probability and mitigation measures

| Project Risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description | Type | Impact & Probability, and Risk level | Mitigation Measures | Owner | Status |
| Enter a brief description of the risk | Category of risk | Describe the potential effect on the project if this risk were to occur: Probability P from 1 (low) to 5 (high) Impact I from 1 (low) to 5 (high) | What actions have been taken/will be taken to counter this risk | Who is appointed to keep an eye on this risk | e.g. over, reducing, increasing, no change |
| Delays and uncertainties in achieving government approval for proposed legislative changes and international agreements related to combatting IWT. Such delays may be attributable to lengthy bureaucratic procedures, opposition from certain quarters, or lack of interest / lack of priority afforded to their completion. | Political | P=3, I=3 MODERATE | There is a strong baseline on strengthening the legal and institutional frameworks for combating the illegal wildlife trade, including a rapid assessment of current knowledge, trends and priority actions for wildlife crime, and a detailed analysis of the policy and legal context with support from USAID, with subsequent support to MoEF to implement report recommendations for legal revisions to improve species protection. This has included significant achievements – government agreement to revise the Conservation Law 5/1990 during 2016, MoEF agreement that the revised Law should always reflect the current and existing CITES list, and progress towards updating the Protected Species List in 2016. This process has received significant support from CSOs, with WCS playing a leading role, which the project will provide additional resources to follow through on key legislation. Engagement with neighbouring countries occurs through ASEAN WEN but remains weak, and by developing a national IWT strategy associated with a national task force, increasing the capacity of MoEF’s Gakkum to play a leading role in IWT enforcement, and strengthening its international exposure and engagement through the GEF GWP, increased momentum will be provided for such agreements to be developed and put into action. | Project Manager | Decreasing |
| Mal-governance and Corruption: this is a major factor in wildlife trade, and accordingly one that has not been underestimated. Even when laws and mandates are clear, the mandated response is not always forthcoming. This is related to low motivation, poor resource allocation, but also to the insidious effects of corruption, that thrives in the poorly regulated environment. | Political, Operational & Strategic | P= 3; I= 3 MODERATE | Addressing corruption requires considerable high-level political support. Reducing its impact requires action against corruptors, but can also be addressed through tighter regulatory structures and improved monitoring that highlight when appropriate action is not being taken. Many of the described project components are designed to specifically address corruption and other forms of mal-practice and mal-governance. For example, strengthening the regulatory framework and government capacity will enhance oversight and limit opportunities for malpractice. Key agencies responsible for anti-corruption measures, namely the Corruption Eradication Commission (KPK) and Financial Transactions Analysis and Reporting Centre (PPATK) will participate in the project Technical Advisory Committee and will be key project partners in strengthening the multi-door approach to IWT prosecutions in Components 1 and 2. The presence of an internationally funded high profile project will further support the government’s efforts to fight corruption. | Project Manager | Possibly decreasing |
| Lack of industry support due to links with IWT: the wildlife trade industry is secretive, fragmented as well as multi-national. There is often a link to criminal syndicates. This presents challenges for project implementation, industry engagement and enforcement | Strategic | P= 3; I= 3 MODERATE | The project implementers have considerable experience with such trade participants, and will seek to engage industry at all levels, as well as devise a strategy with international organisations to counter criminal syndicates. The project activities have been developed based on a thorough situation analysis based on the latest global information, data and knowledge on the structure of the international and national trade compiled by international organisations and individuals, and supported by a series of consultation workshops and other stakeholder consultations involving all relevant agencies. The project will support the strengthening of intelligence analysis based on WCU capacity, and agreements for information exchange between agencies and collaboration with CSOs such as TRAFFIC to enable understanding and adaptation to changing IWT and legal trade trends. The development of relationships with recognized reputable traders and documentation of their practices as models has potential as a way forward in encouraging responsible trade. | Project Manager | Stable |
| Suboptimal collaboration between IWT enforcement agencies: coordination between various agencies may be constrained due to sectionalism, bureaucracy, the demands of coordination, and/or unclear mandates, impacting the effectiveness of IWT responses. | Operational | P= 3; I= 3 MODERATE | This project has been developed in full collaboration with the Indonesian government and its agencies. There have already been considerable discussions and joint efforts between key government law enforcement agencies. The momentum created by the project will further strengthen and institutionalise the coordination and joint action mechanisms. Joint work will be demonstrated at both national and local levels and necessary systemic and institutional capacities will be installed to ensure sustainability. The WCS-WCU has demonstrated that inter-agency cooperation to conduct collaborative counter-IWT operations can be successful through a number of investigations leading to prosecution of high profile IWT traders, and will continue to support this approach throughout the project. In addition, the involvement of Bappenas as a high level coordinating ministry in the Project Board should help to facilitate inter-agency cooperation. | Project Manager | Stable / decreasing |
| Major natural disasters: natural disasters such as earthquakes, floods, volcanic eruptions, etc. inhibit or divert the increase in national and provincial government’s attention towards and investment in combatting illegal wildlife trade | Environmental | P= 2; I= 2 LOW | This risk is very prevalent in Indonesia. The project will elevate the illegal wildlife trade issues to the national political and economic agenda, as well as developing the National Strategy to Combat Illegal Wildlife Trade. Increased awareness that illegal wildlife trade is a national and global crisis and security issues should minimise shifting of resources away from the work to natural disaster emergency work. The project is also designed to institutionalise every output and install the necessary systemic and institutional capacity for tackling illegal wildlife trade, operationalising essential inter-agency coordination at both national and local level, and this will ensure continuation of core work even in the event of natural disasters. | Project Manager | Stable |
| Climate change impacts on endangered wildlife species populations: climate change may undermine the conservation objectives of the Project by impacting populations of endangered species in situ. | Environmental | P= 2; I= 2 LOW | Responses to the impacts of climate change on animal populations lie outside the scope of this project and are being addressed through other initiatives. The exact nature of this risk will vary substantially between different taxonomic groups and species, but are generally considered to be slow-acting – beyond the project timescale. By removing a major anthropogenic pressure on wildlife populations, this project would contribute towards reducing their overall vulnerability as small population size is a sensitivity factor for climate change impacts. | Project Manager | Increasing |

Social and environmental safeguards:

- The Social and Environmental Screening Procedure (SESP) was followed during project preparation, as required by the SESP Guidance Note of the UNDP (see Table 4). Accordingly, the social and environmental sustainability of project activities will be in compliance with the SESP for the project (see Annex 6). The SESP identified moderate social risks for this project that would have potential negative impacts in the absence of safeguards. Overall, the project is expected to result in major long term positive impacts for biodiversity conservation and socio-economic benefits to the nation and local communities through the more sustainable use of wildlife and natural resources. At the landscape level, it is planned that greater participation of local and indigenous communities in PA management processes should result from the project activities.

- The project’s community-related interventions will be focused on communities in key wildlife source areas, markets and trading ports along trade chains within the two demonstration subnational regions, namely Northern Sumatra and North Sulawesi – Gorontalo. Given the project’s conservation objectives, the anticipated environmental impacts of the project are overwhelmingly positive. The project also aims to have a positive social impact, by strengthening the sustainability of natural resource use which will benefit dependent communities in natural landscapes in the long term through sustained ecosystem service provision. Communities in such areas will also benefit from increased PA management capacity for community outreach and participatory management through related GEF projects, as well as establishing mechanisms for securing alternative livelihoods where needed.

- Despite the above, based on the results of the SESP, several issues will need to be carefully considered during project implementation. These include the need to ensure that recognition of human rights is fully incorporated into training for enforcement agency staff at all levels and considered in plans and strategies for enhanced wildlife trade enforcement. An oversight mechanism will be put in place to ensure that all project activities are carried out in accordance with Indonesian Law and international legal obligations, and that any prosecutions supported by the project are carried out correctly and fairly. This will consist of an SESP ombudsman appointed by the UNDP CO and DG Law Enforcement (MoEF) during the project inception period who will review project progress reports and news from stakeholders, as well as providing a telephone hotline and email contact address for complaints from affected parties. Specific measures will be incorporated for activities in the demonstration areas to ensure that project activities do not restrict legal access of local people to natural resources and that legal cultural traditions are respected. This will include sensitization of project staff to human rights and other social and environmental issues before the outset of field activities. Mitigation measures will be considered by project management if it is judged that project activities will curtail illegal activities which form a significant portion of local peoples’ livelihoods, such as a consultation process with affected stakeholders to determine alternative approaches. Specific measures will be applied to ensure that regulatory reform activities will include appropriate consultation with key stakeholders, including umbrella groups that represent the interests of local forest dependent and indigenous peoples. At the demonstration area scale, consultation mechanisms are proposed in the stakeholder engagement plan to be used during project implementation. The project capacity-building component (Component 2) has been designed to enhance the capacity and understanding of Indonesian law enforcement agencies to ensure that the law is applied correctly.

- Project activities may also have impacts that could affect women’s and men’s ability to use, develop and protect natural resources. This may particularly affect communities that are directly involved in hunting or fishing activities that include the regular taking of protected species or unsustainable harvesting of unprotected species (such as the wide range of reptiles such as turtles, snakes and geckos). While effective law enforcement is required to control such impacts on biodiversity, it will need to be coupled with programs that provide alternative income sources or other social benefits (e.g. education and health, access to credit) in order to be sustainable, and also to mitigate impacts on households that may already be close to the poverty line. Prioritizing the apprehension and prosecution of middlemen and higher level traders and exporters rather than village hunters, fishermen and collectors will help to limit such impacts.

- Selection of target communities will be done in a transparent fashion, based on criteria such as location of the communities in relation to protected areas and key biodiversity areas outside the protected areas, likelihood of involvement in illegal and legal wildlife trade, type of livelihood activities and their impacts on biodiversity and protected area management. Different roles played by women and men in households and communities will be fully taken into account to ensure that the project benefits both genders equitably. The project will ensure that all stakeholders will be involved in the development of conservation agreements and other local area management plan development, and capacity will be developed (within both genders) for their implementation, thereby increasing women’s and men’s ability to use, develop and protect natural resources. Further consultations will be conducted in the demonstration regions during project implementation to obtain Free Prior Informed Consent for the communities that are identified for targeted interventions according to further analysis of wildlife trade chains including source areas, transportation routes, markets and ports.

- In line with UNDP standard procedures, the Project will set up and manage a grievance redress mechanism (GRM) as recommended by UNDP (2014) that would address project affected persons’ (PAP) grievances, complaints, and suggestions. The GRM will be managed and regularly monitored by the PMU. It will comply with the following requirements:

- Uptake. The GRM will have multiple uptake locations and channels. PAPs in the project areas will be able to submit complaints or suggestions to PMU or members of SC in person, via mail, email, via special page of the Project web-site, and phone. These channels will be locally-appropriate, widely accessible and publicized in written and verbal forms on all project communication materials, and in public locations in the project areas.

- Sort & process. All grievances will be registered by PMU. All complaints submitted to PMU or members of SC will be registered by the PMU and the complaint will be assigned a unique tracking number upon its submission. PMU will maintain a database with full information on all submitted complaints and responses taken. These data are important to assess trends and patterns of grievances across the Project regions and for monitoring & evaluation purposes.

- Investigate & act. Strict complaint resolution procedures will be developed and observed, and personnel at the PMU will be assigned to handle the grievances. PMU will develop clear and strict grievance redress procedures, and assign responsibilities. To the extent possible, complaints will be handled at the level of PMU, as close as possible to the complainant. Difficult situations and conflicts will be brought to the attention of SC and UNDP CO if PMU is unable to find appropriate solution. Complaints that are beyond the Project scope will be conveyed by PMU to relevant local or regional authorities in the project areas.

- Provide feedback. Feedback will be provided in response to all registered grievances. PMU will provide feedback by contacting the complainant directly (if his/her identity is known), by reporting on actions taken in community consultations and/or by publishing the results of the complaints on the Project web-site, local newspapers and as part of project materials.

- Enable appeals. Complainants will be notified of their right to appeal the decision taken by the PMU. If complainants are not satisfied with PMU response to their grievance, they will be able to appeal the PMU decision to members of SC and UNDP CO via mail, e-mail or the Project web-site.

- Monitor & Evaluate. The performance of the GRM will be regularly monitored.  As all information about the grievances and their resolution will be recorded and monitored. This data will be used to conduct in-depth analyses of complaint trends and patterns, identify potential weaknesses in the Project implementation, and consider improvements. Environmental and social grievances will be reported to the GEF in the annual PIR.

Sustainability and Scaling Up:

- The project will address sustainability as follows. The development of cost-effective and sustainable solutions to reduce the detrimental impacts of wildlife trade is central to all aspects of this project. The project will work to support and strengthen Indonesian and regional institutions and authorities to reduce poaching and illegal wildlife trafficking. The underlying premise of the project is that interest already exists within the Government of Indonesia, especially its enforcement agencies, in controlling poaching and wildlife trafficking; what is needed is a combination of facilitation and demonstration to show that those resources can be applied for the benefit of globally important biodiversity and Indonesia’s economic development.

- Financial sustainability will be achieved by working through existing government agencies and mechanisms as far as possible such that the outcomes are mainstreamed into the regular operations and budgets of these agencies (e.g. MoEF, MMAF, Indonesian National Police, Customs and Excise, and provincial government). Following the completion of the project these institutions and authorities will be empowered and better equipped to exercise their mandates, without requiring further external resources. The project will also test cost-recovery mechanisms from illegal trade seizures using money laundering legislation and from legal trade through fiscal regulations to ensure trade is taxed at a level commensurate with the cost of regulating it. These types of approaches have been often discussed with respect to wildlife trade, but have never been trialled in the region.

- The project will build on existing initiatives and policies to develop better collaboration and information exchange, rather than creating new costly systems. The project will promote the legitimate industry over unscrupulous traders by developing the market and regulatory environment into one which provides a clear competitive advantage for legal, sustainable and responsible trade. The project’s goal is to put in place a comprehensive system to control trade which will eliminate the risk of further loss and extinction of wildlife, and which requires no further donor input.

- In addition, the project has been designed to ensure that the major costs involved in setting up new systems and technologies are covered during the project period, with any necessary long-term maintenance costs related to project initiatives remaining affordable. Most project components will be completed within the project period, including improvement of policies, laws and regulations, capacity building, demonstration activities at the selected sites including site management and monitoring plans, enhanced law enforcement and monitoring, biodiversity monitoring systems, community participation and development programmes, and education and awareness programmes. At the target landscape level, it is recognised that sufficient financial sustainability must be established to cover long term management costs, especially patrolling and monitoring.

- Institutional sustainability will be improved through systematic capacity development measures for the law enforcement and natural resource management agencies involved in combating wildlife crime, and the upgrading of key technical skills such as the SMART patrol and data management system, which will contribute directly towards piloting effective implementation of RBM at the demonstration sites, techniques for evidence collection, species identification at ports and markets, etc. It is intended that the capacity development through this project will contribute towards enhanced national training systems for agencies engaged in combating wildlife crime, in order to enhance professionalism and the uptake of progressive techniques in line with rapidly advancing global responses across international trading routes.

- Social sustainability will be improved through the development/strengthening of stakeholder participation mechanisms for the target demonstration landscapes and sites, establishment of landscape level partnerships for biodiversity conservation and wildlife crime enforcement, and local level community-based natural resource management committees. Local communities will be empowered through involvement in PA management, wildlife trade informant networks and demonstration activities in the wider landscape activities, as well as sustainable livelihood development and awareness raising to address existing local resource use conflicts and empower women. Long-term investments to raise staff and institutional capacities for stakeholder participation, and sustained improvements in relations with local communities (through regular communication, joint field operations and targeted awareness raising) will lead to increased levels of local participation and improved PA governance, contributing to the overall sustainability of project outcomes. Given that the agencies involved are already receiving technical support from local and international CSOs through species assessments, trade studies, capacity building and joint operations (see baseline analysis), this project will serve to strengthen such partnerships both nationally and locally for greater cumulative impact in addressing the illegal wildlife trade.

- Environmental sustainability will be achieved through a coordinated approach involving a wide range of government and civil society organizations to shift the baseline for wildlife crime such that the risks will outweigh potential rewards, through strengthening the policies, legislation and the institutional capacity to implement throughout the wildlife trade supply chains and with particular focus on priority species and landscapes. This project is one element of the global GEF Program on Illegal Wildlife Trade that will work across the criminal chain and in source-transit-demand countries to establish the enabling environment for preventing IWT. In the demonstration landscapes, improved natural resource management, PA management effectiveness and reduction of external threats on PAs and wildlife through landscape level partnerships, will enhance controls on the wildlife trade and poaching.

- Innovation and scaling up: particularly innovative aspects of this project include scaling-up the Wildlife Crimes Unit (WCU) approach and the development of cost recovery mechanisms. The WCU is already one of the most successful approaches to combat illegal wildlife trafficking in Asia, albeit on a modest scale currently, and key to the success is the partnership of Indonesian law enforcement agencies (MoEF, INP, MMAF, AGO, PPATK, etc.) working together to combat wildlife crimes. Activities for capturing best practices will be used in the project to help promote replicability, shared through training programmes and the project’s Knowledge Management activities.

- Overall, the project will ensure that information and knowledge accumulated within the project will be codified and documented for sharing and upscaling efforts. It will do this through annual rigorous project implementation review exercises, mid-term and final project review, as well as publication of discussion papers and communication pieces. This project is part of the GEF Programmatic Approach to Prevent the Extinction of Known Threatened Species, and is specifically included in the GEF Programme Global Partnership On Wildlife Conservation and Crime Prevention For Sustainable Development (9071). Under this programmatic framework, with the coordination through the programme steering committee, coordinated knowledge management and cross-fertilisation of the individual regional and national projects will be assured. In addition, design of the project incorporates a number of features related to strengthening the country’s knowledge management system and capacity.  The project will support establishment of systems for storing and sharing information on illegal and legal wildlife trade volumes, revenues and enforcement actions, including operationalisation of transnational intelligence and information exchange systems with international partners.

Economic and/or financial analysis: N/A

# Project Results Framework

| Intended Outcome as stated in the UNDAF/Country Programme Results and Resources Framework: Outcome 3. By 2020, Indonesia is sustainably managing its natural resources, on land and at sea, with an increased resilience to the effects of climate change, disasters and other shocks. Output 3.3: National/local governments have improved policies, systems, and partnerships with non-state actors to protect biodiversity and endangered species. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outcome indicators as stated in the Country Programme Results and Resources Framework, including baseline and targets: CP Output Indicator 1: Extent to which progress is made on the development and implementation of a) the law on conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, and b) guideline on IUU Fishing and illegal wildlife trade; Baseline: 2 (Very Partially); Target: 2 (Largely) |  |  |  |  |  |
| Applicable Outputs from the 2014 – 2017 UNDP Strategic Plan: Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste. Output 2.5: Legal and regulatory frameworks, policies and institutions enabled to ensure the conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation. |  |  |  |  |  |
| Applicable Output Indicators from the UNDP Strategic Plan Integrated Results and Resources Framework: Output 1.3 indicator 1.3.1: Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or sub-national level ,disaggregated by partnership type Output 2.5 indicator 2.5.1: Extent to which legal or policy or institutional frameworks are in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems. |  |  |  |  |  |
|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Assumptions |
| Project Objective: To reduce the volume of unsustainable wildlife trade and the rate of loss of globally significant biodiversity in Indonesia and East and South-East Asia | 0.1: Extent to which legal or policy or institutional frameworks are in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems. (IRRF Output 2.5 indicator 2.5.1) | UU5/1990 need to be revised (the current law has not specifically addressed IWT issue; PP7/1999 has not been revised | At least 3 additional policies/laws under review; Policy and institutional framework with specification on articles related to IWT PP7/1999, PP8/1999, Permen 447/2003 Working procedure of DG Gakkum and DG KSDAE, as well as MoEF and Ministry of Marine and Fisheries are developed. | At least 2 additional laws/policies completed Articles on IWT are accommodated in the revised UU 5/90 National strategy for combating IWT developed | There is sufficient political will to support revision of key policies, laws and regulations There are no major bureaucratic delays in seeing revisions through to approval stage |
|  | 0.2: Number of direct project beneficiaries: - Number of government agency staff including enforcement officers who improved their knowledge and skills on IWT due to the project (m/f) - Number of local people in project demonstration areas benefiting from engagement in conservation activities, reduced HWC impacts and improved livelihoods (m/f) | 0 | At least 1000 personnel have improved knowledge on IWT (500m/500f); At least 300 local people in project demo areas benefit directly from project intervention (150m/150f); | At least 2100 personal have improved knowledge on IWT (1050m/1050f); At least 600 local people in project demo areas benefit directly from project intervention (300m/300f); | Continuing level of political will to support the project intervention Good relationship continues between enforcement agencies and key CSO partners Local people refers to member of Community-Based Partner of Forest Rangers (Masyarakat Mitra Polhut/MMP, CSOs, villagers who act as collector and distributor of illegal wildlife products |
|  | 0.3: Expert evaluation of IWT annual volume (number of animal specimens – body parts or live animals) in Indonesia based on the WCS IWT database | 4666 wild animals are seized from 34 protected species Source: Lakip, Gakkum 2016 | Increasing number of cases prosecuted | Increasing number of settled cases on IWT | Improved legislation (Component 1) and law enforcement (Component 2 and 3) will allow the Indonesian government to decrease the level of unsustainable WT. |
|  | 0.4: Number of individuals of IWT flagship species (Sumatran Tiger, Sumatran Rhinoceros, Sumatran Elephant, Black-crested macaque, Anoa and Babirusa) killed by poachers annually in the 2 project demonstration areas | 2015: Tiger (5 poached); Elephant (7 poached); Rhino (1 poached); Anoa (10 poached), Babirusa (12), Black-crested macaque (~200) | >20% reduction from baseline | >40% reduction from baseline | Decrease in IWT will lead to decrease in poaching as a main driver of species loss. |
| Component 1: Effective national framework for managing wildlife trade Outcome 1: Strengthened national policy, legal and institutional framework for regulating illegal commercial wildlife trade and combating illegal wildlife trade | 1.1: The following key legislation gaps are addressed by improved IWT legislation documents approved by Government: -Minimum fines and sentences increased to provide deterrent effect; -Non-native endangered species including elephant, rhinoceros, big cat and pangolin species given legal protection -Indonesian protected species list updated to include all CITES Appendix 1 and globally threatened species - Authority of forestry civil investigators improved - Detention/prison evaluation for creating deterrent effect and rehabilitation for criminals. - online trade regulation to address online wildlife trafficking. | 0 | -Minimum fines increase by 25% Average sentences increase by 10% on baseline. Indonesian protected species list updated to include all CITES Appendix 1 and globally threatened species, including non-native species | All key gaps incorporated in the issued legislation and be implemented. | There is sufficient political will to support revision of key policies, laws and regulations There are no major bureaucratic delays in seeing revisions through to approval stage |
|  | 1.2: Inter-agency taskforce in place and operational as indicated/measured by the signing of an inter-agency agreements targeting IWT | 0 | Inter-agency taskforce in place and operational; 1 inter agency collaboration agreement | Inter-agency taskforce operational; 1 formal inter agency collaboration agreements | National organizations are willing to collaborate on IWT |
| Component 2: Institutional capacity for implementation and enforcement at the national and international levels Outcome 2: Strengthened institutional capacity for regulatory coordination, implementation and enforcement at the national and international levels | 2.1: Strengthened institutional capacity to combat IWT as indicated by i) the ICCWC Indicator Framework (note – baselines to be determined in year 1), ii) UNDP Capacity Development Scorecard for Gakkum (see Annex 18), and iii) Operational status of Gakkum’s Information System | i)ICCWC Indicator Framework – Baseline scores TBD ii)UNDP CD Scorecard Baseline Score: 60% iii) Operational database within Gakkum | i)ICCWC Indicator Framework – Midterm targets TBD ii)UNDP CD Scorecard Midterm Target:70% iii) Data sharing agreements enacted between government agencies | i)ICCWC Indicator Framework – Project Completion targets TBD ii)UNDP CD Scorecard EOP Target: 80% iii) Information System is fully operational and operated by trained staff | Assessments are carried out consistently between years and agencies Strengthened inter-agency collaboration is reflected in the increased scores Political support continues for Gakkum’s role in managing the information system on IWT |
|  | 2.2: - annual number seizures/arrests - annual number of successful prosecutions | Official national statistics on seizures/arrests and prosecutions From mid-2015 to mid-2106: The WCU facilitated law enforcement operations for 31 cases with 55 people arrested and taken to court. Of those with a known outcome, 41 were prosecuted (100% prosecution). This is for terrestrial species in Sumatra and Java. | Official national statistics on seizure/arrests and prosecutions >10% increase in seizures/arrests from baseline >50% cases prosecuted | Official national statistics on seizures/arrests and prosecutions >25% increase in seizures/arrests from baseline >75% cases prosecuted | Official national statistics are made available to the project as required in a timely manner |
|  | 2.3: - Annual number of joined up transnational counter-IWT operations- - Annual number of seizures as a result of transnational counter-IWT operations | No transnational operations | 1 transnational operation/seizure | 3 transnational operations / seizures | Political support is sustained for international collaboration with key countries |
| Component 3: Scaling-up improved enforcement strategy at key trade ports and connected ecosystems Outcome 3: Improved enforcement strategy demonstrated and scaled up at key trade ports and connected subnational regions with key ecosystems | 3.1: Enforcement effectiveness at 5 key trade ports (Jakarta, Surabaya, Bitung, Belawan and Kualanamu airport), indicated by: - Annual PortMATE assessment tool scores (average score for KSDA, Customs, Port Management Authority at each port) | PortMATE Baseline scores: Surabaya (Tg Perak):17.00 Belawan: 18.67 (Jakarta, Bitung and Kualanamu to be done in Year 1) | 25% increase over baseline score | 50% increase over baseline score | Statistics reflect an increase in enforcement effectiveness and not simply improved monitoring and reporting |
|  | 3.2: Effective enforcement of two subnational regions known to include significant wildlife trade routes, measured by: - annual number of IWT seizures at the project sites - annual number of IWT investigations leading to arrests at the project sites; - annual number of successful IWT prosecutions at the project sites | 4666 wild animals seized from 34 protected species Source: Lakip, Gakkum 2016 | Increasing number of cases prosecuted (c.10%) | Increasing number of settled cases on IWT | Assessments are carried out consistently between years and sites |
| Component 4: Knowledge Management, M&E and Gender Mainstreaming Outcome 4: Implementation and upscaling/replication of project approaches at national and international levels is supported by effective knowledge management and gender mainstreaming | 4.1: number of project lessons documented and used by other national and international projects. | 0 | At least 3 project lessons used by other national and international projects | At least 5 project lessons used by other national and international projects |  |

# Monitoring and Evaluation (M&E) Plan

- The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.  Supported by Component 4, which includes knowledge management and M&E, the project monitoring and evaluation plan will also facilitate learning and ensure knowledge is shared and widely disseminated to support the scaling up and replication of project results.

- Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. While these UNDP requirements are not outlined in this project document, the UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

- In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.

M&E Oversight and monitoring responsibilities:

- Project Manager:  The Project Manager is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Manager will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Manager will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

- The Project Manager will develop annual work plans based on the multi-year work plan included in Annex 1, including annual output targets to support the efficient implementation of the project. The Project Manager will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. gender strategy, knowledge management strategy, communications strategy, etc.) occur on a regular basis.

- Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. Immediately following the Mid Term Review, the Project Board will meet to determine the management response to its findings. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

- Project Implementing Partner:  The Implementing Partner is responsible for providing any and all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary and appropriate. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used by and generated by the project supports national systems.

- UNDP Country Office:  The UNDP Country Office will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission.  The UNDP Country Office will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

- The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Manager.

- The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure in order to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).

- UNDP-GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Regional Technical Advisor and the UNDP-GEF Directorate as needed.

- Audit: The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies on NIM implemented projects.

Additional GEF monitoring and reporting requirements:

- Inception Workshop and Report:  A project inception workshop will be held within three months after the project document has been signed by all relevant parties to, amongst others:

  - Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project implementation;

  - Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

  - Review the results framework and finalize the indicators, means of verification and monitoring plan;

  - Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

  - Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; Environmental and Social Management Plan and other safeguard requirements; the gender strategy; the knowledge management strategy, and other relevant strategies;

  - Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

  - Plan and schedule Project Board meetings and finalize the first year annual work plan.

- The Project Manager will prepare the inception report no later than one month after the inception workshop. The inception report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.

- GEF Project Implementation Report (PIR):  The Project Manager, the UNDP Country Office, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR. Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

- The PIR submitted to the GEF will be shared with the Project Board. The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders to the PIR as appropriate. The quality rating of the previous year’s PIR will be used to inform the preparation of the subsequent PIR.

- Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyse and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally. This will be supported by knowledge management activities in Component 4, including the sharing of experiences through annual Stakeholder Forum meetings, national and regional workshops and exchange visits, and online information exchange.

- GEF Focal Area Tracking Tools:  The following GEF Tracking Tool will be used to monitor global environmental benefit results: GEF Global Wildlife Programme Tracking Tool. The baseline/CEO Endorsement GEF Focal Area Tracking Tool – submitted as Annex 4 to this project document – will be updated by the Project Manager/Team and shared with the mid-term review consultants and terminal evaluation consultants (not the evaluation consultants hired to undertake the MTR or the TE) before the required review/evaluation missions take place. The updated GEF Tracking Tool(s) will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

- Independent Mid-term Review (MTR):  An independent mid-term review process will begin after the second PIR has been submitted to the GEF, and the MTR report will be submitted to the GEF in the same year as the 3rd PIR. The MTR findings and responses outlined in the management response will be incorporated as recommendations for enhanced implementation during the final half of the project’s duration. The terms of reference, the review process and the MTR report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center (ERC). As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final MTR report will be available in English and will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and approved by the Project Board.

- Terminal Evaluation (TE):  An independent terminal evaluation (TE) will take place upon completion of all major project outputs and activities. The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as project sustainability. The Project Manager will remain on contract until the TE report and management response have been finalized. The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by the UNDP IEO for GEF-financed projects available on the UNDP Evaluation Resource Center. As noted in this guidance, the evaluation will be ‘independent, impartial and rigorous’. The consultants that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing or advising on the project to be evaluated. The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process. Additional quality assurance support is available from the UNDP-GEF Directorate. The final TE report will be cleared by the UNDP Country Office and the UNDP-GEF Regional Technical Adviser, and will be approved by the Project Board.  The TE report will be publicly available in English on the UNDP ERC.

- The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC). Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.

- Final Report: The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package. The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

Table 5. Mandatory GEF M&E Requirements and M&E Budget

| GEF M&E requirements | Primary responsibility |  | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | GEF grant | Co-financing |  |  |
| Inception Workshop | UNDP Country Office |  | USD 15,000 |  | Within three months of project document signature |  |
| Inception Report | Project Manager |  | None | None | Within two weeks of inception workshop |  |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office |  | None | None | Quarterly, annually |  |
| Monitoring of indicators in project results framework | Project Manager |  | Per year: USD 4,000 x 6 yrs = USD 24,000 |  | Annually |  |
| GEF Project Implementation Report (PIR) | Project Manager and UNDP Country Office and UNDP-GEF team |  | None | None | Annually |  |
| NIM Audit as per UNDP audit policies | UNDP Country Office |  | Per year: USD 4,000 x 6 yrs = USD 24,000 |  | Annually or other frequency as per UNDP Audit policies |  |
| Lessons learned and knowledge generation | Project Manager |  | USD 18,000 |  | Annually |  |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager UNDP CO |  | None |  | On-going |  |
| Addressing environmental and social grievances | Project Manager UNDP Country Office BPPS as needed |  | None for time of project manager, and UNDP CO |  |  |  |
| Project Board meetings | Project Board UNDP Country Office Project Manager |  | USD 1000 per meeting x 12 = USD12,000 |  | Meeting twice annually |  |
| Technical Advisory Group meetings* | Technical Advisory Committee UNDP Country Office Project Manager | USD 1000 per meeting x 12 = USD 12,000 |  |  | Meeting twice annually |
| Supervision missions | UNDP Country Office |  | None |  | Annually |  |
| Oversight missions | UNDP-GEF team |  | None35 |  | Troubleshooting as needed |  |
| Knowledge management as outlined in Outcome 4 | Project Manager |  | 1% of GEF grant = USD 66,500 |  | On-going |  |
| Development and monitoring of gender mainstreaming strategy | M&E and Gender Mainstreaming Specialist |  | USD 10,000 |  | Develop strategy year 1, monitor implementation annually |  |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP-GEF team |  | None |  | To be determined. |  |
| Mid-term GEF Tracking Tool to be updated by (add name of national/regional institute if relevant) | Project Manager |  | USD 5,000 |  | Before mid-term review mission takes place. |  |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team |  | USD 40,000 |  | Between 2nd and 3rd PIR. |  |
| Terminal GEF Tracking Tool to be updated by (add name of national/regional institute if relevant) | Project Manager |  | USD 5,000 |  | Before terminal evaluation mission takes place |  |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team |  | USD 35,000 |  | At least three months before operational closure |  |
| Translation of MTR and TE reports into English | UNDP Country Office |  | USD 10,000 |  |  |  |
| TOTAL indicative COST (3-5% of GEF grant) Excluding project team staff time, and UNDP staff and travel expenses |  |  | USD 276,500 |  |  |  |

# Governance and Management Arrangements

- Roles and responsibilities of the project’s governance mechanism:  The project will be implemented following UNDP’s national implementation modality, according to the Standard Basic Assistance Agreement between UNDP and the Government of Indonesia, and the Country Programme.

- The Implementing Partner for this project is the Directorate General of Law Enforcement of the Ministry of Environment and Forestry (Gakkum).  The Implementing Partner is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources.

- The project organisation structure diagram is given below (Figure 5 below).

- The Project Board (also called the Project Steering Committee) is responsible for making by consensus management decisions when guidance is required by the Project Manager, including recommendations for UNDP/Implementing Partner approval of project plans and revisions. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value for money, fairness, integrity, transparency and effective international competition. In case a consensus cannot be reached within the Board, final decision shall rest with the UNDP Programme Manager. The Project Board shall meet at least twice each year.

- The terms of reference for the Project Board are given in Annex 5. These will be reviewed and finalized at the Project Inception Workshop. The Project Board consists of representatives of the following institutions:

- Gakkum, Ministry of Environment and Forestry (MOEF)

- Directorate of Forestry and Water Conservation, Ministry of National Development Planning (BAPPENAS)

- Directorate of Loan and Grant, Ministry of Finance (MoF)

- Directorate General of Customs and Excise, Ministry of Finance (MoF)

- Indonesian Institute of Science (LIPI)

- Criminal Investigation Department, Indonesian National Police (INP)

- UNDP Country Office Indonesia

- Other organizations may be added as necessary and agreed by the Project Board. The PMU will serve as secretary for the Project Board.

- The Director of Forest Protection and Surveillance, of the Directorate General of Law Enforcement of Environment and Forests will act as the Project Director (PD), who is the MoEF Focal Point for the project. The PD will be responsible for providing government facilitation and guidance for project implementation. The PD will not be paid from the project funds, but will represent a Government in-kind contribution to the Project.

Key to the roles in the Project Organization Structure diagram (according to the UNDP template):

Executive: individual representing the project ownership to chair the Project Board.

Senior Supplier: individual or group representing the interests of the parties concerned which provide funding for specific cost sharing projects and/or technical expertise to the project. The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project.

Senior Beneficiary: individual or group of individuals representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries.

The Project Assurance role supports the Board/Committee’s Executive by carrying out objective and independent project oversight and monitoring functions. The PC and Project Assurance roles should never be held by the same individual for the same project.  This is the function of UNDP, as UNDP will be responsible for reporting to GEF SEC.

Project Board

Senior Beneficiaries:

MoEF, Police, Customs, BAPPENAS, Ministry of Finance

Executive:

MoEF (Directorate General of Law Enforcement)

Senior Suppliers:

UNDP

Project Assurance

UNDP

Figure 5. Project Organisation Structure

PIU for North Sumatra Subnational Region

(DG Law Enforcement Sumatra Office, Medan – covers Kualanamu Int. Airport and Belawan port, Medan)

PIU for Surabaya Port

(DG Law Enforcement Java Office, Surabaya)

Note: Intervention at Jakarta (Tanjung Priok) Port handled by DG Law Enforcement HQ

PIU for North Sulawesi Subnational Region

(DG Law Enforcement Manado Section Office – covers Bitung port)

Technical Advisory Committee

MOEF (PD - Chair), Nat govt, local govt, CSOs, experts, etc)

Project Director

Directorate General of Law Enforcement (MOEF)

Project Director

Director of Forest Protection and Surveillance

Responsible Parties and contracted service providers

Other government agencies, departments and CSO partners

Project Management Unit (located in DG Law Enforcement)

National Project Manager

Project Support

Project Board

Senior Beneficiaries:

MoEF, Police, Customs, BAPPENAS, Ministry of Finance

Executive:

MoEF (Directorate General of Law Enforcement)

Senior Suppliers:

UNDP

Project Assurance

UNDP

Figure 5. Project Organisation Structure

PIU for North Sumatra Subnational Region

(DG Law Enforcement Sumatra Office, Medan – covers Kualanamu Int. Airport and Belawan port, Medan)

PIU for Surabaya Port

(DG Law Enforcement Java Office, Surabaya)

Note: Intervention at Jakarta (Tanjung Priok) Port handled by DG Law Enforcement HQ

PIU for North Sulawesi Subnational Region

(DG Law Enforcement Manado Section Office – covers Bitung port)

Technical Advisory Committee

MOEF (PD - Chair), Nat govt, local govt, CSOs, experts, etc)

Project Director

Directorate General of Law Enforcement (MOEF)

Project Director

Director of Forest Protection and Surveillance

Responsible Parties and contracted service providers

Other government agencies, departments and CSO partners

Project Management Unit (located in DG Law Enforcement)

National Project Manager

Project Support

- UNDP is the sole GEF Implementing Agency for the project, providing the project assurance and cycle management services. As such, UNDP holds overall accountability and responsibility for the delivery of results to the GEF. Working closely with MoEF, the UNDP Country Office (UNDP CO), specifically the Environment Unit Programme Manager,  will provide the project assurance role and will: 1) provide financial and audit services to the project including budget release and budget revision, 2) oversee financial expenditures against project budgets, 3) ensure that all activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures,  4) ensure that the reporting to GEF is undertaken in line with the GEF requirements and procedures, 5) ensure project objectives achievement and timeliness, 6) facilitate project learning, exchange and outreach within the GEF family, 7) contract the project mid-term and final evaluations, and 8) trigger additional reviews and/or evaluations as necessary and in consultation with the project counterparts. The UNDP Country Director or his designated officials will be represented on the Project Board. Strategic oversight and additional quality assurance will be provided by the UNDP/GEF Regional Technical Advisor (RTA) responsible for the project. This oversight will include ensuring that the project practices due diligence with regard to UNDP’s Social and Environmental Screening Procedure (see Annex 6).

- The Project Manager (PM) will run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board, and head the Project Management Unit (PMU). The Project Manager function will end when the final project terminal evaluation report, and other documentation required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project).  The PM will be responsible and accountable for the implementation of the project. The PM will be paid by project funds. See Annex 5 for the ToR for this position.

- A Technical Advisory Committee (TAC) will be established to provide technical advice and inputs relating to project implementation and will be chaired by the PD with support from the PM.  The members of the TAC will consist of representatives from MoEF, UNDP, AG Office, Ministry of Justice, Quarantine, provincial governments, other relevant government agencies, research and educational organizations, NGOs (including WCS), technical experts and other relevant stakeholders to be agreed by the Project Director. Technical experts may be invited in to discuss specific issues.

- While the TAC will primarily focus on project-related issues, the intention is that this group would evolve to provide technical support to the Gakkum/MoEF on a wide range of issues concerning illegal and unsustainable wildlife trade. During the project period, the TAC will provide a means of updating related stakeholders at the national level about project implementation progress, to share lessons learned from project implementation, to obtain information about and coordinate with related initiatives, and to obtain technical advice on specific issues. There should be an option to request the TAC or a subset of its members to undertake specific project-related tasks, such as preparing or reviewing analytical reports, strategies and action plans, etc. See Annex 5 for ToR for the TAC.

Governance role for project target groups:

- Components 1 and 2 of this project focus on agency staff involved in policy and legislation development, law enforcement, the judiciary, and supportive scientific bodies related to unsustainable and illegal wildlife trade. The key target groups will all be represented on the Project Board (see above), while others including technical advisory organizations will be represented on the Technical Advisory Committee.

- Component 3 focuses on the two demonstration subnational regions in northern Sumatra and northern Sulawesi, where technical assistance would be provided by the Wildlife Conservation Society (WCS) and local CSOs. Component 3 also focuses on demonstration activities at four ports and one airport (three of which fall within the demonstration subnational regions) at which the DG of Customs and Excise of the Ministry of Finance would be an important partner.

- Implementation of local stakeholder involvement will start out with identifying key communities within each demonstration subnational region to work with on specific issues, according to baseline information and consultations during the PPG (see Annexes 11 and 16, on landscape profiles and socioeconomic assessment respectively). It recognizes the need for strong local CSOs and CBOs as effective partners for addressing wildlife trade issues (especially in source areas), and will seek to strengthen existing local CSOs/CBOs and/or develop new CBOs to fulfil such roles. The CSOs/CBOs will be responsible for specific tasks in the demonstration regions and will be supported by central project management and the demonstration region management teams. Experienced staff will be appointed to act as focal points for community engagement and development, and will assign and train community facilitators to lead the community participation and capacity development processes. There will be proactive consideration of the involvement of women and ethnic minorities on local level committees and groups related to project activities including community co-management, training and awareness activities.  See the Results and Partnerships  Section IV for further details.

- UNDP Direct Project Services as requested by Government (if any): The UNDP, as GEF Agency for this project, will provide project management cycle services for the project as defined by the GEF Council.  In addition the Government of Indonesia may request UNDP direct services for specific projects, according to its policies and convenience.  The UNDP and Government of Indonesia acknowledge and agree that those services are not mandatory, and will be provided only upon Government request. If requested, the services would follow the UNDP policies on the recovery of direct costs. These services (and their costs) are specified in the Letter of Agreement (Annex 10). As is determined by the GEF Council requirements, these service costs will be assigned as Project Management Cost, duly identified in the project budget as Direct Project Costs. Eligible Direct Project Costs should not be charged as a flat percentage. They should be calculated on the basis of estimated actual or transaction based costs and should be charged to the direct project costs account codes: “64398- Direct Project Costs – Staff” and “74598- Direct Project Costs – General Operating Expenses (GOE)”.

- Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  In order to accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

Project management:

- The Project Management Unit (PMU) will be established within the Gakkum at MoEF Headquarters in Jakarta headed by the PM and staffed by project hired personnel, and supported by project partner staff according to the terms of related agreements for cooperation between the MoEF and the project partners.

- Senior staff experts from the project partners will provide the primary technical assistance required by the project for policy, legal and regulatory analysis and development, and information management (component 1); institutional capacity building and training (component 2); coordinated law enforcement operations for landscapes and ports, including awareness raising and community engagement (component 3); and knowledge management and monitoring (component 4). These inputs will be delivered through agreements between the project partners, and subcontracts between UNDP CO and service providers. Beyond these inputs, additional technical experts will be recruited to assist the Project Manager, PMU and Gakkum staff with implementation of specific project activities.

- Recruitment of specialist services for the project will be done by the PM (MoEF) in consultation with the UNDP. The PM will also liaise and work closely with all partner institutions to ensure strong coordination with other complementary national programmes and initiatives. The organogram for project management illustrates the working relationship between the main project implementing units and parties.

- The demonstration activities in Component 3 of the project (for two subnational regions, four seaports and one airport) will be coordinated by Project Implementation Units (PIUs), each of which will be led by a manager of the relevant regional or local office of the Gakkum and supported by one Project Liaison Officer per region. Existing regional and local capacity and key stakeholders for IWT enforcement in each of the demonstration regions is outlined in the regional profiles (see Annex 11). Technical assistance will be provided for project implementation in each demonstration region through subcontracted inputs from WCS and other partners. Key features of the two demonstration regions are summarized in Table 6 below:

Table 6. Key features of the project demonstration regions

| Features | Demonstration Regions |  |
| --- | --- | --- |
| Name | Northern Sumatra | Northern Sulawesi |
| Administrative Units | Aceh province and Langkat Regency of North Sumatra province | Gorontalo and North Sulawesi provinces |
| DG Law Enforcement Offices | Medan (Sumatra regional office) | Manado (Section office) Sulawesi regional office is in Makassar |
| Land area | 6,272 km² (Langkat Regency) 58,377 km2 (Aceh Province) Total: 64,649 km2 | 11,257 km2 (Gorontalo) 13,851 km2 (North Sulawesi) Total: 25,108 km2 |
| Population (Jan 2014 Estimate) | 967,535 (Langkat Regency) 4,731,705 (Aceh) Total: 5,699,240 | 1,134,498 (Gorontalo) 2,382,941 (North Sulawesi) Total: 3,517,439 |
| Key Protected Areas and size in ha | Gunung Leuser NP 1,094,692 ha | Bogani Nani Wartabone NP 287,115 ha |
| Globally significant species | Sumatran Tiger, Sumatran Elephant, Sumatran Orang-utan, Sumatran Rhinoceros, Sunda Pangolin | Anoa, Babirusa, Celebes Crested Macaque, Yellow-crested cockatoo, Maleo, Green and Hawksbill Turtles. |
| Key species impacted by wildlife trade | Sunda Pangolin, Sumatran Tiger, Sumatran Elephant, tortoises and freshwater turtles, birds, Greater Slow Loris, macaques, Sun Bear, Sumatran Rhinoceros | Birds sourced locally and in transit, including Yellow-crested cockatoo, parrots and lories, white-eyes, munias, and hornbills. Green and Hawksbill Turtles, sharks, Pangolins, Tarsier, Slow Loris, etc. Many species taken for local bushmeat trade including Anoa, Babirusa, Black Crested Macaque, Maleo eggs. |
| Key ports and markets involved in wildlife trade | Kuala Namu international airport and Belawan seaport, Medan market | Bitung seaport, Manado port, Tomohon market |
| Key local stakeholders | BKSDA, NP staff, local and int CSOs, port authorities, police, etc. | BKSDA, NP staff, local and int CSOs, port authorities, police, etc. |

# Financial Planning and Management

- The total cost of the project is USD 51,937,595.  This is financed through a GEF grant of USD 6,988,853, and USD 44,948,742 in parallel co-financing.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.

Parallel co-financing:  The planned parallel co-financing will be used as follows:

| Co-financing source | Co-financing type | Co-financing amount | Planned Activities/Outputs | Risks | Risk Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Government (MoEF) | Grant | 42,848,742 | Office space for PMU, staff inputs to implementation of all project components, use of government equipment, vehicles, facilities, etc. Routine law enforcement patrols, routine operations to protect forest area, infrastructures procurement and maintenance related to law enforcement activities, training for forest rangers, equipment for monitoring and patrolling, coordination and collaborations on forest protection and surveillance, pre-emptive and preventive activities related to forest protection and surveillance. | Unforeseen budget cuts to relevant agencies | GEF budget allocated for specific activities and outputs sufficient to achieve results |
| CSO (WCS) | Grant | 2,000,000 | Various outputs in Components 1, 2 and 3 | Changes in relations with government | WCS has agreements with MoEF covering project related interventions |
| UNDP | Grant | 100,000 | Strengthen coordination among law enforcement agencies, promoting knowledge exchange, and leveraging possible resources to sustain project results. | Change in Government structure may affect programming priority and participation of relevant key Government partner in the project activities. | UNDP and the project team will provide equal information and written progress report to the beneficiaries both policy maker and technical staff. Further, regular project reporting will be distributed to the project board members and strengthen knowledge management system |

- The actual realization of project co-financing will be monitored during the mid-term review and terminal evaluation process and will be reported to the GEF.

- Budget Revision and Tolerance:  As per the UNDP requirements outlined in the UNDP POPP, the project board can agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the project board. Should the following deviations occur, the Project Manager and UNDP Country Office will seek the approval of the UNDP-GEF team as these are considered major amendments by the GEF: a) budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) introduction of new budget items/or components that exceed 5% of original GEF allocation.

- Project Closure:  Project closure will be conducted as per the UNDP requirements outlined in the UNDP POPP (see  (https://info.undp.org/global/popp/ppm/Pages/Closing-a-Project.aspx) On an exception basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

- Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed including the final clearance of the Terminal Evaluation Report that must be available in English, and after the final project board meeting. The Implementing Partner through a Project Board decision, will notify the UNDP Country Office when the operational closure has been completed. The relevant parties will then agree on the disposal of any equipment that is still the property of UNDP.

- Financial completion:  The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the implementing partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the implementing partner have certified a final Combined Delivery Report (which serves as final budget revision).

- The project will be financially completed within 12 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the Country Office.

- Refund to Donor:  should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

# Total Budget and Work Plan

NOTE to project developer:  This table must be completing using a separate excel file and then copied here.  All sub-totals and totals should be tally. All figures must be “numeric value”, not as “text”. The TBWP table of the ProDoc need to be compliant with the table B and D of the CEO endorsement template).

| Total Budget and Work Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Atlas Proposal or Award ID |  |  | 00094636 |  |  |  |  |  |  |  |  |  |  |
| Atlas Project ID |  |  | 00098732 |  |  |  |  |  |  |  |  |  |  |
| Atlas Proposal or Award Title |  |  | Illegal Wildlife Trade Indonesia |  |  |  |  |  |  |  |  |  |  |
| Atlas Business Unit |  |  | IDN10 |  |  |  |  |  |  |  |  |  |  |
| Atlas Primary Output Project Title |  |  | Combatting Illegal and Unsustainable Trade in Endangered Species in Indonesia |  |  |  |  |  |  |  |  |  |  |
| UNDP-GEF PIMS No. |  |  | 5391 |  |  |  |  |  |  |  |  |  |  |
| Implementing Partner |  |  | Ministry of Environment and Forestry (Directorate General for Law Enforcement of Environment and Forestry) |  |  |  |  |  |  |  |  |  |  |

| GEF Component/Atlas Activity | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Amount Year 6 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT/ OUTCOME 1: Strengthened national policy, legal and institutional framework for regulating commercial wildlife trade and combating illegal wildlife trade | 71200 | International Consultants | - | - | - | - | - |  | - |  |
|  | 71300 | Local Consultants | - | - | - | - | - |  | - |  |
|  | 72100 | Contractual Services-Companies | 68,200 | 54,560 | 54,560 | 54,560 | 54,560 | 54,560 | 341,000 | 1 |
|  | 71600 | Travel | 13,800 | 11,040 | 11,040 | 11,040 | 11,040 | 11,040 | 69,000 | 2 |
|  | 72200 | Equipment & Furniture | 22,000 | - | - | - | - |  | 22,000 | 3 |
|  | 72800 | Information Technology Equipmt | 7,700 | 6,160 | 6,160 | 6,160 | 6,160 | 6,160 | 38,500 | 4 |
|  | 72400 | Communication & audio visual equipment | 3,600 | 2,880 | 2,880 | 2,880 | 2,880 | 2,880 | 18,000 | 5 |
|  | 72500 | Supplies | 3,000 | 2,600 | 2,600 | 2,600 | 2,600 | 2,600 | 16,000 | 6 |
|  | 74200 | AV & print production costs | 7,000 | 5,600 | 5,600 | 5,600 | 5,600 | 5,600 | 35,000 | 7 |
|  | 75700 | Training, Workshops and Confer | 101,700 | 81,360 | 81,360 | 81,360 | 81,360 | 81,360 | 508,500 | 8 |
|  |  | Total Outcome 1 | 227,000 | 164,200 | 164,200 | 164,200 | 164,200 | 164,200 | 1,048,000 |  |
| COMPONENT/ OUTCOME 2: Strengthened institutional capacity for regulatory coordination, implementation and enforcement at the national and international levels | 71200 | International Consultants | - | - | - | - | - | - | - |  |
|  | 71300 | Local Consultants | - | 18,600 | 23,250 | 23,250 | 18,600 | 9,300 | 93,000 | 9 |
|  | 71400 | Contractual Services-Companies | 102,850 | 205,700 | 257,125 | 257,125 | 102,850 | 102,850 | 1,028,500 | 10 |
|  | 71600 | Travel | 17,950 | 35,900 | 35,900 | 35,900 | 35,900 | 17,950 | 179,500 | 11 |
|  | 72200 | Equipment & Furniture | - | 76,000 | - | - | - | - | 76,000 | 12 |
|  | 72800 | Information Technology Equipment | - | 109,500 | 36,500 | - | - | - | 146,000 | 13 |
|  | 72400 | Communication & audio visual equipment | 12,500 | 12,500 | 12,500 | 12,500 | 12,500 | 12,500 | 75,000 | 14 |
|  | 72500 | Supplies | 8,150 | 16,300 | 16,300 | 16,300 | 16,300 | 8,150 | 81,500 | 15 |
|  | 74200 | AV & print production costs | 11,100 | 22,200 | 22,200 | 22,200 | 22,200 | 11,100 | 111,000 | 16 |
|  | 75700 | Training, Workshops and Confer | 42,150 | 84,300 | 84,300 | 84,300 | 84,300 | 42,150 | 421,500 | 17 |
|  |  | Total Outcome 2 | 194,700 | 581,000 | 488,075 | 451,575 | 292,650 | 204,000 | 2,212,000 |  |
| COMPONENT/ OUTCOME 3: Improved enforcement strategy demonstrated and scaled up at key trade ports and connected subnational regions with key ecosystems | 71200 | International Consultants | 12,000 | 24,000 | 24,000 | 24,000 | 24,000 | 12,000 | 120,000 | 18 |
|  | 71300 | Local Consultants | 14,000 | 28,000 | 28,000 | 28,000 | 28,000 | 14,000 | 140,000 | 19 |
|  | 71400 | Contractual Services-Companies | 68,400 | 205,200 | 273,600 | 342,000 | 273,600 | 205,200 | 1,368,000 | 20 |
|  | 71600 | Travel | 37,900 | 75,800 | 75,800 | 75,800 | 75,800 | 37,900 | 379,000 | 21 |
|  | 72200 | Equipment & Furniture | 4,000 | 8,000 | 8,000 | 8,000 | 8,000 | 4,000 | 40,000 | 22 |
|  | 72800 | Information Technology Equipment | 3,200 | 6,400 | 6,400 | 6,400 | 6,400 | 3,200 | 32,000 | 23 |
|  | 72400 | Communication & audio visual equipment | 9,150 | 18,300 | 18,300 | 18,300 | 18,300 | 9,150 | 91,500 | 24 |
|  | 72500 | Supplies | 11,000 | 22,000 | 22,000 | 22,000 | 22,000 | 11,000 | 110,000 | 25 |
|  | 74200 | AV & print production costs | 11,100 | 22,200 | 22,200 | 22,200 | 22,200 | 11,100 | 111,000 | 26 |
|  | 75700 | Training, Workshops and Confer | 73,000 | 146,000 | 146,000 | 146,000 | 146,000 | 73,000 | 730,000 | 27 |
|  |  | Total Outcome 3 | 243,750 | 555,900 | 624,300 | 692,700 | 624,300 | 380,550 | 3,121,500 |  |
| COMPONENT/ OUTCOME 4: Strengthened national policy, legal and institutional framework for regulating commercial wildlife trade and combating illegal wildlife trade | 73400 | International Consultants |  |  | 16,250 |  |  | 19,500 | 35,750 | 28 |
|  | 74100 | Local Consultants | 15,000 | 20,000 | 28,750 | 15,000 | 15,000 | 30,500 | 124,250 | 29 |
|  | 74700 | Travel |  |  | 8,500 | 3,500 | 3,500 | 3,500 | 19,000 | 30 |
|  | 74200 | AV & print production costs | 500 |  | 1,000 | 1,000 | 1,000 | 1,000 | 4,500 | 31 |
|  | 74100 | Professional Services | 4,000 | 4,000 | 9,000 | 4,000 | 4,000 | 9,000 | 34,000 | 32 |
|  | 75700 | Training, Workshops and Confer | 19,000 | 14,000 | 14,000 | 4,000 | 4,000 | 4,000 | 59,000 | 33 |
|  |  | Total Outcome 4 | 38,500 | 38,000 | 77,500 | 27,500 | 27,500 | 67,500 | 276,500 |  |
| Project Management Unit |  |  |  |  |  |  |  |  |  |  |
|  | 74100 | Local Consultants | 26,558 | 26,559 | 26,559 | 26,559 | 26,559 | 26,559 | 159,353 | 34 |
|  | 74700 | Travel | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 24,000 | 35 |
|  | 72200 | Equipment & Furniture | 3,000 |  |  |  |  |  | 3,000 | 36 |
|  | 72800 | Information Technology Equipment | 12,000 | 1,500 | 1,500 | 1,500 | 1,500 | 1,500 | 19,500 | 37 |
|  | 72400 | Communication & audio visual equipment | 3,000 |  |  |  |  |  | 3,000 | 38 |
|  | 72500 | Supplies | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 6,000 | 39 |
|  | 74200 | AV & print production costs | 1,000 | 2,000 | 3,000 | 3,000 | 4,000 | 5,000 | 18,000 | 40 |
|  | 74598/64398 | UNDP Direct Project Costs | 20,000 | 15,000 | 15,000 | 10,000 | 10,000 | 10,000 | 80,000 | 41 |
|  | 74500 | Miscellaneous | 1,000 | 2,000 | 3,000 | 3,000 | 4,000 | 5,000 | 18,000 | 42 |
|  |  | Total Project Management | 71,558 | 52,059 | 54,059 | 49,059 | 51,059 | 53,059 | 330,853 |  |
|  | SUB-TOTAL GEF |  | 775,508 | 1,391,159 | 1,408,134 | 1,385,034 | 1,159,709 | 869,309 | 6,988,853 |  |
|  | PROJECT TOTAL |  |  |  |  |  |  |  | 6,988,853 |  |

Budget Summary

|  | Amount | Amount | Amount | Amount | Amount | Amount | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Year1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 |  |
| GEF | 775,508 | 1,391,159 | 1,408,134 | 1,385,034 | 1,159,709 | 869,309 | 6,988,853 |
| MoEF | 7,143,457 | 7,141,457 | 7,141,457 | 7,141,457 | 7,141,457 | 7,141,457 | 42,848,742 |
| WCS | 200,000 | 360,000 | 360,000 | 360,000 | 360,000 | 360,000 | 2,000,000 |
| UNDP | 25,000 | 25,000 | 25,000 | 25,000 | - | - | 100,000 |
| TOTAL | 8,143,965 | 8,917,616 | 8,934,591 | 8,911,491 | 9,661,166 | 8,370,766 | 51,937,595 |

Budget Notes

|  | ## Component 1 |
| --- | --- |
| 1 | Cost of contracting service providers/companies to, - Prepare & facilitate workshops for 5 key themes (consultancy fee = $60,000; travel = $5500; 2 laptops = $3000; communications = $3000; printing = $3000) (Output 1.1) - Support CITES implementation, permitting process/listed species, and regulatory mechanisms with training workshops and technical support (consultancy fee = $55,000; travel = $5500; 1 laptop = $1500; supplies = $1500; communications = $3000; printing = $3000) (Output 1.1). - Support establishment of national Taskforce (consultancy fee = $22,500; travel = $1500; 1 laptop = $1500; communications = $1500; printing = $1500) and support Taskforce strategy development (consultancy fee = $22,500; travel = $1500) (Output 1.2). - Conduct economic assessment and facilitate consultation workshops (consultancy fee = $38,000; travel = $3000; 1 laptop = $1500; supplies = $1500; communications = $1500; printing = $3000; 2 consultation workshops = $6000 and 1 dissemination workshop = $3000) (Output 1.3). - Conduct study of cost recovery mechanisms and facilitate consultation workshops (consultancy fee = $30,000; travel = $1500; printing = $1500; 2 workshops = $7000) (Output 1.3). - Support formulation of policy and actions on cost-recovery (consultancy fee = $30,000; travel = $3000; communications = $1500; printing = $1500; 2 workshops = $10,500) (Output 1.3). Total estimated cost is $341,000 |
| 2 | Costs towards travel expenses is $96,000 (approx. $11,500/year), which is primary for supporting travel to training, workshops and other meetings (Outputs 1.1-1.2). |
| 3 | Office equipment and furniture for Gakkum/Taskforce (meeting table/chairs, computer table/chairs, filing cabinets etc) (Outputs 1.1-1.2). Total estimated cost is $22,000. |
| 4 | Procure information technology equipment for use by Gakkum and Taskforce including computers (at $1500 each, 10 units), digital cameras (at $1500 each, 3 units), colour printers (at $5000 each, 3 units) and in-focus (at $2000 each, 2 units) (Outputs 1.1-1.2). Total estimated cost is $38,500. |
| 5 | Costs of mobile phone vouchers/communication over project lifespan ($3000/year). Total estimated cost is $18,000. |
| 6 | Cost of purchasing office supplies and stationery for the project office (at approx. $222/month). Total estimated cost is $16,000. |
| 7 | Costs of printing and publication - As part of the development of training materials, policy briefs, technical reports, strategy documents and communication activities for internal meetings, trainings, workshops and conferences. Total estimated cost is $35,000. |
| 8 | Costs of conducting training and training workshops as follows: - Policy revisions including i) Confirmation of policy, legislative and regulatory needs for key partner agencies; ii) Finalization of new/revised Act to replace UU5/1990; iii) Plan to renew the list of protected species in PP7/1999; iv) Regulation/permitting for sustainable breeding of commonly traded wildlife; v) Protection of non-natives species. 6 meeting for each of the 5 core themes with an average meeting cost of $12,500 (this will involve a combination of multiple small meetings and 1-2 larger workshops) and Facilitate improvements to legislative framework (protect ted species list, minimum penalty for wildlife crimes, test/implement anti money-laundering act re IWT) - 5 annual meetings/core theme (30 meetings = $375,000) (Output 1.1). - Support to regulatory mechanisms development - CITES technical training (2 training sessions, $9000 each) and piloting CITES e-permits (2 workshops, $9000 each) (Output 1.1). - Develop National Wildlife Crime Taskforce proposal (2 workshops, $11,250 each), Facilitate the establishment of a National Wildlife Crime Taskforce (4 meetings, $7500 each), and Taskforce IWT meetings (6 meetings, $7500 each) (12 meetings = $97,500) (Output 1.2). Total estimated cost is $508,500 |
|  | ## Component 2 |
| 9 | Cost of contracting local consultants to, - Improved investigator training in forensic analysis (consultancy fee = $45,000) (Output 2.3). - Collaboration with Eijkman Institute and litbang hut (FORDA) for technical support for laboratories (consultancy fee = $48,000) (Output 2.3). Total estimated cost is $93,000 |
| 10 | Cost of contracting service providers/companies to, - Provide technical assistance to strengthen Gakkum to operate in Sumatra, Java, and Wallacea region, with support from WCS-WCU over 6 years (consultancy fee = $300,000; travel = $36,000; 1 laptop = $1500; communications = $30,000; biannual review meetings with WCU and key government partners) (Output 2.1). - Provide technical assistance/training to strengthen Gakkum operation room as intelligence /cybercrime analysis centre for law enforcement operation, with support from the WCS-WCU (consultancy fee = 60,000; travel = $9000; communications = $3000) (Output 2.1). - Provide technical assistance to Gakkum to conduct research on wildlife trafficking, producing various peer-reviewed articles, and strategy formulation, with support from WCS-WCU (consultancy fee = $90,000; travel = $9000; communication = $6000; supplies = $6000; 12 bi-annual coordination meetings = $12,000) (Output 2.1). - Develop training modules with various agencies (e.g. detection, species identification, investigators, prosecutors, international conventions/agreements) (consultancy fee = $126,000; travel = $12,000; communications = $3000; supplies = $3000; 6 meetings = $6000) (Output 2.2). - Deliver high quality training in priority IWT topics (consultancy fee = $210,000 for training over 6 yrs) (Output 2.2). - Training for improved investigator training in forensic analysis (including securing crime scene, DNA sampling (consultancy fee = $51,000) (Output 2.3). - Develop and support a systematic approach to increase media coverage of IWT cases (consultancy fee = $15,000) (Output 2.5). - Use social/online media to distribute IWT case information (consultancy fee = $15,000; 5 meetings =$10,000) (Output 2.5). - Support targeted awareness campaigns (consultancy fee = $15,000) (Output 2.5). Total estimated cost is $1,028,500 |
| 11 | Costs towards travel expenses is $179,500 (approx. $29,917/year), which is primary for supporting travel to training, workshops and other meetings. |
| 12 | Office equipment and furniture for Gakkum operations room (meeting table/chairs, computer table/chairs, filing cabinets etc) and equipment for Gakkum/Eijkmann as determined during project. Total estimated cost is $76,000. |
| 13 | Procure information technology equipment for use by Gakkum and other partnering law enforcement agencies (30 laptops at $1500 each; 3 high spec PCs at $6500 each; 4 i2 software licences at $10,000 each; 3 in-focus at $2000 each; 6 digital cameras at $1000 each, 3 high spec printer at $7500 each). Total estimated cost is $146,000. |
| 14 | Costs of mobile phone vouchers/communication over project lifespan ($12,500/year). Total estimated cost is $75,000. |
| 15 | Cost of purchasing office supplies and stationery for the project office (at approx. $1,132/month). Total estimated cost is $81,500. |
| 16 | Costs of printing and publication - As part of the development of training materials, policy briefs, technical reports, strategy documents, communication pieces (Output 2.5) for internal meetings, trainings, workshops and conferences. Total estimated cost is $111,000. |
| 17 | Costs of conducting training and training workshops as follows: - Strengthen Gakkum (12 meetings/training, $4000 each) (Output 2.1) - Provide technical assistance/training to strengthen Gakkum as intelligence /cybercrime analysis centre for law enforcement operation (3 trainings, $6000 each) (Output 2.1) - Meetings on producing counter-IWT job descriptions and performance criteria (6 meetings, $5000 each) (Output 2.2). - Deliver high quality training in IWT priority topics (24 training workshops, $10,000 each) (Output 2.2). - Preparation for improved investigator training in forensic analysis (6 meetings, $2500 each) (Output 2.3). - Training for improved investigator training in forensic analysis (3 training workshops, $5000 each) (Output 2.3). - Collaboration with Eijkman Institute and litbang hut (FORDA) for technical support for laboratories (6 annual meetings, $2500 each) (Output 2.3). - Develop and implement project communications strategy to reduce IWT demand (3 meetings, $1000 each) (Output 2.5). - Develop and support a systematic approach to increase media coverage of IWT cases (5 meetings, $1500 each) (Output 2.5). - Support targeted awareness campaigns (6 events, $5000 each) (Output 2.5). Total estimated cost is $421,500. |
|  | ## Component 3 |
| 18 | Cost of contracting international consultants to, - Use of PortMATE assessment tool to track improvements in enforcement at all five ports in line with the global wildlife trafficking and ports project (consultancy fee = $40,000) (Output 3.1) - Capacity building / training activities (taken from global ports project) (consultancy fee = $40,000) (Output 3.1) - Pilot Dubai Customs World system at Surabaya port as contribution to / with TA from the global wildlife trafficking and ports project (consultancy fee = $40,000) (Output 3.1). Total estimated cost is $120,000 |
| 19 | Cost of contracting local consultants to, - Information sharing mechanisms (national level forum discussion between relevant agencies) (consultancy fee = $7500) (Output 3.1). - To consider: development of wildlife handling facilities for each port, with trained staff, and procedures for how to dispose of confiscated wildlife quickly and efficiently in terms of welfare, supporting conservation efforts, etc., without impacting legal evidence requirements for cases (consultancy fee = $7500) (Output 3.1). - Engage local NGOs/CSOs to conduct awareness programmes in schools, churches, mosques, and community centres + capacity development for communities (consultancy fee = $125,000) Total estimated cost is $140,000. |
| 20 | Cost of contracting service providers/companies to, - Provide technical support to set up subnational level IWT forum to facilitate inter-agency coordination for each demonstration region based on series of stakeholder consultations to detail wildlife trade chains, key species involved, key actors (consultancy fee = $40,000) (Output 3.2). - Coordination of information through CID, customs, quarantine, INTERPOL, immigration, anti-corruption agency and other information systems to combat IWT (consultancy fee = $63,000; travel = $12,000; supplies = $3000; 6 meetings = $6000) (Output 3.2). - Provide technical assistance to support Gakkum to establish/expand in northern Sumatra and northern Sulawesi demonstration regions, technical assistance provided by WCS-WCU (consultancy fee = $70,000 for 2 landscapes; travel = $10,000; supplies = $2000; printing = $4000) (Output 3.3). - Work with local stakeholders to monitor and report IWT in northern Sumatra and northern Sulawesi demonstration sites over 6 years (Consultancy fees for 2 landscape teams = $240,000; travel = $36,000; supplies = $24,000; printing = $24,000; monthly stakeholder meetings over 6 yrs = $48,000); and in Ulu Masen (1 landscape; consultancy fee = $60,000; travel = $24,000; supplies = $12,000; printing = $12,000; monthly stakeholder meetings over 6 yrs = $24,000) (Output 3.3). - Employment of local people as informants (NGO consultancy fee = $144,000; community informant honorarium = $240,000; travel $36,000; 1 laptop = $1500; digital camera = $1500; supplies = $12,000; printing = $18,000; 6 annual strategic planning meetings $24,000) (Output 3.4). - Engagement of local communities in patrolling, market surveillance, HWC mitigation/livelihood issues (consultancy fee = $72,000; travel = $18,000; 2 laptops = $3000; communications = $18,000; supplies = $12,000; printing = $18,000; 6 meetings $36,000) (Output 3.4). Total estimated cost is $1,368,000. |
| 21 | Costs towards travel expenses is $379,000 (approx. $63,167/year), which is primary for supporting travel to training, workshops and other meetings. |
| 22 | Office equipment and furniture for partner agencies to monitor online IWT/hold inter-agency meetings at Gakkum subnational offices (meeting table/chairs, computer table/chairs, filing cabinets etc). Total estimated cost is $40,000. |
| 23 | Procure information technology equipment for use by Gakkum and other partnering law enforcement agencies in 2 subnational demonstration sites (8 laptops = $12,000; 4 digital cameras = $4000; 2 in-focus = $4000; 2 colour printers = $10,000). Total estimated cost is $32,000. |
| 24 | Costs of mobile phone vouchers/communication over project lifespan ($15,250/year). Total estimated cost is $91,500. |
| 25 | Cost of purchasing office supplies and stationery for the project office (at approx. $1528/month). Total estimated cost is $110,000. |
| 26 | Costs of printing and publication - As part of the development of training materials, policy briefs, technical reports, strategy documents, communication pieces for internal meetings, trainings, workshops and conferences. Total estimated cost is $111,000. |
| 27 | Costs of conducting training and training workshops as follows: - Use of PortMATE assessment tool to track improvements in enforcement at all five ports in line with the global wildlife trafficking and ports project (5 ports, meetings to assessment/review/adapt, $20,000/port) (Output 3.1). - Capacity building / training activities (taken from global ports project) (5 port training workshops, $20,000 each) (Output 3.1). - Pilot Dubai Customs World system at Surabaya port as contribution to / with TA from the global wildlife trafficking and ports project (5 annual review meetings, $20,000 each) (Output 3.1). - Information sharing mechanisms (national level forum discussion between relevant agencies) (6 annual multi-agency meetings, $4000 each) (Output 3.1). - To consider: development of wildlife handling facilities for each port, with trained staff, and procedures for how to dispose of confiscated wildlife quickly and efficiently in terms of welfare, supporting conservation efforts, etc., without impacting legal evidence requirements for cases (6 meetings, $4000 each) (Output 3.1). - Operationalise subnational level IWT forum to facilitate inter-agency coordination for each demo region based on series of stakeholder consultations to detail wildlife trade chains, key species involved, key actors (2 multi-agency workshops, $18,500 each) (Output 3.2). - Coordination meetings and information sharing through CID, customs, quarantine, INTERPOL, immigration, anti-corruption agency and other information systems to combat IWT (6 annual meetings, $7500 each) (Output 3.2). - Gakkum to establish/expand in northern Sumatra and northern Sulawesi demonstration regions (12 meetings, $7500 each) (Output 3.3). - Engagement of local communities in patrolling, market surveillance, local informant networks (6 Gakkum local coordination meetings/landscape, $7500 each) (Output 3.3). - Engage local NGOs/CSOs to conduct awareness programmes in schools, churches, mosques, and community centres + capacity development for communities (2 landscapes and 48 meetings/events, $1800 each) (Output 3.4). Total estimated cost is $730,000. |
|  | COMPONENT 4 |
| 28 | International Consultant for MTR (16250) Y3 and TE (19500) Y6 (Output 4.2) |
| 29 | Local Consultant for MTR (8750) Y3 and TE (10500) Y6; updating GEF GWP TT for MTR Y3 and TE Y6 (5000 and 5000) (Output 4.2); develop IWT indicators Y2 (5000) (Output 4.2); KM consultant for lessons learned 2000/year over 6 yrs (Output 4.1); M&E and gender mainstreaming consultant 4000 / year over 6 yrs (output 4.2); Local Consultant for communications inputs (output 4.1) at 1000/m (8000 each year over 6 yrs) |
| 30 | Travel for MTR (5000) and TE (5000) (Output 4.2); travel to GWP and International conference events for KM purposes at 3000/trip in years 3,4,5,6 and case studies travel at $2000 (Output 4.1) |
| 31 | Printing of case studies (4000) and communications strategy (500) (Output 4.1) |
| 32 | Audit 4000/year over 6 years; translation for MTR and TE 5000 each (Output 4.2) |
| 33 | PB meetings and TAC meetings twice each year at $1000 each; Inception workshop Y1 (15000), National Indicators workshop Y2 (10,000); MTR workshop (10,000) (Output 4.2) |
|  | PROJECT MANAGEMENT COSTS |
| 34 | Project Manager (local consultant full time over 6 years starting 2,000/month); Accountant/admin assistant (local consultant full time over 6 years starting 600/month). The shortfall amount will be covered by co-financing. |
| 35 | PMU travel at 4,000/year |
| 36 | PMU office equipment and furniture 3,000 |
| 37 | PMU IT equipment, including: 4 computers (incl. for comms consultant and M&E consultant inputs) 8000, 1 Combo Printer/Scanner/Fax 500; 1 Laser printer 500, 1 Digital camera 1000, IT Accessories 3500, and Software purchase and subscription renewals 6000. |
| 38 | Communication and AV equipment LCD projector, mobile phones, etc. |
| 39 | PMU office supplies- stationery, printer cartridges, etc |
| 40 | AV and print production costs – for printing and circulating project technical reports, publicity materials, lessons learned, terminal report 18,000 |
| 41 | UNDP Direct Project Costs – Refer to LOA in Annex 10 for breakdown of itemized services and their associated costs. |
| 42 | Miscellaneous – to allow for contingency, PMU translation needs, administrative services |

# Legal Context

Consistent with the Article III of the Standard Basic Assistance Agreement (SBAA), the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document [and the Project Cooperation Agreement between UNDP and the Implementing Partner].

The Implementing Partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml. This provision must be included in all sub-contracts or sub-agreements entered into under/further to this Project Document”.

Note that any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Mandatory Annexes

- Multi-year Workplan

- Monitoring Plan

- Evaluation Plan

- GEF Global Wildlife Programme Tracking Tool at baseline

- Terms of Reference for A) Project Board, B) TACC and C) PMU staff

- UNDP Social and Environmental and Social Screening Template (SESP)

- UNDP Project Quality Assurance Report  “Pending”

- UNDP Risk Log “Pending”

- Results of the capacity assessment of the project implementing partner and HACT micro assessment

- Additional agreements: 1) Co-financing letters and 2) Letter of Agreement LOA “pending”

See separate files for annexes

# Optional Annexes

- Landscape profiles for the demonstration subnational regions

- A-Lists of people consulted during project development

12.  B-Attendance list

- Situation analysis

- Baseline report on databases

- Baseline report on policy, legal and regulatory framework

- Baseline socio-economic assessment

- Baseline assessments of demonstration ports

- Capacity development scorecard for DG Law Enforcement, MOEF

- Stakeholder Engagement Strategy

Annex 1

Multi Year Workplan:

-See separate files-

Annex 2

Monitoring Plan

The Project Manager/Coordinator will collect results data according to the following monitoring plan.

| Monitoring | Indicators | Data source/Collection Methods | Frequency | Responsible for data collection | Means of verification | Assumptions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
| Project objective: To reduce the volume of unsustainable wildlife trade and the rate of loss of globally significant biodiversity in Indonesia and East and South-East Asia | 0.1: Extent to which legal or policy or institutional frameworks are in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems. (IRRF Output 2.5 indicator 2.5.1) | Consultations with government institutions and partners to review policy and legal frameworks status | Annually | Project Manager/ M&E Officer Coordinator IP | Official government notifications and announcements for new legislation Monitoring progress reports | Assumptions: There is sufficient political will to support revision of key policies, laws and regulations There are no major bureaucratic delays in seeing revisions through to approval stage Risks: Political change |
|  | 0.2: Number of direct project beneficiaries: - Number of government agency staff including enforcement officers who improved their knowledge and skills on IWT due to the project (m/f) - Number of local people in project demonstration areas benefiting from engagement in conservation activities, reduced HWC impacts and improved livelihoods (m/f) | Review of project reports; questionnaire surveys for target communities in demo areas | MTR and TE | Project Manager/ M&E officer Coordinator IP | Reports from consultation processes Survey Results Monitoring progress reports | Assumptions: Continuing level of political will to support the project intervention Good relationship continues between enforcement agencies and key CSO partners Risks: Communities do not accept project intervention in their areas |
|  | 0.3: Expert evaluation of IWT annual volume (number of incidents or total number of animals) in Indonesia based on the WCS IWT database | WCS-WCU database | Annually | Project Manager/ M&E officer Coordinator IP | WCS-WCU database reports | Assumptions: Improved legislation (Component 1) and law enforcement (Component 2 and 3) will allow the Indonesian government to decrease the level of unsustainable WT. Risks: Data are very incomplete or unreliable |
|  | 0.4: Number of individuals of IWT flagship species (Sumatran Tiger, Sumatran Rhinoceros, Sumatran Elephant, Black-crested macaque, Anoa and Babirusa) killed by poachers annually in the 2 project demonstration areas | WCS-WCU database | Annually | Project Manager/ M&E officer Coordinator IP | WCS-WCU database; project reports | Decrease in IWT will lead to decrease in poaching as a main driver of species loss. Risks: Increasing value and demand of wildlife products drives IWT and poaching rates up still higher |
| Project Outcome 1 Strengthened national policy, legal and institutional framework for regulating commercial wildlife trade and combating illegal wildlife trade indicated by: | 1.1: The following key legislation gaps are addressed by improved IWT legislation documents approved by Government: -Minimum fines and sentences increased to provide deterrent effect; -Non-native endangered species including elephant, rhinoceros, big cat and pangolin species given legal protection -Indonesian protected species list updated to include all CITES Appendix 1 and globally threatened species - Authority of forestry civil investigators improved - Detention/prison evaluation for creating deterrent effect and rehabilitation for criminals. - online trade regulation to address online wildlife trafficking. | Consultations with government institutions and partners to review changes in IWT legislation | Annually | Project Manager/ M&E Officer Coordinator IP | Official government notifications and announcements for new legislation Monitoring progress reports | Assumptions: There is sufficient political will to support revision of key policies, laws and regulations Risks: bureaucratic delays in seeing revisions through to approval stage |
|  | 1.2: Inter-agency Taskforce in place and operational as indicated/measured by the signing of an inter-agency agreements targeting IWT | Consultations with MOEF staff | Annually | Project Manager/ M&E officer Coordinator IP | Official government notifications and announcements for new agreements; Monitoring progress reports | Assumptions: National organizations are willing to collaborate on IWT Risks: bureaucratic delays stall the finalization and approval of agreements |
| Project Outcome 2 Strengthened institutional capacity for regulatory coordination, implementation and enforcement at the national and international levels | 2.1: Strengthened institutional capacity to combat IWT as indicated by i) the ICCWC Indicator Framework (note – baselines to be determined in year 1), ii) UNDP Capacity Development Scorecard for Gakkum (see Annex 18), and iii) iii) Operational status of Gakkum’s Information System | i) ICCWC Indicator Framework assessments ii) UNDP CD Scorecard assessments iii) Operational database within Gakkum | At project inception; MTR and TE | Project Manager/ M&E officer Coordinator IP | ICCWC Indicator Framework assessment reports; UNDP CD Scorecard assessment reports; Information System is fully operational and operated by trained staff | Assumptions: Assessments are carried out consistently between years and agencies Strengthened inter-agency collaboration is reflected in the increased scores Political support continues for DG Law Enforcement’s role in managing the information system on WT Risks: Difficulty to find trained staff to conduct ICCWC IF assessments Lack of collaboration from key partners constrains effective information flow |
|  | 2.2: - annual number seizures/arrests - annual number of successful prosecutions | WCU database | Annually | Project Manager/ M&E officer Coordinator IP | WCU database; project reports | Assumptions: Official national statistics are made available to the project as required in a timely manner Risks: Corruption and interference in enforcement operations |
|  | 2.3: - Annual number of joined up transnational counter-IWT operations- - Annual number of seizures as a result of transnational counter-IWT operations | Gakkum information system | Annually | Project Manager/ M&E officer Coordinator IP | Official announcements reporting on transnational IWT operations and seizures; Gakkum/MOEF annual reports | Assumptions: Political support is sustained for international collaboration with key countries Risks: Language, communication and cultural barriers inhibit transnational joint operations |
| Project Outcome 3 Improved enforcement strategy demonstrated and scaled up at key trade ports and connected subnational regions with key ecosystems | 3.1: Enforcement effectiveness at 5 key trade ports (Jakarta, Surabaya, Bitung, Belawan and Kualanamu airport), indicated by: - Annual PortMATE assessment tool scores (average score for KSDA, Customs, Port Management Authority at each port) | PortMATE assessments at demo ports | Annually | Project Manager/ M&E officer Coordinator IP | PortMATE assessment reports | Assumptions: Statistics reflect an increase in enforcement effectiveness and not simply improved monitoring and reporting Risks: Lack of interest in participating in annual PortMATE assessments |
|  | 3.2: Effective enforcement of two subnational regions known to include significant wildlife trade routes, measured by: - annual number of IWT seizures at the project sites - annual number of IWT investigations leading to arrests at the project sites; - annual number of successful IWT prosecutions at the project sites | Consultations with regional Gakkum staff and other key project stakeholders including INP, Customs, WCS; WCS-WCU database | Annually | Project Manager/ M&E officer Coordinator IP | Official announcements on IWT seizures, investigations and prosecutions; project reports; WCS-WCU database | Assumptions: Assessments are carried out consistently between years and sites Risks: Lack of interest in collaboration by agencies other than IP |
| Project Outcome 4 Implementation and upscaling/replication of project approaches at national and international levels is supported by effective knowledge management | 4.1: - number of project lessons used by other national and international projects. | Review of GEF GWP website, other websites and social media, reports on related projects, technical and scientific publications; communication with related project staff | Annually | Project Manager/ M&E officer Coordinator IP | Reports from related projects; communications with GWP and related project staff | Assumptions: project lessons are promptly and widely disseminated to other relevant projects. Risks: Synthesis and translation of M&E information into generation of lessons learned is often hampered by time constraints. |
| Mid-term GEF Tracking Tools | GEF GWP TT | Baseline GEF GWP Tracking Tool included in Annex 4 | After 2nd PIR submitted to GEF | Project Manager and IP | Completed GEF GWP Tracking Tool | Assumptions: Continuous monitoring of project results on a quarterly basis will facilitate completion of the mid-term GEF GWP Tracking Tool prior to the MTR evaluation mission. Project team has the capacity and resources to complete the Tracking Tool Risks: Project team fails to conduct periodic monitoring of project results and therefore compromise the quality and completeness of the tracking tool. Lack of consistency in how the tracking tool are completed. |
| Final GEF Tracking Tools | GEF GWP TT | Baseline GEF GWP Tracking Tool included in Annex 4 | After final PIR submitted to GEF | Project Manager and IP -NEC | Completed GEF GWP Tracking Tool | Assumptions: continuous monitoring of project results on a quarterly basis will facilitate completion of the GEF GWP tracking tool prior to the TE mission. Project team has the capacity and resources to complete the Tracking Tool Risks: Project team fails to conduct periodic monitoring of project results and therefore compromise the quality and completeness of the tracking tool. Lack of consistency in how the tracking tools are completed. |
| Mid-term Review and management response | N/A | Independent evaluators | Submitted to GEF same year as 3rd PIR | Independent Evaluators as contracted by UNDP | UNDP Cleared MTR Report | Assumptions: The budgeted resources are sufficient to support a comprehensive MTR process. Risks: The MTR team do not have access to all stakeholders and fully updated and completed information on the project There is a delayed or ineffective management response to the MTR findings by the Project Board. |
| Terminal Evaluation and management response | N/A | Independent evaluators | Initiate 3 months before operation closure; to be submitted to GEF within three months of operational closure | Independent Evaluators as contracted by UNDP | UNDP Cleared TE Report | Assumptions: The budgeted resources are sufficient to support a comprehensive TE process. Risks: The TE team do not have access to all stakeholders and fully updated and completed information on the project. There is a delayed or ineffective management response to the TE findings by the Project Board. |

Annex 3

Evaluation Plan:

| Evaluation Title | Planned start date Month/year | Planned end date Month/year | Included in the Country Office Evaluation Plan | Budget for consultants | Other budget (i.e. travel, site visits etc…) | Budget for translation |
| --- | --- | --- | --- | --- | --- | --- |
| Terminal Evaluation | Add date: 3 months before operation closure | Add date: To be submitted to GEF within three months of operational closure | Yes/No Mandatory | USD 35,000 | Travel: 5,000 | 5,000 |
| Total evaluation budget |  |  |  | USD 45,000 |  |  |

Annex 4

GEF Global Wildlife Programme Tracking Tool Baseline:

-See separate files-

Annex 5

Terms of Reference:

Terms of Reference for the Project Board

The Project Board (PB) will serve as the project’s decision-making body. It will meet according to necessity, at least  twice each year, to review project progress, approve project work plans and approve major project deliverables. The PB is responsible for providing the strategic guidance and oversight to project implementation to ensure that it meets the requirements of the approved Project Document and achieves the stated outcomes. The PB’s role will include:

- providing strategic guidance to project implementation;

- assuring coordination between various donor funded and government funded projects and programmes;

- ensuring coordination with various government agencies and their participation in project activities;

- approving annual project work plans and budgets, at the proposal of the Project Manager;

- approving any major changes in project plans or programmes;

- overseeing reporting in line with GEF requirements;

- ensuring commitment of human resources to support project implementation, arbitrating any issues within the project;

- negotiating solutions between the project and any parties beyond the scope of the project;

- overall project evaluation; and

- ensuring that UNDP Social and Environmental Screening Procedure safeguards are applied to project implementation.

These terms of reference will be finalized during the Project Inception Workshop.

Terms of Reference for the Technical Advisory Committee (TAC)

The TAC will provide technical advice and inputs relating to project implementation and will be chaired by the PD with support from the PM.  The members of the TAC will consist of representatives from MoEF, UNDP, other relevant government agencies, research and educational organizations, NGOs (including WCS), technical experts and other relevant stakeholders to be agreed by the Project Board. Technical experts may be invited in to discuss specific issues. Indicative Terms of Reference are as follows. These will be reviewed by the Project Board during project inception and may be extended as necessary.

- Review planned activities and ensure that they are technically sound and that, wherever possible, there is integration and synergy between the various project components during planning and implementation;

- promote technical coordination between institutions, where such coordination is necessary and where opportunities for synergy and sharing of lessons exist;

- provide technical advice and guidance on specific issues concerning illegal and unsustainable wildlife trade;

- share information on project progress and lessons learned with related stakeholders at the national level;

- the TAC or a subset of its members may be requested to undertake specific project-related tasks, such as preparing or reviewing analytical reports, strategies and action plans, etc.;

- Other tasks as indicated by the Project Board

Terms of Reference for Key Project Staff

Project Director

Background

The Project Director (PD) is the Deputy Director General of Law Enforcement of the MOEF, who will be accountable to the MoEF and UNDP for the achievement of objectives and results in the assigned Project. The PD will be part of the Project Steering Committee and answer to it. The PD will be financed through national government funds (co-financing), whose appointment will be made by the Director General of Law Enforcement, in consultation with the UNDP CO.

Duties and Responsibilities

- Serve as a member of the Project Board.

- Supervise compliance with objectives, activities, results, and all fundamental aspects of project execution as specified in the project document.

- Supervise compliance of project implementation with MoEF policies, procedures and ensure consistency with national plans and strategies.

- Facilitate coordination with other organizations and institutions that will conduct related conservation activities for the protected area system, same target landscapes or same themes from elsewhere in Indonesia, especially related to the UNDP/GEF E-PASS project in Sulawesi and UNDP/GEF Project Transforming effectiveness of biodiversity conservation in priority Sumatran landscapes.

- Participate in project evaluation, testing, and monitoring missions.

- Coordinate with national governmental representatives on legal and financial aspects of project activities.

- Coordinate and supervise government staff inputs to project implementation.

- Coordinate, oversee and report on government cofinancing inputs to project implementation.

Project Manager

Background

The Project Manager (PM), will be locally recruited following UNDP procedure, with input to the selection process from the Project partners. The position will be appointed by the project implementing agencies and funded entirely from the Project. The PM will be responsible for the overall management of the Project, including the mobilisation of all project inputs, supervision over project staff, consultants and sub-contractors. The PM will report to the PD in close consultation with the assigned UNDP Programme Manager for all of the Project’s substantive and administrative issues. From the strategic point of view of the Project, the PM will report on a periodic basis to the Project Board, based on the PD’s instruction. Generally, the PM will support the PD who will be responsible for meeting government obligations under the Project, under the NIM execution modality. The PM will perform a liaison role with the government, UNDP and other UN agencies, CSOs and project partners, and maintain close collaboration with other donor agencies providing co-financing. The PM will work closely with the Project Implementation Unit Coordinators.

Duties and Responsibilities

- Plan the activities of the project and monitor progress against the approved work-plan.

- Supervise and coordinate the production of project outputs, as per the project document in a timely and high quality fashion.

- Coordinate all project inputs and ensure that they are adhere to UNDP procedures for nationally executed projects.

- Supervise and coordinate the work of all project staff, consultants and sub-contractors ensuring timing and quality of outputs.

- Coordinate the recruitment and selection of project personnel, consultants and sub-contracts, including drafting terms of reference and work specifications and overseeing all contractors’ work.

- Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments, or reimbursement using the UNDP provided format.

- Prepare, revise and submit project work and financial plans, as required by Project Board and UNDP.

- Monitor financial resources and accounting to ensure accuracy and reliability of financial reports, submitted on a quarterly basis.

- Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log.

- Liaise with UNDP, Project Board, relevant government agencies, and all project partners, including donor organisations and CSOs for effective coordination of all project activities.

- Facilitate administrative support to subcontractors and training activities supported by the Project.

- Oversee and ensure timely submission of the Inception Report, Combined Project Implementation Review/Annual Project Report (PIR/APR), Technical reports, quarterly financial reports, and other reports as may be required by UNDP, GEF and other oversight agencies.

- Disseminate project reports and respond to queries from concerned stakeholders.

- Report progress of project to the steering committees, and ensure the fulfilment of PSC directives.

- Oversee the exchange and sharing of experiences and lessons learned with relevant community based integrated conservation and development projects nationally and internationally.

- Assist community groups, municipalities, CSOs, staff, students and others with development of essential skills through training workshops and on the job training thereby increasing their institutional capabilities.

- Encourage staff, partners and consultants such that strategic, intentional and demonstrable efforts are made to actively include women in the project, including activity design and planning, budgeting, staff and consultant hiring, subcontracting, purchasing, formal community governance and advocacy, outreach to social organizations, training, participation in meetings; and access to program benefits.

- Assists and advises the Project Implementation Units responsible for activity implementation in the target sites.

- Carry regular, announced and unannounced inspections of all sites and the activities of the Project Implementation Units.

Required skills and expertise

- A university degree (MSc or PhD) in a subject related to natural resource management or environmental sciences.

- At least 10 years of experience in natural resource management (preferably in the context of wildlife conservation and law enforcement).

- At least 5 years of demonstrable project/programme management experience.

- At least 5 years of experience working with ministries, national or provincial institutions that are concerned with natural resource and/or environmental management.

Competencies

- Strong leadership, managerial and coordination skills, with a demonstrated ability to effectively coordinate the implementation of large multi-stakeholder projects, including financial and technical aspects.

- Ability to effectively manage technical and administrative teams, work with a wide range of stakeholders across various sectors and at all levels, to develop durable partnerships with collaborating agencies.

- Ability to administer budgets, train and work effectively with counterpart staff at all levels and with all groups involved in the project.

- Ability to coordinate and supervise multiple Project Implementation Units in their implementation of technical activities in partnership with a variety of subnational stakeholder groups, including community and government.

- Strong drafting, presentation and reporting skills.

- Strong communication skills, especially in timely and accurate responses to emails.

- Strong computer skills, in particular mastery of all applications of the MS Office package and internet search.

- Strong knowledge about the political and socio-economic context related to the Indonesian protected area system, biodiversity conservation and law enforcement at national and subnational levels.

- Excellent command of English and Indonesian languages.

Project Monitoring and Evaluation and Gender Mainstreaming Officer

Under the overall supervision and guidance of the Project Manager, the M&E and GM Officer will have the responsibility for monitoring and evaluation and gender mainstreaming. The M&E and GM Officer will work closely with the Communications Officer on knowledge management aspects of the project. Specific responsibilities will include:

- Monitor project progress and participate in the production of progress reports ensuring that they meet the necessary reporting requirements and standards;

- Oversee and ensure the implementation of the project’s M&E plan, including periodic appraisal of the Project’s Theory of Change and Results Framework with reference to actual and potential project progress and results;

- Align the project’s M&E requirements with those of GoI, and ensure that both GoI and UNDP M&E requirements are effectively coordinated and addressed;

- Develop and coordinate implementation of the project gender mainstreaming strategy, monitor gender mainstreaming effectiveness according to indicators in the M&E Plan and gender strategy;

- Oversee and guide the design of surveys/ assessments commissioned for monitoring and evaluating project results;

- Facilitate mid-term and terminal evaluations of the project;

- Facilitate annual reviews of the project and produce analytical reports from these annual reviews;

- Liaise with UNDP Indonesia and responsible parties for implementation of project activities in matters related to M&E and knowledge resources management;

- Visit project sites as and when required to appraise project progress on the ground and validate written progress reports.

The Project M& E Officer will be recruited based on the following qualifications

- Masters degree, preferably in the field of environmental or natural resources management;

- At least five years of relevant work experience preferably in a project management setting involving multi-lateral/ international funding agency. Previous experience with UN project will be a definite asset;

- Significant experience in collating, analyzing and writing up results for reporting purposes;

- Very good knowledge of results-based management and project cycle management, particularly with regards to M&E approach and methods. Formal training in RBM/ PCM will be a definite asset;

- Knowledge and working experience of the application of gender mainstreaming in international projects;

- Understanding of biodiversity conservation, law enforcement, sustainable livelihoods and associated issues;

- Very good inter-personal skills;

- Proficiency in computer application and information technology.

- Excellent language skills in English (writing, speaking and reading) and in Bahasa Indonesia

Project Assistant

Under the guidance and supervision of the Project Manager, the Project Assistant will carry out the following tasks:

- Assist the Project Manager in day-to-day management and oversight of project activities;

- Assist the M&E officer in matters related to M&E and knowledge resources management;

- Assist in the preparation of progress reports;

- Ensure all project documentation (progress reports, consulting and other technical reports, minutes of meetings, etc.) are properly maintained in hard and electronic copies in an efficient and readily accessible filing system, for when required by PB, TAC, UNDP, project consultants and other PMU staff;

- Provide PMU-related administrative and logistical assistance.

The Project Assistant will be recruited based on the following qualifications:

- A Bachelors degree or an equivalent qualification;

- At least three years of work experience preferably in a project involving biodiversity conservation, natural resource management and/or sustainable livelihoods. Previous experience with UN project will be a definite asset;

- Very good inter-personal skills;

- Proficiency in the use of computer software applications especially MS Word and MS Excel.

- Excellent language skills in English (writing, speaking and reading) and in Bahasa Indonesia

Project Accountant

Under the guidance and supervision of the Project Manager, the Project Accountant will have the following specific responsibilities:

- Keep records of project funds and expenditures, and ensure all project-related financial documentation are well maintained and readily available when required by the Project Manager;

- Review project expenditures and ensure that project funds are used in compliance with the Project Document and GoI financial rules and procedures;

- Validate and certify FACE forms before submission to UNDP;

- Provide necessary financial information as and when required for project management decisions;

- Provide necessary financial information during project audit(s);

- Review annual budgets and project expenditure reports, and notify the Project Manager if there are any discrepancies or issues;

- Consolidate financial progress reports submitted by the responsible parties for implementation of project activities;

- Liaise and follow up with the responsible parties for implementation of project activities in matters related to project funds and financial progress reports.

The Project Accountant will be recruited based on the following qualifications:

- A Bachelors degree or an advanced diploma in accounting/ financial management;

- At least five years of relevant work experience preferably in a project management setting involving multi-lateral/ international funding agency. Previous experience with UN project will be a definite asset;

- Proficiency in the use of computer software applications particularly MS Excel;

- Excellent language skills in English (writing, speaking and reading) and in Bahasa Indonesia

Project Communications Officer

Under the overall supervision and guidance of the Project Manager, the Communications Officer will have the responsibility for leading knowledge management outputs in Component 4 and developing the project communications strategy at the project outset and coordinating its implementation across all project components. The Communications Officer will work closely with the M&E Officer on knowledge management aspects of the project. Specific responsibilities will include:

- Develop a project communications strategy / plan, incorporate it with the annual work plans and update it annually in consultation with project stakeholders; coordinate its implementation

- Coordinate the implementation of knowledge management outputs of the project;

- Coordinate and oversee the implementation of public awareness activities across all project components;

- Facilitate the design and maintenance of the project website/webpages and ensure it is up-to-date and dynamic;

- Facilitate learning and sharing of knowledge and experiences relevant to the project;

The Project Communications Officer will be recruited based on the following qualifications:

- A Bachelors degree, preferably in the field of community development or natural resource / environmental management;

- A communications qualification (diploma, Bachelors degree)

- At least three years of relevant work experience of communications for project or programme implementation, ideally involving international donors. Previous experience with UN projects will be a definite asset;

- Previous experience in developing and implementing communications strategies for organizations or projects

- Strong professional working capacity to use information and communications technology, specifically including website design and desk top publishing software

- Understanding of illegal wildlife trade, biodiversity conservation, sustainable livelihoods and associated issues;

- Very good inter-personal skills

- Excellent language skills in English (writing, speaking and reading) and in Bahasa Indonesia

Annex 6

Social and Environmental Screening for CEO Endorsement Stage:

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document. Please refer to the Social and Environmental Screening Procedure for guidance on how to answer the 6 questions.]

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | Combatting illegal and unsustainable trade in endangered species in Indonesia |
| - Project Number | 5391 |
| - Location (Global/Region/Country) | Indonesia |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

The project focuses on improving the regulatory and institutional framework to ensure effective action to combat illegal wildlife trade and regulate the legal wildlife trade, at national, provincial and landscape levels in Indonesia. This will include enhancing the effectiveness of law enforcement agencies and their agents, which has the potential to enhance overall governance in Indonesia, including recognition of human rights and sound application of the law. Enhanced law enforcement does also have the potential to lead to negative impacts on some people, if not properly managed. The project will therefore put in place rigorous controls to ensure that all activities are consistent with Indonesian law and international legal obligations, including the Universal Declaration on Human Rights. Component 1 will ensure good governance, including respect for human rights, through the improvements in the institutional and regulatory framework governing wildlife trade in Indonesia. Through the capacity-building component (Component 2) the project will ensure that rights of people involved with or impacted by wildlife trade are respected, including the rights of those accused of wildlife trafficking to fair treatment under the legal system. Under Component 3, the project will work closely and in a culturally appropriate context on crime reduction with the leaders of villages in wildlife trade sources areas adjacent to the Leuser ecosystem in Northern Sumatra (a critical tiger, Asian elephant, rhinoceros, orang-utan and pangolin landscape) and to Bogani Nani Wartabone NP in Northern Sulawesi (a key ecosystem for endemic globally threatened species including babirusa, anoa and maleo fowl).

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The project will integrate gender equality and a social inclusion perspective in programme/project planning and implementation. This is to ensure equal participation of both women and men and people from different economic and social backgrounds in project planning and decision making, in order to make certain that neither of the groups is disadvantaged by the project activities and will derive equal benefits from the project activities. In order to achieve gender mainstreaming in this project, the PPG (project preparation phase) has undertaken baseline assessments in the project landscapes to identify the measures needed to ensure the equal participation of men and women so as to fully take into account the different perspectives, priorities and socio-economic realities that women and men face. The equal participation of women has been taken into account in project design for planning and decision making among the key stakeholders, including the national, provincial and local government agencies and local communities. Project design pertaining to institutional strengthening and capacity building has also ensured that target trainees will include both sexes and institutional development will mainstream gender in the institutional system and decision making mechanisms. At the landscape level, consultation sessions have been held to obtain views and inputs of a wide range of local stakeholders in selected landscapes to develop the project activities and to develop a robust stakeholder involvement plan with full gender considerations. Relevant indicators including gender disaggregated targets and baselines have also been included as part of the project results framework and monitoring plan.

Briefly describe in the space below how the Project mainstreams environmental sustainability

In line with the project’s biodiversity conservation objectives, its environmental impacts are expected to be overwhelmingly positive, through ensuring appropriate control of wildlife trade and action to address illegal wildlife trade in the Indonesian regulatory and institutional framework, and addressing capacity constraints at all scales in Indonesia. Under Component 3, the project will also support specific demonstration and scaling-up activities to determine, monitor and interrupt trade chains across the demonstration areas including strengthening surveillance and enforcement capacity at key IWT ports and markets and for source areas around key protected area ecosystems. Overall, the project will assist Indonesia to meet its commitments under the CBD and CITES.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |  |
| Risk 1: Adverse impacts on human rights of local communities, including marginalized groups. | I = 3 P = 4 | Moderate | Enhanced enforcement by Indonesian government agencies could lead to negative impacts for some local people, if they are engaged in illegal activities such as poaching, illegal fishing and wildlife trade. |  | During the project design, measures have been included to ensure that recognition of human rights are fully incorporated into the project plans. An oversight mechanism will be put in place to ensure that all project activities are carried out in accordance with Indonesian Law and international legal obligations, and that any prosecutions supported by the project are carried out correctly and fairly. This will consist of an SESP ombudsman appointed by the UNDP CO and DG Law Enforcement (MoEF) during the project inception period who will review project progress reports and news from stakeholders, as well as providing a telephone hotline and email contact address for complaints from affected parties. As the project demonstration area in Sulawesi covers a large area, it does include areas occupied by different ethnic groups, and some of these are engaged in bushmeat trade and pet trade involving nationally protected species. In these cases, the law would be applied equally irrespective of ethnicity, and legally established cultural traditions would be respected. |  |
| Risk 2: Restricted access to natural resources due to enhanced enforcement for local communities, including marginalized groups. | I = 3 P = 4 | Moderate | Enhanced enforcement by Indonesian government agencies could restrict access to natural resources for some local people, if they are engaged in illegal activities such as poaching, illegal fishing and wildlife trade. |  | During the project design, specific measures have been incorporated to ensure that project activities do not restrict legal access of local people to natural resources. This will include sensitization of project staff to human rights and other social and environmental issues before the outset of field activities. Mitigation measures will be considered by project management if it is judged that project activities will curtail illegal activities which form a significant portion of local peoples’ livelihoods, such as a consultation process with affected stakeholders to determine alternative approaches. As for risk 1, the project demonstration area in Sulawesi covers a large area including areas occupied by different ethnic groups, in which case specific attention will be given to ensuring that legal access to natural resources is not hindered by project activities, and that cultural traditions are taken into account. |  |
| Risk 3: Exclusion of potentially affected stakeholders, in particular marginalized groups, from participating in decisions that might affect them. | I = 1 P = 4 | Low | Reform of Indonesian law enforcement regulations and the protected species list could further restrict the opportunities for local people to legally exploit wildlife. |  | During the project design, PMU staff will ensure that project groups involved in regulatory reform activities consult appropriately with key stakeholders, including umbrella groups that represent the interests of local forest dependent peoples. At the project demonstration area scale, appropriate consultation mechanisms have been established for use during the project implementation. |  |
| Risk 4: Indonesian law enforcement agencies do not apply the law correctly. | I = 3 P = 4 | Moderate | Increasing the capacity of Indonesian law enforcement agencies carries the risk of improper application of the law, unless mitigation measures are put in place. |  | The project capacity-building component (Component 2) should be specifically designed to enhance the capacity and understanding of Indonesian law enforcement agencies to ensure that the law is applied correctly. |  |
| Risk 5: Project activities are within or adjacent to environmentally sensitive areas including PAs. | I = 1 P = 5 | Low | Some project activities will occur in protected areas, but these are expected to benefit biodiversity. |  | None required |  |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  |  |  | Comments |
|  | Low Risk |  |  | ☐ |  |  |
|  | Moderate Risk |  |  |  |  | It is considered that the project activities with potential adverse social risks are limited in scale, can be identified with a reasonable degree of certainty, and can be addressed through application of standard best practice, mitigation measures and stakeholder engagement during project implementation. |
|  | High Risk |  |  | ☐ |  |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
|  | Check all that apply |  |  |  |  | Comments |
|  | Principle 1: Human Rights |  |  |  |  | It is considered that the project activities with potential adverse social risks are limited in scale, can be identified with a reasonable degree of certainty, and can be addressed through application of standard best practice, mitigation measures and stakeholder engagement during project implementation. |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | ☐ |  |  |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  | ☐ |  |  |
|  | 2. Climate Change Mitigation and Adaptation |  |  | ☐ |  |  |
|  | 3. Community Health, Safety and Working Conditions |  |  | ☐ |  |  |
|  | 4. Cultural Heritage |  |  | ☐ |  |  |
|  | 5. Displacement and Resettlement |  |  | ☐ |  |  |
|  | 6. Indigenous Peoples |  |  |  |  | During the project design, measures have been included to ensure that recognition of human rights are fully incorporated into the project plans. In addition, appropriate oversight mechanisms have been put in place to ensure that all activities are carried out in accordance with Indonesian Law and international legal obligations, and that any prosecutions supported by the project are carried out correctly and fairly. |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | ☐ |  |  |

.Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | - UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | Yes |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | Yes |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | Yes |
| 5. Are there measures or mechanisms in place to respond to local community grievances? | No |
| 6. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | Yes |
| 7. Is there a risk that rights-holders do not have the capacity to claim their rights? | Yes |
| 8. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 9. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 3. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | Yes |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | No |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | Yes |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas)? | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.4 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.5 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.6 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.7 Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | Yes |
| 6.8 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

Annex 7

UNDP Project Quality Assurance Report

-See separate file-

Annex 8

UNDP Risk Log:

| Description | Type | Impact & Probability, and Risk level | Mitigation Measures | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| Enter a brief description of the risk | Category of risk | Describe the potential effect on the project if this risk were to occur: Probability P from 1 (low) to 5 (high) Impact I from 1 (low) to 5 (high) | What actions have been taken/will be taken to counter this risk | Who is appointed to keep an eye on this risk | e.g. over, reducing, increasing, no change |
| Delays and uncertainties in achieving government approval for proposed legislative changes and international agreements related to combatting IWT. Such delays may be attributable to lengthy bureaucratic procedures, opposition from certain quarters, or lack of interest / lack of priority afforded to their completion. | Political | P=3, I=3 MODERATE | There is a strong baseline on strengthening the legal and institutional frameworks for combating the illegal wildlife trade, including a rapid assessment of current knowledge, trends and priority actions for wildlife crime, and a detailed analysis of the policy and legal context with support from USAID, with subsequent support to MoEF to implement report recommendations for legal revisions to improve species protection. This has included significant achievements – government agreement to revise the Conservation Law 5/1990 during 2016, MoEF agreement that the revised Law should always reflect the current and existing CITES list, and progress towards updating the Protected Species List in 2016. This process has received significant support from CSOs, with WCS playing a leading role, which the project will provide additional resources to follow through on key legislation. Engagement with neighbouring countries occurs through ASEAN WEN but remains weak, and by developing a national IWT strategy associated with a national task force, increasing the capacity of MoEF’s Gakkum to play a leading role in IWT enforcement, and strengthening its international exposure and engagement through the GEF GWP, increased momentum will be provided for such agreements to be developed and put into action. | Project Manager | Decreasing |
| Mal-governance and Corruption: this is a major factor in wildlife trade, and accordingly one that has not been underestimated. Even when laws and mandates are clear, the mandated response is not always forthcoming. This is related to low motivation, poor resource allocation, but also to the insidious effects of corruption, that thrives in the poorly regulated environment. | Political, Operational & Strategic | P= 3; I= 3 MODERATE | Addressing corruption requires considerable high-level political support. Reducing its impact requires action against corruptors, but can also be addressed through tighter regulatory structures and improved monitoring that highlight when appropriate action is not being taken. Many of the described project components are designed to specifically address corruption and other forms of mal-practice and mal-governance. For example, strengthening the regulatory framework and government capacity will enhance oversight and limit opportunities for malpractice. Key agencies responsible for anti-corruption measures, namely the Corruption Eradication Commission (KPK) and Financial Transactions Analysis and Reporting Centre (PPATK) will participate in the project Technical Advisory Committee and will be key project partners in strengthening the multi-door approach to IWT prosecutions in Components 1 and 2. The presence of an internationally funded high profile project will further support the government’s efforts to fight corruption. | Project Manager | Possibly decreasing |
| Lack of industry support due to links with IWT: the wildlife trade industry is secretive, fragmented as well as multi-national. There is often a link to criminal syndicates. This presents challenges for project implementation, industry engagement and enforcement | Strategic | P= 3; I= 3 MODERATE | The project implementers have considerable experience with such trade participants, and will seek to engage industry at all levels, as well as devise a strategy with international organisations to counter criminal syndicates. The project activities have been developed based on a thorough situation analysis based on the latest global information, data and knowledge on the structure of the international and national trade compiled by international organisations and individuals, and supported by a series of consultation workshops and other stakeholder consultations involving all relevant agencies. The project will support the strengthening of intelligence analysis based on WCU capacity, and agreements for information exchange between agencies and collaboration with CSOs such as TRAFFIC to enable understanding and adaptation to changing IWT and legal trade trends. The development of relationships with recognized reputable traders and documentation of their practices as models has potential as a way forward in encouraging responsible trade. | Project Manager | Stable |
| Suboptimal collaboration between IWT enforcement agencies: coordination between various agencies may be constrained due to sectionalism, bureaucracy, the demands of coordination, and/or unclear mandates, impacting the effectiveness of IWT responses. | Operational | P= 3; I= 3 MODERATE | This project has been developed in full collaboration with the Indonesian government and its agencies. There have already been considerable discussions and joint efforts between key government law enforcement agencies. The momentum created by the project will further strengthen and institutionalise the coordination and joint action mechanisms. Joint work will be demonstrated at both national and local levels and necessary systemic and institutional capacities will be installed to ensure sustainability. The WCS-WCU has demonstrated that inter-agency cooperation to conduct collaborative counter-IWT operations can be successful through a number of investigations leading to prosecution of high profile IWT traders, and will continue to support this approach throughout the project. In addition, the involvement of Bappenas as a high level coordinating ministry in the Project Board should help to facilitate inter-agency cooperation. | Project Manager | Stable / decreasing |
| Major natural disasters: natural disasters such as earthquakes, floods, volcanic eruptions, etc. inhibit or divert the increase in national and provincial government’s attention towards and investment in combatting illegal wildlife trade | Environmental | P= 2; I= 2 LOW | This risk is very prevalent in Indonesia. The project will elevate the illegal wildlife trade issues to the national political and economic agenda, as well as developing the National Strategy to Combat Illegal Wildlife Trade. Increased awareness that illegal wildlife trade is a national and global crisis and security issues should minimise shifting of resources away from the work to natural disaster emergency work. In addition, the project is designed to institutionalise every output and install the necessary systemic and institutional capacity for tackling illegal wildlife trade, operationalising essential inter-agency coordination at both national and local level, and this will ensure continuation of core work even in the event of natural disasters. | Project Manager | Stable |
| Climate change impacts on endangered wildlife species populations: climate change may undermine the conservation objectives of the Project by impacting populations of endangered species in situ. | Environmental | P= 2; I= 2 LOW | Responses to the impacts of climate change on animal populations lie outside the scope of this project and are being addressed through other initiatives. The exact nature of this risk will vary substantially between different taxonomic groups and species, but are generally considered to be slow-acting – beyond the project timescale. By removing a major anthropogenic pressure on wildlife populations, this project would contribute towards reducing their overall vulnerability as small population size is a sensitivity factor for climate change impacts. | Project Manager | Increasing |

Annex 9

- To be submitted during project inception. -

Annex 10

Additional agreements: Co-financing letters:

Additional agreements: Letter of Agreement:

Country Office Support Service Agreement

COUNTRY OFFICE SUPPORT SERVICE (COSS) AGREEMENT

AGREEMENT BETWEEN UNDP AND THE GOVERNMENT

FOR THE PROVISION OF SUPPORT SERVICES

- Reference is made to consultations between officials of the Government of Indonesia Ministry of Environment and Forestry c.q. Directorate General of Law Enforcement on Forestry and Environment (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects. UNDP and the Government hereby agree that the UNDP country office may provide such support services at the request of the Government through its institution designated in the relevant programme support document, as described below.

- The UNDP country office may provide support services for assistance with reporting requirements and direct payment. In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly. The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

- The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme:

- Identification and/or recruitment of project personnel and technical expertise;

- Procurement of goods and services to undertake agreed activities;

- Administration of the donor contribution;

- Management of grant agreements and related disbursements for project-related activities (to be specified in the project details).

- The procurement of goods and services and the recruitment of programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.

- The relevant provisions of the Revised Basic Agreement for Technical Assistance signed 29 October 1954 between the United Nations, the International Labour Organization, the Food and Agriculture Organization of the United Nations, the United Nations Educational, Scientific and Cultural Organization, the International Civil Aviation Organization, and the World Health Organization and the Government of the Republic of Indonesia, the Standard Agreement on Operational Assistance signed 12 June 1969 between the United Nations, the International Labour Organization, the Food and Agriculture Organization of the United Nations, the United Nations Educational, Scientific and Cultural Organization, the International Civil Aviation Organization, the World Health Organization, the International Telecommunication Union, the World Meteorological Organization, the International Atomic Energy Agency, the Universal Postal Union, the Inter-Governmental Maritime Consultative Organization and the United Nations Industrial Development Organization and the Government of the Republic of Indonesia and the Agreement signed 7 October 1960 between the United Nations Special Fund and the Government of the Republic of Indonesia including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme through its designated institution. The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document.

- Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the above mentioned agreements.

- The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall refer to the enhanced UNDP UPL (Universal Price List) effective date 1 January 2015.

- The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

- Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Christophe Bahuet

Country Director, UNDP Indonesia

[Date]

_____________________

For the Government

Bambang Hendroyono

Secretary General, Ministry of Environment and Forestry

[Date]

Indicative COSS for the Combatting illegal and unsustainable trade in endangered species in Indonesia Project has been calculated as follows:

| No | Service Name | Unit | Volume | Unit Cost (US$)* | Total (US$) |
| --- | --- | --- | --- | --- | --- |
| 1 | Payment of DSA advance and its settlement | Financial Resource Management Unit | 360 | 80.47 | 28,969.20 |
| 2 | Payment process | Financial Resource Management Unit | 336 | 40.24 | 13,520.64 |
| 3 | Payment Process for Cash Distribution via Service Provider | Financial Resource Management Unit | 56 | 72.68 | 4,070.08 |
| 4 | Review and approval of APJV and GLJE (adjustment/correction/petty cash report) | Financial Resource Management Unit | 28 | 26.84 | 751.52 |
| 5 | Procurement Process < USD 5,000 | Procurement | 30 | 235.73 | 7,071.90 |
| 6 | Procurement Process Without ACP Approval (below USD 50,000) | Procurement | 15 | 235.73 | 3,535.95 |
| 7 | Individual Consultant without ACP Approval (below USD 100,000) | Procurement | 4 | 260.7 | 1,042.80 |
| 8 | Individual Consultant < USD 5,000 | Procurement | 20 | 104.28 | 2,085.60 |
| 9 | Vendor registration for supplier | Procurement | 50 | 21.73 | 1,086.50 |
| 10 | Request for PO creation only | Procurement | 69 | 58.93 | 4,066.17 |
| 11 | RECRUITMENT : Service Contract (SC 3 – 7) | Human Resource | 4 | 934.94 | 3,739.76 |
| 12 | RECRUITMENT : Service Contract (SC 8 – 11) | Human Resource | 4 | 972.14 | 3,888.56 |
| 13 | Vendor registration for staff and SC | Human Resource | 8 | 21.73 | 173.84 |
| 14 | Extension of Service Contract | Human Resource | 8 | 103.2 | 825.60 |
| 15 | PO Ticket/Travel Creation (For Travel with Ticket Value USD 2500 and Above Only) | Administration Unit | 50 | 55.15 | 2,757.50 |
| 16 | Courier services (City Courier, Domestic, International) | Administration Unit | 20 | 30.94 | 618.80 |
| 17 | Vendor Registration (for Workshop/Meeting Participant Only) | Administration Unit | 20 | 21.73 | 434.60 |
| 18 | Creation UNDP's email address for new recruit under UNDP' contract management | Information Communication | 8 | 13.06 | 104.48 |
| 19 | Asset management/disposal | Administration Unit |  |  | 1,256.5 |
|  | TOTAL |  |  |  | 80,000.00 |
| *Based on UPL 2015 + 20% for the change in pricing for 6 years period. |  |  |  |  |  |

Annex 11

Landscape profiles for the demonstration subnational regions:

-See separate files-

Annex 12A.

List of Stakeholders Consulted during the PPG Process

- During the PPG process, a stakeholder analysis was undertaken to identify key stakeholders, assess their interests in the project and define their roles and responsibilities in its implementation. Overall, support for the project and involvement in it was secured from a diverse group of stakeholders, whose roles are summarised in Table 2 (main project document). PPG stakeholder meetings were convened on 16 February 2016 in Jakarta, 18-19 February 2016 in Bogor, 14-16 March 2016 (combined with the Focus Group Discussion Meeting on Databases) in Bogor; 2 June 2016 in Bogor, 22-23 August 2016 in Bogor; 26 September in Surabaya, 13 October in Medan, 20-21 October 2016 in Bogor and on 7 December in Bogor. The UNDP Country Office maintained records of all participants of these meetings (see attached PDF files).

- The national consultancy team from the Faculty of Forestry at the Agricultural Institute of Bogor (Institut Pertanian Bogor, IPB) convened a series of Focus Group Discussion (FGD) meetings to consult with key stakeholders on the key themes being reviewed, supported by extensive interviews and field visits. The lists of consultees are given below.

- The national socio-economic consultant conducted Interviews with local people who live around Gunung Leuser National Park in Bahorok District, covering at least 10 respondents per village as follows: head of village, head of customary (adat)/ community leader, young generation/youth (karang taruna), woman group/PKK, member of farmer group (woman), member of farmers group (man), religious leader, teacher  (man), teacher (woman). These surveys were conducted for the following villages: Timbang Lawang, Timbang Jaya, Samperaya, Bukit Lawang, Batu Jong-jong.

- The national socio-economic consultant also conducted a series of interviews with national experts on illegal wildlife trade / wildlife conservation, listed in Annex 16.

- Details including lists of all those consulted are presented in the following annexes:

a.	Annex 11 - Landscape profiles for the demonstration subnational regions

b.	Annex 14 - Baseline report on databases

c.	Annex 15 - Baseline report on policy, legal and regulatory framework

d.	Annex 16 - Baseline socio-economic assessment

e.	Annex 17 - Baseline assessments of demonstration ports

List of interviewed resource persons for the IPB Policy Report (Annex 15)

| No. | Name | Occupation | Phone Number | email |
| --- | --- | --- | --- | --- |
| 1 | Rasio Ridho Sani | Director General Law Enforcement for Environment and Forestry, Ministry of Environment and Forestry | Secretary: Melinda 087888759915 | rasiosani@yahoo.com Secretary: Melinda melindanovianty.gakumklhk@yahoo.com |
| 2 | Ilyas Asaad | Special Assistant to the Minister of Environment and Forestry on Collaboration Among Central Government |  | ilyasasaad@menlh.go.id |
| 3 | I Made Subadia Gelgel | Ex Special Assistant to the Minister of Environment and Forestry for Collaboration Among Institutions |  |  |
| 4 | Bambang Dahono Aji | Director of Biodiversity Conservation, Ministry of Environment and Forestry (CITES Management Authority) | 081398727758 | kukuh1980@gmail.com (staff) |
| 5 | Indra Exploitasia | Ministry of Environment and Forestry (CITES Management Authority) |  |  |
| 6 | Puja Utama | Vice Director for Program and Convention, Directorate of Biodiversity Conservation, Ministry of Environment and Forestry (CITES Management Authority) | 08127963755 | putamapuja@gmail.com |
| 7 | Badiah | Directorate of Biodiversity Conservation, Ministry of Environment and Forestry (CITES Management Authority) |  | badiahsaid@gmail.com staff: drajatdh@gmail.com |
| 8 | Awen Supranata | Head of BKSDA Jakarta | 081284080008 | - |
| 9 | Dr. Tonny Soehartono | Ex Director of Biodiversity Conservation, Ministry of Environment and Forestry | 08121001291 | trsoehartono@gmail.com |
| 10 | Medrizal | Bappenas |  |  |
| 11 | Dr. Gono Semiadi | P2B, LIPI (CITES Scientific Authority) | 08121105030 | semiadi@gmail.com |
| 12 | Dr. Rosichon Ubaidillah | P2B, LIPI (CITES Scientific Authority) |  |  |
| 13 | Dr. Suharsono | P2O, LIPI (CITES Scientific Authority) |  |  |
| 14 | Yani Septiani | Team Leader on Socio-Economic Studies, UNDP | 08121069564 | Yaniseptiani13@gmail.com |
| 15 | Asep Adi Saputra | Tipidter V, Bareskrim, Indonesian National Police | 0811919494 | adisaputra_tp94@yahoo.co.id daniel.laoli@yahoo.co.id |
| 16 | Heru Yulianto | Tipidter V, Bareskrim, Indonesian National Police | 081385468007 | - |
| 17 | Noviar Andayani | National Coordinator, WCS – Indonesia Program |  |  |
| 18 | Dwi Adhiasto | WCS – Indonesia Program | +1(917)3796194 | adhiasto@gmail.com |
| 19 | Chairul Saleh | WWF Indonesia | 0811102902 | csaleh@wwf.co.id; csaleh@wwf.id |
| 20 | Hadi Wijaya | Trader and exporter |  |  |

List of consultees involved in field interviews and discussions during visits to the target landscapes (Annex 11)

| No. | Name | Institution | Phone Number | email |
| --- | --- | --- | --- | --- |
| Field interview in Gorontalo-North Sulawesi Landscape |  |  |  |  |
| 1 | Sudiyono | BKSDA North Sulawesi | 081341259818 | 81sudiyono@gmail.com |
| 2 | Alfons Patundung | WCS – Indonesia Program |  | apatandung@gmail.com |
| 3 | Iwan Honowu | WCS – Indonesia Program |  | iwan.hunowu@gmail.com |
| 4 | Simon Purser | Head of Tasikoki Rescue Center |  |  |
| 5 | John Tasirin | University of Sam Ratulangi | 08152301590 | jtasirin@gmail.com |
| 6 | Febriyanto Kolanus | University of Gorontalo |  |  |
| 7 | Iswan Dunggio | University of Gorontalo |  | faperta@unigo.ac.id |
| 8 | Ikhwanuddin | University of Gorontalo |  |  |
| Field interview in Leuser-Ulu Masen Landscape |  |  |  |  |
| 1 | Hotmauli Sianturi | Kepala BBKSDA Sumatera Utara |  |  |
| 2 | Garendel Siboru | Kabid Teknis, BBKSDA Sumatera Utara |  |  |
| 3 | Gunung Gea | Scorpion | 085280108401 | gununggea@gmail.com |
| 4 | Ian Singleton | Sumatran Orangutan Conservation Program (SOCP) |  |  |
| 5 | Panut Hadisiswoyo | Orangutan Information Center (OIC) |  |  |
| 6 | Halen Purba | Dinas Kehutanan Sumatera Utara |  |  |
| 7 | Giyanto | WCS - Medan | 0811632179 | giyanto@wcs.org |
| 8 | Dede Suhendra | WWF – Medan | 085770193532 | dhe.domain68@gmail.com |
| 9 | Syafrizaldi Aal | FFI - Medan |  | syafrizaldi@gmail.com |
| 10 | Group Discussion | Oil Palm Company |  |  |
| List of FGD participants at Gorontalo Forest and Mining Office |  |  |  |  |
| 1 | Ir. Rugaya, M.Si | Dinas Kehutanan dan Pertambangan Provinsi Gorontalo (Plh. Kepala Dinas) |  |  |
| 2 | Khaeruddin, S.Hut, M.Si | Dinas Kehutanan dan Pertambangan Provinsi Gorontalo |  |  |
| 3 | Indra | Dinas Kehutanan dan Pertambangan Provinsi Gorontalo | 085341997500 | - |
| 4 | Wilda Taha | Dinas Kehutanan dan Pertambangan Provinsi Gorontalo | 085398628871 | wildataha04@gmail.com |
| 5 | Syahbuddin Buata | Dinas Kehutanan dan Pertambangan Provinsi Gorontalo | 085240550300 | syahbuddinbuata@yahoo.co.id |
| 6 | Gafar Musa | Dinas Kehutanan dan Pertambangan Provinsi Gorontalo | 085290946377 | musagafar@ymail.com |
| 7 | Andy Waskitho | TN. Nani Wartabone | 082344274567 | bonggegode@gmail.com |
| 8 | Ferdiyanto Padungge | TN. Nani Wartabone | 081340155744 | ferdyskuna09@gmail.com |
| 9 | Tatang Abdulah | BKSDA Sulawesi Utara | 085397310422 | tatangabdulah13@gmail.com |
| 10 | Eri | BKSDA Sulawesi Utara | 082225833338 | eryryey03@gmail.com |
| 11 | Sjamsuddin Hadju | BKSDA Sulawesi Utara (Kepala Seksi KSDA II SUlut) | 085340262055 | sjamsuddinhadju@gmail.com |
| 12 | Sugeng | JAPESDA | 081340406025 | - |
| 13 | Purnomo Windu | BAPPEDA Provinsi Gorontalo | 081326567340 | purnomo.windu@gmail.com |
| 14 | Akbar Mahmud | Balai Pemantapan Kawasan Hutan (BPKH) XV Gorontalo | 082394546523 | Akbarmahmud06@gmail.com |
| 15 | Feri Novriyal | Balai Pemantapan Kawasan Hutan (BPKH) XV Gorontalo | 081244050985 | dblackhent@hotmail.com |
| 16 | Tasrif | Balai Pengelolaan Daerah Aliran Sungai (BPDAS) Bonebolango | 081213053928 | tasrif_tahana22@yahoo.co.id |
| 17 | Irpana Nur | Balai Pengelolaan Daerah Aliran Sungai (BPDAS) Gorontalo | 08124463125 | Irpana_nur@yahoo.co.id |
| 18 | Amsurya Warman A. | Burung Indonesia/Coordinator | 08114340751 | a.warman@burung.org |
| 19 | Nur Indah Ristiana | Burung Indonesia | 081298523550 | n.ristiana@burung.org |
| 20 | Duman Wau | ICRAF-AGFOR Sulawesi | 08119471420 | d.wau@cgiar.org |

List of key persons interviewed for baseline study on databases (Annex 14).

| No | Name | Institution |  |  |
| --- | --- | --- | --- | --- |
| 1 | Bambang Dahono Aji | Directorate of Biodiversity Conservation (Direktorat Konservasi Keanekaragaman Hayati, KKH), MoEF | 081398727758 | kukuh1980@gmail.com (staff) |
| 2 | Puja Utama | Directorate of Biodiversity Conservation (Direktorat Konservasi Keanekaragaman Hayati, KKH), MoEF | 081398727758 | putamapuja@gmail.com |
| 3 | Badiah | Directorate of Biodiversity Conservation (Direktorat Konservasi Keanekaragaman Hayati, KKH), MoEF |  | badiahsaid@gmail.com staff: drajatdh@gmail.com |
| 4 | Rasio Ridho Sani | Directorate of Forest Prevention and Protection (Direktorat Pencegahan dan Pengamanan Hutan, PPH), MoEF | Secretary: Melinda 087888759915 | rasiosani@yahoo.com Secretary: Melinda melindanovianty.gakumklhk@yahoo.com |
| 5 | Istanto | Directorate of Forest Prevention and Protection (Direktorat Pencegahan dan Pengamanan Hutan, PPH), MoEF | 0818555444 | istanto62@yahoo.co.id |
| 6 | Ardi Risman | Directorate of Forest Prevention and Protection (Direktorat Pencegahan dan Pengamanan Hutan, PPH), MoEF | 08129451350 | ardi.risman@gmail.com |
| 7 | Ahmad Pribadi | Directorate of Forest Prevention and Protection (Direktorat Pencegahan dan Pengamanan Hutan, PPH), MoEF | 081298287684 | achmad.pribadi@gmail.com |
| 8 | Siswoyo | Directorate of Forest Prevention and Protection (Direktorat Pencegahan dan Pengamanan Hutan, PPH), MoEF | 08121075045 | siswoyo2009@yahoo.co.id |
| 8 | Awen Supranata | Head, BKSDA DKI Jakarta | 081284080008 | - |
| 9 | Asep Adisahputra | Indonesian National Police (i.e. Direktorat Tindak Pidana Tertentu/Tipidter V – Badan Reserse Kriminal) | 0811919494 | adisaputra_tp94@yahoo.co.id |
| 10 | Heru Yulianto | Indonesian National Police (i.e. Direktorat Tindak Pidana Tertentu/Tipidter V – Badan Reserse Kriminal) | 081385468007 | - |
| 11 | Noviar Andayani | Wildlife Conservation Society – Indonesia Program |  |  |
| 12 | Dwi Adhiasto | Wildlife Conservation Society – Indonesia Program | +1(917)3796194 | adhiasto@gmail.com |
| 13 | Sofi Mardiah | Wildlife Conservation Society – Indonesia Program |  |  |
| 14 | Mbak Wian | Wildlife Conservation Society – Indonesia Program |  |  |
| 15 | Chairul Saleh | World Wide Fund for Nature (WWF) – Indonesia Program | 0811102902 | csaleh@wwf.co.id; csaleh@wwf.id |
| 16 | Mas Novi | World Wide Fund for Nature (WWF) – Indonesia Program |  |  |
| 17 | Agus Budi Utomo | Burung Indonesia | 081294299419 | agus@burung.org |
| 18 | Jihad | Burung Indonesia | 08568290205 | jihad@burung.org |
| 19 | Asep Adhikerana | Zoological Society of London | 081298287684 | asepadhikerana@gmail.com |
| 20 | Donny Gunadi | Fauna and Flora International – Indonesia Programme | 082183774587 | d.gunadi@gmail.com |
| 21 | Jamartin Sihite | Borneo Orangutan Survival Foundation |  |  |
| 22 | Wahjudi Wardojo | The Nature Conservancy |  |  |
| 23 | Ketut Sarjana Putra | Conservation International – Indonesia Program |  |  |
| 24 | Waladi Isnan | YABI (Yayasan Badak Indonesia) |  |  |
| 25 | Yus R. Noor | Wetlands International – Indonesia Programme |  |  |
| 26 | Haryo T. WIbisono | Froum Harimau Kita | 08121099557 | haryo.wibisono@faua-flora.org |
| 27 | Herry Joko Susilo | FORINA |  |  |

List of resource persons interviewed for baseline study on demonstration ports (Annex 17).

| No. | Name | Institution |  |  |
| --- | --- | --- | --- | --- |
| Interview in Jakarta and Bogor |  |  |  |  |
| 1 | Rasio Ridho Sani | DG Gakkum, MoEF | Secretary: Melinda 087888759915 | rasiosani@yahoo.com Secretary: Melinda melindanovianty.gakumklhk@yahoo.com |
| 2 | Istanto | DG Gakkum, MoEF | 0818555444 | istanto62@yahoo.co.id |
| 3 | Ahmad Pribadi | DG Gakkum, MoEF | 0818253931 | achmad.pribadi@gmail.com |
| 4 | Ardi Risman | DG Gakkum, MoEF | 08129451350 | Ardi.risman@gmail.com |
| 5 | Siswoyo | DG Gakkum, MoEF | 08121075045 | siswoyo2009@yahoo.co.id |
| 6 | Bambang Dahono Aji | CITES Management Authority, MoEF | 081398727758 | kukuh1980@gmail.com (staff) |
| 7 | Indra Exploitasia | CITES Management Authority, MoEF |  |  |
| 8 | Puja Utama | CITES Management Authority, MoEF | 08127963755 | putamapuja@gmail.com |
| 9 | Awen Supranata | BKSDA DKI Jakarta | 081284080008 | - |
| 10 | Asep Adi Saputra | Tipidter V, Bareskrim, Indonesian National Police | 0811919494 | adisaputra_tp94@yahoo.co.id |
| 11 | Heru Yulianto | Tipidter V, Bareskrim, Indonesian National Police | 081385468007 | - |
| 12 | Noviar Andayani | National Coordinator, WCS – Indonesia Program |  |  |
| 13 | Dwi N. Adhiasto | WCS – Indonesia Program | +1(917)3796194 | adhiasto@gmail.com |
| 14 | Chairul Saleh | WWF Indonesia | 0811102902 | csaleh@wwf.co.id; csaleh@wwf.id |
| 15 | Hadi Wijaya | Trader and exporter |  |  |
| Field interview in Manado, Gorontalo and Bitung Seaport |  |  |  |  |
| 1 | Sudiyono | BKSDA North Sulawesi | 081341259818 | 81sudiyono@gmail.com |
| 2 | William Tengker | Head of Gakkum, North Sulawesi |  |  |
| 3 | Alfons Patundung | WCS – Indonesia Program |  | apatandung@gmail.com |
| 4 | Iwan Honowu | WCS – Indonesia Program |  | iwan.hunowu@gmail.com |
| 5 | Simon Pulzer | Head of Tasikoki Rescue Center |  |  |
| 6 | John Tasirin | University of Sam Ratulangi | 08152301590 | jtasirin@gmail.com |
| 7 | Febriyanto Kolanus | University of Gorontalo |  |  |
| 8 | Iswan Dunggio | University of Gorontalo |  |  |
| 9 | Ikhwanuddin | University of Gorontalo |  |  |
| 10 | Abdul Rasyid | Kepala Pelayanan Bea Cukai Menado |  |  |
| 11 | Kompol Robby Bakko | Polisi Air Polda Sulawesi Utara |  |  |
| 12 | AKBP Nonie Sengkey | Korwas Polda Sulawesi Utara |  |  |
| 13 | Bripka Hasan | Penyidik Pembantu Tipidter III |  |  |
| 14 | Noh Rumondang | Head of Bitung Seaport Authority |  |  |
| Field interview in Medan, Belawan and Kuala Namu |  |  |  |  |
| 1 | Hotmauli Sianturi | Kepala BBKSDA Sumatera Utara |  |  |
| 2 | Garendel Siboru | Kabid Teknis, BBKSDA Sumatera Utara |  |  |
| 3 | Gunung Gea | Scorpion | 085280108401 | gununggea@gmail.com |
| 4 | Ian Singleton | Sumatran Orangutan Conservation Program (SOCP) |  |  |
| 5 | Panut Hadisiswoyo | Orangutan Information Center (OIC) |  |  |
| 6 | Halen Purba | Dinas Kehutanan Sumatera Utara |  |  |
| 7 | Drh. Cahyono | BKP Belawan |  |  |
| 8 | Drh. Wiwin Winarni | BKP Kualanamu |  |  |
| 9 | Giyanto | WCS - Medan | 0811632179 | giyanto@wcs.org |
| 10 | Dede Suhendra | WWF – Medan |  |  |
| 11 | Syafrizaldi Aal | FFI - Medan |  |  |
| 12 | Group Discussion | Oil Palm Company |  |  |
| Field interview in Tanjung Priok Seaport |  |  |  |  |
| 1 | Lily Saderiansyah | Staff P2 Bea dan Cukai Pelabuhan Tanjung Priok | 0821 34784483 | l.saderiansyah@gmail.com |
| 2 | Nur Hartanto | Kepala Seksi P2 Karantina Hewan Balai Besar Karantina Pertanian Tanjung Priok |  | m45tanto@yahoo.co.id – nurhartanto@pertanian.go.id |
| 3 | Rahmadi Imam | Koordinator Fungsional Karantina Hewan | 0813 17440773 | imamthok@yahoo.com |
| Field interview in Tanjung Perak Seaport |  |  |  |  |
| 1 | Toyib | Kepala Bagian Lalu Lintas Laut |  |  |
| 2 | Drh. Retno Oktarina | Kepala Seksi P2 Balai Besar Karantina Pertanian | 08123263454 | oktarinahtp@yahoo.com |
| 3 | Drh. Heli Apriantoro | Kepala Seksi P2 Karantina Hewan Pelabuhan Tj. Perak | 08123433724 | brainvet234@gmail.com |
| 4 | Hardiastutik | Bagian P2 Pelabuhan Tanjung Perak | 08123020896 |  |
| 5 | Sarjono | Polhut BBKSDA Jatim |  |  |
| Field interview in Tanjung Mas Seaport |  |  |  |  |
| 1 | Drh. Andjar | Koordinator Fungsional Karantina Pelabuhan Tj. Emas | 0817 5410932 | infobkp1semarang@gmail.com |
| 2 | Drh. Krisna | Kepala Seksai Dak Karantina Pelabuhan Tanjung Emas |  |  |
| 3 | Syamsudin | Analis P2 Bea dan Cukai Pelabuhan Tanjung Emas | (024) 76631968 | pli.temas@gmail.com |
| 4 | Anastasia Krisna W. | Sekretaris/ Penyusun Data dan Laporan Angkutan Laut | 0822 25834990 | tis_nav@rocketmail.com |

Annex 12B

Attendance list:

-see separated file-

Annex 13

Situation analysis:

UNDP/GEF Project 5391

Combatting illegal and unsustainable trade in endangered species in Indonesia

Annex 13: Situation Analysis

Crawford Prentice

GEF project design consultant

Table of Contents

Table of Contents	126

Acronyms and Abbreviations	127

Situation Analysis	129

Preamble	129

Introduction	129

Context and global significance	131

Threats, Root causes and Impacts	147

Long-term solution and barriers to achieving the solution	149

Baseline analysis	157

List of Figures and Tables

Figure 1. Law enforcement process for forest and wildlife crimes and administrative violations (Suryadi et al. 2007)	136

Figure 2. Case handling for forest and wildlife crime	137

Figure 3. Principal legislation relating to wildlife crimes and biodiversity conservation in Indonesia.	139

Figure 4. Act No. 5/1990 and Subsidiary Regulations	141

Figure 5. Biodiversity Action Plans in Indonesia	142

III Acronyms and Abbreviations

| AMDAL |  | Analisis Dampak Lingkungan (Environmental Impact Assessment) |
| --- | --- | --- |
| APBN |  | Anggaran Pendapatan dan Belanja Negara (State budget) |
| APR/PIR |  | Annual Project Review/ Project Implementation Reports |
| ASEAN-WEN |  | Association of South East Asian Nations – Wildlife Enforcement Network |
| BAPPEDA |  | Badan Perencana Pembangunan Daerah (Regional Body for Planning and Development) |
| BAPPENAS |  | Badan Perencanaan Pembangunan Nasional (Body for National Development Planning) |
| BBTN |  | Balai Besar Taman Nasional (Grand National Park Agency) |
| BKSDA |  | Natural Resources Conservation Agency |
| BPDAS |  | Watershed Management Agency |
| BTN |  | Balai Taman Nasional (National Park Agency) |
| CBD |  | Convention on Biological Diversity |
| CID |  | Criminal Investigation Division (of the Indonesian National Police) |
| CITES |  | Convention on International Trade in Endangered Species |
| CSO |  | Civil Society Organization – used interchangeably with local NGO |
| Dishut |  | Dinas Kehutanan (Forestry Agency) |
| DNS |  | Debt for Nature Swaps |
| EIA |  | Environmental Impact Assessment |
| EOP |  | End of Project |
| ERC |  | Evaluation Resource Center (of UNDP Evaluation Office) |
| E-PASS |  | UNDP/GEF project - Enhancing the Protected Area System in Sulawesi |
| FFI |  | Fauna & Flora International |
| FPIC |  | Free Prior and Informed Consent |
| GDP |  | Gross Domestic Product |
| GEF |  | Global Environment Facility |
| GTI |  | Global Tiger Initiative |
| Ha |  | Hectare |
| HDI |  | Human Development Indices |
| IBSAP |  | Indonesian Biodiversity Strategy and Action Plan |
| ICCWC |  | International Consortium on Combatting Wildlife Crime |
| IDR |  | Indonesian Rupiah |
| INGO |  | International Non Governmental Organization |
| INP |  | Indonesian National Police |
| IUCN |  | International Union for Conservation of Nature |
| IP |  | Implementing Partner |
| IW |  | (Project) Inception Workshop |
| KfW KSDAE |  | German Development Bank Directorate of Conservation of Natural Resources and Ecosystems |
| KPK |  | Komisi Pemberantasan Korupsi (Corruption Eradication Commission) |
| KUHAP |  | Indonesian Code of Criminal Procedures |
| LIPI |  | Indonesian Institute of Science |
| M&E |  | Monitoring and Evaluation |
| METT |  | Management Effectiveness Tracking Tool |
| MMAF |  | Ministry of Marine Affairs and Fisheries |
| MoEF |  | Ministry of Environment and Forestry |
| MoHA |  | Ministry of Home Affairs |
| MoU |  | Memorandum of Understanding |
| NGO |  | Non-Governmental Organization (used interchangeably with CSO) |
| NP |  | National Park |
| NTFP |  | Non Timber Forest Products |
| NTRP |  | National Tiger Recovery Plan |
| PA |  | Protected Area |
| PHKA |  | Forest Protection and Nature Conservation (under MoEF) |
| PIF |  | Project Identification Form (for GEF) |
| PIMS |  | Project Information Management System |
| PMU |  | Project Management Unit |
| POPP |  | Programme and Operation Policies and Procedures |
| PoWPA |  | Programme of Work on Protected Areas (of CBD) |
| PPATK |  | Pusat Pelaporan dan Analisis Transaksi Keuangan (Indonesian Financial Transaction Reports and Analysis Centre) |
| PPG |  | Project Preparation Grant (for GEF) |
| PPH |  | Penyidikan dan Pengamanan Hutan (Forest Security and Investigation) |
| PPNS |  | Penyidik Pegawai Negeri Sipil (Civil Service Investigator) |
| PPR |  | Project Progress Report |
| PusDikLat |  | Pusat Pendidikan dan Pelatihan (Training and Education Centre) |
| RBM |  | Resort Based Management |
| RCU |  | (UNDP-GEF) Regional Coordinating Unit |
| RSPO |  | Round table for Sustainable Palm Oil |
| RTA |  | Regional Technical Advisor (of UNDP) |
| SESP |  | UNDP Social and Environmental Screening Procedure |
| SPORC |  | Satuan Polhut Reaksi Cepat (Rapid Response Forest Police Unit) |
| RF |  | Results Framework |
| UN |  | United Nations |
| UN-REDD |  | United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation in Developing Countries |
| UNDAF |  | United Nations Development Assistance Framework |
| UNDP |  | United Nations Development Programme |
| UNDP-CO |  | UNDP Country Office |
| UNDP EEG |  | UNDP Environment and Energy Group |
| UNFCC |  | United Nations Framework Convention on Climate Change |
| UNEP |  | United Nations Environment Programme |
| UNESCO |  | United Nations Educational, Scientific and Cultural Organization |
| UPT |  | Unit Pelaksanaan Teknis (Technical Implementation Unit) |
| UPT KKJI |  | Unit Pelaksanaan Teknis Konservasi Kawasan dan Jenis Ikan (Technical Implementation Unit of Aquatic Species and Area Conservation - of MMAF) |
| US$ |  | United States Dollar |
| WHC |  | World Heritage Convention |
| WWF |  | World Wide Fund for Nature |
| WCS |  | Wildlife Conservation Society |
| YABI |  | Yayasan Badak Indonesia (Rhino Foundation of Indonesia) |
| ZSL |  | Zoological Society of London |

IV Situation Analysis

Preamble

This document was prepared for UNDP in December 2015 and subsequently updated in March 2016. It has been superseded by the baseline assessment of the policy, legal and regulatory framework given in Annex 15, but is retained as it contains fairly detailed information on the illegal wildlife trade threats, issues and barriers which elaborate on parts of the rationale provided in the project document.

Introduction

The illegal trade in fauna and flora (other than fisheries and timber) has been estimated by different sources to be worth US$ 7-23 billion dollars annually and US$ 2.5 billion in East Asia and the Pacific alone. This trade has already caused the decline and local extinction of many species across SE Asia, including those inside protected areas. Much of the trade is highly organized, benefits a relatively small criminal fraternity, whilst depriving developing economies of billions of dollars in lost revenues and development opportunities. Within Southeast Asia, a significant amount of this trade starts from Indonesia, one of the world’s top 10 ‘megadiverse’ countries and the largest supplier of wildlife products in Asia, both ‘legal’ and illegal. Illegal wildlife trade is the preeminent threat to Sumatran Rhinoceros (Critically Endangered; population 100-120 individuals), Sumatran Tigers (Critically Endangered; 650 individuals), Asian Elephants (Endangered) and Sunda Pangolin (Critically Endangered). Indonesia is also becoming an important transit point for the illegal wildlife trade from Africa to East Asia, such as African Ivory. In fact a wide range of animal species are threatened by unsustainable harvest and trade. The unsustainable use of wildlife creates a risk both for biodiversity conservation and for local livelihoods, as depletion of wildlife resources may compromise economic and livelihood opportunities associated with them. The value of the illegal trade in Indonesia alone is estimated at up to US$ 1 billion per year. Factoring in the unsustainable legal trade, the value rockets, translating into an enormous economic, environmental, and social loss.

Combatting the illegal wildlife trade in Indonesia is hindered by its low domestic political profile, which translates into a lack of interest and poor collaboration between law enforcement agencies. There is also a widespread lack of understanding regarding laws and enforcement procedures at all levels, and regulatory loopholes and inconsistencies that prevent successful prosecutions. For example, inside Indonesia the trade and sale of African ivory and non-native tiger or rhino parts is technically not illegal. Regulatory reform is critical to address these issues. The underlying socio-economic factors contributing to these threats include population growth and poverty in rural and protected area boundary zones, which reduce the ability of local communities to practice sustainable agriculture and natural resource use.  Productive job opportunities – which might provide local residents with an alternative source of livelihood – are limited, driving some to engage in illegal poaching activities. The impacts of logging, fragmentation of forests and their conversion for agricultural land and plantations on globally significant wildlife are inadequately addressed through existing legal and environmental management frameworks, providing key entry points into wildlife trade supply chains. Even biodiversity within the PA system is not shielded from poaching to supply the domestic and international illegal wildlife trade.

While there is considerable baseline activity from both government and civil society to conserve biodiversity in situ and to address illegal wildlife trade concerns, the policy, legal, regulatory and institutional frameworks need to be strengthened, including increased capacity and resources, together with the ability to upscale successful models (e.g. the Wildlife Crimes Unit). Until this is achieved, current trends indicate that wildlife trade, both illegal and legal, will substantially increase or, at best, will continue unabated, resulting first in local declines followed by outright extinctions of key Indonesian wildlife species, including tigers and rhinos. Illegal wildlife trade will continue to operate as organized crime, while the legal trade in wildlife will remain poorly regulated, raising few revenues for the state, and acting as a cover behind which illegal trade can flourish.

This project aims to remove the systemic and institutional barriers to combat illegal wildlife trade and regulate the legal wildlife trade at national, provincial and landscape levels through improved regulatory and institutional frameworks, and enhanced and coordinated government action. The main loopholes and channels by which illegal trade can masquerade as legal will be closed.  Irresponsible legal trade will become more tightly regulated, while responsible legal trade will be given more freedom. In coordination with the global GEF Program on the Illegal Wildlife Trade, capacity amongst national and regional enforcement agencies will be increased, there will be greater awareness of the importance of reducing the use of wildlife products, and enhanced high-level political will to act. A nation-wide system for monitoring wildlife trade and wildlife crime cases will be established for the first time and operationalised. The Indonesian state and people will benefit economically while the globally significant wildlife of Indonesia, such as rhinos and tigers, will be lifted from the threat of extinction caused by unsustainable exploitation.

Indonesia is one of the world’s top 10 ‘megadiverse’ countries and the largest supplier of wildlife products in Asia, both ‘legal’ and illegal. Despite having only 1.3% of the world’s land surface, Indonesia supports 12% of the world’s mammals, 7.3% of the world’s amphibians and reptiles, and 17% of the world’s birds. Of these, 1,246 species of fauna and flora are globally threatened, the fourth most of any nation, including mammals (186 species, more than any other country in the world), birds (131 species, second highest in the world), amphibians and reptiles (64 species), fish (149 species), molluscs and other invertebrates (290 species), and plants (426 species).

Within Indonesia, one of the major causes of species decline, particularly for about one-third of bird and mammal species and all species of reptiles, is over-exploitation. Across the archipelago, key species including tiger, rhino, elephant, at least 14 primate species including orang-utan, birds, bears, orchids, marine and freshwater fish, turtles, fragrant timber (agarwood), pangolins, coral, snakes, bats, sharks, and rodents are being hunted and traded in enormous volumes. Illegal wildlife trade is the preeminent threat (along with habitat loss) to Sumatran Rhinoceros (Critically Endangered; population 100-120 individuals), Sumatran Tigers (Critically Endangered; 650 individuals), Asian Elephants (Endangered) and Sunda Pangolin (Critically Endangered). The small populations and low reproductive rate of many of these species places them at particular risk of local and/or global extinction in the face of such targeted, pervasive and increasingly intense exploitation.

Due to its geographic setting and status as a major trading nation, Indonesia is a large source, destination and transit point for smuggling and laundering of wildlife, such as African ivory. The consequence of the unsustainable trade is a massive threat to globally important wildlife. The value of the illegal trade in Indonesia alone is estimated at up to US$ 1 billion per year. Factoring in the unsustainable legal trade, the value significantly increases, translating into an enormous economic, environmental, and social loss.

Capture for the pet trade is the primary threat category for 34 bird species in Asia and is a major problem for several threatened birds in Indonesia, where protected species are also traded. Key species of concern include the Helmeted Hornbill (Rhinoplax vigil), numerous species of songbirds, and many parrot species. Populations of the Critically Endangered Helmeted Hornbill have been in serious decline, partly due to habitat destruction but mainly due to intense poaching for their beak ivory, also known as ‘red ivory’. In China, Helmeted Hornbill beaks are traded and processed through the same carving industries as elephant and rhino ivory, and sold in shops as luxury products, namely jewellery and decorative ornaments. With prices in China estimated at RMB40 per gram (USD 6.400 per kg), it commands an estimated five times the average price of black market elephant  ivory by weight, and is seen in some areas as a more ‘prestige’ product.

Of Indonesia’s 85 parrot species, 14 are classified as threatened. One of the regions with many parrot species is Wallacea which includes Sulawesi, Nusa Tenggara, and the Maluku Islands where trapping for domestic and international trade, combined with habitat loss has resulted in local extinctions for some species. These include the Critically Endangered Yellow-crested Cockatoo (Cacatua sulphurea), Vulnerable Salmon-crested Cockatoo (Cacatua moluccensis), Endangered Red-and-blue Lory (Eos histrio), and the Vulnerable Chattering Lory (Lorius garulus).

Evidence points to the decline of formerly common species which are legally traded domestically in Indonesia, such as the White-rumped Shama and Straw-headed Bulbul, which have declined to near extinction inside otherwise stable national parks. Such trade does not just affect species directly; removal of important ecological components can undermine the whole integrity of an ecosystem. This is particularly amplified when the species removed plays a ‘keystone’ role in an ecosystem.

Reptiles (Squamata, Crocodilia, Testudines) are among the most intensively harvested vertebrates for international export from Indonesia; extremely large volumes are traded both legally and illegally to supply the global demand for pets, traditional medicines, skins and food. There are at least 14 species of testudines, 22 species of squamatas, and 2 species of crocodilian poached and traded in Indonesia. Decline in many of these species groups is due largely to overexploitation, together with habitat degradation and loss.

Marine fish are a key source of subsistence and revenue across the Indonesian archipelago. Among them, manta rays, sawfish and sharks are large charismatic fish subject to international trade, with manta rays and sawfish being nationally protected. All sawfish species are globally Endangered or Critically Endangered. The characteristic toothed rostrum of sawfishes in combination with their shallow-water distribution, makes them extremely susceptible to entanglement in fishing gear particularly gillnets and trawl nets. Sawfishes were once found throughout the coastal and inshore regions of the tropical Atlantic, Pacific, and Indian Oceans; they were historically present in 90 countries and overseas territories.  Sawfishes are used for a range of products, many of which are of unusually high value even at the first point of sale by fishers. The fins from a large sawfish are highly prized for Asian shark fin soup. A set of sawfish fins can sell for several thousand dollars, making them among the most valuable marine fish products. Sawfish rostra have long been traded as curios and for other purposes, including currently on internet auction sites.

Sharks are landed and sold in domestic Indonesian markets and contribute to subsistence requirements in some coastal communities. However, international demand for shark meat, and particularly shark fins, is the driving force behind most shark landings. The high prices for some shark meat, for example spiny dogfish and porbeagle, as well as the premium prices paid for shark fins has prompted the increased targeting of some shark species and the increased retention of sharks taken as bycatch. Indonesia’s average annual reported shark catch between 2000-2010 was 106,288 tonnes representing 13.1% of reported global catch. According to FAO data, Indonesia catches more sharks than any other country in the world. Some shark species recognized as globally threatened are included in this trade, including the Vulnerable Whale Shark Rhincodon typus and Endangered Scalloped Hammerhead Sphyrna lewini. National efforts are underway to introduce new regulations on sharks designed to support sustainable use, however, these remain in the early stages.

Manta ray aggregations have been monitored and investigated in various locations around the world, including Indonesia. Some of these locations experience regular peaks in manta ray abundance, while others are only visited by the species seasonally, such as Komodo Marine Park, where long-term site fidelity by a part of the manta ray population has been reported. Mantas are targeted and also retained as valuable by catch to supply the international gill raker trade in Singapore, Hong Kong, Macao, Taiwan and Guangzhou, China. Some sharks teeth, and sawfish rostra are going to Bali and Mataram for handicrafts or souvenirs. Fresh products such as skin, meat, and entrails are typically sold within local markets. Both manta species occurring in Indonesia (Oceanic manta ray Manta Birostris and Reef manta ray Manta alfredi) are globally Vulnerable.

#### Institutional context

- Overarching Institutional Structure for Wildlife Crime Law Enforcement

According to an analysis by WCS There are a number of institutions at the regency, provincial, and national levels, which are directly or indirectly involved in forest governance and wildlife crimes. These include:

- Law Enforcement: National Police, the Attorney General’s Office, Ministry of Justice, and Supreme Court (adjudication).

- Environment and Forestry Sectors: MoEF, Provincial/Regency Forest Services, Provincial Natural Resources Conservation Agency (BKSDA), and Regional Environment Agencies

- Trade and Industry Institutions: Ministries of Industry and Trade, Customs and Excise, and Quarantine

- Agriculture: Ministry of Agriculture, Ministry of Agrarian Affairs and Spatial Planning/National Land Agency

- Transportation Institutions: Ministry of Transportation, and Port Administration

- Budget and policy institutions: Ministry of Finance, provincial governors, and regency heads

- Research Institutions: Indonesia Institute of Science (LIPI), Ministry of Research and Technology

- Coordinating Agencies: Coordinating Ministry of Politics and Security, and Ministry of National Planning.

According to the Indonesian Code of Criminal Procedures (KUHAP), there are four government agencies directly dealing with law enforcement: police investigators, prosecutors, prisons and courts, although the function of the courts is to adjudicate the cases filed by the law enforcers (criminal cases) or other government entities and the public (civil cases). The state police are the only institution to operate at the district level (kecamatan), while the other three operate at the regency/city (kabupaten/kota), where the lowest court (pengadilan negeri) exists, the province (the high court), and nationally (the supreme court). Usually, each institution at the lower level should report to, or coordinate with, its counterpart at the higher level. The courts are expected to exercise independent decision-making in their cases at each level.

The District Courts/Prosecutors (first level) are usually located in the capital city of the regency whereas the Provincial Court/Prosecutors (second level) are in the provincial capital. Either party may appeal to the higher (provincial) court if they are not satisfied with the verdict of lower court. The Supreme Court is the highest court, located in Jakarta. The Attorney General’s Office headquarters is also located in Jakarta.

- The Indonesian Criminal Justice System as Related to Wildlife Crime

The standard procedures to handle crimes at the level of enforcement agencies are regulated in Act No. 8/1981 on the Code of Criminal Procedures (Kitab Undang-Undang Hukum Acara Pidana, or KUHAP). The Criminal Code is generally applied to all types of crimes unless otherwise specified by another Act, in which case priority is given to the specific law under the principle of lex specialis derogate lex generali (e.g., Hukum konservasi [special crimes] vs. lebih diutamakan dibandingkan KUHP [general crimes]). Therefore, in practice, prosecution for wildlife crimes or crimes against conservation should use the Conservation or Forestry Acts instead of the Criminal Code, although certain crimes detailed within the criminal code can also be used as secondary or tertiary charges to back up the main charge. Similarly, all procedures to investigate and prosecute crimes must use the Code of Criminal Procedures unless specified by other laws.

The handling of legal issues in forestry and biodiversity conservation is not just a matter of criminal law, but also includes administrative law and civil law. Examples of civil lawsuits might include when the government is sued by the public due to tenure conflicts, or the government sues a company for improper behaviour. For example, the government has been sued using administrative law for granting of plantation rights in Rawa Singkil Wildlife Reserve, Aceh, which is the habitat of orangutans.

- Investigating Wildlife Crime

- The KUHAP states that criminal investigations should be carried out by police investigators or a civil investigators (Penyidik Pegawai Negeri Sipil - PPNS) who have been authorized by the law to carry out criminal investigations and file criminal cases in accordance with the Acts under which they operate.

- The MoEF has a number of officials who have been trained as civil investigators (PPNS) to investigate particular cases under the authority of their Ministries. Most of the MoEF rangers and investigators are posted in national parks or provincial BKSDA under the Directorate of Conservation of Natural Resources and Ecosystem (KSDAE -formerly the Directorate of Nature Conservation and Forest Protection - PHKA). Under the new structure of MoEF the Directorate of Law Enforcement (Gakkum)  is responsible for law enforcement. Although currently centrally based, Gakkum plans to establish Technical Implementation Units (UPT) at the field level to support enforcement However both rangers and PPNS remain under the KSDAE.

In contrast to police investigators, the PPNS of the MoEF can only investigate specific crimes in accordance with the laws under which they have jurisdiction, in this case forestry and wildlife crimes, and the PPNS of the MMAF can only investigate fisheries crimes. In addition, only civil investigators who have national licences can carry out investigations throughout Indonesia. Otherwise, they can only operate within specific working areas. Fully trained civil investigators are not automatically authorized to investigate criminal offences.

They must also have a Ministerial Decree from the Ministry of Justice as a ‘license’ to investigate. In fact, many investigators who have been trained do not have licenses, or they have licenses that have expired, or they operate outside their jurisdiction area. As a result, and because the police are authorized to investigate any form of crime, most of the cases are handled by police investigators. Customs and quarantine officers may also support the investigations of wildlife crime to monitor for the potential export/import/transport of wildlife from one site to another within Indonesia or other countries.

In the future, one recommendation is that all investigations on wildlife crime should be conducted by civil investigators as they have better specific technical knowledge than the national police, especially when dealing with searches, collecting evidence, or building cases for conservation-related crimes. Civil investigators only need regular training on searching, investigatory techniques and management of evidence. The process of investigating and delivering cases for prosecution is shown below.

Figure 1. Law enforcement process for forest and wildlife crimes and administrative violations (Suryadi et al. 2007)

- Ministry of Environment and Forestry

Prior to January 2015, the Directorate General of Nature Conservation and Forest Protection (Direktorat Jenderal Perlindungan Hutan dan Konservasi Alam, or PHKA) within the Ministry of Forestry was the responsible institution for biodiversity conservation and protected areas. After the merger of the Forestry and Environment Ministries, the Nature Conservation Agency (Balai Konservasi Sumber Daya Alam, or BKSDA, usually at province level) and National Park (NP) Office are the representatives (implementing units) of central government with responsibility to manage biodiversity and protected and conservation areas under the direction of the Directorate of Conservation of Natural Resources and Ecosystem (KSDAE) .The Directorate of Forest Law Enforcement within PHKA is a new Directorate General for Environment and Forestry Law Enforcement (Gakkum). The combination of law enforcement capacities between ministries is a particularly promising step in further reducing wildlife crime and forest crime, although there remains a limited number of law enforcement officers within the merged Ministries.

Currently, for the enforcement of wildlife crime Indonesia depends heavily on special forest rangers (forest rangers, or Polhut) and civil investigators (PPNS) whose establishment is mandated under Act No. 41/1999 on Forestry, and are given special authority to police matters relating to forest and wildlife crime. Operations of forest rangers are stipulated by the Decree of the Minister of Forestry No. 75/2014. Ministerial Decree No. 56/2014 also enables ranger-community partnerships (Masyarakat Mitra Polhut, or MMP), under which communities can be recruited and trained to assist rangers to protect forests and wildlife, join patrols, undertake awareness-raising activities, and provide information about illegal activities.

Every management unit (national park or BKSDA) employs forest rangers and civil investigators to undertake patrols for protection and law enforcement purposes. There is a total of 7,908 forest rangers across Indonesia, including 833 rangers who have been specially trained and form one of 11 regional rapid response units (Satuan Polhut Reaksi Cepat, or SPORC) to assist national parks or BKSDA for special enforcement operations. Only 2,999 forest rangers are based within protected area authorities. In addition, there are 1,841 civil investigators (PPNS) posted in national parks or BKSDA offices.

Taken together, this level of resourcing is far from sufficient compared with the >100 million hectares of forest area in Indonesia, the large number of islands and hundreds of conservation areas. Furthermore, even though rangers are authorized to enforce wildlife-related crimes, their authority is limited, and they do not have powers similar to the national police, such as the ability to detain suspects. It is important,that the capacity and authority of the forest rangers and civil investigators is increased to tackle the increasing number and the sophistication of biodiversity-related crimes (including wildlife crime, forest/habitat encroachment and bio-piracy). A second important limitation of the current system is that civil investigators are not able to directly submit official records of cases directly to the prosecutors. Instead, they must submit the official documents through the police investigators. Figure 2 below outlines the standard process for handling forestry/wildlife crimes.

Figure 2. Case handling for forest and wildlife crime

- (FR: Forest Ranger; FCI: Forest Civil Investigator)

- Ministry of Marine Affairs and Fisheries

Among the five Directorates General within MMAF, there are two Directorates General relevant to species conservation and conservation areas: the Directorate General for Marine Spatial Management; and the Directorate General for Supervision/Monitoring of Marine and Fisheries Resources, which is responsible for law enforcement. The Minister of MMAF has authorization under the Fisheries Law 31/2004 to define and decide protected species, quotas, and create conservation areas for fisheries resources under Government Regulation No. 60/2007 on Conservation of Fishery Resources. Similar to the MoEF, the MMAF has civil investigators (PPNS) with responsibility to investigate fisheries offences (including species protected under the Fisheries Law, such as mantas). However, the MMAF has no equivalent to forest rangers and the SPORC (i.e. rapid response units). This is a significant gap, particularly if the Ministry is willing to take over the CITES management authority for marine species from the MoEF. According to Act No. 1/2014, the MoEF should hand over the management authority for several marine national parks to the MMAF. However, the authority to manage these national parks currently remains under MoEF.

#### Policy and Legislative context

The Indonesian Constitution (1945) and the ‘Pancasila’ provide the overarching legal framework and basis for all laws and norms in the country (Soeprapto, 1998). Laws and policies related to the management of natural resources, including wildlife conservation, largely stem from Article 33 of the Constitution, paragraphs 3 and 4:

- The land, waters and natural resources contained therein shall be controlled by the State and be utilized for the greatest benefit of people’s welfare”….

- The organisation of the national economy shall be conducted on the basis of economic democracy upholding the principles of togetherness, efficiency with justice, continuity, environmental perspective, self-sufficiency, and keeping a balance in the progress and unity of the national economy.

The Second Amendment of the Constitution also supports the right of the population to have a healthy environment. These provide the basis for the laws and policies which regulate the sustainable management of natural resources for the welfare of Indonesian people. The national legal framework is regulated by Act No. 12/2011 (replacing Act No. 10/2004), on the Development of Laws and Regulations. Lower regulations must not conflict with the higher rank of laws nor supersede them, and the hierarchy of laws is as follows:

- The 1945 Constitution;

- Decree of the People’s Consultative Assembly;

- Parliamentary Act (Undang-Undang)/Government Regulation in Lieu of Law (Peraturan Pemerintah Pengganti Undang-Undang) – the highest law in the hierarchy of regulations. It can apply punishments such as prison sentences, fines, or administrative sanctions, and it is immediately binding;

- Government Regulation (Peraturan Pemerintah) – used to implement Acts;

- President’s Regulation (Peraturan Presiden) – used to implement Acts and/or Government Regulations. Ministers may issue Ministerial regulations in order to assist the President in the implementation of a higher rank of laws; and

- Regional Regulations (at Province/Regency/City level) (Peraturan Daerah).

In order to avoid abuse of power from lawmakers through legislation and regulations, the Indonesian Constitution reserves citizens’ constitutional rights to request a judicial review of any laws and regulations produced by the Constitutional Court or Supreme Court. A judicial review is a right to examine the validity of a legislation/regulation against a higher rank of laws. There are two types of judicial review: (1) a review of an Act against the Constitution, under the authority of the Constitutional Court; and (2) a review of a lower ranking regulation against higher regulations, under the authority of the Supreme Court. For example, the Ministry of Forestry Regulation establishing Batang Gadis National Park was reviewed against Act No.41/1999, by the Supreme Court at the request of a mining company inside the park.

- Relevant Policies, Legislation And Subsidiary Regulations

Land in Indonesia is classified into two main uses, Forest Areas and Non-Forest Areas (Area Penggunaan Lain/Land allocated for other purposes, or APL). Forest Areas come under the jurisdiction of the MoEF, with conservation and forestry laws providing the basis for issuing permits for management of forests areas and changes in forest functions. Land allocated for other purposes falls under the jurisdiction of the National Land Agency, with the Agrarian/Land Law providing the basis for issuing land rights and changes on land rights. All development, agriculture, plantations and other businesses activities can only be performed in ‘land allocated for other purposes’. With appropriate approvals, a Forest Area can be converted to ‘land allocated for other purposes,’ and vice versa.

Based upon the Spatial Plans Law, the Ministry of Agrarian Affairs and Spatial Planning (previously under the direction of the Ministry of Public Works) divides land categories into cultivation areas (kawasan budidaya) and non-cultivation areas (kawasan lindung). Non- cultivation areas are usually in the form of protected areas and forest areas, while cultivated areas are usually included in the ‘and allocated for other purposes’ category.

Coastal areas, small islands, and seas are under the authority of the MMAF. The Ministry’s authority overlaps with the MoEF on islands and coastal regions with respect to granting land rights and permits if the land is Forest Area. Overlaps of authority also occur with respect to management of conservation areas that consist of both land/island and sea.

Figure 3. Principal legislation relating to wildlife crimes and biodiversity conservation in Indonesia.

There is also a degree of overlap between ministerial authorities relating to species such as turtles, which fall both under the mandate of the Fisheries Act No. 31/2004 and the associated MMAF, and MoEF regulations on conservation and the environment.

Overlaps between the authority of ministries also occurs with respect to the Environmental Law, which provides for regulations relating to environmental management across the lands, rivers, lakes, sea, and air of Indonesia. The Environmental Law is best reviewed as an ‘umbrella’ act, which applies across sectors and subsidiary regulations. The main sectoral laws and subsidiary regulations are summarized below.

The USAID report on the policy and legal context for wildlife trade in Indonesia provides a full description of the legislation pertaining to species conservation, wildlife trade and wildlife crime, available online. The relevant legislation can be summarized as follows:

- Environmental Law

- Act No. 32/2009, on Environmental Management and Protection

- Conservation and Forestry Laws

- Act No. 5/1990: Conservation of Living Resources and Their Ecosystems (see Fig. 4 for subsidiary regulations)

- GR No.7/1999: Plant and Animal Preservation

- GR No.8/1999: Wildlife Utilization

- GR No.13/1994: Wildlife Hunting

- GR No.36/2010: Nature Tourism Enterprises in Wildlife Sanctuary, National Park, Grand Forest Park, and Natural Recreation Park

- GR No.28/2011: Management of Sanctuary Reserve and Nature Conservation Area

Figure 4. Act No. 5/1990 and Subsidiary Regulations

- Act No.16/1992: Plant, Fish and Animal Quarantine

- Act No. 41/1999: Forestry

- GR No. 45/2004: Forest Protection

- GR No. 6/2007: Forest management plan, forest use, and forest area management

- Act No. 18/2013: Prevention and Eradication Forest Destruction

- Marine and Fisheries Laws

- Act No. 27/2007, in conjunction with Act 1/2014: Management of coastal areas and small islands

- Act No. 31/2004 in conjunction with Act No.45/2009: Fisheries

- Act No. 32/2014: Marine

- Other Legislation

- Act No. 15/2002 and Act No. 8/2010: Prevention and Eradication of Money Laundering Crimes

- Act No. 20/2001: Eradication of Corruption

- biodiversity And Species Action Plans

The overarching policy document for the environmental sector is the Indonesian Biodiversity Strategy and Action Plan 2003-2020 (Strategi dan Rencana Aksi Keanekaragaman Hayati Nasional, or IBSAP), which was drafted by the government to replace the earlier Biodiversity Action Plan for Indonesia (BAPI), from 1993. It was intended to meet Indonesia’s obligations under the Convention on Biological Diversity to develop national strategies, plans, or programmes for the conservation and sustainable utilization of biological diversity. The IBSAP document contains a strategic plan and an action plan. The strategic plan contains the vision, mission, goals, objectives, and strategy for biodiversity conservation management, while the action plan is a more detailed elaboration of the strategic plan, and includes the policy direction, programs, performance indicators, and potential partners to implement the program. Overall, the document is a fairly comprehensive reference document that describes the condition of biodiversity in 2003, and the goals to be achieved by 2020. Since 2013, the Ministry of Environment has been evaluating the IBSAP implementation, and in January 2016 the revised IBSAP was launched by Bappenas for the period 2015-2020.

In addition to the general action plans, MoEF has also issued conservation strategies and action plans for several priority species. These documents are expected to be the reference and guidelines for parties interested in the conservation of certain species - see Figure 5 below (note – further National Plans of Action are in preparation for sharks and rays, and manta rays). Each of these action plans contain provisions and indicators which refer to measures to reduce the illegal poaching and trade in Indonesian wildlife. However, little comprehensive analysis exists of the complementarity or conflict between the various stipulations in these action plans in relation to their effectiveness to reduce wildlife trade.

Figure 5. Biodiversity Action Plans in Indonesia

| No |  | Species | Main Issues |  |
| --- | --- | --- | --- | --- |
| 1 |  | National Species | MoF Regulation No. 57/2008 National Species Conservation Strategy 2008-2018 Define priority species list and general actions to be carried out. |  |
| 2 |  | Sumatran Rhino | MoF Regulation No. 42/2007 Strategy and Conservation Action Plan for Rhino 2007-2017 |  |
| 3 |  | Sumatran Tiger | MoF Regulation No. 43/2007 Strategy and Conservation Action Plan for Tiger 2007-2017 |  |
| 4 |  | Elephant | MoF Regulation No. 44/2007 Strategy and Conservation Action Plan for Elephant 2007-2017 |  |
| 5 |  | Orangutan | MoF Regulation No. 53/2007 Strategy and Conservation Action Plan for Orangutan |  |
| 6 |  | Banteng | MoF Regulation No. 58/2011 Strategy and Conservation Action Plan for Banteng 2010-2020 |  |
| 7 |  | Anoa | MoF Regulation No. 54/2013 Strategy and Conservation Action Plan for Anoa |  |
| 8 |  | Babirusa | MoF Regulation No. 55/2013 Strategy and Conservation Action Plan for Babirusa |  |
| 9 | Tapir |  |  | MoF Regulation No. 57/2013 Strategy and Conservation Action Plan for Tapir |
| 10 | Javan-Hawk Eagle |  |  | MoF Regulation No. 58/2013 Strategy and Conservation Action Plan for Javan-Hawk Eagle |

- CITES, SPECIES PROTECTION AND TRADE

- The Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES)

Indonesia acceded to CITES in 1978, and enacted by Act No. 5/1990 and its associated subsidiary regulations as the principal national legislation for CITES implementation. The MoEF is the CITES Management Authority, and the Indonesian Institute of Sciences (LIPI) is the CITES Scientific Authority.

CITES regulates and monitors trade in the manner of a ‘negative list’ such that trade in all species is permitted and unregulated unless the species in question appears in the appendices. Protected species are listed in one of three appendices: Appendix I, about 1,200 species, are species that are threatened with extinction and are or may be affected by trade. Commercial trade in wild-caught specimens of these species is illegal (permitted only in exceptional licensed circumstances for non- commercial purposes). Appendix II, about 21,000 species, are species that are not necessarily threatened with extinction, but may become so unless trade in specimens of such species is subject to strict regulation to avoid utilization incompatible with the survival of the species in the wild. International trade in Appendix II species may be authorized by the granting of an export permit or re- export certificate by the management authority of the exporting country. Appendix III, about 170 species, are species that are listed after one member country has asked other CITES parties for assistance in controlling trade in a species. The species are not necessarily threatened with extinction globally. In all member countries, trade in these species is only permitted with an appropriate export permit and a certificate of origin from the state of the member country that has listed the species.

- CITES Legislation in Indonesia

Although Indonesia acceded to CITES in 1978, it took until 1990 before national implementing legislation was put in place. Act No. 5/1990, on Conservation of Living Resources and their Ecosystems, is the principal legislation for CITES implementation. However, it took until 1999 for the necessary subsidiary regulations to put in place. These include Government Regulation No. 7/1999, on Preservation of Animal and Plant Species, and Government Regulation No. 8/1999, on Utilisation of Wild Plant and Animal Species. Further subsidiary regulations include the Decree of the Minister of Forestry, No.P7/2003, on Administration Directives of Harvest or Capture and Distribution of the Specimens of Wild Plant and Animal Species, and the Decree of the Minister of Forestry No. P.19/2005, on Captive Management of Wild Plant and Animal Species.

The framework provided by Act No. 5/1990, and the subsidiary regulations, has been assessed by CITES to be sufficient for national implementation of the Convention. However, substantial loopholes in this legislation exist with regards to non-native species, and difficulties in updating the protected species lists to reflect new additions to the CITES appendices. The Act also does not provide any regulation for the sustainable use of non-protected species.

Although Government Regulation No. 7/1999 and Government Regulation No. 8/1999 provide some legal protection for non-protected species using other laws, such as the General Criminal Law, Customs and Excise Law and Quarantine Law, implementation of these regulations has so far been ineffective.

The regulations establish permitting systems for CITES-listed species, which include harvest management, catch quota setting, control of transport and control of captive management systems. Following workshops in Indonesia focused on non-detriment finding methodologies in 2002, the Indonesian CITES Scientific Authority is now using the IUCN Guidelines to assist in making non-detriment findings for Appendix-II exports. Quotas are established on an annual basis, based on non-detriment finding assessments through a consultation procedure culminating in a Decree of the Director General of Forest Protection and Nature Conservation that identifies the annual allowable harvest of each species at national level, allocated between various provinces.

The Decree of the Minister of Forestry No. 447/2003 establishes procedures for inspection and controls conducted by authorities at all levels (BKSDA and central office of KSDAE) on harvests, middlemen, traders, transporters and exporters or importers, which must be in accordance with allocated quotas. Captive-based production of specimens is directed and regulated by the Decree of the Minister of Forestry, No. 19/2005. This decree provides guidance and regulation on captive breeding in accordance with CITES Article VII and Resolution Conf. 10.16.

Although this regulatory framework is impressive, there are a number of significant problems with the legislation, the most important of which is the protected species list attached as an Annex to Government Regulation No.7/1999.

- Government Regulation No.7/1999: The Protected Species List

At the heart of this regulatory framework is Government Regulation (GR) No.7/1999, which provides the list of protected species in Indonesia. The list covers 294 species or species groups: 70 mammals, including cetaceans; 93 birds; 31 reptiles: monitor lizards, gharials and crocodiles, some pythons, some freshwater and land turtles, all sea turtles, sailfin lizards; 20 insects: all butterflies; 7 fish: including sawfishes (Pristis spp.); 1 coral: black coral; 14 molluscs: clams, nautilus, giant triton, coconut crab; 58 plants: including orchids, rafflesia, pitcher plants and dipterocarps.

Catching from the wild or trafficking any of these species is an offence under Act No. 5/1990, with a penalty of up to five years imprisonment and a fine of up to 100 million Rupiah.

Further, GR No. 8/1999, Article 34, lists 11 species or species groups that can only be utilised and exchanged by the President of the Republic of Indonesia. These are: Anoa Anoa depressicornis, Anoa quarlesi; Babirousa Babyrousa babyrussa; Javan rhinoceros Rhinoceros sondaicus; Sumatran rhinoceros Dicerorhinus sumatrensis; Komodo dragons Varanus komodoensis; Birds of paradise (All species from the family Paradiseidae); Javan Hawk-eagles Spizaetus bartelsi; Sumatran tigers Panthera tigris sumatrae; Mentawai gibbons Presbytis potenziani; Orangutans Pongo pygmaeus; and Javan molochs Hylobates moloch.

There are, however, a number of significant problems with the protected species list, and the provisions in GR No. 8/1999. In the 16 years since the issuance of GR No. 7/1999, no evaluations or updates have been made for the protected species list. These therefore do not reflect the more recent changes in CITES restrictions and bans, as well as nomenclature changes

- CITES implementation in Indonesia

Implementation of CITES, including enforcement of all related legislation, requires cooperation and coordination amongst related agencies and ministries at the national level. It also needs close cooperation through bilateral, regional and international organisations, including international organisations and non-governmental organisations. At the national level, the CITES Management Authority, MoEF, must coordinate CITES implementation and enforcement with many other agencies, including customs, quarantine, police and other related agencies. Several training manuals, guidelines on species identification and CITES have been produced accordingly. Training and capacity building for law enforcement officers of related agencies has been conducted by the CITES Management Authority, and collaborations with bilateral and non-government organisations are used to detect illegal wildlife trade, undertake population monitoring and other CITES-related matters.

Cooperation with ICPO-Interpol is also helpful to assist law enforcement at the international level and enhance the networking capacity of the CITES and law enforcement authorities in Indonesia.

At the regional and international level, Indonesia leads the implementation of the ASEAN- Wildlife Enforcement Network (ASEAN-WEN). This network could be used to share intelligence information and for cooperation on CITES matters with ASEAN member countries. In addition, the Government of Indonesia has been developing bilateral agreements with particular countries such as Vietnam, which is a frequent source destination of illegal wildlife products from Indonesia. Under a bilateral MoU with the United States of America, Indonesia is also prioritising action on combatting illegal wildlife trade. Finally, Indonesia was a signatory to the London Declaration on Illegal Wildlife Trade in February 2014.

CITES management arrangements for marine species

Currently the MoEF is the only CITES Management Authority in Indonesia, and LIPI is the CITES Scientific Authority. Under this system, regulation of CITES-listed marine species is problematic, because they also fall under the jurisdiction of MMAF. Article IX of CITES provides that each party shall designate for the purposes of the present convention: (a) one or more Management Authorities competent to grant permits or certificates on behalf of that Party; and (b) one or more Scientific Authorities. It is therefore possible for the CITES Management Authority, MoEF, to share its roles with MMAF with respect to marine species in Indonesia. But this would require a modification of the existing CITES implementation regulations.

National legislation for CITES implementation must be able to meet at least four criteria: (1) designate management and scientific authorities; (2) take appropriate measures to enforce the provisions of the present Convention and to prohibit trade in specimens in violation thereof; (3) penalize trade in, or possession of, such specimens, or both; and (4) provide for the confiscation or return to the State of export of such specimens. However, there is concern that the Fisheries Laws (Act No. 31/2004 and as amended with Act No.45/2009) do not provide for item (2), and would require reform in order to become suitable for CITES implementation in Indonesia.

Development of CITES implementation regulations by any additional CITES Management Authority should meet the same criteria. For MMAF there are two basic options:

Option 1: Continue to use Act No. 5/1990 and its subsidiary regulations as the basis for CITES implementation and designation of protected species. Under this scenario, the Fisheries Laws (Act No. 31/2004 and No. 45/2009) are used as complementary legislation. MMAF could establish additional complementary implementing regulations specific to marine species as necessary.

Option 2: The Fisheries Laws (Act No. 31/2004 and No. 45/2009) are used as separate national legislation for CITES implementation on marine species. However, since the Fisheries Laws do not meet all the requirements for CITES legislation, Act No. 45/2009 would need to be amended to meet the CITES requirements prior to its application as the national legislation for marine species.

The institutional framework which must be built to transfer the authority from the MoEF to MAAF on marine species has been recommended as follows:

- CITES management Authority in Indonesia may be operated by two agencies, with additional authority for marine species operated by MMAF;

2)	In the case two Management Authorities are operational, there must be designated one coordinator or focal institution to communicate with CITES Secretariat and other Parties. In this case MoEF may be designated as the focal point to represent Indonesia;

3)	For the time being the MMAF uses Act No. 5/90 and its implementing regulations for CITES as the principal legislation for the CITES implementation on marine species.

4)	Prepare organization structure, especially control mechanism, including permit issuance, inspection including monitoring of catch and transport:

a.	Organization structure at the national level consists of agencies under the ministry to perform the functions of Management Authority for marine species at national level;

b.	Organization structure at local level which perform the Management Authority’s function in inspection, monitoring of harvest, captive breeding and grow out and data base management system for control purposes;

5)	Law enforcement structure devised to perform the authority’s function in investigation of crimes and protection of marine species.

6)	Organization structure to establish Non-Detriment Findings (NDF) specifically devised for marine species, including for quota establishment, population monitoring, development of NPOA and poliy development;

7)	Designate transition period to transfer the authority from the MoEF to MMAF;

8)	Review Fisheries Laws and revise as necessary to meet CITES requirements for the implementation of the Convention.

Whichever option is chosen, once the designation of the MMAF as a CITES Management Authority is in effect, an effective institutional strengthening and capacity-building process is required for issues relating to issuance of permits, control of harvests, control of transport and law enforcement.

Threats, Root causes and Impacts

This project specifically addresses the threats posed by the illegal and unsustainable wildlife trade to endangered species in Indonesia. The illegal trade in fauna and flora (other than fisheries and timber) has been estimated by different sources to be worth US$ 7-23 billion dollars annually and US$ 2.5 billion in East Asia and the Pacific alone. Some of the values associated with wildlife products are huge; ivory is being traded at over $2000/kg whilst Rhino horn can fetch over $66,000/kg, Helmeted Hornbill beaks trade for $6400/kg in China, Sun Bear gall bladders up to $2000 each, Tiger canine pairs at $6200-7200 and Pangolin scales $3000/kg.

This trade has already caused the decline and local extinction of many species across SE Asia, including those inside protected areas. The impacts have been particularly strong in this region, with populations of tigers, Asian elephants and various turtle species showing severe losses . Much of the trade is highly organized, benefits a relatively small criminal fraternity, whilst depriving developing economies of billions of dollars in lost revenues and development opportunities

Combatting the illegal wildlife trade in Indonesia is hindered by its low domestic political profile, which translates into a lack of interest and poor collaboration between law enforcement agencies. There is also a widespread lack of understanding regarding laws and enforcement procedures at all levels, and regulatory loopholes and inconsistencies that prevent successful prosecutions (see barriers section for further information). For example, inside Indonesia the trade and sale of African ivory and non-native tiger or rhino parts is technically not illegal. Regulatory reform is critical to address these issues.

Wildlife crime is driven by complex demands from various complex and fluid markets. Opinions on the primary drivers behind wildlife crime (and the corollary responses to address them) differ widely amongst different wildlife experts, partly due to a lack of data and partly due to most workers in the field focusing on a specific species or area with few having a wider view across the supply chain. Many of the variations in wildlife crime can certainly be attributed to variations in markets, and most supply chains displaying high levels of variability in response to changes in supply and demand. Furthermore, increasing economic wealth is thought to be a significant factor behind increasing demand for wildlife products and the trappings of economic growth such as better infrastructure and freer trading markets are also thought to have had significant impact on wildlife crime. One of the key sources of demand for wildlife products has been the Traditional Chinese Medicine (TCM) industry, which has ancient cultural roots but has been increasing in popularity in recent years in tandem with rapid economic growth in China and countries where Chinese medicine is popular, and new trends are also occurring. However, other sources of demand are also important, including the pet trade, food (for protein intake, and also as delicacies), curios and souvenirs and fur and skins. The few market-based instruments that have been used to address wildlife crime such as certification, taxation and buying agreements – used particularly for timber – do appear to be having some success.

Without enforcement, laws and sanctions alone do little to deter wildlife criminals. Laws and regulations are generally thought to be a critical part of the framework for addressing wildlife crime. However, the existence of laws and punishments alone do not necessarily have any impact on wildlife crime, with the risk of detection being a key factor for compliance.

The underlying socio-economic factors contributing to these threats include population growth and poverty in rural and protected area boundary zones, which reduce the ability of local communities to practice sustainable agriculture and natural resource use.  Productive job opportunities – which might provide local residents with an alternative source of livelihood – are limited, driving some to engage in illegal poaching activities. However, middle-men and traders gain significantly more from the trade in wildlife products and are usually based in urban centres. Whilst links between poverty and the wildlife trade evidently exist, particularly with regards to leaving the trade, the relationships appear to be so complex that initiatives to counter wildlife crime through alternative livelihoods or increased incomes do not seem to be very successful. As with the impacts of livelihoods, the relationship between awareness and wildlife crime also appear to be highly complex and relatively poorly understood.

The economic and social impacts of wildlife crime are far less understood but potentially far more serious. The impacts of wildlife crime are not only environmental. Illegal wildlife trade involves wide, complex markets involving people from wide and various social and economic backgrounds from poor rural villagers to small scale traders to wealthy, politically connected importers and exporters. The impacts of the industry can therefore be far reaching . Firstly, the environmental impacts will have social implications through the loss of ecosystem functionality, the spread of zoonotic diseases, the reduction in available natural assets and through missed taxation revenue. In Asia, this is particularly a risk for poorer communities strongly reliant on natural resources. But there is also plenty of evidence that the social impacts of wildlife trade go even further than that, including direct threats to the lives of people working in the sector, the proliferation of weapons, the fuelling of social conflict and undermining governance, socio-economic stability and even national security. Furthermore, wildlife crime is often associated with other serious, organised criminal activities and/or political rebel groups (particularly in Africa) with shared personnel, trading networks, finances and methods to undermine the rule of law. Much of the world’s wildlife crime is now run by extremely organized and increasingly sophisticated and well-equipped criminal syndicates.

Long-term solution and barriers to achieving the solution

The proposed long-term solution is to conserve key wildlife species in Indonesia, by ensuring that the legal wildlife trade is ecologically and economically sustainable, while reducing the scale and impact of illegal wildlife trafficking, both from Indonesia and in transit through the country. Wildlife is a natural resource that if exploited well can fuel development, provide considerable state revenues and provide financial incentives to manage wildlife and ecosystems. However, in order to achieve this long-term solution, a number of policy, legislative, regulatory and institutional and human capacity barriers have to be overcome. These will be addressed through the project alternative, which aims to reduce the volume of unsustainable wildlife trade and the rate of loss of globally significant biodiversity in Indonesia and East and Southeast Asia.

- Barriers

Although the legal framework for wildlife protection and regulation of wildlife trade in Indonesia is relatively well developed, it contains a number of significant loopholes, which are facilitating or enabling the continuing illegal trade of legally protected, and otherwise threatened species in Indonesia. In addition, there are a number of significant implementation challenges which hamper the enforcement of the existing legal framework. Thus, while the government has made tremendous efforts to control poaching and illegal wildlife trade as described above, its efforts have been impeded by a number of barriers. These can be summarized as: (1) Weak policy and regulatory framework and insufficient information and tools to understand, regulate and combat illegal wildlife trade; (2) Suboptimal institutional capacity for compliance monitoring and enforcement; and (3) Ineffective enforcement at the site and landscape level, inlcuding exit points from the country.

- Weak policy and regulatory framework and insufficient information and tools to understand, regulate and combat illegal wildlife trade

There are a number of key issues that need to be resolved regarding the legal framework, particularly concerning the outdated and weak GR No. 7/1999, under Act No. 5/1990, which fails to protect some CITES listed species, and other species that are of critical conservation concern in Indonesia. These issues include:

- The protected species list was approved in 1999, and has never been updated, despite the mandate of Article 4 of the regulation which enables the Minister to change the list. Many species are protected by CITES or recognised as highly threatened by international bodies (e.g. the IUCN Red List) but are not legally protected in Indonesia.

- Taxonomic corrections are required to the protected species list.

- A finer level of species classification is needed for the protected species list to support national implementation of CITES, for which it would be desirable to identify additional categories, such as unprotected species for which trade is regulated.

- Generally all the species on the protected species list are found in Indonesia (one exception being Indian Elephant), there is no provision for non-native species which are protected under CITES (e.g., African Elephants, or non-native tiger subspecies – the Sumatran tiger subspecies is listed in PP7 rather than the species). Therefore, it is not an offence to trade these species within Indonesia (although import and export should be tightly regulated according to CITES), a significant loophole.

- Very few marine species are on the protected species list, and the jurisdictional authority over marine species is unclear (see above), since they are covered by both the Conservation Law No. 5/1990, and the Fisheries Law No. 31/2004, with some regulatory differences.

- The list in Government Regulation No. 7/1999 covers only a few of the priority species of significant conservation concern in Indonesia. Even amendment in line with CITES may leave Indonesia at risk of the extirpation from the wild of many endemic species.

In addition, many species protected under Government Regulation No.7/1999 have significant populations outside the protected area network, in forest areas which overlap with agricultural concessions and areas of human habitation. These unprotected forest areas are often critical habitat for key species – for example, up to 75% of orangutan habitat has no legal protection. Despite the legal protection for protected species on paper, if they are found outside protected areas the result is often that they are killed, purposefully displaced, or enter the illegal wildlife trade. Land owners have little incentive to admit they have protected species on their land, and little support for the management or relocation of these species, if present.

Although Environmental Impact Assessments (AMDALs) or Environmental Management  and Monitoring documents (UKL-UPL) must be completed by concession owners once land is obtained, there are numerous issues with the correct issuance of these permits and they are often viewed as a minor administrative hurdle, with little or no follow up. Members of the Roundtable on Sustainable Palm Oil (RSPO) are also required to conduct a High Conservation Value (HCV) assessment of their concessions, one aspect of which is a biodiversity management plan. However, HCV assessments are not a legal requirement and monitoring of the implementation of the HCV biodiversity monitoring plan is often limited. Overall, linking habitat protection and species protection through the legal framework is therefore a critical loophole which must be addressed in order to conserve species more effectively in situ, and prevent entry into wildlife trade supply chains.

Key legal reforms required include updating the status of the protected species lists (now in progress), increasing the sanctions and sentences (including the introduction of minimum sentences), ensuring wildlife crime is classed as a serious crime in law, (allowing coverage by the UN Convention on Drugs and Organised Crime), making wildlife crime a ‘predicate offence’ under the Financial Action Task Force enabling forfeiture of criminal assets and revising and clarifying the shared authority and responsibilities of the forest police and national police and addressing any conflicts of interest risked when tasking the same government divisions with issuing permits for legal trade whilst simultaneously being responsible for prosecuting those who break the law, many of whom may be the same people.

There is in general a lack of awareness amongst the judiciary, prosecutors and investigators of the economic impacts of wildlife and forest crime, which can be extremely large when proper environmental valuations are accounted for. Market values of wildlife and wildlife products can be an indicator of the gravity of these crimes, but even these do not account for the broader economic costs of the loss of wildlife or habitat. Public awareness of the willingness to apply severe sentences for wildlife crime and forest or marine crimes can act as a strong deterrent. In the context of the imposition of financial penalties for example, the level of fines could take into account the state's current and future losses as the result of criminal acts in the sector of conservation. In addition, the perpetrators could be penalized to pay the entire cost of law enforcement and court fees, including costs incurred as the result of the maintenance of plants and wildlife.

- (2) Suboptimal institutional capacity for compliance monitoring and enforcement

Lack of technical knowledge within investigators and prosecutors - Overall, there is a need for a continuing and targeted focus on capacity building and improved coordination among police, civil investigators and prosecutors, specifically with relevance to wildlife crime and trade, protected species, the environmental and economic benefit of species, and the full range of relevant and appropriate laws and regulations that should be applied. The development of a Wildlife Crimes Unit within the national police and its local offices is needed to combat wildlife crime more effectively.

Insufficient knowledge/training for enforcement officers – There is a need to improve training on effective enforcement techniques and processes for port officers/customs including through working partnerships with civil investigators. This needs to include knowledge on CITES regulations, listed species and support for species identification, as well as the development of standard operating procedures for various scenarios.

Limited capacity of civil investigators - Act No. 5/1990 refers to animal "parts" – however determining what parts have come from illegal wildlife requires some specialist knowledge.  Investigators are often incorrectly unwilling, or belive they are unable to conduct confiscation or order arrests based on ‘probable cause’, (e.g. suspicion that jewelry is elephant ivory) and therefore often demand certainty before the initial enforcement action is taken. If this requires laboratory testing for example, this can significantly delay enforcement action. Improved investigator training is therefore required to improve understanding and confidence in their existing legal mandate, but also to support better understanding of the appropriate use of forensic analysis in supporting prosecutions, and its correct application. This will require regular training and cooperation with forensic laboratories, such as the Eijkman Institute and the police.

In view of existing challenges in securing successful prosecutions and deterrent sentences, the government needs to apply a more integrated approach to law enforcement, which leverages multiple laws to secure successful prosecutions, i.e., a “multi-door” approach. This new approach to prosecutions was launched in Indonesia in 2012, but has not been exploited fully due to the limited experience and awareness of police and prosecutors in pursuing this kind of strategy for investigations and prosecutions. Applicable laws for prosecutions related to wildlife crime could include the relevant Acts on forestry, the environment, conservation, fisheries, quarantine and customs, corruption and money laundering. A forestry or marine crime may actually be better prosecuted under an alternative act for which sentences are longer or fines are larger.  An important challenge is that these different types of charges are handled by different divisions within the prosecutors’ offices (special and general crimes) and different types of courts (i.e., some special courts are only located in a few locations, e.g., fisheries, human rights, corruption, and not all district courts yet have certified environmental judges). Secondly, environmental certification for judges does not include marine cases; fisheries cases are the subject of a separate certification program. Thirdly, there is no integrated justice sector training or approach for managing all environmental cases or for applying the multi-door approach.

Improved institutional coordination between agencies, data sharing and data management: Improved institutional coordination is needed between relevant agencies, including customs, wildlife protection, quarantine, police and civil investigators. Data and information play important roles in successful law enforcement, therefore protocols on data exchange need to be developed at national and international levels. Intelligent data exchange should be made possible at the international level through the development of bilateral, regional (such as ASEAN-WEN) and international (CITES, ICPO-Interpol and World Customs Organisation) collaboration agreements. Improved and shared database systems between agencies, including for example standardized data collection/sharing protocols, and alert systems, is needed to support inter-agency collaboration. In addition, use of existing international systems, such as Eco Message of ICPO-Interpol and Alert of CITES will increase the capacity of law enforcement at national level. Such data sharing systems should also include inputs from the public, such as investigations, evidence, complaints, tips, etc., and should make key information available to the public to enhance transparency and accountability.

Increased bilateral, regional and international cooperation: There is a need to prioritise the development of strong relationships with other countries in the region to facilitate searches, investigations and the repatriation of evidence when intercepted elsewhere. Joint extradition agreements for suspects related to wildlife and forest crime between key buyer/seller countries when the suspect is detained overseas should be explored. At the regional and international level, Indonesia leads the implementation of the ASEAN-Wildlife Enforcement Network (ASEAN-WEN), which could be used to share intelligence information and for cooperation on CITES matters with ASEAN member countries. Cooperation with ICPO-Interpol is also helpful to assist law enforcement at the international level and enhance the networking capacity of the CITES and law enforcement authorities in Indonesia. In addition, the Government of Indonesia has been developing bilateral agreements with particular countries such as Vietnam, which is a frequent source destination of illegal wildlife products from Indonesia.

Awareness raising – While the relationship between raising awareness and wildlife crime appears to be highly complex and relatively poorly understood (TRAFFIC 2008a), with consequent risks for running effective campaigns, there is a need to raise awareness of wildlife trade cases and penalties in order to staunch demand for wildlife products and increase pressure for improved enforcement. NGOs in Indonesia play a critical role in developing and supporting awareness raising and  capacity development and should be encouraged by the government, including increased cooperation with the justice sector.

- (3) Ineffective enforcement at the site and landscape level

This barrier concerns two principal nodes in wildlife trade supply chains – enforcement at ports involved in wildlife trade, and in natural landscapes containing significant protected areas which act as source areas for the wildlife trade, impacting populations of globally significant biodiversity. Preventive enforcement actions in natural landscapes that stop wildlife entering the wildlife trade are of great significance, as they will directly help to sustain wild populations.

Wildlife crime in Indonesia appears to be increasing, in line with global trends, and demonstrates increasing organization within the trade. With assistance and lobbying from CSOs, progress has been made in increasing the effectiveness of enforcement procedures, and seizures of illegal wildlife and wildlife products are now being regularly made with a higher percentage of offenders being prosecuted. Still, there are weaknesses in the enforcement system that require urgent attention in view of the pervasive and immediate threat to very rare wildlife species. These weaknesses and challenges can be summarized as follows:

Government driven detection is limited by insufficient resources. It is often led or assisted by CSOs, such as the Wildlife Conservation Society (WCS), Fauna and Flora International (FFI), Jakarta Animal Aid Network (JAAN), ProFauna, TRAFFIC and others. Ranger/community partnerships can provide a source of information, which could be scaled-up and targeted to particularly vulnerable areas.

In the organizational structure of SPORC there are intelligence units, but these are very few in number and do not have the resources to monitor all the major illegal wildlife trade centres in Indonesia. The MMAF does not currently have any equivalent rangers or SPORC. With the creation of the new Directorate General for Environmental and Forestry Law Enforcement, there may be an opportunity to significantly scale-up the number of civil investigators and increase their intelligence capacity through specialized training, and apprenticeship/training programs with the police.

There is also an inadequate focus on markets and transport hubs, which are key focal points in the illegal wildlife trade. Here officers from other government agencies (airport and seaport security, customs, etc.) could be brought in to increase the overall surveillance effort.

Monitoring and reporting on wildlife crimes is also difficult for members of the public, and, even when reports are received, follow-up rates are often low, decreasing the motivation to report crimes. As wildlife crime and the trafficking of species becomes more sophisticated, detecting crimes often requires specialist training and tools, but these are not available at the point of need – for example, proving the type and origin of species of animals and plants in a port area cannot be done by Forestry Police and Forestry Investigators since the location is under the authority of the Customs or the Quarantine; while investigators from Customs or Quarantine do not have the authority and capacity to investigate forestry crimes. There are also insufficient sanctions and disincentives for officers who fail to carry out their duties correctly.

There are various procedural challenges associated with arrest and detention protocols. Law enforcement against wildlife crimes is under the jurisdiction of the police, forest rangers (Polhut), and forestry civil investigators (PPNS). Forest rangers are not automatically authorized to investigate wildlife crime or act as PPNS – only limited numbers of rangers or forestry officers are licensed to do so. However, the forestry PPNS cannot arrest suspects of wildlife crime directly, they must instead involve the police. By contrast, Act No. 41/1999 does authorize the forestry PPNS to arrest suspects for forestry crimes.

Wildlife trade increasingly takes place online, and the legal framework to control it exists, however forestry investigators have no authority in such cases despite having the technical knowledge required. A second obstacle is that the Conservation Law has yet to regulate the use of photos, videos or electronic files as evidence in wildlife and forestry crimes. This is critical in wildlife crime cases, where ‘evidence’ is often live and needs specialist care before it can be transported back to rehabiltation centres. The length of time required for investigation often puts confiscated animals at risk of dying while cases are in court.

In terms of case registration and prosecution, there is inadequate collaboration between forestry rangers, civil investigators and the police in some cases. There is also limited collaboration, and no standard procedure, between BKSDA/Forestry with the police/military in the prosecution of wildlife crimes.

Overlapping mandates over marine resources also result in implementation challenges (e.g., overlapping/gaps in budgets, and conflicting authorities) on the ground, and enable wildlife trade networks to take advantage of the resulting gaps in enforcement.

There are additional challenges in the enforcement and implementation of legal ‘non- detrimental’ harvest quotas of CITES listed species. The process for determining quotas in Indonesia faces considerable challenges, and in the past has been poorly administered and open to abuse. The ongoing paucity of scientific data to adequately determine non- detrimental harvests is likely to remain a continuing challenge for many species.

The lack of financial resources has been highlighted by stakeholders inside and outside the government as a critical barrier to effective enforcement. The amount budgeted to the Ministry of Forestry for all wildlife management is just USD $70 million, to cover an area of 130 million hectares, an average of 16,000 ha per staff member. Investigations, patrols and other ground-level interventions have the benefit of stopping wildlife crime before animals are killed. Intelligence and investigative actions are a proven tool for addressing wildlife crime across the supply chain. However, it is an area where the mandate and authority of Forest Police and Civil Investigators overlaps strongly with the police, and the numbers of patrol staff on the ground are insufficient to act as a deterrent for poaching, and wages are low. Technical resources and staff capacity are also often lacking – for instance, DNA identification technology has been requested to identify source sites for wildlife, and the Customs Authority has requested simple identification manuals of CITES-listed species. However, although resources are limited, they are not always efficiently utilised – ratios of office vs. patrol staff in national parks are weighted to keep most employees in park headquarters. NGO-government partnerships established by WCS and FFI have also been identified as good hybrid models for the interim which are achieving firm results on the ground, albeit in limited areas, and require further financial support for upscaling. Many cases are strongly reliant on funding through NGOs to support procedures through to prosecution.

Management and enforcement of natural resource violations is also hindered by the lack of coordination between relevant agencies – the distribution of forest and wildlife extend beyond protected area borders and across different provinces. Therefore, to strengthen efforts towards collectively tackling the illegal wildlife trade, a broader range of partner agencies need to collaborate more closely. This should involve traditional partners such as BKSDA and the Forestry Agency. It should also involve non-conservation agencies that share similar high-level goals, such as tackling corruption, especially where the legislative framework already exists. The highly effective Corruption Eradication Commission and the Indonesian Financial Transaction Reports and Analysis Centre (PPATK) have yet to play a prominent role in addressing wildlife crimes, but have had several successes in providing irrefutable evidence and novel approaches for prosecuting illegal logging cases, such as on money laundering charges.

Taking a multi-agency landscape-level approach is integral to securing wildlife and their habitat beyond protected area borders. This process has already started in the Kerinci Seblat landscape in Sumatra with the development of a cross-agency network formalised under an MoU that enables inter-institutional and trans-border law enforcement actions to be conducted by the national park authority, police and wildlife agencies. In the Leuser landscape, the same agencies are involved and making regular arrests and prosecutions, but are operating under a different modality with individual institutional agreements in place.

Civil society participation needs to be strengthened to achieve conservation goals outside protected areas - experience from several landscapes in Indonesia has demonstrated the merits of using carefully cultivated local information networks to more effectively tackle the illegal trade of wildlife and timber. This trade is predominantly conducted through organized criminal networks, which therefore requires an organized multi-agency response. However, additional support is needed for civil society groups to conduct on the-ground actions, such as anti-poaching information gathering and reporting. In turn, this will enable protected area and/or law enforcement agencies to conduct more successful intelligence-based forest patrols to detect and destroy snare traps and to conduct sting operations to arrest poachers/traders.

While this project deals with wildlife trade issues, the entry point for many animals into legal and illegal wildlife trade routes often starts with habitat conversion and PA encroachment and associated human-wildlife conflicts and trapping / poaching of wildlife. Addressing hunting is critical to cutting off the supply chain at its roots, and NGO and government efforts to enforce protected area boundaries and patrol national parks are critical and need further resources. Similarly, implementation of the MoEF’s human-tiger conflict mitigation protocol requires further support. The lack of clearly demarcated boundaries is a common issue for protected areas (e.g. Kerinci Seblat, Gunung Leuser and Bukit Barisan Selatan National Parks in Sumatra), impacting the effectiveness of enforcement of encroachment and wildlife infringements. The long-term engagement of neighbouring communities through education, awareness and rural development programmes, coupled with improved patrolling and enforcement, is needed to redue encroachment and wildlife crime, with the support of related local government agencies.

In addition, the capacity for effective protected area management in most parts of Indonesia remains weak in terms of the manpower to cover such huge and remote areas. Management would be strengthened if the number of staff, especially active forest rangers, were increased and spread to provide wider coverage across protected areas, especially those containing species prized by traders. However, a lack of able staff, especially forest police (Polhut), and a need to recruit more has been recognized as a common constraint facing protected areas. Consequently, ranger teams may be supplemented through sourcing suitable candidates from nearby communites, which offers additional benefits through access to local informants. However, these community rangers have an honorary status and therefore lack job security, opportunities for promotion and personal safety, especially as they enforce the law in villages and subdistricts where they may be known to offenders.

The human resources situation also extends to a lack of available expertise in the form of elite wildlife crime investigators. Working as Civil Service Investigators (Penyidik Pegawai Negeri Sipil, PPNS), these personnel are vital for handling law enforcement cases once an arrest and/or confiscation has been made, however only some PPNS participate in wildlife crime investigations, which is due in part to a lack of focus on this issue.

Lack of a standardised and operational adaptive management system lessens protected area effectiveness - a robust law enforcement response underpins the strategy of any well-managed protected area. This almost always employs national park and/or community ranger teams to conduct field-based patrols that directly tackle on-the-ground threats, such as poaching and illegal logging. Recent significant advances have been made in improving these patrol-based strategies through the development of the SMART standards and analytical software. This can be used to motivate rangers, and to provide timely and critically important information to PA managers on ranger team performance that can be used to plan strategically to enhance patrol effectiveness. Similarly, SMART databases can be used to improve the flow of information collected by forest ranger teams to the senior level technicians for management decision-making.

KSDAE is applying Resort Based Management (RBM) as a principal strategy for improving protected area management effectiveness. It will devolve greater power and responsibility to the smallest field operational units (“resorts”) based within national parks. This typically includes a ranger and a forest technician, who are directly responsible and therefore accountable for a resort. Activities include field monitoring and law enforcement, amongst others. The ability to effectively assess resort performance depends on having a robust reporting and evaluation system between the resort and the regional and national headquarters in place, which in most cases has not yet been established.

Lack of a robust system for monitoring biodiversity and forests to inform resource management - most protected areas in Indonesia lack biodiversity baseline data, beyond species lists for different taxa. Species monitoring data are even scarcer. Biodiversity surveys tend to be conducted using presence/absence techniques to generate species lists, but their usefulness is limited by not accounting for bias and errors. No scientifically robust sampling framework is being systematically implemented in across the PA system to collect and analyse biodiversity data. Outside protected areas the situation is worse and the lack of data means that biodiversity concerns cannot be adequately considered in determining the impacts of threats such as illegal wildlife trade, or in planning processes, such as EIAs.

Baseline analysis

Indonesia was a signatory to the Declaration agreed upon at the London Conference on the Illegal Wildlife Trade in February 2014. The Ministry of Environment and Forestry (MoEF) is the focal agency for wildlife crime via the Directorate of Conservation of Natural Resources and Ecosystem (KSDAE) KSDAE also manages the national protected area system, and has a budget of US$ 148 million, including BKSDA in each province. KSDAE has around 7,908 forest rangers across Indonesia of which about 2,999 are protected area rangers. These are supported by 1,025 forestry civil investigators, including some under the authority of local government, and 11 brigades of SPORC (special ranger investigation units), consisting of 796 personnel. Rangers do not have powers of arrest, so patrolling is not very effective and there is a need for improving coordination with the police and the army. Much of the enforcement effort is directed towards forestry offences.

The Criminal Investigation Division (CID, Bareskrim POLRI) of the Indonesian National Police (INP) is a key agency in combatting nationwide illegal wildlife trade. Unit 1 is specifically tasked with targeting environmental crimes, and has 7 staff and an annual budget of $50,000.  It has played a leading role in the majority of high-profile prosecutions brought successfully in Indonesia over the past 5 years, however is hampered by limited staffing, budgets, capacity and the limited importance attached to wildlife crimes by prosecutors, the judiciary and customs. Other relevant Indonesian Law enforcement agencies include the Attorney General’s Office (AGO), the Ministry of Marine Affairs and Fisheries, Customs, Quarantine, the Corruption Eradication Commission (KPK) and the Financial Trans-projects Analysis and Reporting Centre (PPATK).

The government’s effort has been complemented by investments from bilateral and multilateral agencies, and international NGOs over the past years. Since 2003, the Wildlife Conservation Society (WCS) has pioneered an innovative approach to working with law enforcement agencies across local, regional and national scales to combat illegal wildlife trade in Indonesia, called the “Wildlife Crimes Unit” (WCU). The WCU has supported the Indonesian government to conduct more than 350 arrests in Sumatra, Java, Kalimantan, Sulawesi, Bali, Nusa Tenggara, and Papua. To date, the WCU consists of 6 units to protect both terrestrial and marine protected species. More than 400 wildlife traffickers have been arrested (with a successful prosecution rate of >90%), and thousands of protected animals and tones of animal parts have been seized from sting operations. This is unparalleled in the Asian context, and the WCU is the most successful example of an approach to combat illegal wildlife crime in the region. WCS currently invests c.$250,000/year in work on illegal wildlife trade in Indonesia, including projects on combating trade of sharks and rays, and strengthening institutional frameworks to combat wildlife trafficking in Indonesia.

Progress in 2015 on strengthening the legal and institutional frameworks for combating the illegal wildlife trade supported by WCS has included a rapid assessment of current knowledge, trends and priority actions for wildlife crime, and a detailed analysis of the policy and legal context with support from USAID, with subsequent support to MoEF to implement report recommendations for legal revisions to improve species protection. This has included significant achievements – government agreement to revise the Conservation Law 5/1990 during 2016, MoEF agreement that the revised Law should always reflect the current and existing CITES list, and progress towards updating the Protected Species List by January 2016. In addition, trainings were conducted for MoEF, the police, customs, and the Financial Transactions Analysis and Reporting Centre (PPATK) to build capacity for handling wildlife crime. These included training of 35 police officials from around the country to detect wildlife crime; training of 50 staff from law enforcement agencies and journalists in use of forensics for species identification, with TRACE Wildlife Forensics Network and the Eijkman Institute; and training for 15 PPATK staff.

Indonesian law enforcement agencies also carried out at least 26 arrests involving 37 perpetrators during 2015 with the assistance of the WCU, with cases including 5 tons of pangolins from Medan; over 1 ton of manta ray bone and gill plates, 6 tiger cases, 2 ivory cases, over 500kg of oceanic whitetip shark fins, and the conviction of an orang-utan trader. Such cases have been publicised in the Indonesian media through collaboration with the Alliance of Independent Journalists and Indonesian Journalists Association.

Marine wildlife protection has progressed, with four convictions of traders in manta ray parts reflecting the tough new stance of the MMAF to protect these species, and the WCU and MMAF handled a total of 9 manta and shark test cases in total between November 2014 and October 2015. WCS also worked with MMAF, MoEF, LIPI and other institutions towards preparing a legal framework for shark and ray protection through the development of  National Plans of Action for sharks and rays (NPOA 2015-2019) and for manta rays (NPOA 2016-2020) and associated revision of the Conservation Act 5/1990 and updating of the annex of GR7/1999 to include enhanced protection for shark and ray species in line with CITES through the Protected Species List, with the final updated list expected to be issued through Ministerial Decree at the end of 2015. Training has been conducted for management and enforcement agencies (including MMAF, Customs and PPATK) regarding CITES-listed shark and ray species, relevant legislation for prosecution for related trafficking offences, and identification of species. Training also included 50 provincial and district staff of MMAF’s Technical Implementation Unit of Aquatic Species and Area Conservation on WCU approaches and identification of shark and manta products. WCU has also agreed with the Misool Baseftin Foundation (MBF) to conduct joint sea patrols in Lamakera, Nusa Tenggara province, to protect manta rays and whale sharks from hunting, involving police officers from the Directorate of Coast and Sea Guarding Police (POLAIR) and one WCU staff. Two equipped guard posts will be established in Lamakera to support the patrols and alternative livelihood program for the local community, especially manta hunters.

At the landscape level, WCS supported Wildlife Response Units (WRUs) in two critical tiger landscapes in Sumatra –Leuser and Bukit Barisan Selatan, which responded to at least 44 human-wildlife conflict cases, 17 involving tigers, with domestic livestock killed in some cases. In responding to such conflicts, the WRUs secure and stabilize the situation, and assist communities to remain safe and to protect their livestock, benefiting both the communities and the tigers.

Under a 2014 MoU between the Government of Indonesia and the United States Government (USG), US Government agencies are providing capacity-building assistance to law enforcement agencies on environmental crimes (including wildlife trafficking) and are facilitating regional dialogues of action to reduce illegal wildlife trade. These are implemented by US Department of Justice (US-DoJ) International Criminal Investigative Training Program (ICITAP), US-DoJ Office of Overseas Prosecutorial Development, Assistance and Training (OPDAT), and the US Agency for International Development (USAID). Regional initiatives include USAID-ARREST (Asia’s Regional Response to Endangered Species Trafficking, 2010-2016); The Association of Southeast Asian Nations’ Wildlife Enforcement Network (ASEAN-WEN); efforts by the International Consortium for Combatting Wildlife Crimes (ICCWC) partners, including the CITES secretariat, Interpol, World Customs Organisation, United Nations Office on Drugs and Crime and the World Bank. In December 2012 Indonesia and Vietnam also signed a MoU on Wildlife Law Enforcement, which is driving bilateral cooperation within the region.

Overall, in the baseline situation described above, there remain regulatory loopholes, lack of coordination between enforcement agencies, a lack of capacity and resources, and a limited ability to upscale successful models (e.g. the Wildlife Crimes Unit) with the consequence that wildlife trade, both illegal and legal, will substantially increase or, at best, will continue unabated, resulting in local declines and the increased likelihood of extinctions of key Indonesian wildlife species, including elephants, tigers and rhinos. Even biodiversity within the PA system is not shielded from poaching to supply the domestic and international illegal wildlife trade. Illegal wildlife trade will continue to operate as organized crime, while legal wildlife trade will remain poorly regulated, raising few revenues for the state, and acting as a cover behind which illegal trade can flourish. Thus, these baseline activities, although significant, fall short of the proposed long-term solution: to conserve key wildlife species in Indonesia, by ensuring that the legal wildlife trade is ecologically and economically sustainable, while reducing the scale and impact of illegal wildlife trafficking, both from Indonesia and in transit through the country.

Annex 14

Baseline report on database:

-See separate files-

Annex 15

Baseline report on policy, legal and regulatory framework:

-See separate files-

Annex 16 a, b and c

Baseline socio-economic assessment:

-See separate file -

Annex 17

-See separate file -

Annex 18

Capacity Assessment Scorecard for the Directorate General of Law Enforcement for Environment and Forests, Ministry of Environment and Forestry:

Project/Programme Name: Combatting illegal and unsustainable trade in endangered species in Indonesia

UNDP-GEF PIMS ID number: 5391

Project/Programme Cycle Phase: PPG.

Date: 1 November 2016

UNDP Capacity Development Scorecard

Summary Results of the UNDP Capacity Development Scorecard for Institutions responsible for combating poaching and IWT

| Strategic Areas of Support | Systemic |  |  |  | Institutional |  |  | Individual |  |  | Average % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Project Scores | Total possible score |  | % achieved | Project Scores | Total possible score | % achieved | Project Scores | Total possible score | % achieved |  |
| (1) Capacity to conceptualize and formulate policies, legislations, strategies and programs | 4 | 6 |  | 67 | 1 | 3 | 33 | - | - |  | 50 |
| (2) Capacity to implement policies, legislation, strategies and programs | 2 | 6 |  | 33 | 16 | 24 | 67 | 4 | 9 | 44 | 48 |
| (3) Capacity to engage and build consensus among all stakeholders | 5 | 6 |  | 83 | 4 | 6 | 67 | 2 | 3 | 67 | 72 |
| (4) Capacity to mobilize information and knowledge | 1 | 3 |  | 33 | 1 | 3 | 33 | 2 | 3 | 67 | 44 |
| (5) Capacity to monitor, evaluate, report and learn | 3 | 3 |  | 100 | 3 | 6 | 50 | 1 | 3 | 33 | 61 |
| TOTAL Score and average for %'s | 15 | 24 |  | 62.5 | 25 | 42 | 60 | 9 | 18 | 50 | 57 |
| Total Answered Questions: 28 |  |  |
| Total Score: 49 (Total Possible Score: 84) |  |  |

Detailed Results from the Capacity Development Scorecard

| Strategic Area of Support | Target for CD | Outcomes | Outcome Indicators (Scorecard) | Initial Evaluation | Evaluative Comments |
| --- | --- | --- | --- | --- | --- |
| 1. Capacity to conceptualize and formulate policies, legislations, strategies and programs |  |  |  |  |  |
| 1. Capacity to conceptualize and formulate policies, legislations, strategies and programs | Systemic | 1.The agenda to combat poaching and IWT is being effectively championed / driven forward | 0 -- There is essentially no agenda on combating poaching and IWT; 1 -- There are some persons or institutions actively pursuing anti-poaching agenda but they have little effect or influence; 2 -- There are a number of persons and institutions that drive the anti-poaching agenda, but more is needed; 3 -- There are an adequate number of able "champions" and "leaders" effectively driving forwards anti-poaching and IWT agenda | 2 | There are number of institutions that drive the anti-poaching agenda but it still need to be improved e.g. develop Strategies and action plan for combatting illegal wild life activities (illegal trading, trafficking and poaching) as basic reference for all stakeholders. The institutions in charge include: - Law enforcement agencies: DG Law Enforcement MoEF - NPs and Regional Conservation Regional Office – DG KSDAE - Protection and Law Enforcement Regional Office (Balai Pengamanan dan Penegakan Hukum) MoEF (TIUs, in 5 regional offices) - Directorate Tipiter, Bareskrim - POLRI - Local and international NGOs Recommendation Action by project - Identify potential leaders and champions and support more leaders specifically for anti-poaching and wildlife trafficking - Conduct campaign, socialization and public awareness for the targeted communities. The activities involve national as well as local leaders, other proposed activities such as counter-IWT and poaching day, or other activities |
|  | Systemic | 2.There is a strong and clear legal mandate for combating poaching and IWT | 0 -- There is no legal framework to support efforts aimed at combating poaching and IWT; 1 -- There is a partial legal framework supporting efforts aimed at combating poaching and IWT, but it has many inadequacies; 2 – There is a reasonable legal framework supporting efforts aimed at combating poaching and IWT but it has a few weaknesses and gaps; 3 -- There is a strong and clear legal mandate supporting efforts aimed at combating poaching and IWT; | 2 | Sub Directorate of Investigation of Illegal Logging and Illegal Activities on Wildlife, Directorate of Criminal Law Enforcement (Direktorat Penegakan Hukum Pidana) - MoEF and 5 Technical Implementation Units (TIUs) in each region have clear and legal mandate for combating poaching and IWT. The operational working procedure or working arrangement still needs to be improved to ensure similar understanding and perceptions on tackling various IWT-related issues between central and local institutions, as well within internal MoEF (i.e between DG Law Enforcement and DG KSDAE). Having an internally well-coordinated working arrangement is important to accomplish better communication with other relevant institutions. As an example, conservation within forest areas is prioritizing more on prevention-related measures; meanwhile illegal activities on wildlife become responsibility of each management authority. At the moment, Ministerial Regulation on Working Arrangement is under development, coordinated by Sekditjen DG Law Enforcement and involving relevant stakeholders. It is also recommended to accelerate revision of Ministerial Regulation 18/2015. Recommendations for the project - Campaign and awareness - Targeted community empowerment - Assessing the root cause of the illegal activities on wildlife (e.g. assessing whether the trade was caused/triggered by any others activities or whether the poaching was caused by subsistence need or others, to design most efficient intervention actions. |
|  | Institutional | 3. Institutions responsible for combating poaching and IWT are able to strategize and plan | 0 -- Institutions responsible for combating poaching and IWT have no plans or strategies; 1 -- Institutions responsible for combating poaching have strategies and plans, but these are old and no longer up to date or were prepared in a totally top-down fashion; 2 -- Institutions responsible for combating poaching and IWT have some sort of mechanism to update their strategies and plans, but this is irregular or is done in a largely top-down fashion without proper consultation; 3 – Institutions responsible for combating poaching and IWT have strategies and plans which are relevant, prepared in a participatory manner and regularly updated | 1 | Regulations related to combating poaching and IWT as working framework are UU 5/90, UU 41/1999, PP 7/1999, PP.8/1999, Permen 447/2003. All of these provide clear and strong legal mandate to combat poaching and IWT. To implement these regulations, the above regulations are further translated into a mid-term (5 years) Strategic Planning and short-term planning (Annual Work Plan/ RKT) of MoEF. More specifically: Renstra MoEF, Renstra DG Law Enforcement and Renstra Directorate PPH. The short term planning (RKT) is evaluated annually to adjust the target output. Some policies are developed by using top down fashion, especially for those which have global influence, even though the detail needs to be broken down involving adaptive public consultation in each location (TIUs). The top down policies sometimes are not applicable/relevant when being used to solve problems in the field. For example, with regard to resource allocation to national parks (NP), which was not done based on specific need and situation (i.e related to threat and the extent of each NP) in each location. For example Komodo NP which has more threats on rusa deer poaching and illegal fishing has similar amount of resource allocation with Kelimutu NP which relatively under a very low threat situation. Recommendation Action by project It is expected that this project could produce a Strategic and Action Plan for combating illegal activities on wildlife. The action plan will be become reference for of the institutions working on combating IWT. These should be developed by involving relevant stakeholders based on inputs and by using most accurate data from the field. It also needs to be in line with Species Strategic and Action Plans under DG KSDAE. |
| 2. Capacity to implement policies, legislation, strategies and programs |  |  |  |  |  |
| 2. Capacity to implement policies, legislation, strategies and programs | Systemic | 4.There are adequate skills for combating poaching and IWT | 0 -- There is a general lack of skills for combating poaching and IWT; 1-- Some skills exist but in largely insufficient quantities to guarantee effective anti-poaching and prevention of IWT; 2 -- Necessary skills for effective anti-poaching and prevention of IWT do exist but are stretched and not easily available; 3 -- Adequate quantities of the full range of skills necessary for effective anti-poaching and prevention of IWT are easily available | 1 | Insufficient skills and quantity to guarantee effective anti-poaching and prevention of IWT, such as: - Skills need to be improved such as: species identification, wildlife forensics, intelligence and investigations, handling wildlife injured by conflicts, etc. - To achieve optimal staff performance, they also need to be sufficiently-equipped (including: binoculars, cameras, CCTV, camera-traps, weapons, and anesthesia guns, transfer cages, temporary cages, boats, speed boats, etc. - Identify relevant partners to develop network for increasing staff capacity, as well engaging other institutions which have expertise in support combating poaching and IWT. - In addition, techniques and method for preventive activities also need to be updated and adjusted to local needs. |
|  | Systemic | 5.There is a fully transparent oversight authority for the institutions responsible for combating poaching and IWT | 0 -- There is no oversight at all of institutions responsible for combating poaching and IWT; 1 -- There is some oversight, but only indirectly and in a non-transparent manner; 2 -- There is a reasonable oversight mechanism in place providing for regular review but lacks in transparency (e.g. is not independent, or is internalized) ; 3 -- There is a fully transparent oversight authority responsible for combating poaching and IWT | 1 | Independent and transparent oversight mechanism is regularly undertaken by high-level authority, such as Presidential Chief Staff (Kepala Staff Kepresidenan/ KSP), National Planning Agency (Bappenas), BPK and BPKP, as well Inspectorate for internal oversight – however, none of these oversight methods are specifically addressing/evaluating issues related to combating poaching and IWT. It is important to note that combating poaching and IWT is not a key performance indicator (KPI) for Gakkum MoEF. Instead, reducing poaching and IWT are the subsequent impact once the KPI of Gakkum are achieved (i.e. KPI of DG Law Enforcement are: forest area which can be maintained from any forest disturbance increase annually, and existence of management support). |
|  | Institutional | 6.Institutions responsible for combating poaching and IWT are effectively led | 0 – Institutions responsible for combating poaching and IWT have a total lack of leadership; 1 -- Institutions responsible for combating poaching and IWT exist but leadership is weak and provides little guidance; 2 -- Institutions responsible for combating poaching and IWT have reasonably strong leadership but there is still need for improvement; 3 -- Institutions responsible for combating poaching and IWT are effectively led | 2 | Institutions responsible for combating poaching and IWT are in place already, but there is still a need for improvement to achieve effective work such as strong leadership in each institution to combat poaching and IWT. More effort and support is needed to put poaching and IWT as national priority issue. Data need to be updated and integrated in a strong system to justify the importance of this issue. In addition, clear guidelines and working procedures, as well as intensive coordination and communications between institutions are also needed to achieve effective leadership on combating poaching and IWT. |
|  | Institutional | 7.Human resources are well qualified and motivated | 0 -- Human resources are poorly qualified and unmotivated; 1 -- Human resources qualification is spotty, with some well qualified, but many only poorly and in general unmotivated; 2 -- HR in general reasonably qualified, but many lack in motivation, or those that are motivated are not sufficiently qualified; 3 -- Human resources are well qualified and motivated. | 2 | In general, human resources are reasonably qualified, but still lack motivation, or those that are motivated are not sufficiently qualified. The motivation for increased qualifications and working performance of the staff could be done through incentive and dis-incentive mechanisms Another challenge is the limited number of existing Polhut and PPNS partly due to administrative functional problems. Note The number of functional forest rangers (Polhut) which are handling forest crime including poaching and IWT is 3,175 individuals (registered as central government staff and posted in both central office and TIUs DG KSDAE offices). Meanwhile 5,113 Polhut are registered as Provincial and District Forestry Agency staff. Central government Polhut comprises: 842 personnel of Forest Ranger Quick Response Unit (SPORC), and 1,426 personnel of PPNS. SPORC already exists in 11 provinces identified as having high forest crime occurrence - including poaching and IWT activities. |
|  | Institutional | 8.Plans are implemented in a timely manner effectively achieving their objectives | 0 -- There is very little implementation of plans; 1 -- Plans are poorly implemented and their objectives are rarely met; 2 -- Plans are usually implemented in a timely manner, though delays typically occur and some objectives are not met; 3 -- Plans are implemented in a timely manner effectively achieving their objectives | 2 | Plans are usually implemented in a timely manner, though delays typically occur and some objectives are not met, for example due to national policy on budget cutting/reduction – consequently the achievement of targeted output will be affected. |
|  | Institutional | 9. Institutions for combating poaching and IWT are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 0 -- Institutions responsible for combating poaching and IWT typically are severely underfunded and have no capacity to mobilize sufficient resources; 1 -- Institutions responsible for combating poaching and IWT have some funding and are able to mobilize some human and material resources but not enough to effectively implement their mandate; 2 -- Institutions responsible for combating poaching and IWT have reasonable capacity to mobilize funding or other resources but not always in sufficient quantities for fully effective implementation of their mandate; 3 -- Institutions responsible for combating poaching and IWT are able to adequately mobilize sufficient quantity of funding, human and material resources to effectively implement their mandate | 1 | Gakkum (MoEF) which is responsible for combating poaching and IWT has only limited funding to mobilize some human and material resources for efficient measures in tackling poaching and IWT Recommendation by this Project - Need more personnel involving local community such as TPHL non PNS and MMP. - 1 forest ranger at the moment is responsible to cover working area as large as 14,521 ha (reference data mentioned that 1forest ranger should effectively cover about 1:5,000 ha). Assessment to indicate effective working area coverage for Indonesia case is therefore necessary to plan for future actions. |
|  | Institutional | 10.Institutions for combating poaching and IWT are effectively managed, efficiently deploying their human, financial and other resources to the best effect | 0 -- Institution for combating poaching and IWT exists but it has no management; 1 -- Institutional management is largely ineffective and does not deploy efficiently the resources at its disposal; 2 -- The institution is reasonably managed, but not always in a fully effective manner and at times does not deploy its resources in the most efficient way; 3 -- The institution for combating poaching and IWT is effectively managed, efficiently deploying its human, financial and other resources to the best effect | 2 | The institution is reasonably managed, but not always in a fully effective manner and at times does not deploy its resources in the most efficient way. Distribution of resources for each region should be adjusted based on their threats and size of area; thus redistribution and reallocation of resources is needed to create the most efficient result. Recommended actions by project: Mapping illegal wildlife trade, hunting, trafficking in each regions in Sumatera, Kalimantan, Sulawesi and Papua. |
|  | Institutional | 11.Institutions for combating poaching and IWT are highly transparent, fully audited, and publicly accountable | 0 – Institutions for combating poaching and IWT are totally non-transparent, not being held accountable and not audited; 1 – Institutions for combating poaching and IWT are not transparent but are occasionally audited without being held publicly accountable; 2 -- Institutions for combating poaching and IWT are regularly audited and there is a fair degree of public accountability but the system is not fully transparent; 3 -- The Institutions for combating poaching and IWT are highly transparent, fully audited, and publicly accountable | 3 | Accountability mechanisms for Gakkum as well other institutions within MoEF are in place (i.e regular audit by BPK, BPKP, and Inspectorate). However, combating poaching and IWT are not specifically mentioned as KPIs for performance audit of Gakkum. Note: transparency is dynamic, so it always has scope to be improved. |
|  | Institutional | 12.There are legally designated institutions for combating poaching and IWT with the authority to carry out their mandate | 0 -- There is no lead institution or agency with a clear mandate or responsibility for combating poaching and IWT; 1 -- There are one or more institutions or agencies dealing with anti-poaching and IWT but roles and responsibilities are unclear and there are gaps and overlaps in the arrangements; 2 -- There are one or more institutions or agencies dealing with anti-poaching and IWT, the responsibilities of each are fairly clearly defined, but there are still some gaps and overlaps; 3 -- Institutions for combating poaching and IWT have clear legal and institutional mandates and the necessary authority to carry out this out | 2 | Clear and legal mandate has been given to responsible institutions for combating poaching and IWT. This includes: Police, Quarantine, Customs, Airport and Seaport authority. However, better coordination and communications between these institutions is inevitably required during implementation to put the mandate into practice. |
|  | Institutional | 13.Anti-poaching and IWT prevention are effectively carried out | 0 -- No enforcement of regulations is taking place; 1 -- Some enforcement of regulations but largely ineffective and external threats remain active; 2 -- Regulations are regularly enforced but are not fully effective and external threats are reduced but not eliminated; 3 -- Regulations are highly effectively enforced and all external threats are negated | 2 | Prevention of poaching and IWT need to be improved as poachers and illegal traders of wildlife will always find gaps to trade and or smuggle. Economic demand mostly drives IWT activities. To be able to get the interest of relevant key stakeholders, available data in Gakkum need to be updated. By doing so, the information on poaching and IWT have strong advocacy and have national priority to allow buy-in and implementation within institutions. Furthermore, synchronization of data with relevant NGOs needs to be followed up to build better communication to achieve the goals. Prevention activities need to be conducted effectively in protecting the areas to reduce IWT. On the other hand, revision on regulations such as Permen 447/2003 and acceleration on revision of law UU 5/1990 are also necessary. |
|  | Individual | 14.Individuals are able to advance and develop professionally | 0 -- No career tracks are developed and no training opportunities are provided; 1 -- Career tracks are weak and training possibilities are few and not managed transparently; 2 -- Clear career tracks developed and training available; HR management however has inadequate performance measurement system; 3 -- Individuals are able to advance and develop professionally | 1 | Career track for Forest Rangers as functional staff is reasonably clear, though it still need to be improved; one of them is related to increasing staff capacity through trainings. Due to limited resources, trainings can only be provided for limited numbers of personnel (quota-based) and sometime the criteria of selection staff to join the training are not clear and transparent. |
|  | Individual | 15.Individuals are appropriately skilled for their jobs | 0 -- Skills of individuals do not match job requirements; 1 -- Individuals have some or poor skills for their jobs; 2 -- Individuals are reasonably skilled but could further improve for optimum match with job requirement; 3 -- Individuals are appropriately skilled for their jobs | 2 | Individuals are reasonably skilled but could further improve their skills to fulfill their job requirement. For example, some of the rangers posted at airport and seaport do not possess sufficient skills needed to identify important species; in other situation lack of intelligence skills, forensic skills, effective communication skills have been also identified. Recommendations to the project: Providing more knowledge materials for species identification, guideline for intelligence techniques, and other resource materials to allow forest rangers and other relevant authorities to learn about the issues independently – considering also the limited resources for training. |
|  | Individual | 16.There are appropriate systems of training, mentoring, and learning in place to maintain a continuous flow of new staff | 0 -- No mechanisms exist; 1 -- Some mechanisms exist but unable to develop enough and unable to provide the full range of skills needed; 2 -- Mechanisms generally exist to develop skilled professionals, but either not enough of them or unable to cover the full range of skills required; 3 -- There are mechanisms for developing adequate numbers of the full range of highly skilled protected area professionals | 1 | Some mechanisms exist but unable to develop enough and unable to provide full range of skills needed. Currently, there is no such mechanism to ensure regeneration or sustainability of the skills, once the trained/skilled staff has to be transferred to other division or province. A mechanism to ensure that all needed skills are available from time to time should be put in place. |
| 3. Capacity to engage and build consensus among all stakeholders |  |  |  |  |  |
| 3. Capacity to engage and build consensus among all stakeholders | Systemic | 17.Institutions for combating poaching and IWT have the political commitment they require | 0 -- There is no political will at all, or worse, the prevailing political will runs counter to the interests of institutions; 1 -- Some political will exists, but it is not strong enough to make a difference; 2 -- Reasonable political will exists, but is not always strong enough to fully support institutions; 3 -- There are very high levels of political will to support institutions | 3 | Political commitment to support institutions are already put in place, such as through “multi-door*” approaches. Investigation training has been conducted for State Investigator (PPNS), Police, and Prosecutors in 3 Provinces. However, this multi door approach should be further explored and strengthened as there is still a need to improve capacity at technical and field level. *Multi-door approach means the ability to prosecute IWT offenders using a variety of different legislation (eg money-laundering and anti-corruption laws) |
|  | Systemic | 18.Institutions for combating poaching and IWT have the public support they require | 0 -- The public has little interest in institutions responsible for combating poaching and IWT and there is no significant lobby for these institutions; 1 -- There is limited support for institutions responsible for combating poaching and IWT; 2 -- There is general public support for institutions responsible for combating poaching and IWT and there are various lobby groups such as environmental NGO's strongly pushing them; 3 -- There is tremendous public support in the country for institutions responsible for combating poaching and IWT | 2 | General public support for institutions responsible for combating poaching has been facilitated through the establishment and management of website of DG Law Enforcement which provides a channel for public reporting, complaints, press releases, media online information update, etc. In addition to that, various support and lobby groups from environmental NGO's exist, which trigger and mobilize volunteer network and wildlife lovers (site-specific and in some areas related to site-specific endangered species. However, all of this existing support still needs to be optimized to increase public support and public trust on activities combatting IWT. Activities involving public support can be improved by whistle blower mechanism, social control, involving community as informants for monitoring poaching and IWT. |
|  | Institutional | 19.Institutions responsible for combating poaching and IWT are mission oriented | 0 -- Institutional mission not defined; 1 -- Institutional mission poorly defined and generally not known and internalized at all levels; 2 -- Institutional mission well defined and internalized but not fully embraced; 3 – Institutional missions are fully internalized and embraced | 2 | Institutional mission has been well defined within Gakkum, even though it is not internalized and fully embraced as it is not mentioned specifically for combating poaching and IWT. Yet combating poaching and IWT are not fully bought-in as a priority mission for all institutions which can actually support measures to counter these illegal activities. |
|  | Institutional | 20.Institutions responsible for combating poaching and IWT can establish the partnerships needed to achieve their objectives | 0 -- Institutions responsible for combating poaching and IWT operate in isolation; 1 -- Some partnerships in place but significant gaps and existing partnerships achieve little; 2 -- Many partnerships in place with a wide range of agencies, NGOs etc., but there are some gaps, partnerships are not always effective and do not always enable efficient achievement of objectives; 3 -- Institutions responsible for combating poaching and IWT establish effective partnerships with other agencies and institutions, including national and local governments, NGO's and the private sector to enable achievement of objectives in an efficient and effective manner | 2 | Partnerships with a wide range of agencies, NGOs etc. need to be improved especially in establishing effective communications to develop more trust and partnerships. The agreed strategic and action plans should be used as reference for sharing work and responsibility, and this should be evaluated together regularly and transparently for more efficient achievement of the objectives. |
|  | Individual | 21.Individuals carry appropriate values, integrity and attitudes | 0 -- Individuals carry negative attitude; 1 -- Some individuals have notion of appropriate attitudes and display integrity, but most don't; 2 -- Many individuals carry appropriate values and integrity, but not all; 3 -- Individuals carry appropriate values, integrity and attitudes | 2 | In general, individuals carry appropriate values, integrity and attitudes, but it still need to be improved. The leadership is important in each institution to maintain and increase appropriate values, integrity and attitudes for individuals. |
| 4. Capacity to mobilize information and knowledge |  |  |  |  |  |
| 4. Capacity to mobilize information and knowledge | Systemic | 22.Institutions responsible for combating poaching and IWT have the information they need to develop and monitor strategies and action plans for the management of (IWT) | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality, is of limited usefulness, or is very difficult to access; 2 -- Much information is easily available and mostly of good quality, but there remain some gaps in quality, coverage and availability; 3 -- Institutions responsible for combating poaching and IWT have the information they need to develop and monitor strategies and action plans for the management of the protected area system | 1 | Some information exists, but it is of poor quality, and of limited usefulness, or is very difficult to access. Need to develop updated and integrated database system. In addition, need to build more coordination, intensive communication, also develop more trust with relevant partners which these related with data property rights, the accuracy and avoiding mis-use of data. |
|  | Institutional | 23.Institutions responsible for combating poaching and IWT have the information needed to do their work | 0 -- Information is virtually lacking; 1 -- Some information exists, but is of poor quality and of limited usefulness and difficult to access; 2 -- Much information is readily available, mostly of good quality, but there remain some gaps both in quality and quantity; 3 -- Adequate quantities of high quality up to date information for institutions responsible for combating poaching and IWT to carry out planning, management and monitoring is widely and easily available | 1 | In order to combat poaching, trafficking, and IWT, the available information that exists needs to be improved in terms of quality, accuracy and accessibility. As data and information available now are still not enough to convince the key stakeholders on the importance of law enforcement for combating poaching and IWT. The DG need to strengthen its coordination and communication with relevant partners and institutions in order to be able to pool strategic data and to develop database system. This system is important to provide a quick response and better planning, as well as strong support from the key stakeholders to support effort in combatting poaching and IWT as serious crime. |
|  | Individual | 24.Individuals working with institutions responsible for combating poaching and IWT work effectively together as a team | 0 -- Individuals work in isolation and don't interact; 1 -- Individuals interact in limited way and sometimes in teams but this is rarely effective and functional; 2 -- Individuals interact regularly and form teams, but this is not always fully effective or functional; 3 -- Individuals interact effectively and form functional teams | 2 | Individuals have interacted regularly and form teams, such as through routine patrols, joint operations or special operations involving TNI/POLRI, or immigration personnel, prosecutors, or Pol PP, depending on situational needs. The guidelines for patrolling protection forest areas is already available: Guideline Book, Dir PPH 20013 and for operation team is Ministerial Regulation 75/2014. However, they are not always fully effective or functional, as mostly it works on project basis and very much depend on budget availability. Therefore, it is important to increase the motivation of all individuals to work effectively together as a team. Some constraints include: the absence of internal working procedure/arrangement at MoEF, lack of guideline for combating poaching and IWT as reference for institutions, updated and accurate database system as baseline for the team actions – all of which have contributed to individuals being not always able to work in fully effective or functional manner. In addition, fair and transparent incentive and dis-incentive schemes for individual and team work achievement need to be improved to encourage more efficient performance. |
| 5. Capacity to monitor, evaluate, report and learn |  |  |  |  |  |
| 5. Capacity to monitor, evaluate, report and learn | Systemic | 25.Policies for institutions responsible for combating poaching and IWT are continually reviewed and updated | 0 -- There is no policy or it is old and not reviewed regularly; 1 -- Policy is only reviewed at irregular intervals; 2 -- Policy is reviewed at least every 5 years; 3 -- Institutional policy for combating poaching and IWT is reviewed at least every 3 years | - | Not applicable – not yet happening. The DG has been established for less than one year (before it was a directorate under DG of Natural Resources and Ecosystem Conservation). However, it is planned that the DG will review policies for institutions responsible for combating poaching and IWT in every 5 years or depending on situations if needed. |
|  | Systemic | 26.Society monitors the state of institutions responsible for combating poaching and IWT | 0 -- There is no dialogue at all; 1 -- There is some dialogue going on, but not in the wider public and restricted to specialized circles; 2 -- There is a reasonably open public dialogue going on but certain issues remain taboo; 3 -- There is an open and transparent public dialogue about the state of the institutions responsible for combating poaching and IWT | 3 | For public accountability, a reasonably open public dialogue is going on and there is no taboo issue that has been hidden from the public. For example, to update activities on combating poaching and IWT, regular press releases related to operations on IWT have been conducted at least once a month, updating “law enforcement-related” application which providing update news, information, tips, complaint, etc. In addition, various news on IWT-related issues are also published through online media electronic such as www.detik.com, and other local media to advocate for IWT issues and increase awareness. |
|  | Institutional | 27.Institutions are highly adaptive, responding effectively and immediately to change | 0 -- Institutions resist change; 1 -- Institutions do change but only very slowly; 2 -- Institutions tend to adapt in response to change but not always very effectively or with some delay; 3 -- Institutions are highly adaptive, responding effectively and immediately to change | 2 | The institution has some flexibility to adapt annual planning (short term) in order to respond to current issues, even though implementation will depend on available resources, and other urgent as well as priority activities (e.g. pangolin smuggling case). Meanwhile changing a Strategic Plan (mid-term planning) is not an easy process, as the DG and Directorates performance indicator (IKU) has already been locked and registered nationally. The key performance indicator of the DG has been approved as criteria for institution’s performance evaluation by the National Planning Agency (Bappenas). |
|  | Institutional | 28.Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 0 -- There are no mechanisms for monitoring, evaluation, reporting or learning; 1 -- There are some mechanisms for monitoring, evaluation, reporting and learning but they are limited and weak; 2 -- Reasonable mechanisms for monitoring, evaluation, reporting and learning are in place but are not as strong or comprehensive as they could be; 3 -- Institutions have effective internal mechanisms for monitoring, evaluation, reporting and learning | 1 | The institution has internal mechanisms for monitoring, evaluation, reporting and learning. Gakkum has a Section of Evaluation and Reporting under Secretariat of DG. Each directorate within this DG also has division with a function to coordinate internal evaluation program and achievement of the respective Directorate annually. However, the learning part still requires a lot of improvement in order to follow up the reporting part. The result of the evaluation has not always been used as a key reference for the next planning stage. |
|  | Individual | 29.Individuals are adaptive and continue to learn | 0 -- There is no measurement of performance or adaptive feedback; 1 -- Performance is irregularly and poorly measured and there is little use of feedback; 2 -- There is significant measurement of performance and some feedback but this is not as thorough or comprehensive as it might be; 3 -- Performance is effectively measured and adaptive feedback utilized | 1 | Guidance to monitor the performance of Forest Rangers is available through Ministerial Regulation No 54/2015. The criteria to measure individual performance is deemed clear, however the monitoring result has not always been used as a basis for giving feedback to the respective individuals. |
| Total Score: (for 28 answered questions – 1 question is not applicable) |  |  |  | 49 |  |

Annex 19

Stakeholder Engagement Strategy:

During the PPG process, a stakeholder analysis was undertaken to identify key stakeholders, assess their interests in the project and define their roles and responsibilities in its implementation. Overall, support for the project and involvement in it was secured from a diverse group of stakeholders, whose roles are summarised in Table 2 (main project document).

The roles of key stakeholders in project management and implementation are also provided in the Governance and Management Arrangements section of the Project Document (ie Project Board members, Technical Advisory Group members, responsible parties, project management office and project implementation units), so it is not repeated here.

In addition, the Multi Year Workplan in Annex 1 also lists the lead responsibility and supporting partners for all proposed activities. This annex provides strategic guidance on the mechanisms for stakeholder engagement during project implementation, and it is proposed that a full Stakeholder Engagement Plan should be prepared during project inception.

Stakeholder Engagement for Implementation of the Project Components

Component 1 of the project will involve an extensive process of stakeholder engagement in the review and adoption of revised policies, regulations and procedures targeted by the project in line with national policy-making and legislative procedures. The MoEF and LIPI, with technical support from WCS, are building upon the findings of the PPG baseline assessment report (see Annex 15) through updating and amending PP7/1999 and UU5/1990, which includes, for example, stiffer fines and penalties for wildlife crimes. The GEF project has been designed to fully complement these ongoing efforts by facilitating ongoing dialogue through focus group discussions (FGDs) and workshops, engaging with parliament, and supporting subsequent revisions to policy drafts until they reach completion. For other policies and regulations, the project will conduct timely and high-quality research that identify gaps, weakness, needs and makes feasible recommendations for revisions of other policies, which are presented in academic policy papers and disseminated and discussed through FGDs and workshops. It is envisioned that this will be achieved through creating expert working groups (POKJA) that partner with key government institutions that discussing and then call for the issuance of a new Ministerial Decrees or other policy reforms, with appropriate technical support provided thereafter.

To improve intersectoral coordination at the national level, project will support the conceptualization, development and operation of an inter-agency National Wildlife Crime Taskforce. This will first involve a review of the organizational options for improving coordination across the range of national agencies involved in fighting wildlife crime, including MoEF (particularly Gakkum), MMAF, Police, Attorney General, Customs, PPATK and KPK.

The project will establish a system for storing and sharing information on illegal and legal wildlife trade volumes, revenues and enforcement actions, including operationalisation of transnational intelligence and information exchange systems with international partners, as needed. To achieve this it will facilitate the development of inter-agency IWT agreements for database and information sharing, and conduct workshops on data collection, management, sharing, procedures etc for key national stakeholders, especially INP, NCB Interpol, Customs, Quarantine, Military, MMAF, WCS. To tackle online IWT, the INP’s Cybercrime Division, the WCU and social networking companies, such as Facebook, whose networking platforms are being used by online wildlife traders have begun working together.

Component 2 primarily aims to improve the capacities of the Implementing Partner (DG Law Enforcement (or Gakkum) and related agencies for collaborative response to tacking IWT. This aims to build on the Wildlife Crime Unit, established by the WCS Indonesia Program in 2003, as part of an innovative partnership designed to combat illegal wildlife trade in Indonesia. The partner base is both strong and diverse including MoEF, MMAF, INP, Attorney General, Customs and excise; anti-corruption agencies (PPTAK); civil society and media organisations. Over 290 cases have been prosecuted by law enforcement agencies based upon information from the WCU, including the 10 largest wildlife crime cases in Indonesia, with a success rate of >85%. This is unparalleled in the Southeast Asian context, and the WCU is the most successful example of an approach to combat illegal wildlife crime in the region. In this project, WCS will provide technical assistance to Gakkum and scale-up lessons learned from 10 years of operating the WCU, to address the systemic institutional and capacity barriers that limit effective national-level action on illegal wildlife trade in Indonesia and the region. This will include i) strengthening Gakkum’s capacity at the national level, including the ongoing development of i2 criminal network mapping and analyses, tackling online trade, and developing high-quality briefing papers; and ii) enhancing regional collaborations between Government of Indonesia law enforcement agencies and other Southeast Asian nations (especially Vietnam, a prime destination for Indonesia’s wildlife) and international bodies (such as INTERPOL). This is intended to serve as a model for inter-agency and south-south collaboration to combat illegal wildlife trade.

The project will support the WCU to expand its national partner base to include the Eijkman Institute and TRACE Wildlife Forensics Network to support the Indonesian law enforcement agencies in forensic techniques.

Secondly, the project will significantly invest in capacity building of various government institutions to raise awareness of illegal wildlife trade as a serious crime, Indonesian law pertaining to this, the respective institutional mandates for tackling the trade and, ultimately, strengthen the government’s ability to achieve successful detections, arrests, prosecutions and deterrent sanctions. A training syllabus consisting of a set of thematic modules, tailored to each institution, will be developed. Incentive mechanisms, such as accreditation for career points, for increasing the motivation of field staff will be included. The formal adoption of the training syllabus will enable it to be included in annual work plans that are sustainably financed by government. Expert training will be supported by WCS, for which there are past successes with the police, MoEF, Attorney General and others. After this, a Training of Trainers course will be run for government institutions own trainers, who will then go on to run future training courses. Agencies involved will include: AGO, Supreme Court, Indonesian National Police, Aviation Security/Ports authority, customs, quarantine, MMAF, WCS.

Thirdly, the project will provide technical assistance to support the GoI in participating in international agreements/initiatives related to IWT (international meetings - e.g. CITES, INTERPOL, ASEAN-WEN) and to establish and implement agreements for strengthened bilateral collaboration (Indonesia-China, Indonesia-Vietnam and Indonesia-US). This will be supported by the INP and WCS.

In Component 3, Capacity development will be supported at five demonstration ports including training of key agency staff on CITES and IWT control and introduction of upgraded port handling system at Surabaya port. Under this component, the project will work closely with the UNDP/GEF Ports of Excellence project (under the GEF Global Wildlife Programme), on application of the PortMATE assessment tool at all 5 ports, and in collaborative work at Surabaya port to demonstrate more intensive capacity development for IWT detection and enforcement, with support from UNODC, UNDP and other partners. The key agencies involved in combatting illegal wildlife trafficking at ports are customs, immigration, quarantine, BKSDA and Gakkum, plus NGO partners (WCS, Traffic, ProFauna, etc).

For the demonstration sub-regions (Sumatra and Sulawesi), WCS-WCU technical assistance to Gakkum will continue to enable the operationalization of Gakkum and target ports. This will include: i) institutionalization of inter-agency joint action at the site level; ii) establishment and operation of informant networks in forested landscapes and major trade centres gathering evidence for government to prosecute crimes; iii) collaborating with local enforcement agencies, building the understanding of prosecutors and judges to ensure that cases are fully and fairly administered; and, iv) working with media to keep the judicial proceedings transparent.  The project will provide TA on law enforcement training such as SMART-RBM patrolling for resort management staff in Leuser and Bogani-Nani Wartabone National Parks and adjoining areas within the demo regions. It will also pilot the operation of a provincial /regional level IWT Task Force (or similar mechanism) to facilitate inter-agency coordination for each demo region based on series of stakeholder consultations to detail wildlife trade chains, key species involved, key actors etc.  A workshop will be organised to discuss the feasibility, efficiency and usefulness of a subnational taskforce, as well as raising awareness over illegal wildlife trade and identifying capacity building needs. Workshop participants will include MoEF, INP, Customs and Excise, prosecutors, judges etc.

The project will also support the development of staff incentive mechanisms for partnering institutions (in particular, MoEF, INP and Customs and Excise) to improve staff performance and national/site-level institutional performance. Incentive mechanisms, such as accreditation or career points, for increasing the motivation of field staff will be considered.

The project’s activities will respond to the anticipated effects of tackling illegal wildlife trade on women and recognize the gender-differentiated impacts that this may have on men and women and their households. A particular focus of the project gender strategy will be on female empowerment in rural livelihood development options. These activities will focus on communities in identified source areas for IWT within the two demonstration landscapes, supported by awareness programmes. Activities will include the engagement of local NGOs/CSOs to conduct awareness programmes in schools, churches, mosques, and community centres and capacity development for communities; employment of local people as community rangers and informants; identifying opportunities for empowerment of local communities through new partnerships with government agencies; and targeted support for response to HWC issues in priority IWT source areas including crop and livestock protection.

The characteristics and potential roles of key local stakeholders in each of the demonstration regions are described in the Landscape profiles in Annex 11. Further consultations will be conducted in the demonstration regions during project implementation to obtain Free Prior Information Consent for the communities that are identified for targeted interventions according to further analysis of wildlife trade chains including source areas, transportation routes, markets and ports.

In Component 4, Knowledge management will be coordinated with other GEF projects through the GEF Programmatic Framework to Prevent the Extinction of Known Threatened Species, coordinated by the Project Management Unit and UNDP. Monitoring and evaluation will involve sharing of project reports with the global programme’s Steering Committee for information and feedback.

Long-term stakeholder participation

The project will provide the following opportunities for long-term participation of all stakeholders, with a special emphasis on the active participation of women and indigenous and local communities, and enhancement of inter-sectoral coordination for implementation of the activities to combat IWT.

Decision-making – through the establishment of the Project Board. The establishment of the structure will follow a participatory and transparent process involving the confirmation of all key project stakeholders; conducting one-to-one consultations with all stakeholders; development of Terms of Reference and ground-rules; inception meeting to agree on the constitution of the PB.

Capacity building – at systemic, institutional and individual levels – is one of the key strategic interventions of the project and will target all stakeholders that have the potential to be involved in implementation of the project, including demonstration activities at the community level. Women and indigenous / minority groups will be proactively considered for capacity building activities based on specific needs assessments.

Communication - will include the participatory development of an integrated communication strategy. The communication strategy will be based on the following key principles: providing information to all stakeholders; promoting dialogue between stakeholders; and promoting access to information.

The project’s design incorporates several features to ensure on-going and effective stakeholder participation in the project’s implementation. The mechanisms to facilitate involvement and active participation of different stakeholders in project implementation will comprise a number of different components:

  - Project inception workshop

The project will be launched by a multi-stakeholder workshop. This workshop will provide an opportunity to provide all stakeholders with the most updated information on the project, refine and confirm the work plan, and will establish a basis for further consultation as the project’s implementation commences.

  - ii) Constitution of the Project Board

The Project Board’s constituency will be constituted to ensure broad representation of all key interests throughout the project’s implementation. The representation, and broad terms of reference, of the PB are described in the Governance and Management Arrangements section of the Project Document.

  - iii) Establishment of the Project Management Unit

The Project Management Unit will take direct operational responsibility for facilitating stakeholder involvement and ensuring increased local ownership of the project and its results. The PMU will be located in the Gakkum offices in Jakarta to ensure coordination among key stakeholder organizations at the national level during the project period.

  - iv)  Establishment of local working groups

At the activity level, local or specialist working groups (e.g., capacity development team, monitoring and evaluation team, community involvement team) will be established, as required, to facilitate the active participation of affected institutions, organisations and individuals in the implementation of the respective project activities. Different stakeholder groups may take the lead in each of the working groups, depending on their respective mandates. There will be equitable representation of women and ethnic minorities in community level activities such as capacity building, livelihoods and awareness programmes.

v) Project communications

The project will develop, implement and annually update a communications strategy to ensure that all stakeholders are informed on an on-going basis about: the project’s objectives; the project’s activities; overall project progress; and the opportunities for stakeholders’ involvement in various aspects of the project’s implementation.

vi) Implementation arrangements

Demonstration activities in component 3 have specifically been designed to directly involve local stakeholders during implementation, and to ensure that they benefit from the capacity building, awareness raising and final outcomes of these activities. Women and indigenous groups will be proactively considered for participation in these demonstration activities.

Nellemann, C., Henriksen, R., Raxter, P., Ash, N., Mrema, E. (Eds). 2014. The Environmental Crime Crisis – Threats to Sustainable Development from Illegal Exploitation and Trade in Wildlife and Forest Resources. A UNEP Rapid Response Assessment. United Nations Environment Programme and GRID-Arendal, Nairobi and Arendal, www.grida.no.

UNODC. 2013. Transnational Organized Crime in East Asia and the Pacific. A threat assessment. United Nations Office on Drugs and Crime.

Values quoted from various sources in: USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

TRAFFIC. 2008. What’s Driving the Wildlife Trade? A Review of Expert Opinion on Economic and Social Drivers of the Wildlife Trade and Trade Control Efforts in Cambodia, Indonesia, Lao PDR and Vietnam.

EIA. 2011. Enforcement Not Extinction - Zero tolerance on tiger trade. London. UK.

TRAFFIC 2008. Ibid.

World Bank. 2005. Going, going, gone: The illegal trade in wildlife in East and Southeast Asia. Page 23. Washington DC.

TRAFFIC. (n.d.). Wildlife Trade in South-East Asia. Petaling Jaya, Malaysia.

TRAFFIC 2008. Ibid.

TRAFFIC 2008. Ibid.

Rowcliffe, J. M., E. de Merode, and G. Cowlishaw. 2004. Do wildlife laws work? Species protection and the application of a prey choice model to poaching decisions.

Proceedings. Biological sciences / The Royal Society 271:2631–2636.

TRAFFIC. 2008. What’s Driving the Wildlife Trade? A Review of Expert Opinion on Economic and Social Drivers of the Wildlife Trade and Trade Control Efforts in Cambodia, Indonesia, Lao PDR and Vietnam.

Lawson, K., and A. Vines. 2014. Global Impacts of the Illegal Wildlife Trade: The costs of crime, insecurity and institutional erosion.

TRAFFIC 2008. Ibid.

EIA. 2014. In cold blood: Combating organised wildlife crime. London, UK.

WWF International. 2012. Fighting Illicit Wildlife Trafficking. Gland, Switzerland.

USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

Changes for Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. USAID. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Note – the expected trend would be initial increase in seizures/arrests and prosecutions as enforcement is strengthened, followed by an eventual decrease as increased awareness and deterrence take effect. The timeline for this process is unclear, but the latter stages are likely to occur after the end of the project

These initial negotiations are still in progress with Customs Dept

CITES, September 2016. ESTABLISHING AND WORKING WITH RESCUE CENTRES DESIGNATED UNDER CITES. White Paper Prepared by Members of the Species Survival Network (SSN) Animals in Captivity Working Group (AiCWG). Seventeenth meeting of the Conference of the Parties Johannesburg (South Africa), 24 September – 5 October 2016. CoP17 Inf. 74

UNDP, with the support of United for Wildlife Transportation Taskforce members, are partnering on a Ports of Excellence project financed by the Global Environment Facility (GEF). The project is aiming to reduce the maritime trafficking of wildlife through incentivizing best practice at sea ports, strengthening customs and law enforcement capacity, and building port-to-port cooperation.

See for example: WCS 2015. Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  Report to USAID. http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

Changes for Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. USAID. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Baseline, mid-term and end of project levels must be expressed in the same neutral unit of analysis as the corresponding indicator.

Risks must be outlined in the Feasibility section of this project document.

Act on conservation of living resources and their ecosystems

Government Regulation on the Protected Species List

See also GEF Global Wildlife Program Tracking Tool in Annex 4

Note – the expected trend would be initial increase in seizures/arrests and prosecutions as enforcement is strengthened, followed by an eventual decrease as increased awareness and deterrence take effect. The timeline for this process is unclear, but the latter stages are likely to occur after the end of the project

Note – the expected trend would be initial increase in seizures/arrests and prosecutions as enforcement is strengthened, followed by an eventual decrease as increased awareness and deterrence take effect. The timeline for this process is unclear, but the latter stages are likely to occur after the end of the project

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

January 2014: Estimasi Penduduk Menurut Umur Tunggal Dan Jenis Kelamin 2014 Kementerian Kesehatan http://www.depkes.go.id/downloads/Penduduk%20Kab%20Kota%20Umur%20Tunggal%202014.pdf

2010 census

Use bracketed text only when IP is an NGO/IGO

See also GEF Global Wildlife Program Tracking Tool in Annex 4

The budget will vary depending on the number of consultants required (for full size projects should be two consultants); the number of project sites to be visited; and other travel related costs.  Average # total working days per consultant not including travel is between 22-25 working days.

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

Changes For Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. USAID. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Nellemann, C., Henriksen, R., Raxter, P., Ash, N., Mrema, E. (Eds). 2014. The Environmental Crime Crisis – Threats to Sustainable Development from Illegal Exploitation and Trade in Wildlife and Forest Resources. A UNEP Rapid Response Assessment. United Nations Environment Programme and GRID-Arendal, Nairobi and Arendal, www.grida.no.

UNODC. 2013. Transnational Organized Crime in East Asia and the Pacific. A threat assessment. United Nations Office on Drugs and Crime.

CITES. 2013. Status of African elephant populations and levels of illegal killing and the illegal trade in ivory: A report to the African Elephant Summit. December 2013, CITES Secretariat, IUCN / SSC African Elephant Specialist Group, TRAFFIC International.

International Trade Centre (ITC). The Trade in Wildlife: A Framework to Improve Biodiversity and Livelihood Outcomes

Geneva: ITC, 2015. xii, 29 pages (Technical paper). Doc. No.: SC-15-311.E

GEF Program 9071. Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development.

This subsection draws on the USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

IUCN (2014). The IUCN Red List of Threatened Species version 2014.3. Table 5 - Number of threatened

species (Critically Endangered, Endangered and Vulnerable categories only) in each major group of organisms by country. http://www.iucnredlist.org. Accessed November 2015.

Birdlife International. 2003. Saving Asia’s Threatened Birds: A Guide for Government and Civil Society. Birdlife International, Cambridge, UK.

EIA, Seeing ‘red’ – the often hidden colour of wildlife contraband, January 26, 2015, http://eia-international.org/seeing-red-the-oftenhidden-colour-of-wildlife-contraband

Nijman, V., C. R. Shepherd, Mumpuni, and K. L. Sanders. 2012. Over-exploitation and illegal trade of reptiles in Indonesia. Herpetological Journal 22:83–89.

E.g. Lyons, J. A., D. J. D. Natusch, and C. R. Shepherd. 2013. The harvest of freshwater turtles (Chelidae) from Papua, Indonesia, for the international pet trade. Oryx 47:298–302.

SUTARNO, and SETYAWAN, AHMAD DWI and SUYATNA, IWAN (2012) Species diversity of critically endangered pristid sawfishes (Elasmobranchii: Pristidae) of Nusantara waters (Malay Archipelago). BIODIVERSITAS, 13 (4). pp. 161-171. ISSN 1412-033X E-ISSN: 2085-4722

Lack, Mary, and Glenn Sant. World shark catch, production and trade 1990-2003. Department of the Environment and Heritage, 2006.

FAO (2012) World review of fisheries and aquaculture. http://www.fao.org/docrep/016/i2727e/i2727e01.pdf

Dewar, H., P. Mous, M. Domeier, A. Muljadi, J. Pet, and J. Whitty. 2008. Movements and site fidelity of the giant manta ray, Manta birostris, in the Komodo Marine Park, Indonesia. Marine Biology 155:121–133.

WCS, 2015. Analysis of regulatory framework and Institutional Protection of Species and Implementation of CITES in Indonesia. Jakarta, Indonesia.

Changes for Justice Project – Wildlife Trade, Wildlife Crimes and Species Protection in Indonesia: Policy and Legal Context. Prepared by WCS for Chemonics International. USAID.

USAID 2015. Changes for Justice Project. Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context.  http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Naval Officers also have authority to carry out criminal investigations as stipulated by Act No.27/2007.

The official philosophical foundation of the Indonesian state, consisting of five moral principles: 1) belief in  the one and only God (Ketuhanan Yang Maha Esa); 2) just and civilized humanity (Kemanusiaan Yang Adil dan Beradab); 3) the unity of Indonesia (Persatuan Indonesia); 4) democracy led by the wisdom of deliberations among representatives (Kerakyatan Yang Dipimpin oleh Hikmat Kebijaksanaan, Dalam Permusyawaratan dan Perwakilan); and 5) social justice (Keadilan Sosial bagi seluruh Rakyat Indonesia).

This subsection draws on the USAID report Changes For Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Fourth Amendment of Constitution in 2002.

Chapter XA, Article 28H, Paragraph 1).

The two types of laws which may regulate penal sanction are Acts and Regional Regulations (Province/Regency). The maximum penal sanction for a Regional Regulation is 6 months in jail or a 50 million rupiah fine

vide: 3rd Amendment of Indonesia Constitution 1945, Article 24 C Paragraph I and Act No. 24/2003 regarding

Constitutional Court, Article 10, paragraph I letter a.

vide: 3rd Amendment of Indonesia Constitution 1945 ,Article 24 Paragraph 1 and Act No. 14 of 1985 regarding Supreme Court, Article 31.

Changes For Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. USAID. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Rosser, A and Haywood, M. 2002. The IUCN Species Survival Commission Guidance for CITES. IUCN, Gland, Switzerland

The full list can be found at http://www.hukumonline.com/pusatdata/download/fl359/node/250

Changes For Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. USAID. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf

Nellemann, C., Henriksen, R., Raxter, P., Ash, N., Mrema, E. (Eds). 2014. The Environmental Crime Crisis – Threats to Sustainable Development from Illegal Exploitation and Trade in Wildlife and Forest Resources. A UNEP Rapid Response Assessment. United Nations Environment Programme and GRID-Arendal, Nairobi and Arendal, www.grida.no.

UNODC. 2013. Transnational Organized Crime in East Asia and the Pacific. A threat assessment. United Nations Office on Drugs and Crime.

Values quoted from various sources in: USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

TRAFFIC. 2008. What’s Driving the Wildlife Trade? A Review of Expert Opinion on Economic and Social Drivers of the Wildlife Trade and Trade Control Efforts in Cambodia, Indonesia, Lao PDR and Vietnam.

EIA. 2011. Enforcement Not Extinction - Zero tolerance on tiger trade. London. UK.

TRAFFIC 2008. Ibid.

World Bank. 2005. Going, going, gone: The illegal trade in wildlife in East and Southeast Asia. Page 23. Washington DC.

TRAFFIC. (n.d.). Wildlife Trade in South-East Asia. Petaling Jaya, Malaysia.

TRAFFIC 2008. Ibid.

TRAFFIC 2008. Ibid.

Rowcliffe, J. M., E. de Merode, and G. Cowlishaw. 2004. Do wildlife laws work? Species protection and the application of a prey choice model to poaching decisions.

Proceedings. Biological sciences / The Royal Society 271:2631–2636.

TRAFFIC. 2008. What’s Driving the Wildlife Trade? A Review of Expert Opinion on Economic and Social Drivers of the Wildlife Trade and Trade Control Efforts in Cambodia, Indonesia, Lao PDR and Vietnam.

Lawson, K., and A. Vines. 2014. Global Impacts of the Illegal Wildlife Trade: The costs of crime, insecurity and institutional erosion.

TRAFFIC 2008. Ibid.

EIA. 2014. In cold blood: Combating organised wildlife crime. London, UK.

WWF International. 2012. Fighting Illicit Wildlife Trafficking. Gland, Switzerland.

Wilson HB, Meijaard E, Venter O, Ancrenaz M, Possingham HP (2014) Conservation Strategies for Orangutans: Reintroduction versus Habitat Preservation and the Benefits of Sustainably Logged Forest. PLoS ONE 9(7): e102174. doi:10.1371/journal.pone.0102174

Note - the efficacy of increased penalties is strongly disputed by some, although making wildlife crimes punishable by four years or more would allow them to be covered by the UN Convention against Transnational Organised Crime

USAID Report Changes for Justice Project Wildlife Crime In Indonesia: A Rapid Assessment Of The Current Knowledge, Trends And Priority Actions. 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society.  http://pdf.usaid.gov/pdf_docs/PA00KH52.pdf

Changes For Justice Project Wildlife Trade, Wildlife Crimes And Species Protection In Indonesia: Policy And Legal Context. March 2015. Prepared for Chemonics International Inc. by the Indonesia Program of the Wildlife Conservation Society. USAID. http://pdf.usaid.gov/pdf_docs/PA00KH4Z.pdf