REQUEST FOR BIODIVERSITY enabling activity

Proposal for Funding Under the GEF Trust Fund

part i:  project IDentifiers

| EA Title: | National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Malaysia |  |  |
| --- | --- | --- | --- |
| Country(ies): | Malaysia | GEF Project ID: | t.b.d. |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 4803 |
| Other Executing Partner(s): | Ministry of Natural Resources and Environment | Submission Date: Resubmission Date: | February 3, 2012 February 27, 2012 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) | 36 |
| Check if applicable: | NCSA NAPA | Agency Fee ($): | 22,000 |

- EA framework

### EA Objective: To integrate Malaysia’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

| ### EA Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Grant Amount ### ($) | ### Confirmed Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
| 1) Stocktaking and national target setting | TA | - By early 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By October 2012, national targets in response to the global Aichi Targets are developed. | 1.1 Review and stocktaking of the current biodiversity plans and programmes and their outcomes at the national level are carried out in participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to Malaysia’s circumstances. 1.3 The achievement of national biodiversity targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, Malaysia taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). | 32,000 | 193,000 |
| 2) NBSAP update | TA | - By early 2014, Malaysia’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP | 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for Malaysia, anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAPs for Malaysia is submitted to the CBD preferably within the deadline set by the COP. 2.3 Strategic studies that support the update/revision of NBSAP are carried out. The studies include: - Local TEEB (The Economics of Ecosystems and Biodiversity) Study: Assessing and capturing value in ecosystems’ goods and services in Malaysia - Mainstreaming biodiversity into key sectors, and developing opportunities for conservation and sustainable use. - Exploring and costing options for promoting ecosystem-based adaptation and resilience to climate change in Malaysia, including mapping species’ and ecosystems’ distributions in scenarios of climatic variability and change as an aid to the analysis of ecosystem vulnerability and resilience - Strengthening the PoWPA Action Plan by integrating key Aichi Targets into national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) | 85,000 | 496,000 |
| 3) National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms |  | - By 2013, complete the updating and improvement of national clearing house mechanisms - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment | 3.1 National frameworks for NBSAP implementation are in place and include: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 A comprehensive, user-friendly and easily updatable country-driven CHM site is developed; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. 3.3. Immediate CBD reporting obligations are met by Malaysia in a timely manner: the Fifth National Report to the CBD by 31 March 2014. 3.4. A permanent framework for CBD reporting is established and receives recurrent funding from government and other sources according to needs and in a timely manner; such framework may include: institutional anchoring, the statutory establishment of technical committees, facilities and arrangements in place for data sourcing and monitoring, etc. | 92,000 | 247,000 |
| Subtotal |  |  |  | 209,000 | 936,000 |
| EA Management Cost |  |  |  | 11,000 | 164,000 |
| Total EA Cost |  |  |  | 220,000 | 1,100,000 |

- Co-financing for the EA by source and by name

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | Government of Malaysia* | Grant | 800,000 |
| GEF agency | UNDP | Grant | 300,000 |
| Total Co-financing |  |  | 1,100,000 |

* Includes $450K in government cost-sharing detailed in budget in Annex D plus $350K government managed funds under the 10th Malaysian Plan.

- Grant  Resources Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | EA Amount (a) | Agency Fee (b) | Total (c)=(a)+(b) |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF TF | Biodiversity Focal Area Set-Aside | Malaysia | 220,000 | 22,000 | 242,000 |
| Total Grant Resources |  |  |  | 220,000 | 22,000 | 242,000 |

- EA Management Cost

| ### Cost Items | ### [GEF only] Total Estimated Person Weeks/Months | ### Grant Amount ($) | ### Co-financing ($) | ### EA Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 0 | 0 | 117,000 | 117,000 |
| ### International consultants* | 0 | 0 | 0 | 0 |
| ### Office facilities, equipment, vehicles and communications* |  | 4,500 | 8,000 | 12,500 |
| ### Travel* |  | 6,500 | 30,000 | 36,500 |
| ### Other: Printing of M&E reports |  |  | 6,000 | 6,000 |
| Other: Workshops: 6 PSC meetings, 12 TWC meetings and 6 project meetings in Peninsular Malaysia, States of Sabah and Sarawak |  | 0 | 3,000 | 3,000 |
| Total |  | 11,000 | 164,000 | 175,000 |

*   Details are provided in Annex A and Annex D.

Additional information for Table D, if applicable:

If costs for office facilities, equipment, vehicles and communications, travels are requesting for GEF financing, please provide justification here:

Over 90% of the project management cost is borne by the government and UNDP co-financing, including the project manager and assistant costs (refer to the Total Budget and Workplan in Annex D for all the details). However, a small amount of equipment and travel budget is requested from the GEF funding, to cover the project manager’s domestic travels for project monitoring including inter-states flights (especially the states of Sabah & Sarawak) flight, small amount of communication cost and one lap-top computer to be used for the NBSAP development and consultation processes.

part ii:  Enabling Activity JustiFication

A. Enabling Activity Background and Context

- Malaysia, located between 1oN and 7oN of the equator in the South East Region, covers an area of approximately 329,750 km2. The warm and humid climate throughout the year with temperature in the lowlands ranging from 21oC to 32oC provides support to a vast and diverse range of ecosystems, habitats and species. Most of the nation lies within the Sundaland Hotspot and it is one of the 17 mega-diverse countries in the world, harbouring up to 7% of the global biodiversity. This include 15,000 species of vascular plants (~26% endemic in Peninsular Malaysia), 306 species of mammals, 742 species of birds (6 % endemic), 567 species of reptiles, 242 species of amphibians and more than 449 species of freshwater fishes. The conservative estimate is that there are more than 150,000 species of invertebrates, many of which are endemic. - Malaysia is a Federation, consisting of Peninsular Malaysia (eleven states and two federal territories) and East Malaysia (the states of Sabah and Sarawak, and the Federal Territory of Labuan). A multi-ethnic country, Malaysia has a total population of 28.3 million in 2010, where the population growth has been maintained at 1.3% per annum in the last 5 years. More than 80% of the population resides in Peninsular Malaysia, with 9.9% in Sabah and 9.4% in Sarawak. The country is ranked 61 among the 187 countries assessed in the UNDP Human Development Report 2011 with a Human Development Index (HDI) score of 0.761. The economy of Malaysia has experienced three decades of impressive growth, which is on three sectors -- namely services, manufacturing and agriculture. This has enabled the nation to provide for the health and education of its people and to significantly reduce poverty in many parts of the country. While poverty has been reduced from 17% in 1990 to below 4% in 2009, the 9th Malaysia Plan reports that income disparity among ethnic groups and between urban and rural areas is still sizeable and has increased in recent years. Moreover, poverty continues to be predominantly a rural phenomenon with 70.6% of the poor residing in the rural areas. The availability and sustainability of biological resources has a direct relevance to poverty reduction in rural communities as they derive a significant proportion of their food and income from biological resources. - This globally significant biodiversity state faces a number of threats. These include: - Land use change – at the turn of the 19th century, primary rainforest covered over 90% of Malaysia. Currently, forests cover 56.4% of the total land area. 58% or 19.2 million ha of the forest cover is intact primary forest. The latest IUCN Red List (IUCN 2009) upgraded the threat status of many local mammals compared with the 2007 assessment. This is a direct result of the fact that many lowland dipterocarp forests have been converted to agricultural plantations through government and private land development schemes, driven by Federal and state agricultural development policies, without internalising the externalities of the forest loss. Undervaluing the true economic value of the forests, biodiversity and associated ecosystem services is another root cause for this threat. Habitat loss and land degradation in the highlands due to development activities are also emerging issues, especially in the established hillside settlements for commercial agriculture and tourism, resulting in more frequent natural disasters such as flash floods and landslides. Although the deforestation rate has been stabilised in Peninsular Malaysia, noting that the chief economic activities shifted from the forestry sector to industry and services, the residual effect of habitat loss combined with cumulative impacts of forest fragmentation due to construction of roads, pipelines and railways are posing threats to biodiversity. This fragmentation contributes to the genetic isolation of populations of endangered species and reduced habitat value due to edge effects. - Overexploitation – Illegal logging is currently under control and is no longer regarded as a major threat. However, encroachment (land clearance), poaching and the illegal collection of non-timber forest products such as agarwood are of growing concern. Evidence of poaching exists, as evidenced by the seizures of smuggled wildlife at border crossings and regional markets. These illegal activities have the potential to affect the local viability of threatened species in a very short time. Wildlife populations have declined in many parts of their former range due to poaching for illegal trade. The real scale of poaching is difficult to estimate, as there is currently limited monitoring and no systematic estimation of remaining populations of species such as tigers and elephants. - Invasive alien species – Invasive alien species (IAS) in the past had caused serious damage to respective economic sectors and habitats, especially agriculture sector. Some of the impacts recorded are reduction of yield and increased production costs. These invasive alien species recorded include insects, diseases (bacteria, viruses, mycoplasma), weeds and molluscs, etc. The total damages inflicted by invasive alien species are not well established as there is limited assessment of the impacts of invasive alien species. - Pollution – Water pollution as a result of surface runoff of agricultural activities, sewage and effluent discharge is one of the major threats to freshwater, coastal and marine biodiversity. Development pressures such as urbanization are aggravating existing problems with water pollution. - Climate change – Some potential impacts of climate change in the Malaysian context would include sea level rise, reduced crop yields, greater rates of disease among forest species and biodiversity loss, erosion of shorelines, increased flood intensities, coral reef bleaching, increased incidences of human disease, tidal inundation of coastal areas, decreased water availability, and more droughts. Although there is no detailed analysis of the potential impacts of climate change on biodiversity, some of the more vulnerable ecosystems and species, especially those located at coastal areas and mountain tops will be impacted. - The primary government agency responsible for biodiversity management is the Biodiversity and Forestry Management Division at the Ministry of Natural Resources and Environment, which is also the national focal point for CBD. The division works closely with other agencies and institutions in various thematic areas of biodiversity management. Other agencies/institutions which play an important role in managing biodiversity as part of their operating mandates are Forestry Department of Peninsular Malaysia, Department of Wildlife and National Parks, Department of Marine Park, Forest Research Institute Malaysia, Department of Fisheries, Department of Town and Country Planning, Department of Environment, Department of Agriculture, Malaysian Agricultural Research and Development Institute, Ministry of Plantation Industries and Commodities, State Planning Units, State Forestry Departments, State Park Corporations and State Biodiversity Centres. In addition, there is an inter-ministerial and cross sectoral council called National Biodiversity Council to provide policy direction and coordination in the sustainable use, management and conservation of biodiversity. - According to the Provisional Master List of Protected Areas in 2009, there are 385 formal PAs, covering 4.35 million ha of the land surface and territorial seas. These include 53 marine PAs and 340 terrestrial PAs covering approximately 3.5 million ha, or 10.6 % of Malaysia’s land area. In Peninsular Malaysia, 193 terrestrial protected areas cover about 12.8 % (1.7 million ha) of its total land area. These sites are managed by a range of agencies, each of which is responsible for individual networks of varying size, managed with varying degrees of effectiveness. In Peninsular Malaysia alone there are separate networks managed by institutions including the Federal agencies such as Department of Wildlife and National Parks (DWNP) and Department of Marine Park, state-level agencies such as Forestry Departments and State-owned park corporations in Johor and Perak. In the State of Sabah alone there are at least five agencies involved in various aspects of PA management. Since Malaysia has a federated system, these agencies at state level each operate under different legal and institutional management structures. - Malaysian Government has put in place a series of long and medium term national development plans such as Vision 2020, Third Outline Perspective Plan (1991 – 2020) and 5-year Malaysia Plan that incorporate biodiversity and natural resources. In addition to the National Policy and Action Plan on Biological Diversity which has not been updated since 1998, the National Biodiversity Council endorsed A Common Vision on Biodiversity in 2009 that outlines a three-pronged implementation approach to biodiversity planning and management at all levels and sectors, which are (i) strengthening the protected areas system; (ii) landscape management for biodiversity; and (iii) mainstreaming of biodiversity. Currently, the Ministry of Natural Resources and Environment is conducting a feasibility study of establishing a National Biodiversity Centre, which is envisaged to have strong mandate to integrate biodiversity consideration into development policies and sectoral plans including emerging issues in biodiversity management and conservation. This centre also aims to enhance science-policy interface for better biodiversity governance. At the sub-national level, some state governments such as the States of Sabah and Sarawak have enacted their own legislation for biodiversity. For example, the Sarawak Biodiversity Centre (Amendment) Ordinance 2003 and Sarawak Biodiversity Regulations 2004 and Sabah Biodiversity Enactment 2000. - On biosafety issues, a National Biosafety Department was established under the Ministry of Natural Resources and Environment to ensure the enforcement of the National Biosafety Act 2007 and its subsidiary regulations. In the mean time, Malaysia is in the process of establishing a national regulatory framework for access and benefit sharing of biological resources with the support of UNDP CO through a project, which also aims to develop an institutional arrangement for implementing the ABS law and its subsidiary regulations. The States of Sabah and Sarawak are also making preparation for inclusion of ABS to strengthen its biodiversity strategy and legislation. - There are a few barriers to effective implementation of the CBD Strategic Plan at the national and sub-national level. - Federal and state government capacity constraints to implement National Policy on Biological Diversity and Action Plan (NBSAP) and mainstream biodiversity into development policies, plans and practices, and production sectors – The capacities for biodiversity management has been significantly strengthened since the formulation of National Policy on Biological Diversity, the creation of National Biotechnology-Biodiversity Council in 2001 and subsequently, the establishment of the Ministry of Natural Resources and Environment in 2004. Nevertheless, the extent of implementation and mainstreaming across sectors and at the sub-national and local level can only be enhanced by addressing the following issues: - Policy and regulatory framework - The National Policy on Biological Diversity has not been updated since 1998. In general, it does not stipulate mandates, regulatory and standards provision for biodiversity mainstreaming. Existing laws and regulations related to biodiversity do not define which habitats, species, and ecosystem goods and services need to be accounted for in sectoral planning. It lacks methodologies and implementation mechanisms (sequences-of-action with defined roles of various agencies and inter-agency cooperation) for mainstreaming biodiversity conservation concerns into sectoral planning and, in turn, into economic activities whose location and methods are governed by local plans. There is a critical need to harmonise existing policies and laws for effective biodiversity planning and management; - Information base for decision making – Sectoral planning is often constrained by the fact that decision-makers (particularly the state and local agencies) do not have access to appropriate information and tools for making choices about resource use or conservation options. The information gaps in this context refer to spatial and temporal data on habitats and species, impacts of climate change, and economic valuation of the full range of ecosystem goods and services; - Financing sustainability – Without a sustainable finance mechanism in place, it is difficult to ensure long-term finance for implementing the CBD Strategic Plan. By assessing the value of key ecosystem services, and by incorporating these values into the national economy, Malaysia plans to identify innovative mechanisms for sustainable financing implementation of the CBD Strategic Plan, such as payment for ecosystem services (PES), reduced emissions from deforestation and forest degradation (REDD+), etc. - Science-policy interface – Currently there is a lack of interface for sound science to guide policy-making; this can be attributed to lack of proper institutional framework and baseline scientific information on biodiversity. Furthermore, the pool of expertise in the field of biodiversity needs to be increased and be given adequate technical capacity and resources to enhance research. - Institutional and individual capacity in the enforcement of laws and regulations – Institutional capacities need to be enhanced in enforcement of an ecosystem approach to protection of wildlife and marine species, fisheries and eco-tourism planning. The capacity to enforce and monitor existing regulations is restricted due to understaffing, lack of requisite information, tools, equipment and incentives. The GEF fund in this enabling activities project will assist Malaysia in removing these barriers to implement the updated NBSAP across sectors as well as different levels of governance. - National Reporting to CBD. Reports; Date of Submission to CBD Secretariat; Current Status*; Comments. National Biodiversity Strategy and Action Plan; 2 May 1998; Submitted; Outdated. Revision of NBSAP; Not started; Funding being applied for this purpose. 1st National Report; 9 March 1998; Submitted; 30 August 2007. 2nd National Report; 29 November 2005; Submitted; Outdated. 3rd National Report; 20 November 2005; Submitted; Updated information from 1st NR. 4th National Report; 30 April 2009; Submitted; Updated information from 2nd NR. 1st Biosafety Report; 30 August 2007; Submitted. 2nd Biosafety Report; Not started; Funding will be applied through UNEP for the purpose. - Capacity Needs Assessments carried out YES NO. Start Date 1 January 2007; End Date 31 August 2008. Please list all of the CBD Program of Work and cross-cutting themes that were addressed in the Biodiversity Enabling Activities Capacity Needs Assessments:; Dates. - Thematic Assessment and Cross-Cutting Report Implementation of United Nations Convention of Biological Diversity, Framework Convention on Climate Change, Convention to Combat Desertification in Malaysia; 2007-2008. - Under the 3rd National Report to the CBD: - Inland water system - Marine and coastal biological diversity - Forest biological diversity - Mountain biodiversity; 2004-2005. - Under the 4th National Report to the CBD: - Current status of NBSAPs - Sectoral and cross-sectoral integration and mainstreaming of biodiversity (cursory analysis) - 2010 Target; 2008-2009. 3) Clearing House Mechanism (CHM) established?; YES NO. CHM link(s):; www.frim.gov.my/. Is the CHM website maintained up to date?; YES NO. How many people currently operate and maintain the national CHM?; 1 full time staff. How many people visited the national CHM website in the past 12 months?; 2,900. Note: Malaysia has established a CHM maintained and updated by Forest Research Institute of Malaysia since 2006..

B. Enabling Activity Goals and Objectives

The Baseline Project: The Current NBSAP and the new CBD Strategic Plan The new CBD Strategic Plan, adopted at CoP-10 in 2010 in Nagoya, clearly addresses the need for updating NBSAPs, stating in Target 17 that “By 2015, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan.” The strategic plan also covers a range of issues that will need to be incorporated into the revised NBSAPs, including guidance to countries to: a) fully realise the value of biodiversity and ecosystem services, and incorporate these values into national and local development and poverty reduction strategies (Targets 1 and 2); b) increase the global terrestrial protected area estate from 12% to 17% and the marine estate from 6% to 10% (Target 11); c) restore and safeguard key ecosystem services, especially for water, health and livelihoods (Target 14); and d) strengthen ecosystem resilience to climate change and promote ecosystem-based approaches to climate change adaptation and mitigation (Target 15). The most recent NBSAP for Malaysia was completed in 1998. This version of the NBSAP does not include the following elements of the CBD Strategic Plan’s Aichi Targets: - A plan for integrating the value of biodiversity into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems (Target 2) - A plan for creating incentives and removing harmful subsidies (Target 3) - A plan for developing landscapes that have sustainable production and consumption and ensure the use of natural resources falls well within safe ecological limits. (Target 4) - A plan for fully implementing the Programme of Work on Protected Areas, including increased protection and landscape/seascape connectivity (Target 11) - A plan for restoring and safeguarding ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being (Target 14) (although the NBSAP did include a section on biodiversity for food security) - A plan for strengthening ecosystem resilience and the contribution of biodiversity to carbon stocks, including the restoration of at least 15 per cent of degraded ecosystems (Target 16) - A plan for the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources (Target 20) Proposed Response and Rationale: The New Generation of BD EA This project seeks to fully incorporate the above issues into the NBSAP. This ‘new generation’ of NBSAP will help set a national standard of excellence by creating a road map for achieving the Aichi Targets in Malaysia. Special emphasis will be placed on mainstreaming biodiversity into development plans, incorporating protected area networks and sustainable production systems into ecosystem-based climate adaptation and resilience plans, and creating sustainable finance for biodiversity conservation through the full valuation of key ecosystem services. Alignment with Focal Area Outcome(s): BD5 Objective: Integrate CBD Obligations into National Planning Processes through Enabling Activities (herein serving as the ‘Project Development Goal’): Focal Area Outcome 5.1: Development and sectoral planning frameworks at country level integrate measurable biodiversity conservation and sustainable use targets. The Project Objective is: To integrate Malaysia’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020. This will be achieved through the following Outcomes (corresponding to components described in detail below): - Outcome 1 – A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets. - Outcome 2 – The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience. - Outcome 3 – National frameworks for resource mobilization, Convention reporting and exchange mechanisms are established and strengthened. Refer to Part I, Table A and to the next section for more details. How the Project Plans to Build National Capacity Enabling Activities are considered foundation activities within the framework of the GEF. The ultimate goal of Biodiversity Enabling Activities is to build national capacity across the board for biodiversity management. The effective achievement of global biodiversity benefits depends on the development of national capacity for managing biodiversity. The more robust this capacity is in a given country, the more effective will the national implementation of the CBD be. The approach to building of national capacity in this proposal follows the guidance from the GEF Strategic Approach to Enhance Capacity Building (2003) under the GEF’s cross-agency Capacity Development Initiative. Three levels of capacity were identified: individual, organizational and systemic. Quoting from a recent GEF publication on the theme of capacity (GEF 2010): “At the individual level, capacity development refers to the process of changing attitudes and behaviours, most frequently through imparting knowledge and developing skills through training. However it also involves learning by doing, participation, ownership, and processes associated with increasing performance through changes in management, motivation, morale, and improving accountability and responsibility. Capacity development at the organizational level focuses on overall performance and functioning capabilities, such as developing mandates, tools, guidelines and management information systems to facilitate and catalyze organizational change. At the organizational level, capacity development aims to develop a set of constituent individuals and groups, as well as to strengthen links with its environment. At the systemic level, capacity development is concerned with the “enabling environment”, i.e., the overall policy, economic, regulatory, and accountability frameworks within which organizations and individuals operate. Relationships and processes between organizations, both formal and informal, as well as their mandates, are important.” In this light, this project will build national capacity in Malaysia in the following manner: Individual; Technical working groups will be set up and coordinated by the Ministry of Natural Resources and Environment. This is a common practice and an ideal forum for imparting knowledge among different individuals (civil service, NGO, academic, etc.) involved in the implementation of UNDP/GEF projects and involved in environmental projects in Malaysia in general.. Organizational; UNDP’s approach to Biodiversity Enabling activities in GEF5 goes beyond the mere production of national reports and strategies to the CBD and the development of a website for the CHM. Rather, it is concerned with the development of a permanent framework for reporting to the CBD and for maintaining the CHM interesting and up to date. This implies institutionalising the capacity for eventually achieving this with as little external assistance as possible. Given the ambitious targets of the CBD Strategic Plan (2011-2020), it is recognised that actions to engage external assistance and retain national organizational capacities are in the meanwhile needed. This will be availed through the project. In particular, the following activities are specially targeted at building organisational capacity: - Taking stock of the NBSAP and identifying barriers to its implementation - Setting targets and priorities - Developing implementation plans for the revised NBSAP - Assessing and strengthening capacity needs - Developing clearinghouse mechanisms - Developing a permanent framework for reporting to the CBD. Systemic; The approach that UNDP has developed for Biodiversity Enabling Activities in GEF5 is transformational with respect to systemic capacity elements (i.e. policy, economic, regulatory, and accountability frameworks within which organizations and individuals operate). The aim is to ensure that the objectives, targets and guidance from the CBD Strategic Plan (2011-2020) become fully anchored into national development frameworks. This will be achieved by the development of the following new aspects of the CBD strategic plan: (i) the valuing of ecosystem goods and services; (ii) mainstreaming; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. The knowledge developed through these activities will become part of Malaysia’s new NBSAP and will have a greater chance of influencing a wide range of policies and even becoming policy. In particular, the following activities are specially targeted at building systemic capacity: - Assessing and integrating ecosystem services through economic valuation - Mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies - Incorporating climate change issues into NBSAPs - Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan - Securing sustainable finance for NBSAP implementation - Monitoring and reporting on the status of biodiversity under climate change scenarios. Some stakeholders will benefit from the implementation of the capacity building activities. The potential beneficiaries are listed in the categories below. Government; - Ministry of Natural Resources and Environment - Economic Planning Unit - Ministry of Finance - Ministry of Agriculture and Agro-based Industries - Ministry of Plantation Industries and Commodities - Ministry of Tourism - Ministry of Energy, Green Technology and Water - Ministry of Science, Technology and Innovation - Forestry Department of Peninsular Malaysia - Department of Wildlife and National Parks - Department of Agriculture - Department of Town and Country Planning - Department of Orang Asli Development - State Economic Planning Units - Sabah Biodiversity Centre - Sarawak Biodiversity Centre - Sabah State Forest Department - Sarawak Forestry Department - State Forestry Departments - Local Authorities. NGOs; - Centre for Orang Asli Concerns - Global Environment Centre - Malaysian Nature Society - Third World Network - TRAFFIC - Wetlands International - Wildlife Conservation Society - WWF Malaysia. Research and Higher Learning Institute; - Forest Research Institute of Malaysia (FRIM) - Malaysian Agricultural Research and Development Institute - National University of Malaysia - University of Putra Malaysia - University Malaya.

C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A ).

Detailed Description of Activities per Project Component / Outcome The description that follows indicates precisely how the project will develop national capacity and how the project will ensure the sustainability of its outcomes. That description has been organized in five modules (I -V), following the GEF’s guidance, but which for the sake of simplicity were grouped within the three already mentioned Components / Outcomes. The following are modules: Component; Outline of modules for NBSAP Revision and Related Activities; [Indicative percentage of total GEF funding in the proposal. 1; I. Preparation; 5.0%. II. Setting national targets, principles, & main priorities of the strategy; 10.0%. 2; III. Strategy and action plan development; 45.0%. 3; IV. Development of Implementation plans and related activities; 15.0%. V. Institutional, monitoring, reporting and exchange; 20.0%. Component 1. Stocktaking and national target setting Key outputs expected under this component includes the following: 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to the Malaysian context. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, Malaysia taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). Key products or publications (maybe combined into one): - Brief Review of the Biodiversity Planning Process in Malaysia - Biodiversity Targets for Malaysia that are aligned with the national and sub-national contexts: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 In connection with the above outputs and deliverables, and as a result of the activities outlined below, Malaysia will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By early 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By October 2012, national targets in response to the global Aichi Targets are developed. Key Activities (I and II): - Preparing for the NBSAP revision - Taking stock of the NBSAP and identifying barriers to its implementation: This activity will focus on rapidly but accurately taking stock of existing plans, policies and practices, and of the root causes of biodiversity loss. Within country-specific contexts, the aim is not only to identify key threats, but to understand the drivers behind these threats, as well as the key aspects of the policy environment that are barriers and challenges to effective conservation/sustainable use. Based on existing studies and analyses, the emphasis of this activity will be on identifying key gaps in the existing NBSAP, understanding the primary drivers and root causes, and identifying the means of overcoming existing barriers and challenges. - Stakeholder consultation and participation: This activity will focus on ensuring a robust consultative process that engages representatives from key sectors, administrative leaders, and traditionally under-represented groups including women. The aim is to develop and sustain a participatory process in order to increase the likelihood of successful implementation of the NBSAP. This is especially important relative to the goals of mainstreaming biodiversity into national development plans, and promoting resilient landscapes that include production sectors. Refer to section on stakeholder engagement section further down for more details. The Policy, Institutional and Capacity Development Specialist will play a particularly important role in the stocktaking and stakeholder engagement sub-activities. Together with, and under the guidance from the BD EA Project Manager, the Specialist will lead the formation of a Technical Working Group (or more than one group as applicable) with the following indicative TOR: - Assist the BD EA Project Manager to design a thorough activity workplan for the project and to monitor it. - Provide policy and technical advice on the matters being discussed within the working group(s), e.g. in those formed under to support the work of consultancies, and in project events. - Provide written and review inputs to different reports and products expected from the project, with focus on the new National Biodiversity Strategy and Action Plan for Malaysia and related products (e.g. CHM, 5NR). - Setting targets - Setting targets and priorities: This activity focuses on setting specific, measurable, achievable and time-bound targets for Malaysia’s updated NBSAP based on the global Aichi Targets, including targets on restoration of ecosystems, protected area coverage, overall biodiversity loss, and other aspects of the Strategic Plan. This activity, which is linked to priority setting among different aspects within the NBSAP, will be completed by COP-11. Several project consultants will be involved in this activity under the leadership of the BD EA Project Manager. Targets will need to be validated by an appropriate forum and undergo technical scrutiny. They may be slightly revised (or adjusted) later, once other products become ready (e.g. the actual NBSAP and some of the strategic studies foreseen as part of it). These targets will represent Malaysia’s commitment before the international community in terms of implementing the CBD’s Strategic Plan 2011-2020 and will be presented to the Convention’s COP in due course. Component 2. NBSAP Update Key outputs expected under this component includes the following: 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for Malaysia, anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAPs for Malaysia is submitted to the CBD preferably within the deadline set by the COP. 2.3 Strategic studies that support the update/revision of NBSAP are carried out. The studies include: - Local TEEB (The Economics of Ecosystems and Biodiversity ) Study: Assessing and capturing value in ecosystems’ goods and services in Malaysia - Mainstreaming biodiversity into key sectors, and developing opportunities for conservation and sustainable use. - Exploring and costing options for promoting ecosystem-based adaptation and resilience to climate change in Malaysia, including mapping species’ and ecosystems’ distributions in scenarios of climatic variability and change as an aid to the analysis of ecosystem vulnerability and resilience - Strengthening the PoWPA Action Plan by integrating key Aichi Targets into national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) Key products or publications: - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 1: Study on Ecosystem Valuation in Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Malaysia - Sub-product 4: Development of an updated PoWPA Action Plan to achieve key Aichi Targets . In connection with the above outputs and deliverables, and as a result of the activities outlined below, Malaysia will strive to achieve the following outcome vis-à-vis its CBD obligations: - By early 2014, the Malaysia’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP. Key Activity (III): - Developing the NBSAP This step will seek to achieve the following: (i) Developing the strategy and actions to implement the agreed targets though national consultations; (ii) Application of the NBSAP to sub-national entities through sub-national and local consultations; and (iii) Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations. While the project will focus on updating all aspects of NBSAPs, it will place particular emphasis on those aspects that are both highlighted in the 2011-2020 CBD Strategic Plan. These include the following: Besides the Technical Working Group(s) and under the leadership by the BD EA Project Manager, sub-activities under this Activiy #3 will count on the support from national consultants such as the Policy, Institutional and Capacity Development Specialist, the Environmental Economist and the Biodiversity Finance Specialist, the Climate Change Expert and the Biodiversity/Protected Area Expert. International consultants in particular (Environmental Economist and Biodiversity Finance Specialists) will provide support to a number of more complex tasks related to the preparation of the NBSAP and related products. - Assessing and integrating ecosystem services through economic valuation: The study on the Economics of Ecosystems and Biodiversity (TEEB) has drawn attention to the global economic benefits of biodiversity and ecosystem services and to the growing costs of biodiversity loss and degradation. However, we have not yet linked the value of biodiversity and ecosystem services to Malaysia’s own national development goals, including poverty eradication and sustainable livelihoods. Through this activity, the country will be able to demonstrate the benefits and values of ecosystems and biodiversity at a national level, and better link ecosystems and priority sectors in national development plans, in order to guide allocation of resources. The aim is to strengthen the point that biodiversity not only underpins human well-being, but that biodiversity and associated ecosystem services can make a significant contribution to poverty reduction and sustainable development. By engaging national specialists and providing support from global specialists, hard economic data will be collected and processed at the country level to demonstrate the costs and benefits of investing in biodiversity management. Capacity to carry out the assessments and make important links to priority economic sectors will be simultaneously built within the country. The availability of essential data and the analysis will allow us to “make the case” for biodiversity and will facilitate the process of mainstreaming biodiversity into sectoral planning through concrete biodiversity valuation examples. Specific steps in this process include: - Identify and assess the full range of values of key ecosystem services in Malaysia, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the national TEEB valuation results, the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g., water, carbon), and existing global and regional maps and overlays of key ecosystem services; - Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use; - Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, food security and sustaining livelihoods; - This activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. - Mainstreaming biodiversity into development policies, plans and practices into sectoral plans and strategies: Mainstreaming has been defined as the internalization of biodiversity conservation goals into economic and development sectors, policies and programmes, such that they become an integral part of their functioning of these sectors. As part of this process, Malaysia will focus on sectors that include land use, agriculture, forestry, tourism, water, energy, fishery, oil and gas, commodities, trade, travel and transport (specifically on the issue of IAS). The project will also pay particular attention to poverty alleviation, rural development and livelihoods, education, food security, climate change mainstreaming and urban planning. Specific steps in this process will include: - Forming partnerships between relevant stakeholders interested in biodiversity conservation issues and in development issues; - Explicitly identifying key stakeholders’ interests, and desired outcomes; - Identifying potential conflicts and trade-offs, and work towards mutually acceptable solutions, including strategies that serve mutually beneficial interests and achieve mutually beneficial outcomes; - Embedding and institutionalizing these strategies in the institutions, policies, agreements, programs and mechanisms of each sector. A set of capacity building modules on national biodiversity strategies and action plans, and other aspects of implementation of the Convention, is available at the CBD website. Module B-3 on mainstreaming biodiversity into sectoral and cross-sectoral strategies, plans and programmes has been updated in 2011. It focuses on the theme of biodiversity mainstreaming both into (i) national development and poverty reduction frameworks, as in production sectors. The guidance also suggests a number of tools that can be used for the purpose with examples and further guidance. The document is available in English, French and Spanish. Malaysia will seek inspiration from these materials in its mainstreaming activities in connection with the NBSAP update. - Incorporating climate change issues into NBSAPs: The previous NBSAP did not adequately address aspects of climate change. This activity will involve incorporating aspects of climate change into NBSAPs, including, for example: - Identifying, protecting and appropriately managing areas important for carbon sequestration; - Updating the country’s ecological gap assessment to include predicted future distribution of biodiversity under climate change scenarios; - Assessing the impact of climate change on the functioning of ecosystem services, such as water and carbon sink; - Identifying areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors; - Identifying areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation. - Updating Malaysia’s Protected Area Action Plan: The previous NBSAP did not fully address the development of a robust, comprehensive network of protected areas (both marine and terrestrial) that fully meets Target 11 of the Strategic Plan, but also Targets 2, 3 and 14, among others. This process will include: - Identifying opportunities for expanding existing protected areas; - Identifying threats and problems in managing protected areas; - Identifying opportunities for improving law enforcement; - Identifying areas for creating conservation corridor; - Identifying opportunities to protect key ecosystem services; - Identifying requirements for improving management effectiveness in order to achieve the Aichi Targets; - Identifying opportunities to sustain local livelihoods. Component 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms Key outputs expected under this component includes the following: 3.1 National frameworks for NBSAP implementation are in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 A comprehensive, user-friendly and easily updatable country-driven CHM site is developed; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity.. 3.3 Immediate CBD reporting obligations are met by Malaysia in a timely manner: The Fifth National Report to the CBD by 31 March 2014. 3.4. A permanent framework for CBD reporting is established and receives recurrent funding from government and other sources according to needs and in a timely manner; such framework may include: institutional anchoring, the statutory establishment of technical committees, facilities and arrangements in place for data sourcing and monitoring, etc. Key products or publications: - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP - Fully upgraded and functional CHM for Malaysia, based on best international practice on the matter In connection with the above outputs and deliverables, and as a result of the activities outlined below, Malaysia will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By 2013, complete the updating and improvement of national clearinghouse mechanisms - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment Key Activities (IV-V): - Developing implementation plans This activity will focus on developing an overall plan for implementing the NBSAP. This implementation plan will include the following components: - Assessing and strengthening capacity needs: One of the primary areas of enabling activities is the assessment of capacity needs. The decisions at COP-10 place new and ambitious demands on countries, including requirements to protect and sustainably manage their lands and water, to develop comprehensive plans that integrate climate change into their land use, development and sectoral plans and strategies, and to develop appropriate biodiversity and climate policies, laws and incentives. This activity will ensure that we develop a road map for strengthening these specific capacities. Building on existing capacity needs assessment, and using existing guidance, we will identify the following gaps, along with capacity-building strategies to fill those gaps: - Capacity for regular reporting to CBD - Capacity to harmonise environmental policies and laws addressing biodiversity - Capacity to secure sustainable financing and resources for direct implementation of NBSAP - Capacity to predict climate change impacts and establishing links to biodiversity - Capacity regarding donor requirements and project design, implementation and monitoring The Policy, Institutional and Capacity Development Specialist will play a pivotal role in a assessing and strengthening capacity needs, with the support from the Working Group and other consultants where needed. - Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan: Malaysia is in the process of finalizing its PoWPA implementation plan, and this step will ensure that our work on protected areas, including goals, objectives and next steps, are fully integrated into the NBSAP. Particular emphasis will be placed on those aspects of Target 11 from the CBD Strategic Plan, including plans for expanding protected areas, improving management effectiveness, sustainably financing protected areas, improving connectivity, and integrating protected areas into the wider landscape and seascape. The Biodiversity/Protected Area Expert will play a key role in preparing the required reports under this sub-activities. - Securing sustainable finance for NBSAP implementation: Article 20 of the Convention mentions the need for Parties “to provide, in accordance with its capabilities, financial support and incentives in respect of those national activities which are intended to achieve the objectives of this Convention.” In the past few years, there has been a wide proliferation of innovative biodiversity finance mechanisms, such as payments for ecosystem services (PES), conservation trust funds, biodiversity offsets and bio-carbon funding, among many others. Malaysia is currently in early stages of exploring these mechanisms. For example, the UNDP supported scoping study on PES that look into potential ecosystem services and its users (key sectors). This activity will therefore focus on the following: - Identifying the existing financial gap for implementing the NBSAP; - Identifying potential sources of revenue for filling these gaps; - Assessing the feasibility for these revenue sources; - Developing a detailed plan for operationalizing these revenue sources; - Establish links with and solicit inputs from the EU-UNDP Biodiversity Financing project that aims to develop a financing framework for biodiversity management and mainstreaming, and UNDP-GEF project on “Enhancing Effectiveness and Financial Sustainability of Protected Areas in Malaysia” that is piloting the performance-based financing system for protected areas. - Defining implementation mechanism: The overall implementation plan will delineate major steps, responsible parties, costs for main activities, expected outcomes and a timeline by strengthening existing institutional framework, coordination and operation mechanisms. Accordingly, the project will also assist state governments to develop its own implementation plan for the updated NBSAP. - Communicating and disseminating the NBSAP: The project will develop a communication and dissemination strategy that employs effective tools for creating awareness and understanding of the NBSAP throughout the country particularly the state and local governments, local communities and NGOs. For the successful completion of the communication and dissemination strategy a focus group that comprises of various government institutions, private sector, NGOs and media can be established. The Communication Specialist will play a pivotal role in producing the required reports under this activity. - Institutionalizing, monitoring and reporting - Monitoring and reporting on the status of biodiversity under climate change scenarios: Monitoring and reporting on the status of biodiversity is a key aspect of several Programmes of Work within the CBD. To date, efforts to monitor and report on the status of biodiversity have been sporadic and have typically not taken into full account the status and trends of biodiversity, the status of effective conservation, the contribution of ecosystem services (such as water and carbon), and the likely impacts of climate change on biodiversity and ecosystem services. Through this project, Malaysia will ensure that future monitoring and reporting on the status of biodiversity and ecosystem services is comprehensive, and fully incorporates climate change issues. - Developing clearing house mechanisms (CHM): Malaysia has maintained an up-to-date CHM since 2008. This aspect of the project will help us enhance the CHM to be more effective, user-friendly and easily-updatable. This will enable the country to effectively share information nationally, regionally and globally. The project will also work in collaboration with the CHM of the Secretariat of the CBD, to ensure that lessons and information are disseminated globally. - Developing a permanent framework for reporting to the CBD: Parties to the CBD committed to submitting a fifth national report by 2014. In this project, Malaysia will submit a 5th National Report that fully covers the NBSAPs, key changes in the status and trends in biodiversity status, threats and conservation, and will develop a long-term reporting framework that will enable us to better track changes over time. The mentioned framework may include: institutional anchoring, the statutory establishment of technical committees, facilities and arrangements in place for data sourcing and monitoring, etc. Project consistency with national strategies and plans or reports and assessments relevant for the CBD, as well as other cross-cutting assessments and priority setting exercises Malaysia ratified the UN Convention of Biological Diversity in 2000 and it is making important efforts to fulfill its obligations under it, as well as to implement the Convention at the national level, including several of its Programmes of Work. Yet, there are gaps linked to national capacity and for which Malaysia needs assistance to address. Part II, Section A in this proposal contains a matrix listing different reports and assessments relevant for the CBD, as well as other cross-cutting assessments and priority setting exercises. This proposal fits well with the progress presented in the matrix, including the several gaps that need to be fulfilled in connection with this progress so far. This proposal is consistent with the following national plans and strategies: - 10th Malaysia Plan 2011 – 2015 under the National Programme 4.4 Natural Resource, Energy and Environment - National Policy and Action Plan on Biological Diversity 1998 - National Tiger Conservation Action Plan for 2008 -2020 - National Strategy for Plant Conservation 2009 - National Forestry Policy 1978 (revised 1993) - National Wetland Policy 2004 - The National Policy on Environment 2002 - National Policy on Climate Change 2009 - Fourth National Agriculture Policy 2011 - National Physical Plan This project is also fully complementary to the Master List of Protected Area in Malaysia project being finalised by WWF Malaysia. The final master list will be a valuable input to the development of an updated PoWPA and its implementation plan. The project further compliments the Heart of Borneo (HoB) programme supported by WWF-CARE-IIED. It involves the Governments of Malaysia, Indonesia and Brunei Darussalam within island of Borneo, with a mandate of securing sustainable sources of finance to transform the economies of the three countries to a low carbon green economy through strengthening of policy/legislation, provisioning of incentive schemes and building capacity. Synergetic effects of the Master List of Protected Area project, HoB and this project will be ensured through close collaboration with WWF Malaysia, who will be represented in the Project Steering Committee. Project Implementation Arrangement The project will be implemented over a period of 3 years. The Ministry of Natural Resources and Environment (NRE) is the government institution responsible for the implementation of the project and will act as the Executing Agency. UNDP is the Implementing Agency for the project and accountable to the GEF for the use of funds. The project is nationally implemented (NIM), in line with the Standard Basic Assistance Agreement between the UNDP and the Government of Malaysia, and the Country Programme Action Plan (CPAP) for 2008-2012. The overall responsibility for the project implementation by NRE implies the timely and verifiable attainment of project objectives and outcomes. NRE will provide support to, and inputs for, the implementation of all project activities. The Ministry of Natural Resources and Environment will nominate a high level official who will serve as the National Project Director (NPD) for the project implementation. The NPD will chair the Project Steering Committee (PSC) (and other relevant stakeholder, sectoral and working groups under the project), and will be responsible for providing government oversight and guidance to the project implementation The NPD will not be paid from the project funds, but will represent a Government in-kind contribution to the Project. The estimated value of this in-kind contribution is approximately $96,000. The NPD will be technically supported by a project technical team (national and international) as well as UNDP’s technical backstopping provided by the UNDP/GEF Regional Technical Advisor responsible for the project and the UNDP Environment Focal Point at the Country Office. All consultants hired by the project will be recruited using standard UNDP-CO recruitment procedures and will report directly to the NPD. Working closely with the NRE, the UNDP Country Office (UNDP-CO) will be responsible for: (i) providing financial and audit services to the project; (ii) recruitment of project staff and contracting of consultants and service providers; (iii) overseeing financial expenditures against project budgets approved by PSC; (iv) appointment of independent financial auditors; and (iv) ensuring that all activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures. A UNDP staff member will be assigned with the responsibility for the day-to-day management and control over project finance. A National Project Steering Committee (PSC) will be convened by the Ministry of Natural Resources and Environment, and will serve as the project’s coordination and decision-making body (Project Board). The PSC will include representation of all the key project stakeholders. The PSC meetings will be chaired by the NPD. It will meet according the necessity, but not less than once in 6 months, to review project progress, approve project work plans and approve major project deliverables. The PSC is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document. The day-to-day administration of the project will be carried out by a Project Coordinating Unit (PCU), comprising a Project Manager (PM) and Project Assistant, who will be located within NRE office. The project staff will be recruited using standard UNDP recruitment procedures. The PM will, with the support of the Project Assistant, provide technical advice and manage the implementation of all project activities. The Project Manager will liaise and work closely with all partner institutions to link the project with complementary national programs and initiatives. The PM is accountable to the Ministry of Natural Resources and Environment, and the PSC for the quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds. UNDP’s Comparative Advantage for Biodiversity Enabling Activities and UNDP has historically been the largest GEF implementing agency in terms of assisting countries in undertaking biodiversity enabling activities, having assisted more than 100 countries with it through several projects. The GEF-2 project Biodiversity Support Programme was jointly implemented with UNEP and has set the stage for biodiversity planning among GEF eligible countries. Malaysia has accessed funding through UNDP for preparing the first NBSAP, and for preparing its first, second and fourth national reports to the CBD. UNDP has a large and active GEF biodiversity portfolio in Malaysia. All the UNDP/GEF projects are implemented by a government Project Coordination Unit (PCU). This ensures that projects can effectively share costs and create technical synergies. These synergies will be created primarily with the following projects implemented by the PCU: - Conservation of Biological Diversity through Improved Forest Planning Tools in Malaysia - Enhancing Effectiveness and Financial Sustainability Of Protected Areas In Peninsular Malaysia - Biodiversity Conservation in Multiple-Use Forest Landscapes in Sabah, Malaysia - Third National Communication to UNFCCC (PIF in preparation) - Improving Connectivity in the Central Forest Spine (PIF endorsed by GEF OFP and pending approval from GEF) Synergies will focus on the provision of data and information produced by the projects and through the participation of project teams into key Enabling Activity events, where lessons learned by the project can be shared widely and cross-fertilize other relevant projects. The UNDP Country Office in Malaysia counts on at least three professional staff dedicated to the environment portfolio (plus support from operations and senior management). The Country Office is supported by the UNDP/GEF Regional Coordination Unit for Asia. Both will rely on UNDP's country-level coordination experience in integrated policy development, human resources development, gender issues, institutional strengthening, and non-governmental and community participation. All of these elements are all part of UNDP’s programme in Malaysia. Project’s Alignment with UNDP’s Programme for Malaysia UNDP has in 2008 developed a Country Programme Document for Malaysia (2008 – 2012) with three national priorities or goals: 1) Malaysia has increased its engagement in the global partnership for development, 2) Effectively responded to human development challenges and reduced inequalities, and 3) Malaysia has improved environmental stewardship through sustainable energy development and environmental management. This project will directly contribute to the third goal and its outcome, which is to improve quality of life and enhance sustainable development through environmental management of biodiversity and natural resources. UNDP has a long history of supporting national capacity building activities to ensure effective implementation of policies and programmes in the area of biodiversity conservation and management; and mainstreaming of environmental considerations into the planning and development of non-environmental agencies. Through this, UNDP will provide the key necessary resources and technical assistance in this Biodiversity Enabling Activities in Malaysia. Stakeholder Involvement in the Implementation of the Project The stakeholder involvement element is embedded in the description of several activities within this proposal which will have a consultative and participatory character. A full stakeholder involvement plan will be developed in connection with the preparation of the UNDP Project Document that will operationalise this proposal at the level of UNDP, allowing Malaysia to access the funding. This plan will depart from the following indicative and non-exhaustive list: Government agencies at the national and sub-national level are as follows: - Ministry of Natural Resources and Environment - Economic Planning Unit - Ministry of Finance - Ministry of Agriculture and Agro-based Industries - Ministry of Plantation Industries and Commodities - Ministry of Tourism - Ministry of Energy, Green Technology and Water - Ministry of Science, Technology and Innovation - Ministry of Housing and Local Government - Ministry of International Trade and Industries - Ministry of Foreign Affairs - Forestry Department of Peninsular Malaysia - Department of Wildlife and National Parks - Forest Research Institute of Malaysia - Department of Agriculture - Malaysian Agricultural Research and Development Institute - Department of Town and Country Planning - Attorney General’s Office - Public Services Department - Department of Orang Asli Development - State Economic Planning Units - State Treasuries - Sabah State Forest Department - Sarawak Forestry Department - State Forestry Departments - Local Authorities The project will ensure the participation of CSO/NGO and local communities, including indigenous people and women groups by following the CBD’s guidance on the engagement of traditional and indigenous people in biodiversity planning process. NGOs which were actively involved in the preparation of the 4th national report and remain active in biodiversity, environmental awareness, and environmental policies and legislation will be engaged throughout the project. Their involvement in the consultation process will provide valuable information and feedback for the updating of the NBSAP and the completion of the 5th national report. Some of the key NGOs are as follows: - Centre for Orang Asli Concerns - Global Environment Centre - Malaysian Nature Society - Third World Network - TRAFFIC - Wetlands International - Wildlife Conservation Society - WWF Malaysia The indigenous peoples of Malaysia represent around 12% of the 28.6 million people in Malaysia. At the same time, their livelihoods are still largely dependent on the use of biodiversity. The project coordination and working groups will ensure that the voice of indigenous and traditional groups will be duly heard and taken into consideration in the preparation of the new NBSAP. Special attention will be paid to CBD’s guidance on the engagement of traditional and indigenous peoples in biodiversity planning processes. Specific COP guidance on the matter, linked to implementation of the Convention’s Article 8(j), will be followed. Other stakeholders which will be involved in the project include academic sector and private sector, especially sectors that are closely linked to biodiversity and ecosystem services such as agriculture, fisheries, forestry and tourism. Gender Marking - The importance of gender mainstreaming in environmental and poverty eradication policies has been recognized in a wide range of global agreements and forums, including chapter 24 of Agenda 21 (United Nations Conference on Environment and Development 1992; the Johannesburg Plan of Implementation of the 2002 World Summit on Sustainable Development; the 2000 Millennium Declaration; and the 1975 Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW). - In the thirteenth preambular paragraph of the CBD, Parties recognize “the vital role that women play in the conservation and sustainable use of biological diversity and affirming the need for the full participation of women at all levels of policy making and implementation for biological diversity conservation”. Women, who account for 49.5% of the Malaysian population, constitute an important pool of human resources that contribute to the nation’s development objectives. In December 1989, the Malaysian Government approved the National Policy on Women. It was a) to ensure equitable sharing in the acquisition of resources and information as well as access to opportunities and benefits of development, for men and women; and b) to integrate women in all sectors of national development in line with their abilities and needs in order to improve the quality of life, eradicate poverty, abolish ignorance and illiteracy and ensure a peaceful and prosperous nation. Another important policy is The Plan of Action for the Advancement of Women, which the Government prepared in line with its commitment at the Fourth World Conference on Women in Beijing in 1995. It has the additional feature of identified agencies and ministries responsible for each of the actions. In line with the commitments to gender mainstreaming and gender equality under the CBD and the National Policy on Women, the project will promote the full participation of women at all levels of policy making and implementation of the CBD and National Policy on Biological Diversity particularly ensuring that the different relationships held by women and men in relation to their environment and resources, and the benefits derived from such relationships are also analysed. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men. Furthermore, gender marking implies the production of the following data by the project's year 2 and by its end: - Total number of full-time project staff that are women - Total number of full-time project staff that are men - Total number of Project Board members that are women - Total number of project Board members that are men - The number jobs created by the project that are held by women - The number jobs created by the project that are held by men

D. Describe, if possible, the expected cost-effectiveness of the project:

The project is designed to be cost-effective in several ways. Firstly, the project approach is formulated to ensure that the revised NBSAP becomes a relevant policy instrument, which will be effectively integrated into development plans, development finance, as well as plans, strategies and policies aimed at managing climate risk; and that convention reporting and the CHM frameworks are produced in a cost-effective manner and with technical quality. Secondly, the project closely builds on and is aligned with the government’s past, on-going and planned activities related to the CBD, including GEF financed biodiversity projects. This includes the Biodiversity Policy formulation, enactment of the new Wildlife Conservation Act, establishment of the National Biodiversity Centre and Biodiversity Trust Fund, development of the Central Forest Spine Master Plan, strengthening of the PA system, as well as the planned EU/UNDP supported biodiversity financing project. Thirdly, with the strategic and additional investment by the GEF and the substantial co-financing from the Government and UNDP, the project aims to generate synergetic impact to significantly further the biodiversity agenda in the country, by producing practical tools for NBSAP mainstreaming and implementation, including the TEEB Malaysia version, ecosystem-based adaptation planning, and mainstreaming biodiversity into key sectors. Also, the project’s approach and emphasis on national capacity building and biodiversity financing will enhance the sustainability of the project impacts beyond the project timeframe. With its fast growing economy and correlating pressure on biodiversity in the country, it is critical for Malaysia to take necessary and bold actions immediately to safeguard its biodiversity resources and ecosystem functions. Furthermore, the project is considered cost-effective in that it seeks to produce the new generation of NBSAP which will help set a regional standard of excellence by creating a national road map for achieving the Aichi Target. This is expected to generate positive influence in biodiversity planning in the Asia Pacific Region. Other options have been considered, e.g. sub-contracting an NGO to assist in NBSAP update as an entire ‘package’ of services to be rendered. High costs in fees from service providers would make such option less cost effective, coupled with the risk of biasing a document such as the NBSAP, which is supposed to reflect broad societal views on the national strategy for biodiversity. The project adopts the least-cost means of achieving the project’s objectives and follows the activity norms and cost benchmarks defined by GEF guidelines. It will be built upon the strong foundation of the previous developed NBSAP, Capacity Assessments and National Reports.

E. describe the budgeted M&E Plan:

Type of M&E activity; Responsible Parties; Budget US$ Excluding project team staff time; Time frame. Inception Workshop; Project Coordinator UNDP CO UNDP GEF; $10,000; Within first two months of project start up. Inception Report; Project Team UNDP CO; None; Immediately following IW. Measurement of Means of Verification for Project Purpose Indicators, Project Progress and Performance (measured on an annual basis); Oversight by Project Manager Project team; To be finalized during the inception phase and determined as part of the Annual Work Plan's preparation.; Annually prior to ARR/PIR and to the definition of annual work plans. Simplified Biodiversity Enabling Activities Annual Project Review / Project Implementation Report (APR/PIR); Project Team UNDP-CO UNDP-GEF; None; Annually. Quarterly progress reports; Project team; None; Quarterly. CDRs; Project Manager; None; Quarterly. Issues Log; Project Manager UNDP CO Programme Staff; None; Quarterly. Risks Log; Project Manager UNDP CO Programme Staff; None; Quarterly. Lessons Learned Log; Project Manager UNDP CO Programme Staff; None; Quarterly. Terminal Report; Project team UNDP-CO Local consultant; None; At least one month before the end of the project. Lessons learned; Project team UNDP-GEF Regional Coordinating Unit (suggested formats for documenting best practices, etc.); To be determined as part of the Annual Work Plan's preparation.; Yearly. Audit; UNDP-CO Project team; $2,000 in total To be included in the CO audit plan.; Yearly. TOTAL indicative COST* Excluding project team staff time and UNDP staff and travel expenses; US$ 12,000.

F. Explain the Deviations from typical Cost Ranges (where applicable):

As described earlier, Malaysia is a major storehouse of biodiversity, ranking as one of the World’s 17 megadiverse countries. The flora of Malaysia is exceedingly rich, comprising some15,000 species of flowering plants, and more than 500 species of ferns and their relatives. Many of these are found nowhere else in the world, with well over 26% of the tree species being endemic. The lowland dipterocarp forest is particularly rich in species diversity. The country’s total landmass is 329,847 sq km, separated by the South China Sea into two similarly sized regions, Peninsular Malaysia and Malaysian Borneo. These geographic features has given rise to considerable differences across the country’s territory. They also pose logistical challenges from a project implementation perspective. Furthermore, Malaysia is a federal and multi-ethnic country with 13 states including the two East Malaysian states of Sabah and Sarawak on Borneo Island which have a great degree of autonomy. These states are thoroughly responsible for land uses and natural resource management and thus play a vital role in the development and implementation of the NBSAP. Without their full participation and buy-in, the NBSAP is unlikely to be implemented. As the last NBSAP was formulated in 1998, the country will need to produce a totally new NBSAP which incorporates a number of issues that have emerged since that time. The outdated NBSAP does not include a plan for integrating the value of biodiversity into national or sub-national development and poverty reduction strategies and planning processes. This has hindered its implementation as scarce resources are channeled to those priorities identified in planning processes and that have clear ownership of the state governments. In addition the existing NBSAP does not include all the Aichi Targets and stocktaking and capacity assessments for these needs to be undertaken. Other targets require updating to reflect sub-national current conditions, challenges, potentials and priorities of different states. In consequence a pre-requisite to determining national targets for the updated NBSAP is to first undertake sub-national stocktaking and capacity assessment; and second establish sub-national targets and the priorities that capture the diverse natural characteristics and socio-economic differences across the country’s main regional and constituent states. Only then can national priorities be defined that can be realistically implemented through the Federal and State governing system. If the NBSAP does not reflect these realities there will be no ownership of the NBSAP; specific opportunities will be lost and the implementation of this new NBSAP will suffer. This is no easy undertaking and the proposal presented herein has been designed and costed to ensure that this becomes a reality. The following additional products will need to be delivered that are not normally associated with smaller; less diverse and non Federal countries which do not depend so heavily on State Governments and a multiplicity of institutions for implementation: - Local TEEB (The Economics of Ecosystems and Biodiversity) Study: Assessing and capturing value in ecosystems’ goods and services in Malaysia; - Strategy for strengthening the PoWPA Action Plan by integrating key Aichi Targets into national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA); - Strategy for exploring and costing options for promoting ecosystem-based adaptation and resilience to climate change in Malaysia, including mapping species’ and ecosystems’ distributions in scenarios of climatic variability and change as an aid to the analysis of ecosystem vulnerability and resilience; - Strategy for mainstreaming biodiversity into key sectors, and developing opportunities for conservation and sustainable use. As a result the overall costs of the NBSAP update are greater than in many countries. In order to ensure that national priorities and requisites are adequately addressed and to produce the additional products which facilitate actual implementation of the NBSAP, a substantial amount of co-financing is budgeted for to complement the US$ 220,000 requested from the focal area set aside. This clearly shows the government’s commitments and sense of urgency for producing the new NBSAP as well as a set of practical tools for NBSAP mainstreaming and implementation.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the country endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Dr. Lian Kok Fei | Undersecretary, Climate Change and Environmental Management Division | Ministry of Natural Resources and Environment | February 16, 2012 |

B. Convention Participation*

| Convention | Date of Ratification/ Accession (mm/dd/yy) | National Focal Point |
| --- | --- | --- |
| UNCBD | 24/06/1994 | Mdm. Zurinah binti Pawanteh |

C.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Biodiversity Enabling Activity approval.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec, UNDP/GEF Executive Coordinator |  | February 27, 2012 | Midori Paxton, Regional Technical Advisor – Ecosystems and Biodiversity, UNDP | +66-818787510 | midori.paxton@ undp.org |

Annex A. consultants to be hired for the Enabling Activity (including consultants financed by GEF and co-financing)

*Shaded items indicats consultants financed entirely by co-financing.

| Position Titles | $ / Person Week | Estimated Person Weeks | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management |  |  |  |
| Local |  |  |  |
| Biodiversity Enabling Activity (BD EA) Project Manager – managerial tasks (Not financed by GEF, but with government co-financing. This co-financing has been estimated at $72K throughout the project) | 1,250 | 57.6 | To undertake the general administrative requirements of the project, including those related to project management and funding. The key tasks are: - Ensure that project Objective, Outcomes, Outputs and Activities are executed in a timely and appropriate manner. - Develop annual work plans and budgets, and submit these to the Steering Committee and to the UNDP Country Office for approval. - Develop TORs for Consultants for technical services, consultants, experts, and specifications of materials as required by the project, in consultation with the Project Director/UNDP. - Facilitate, guide and monitor the work of consultants, and approve their deliverables in association with the Project Committee. - Organize and assist in project related activities, where required. These may include planning for meetings, local and national workshops, consultations, trips, and other project related activities. - Establish and maintain linkages with national and international organizations and persons which/who can be of assistance to the objectives of the Project. - Prepare Inception Report within first three months of project start up. - Prepare Final Report two months before the project closure. - Provide timely reporting of project status as required by the Project Committee and the UNDP. - Maintain records of Project Committee meetings, decisions, actions etc. - Coordinate with other initiatives and programs whose outcomes and outputs are relevant to this project’s objectives. - Any other duties assigned by the Project Committee that have direct relevance to the project. Selection criteria: should have a Master’s degree in environmental/natural resources management or related field with a minimum of 5 years management experience at a senior level. Knowledge and understanding of the relevant UN Convention, environmental issues in Malaysia, good leadership, coordination, communication, and facilitation skills are essential. *The estimated time for project management and oversight is 40%. Successful candidate will also provide technical expertise in the stakeholder consultation and update of NBSAP as detailed below. |
| Project Assistant (Not financed by GEF, but with government co-financing. This co-financing has been estimated at $43.2K throughout the project) | 288.46 | 156 | To assist BD EA Project Manager in the general project administration: - Provide administrative and logistic support to the project team. - Manage schedules and project implementation in accordance of the annual work plan. - Undertake secretariat services to specific project activities. - Provide financial and limited backup support to the project team that includes consultants. - Execute financial and budgetary tasks and related activities. Selection criteria: should have a tertiary education in secretarial science degree/diploma or related professional qualifications with a minimum of 3 years experience. Project management and financial management; computer skills are essential. Prior experience in UNDP procedures and practices. |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| BD EA Project Manager (Not financed by GEF, but with government co-financing) | 1,250 | 98.4 | To lead the overall process of the stocktaking, stakeholder consultation, national target setting and the development of the NBSAP and be responsible for the timely drafting and finalization of the NBSAP. The key tasks are: - Serve as team leader for other consultants involved in the NBSAP and be overall responsible for the timely drafting of the document for submission to the CBD Secretariat; strictly adhering to the deadlines agreed to; and ensuring quality control. - Ensure that the inception meeting results in a clear roadmap on the scope of services and project tasks to be accomplished under the guidance of the NBSAP Principal Advisor, key national implementing partners and the UNDP technical staff. - Submit draft and revised versions of all studies and reports of the NBSAP activities to NBSAP Principal Advisor, key national implementing partners and UNDP technical staff, per reporting timelines agreed on or before the inception meeting. - Play a pivotal role in developing a work plan and coordinating the input and outputs of all consultants, as well as overseeing the technical quality of deliverables. - Ensure that all Climate Change-related issues highlighted in the second National Communication to the UNFCCC that affect Biodiversity (Adaptation) or affected by Biodiversity (Mitigation) are integrated and addressed in the final NBSAP. - Ensure that all lessons learnt in the mainstreaming of biodiversity into the production sectors (this includes measures against Invasive Alien Species) are incorporated into the NBSAP. - Identify implementation partners for the undertaking of the various activities and develop an overall implementation plan. - Lead meetings of the Technical Working Groups, sharing this task with the National NBSAP Consultant. - Submit a final draft to the NPD and Technical Working Groups, incorporating stakeholder inputs and guidance provided. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Malaysia - Biodiversity Targets for Malaysia: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 1: Study on Ecosystem Valuation in Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Malaysia - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP Qualifications and experience: Selection criteria: should have a MA or MSc in Natural Resources Management, with particular background in Biodiversity Conservation. Minimum 10 years’ experience in national and international natural resources projects in multi-stakeholder settings, in particular concerning Biodiversity Conservation. Prior GEF project experience. |
| National NBSAP Consultant (Partially financed by GEF: US$40,000 Gov: US$40,000) | 2,000 | 40 | To take stock of the success of the existing NBSAP and develop national targets in line with the global Aichi Targets. The key tasks are: - Take stock of existing plans, policies and practices in Malaysia that result in biodiversity conservation or loss. - Identify the root causes of biodiversity loss in Malaysia by first identifying the threat and then the drivers behind the threats. - Identify the key barriers and challenges in the policy environment to effective biodiversity conservation/sustainable use. - Based on existing studies and analyses, identify key gaps in the existing NBSAP. - Identify the means to overcome existing barriers and challenges. - Develop a stakeholder consultation and participation plan that will ensure that the NBSAP development process is participatory, increasing the likelihood of successful implementation of the NBSAP. - Lead meetings of the Technical Working Groups, sharing this task with the BD EA Project Manager. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Malaysia - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 1: Study on Ecosystem Valuation in Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Malaysia - Sub-product 4: Development of an updated PoWPA Action Plan to achieve key Aichi Targets. Selection criteria: should have an advanced university degree in environmental/natural resources management, public policy or related field with a minimum of 10 years technical experience at a senior level. Proven track record of drafting relevant materials in the biodiversity/ecosystem based adaptation areas (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy and technical quality. Knowledge and understanding of the relevant UN Convention, the existing NBSAP and environmental issues in Malaysia are essential. |
| Policy, Institutional and Capacity Development Specialist (Not financed by GEF, but with UNDP co-financing) | 2,000 | 30 | The consultant will be responsible for the outputs under Components 1, 2 and 3. The key tasks are: - Take stock of and analyse existing policies, legal and institutional framework and operating practices. - Prepare a report for stakeholder consultations at national and sub-national level. - Recommend priority actions to strengthen existing policies, legal and institutional framework for biodiversity. - Conduct capacity needs assessment including technology needs. - Prepare an updated capacity action plan for biodiversity Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Malaysia - Biodiversity Targets for Malaysia that are aligned with the national and sub-national contexts: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP Selection criteria: should have a Master’s degree (MSc) in public policy or administration, with a specialization in environmental policy. At least 8 years of experience in policy impact study and capacity assessment. Knowledge and understanding of policies, legislation and institutions in Malaysia are essential |
| Environmental Economist (Partially financed by GEF: US$10,000 Gov: US$78,000) | 2,000 | 44 | The consultant will be responsible for carrying out the tasks under two sub-activities: i) Assessing and integrating ecosystem services through economic valuation (under Component 2), and ii) the mobilisation of financing for the implementation of the Action Plan of the NBSAP and in raising awareness among key stakeholders on the NBSAP (under Component 3). The tasks foreseen will be carried out in close collaboration with the Economic Planning Unit, Ministry of Natural Resources and Environment, and Ministry of Finance. Key tasks will include: - Identify and assess the full range of values of key ecosystem services within Malaysia, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the national TEEB valuation results, the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g. water, carbon, soil formation, wildlife refugia etc.), and existing global and regional maps and overlays of key ecosystem services. - Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use. - Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. - Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. - Identify priority biodiversity investment needs and opportunities based on the NBSAP - Analyse internal sources of finance for action in the NBSAP including i) the national budget cycle and the allocation to public administrations (ministries), ii) the budget of local governments, iii) national funds to support local development, and iv) fiscal and economic instruments. - Analyse external sources of finance for actions in the NBSAP including i) bilateral sources, ii) multilateral sources, iii) regional development banks, iv) international foundations and non-governmental organisations (NGOs) - Analyse innovative sources of finance for actions in the NBSAP, especially fiscal measures related to: i) tourism and infrastructure development (to encourage the mainstreaming of biodiversity into their operations, ii) bank loans for investment projects. NBSAP Integrated Financing Action Plan summarising concrete activities required to mobilise BD finance for the 10-year period of the implementation of the NBSAP. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Malaysia - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 1: Study on Ecosystem Valuation in Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Malaysia - Sub-product 4: Development of an updated PoWPA Action Plan to achieve key Aichi Targets. - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP |
| Climate Change Expert (Not financed by GEF, but with government co-financing) | 2,000 | 24 | The consultant will be responsible for the writing of a report on climate change aspects in Malaysia with the view of integrating these issues into the Malaysian NBSAP. Key tasks will include: - Identify areas important for carbon sequestration and advice on protection and management strategies. - Update the country’s ecological gap assessment to include predicted future distribution of biodiversity under climate change scenarios. - Assess the impact of climate change on the functioning of important ecosystems services in Malaysia. - Identify areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors. - Identify areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation. Contribution to the following deliverables: - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Malaysia Selection criteria: should have an advanced degree (MSc) in environmental or natural science, with a specialization in ecosystem based climate change adaptation and/or mitigation. Experience in ecosystem based approach, ecosystem based adaptation to climate change and climate change adaptation in biological/ecological services. |
| Biodiversity/Protected Area Expert (Not financed by GEF, but with government co-financing) | 2,000 | 32 | The consultant will be responsible for updating Malaysia’s Programme of Work for Protected Area (PoWPA): Key tasks will include: - Conduct in-depth study of the threats to biodiversity and root cause to biodiversity loss. - Provide technical advice on updating the country’s ecological gap assessment to include predicted future distribution of biodiversity under climate change scenarios. - Review existing PoWPA. - Prepare an updated and comprehensive PoWPA. Contribution to the following deliverables: - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 4: Development of an updated PoWPA Action Plan to achieve key Aichi Targets. |
| Communication Specialist | 1,000 | 12 | The consultant will be responsible for establishing mechanisms for dissemination of information on NBSAP and developing a communication and dissemination strategy for NBSAP implementation. Key tasks will include: - Identify key stakeholders and assist in forming focus group that comprise of various government institutions, private sector, NGO and media. - Develop visual and other information and training materials for raising awareness. - Develop a communication and dissemination strategy that employs effective tools for creating awareness and understanding of the NBSAP throughout the country particularly the state and local governments, local communities and NGOs. - Provide advice on the updating and enhancement of CHM Contribution to the following deliverables: - Second National Biodiversity Strategy and Action Plan for Malaysia - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP |
| International |  |  |  |
| International Climate Change Specialist | 3,000 | 8 | The consultant will be responsible for the writing of a report on climate change aspects in Malaysia with the view of integrating these issues into the Malaysian NBSAP. The input coming from the international Specialist will need to mastery of state-of-the art knowledge available on the matter. The consultant will work closely with the National Climate Change Expert. Key tasks will include: - Identify areas important for carbon sequestration and advice on protection and management strategies. - Update the country’s ecological gap assessment to include future distribution to include predicted future distribution of biodiversity under climate change scenarios. - Assess the impact of climate change on the functioning of important ecosystems services in Malaysia. - Identify areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors. - Identify areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation. Contribution to the following deliverables: - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Malaysia Selection criteria: should have an advanced degree (MSc) in environmental or natural science, with a specialization in ecosystem based climate change adaptation and/or mitigation. Experience in ecosystem based approach, ecosystem based adaptation to climate change and climate change adaptation in biological/ecological services. |
| Environmental Economist | 3,000 | 10 | The consultant will be responsible for carrying out the tasks under Component 3: the mobilisation of financing for the implementation of the Action Plan of the NBSAP and in raising awareness among key stakeholders on the NBSAP. The tasks foreseen will be carried in close collaboration with the Economic Planning Unit, Ministry of Natural Resources and Environment, and Ministry of Finance. Key tasks will include: - Develop the methodologies for the national TEEB valuation in collaboration with local consultant(s). - Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service) in Malaysia based on regional and global studies of the value of biodiversity and ecosystems, including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. - Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. - Identify priority biodiversity investment needs and opportunities based on the NBSAP. - Analyse internal sources of finance for action in the NBSAP including i) the national budget cycle and the allocation to public administrations (ministries), ii) the budget of local governments, iii) national funds to support local development, and iv) fiscal and economic instruments. - Analyse external sources of finance for actions in the NBSAP including i) bilateral sources, ii) multilateral sources, iii) regional development banks, iv) international foundations and non-governmental organisations (NGOs) - Analyse innovative sources of finance for actions in the NBSAP, especially fiscal measures related to: i) tourism and infrastructure development (to encourage the mainstreaming of biodiversity into their operations, ii) bank loans for investment projects. NBSAP Integrated Financing Action Plan summarising concrete activities required to mobilise BD finance for the 10-year period of the implementation of the NBSAP. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Malaysia - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP |
| Biodiversity Finance Specialist (Not financed by GEF, but with UNDP co-financing) | 3,000 | 20 | The consultant will be responsible for carrying out the tasks under Component 3: the mobilisation of financing for the implementation of the Action Plan of the NBSAP and in raising awareness among key stakeholders on the NBSAP. The tasks foreseen will be carried in close collaboration with the Economic Planning Unit, Ministry of Natural Resources and Environment, and Ministry of Finance. Key tasks will include: - Identify priority biodiversity investment needs and opportunities based on the NBSAP. - Analyse internal sources of finance for action in the NBSAP including i) the national budget cycle and the allocation to public administrations (ministries), ii) the budget of local governments, iii) national funds to support local development, and iv) fiscal and economic instruments. - Analyse external sources of finance for actions in the NBSAP including i) bilateral sources, ii) multilateral sources, iii) regional development banks, iv) international foundations and non-governmental organisations (NGOs) - Analyse innovative sources of finance for actions in the NBSAP, especially fiscal measures related to: i) tourism and infrastructure development (to encourage the mainstreaming of biodiversity into their operations, ii) bank loans for investment projects. NBSAP Integrated Financing Action Plan summarising concrete activities required to mobilise BD finance for the 10-year period of the implementation of the NBSAP. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Malaysia - Second National Biodiversity Strategy and Action Plan for Malaysia - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Malaysia - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP |

Annex B. Operational Guidance to Focal Area Enabling Activities

Biodiversity

- GEF/C.7/Inf.11, June 30, 1997, Revised Operational Criteria for Enabling Activities

- GEF/C.14/11, December 1999, An Interim Assessment of Biodiversity Enabling Activities

- October 2000, Revised Guidelines for Additional Funding of Biodiversity Enabling Activities (Expedited Procedures)

- GEF5 Focal Area Strategy (download)

Annex C. SCHEDULE

| Comp | Modules | Guiding activities under each module | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1 | I. Preparation | 1. Rapid stocktaking and review of relevant plans, policies and reports | X | X |  |  |  |  |  |  |  |  |  |  |
|  |  | 2. Identification of stakeholders; consultations and awareness | X | X |  |  |  |  |  |  |  |  |  |  |
|  |  | 3. Rapid assessment of the causes and consequences of biodiversity loss highlighting the value of biodiversity and ecosystem services and their contribution to human well-being |  | X | X |  |  |  |  |  |  |  |  |  |
|  | II Setting regional targets, principles, & main priorities of the strategy | 4. Setting national targets, principles, & main priorities of the strategy though national and sub-national consultations |  | X | X | X |  |  |  |  |  |  |  |  |
| 2 | III. Strategy and action plan updating | 5. Developing the strategy and actions to implement the agreed targets though national and sub-national consultations |  |  |  |  | X | X |  |  |  |  |  |  |
|  |  | 6. Submit updated NBSAP to National Biodiversity Council and Cabinet for approval; |  |  |  |  |  |  | X |  |  |  |  |  |
|  |  | 7. Application of the NBSAP to sub-national entities through sub-national and local consultations |  |  |  |  |  |  | X | X | X | X |  |  |
|  |  | 8. Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations |  |  |  |  |  |  | X | X | X |  |  |  |
| 3 | IV. Development of Implementation plans and related activities | 9. Development of a plan for capacity development for NBSAP implementation. |  |  |  |  |  |  | X | X | X | X |  |  |
|  |  | 10. Technology needs assessment |  |  |  |  |  |  |  |  | X | X |  |  |
|  |  | 11. Development of a communication and outreach strategy for the NBSAP, and outreach activities to disseminate NBSAP |  |  |  |  |  |  | X | X | X | X | X | X |
|  |  | 12. Development of a plan for resource mobilization for NBSAP implementation |  |  |  |  |  |  | X | X | X | X |  |  |
|  | V. Institutional, monitoring, reporting and exchange | 13. Establishment/strengthening of national coordination structures |  |  |  |  | X | X | X | X | X | X | X | X |
|  |  | 14 CHM upgrading/enhancement. |  | X | X | X | X | X | X | X | X | X | X | X |
|  |  | 15. Development of indicators and monitoring approach |  | X | X | X | X | X | X | X | X | X | X | X |
|  |  | 16. Fifth national report |  |  |  |  |  |  |  |  | X | X |  |  |

Annex D. Total Budget And Work plan (including co-financing)

| GEF Component (Outcome) /Atlas Activity |  | Impl. Agent | Fund ID | Donor Name | ERP / ATLAS Budget Code | Atlas Budget Description |  | TOTAL Amount (USD) |  | Amount Year 1 (USD) |  | Amount Year 2 (USD) |  | Amount Year 3 (USD) |  | Budget Notes |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comp 1. Stocktaking and national target setting |  | NIM | 62000 | GEF-10003 | 71300 | Local Consultants |  | 20,000 |  | 20,000 |  | 0 |  | 0 |  | a |  |
|  |  | NIM | 62000 | GEF-10003 | 71600 | Travel |  | 5,000 |  | 5,000 |  | 0 |  | 0 |  | b |  |
|  |  | NIM | 62000 | GEF-10003 | 72400 | Communic & Audio Visual Equip |  | 1,000 |  | 1,000 |  | 0 |  | 0 |  | c |  |
|  |  | NIM | 62000 | GEF-10003 | 75700 | Training, Workshops & Confer |  | 6,000 |  | 6,000 |  | 0 |  | 0 |  | d |  |
|  |  | GEF Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  |  | 32,000 |  | 32,000 |  | 0 |  | 0 |  |  |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71300 | Local Consultants |  | 20,000 |  | 20,000 |  | 0 |  | 0 |  | e |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71600 | Travel |  | 3,000 |  | 3,000 |  | 0 |  | 0 |  | b |  |
|  |  | TRAC Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  |  | 23,000 |  | 23,000 |  | 0 |  | 0 |  |  |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 36,000 |  | 12,000 |  | 12,000 |  | 12,000 |  | f |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 32,000 |  | 32,000 |  | 0 |  | 0 |  | g |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 75700 | Training, Workshops & Confer |  | 2,000 |  | 2,000 |  | 0 |  | 0 |  | d |  |
|  |  | Gov Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  |  | 70,000 |  | 46,000 |  | 12,000 |  | 12,000 |  |  |  |
| TOTAL ACTIVITY 1 (Comp 1) |  |  |  |  |  |  |  | 125,000 |  | 101,000 |  | 12,000 |  | 12,000 |  |  |  |
| Comp 2. NBSAP update |  | NIM | 62000 | GEF-10003 | 71200 | International Consultants |  | 15,000 |  | 0 |  | 15,000 |  | 0 |  | h |  |
|  |  | NIM | 62000 | GEF-10003 | 71200 | International Consultants |  | 24,000 |  | 0 |  | 24,000 |  | 0 |  | i |  |
|  |  | NIM | 62000 | GEF-10003 | 71300 | Local Consultants |  | 10,000 |  | 0 |  | 10,000 |  | 0 |  | j |  |
|  |  | NIM | 62000 | GEF-10003 | 71600 | Travel |  | 25,000 |  | 0 |  | 25,000 |  | 0 |  | k |  |
|  |  | NIM | 62000 | GEF-10003 | 72400 | Communic & Audio Visual Equip |  | 1,000 |  | 0 |  | 1,000 |  | 0 |  | c |  |
|  |  | NIM | 62000 | GEF-10003 | 75700 | Training, Workshops & Confer |  | 10,000 |  | 0 |  | 10,000 |  | 0 |  | l |  |
|  |  | GEF Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  |  | 85,000 |  | 0 |  | 85,000 |  | 0 |  |  |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71200 | International Consultants |  | 36,000 |  | 0 |  | 18,000 |  | 18,000 |  | m |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71300 | Local Consultants |  | 78,000 |  | 0 |  | 50,000 |  | 28,000 |  | j |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71300 | Local Consultants |  | 20,000 |  | 0 |  | 20,000 |  | 0 |  | e |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71600 | Travel |  | 20,000 |  | 0 |  | 10,000 |  | 10,000 |  | k |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 72800 | Information Technology Equipmt |  | 3,000 |  | 0 |  | 3,000 |  | 0 |  | n |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 74200 | Audio Visual&Print Prod Costs |  | 15,000 |  | 0 |  | 0 |  | 15,000 |  | o |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 75700 | Training, Workshops & Confer |  | 25,000 |  | 0 |  | 15,000 |  | 10,000 |  | l |  |
|  |  | TRAC Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  |  | 197,000 |  | 0 |  | 116,000 |  | 81,000 |  |  |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 36,000 |  | 12,000 |  | 12,000 |  | 12,000 |  | f |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 20,000 |  | 0 |  | 20,000 |  | 0 |  | a |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 32,000 |  | 0 |  | 32,000 |  | 0 |  | g |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 48,000 |  | 0 |  | 32,000 |  | 16,000 |  | p |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 72800 | Information Technology Equipmt |  | 3,000 |  | 0 |  | 3,000 |  | 0 |  | n |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 75700 | Training, Workshops & Confer |  | 10,000 |  | 0 |  | 10,000 |  | 0 |  | l |  |
|  |  | Gov Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  |  | 149,000 |  | 12,000 |  | 109,000 |  | 28,000 |  |  |  |
| TOTAL ACTIVITY 2 (Comp 2) |  |  |  |  |  |  |  | 431,000 |  | 12,000 |  | 310,000 |  | 109,000 |  |  |  |
| Comp 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms |  | NIM | 62000 | GEF-10003 | 71200 | International Consultants |  | 15,000 |  | 0 |  | 0 |  | 15,000 |  | h |  |
|  |  | NIM | 62000 | GEF-10003 | 71300 | Local Consultants |  | 20,000 |  | 0 |  | 0 |  | 20,000 |  | a |  |
|  |  | NIM | 62000 | GEF-10003 | 71300 | Local Consultants |  | 12,000 |  | 0 |  | 0 |  | 12,000 |  | q |  |
|  |  | NIM | 62000 | GEF-10003 | 71600 | Travel |  | 10,000 |  | 0 |  | 0 |  | 10,000 |  | k |  |
|  |  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies |  | 9,000 |  | 3,000 |  | 3,000 |  | 3,000 |  | r |  |
|  |  | NIM | 62000 | GEF-10003 | 72400 | Communic & Audio Visual Equip |  | 1,000 |  | 0 |  | 0 |  | 1,000 |  | c |  |
|  |  | NIM | 62000 | GEF-10003 | 72200 | Equipment and Furniture |  | 5,000 |  | 0 |  | 0 |  | 5,000 |  | s |  |
|  |  | NIM | 62000 | GEF-10003 | 72800 | Information Technology Equipmt |  | 5,000 |  | 0 |  | 0 |  | 5,000 |  | t |  |
|  |  | NIM | 62000 | GEF-10003 | 74200 | Audio Visual&Print Prod Costs |  | 5,000 |  | 0 |  | 0 |  | 5,000 |  | u |  |
|  |  | NIM | 62000 | GEF-10003 | 75700 | Training, Workshops & Confer |  | 10,000 |  | 0 |  | 0 |  | 10,000 |  | v |  |
|  |  | GEF Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  |  | 92,000 |  | 3,000 |  | 3,000 |  | 86,000 |  |  |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71200 | International Consultants |  | 24,000 |  | 0 |  | 0 |  | 24,000 |  | m |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71300 | Local Consultants |  | 20,000 |  | 0 |  | 0 |  | 20,000 |  | e |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71600 | Travel |  | 10,000 |  | 0 |  | 5,000 |  | 5,000 |  | w |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 75700 | Training, Workshops & Confer |  | 6,000 |  | 0 |  | 0 |  | 6,000 |  | v |  |
|  |  | TRAC Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  |  | 60,000 |  | 0 |  | 5,000 |  | 55,000 |  |  |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 36,000 |  | 12,000 |  | 12,000 |  | 12,000 |  | f |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71300 | Local Consultants |  | 20,000 |  | 0 |  | 0 |  | 20,000 |  | a |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71600 | Travel |  | 6,000 |  | 2,000 |  | 2,000 |  | 2,000 |  | x |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 74100 | Professional Services |  | 5,000 |  | 0 |  | 0 |  | 5,000 |  | y |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 74200 | Audio Visual&Print Prod Costs |  | 10,000 |  | 0 |  | 0 |  | 10,000 |  | u |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 75700 | Training, Workshops & Confer |  | 10,000 |  | 0 |  | 0 |  | 10,000 |  | v |  |
|  |  | Gov Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  |  | 87,000 |  | 14,000 |  | 14,000 |  | 59,000 |  |  |  |
| TOTAL ACTIVITY 3 (Comp 3) |  |  |  |  |  |  |  | 239,000 |  | 17,000 |  | 22,000 |  | 200,000 |  |  |  |
| Project Mgt |  | NIM | 62000 | GEF-10003 | 71600 | Travel |  | 6,500 |  | 2,500 |  | 2,000 |  | 2,000 |  | y |  |
|  |  | NIM | 62000 | GEF-10003 | 72400 | Communic & Audio Visual Equip |  | 1,500 |  | 500 |  | 500 |  | 500 |  | z |  |
|  |  | NIM | 62000 | GEF-10003 | 72800 | Information Technology Equipmt |  | 3,000 |  | 3,000 |  | 0 |  | 0 |  | aa |  |
|  |  | GEF Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  |  | 11,000 |  | 6,000 |  | 2,500 |  | 2,500 |  |  |  |
|  |  | NIM | 04000 | UNDP TRAC - 00012 | 71600 | Travel |  | 20,000 |  | 6,500 |  | 6,500 |  | 7,000 |  | ab |  |
|  |  | TRAC Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  |  | 20,000 |  | 6,500 |  | 6,500 |  | 7,000 |  |  |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71400 | Contractual Services - Individ |  | 117,000 |  | 39,000 |  | 39,000 |  | 39,000 |  | f |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 71600 | Travel |  | 10,000 |  | 5,000 |  | 0 |  | 5,000 |  | ac |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 72500 | Supplies |  | 3,000 |  | 1,000 |  | 1,000 |  | 1,000 |  | ad |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 72700 | Hospitality/Catering |  | 3,000 |  | 1,000 |  | 1,000 |  | 1,000 |  | ae |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 72800 | Information Technology Equipmt |  | 5,000 |  | 5,000 |  | 0 |  | 0 |  | af |  |
|  |  | NIM | 11888 | Govt CS - 00157 | 74200 | Audio Visual&Print Prod Costs |  | 6,000 |  | 3,000 |  | 0 |  | 3,000 |  | ag |  |
|  |  | Gov Subtotal Atlas Activity 4 (Comp 4) |  |  |  |  |  | 144,000 |  | 54,000 |  | 41,000 |  | 49,000 |  |  |  |
| TOTAL ACTIVITY 4 (Proj Mgt) |  |  |  |  |  |  |  | 175,000 |  | 66,500 |  | 50,000 |  | 58,500 |  |  |  |
|  |  | SUB-TOTAL GEF |  |  |  |  |  | 220,000 |  | 41,000 |  | 90,500 |  | 88,500 |  |  |  |
|  |  | SUB-TOTAL UNDP TRAC |  |  |  |  |  | 300,000 |  | 29,500 |  | 127,000 |  | 143,000 |  |  |  |
|  |  | SUB-TOTAL GOVERNMENT COST-SHARING |  |  |  |  |  | 450,000 |  | 126,000 |  | 176,000 |  | 148,000 |  |  |  |
|  |  | TOTAL (in cash committed in Atlas) |  |  |  |  |  | 970,000 |  | 196,500 |  | 394,000 |  | 379,500 |  |  |  |
|  |  | Additional GOVERNMENT FUND |  |  |  |  |  | 350,000 |  | 350,000 |  | 0 |  | 0 |  |  |  |
|  |  | GRAND TOTAL |  |  |  |  |  | 1,320,000 |  | 546,500 |  | 394,000 |  | 379,500 |  |  |  |

| Budget Notes |  |
| --- | --- |
| a | Nat. NBSAP Consultant (lumpsum $80K or approx. 40 weeks) - budget divided equally among the 3 components |
| b | Inter-states flights + DSA + terminal allowances for local consultants. |
| c | Phone bill and internet services - Year 1 |
| d | 1 Inception Workshop and 2 Sub-national Consultation Workshops in Sabah & Sarawak |
| e | Nat. Policy, Institution & Capacity Expert fees (lumpsum $60K / or approx 30 weeks - budget divided equally among the 3 components) |
| f | Project Manager (lumpsum $180K or approx. 156 weeks - 20% each in component 1, 2 & 3 and 40% in project mgt) |
| g | Nat. Biodiversity/PA Expert (lumpsum $64K / or approx. 32 weeks - budget divided equally between components 1 & 2) |
| h | Int. Env Economist Expert fees (lumpsum $30K / or approx. 12 weeks) - 1/2 budgeted for in component 2 and 1/2 in component 3 |
| i | Int. Climate Change Expert fees (lumpsum $24K / or approx. 8 weeks) |
| j | Nat. Env. Economist Expert fees (lumpsum $88K / or approx. 44 weeks) |
| k | International and domestic flights, DSA and terminal expense for international and local consultants |
| l | 6 Consultation Workshops including 2 in the States of Sabah and Sarawak |
| m | Int. Biodiversity Finance Expert fees for BD financing framework (lumpsum $60K / or approx. 18-20 weeks) |
| n | 1 laptop for consultants |
| o | Printing of National TEEB |
| p | Nat. Climate Change Expert fees (lumpsum $48K / or approx. 24 weeks) |
| q | Communication specialist for NBSAP communication and outreach strategy (lumpsum $12K / or approx. 12 weeks) |
| r | Contract with IT company for CHM |
| s | Equipment for CHM |
| t | IT equipment for CHM |
| u | Printing of Final NBSAP and PoWPA |
| v | 3 Validation Workshops - National (Peninsular Malaysia, Sabah & Sarawak) |
| w | International and domestic flight, DSA and terminal expenses for Int. Biodiversity Finance Specialist |
| x | A budget of $2,000 per year is included for travel expenses which is mainly to cover inter-states (especially the states of Sabah & Sarawak) flights and DSA for meetings |
| y | Translation cost of Final NBSAP to Malay language |
| z | Costs of communication, including telephone bills and internet service provision. |
| aa | 1 laptop for BD EA Project Manager |
| ab | A lumpsum budget of $20K for 3 years is included for travel expenses and DSA which is mainly to cover 6 international flights to NBSAP related workshops/conference |
| ac | 15 days DSA and terminal expenses for 1 delegate to COP |
| ad | Miscellaneous supplies (mainly stationary, printer cartridges, etc). |
| ae | 6 PSC meetings, 12 TWC meetings and 6 project meetings in Peninsular Malaysia, States of Sabah and Sarawak |
| af | 1 laptop for Project Assistant, and 1 printer/scanner/copier |
| ag | Printing of Inception Report and Final Project Report |

Exclude in-kind co-financing.

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

www.teebweb.org

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources.

GEF, 2003:  “Strategic Approach to Enhance Capacity Building”.  Global Environment Facility. See also: GEF Evaluation Office, 2006:  “Evaluation of GEF Capacity Development Activities.  Approach Paper”.GEF EO.

GEF Capacity Development Initiative, Global Support Programme for National Capacity Self-Assessment, 2010: “Monitoring Guidelines of Capacity Development in GEF Operations”.

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

The actual submission of the NBSAP to the CBD Secretariat is the responsibility of the government of Malaysia, not UNDP.

Petersen, C and B. Huntley. 2005. Mainstreaming Biodiversity in Productive Landscapes. Working Paper 20. Washington  DC: GEF.

See www.cbd.int/nbsap/training.

For further details of the kinds of issues that will be addressed, see “Protected Areas for the 21st Century.”

Technical Project Manager will be financed by Government of Malaysia.

Project Assistant will be financed by Government of Malaysia.

The Orang Asli are the indigenous peoples of Peninsular Malaysia. They number 150,000, representing a mere 0.6% of the national population. In Sarawak, the indigenous peoples are collectively called Orang Ulu or Dayak. They constitute around 50% of Sarawak’s population of 2.5 million people. In Sabah, the 39 different indigenous ethnic groups are called natives or Anak Negeri. At present, they account for about 47.4% of the total population of Sabah, a steep drop from the 60% estimated in 2000. (Refer to www.iwgia.org/regions/asia/malaysia).

See e.g. www.cbd.int/traditional.

Additional government co-financing from the 10th Malaysia Plan amounting to US$350,000 that have been committed for (1) review of National Policy on Biological Diversity, (2) CHM and (3) Communication, Education and Public Awareness in the year of 2012.