{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Figure4 GEF"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Figure4 GEF","index":0,"n_rows":132,"n_cols":63,"rows_kept":132,"flags":["formulas_cached_only"]}
["UNDP PIMS 1370 submission Figure 4 - workplan"]
[{"$nulls":30},"PERIOD IN MONTHS"]
["Output","Activity",{"$nulls":5},"Year 1",{"$nulls":12},"Year 2",{"$nulls":11},"Year 3",{"$nulls":11},"Year 4",{"$nulls":10},"Year 5"]
[{"$nulls":3},1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12]
[null,"Objective 1:"]
[null,"Tools for ecological assessment of biodiversity in"]
[null,"tropical forest are improved and disseminated"]
[]
[]
["Output 1.1:","Efficient statistical methods for estimating"]
[null,"biodiversity from small samples"]
[null,"Activity 1.1.1: a) Developing the existing spatial "]
[null,"                          database program at FRIM"]
[null,"                     b) Software maintenance and user support"]
[null,"Activity 1.1.2: Develop a standard data recording system"]
[null,"Activity 1.1.3: Enter existing data on biodiversity in sites"]
[null,"Activity 1.1.4: Building on research undertaken in the  "]
[null,"                     pre-proposal phase of the project "]
[null,"Activity 1.1.5: Develop optimal statistical methods"]
[]
[]
[]
["Output 1.2:","Improved methods for assessing biodiversity  "]
[null,"within and between forest community types"]
[]
[null,"Activity 1.2.1: Develop a statistical procedure"]
[null,"Activity 1.2.2: Develop a computerized system"]
[]
["Output 1.3:","Improved understanding of the impacts of logging"]
[null," on biodiversity in logged forests and in adjacent "]
[null,"or enclosed unlogged forests."]
[]
[null,"Activity 1.3.1: Establish biodiversity assessment plots"]
[null,"                    in 4-5 (VJRs)"]
[null,"Activity 1.3.2: Establish biodiversity assessment plots "]
[null,"                    in PITC concession"]
[null,"Activity 1.3.3: Establish biodiversity assessment plots"]
[null,"                    in Belum Forest Reserve"]
[null,"Activity 1.3.4: Establish biodiversity assessment plots"]
[null,"                    in part of PITC concession"]
[]
["Output 1.4:","Manuals on biodiversity assessment tools"]
[{"$nulls":30},"PERIOD IN MONTH"]
["Output","Activity",{"$nulls":5},"Year 1",{"$nulls":12},"Year 2",{"$nulls":11},"Year 3",{"$nulls":11},"Year 4",{"$nulls":10},"Year 5"]
[{"$nulls":3},1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12]
[null,"Objective 2:"]
[null,"Tools for economic valuation of goods and "]
[null,"services associated with biodiversity in tropical"]
[null,"forest are improved and disseminated"]
[]
["Output 2.1:","Detailed benchmark models that related "]
[null,"economic values associated with biodiversity "]
[null,"to ecological and socioeconomic factors "]
[null,"that influence those values"]
[]
[null,"Activity 2.1.1: Value all nontimber forest product"]
[null,"Activity 2.1.2: Construct a statistical model that predict "]
[null,"                     the impact of changes in land use"]
[null,"Activity 2.1.3: Develop probability-based models for"]
[null,"                  valuing two aspects of genetic resources"]
[null,"Activity 2.1.4: Use economic method to estimate a  "]
[null,"                    system of demand functions that relate                   "]
[null,"                    the number of visits to recreational sites."]
[null,"Activity 2.1.5: Use a choice modeling approach to "]
[null,"                    estimate the value household place"]
[]
["Output 2.2:","Simplified models that relate economic values "]
[null,"associated with biodiversity to ecological and "]
[null,"socioeconomic factors that influence those values"]
[]
[null,"Activity 2.2.1: Use data to develop models that a "]
[null,"                  simpler and less data-intensive than "]
[null,"                  the benchmark models"]
[{"$nulls":30},"PERIOD IN MONTH"]
["Output","Activity",{"$nulls":5},"Year 1",{"$nulls":12},"Year 2",{"$nulls":11},"Year 3",{"$nulls":11},"Year 4",{"$nulls":10},"Year 5"]
[{"$nulls":3},1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12]
[]
[null,"Objective 3:"]
[null,"Tools for integrating ecological and economic "]
[null,"aspects of biodiversity into forest planning "]
[null,"decisions at a landscape level are improved "]
[null,"and disseminated"]
[]
["Output 3.1","Improved models for predicting biodiversity within "]
[null,"and between forest community types, taking into"]
[null,"account logging status and location"]
[]
[null,"Activity 3.1.1: Develop statistical models that relate "]
[null,"           measures of biodiversity and forest community   "]
[null,"                    type to forest characteristic"]
[null,"Activity 3.1.2: Develop a model that predicts the "]
[null,"                    regeneration of forest, and the biodiversity"]
[null,"                    they harbor, after logging"]
[]
["Output 3.2","Improved forest planning model for predicting the "]
[null,"impacts on biodiversity,and associate economic"]
[null,"benefits and cost, of different allocation of forests"]
[null,"in Perak bet. production and protection categories"]
[]
[null,"Activity 3.2.1: Construct a dynamic optimization model"]
[]
[]
[{"$nulls":30},"PERIOD IN MONTH"]
["Output","Activity",{"$nulls":5},"Year 1",{"$nulls":12},"Year 2",{"$nulls":11},"Year 3",{"$nulls":11},"Year 4",{"$nulls":10},"Year 5"]
[{"$nulls":3},1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12]
[null,"Objective 4 :"]
[null,"Enhance the knowledge and capacity on the "]
[null,"assessment of biodiversity and modeling "]
[null,"changes due to human intervention on forest stands"]
[]
["Output 4.1:","Knowledge and Capacity enhanced through "]
[null,"and information disseminated through networking"]
[]
[null,"Activity 4.1.1:  Hands-on training for counterparts and  "]
[null,"                   more formal training for relevant people  "]
[null,"                   from Malaysia, the region and GEF OP3 projects "]
[]
[null,"Activity 4.1.2:   Develop a website on the project status "]
[null,"                   and outputs  that can be assessed by "]
[null,"                   all interested parties"]
[]
[null,"Activity 4.1.3:    Develop scientific exchange programme  "]
[null,"                    through research fellowships"]
[null,"Activity 4.1.4:    Hold annual research seminars for GEF CTAs"]
[]
[null,"Activity 4.1.5: Organise cross project learning visits to PITC"]
[]
[null,"Activity 4.1.6: Organise cross project learning visits to other OP3 project sites"]
[]
[null,"Activity 4.1.7: Develop user-friendly information services"]
[]
[null,"Activity 4.1.8: Ex post evaluation (Year 7)"]