Request for CEO endorsement/Approval

Project Type:

the GEF Trust Fund

Submission Date:      June 18, 2010

| Expected Calendar (mm/dd/yy) |  |
| --- | --- |
| Milestones | Dates |
| Work Program (for FSPs only) | June 2009 |
| Agency Approval date | August 2010 |
| Implementation Start | September 2010 |
| Mid-term Evaluation (if planned) | April 2013 |
| Project Closing Date | August 2015 |

part i:  project Information

GEFSEC Project ID: 3813

gef agency Project ID:

Country(ies): Mexico

Project Title: Integrating trade offs between supply of ecosystem services (ES) and land use options into poverty alleviation efforts and development planning in the Mixteca

GEF Agency(ies): ,

Other Executing partner(s): CONANP, CONAFOR, WWF

GEF Focal Area(s):

GEF-4 Strategic program(s): BD-SP4-Policy

Name of parent program/umbrella project:  N/A

Project framework

Project Objective: Mainstream biodiversity conservation into natural resource use and development planning in the Mixteca Region of Oaxaca integrating ecosystem services (ES) tools and sustainable livelihood options.

| ### Project Components | ### Investment, TA, or STA | Expected Outcomes | ### Expected Outputs | ### GEF Financing |  | Co-Financing |  | Total ($) c=a+ b |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |
| 1. Strengthening the knowledge base on Ecosystem Approach for biodiversity conservation | STA | Outcome 1.1: Stakeholders and decision makers at state and local level have increased access to Ecosystem Services tools applicable to biodiversity conservation and sustainable use Outcome 1.2: Natural Resources, ecosystem services and biodiversity in the project intervention area are assessed, valued and monitored using the new ES tools and knowledge provided through the project | 1. Start-up manual on ES tools and methodologies for decision-makers at the state and local level. 2. Educational materials for methodologies and tools that are adapted to the Oaxacan Mixteca regarding: (1) assessing, (2) valuing ecosystem and (3) monitoring ecosystem services. 3. Supportive audio-visual training materials on ES 4. 80 Trained state and local officials in the project intervention area on the application of ES methodologies and tools. 5. Revised start-up manual on ES and supportive educational materials for use in project replication that takes into account project developments, findings and results 1. Comprehensive data and information on ES in the Oaxacan Mixteca region and in particular in the project intervention area. 2. Detailed studies by ecosystem and priority watersheds assessing and valuing ecosystem services in the Oaxacan Mixteca and in particular in the project intervention area. 3. Geographic information system on the project area and the region’s biodiversity and ecosystem services to support relevant decision-making and investments in the region. 4. On-going programs to assess value and monitor ecosystem services in the Oaxacan Mixteca and in particular in the project intervention area. | 1,300,000 | 65 | 714,000 | 35 | 2,014,000 |
| 2. Supporting biodiversity-friendly policy and program development for land use planning and resource use | TA | Outcome 2.1: Biodiversity and ES considerations are integrated into state and federal support programs and land use planning | 1. Regional inter-institutional working group to support the integration of biodiversity and ES considerations in state and federal support programs and land use planning in the project’s intervention area. 2. Integrating the outcomes of the on-going programs assessing, valuing and monitoring ecosystem services from 1.2 into development policy-making and planning in the Oaxacan Mixteca. 3. Mainstreaming of biodiversity, including ES tools and options into federal and state support programs and land use plans in the Oaxacan Mixteca. 4. Baseline data for the development of comprehensive land use plans applicable to the project intervention area including status assessment of local indigenous knowledge. 5. Environmentally sound land use plans for sustainable development in the project’s intervention area, taking into account the outputs provided by the on-going programs assessing, valuing and monitoring ecosystem services under 1.2. 6. Revised existing land use plans or being developed in the Oaxacan Mixteca to include ecosystem services considerations, taking into account outputs provided by the on-going programs assessing, valuing and monitoring ecosystem services under 1.2. 7. Pilot system of compensation for ecosystem integrity provided by local communities, farmers and other stakeholders. 8. ES indicators for assessing the agricultural projects of SAGARPA and SEDER in the project’s intervention area, particularly as they relate to GAP and good practices for natural resource management. | 1,100,000 | 68 | 506,000 | 32 | 1,606,000 |
| 3. Piloting biodiversity friendly programs on the ground | TA | Outcome 3.1: Local stakeholders apply the ecosystem approach for planning and implementation of productive activities and biodiversity conservation Outcome 3.2: The supply of key Ecosystem Services is secured, improving ecosystem resilience and leading to improved livelihoods Outcome 3.3: Improved land use planning and management practices lead to increased habitat connectivity for globally significant biodiversity within the project intervention area as assessed and monitored under outcome 1.2 | 1. Start-up manual for local stakeholders in the project intervention area on the ecosystem approach for planning and implementing productive activities and biodiversity conservation. 2. Educational materials in each of the following areas that are adapted to the Oaxacan Mixteca: (1) good agricultural practices (GAP) and (2) good practices in natural resource management. 3. Educational materials on the sustainable use of biodiversity, based on the ethno-biological experiences of the local people. 4. Educational materials on the importance of preventing the illegal collection and use of wild biota. 5. Supportive audio-visual training materials on GAP and good practices in natural resource management. 6. Revised start-up manual and supportive educational materials on the ecosystem approach for planning and implementing productive activities and biodiversity conservation for local stakeholders that take into account project developments, findings and results, for use in project replication. 7. Cooperative agreements with rural community planning processes, particularly within the regional natural resources committees and in priority communities in the project’s intervention area, for promoting the integration of biodiversity conservation, ES considerations and sustainable management of agriculture and natural resources. 8. Agreements on priority actions, programs and projects requiring the ecosystem approach through participatory rural community planning exercises. 9. Strategy for mainstreaming alternative tourism based on biodiversity, natural attractions and agro-ecosystems in state and local tourism programs. 10. Alternative tourism strategy for the project’s intervention area based on biological diversity, natural attractions and agroecosystems. 11. Trained and certified ecotourism guides for the Oaxacan Mixteca. 12. Ten micro-watersheds that can serve as models for rural development based on the ES approach and good practices in agriculture and natural resource management. 13. Trained local stakeholders, particularly farmers and local communities, at the 10 pilot demonstration projects in the intervention area on the application of the ecosystem approach for planning and implementing productive activities, natural resource management and biodiversity conservation. 14. Technical assistance to producers for the marketing of goods and services that are the product of GAP and GNRMP, including lama-bordo techniques, exploring opportunities for participating in related certification programs. 1. Degraded lands reforested 2. Degraded lands and ecosystems rehabilitated or in the process of rehabilitation in project intervention areas. 3. Knowledge and information on lama-bordo agricultural systems for soil conservation, improved productivity and the cultivation of native plants traditionally used that contribute to improved family nutrition. 4. Knowledge and information on cultivation of traditionally used native plants that contribute to improved family nutrition particularly through the use of lama-bordo agricultural systems. 5. 5 pilot demonstration projects for (1) rehabilitating lama-bordo systems, (2) testing, monitoring and demonstrating the use of lama-bordo production techniques and their compatibility with sustaining ecosystem services and (3) training local producers in the restoration of lama-bordo terraces and in the application of lama-bordo agricultural practices, including the use of traditional native crops. 6. Trained local producers in the use of lama-bordo techniques. 7. Utilization of fuelwood efficient stoves in ten communities, including the establishment of fuelwood plantations based on native species. 1. Identification in consultation with priority communities potential Community Conservation Areas that could be certified as Areas Voluntarily Destined for Conservation (AVDCs); 2. Identification in consultation with priority communities of areas for the establishment of biological corridors connecting protected areas with well preserved forests; 3. Application of environmentally sound land use plans developed under project component 2 in the establishment of AVDCs and biological corridors. 5. Network of certified Areas Voluntarily Destined for Conservation. Biological corridors connecting protected areas with well preserved forests. 6. Certification process for establishing AVDCs. 7. Certification process for producers within biological corridors applying the ES approach. 8. Management plans for AVDCs. 9. Management plans for biological corridors. 10. Trained local stakeholders participating in the implementation of management plans for AVDCs and biological corridors | 1,920,000 | 24 | 6,149,815 | 76 | 8,069,815 |
| 4. Outreach and dissemination | TA | Outcome 4.1: Project findings, tools and methodologies made available to state and federal decision makers as well as the public, and relevant interest groups Outcome 4.2: Coordination and cooperation established with UNEP Ecosystem Management Program (EMP) | 1. Systematization of methodologies and tools developed by the project, as well as results and findings. 2. Outreach and dissemination strategy for upscaling of project impact based on the systematization of project tools, methodologies, results and findings. 3. Information materials on project findings, tools and methodologies for (1) state and federal decision-makers, (2) stakeholders and (3) the public. 4. Educational and public awareness materials on the provision of ecosystem services to productive sectors in the Mixteco language. 5. Tool kit for the application of ES tools and methodologies for decision-makers at the state and federal levels. 6. Tool kit in Spanish and the Mixteco language on ES tools and methodologies and good practices in agriculture and natural resource management for use by local communities. 1. Consultations and coordination with UNEP EMP in the development and implementation of an outreach and dissemination strategy based on the systematization of project tools, methodologies, results and findings. 2. Project findings, results and products made available for the knowledge base of UNEP’s Ecosystem Management Program | 860,000 | 50 | 843,250 | 50 | 1,703,250 |
| 5. Project M&E |  |  |  | 130,000 | 19 | 550,000 | 81 | 680,000 |
| 6. Project management |  |  |  | 590,000 | 37 | 1,025,465 | 63 | 1,615,465 |
| Total Project Costs |  |  |  | 5,900,000 | 38 | 9,788,530 | 62 | 15,688,530 |

B.   Sources of confirmed Co-financing for the project (expand the table line items as necessary)

| Name of Co-financier (source) | Classification | Type |  | Project total | %* |
| --- | --- | --- | --- | --- | --- |
|  |  | Grant | In-kind |  |  |
| CONAFOR | National Government | 8,800,000 |  | 8,800,000 | 89.90 |
| CONANP | National Government | 693,065 | 195,465 | 888,530 | 9.08 |
| WWF | NGO |  | 100,000 | 100,000 | 1.02 |
| Total Co-financing |  | 9,493,065 | 295,465 | 9,788,530 | 100.00 |

* Percentage of each co-financier’s contribution at CEO endorsement to total co-financing.

C.   Financing Plan Summary For The Project ($)

|  | Project Preparation a | Project b | Total c = a + b | Agency Fee | For comparison: GEF and Co-financing at PIF |
| --- | --- | --- | --- | --- | --- |
| GEF financing | 100,000 | 5,900,000 | 6,000,000 | *590,000 | **5,900,000 |
| Co-financing | 231,726 | 9,788,530 | 10,020,256 |  | 9,531,000 |
| Total | 331,726 | 15,688,530 | 16,020,256 | 590,000 | 15,431,000 |

* Fee for project only as PPG fee has already been claimed.

** GEF PIF clearance letter, April 24, 2009

D.  GEF Resources Requested by Agency(ies), Focal Area(s) and Country(ies)1

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Project (a) | Agency Fee ( b)2 | Total c=a+b |
| Total GEF Resources |  |  |  |  |  |

1 No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

2    Relates to the project and any previous project preparation funding that have been provided and for which no Agency fee has been requested from Trustee.

E.  Consultants working for technical assistance components:

| ### Component | ### Estimated person weeks GEF | ### GEF amount ($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 1,880 | 675,000 | 1,163,000 | 1,838,000 |
| ### International consultants* | 182 | 201,800 | 180,000 | 381,800 |
| ### Total | 2,062 | 876,800 | 1,343,000 | 2,219,800 |

* Details provided in Annex C.

f.   Project management Budget/cost

| Cost Items | Total Estimated person weeks/months | GEF amount |  |  |
| --- | --- | --- | --- | --- |
|  |  | ($) | Co-financing ($) | Project total ($) |
| Local consultants* | 1081/250 | 18,750 | 530,000 | 548,750 |
| International consultants* | 0 |  |  | 0 |
| Office facilities, equipment, vehicles and communications* |  | 115,500 | 185,000 | 300,500 |
| Travel* |  | 74,178 | 79,000 | 153,178 |
| Others** |  | 6,500 |  | 6,500 |
| Project staff |  | 335,072 |  | 335,072 |
| Meetings of the PSC |  | 40,000 | 131,465 | 171,465 |
| External evaluations and audits |  |  |  |  |
| Total | 1081/250 | 590,000 | 925,465 | 1,515,465 |

* Details to be provided in Annex C.   ** Maintenance of office equipment and Rental of equipment.

G.  Does the project include a “non-grant” instrument?  yes     no X
      (If non-grant instruments are used, provide in Annex E an indicative calendar of expected 
        reflows to your agency and to the GEF Trust Fund).

H.  describe the budgeted M &E PLAN:

The project will follow UNEP standard monitoring, reporting and evaluation processes and procedures. Substantive and financial project reporting requirements are summarized in Appendix 8 of the project document. Reporting requirements and templates are an integral part of the UNEP legal instrument to be signed by the executing agency and UNEP.

The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework presented in Annex A includes SMART indicators for each expected outcome as well as mid-term and end-of-project targets. These indicators along with the key deliverables and benchmarks included in Appendix 6 of the project document will be the main tools for assessing project implementation progress and whether project results are being achieved. The means of verification and the costs associated with obtaining the information to track the indicators are summarized in Appendix 7 of the project document. Other M&E related costs are also presented in the Costed M&E Plan and are fully integrated in the overall project budget.

The M&E plan will be reviewed and revised as necessary during the project inception workshop to ensure project stakeholders understand their roles and responsibilities vis-à-vis project monitoring and evaluation. Indicators and their means of verification may also be fine-tuned at the inception workshop. Day-to-day project monitoring is the responsibility of the project management team but other project partners will have responsibilities to collect specific information to track the indicators. It is the responsibility of the Project Manager to inform UNEP of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

The project Steering Committee will receive periodic reports on progress and will make recommendations to UNEP concerning the need to revise any aspects of the Results Framework or the M&E plan. Project oversight to ensure that the project meets UNEP and GEF policies and procedures is the responsibility of the Task Manager in UNEP-GEF. The Task Manager will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of scientific and technical outputs and publications.

At the time of project approval 50 percent of baseline data is available. Baseline data gaps will be addressed during the first year of project implementation. A plan for collecting the necessary baseline data is presented in Appendix 7 of the project document. The main aspects for which additional information is needed are on the current distribution of biodiversity and ES, particularly in the four project intervention areas. In addition, already existing baseline data and new baseline information generated under this project will have to be analysed and interpreted so that comprehensive land use plans applicable to the project intervention areas can be elaborated. Further baseline information on the surface area of degraded lands, farmlands and ecosystems within the four project intervention areas are required. Baseline data on the location, extent, distribution and state of existing and abandoned lama- bordo agricultural lands also needs to be generated for use in land rehabilitation plans in project intervention areas. Finally, an integrated analysis is needed of the kind of eco-tourism products envisaged in the first phases of project intervention in areas where tourist infrastructure is to be developed, including information on the numbers of tourists, the length of time they stay, where they come from and go on to and the kind of activities in which they can participate.

Project supervision will take an adaptive management approach. The Task Manager will develop a project supervision plan at the inception of the project which will be communicated to the project partners during the inception workshop. The emphasis of the Task Manager supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring.  Progress vis-à-vis delivering the agreed project global environmental benefits will be assessed with the Steering Committee at agreed intervals. Project risks and assumptions will be regularly monitored both by project partners and UNEP. Risk assessment and rating is an integral part of the Project Implementation Review (PIR). The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective use of financial resources.

A mid-term management review or evaluation will take place in March 2013 as indicated in the project milestones. The review will include all parameters recommended by the GEF Evaluation Office for terminal evaluations and will verify information gathered through the GEF tracking tools, as relevant. The review will be carried out using a participatory approach whereby parties that may benefit or be affected by the project will be consulted. Such parties were identified during the stakeholder analysis (see section 2.5 of the project document). The project Steering Committee will participate in the mid-term review and develop a management response to the evaluation recommendations along with an implementation plan. It is the responsibility of the UNEP Task Manager to monitor whether the agreed recommendations are being implemented.

An independent terminal evaluation will take place at the end of project implementation. The Evaluation and Oversight Unit (EOU) of UNEP will manage the terminal evaluation process. A review of the quality of the evaluation report will be done by EOU and submitted along with the report to the GEF Evaluation Office not later than 6 months after the completion of the evaluation. The standard terms of reference for the terminal evaluation are included in Appendix 9 of the project document. These will be adjusted to the special needs of the project.

The GEF tracking tools are attached as Appendix 15 of the project document.  These will be updated at  mid-term and at the end of the project and will be made available to the GEF Secretariat along with the project PIR report. As mentioned above, the mid-term and terminal evaluation will verify the information of the tracking tool.

The budget for the implementation of the monitoring and evaluation workplan is provided in the following table.

| M & Activities | Responsible parties | Timeframe | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | comp. 5 | Other components |
| Inception Workshop | National Project Coordinator UNEP/DGEF | 2010 |  | 15,000 |
| Project Steering Committee meetings | National Project Coordinator UNEP/DGEF | Yearly, 2010-2015 | 40,000 |  |
| Key elements of essential baseline data during first year of project including reporting | National Project Coordinator Key Consultants Project Team | August 2010 - July 2011 | 45,000 |  |
| Surveys for key indicator follow up | Project Team Key Consultants | 2011 - 2015 |  | Cost of all surveys related to follow up of key indicators is covered by communication and travel budgets as well as by staff time in relevant components |
| Mid-term review | Evaluation Consultants UNEP/DGEF | 2013 | 20,000 |  |
| Terminal evaluation | 5 Evaluation Consultants UNEP/DGEF | 2015 | 25,000 |  |
| Total |  |  | 130,000 |  |

part ii:  project justification

- State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

National agencies requested UNEP’s technical support in achieving a more effective implementation of the conservation objectives set forth in Mexico’s National Biodiversity Strategy and Action Plan. In particular, they asked for technical support to avert the threats confronting biodiversity conservation in the Mixteca region of Oaxaca. This shall be accomplished by interventions that will specifically help to overcome existing barriers, including covering critical technology and information gaps, designing a program tailored to assess ecosystem services and mainstream the relevant considerations into poverty alleviation, farming and infrastructure programs, and assisting in the field testing and pilot application of these adjusted programs into selected areas with the highest biological value and that comprise as yet unprotected corridors among reserve areas.

The fundamental rationale is that a significant improvement of ecosystem integrity and resilience can be reached through implementing ecosystem management techniques based on the assessment of ecosystem services and this, together with the project’s components described in the project document, in particular, the rehabilitation of degraded lands, will achieve global environmental benefits in biodiversity conservation. This in turn will bring about improved delivery of ES for more sustainable livelihoods, including better water and soil conditions and improved agricultural productivity in the form of higher efficiencies and yields. Productive activity will in turn be concentrated in the most suitable areas thereby decreasing habitat disruption and encroachment on fragile and biologically significant ecosystems.

In parallel, the project will strive for active stakeholder involvement and policy support for conservation of forest areas as well as reforestation and regeneration of vegetative cover to bring about the benefits of improved biodiversity in surrounding ecosystems at the landscape level.  This will be further facilitated by the application of federal support programs delivered at state and local levels, which will by means of the GEF increment include a variety of practical incentives to secure biodiversity conservation goals.  Hence the delivery of global environmental benefits will be primarily derived from significant conservation, rehabilitation and increased connectivity of habitat for globally significant biodiversity in key areas of the Mixteca.  A more detailed description of project outcomes is provided in section 3.3 of the project document and of its indicators and targets in the results framework as well as the appendix 7 to the project document “Costed M&E Work Plan”. The following table provides an overview of local benefits to be derived from the project’s key outcomes and the resultant global benefits that they will in turn generate.

Local and Global Benefits Derived from Project

| Key project outcomes | Local benefits | Global benefits |
| --- | --- | --- |
| 1.1 Stakeholders and decision makers at state and local level have increased access to Ecosystem Services tools applicable to biodiversity conservation and sustainable use 1.2 Natural Resources, ecosystem services and biodiversity in the project intervention area are assessed, valued and monitored using the new ES tools and knowledge provided through the project 2.1 Biodiversity and ES considerations are integrated into state and federal support programs and land use planning | - Installed capacity for applying ES methodologies and tools to development planning - Development based on environmentally sound land use planning that fully takes into account ES - Strengthened coordination and synergies among federal, state and local authorities in support programs contributing to the protection and restoration of ES, especially the provision of water, supporting soil conservation and biodiversity conservation - Compensation of local stakeholders for restoring and/or maintaining ecosystem integrity | - Improved planning and management of areas of particular importance to biodiversity - Reduction of the current rate of loss of globally-significant biodiversity - Rehabilitation and restoration of globally-significant ecosystems |
| 3.1 Local stakeholders apply the ecosystem approach for planning and implementation of productive activities and biodiversity conservation; 3.2 The supply of key Ecosystem Services is secured, improving ecosystem resilience and leading to improved livelihoods | - Restored productivity of lands, including those using lama bordo traditional systems - Control of soil erosion - Reduction and prevention of the expansion of the agricultural frontier - Decreasing habitat disruption and encroachment on fragile and biologically significant ecosystems - Expansion of the region’s vegetative cover as a result of reforestation and afforestation - Protection and restoration of ES, including the provision of food, water and energy; regulating climate and controlling pests; supporting nutrient cycles and crop pollination; and maintaining cultural values, including recreational services such as ecotourism - Strengthening of alternative tourism based on biological diversity, natural attractions and agro-ecosystems - Decreased pressures on existing forest resources as a result of more efficient fuelwood utilization - Extension of plantation forests with native species appropriate for fuelwood - Improved agricultural productivity in the form of higher efficiencies and yields - Improved livelihoods and poverty alleviation | - Reduction of the current rate of loss of globally-significant biodiversity - Rehabilitation and restoration of globally-significant ecosystems - Improved status of threatened species - The preservation and application of traditional knowledge and practices in the sustainable management of natural resources that contribute to the conservation and sustainable use of biodiversity - Enhanced resilience of agro-ecosystems and globally-significant ecosystems and their species to adapt to climate change - Maintenance of biological resources supporting sustainable livelihoods, local food security and health care, especially for the poor Carbon benefits are not within the scope of this project and hence will not be measured as such. They are however considered as additional benefits and in their connection with improved land use leading to increased benefits for biodiversity and include: - Reduced carbon emissions from forest sources contributing to climate change, which is a major threat to biodiversity on a global scale - Increased carbon sequestration from forest plantations, reforestation and afforestation for mitigating climate change that is threatening biodiversity on a global scale |
| 3.3 Improved land use planning and management practices lead to increased habitat connectivity for globally significant biodiversity within the project intervention area as assessed and monitored under outcome 1.2 | - Strengthened ecosystem integrity through increased connectivity - Ecosystem resilience improved - Conservation of biodiversity richness, including significant numbers of endemic species - Engagement of local stakeholders in biodiversity conservation | - Improved planning and management of areas of particular importance to biodiversity - Increased habitat connectivity for globally significant biodiversity within an area of 567,308 hectares - Increased integrity of ecosystems of global biodiversity significance - Reduction of the current rate of loss of globally-significant biodiversity - Improved status of threatened species - Enhanced resilience of agro-ecosystems and globally-significant ecosystems and their species to adapt to climate change |
| 4.1 Project findings, tools and methodologies made available to state and federal decision makers as well as the public, and relevant interest groups | - Replication of local benefits derived from key project outcomes 1 to 6 in other areas of the Oaxacan Mixteca and Mexico | - Replication of global benefits derived from key project outcomes 1.1 to 3.3 |
| 4.2 Coordination and cooperation established with synergic initiatives and other projects, in particular UNEP Ecosystem Management Program (EMP) |  | - Enhanced conservation and sustainable use of biodiversity worldwide as a result of UNEP programmes and projects that incorporate the findings and lessons learned from the GEF Mixteca project |

- Describe the consistency of the project with national and/or regional priorities/plans:

## Mexico signed the Convention on Biological Diversity on 13 June 1992 and ratified it on 11 March 1993. The project is fully aligned with Mexico’s National Biodiversity Strategy and Action Plan in its four strategic lines: (a) protection and conservation, through the fostering of consolidated in situ protection and conservation initiatives and intensifying the actions aimed at rescuing, rehabilitating and recovering ecosystems, communities and species; (b) valuation of biodiversity, reclaiming its value and cultural importance in scientific, social and economic terms; (c) knowledge and information management on ecosystems, species and varieties through the rescuing of traditional knowledge, support to assessments and research and the implementation of dissemination activities, promoting public awareness and comprehension of biodiversity importance; and (d) diversification of biodiversity utilization through the review of present use and fostering sustainable uses of biodiversity. Within the action plan, the most relevant alignment is with PROCODES as described in the baseline under section 2.6 of the project document.

## In addition to other specific national plans and strategies in alignment with the conservation objectives of the present project, first and foremost is the National Program for Natural Protected Areas. In relation to this project, what needs to be highlighted is the strive towards including sustainable development plans and  projects aimed at the conservation and sustainable use of natural resources and biodiversity by fostering sustainable livelihoods in protected areas and buffer zones primarily amongst indigenous people, including women and youth.

## National initiatives which are aligned with the development objectives of this project are gathered under an inter-institutional instrument called “Special Concurrent Program for Rural Sustainable Development” (Programa Especial Concurrente para el Desarrollo Rural Sustentable (PEC)). This includes related programs from different government sectors and has a significant allocation in the yearly national budget. At least 16 of these PEC programs have direct or complementary bearing on the present project. Of special relevance is the national support program implemented nationally by the National Forestry Commission (CONAFOR). The corresponding branch of this initiative for the State of Oaxaca will be contributing an important portion of this project’s co-financing. A series of programs from the agricultural sector (SAGARPA) are also in place, aimed primarily at food security and poverty alleviation goals. Through this project, these investments will be included in a coherent conservation and sustainable production plan and thus channeled so as to maximize conservation of biodiversity of global significance in Mixteca ecosystems. It is also noteworthy that the Federal Commission for the Development of Indigenous Peoples (CDI) has an important budget that boasts economic independence, and important additional investments could be leveraged by the project for the Mixteca region which is a priority area in Mexico of indigenous population groups. Also refer to the project document; section 3.6 (pages 46-47).

- Describe the consistency of the project with gef strategies and strategic programs:

This project will comply with Strategic Programme 4 (SP4) of Strategic Objective 2 (SO2) within the GEF focal area of Biodiversity. Through the project, UNEP will assist Mexico in developing the necessary ecosystem services assessment tools to integrate the conservation and sustainable use of biodiversity into key productive sectors of the economy while seeking the maintenance of the ecosystem goods and services that biodiversity provides to society. Regarding SP4 the proposed project will supply the required technological innovation in terms of tools and methodologies for ecosystem services assessment and monitoring to support the development of the policy and regulatory frameworks that promote and reward mainstreaming and build the necessary institutional capacity. In particular, outcomes will be achieved by linking science with policy thus “removing critical knowledge barriers, developing institutional capacities, and establishing the policies, and the legislative and regulatory frameworks required to integrate biodiversity conservation and sustainable use objectives into the actions of the production sectors”. During the project preparation phase the description provided in the PIF regarding this issue has been further confirmed and still stands as presented.

- justify the type of financing support provided with the gef resources:

GEF intervention funds will re-orientate a substantial amount of funds from federal agencies such as CONAFOR and CONANP in support of the development and integration of knowledge for the use and application of ES methodologies and tools in social, economic and environmental planning at the federal, state and local levels.

GEF funding is strategically targeted to (1) increase the knowledge base for the application of innovative ES methodologies and tools in social and economic development planning in the Oaxacan Mixteca, (2) mainstream biodiversity conservation and the application of ES methodologies and tools into the region's social, economic and development support programs, (3) support the use of good practices in agriculture (GAP) and natural resource management (GNRMP), including  field testing of models in demonstration pilots and the application of traditional knowledge,  that benefit ecosystem integrity and biodiversity conservation, (4) reinforce the establishment of voluntary reserves, including biological corridors connecting protected areas with well-preserved ecosystems and (5) support the replication of project findings and lessons learned throughout the Mixteca and other parts of Mexico. The esablishment with GEF funding of on-going programs for monitoring, assessing and valuing ES for use by decision makers will contribute strategically to the sustainability of the application of innovative ES methodologies and tools in the Oaxacan Mixteca. GEF financial support to the project demonstration sites is crucial for transfering the application of the ecosystem approach and good practices in agriculture and natural resource management to productive sectors on the ground. Thus, GEF funding aims at top-to-bottom results, which in turn will contribute to the conservation of globally significant biodiversity.

- Outline the Coordination with other related initiatives:

Synergies and interaction of this project with other initiatives to maximize learning as well as to avoid repetition of efforts and investments while systematically integrating project findings at the program level with UNEP’s knowledge management has been incorporated into the project by design. On a day to day basis at the output and outcome level, these considerations are part of the fourth component under outcome 4.2 especially designed for this purpose (please refer to section 3.3 of the project document and to the results framework for additional detail on this outcome). For additional detail on coordination with other related initiatives please refer to the more detailed analysis of interaction with specific projects in the project document, section 2.7 (pages 30-32) as well as the Stakeholder mapping and analysis in section 2.5 (pages 22-28).

F.   Discuss the value added BY GEF involvement in the project demonstrated through incremental reasoning :

The Mixteca ecosystem containing globally significant biodiversity finds itself under severe pressure from productive activities that overexploit the ES it provides. National authorities are trying to provide solutions for the socio-economic aspects to address national and local priority issues, such as poverty alleviation and food security, with important financial resources earmarked for the area. Funds from many national programs are also available to be tapped, constituting an important baseline on which to build. Nonetheless, effective action that would ensure biodiversity conservation is not forthcoming because of a set of barriers that include (i) inadequate knowledge related to the management and provision of ES, (ii) a lack of coherence and integrality of support programs and planning towards biodiversity benefits and (iii) the limited capacity of CONANP and partners to upscale interventions for optimizing impact at the landscape level. The GEF increment would remove these barriers so that globally significant biodiversity could be more effectively conserved, taking advantage of significant baseline investments through the aforementioned strategic programs. In essence, the incremental reasoning is that if existing land use planning and support programs continue their present course, the focus will be on local benefits, such as poverty alleviation and food security, while biodiversity degradation would continue. The GEF investment will ensure that global environmental benefits are achieved by bringing biodiversity conservation to the forefront of existing and new poverty alleviation, food security and development programmes. For further detail, please also refer to the project document’s appendix 3, detailing the incremental cost analysis.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved and outline risk management measures:

Project design addresses risks affecting institutional sustainability, as well as social and financial sustainability.  Additional risks to the project along with measures to be taken to manage these risks are described in the following table.

Project Risks and Corresponding Mitigation Measures

| Risk | Rating | Mitigation Strategy |
| --- | --- | --- |
| Mexico’s rural support programs are managed under different allocation lines of one integrated national budget and thus disbursements may experience delays that would affect primarily activities following the agricultural calendar. | M | The project shall devise a strategy to prepare for possible funding delays from one source conceivably using the resource mix available through co-financing. |
| The high migration rate of young and adult men in economically active age groups diminishes the traditional stakeholder base at the project intervention sites. | M | The project will include among its beneficiaries groups of women, elderly persons and youth, focusing on sustainable livelihood activities that are compatible with their capacities and the environment. |
| Varying project ownership among local stakeholder communities. | L/M | The project proposes a participatory approach at the grass roots level reaching out to Mixteca communities. Within the ecosystem approach, the application of indigenous knowledge will be highlighted alongside the tools prepared under component 1 and 2 and translated into profitable, sustainable livelihood alternatives for the target population. |
| Market fluctuations and barriers that hinder the accessibility of goods and services that are produced utilizing the ecosystem approach, including GAP and GNRMP. | M | Through the project, local producers and stakeholders will be provided technical support for marketing goods and services produced by GAP and GNRMP. Involvement of marketing specialists experienced in certification systems will be sought. |
| Perceived security problems at the national level will discourage tourism, affecting the implementation of an alternative tourism strategy for the Oaxacan Mixteca. | L | Ecotourism in Mexico has increased significantly during the past decade, particularly tourism directed at natural protected areas. The number of ecotourists from 2002 to 2005 reached 20 million, spending approximately US$400 million. However, ecotourism is at an incipient stage in Oaxaca. Given the Mixteca region’s diverse ecosystems and high degree of biodiversity, it is very likely that the alternative tourism strategy can contribute to the growth of an important sector and source of income in the region. |
| Extreme weather conditions associated with soil erosion and water shortage problems (flooding and drought) are exacerbated by climate change. | L | The project’s intervention strategy is based on an ecosystem approach. The resulting increase in ecosystem resilience (water conservation, soil stabilization, microclimate regulation) will go a long way to sustainably providing stakeholders with a more solid foundation to withstand any extreme climatic events, such as droughts and flooding which may be exacerbated by climate change. Although no significant external risks derived from the consequences of climate change are foreseen to jeopardize the success of the proposed intervention, climate adaptation and vulnerability assessments will be made by the project to stay abreast of any potential associated problems or limitations. |

Rating: H: High; M: Medium; L: Low

- explain how cost-effectiveness is reflected in the project design:

The cost-effectiveness of this GEF intervention is based on making a single investment in a significant area and achieving the double benefit of generating improved livelihoods and simultaneously conserving important biodiversity.

In analyzing the project’s cost effectiveness, two main aspects need to be considered. First, this project favors an approach that works towards small landholders’ interests, using alternative land use practices and activities that improve yields and benefit the environment while helping to ensure biodiversity conservation, rather than an approach based solely on rules and policing which by itself, although necessary, would have little substantial or cost effectiveness. Local benefits in terms of improved livelihoods/income will be generated through improved basic ES (water, soil, wood) within the project area of 567,308 hectares. This concentration on productive activities will reduce encroachment by deforestation and slash and burn, thus allowing global benefits in terms of improved habitat connectivity to be achieved in the surrounding area of influence.

Second, in Mexico both the federal government and state and local authorities can potentially access ample fiscal funds to provide extensive although basic funding for rural/agricultural development, especially within the social sector for indigenous and other marginalised groups. For a GEF intervention to co-finance a project within this scenario is particularly cost-effective because the relatively small investment in the GEF-UNEP specific STA and TA activities is strategically combined with substantial national incentives that through the project’s leveraging and influence are redirected to contribute to biodiversity conservation-friendly activity. This would reach a large rural population within the Oaxacan Mixteca region and has the potential to be up-scaled by established capacities in CONANP and other counterparts to cover the entire ecosystem which includes parts of two other States, and to other similar social and agro-ecological areas.

part iii:  institutional coordination and support

A.  	Institutional arrangement:

UNEP is the GEF Implementing Agency for this project following a request by the Government of Mexico through the National Commission of Protected Natural Areas (CONANP). The project execution partners are CONANP, the National Forestry Commission (CONAFOR) and the World Wildlife Fund (WWF). CONANP and CONAFOR are the main institutional representatives of national ownership of the project and their tasks will cover involvement in technical aspects as well as the mainstreaming of biodiversity at policy level. WWF-Mexico will be charged with project administration through its national and local offices in Mexico City and Oaxaca respectively, while also contributing to technical aspects in the field.

The present proposal is focused on some of UNEP’s core competencies, such as scientific and technical analysis as well as technical assistance for the assessment and monitoring of ecosystem services and their integration into land management policies and planning. As such it is closely aligned and integrated within UNEP’s broader Ecosystem Management Program (EMP). UNEP’s EMP includes a wide range of issues, some of which are addressed through this project, such as i.e.: the promotion of knowledge about the interdependence of ecological operational tools and livelihoods; use of methodologies of working models for use by policy-makers to analyze ecosystem services and their trade-offs with development policies and resource allocations; defining convincing economic values of ecosystem services and, in particular, of the regulating and cultural services which could be used to evaluate the trade-offs with conventional development strategies; and periodic assessments of the status of ecosystem services to monitor and track changes in those services and their impacts on human well-being.

Ecosystem Management stands among the Strategic Priority Thematic Areas in the Program of Work under UNEP’s Medium Term Strategy 2010-2013. UNEP’s Division for Environmental Policy Implementation (DEPI) is the focal point for the coordination of the Ecosystem Management Programme, and has the mandate to provide technical input to all other UNEP divisions. This set-up ensures an increased level of cooperation and coordination between UNEP divisions. The UNEP DGEF and DEPI are working closely to ensure the continuous exchange of know-how and cross-fertilization among all UNEP projects focusing on the ecosystem approach. This is achieved through regular inter-divisional meetings and established close collaboration between DGEF and DEPI staff based in Nairobi as well as interactions with project Task Managers worldwide on specific projects. UNEP’s EMP includes a wide range of interventions with different emphases, including i.a. Payment for Ecosystem Services (PES), mainstreaming for policy support, ES assessment-valuation-monitoring, as well as other tier/component or combination thereof, all slated to provide critical feedback to the EMP. This set-up maximizes complementarities between projects, streamlining their contribution into the EMP, and is set to generate a critical mass of experiences from a diversity of geographic, environmental, technical, political and socio-economical settings.

B.  	Project Implementation Arrangement:

The project will establish a Project Steering Committee (PSC) consisting of CONANP, CONAFOR and WWF-Mexico as executing partners, and UNEP as GEF implementing agency.  CONANP and CONAFOR as executing partners and WWF-Mexico as national executing agency have spearheaded the development of the project and, as members of the Steering Committee, will play the lead role in implementing and monitoring the project and maintaining its strategic focus. Presided by UNEP, the PSC will be responsible for providing guidance to the execution of project activities, including reviewing and advising on the main outputs of the FSP, ensuring that the Government’s environmental policy is fully reflected in the FSP, ensuring effective communication and decision-making, and assisting with mobilization of expertise as needed for proper execution of FSP outputs. On an annual basis the PSC will meet to fulfill steering mechanism responsibilities including: oversight of project implementation, monitoring of project progress, strategic and policy guidance and to review and approve annual work plans and budgets. Responsibilities of the PSC are detailed in appendix 11 of the project document.

Lead by CONANP, the executing partners will work together as a team on the management of the National Project and meet at least on a quarterly basis. As the project National Executing Agency (NEA), WWF-Mexico will be responsible for implementing the project in accordance with the components outlined in Section 3 of the project document.  A further description of its responsibilities is provided in Appendix 11 of the project document.  UNEP, as the GEF implementing agency, will be responsible for overall project supervision to ensure consistency with GEF and UNEP policies and procedures, and will provide guidance on linkages with related UNEP and GEF funded activities. UNEP will monitor implementation of the activities undertaken during the execution of the project and will be responsible for clearance and transmission of financial and progress reports to the GEF. Appendix 10 of the project document includes a decision-making flowchart and organizational chart for FSP implementation. Responsibilities of the NEA are detailed in appendix 11 of the project document.

WWF-Mexico will cooperate with UNEP so as to allow the organization to fulfill its responsibility as implementing agency accountable to the GEF. To this end, free access to all relevant information will be provided by WWF-Mexico. The NEA will also convene the Project Steering Committee and, in consultation with CONANP, appoint a National Project Coordinator (NPC). In conjunction with the NPC, WWF-Mexico in consultation with CONANP will establish reporting guidelines for all partners and specialists and ensure that they submit quality reports. The NEA and NPC will collaborate to prepare semiannual progress reports, quarterly financial reports and annual summary progress reports for UNEP.

The NPC will be responsible for coordinating, managing and monitoring the implementation of the FSP conducted by the local and international experts, consultants, subcontractors and implementing partners. The NPC will also coordinate and oversee the preparation of the FSP outputs, manage FSP finances, oversee overall resource allocation, and, where relevant, submit proposals for budget revisions to the PSC and UNEP.  Detailed responsibilities of the NPC are detailed in appendix 11 of the project document.

The conceptualization of this project is the product of the collective efforts of CONANP, CONAFOR and WWF-Mexico who, with the support of UNEP, have committed themselves to the mainstreaming of the ecosystem approach in social and economic support programs in the Oaxacan Mixteca to the benefit of biodiversity conservation.  Other actors that will play roles in project implementation include the Secretariat of the Environment and Natural Resources (SEMARNAT), the Secretariat of Agriculture, Livestock, Rural Development, Fisheries and Food (SAGARPA), the Secretariat of Rural Development (SEDER), the Secretariat of Social Development (SEDESOL), the Secretariat of Tourism (SECTUR), the Secretariat of Government (SEGOB), the National Commission for the Development of Indigenous Peoples (CDI) and the National Biodiversity Commission (CONABIO).  Key state and local actors include the State Committee for Development Planning (COPLADE), municipalities in the project’s intervention area and academic and research institutions such as the Technological University of the Mixteca (UTM), as well as civic groups, including the Committee of the Rio Mixteco Watershed, the Regional Natural Resources Committee of the Central Zone of Huajuapan de Leon (CORRENAC)  and Regional Natural Resources Committee of the Mixteca Tlaxiaco-Putla-Juxtlahuaca, A.C., migrant organizations, women’s organizations and private sector groups.

The project will establish a regional Inter-institutional Working Group to support the integration of biodiversity and ES considerations in state and federal support programs and land use planning in the project’s intervention area.  To this end, a workplan for the regional Inter-institutional Working Group in support of the project will be developed.  In addition, for the pilot demonstration projects, activities will be facilitated through Project Site Teams (PSTs) to ensure broad involvement of local communities and key stakeholders, proper planning, and broader consultations with a wide range of agencies, NGOs and key private sector groups, such as farmers, forest owners and hotel and tour operators.

The establishment of a Project Stakeholder Advisory Committee (PSAC) will provide a platform for broader on-going consultations with a wide range of local community representatives, civic groups and private sector representatives on project implementation.

part iv:  explain the alignment of project design with the original PIF

The project design is consistent with the original PIF in its intervention logic. The project goal, project objective and project components and their outcomes remain identical with the PIF design. Some slight re-arrangements of the project strategy were made at the output and activities level due to new findings during the PPG phase. For example, capacity building of decision makers at the state, municipal and community levels on the application of ES methodologies and tools, with the aim of incorporating biodiversity conservation and ES valuation considerations into federal and state support programs, was shifted from component 2 to component 1.  The PPG also brought more into balance activities that will contribute to the achievement of sustainable livelihoods in the Oaxacan Mixteca, as called for in the project’s objective,  with activities directed at biodiversity conservation.

Regarding the project intervention area, the PIF had stated indicative estimates only.  During project preparation, the area in which project impacts will be more directly and inmediately realized has been defined following careful planning which involved local stakeholders and authorities in line with CONANP’s strategic actions on the ground. This area covers approximately one third of the Oaxacan Mixteca and comprises an irregular, mountainous terrain covering 567,308 hectares, 41 municipalities and 98 micro-watersheds.  These areas were chosen as representative of biodiversity hotspots that interconnect with already established protected areas and thereby could provide biological corridors connecting different ecosystems. Detailed information is provided in section 2.1 of the project document (pages 10-13) and the Tracking Tool in appendix 15 of the project document.

At the PIF stage, substantial commitments of co-financing in the amount of $9,531,000 had been reached.  Although during project preparation this figure has increased only slightly to $9,788,530, it is expected that additional co-financing will be mobilized following project inception.

part v:  Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO Endorsement.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Maryam Niamir-Fuller, Director, Division of Global Environment Facility Coordination. GEF Agency Coordinator |  | June 18, 2010 | Robert Erath Task Manager LAC Biodiversity and Land Degradation UNEP/DGEF | +507 305 3171 | robert.erath@unep.org |

Annex A: Project Results Framework

Project Objective: Mainstream biodiversity conservation into natural resource use and development planning in the Mixteca Region of Oaxaca integrating ecosystem services (ES) tools and sustainable livelihood options.

| Outcome | Indicator | Baseline conditions | Mid-term target | End of project target | Means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1: Strengthening the knowledge base on Ecosystem Approach for biodiversity conservation [GEF funding - $1,300,000; cofinancing - $714,000] |  |  |  |  |  |  |
| Outcome 1.1: Stakeholders and decision makers at state and local level have increased access to Ecosystem Services tools applicable to biodiversity conservation and sustainable use | Number of targeted ES tools in support of biodiversity conservation available Number of Government officials and stakeholders trained in the use of ES tools for biodiversity conservation | There is a lack of key ES tools for biodiversity conservation. Expertise at the state and local level in the application of ES tools for biodiversity conservation is suboptimal. | Tools designed and distributed: - ONE Manual on ES tools and methodologies for decision-makers at the state and local level. - ONE KIT Educational materials for methodologies and tools. - ONE KIT Supportive audio-visual training materials on ES 40 Trained state and local officials in the four project potential intervention areas on the application of ES methodologies and tools. | Tools revised: - ONE Manual on ES tools and methodologies for decision-makers at the state and local level. - TWO KITS Educational materials for methodologies and tools. - TWO KITS Supportive audio-visual training materials on ES 80 Trained state and local officials in the four project potential intervention areas on the application of ES methodologies and tools. | Manual distribution log Manual and materials opinion survey Distribution progress reports Distribution and discussion meeting workshops reports | Stakeholders and decision-makers are receptive to incorporating ES tools in land use and development planning. |
| Outputs: - Start-up manual on ES tools and methodologies for decision-makers at the state and local level. - Educational materials for methodologies and tools that are adapted to the Oaxacan Mixteca regarding: (1) assessing, (2) valuing ecosystem and (3) monitoring ecosystem services. - Supportive audio-visual training materials on ES - 80 Trained state and local officials in the project intervention area on the application of ES methodologies and tools. - Revised start-up manual on ES and supportive educational materials for use in project replication that takes into account project developments, findings and results |  |  |  |  |  |  |
| Outcome 1.2: Natural Resources, ecosystem services and biodiversity in the project intervention area are assessed, valued and monitored using the new ES tools and knowledge provided through the project | Application of project products for assessing and valuing ecosystem services (emphasizing areas of outcome 3.1, 3.2 and 3.3) Number of applications of the project’s GIS on the intervention area’s ecosystem services and biodiversity (emphasizing areas under component 3) | Ecosystem services and biodiversity in the project intervention area is not sufficiently appraised Baseline data on the current distribution of biodiversity and ecosystem services in the project intervention area will be established commencing in PY1 and continued henceforth by monitoring and assessment under this outcome. | 3 assessments incl. valuation of ecosystems, watersheds and key species priority studies. A working matrix of priority ecosystem services, key biodiversity and sustainable use studies for the project intervention area 4 institutions provide key information for GIS and utilize it as a planning and monitoring tool in the project intervention area (emphasizing areas under component 3). Monitoring system for the intervention area in operation Two models and analysis tools on the balance between the supply of ecosystem services and primary subsistence options in place | 6 assessments incl. valuation of ecosystem, watersheds and key species priority studies. A working matrix of priority ecosystem services, key biodiversity and sustainable use studies for the project intervention area 8 institutions provide key information for GIS and utilize it as a planning and monitoring tool in the project intervention area (emphasizing areas under component 3). Monitoring system for the intervention area in operation Four models and analysis tools on the balance between the supply of ecosystem services and primary subsistence options developed and applied | GIS and data base Use GIS and data base Manual Technical documents and reports Meeting agreement records of COPLADE´s regional inter-institutional working group. Meeting agreement records of Tlaxiaco, Huajuapan, and Mixtec River Committees, meetings agreements records Project progress reports Mid-term evaluation and terminal evaluation report | For effective monitoring of project implementation solid baseline information is needed. Relevant institutions are committed to incorporating the assessment, valuation and monitoring of ES tools and knowledge into their work programs. Institutions are willing to share information on their activities and investments, as well as relevant basic information. |
| Outputs: - Comprehensive data and information on ES in the Oaxacan Mixteca region and in particular in the project intervention area. - Detailed studies by ecosystem and priority watersheds assessing and valuing ecosystem services in the Oaxacan Mixteca and in particular in the project intervention area. - Geographic information system on the project area and the region’s biodiversity and ecosystem services to support relevant decision-making and investments in the region. - On-going programs to assess value and monitor ecosystem services in the Oaxacan Mixteca and in particular in the project intervention area. |  |  |  |  |  |  |
| Component 2: Supporting biodiversity friendly policy and program development for land use planning and resource use [GEF funding - $1,100,000; cofinancing - $506,000] |  |  |  |  |  |  |
| Outcome 2.1: Biodiversity and ES considerations are integrated into state and federal support programs and land use planning | Agreements of the inter-institutional group meetings Agreements of the CCRM and the CRRNS for Tlaxiaco and Huajuapan in support of project implementation Community level planning includes ES and BD aspects Local application of federal and state supported programs including land use plans for the Mixteca region of Oaxaca, that mainstream ES and biodiversity conservation | ES considerations have not been integrated into state and federal support programs and land use planning in the Mixteca region of Oaxaca. Priority zones for the regional COPLADE´s inter-institutional working group not defined. Communities and/or municipalities do not incorporate the subject of ecosystem services and biodiversity in their annual work programs. Local application of federal and state supported programs including land use plans for the Mixteca region of Oaxaca, do not mainstream ES and biodiversity conservation | Ecosystems services and biodiversity criteria are accepted to prioritize projects COPLADE´s regional inter-institutional working group. Four project piloting areas were accepted as priority zones for the regional COPLADE´s inter-institutional working group 10 communities and/or municipalities incorporate the subject of ecosystem services and biodiversity in their annual work programs 30 local applications using watershed approach to improve biodiversity and ecosystem services status are supported by the CRRN´s and the CCRM, as well as by State and federal programs | Ecosystems services and biodiversity criteria are accepted to prioritize projects COPLADE´s regional inter-institutional working group Eight project piloting areas were accepted as priority zones for the regional COPLADE´s inter-institutional working group 30 communities and/or municipalities incorporate the subject of ecosystem services and biodiversity in their annual work programs 60 local applications using watershed approach to improve biodiversity and ecosystem services status are supported by the CRRN´s and the CCRM, as well as by State and federal programs | Meeting agreement records of COPLADE´s regional inter-institutional working group. Meeting agreement records of Tlaxiaco, Huajuapan, and Mixtec River Committees Municipal development plans Land use plans Municipal council and Community and/or Ejido Assembly minutes Mid-term evaluation and terminal evaluation reports | Political good will of relevant federal and state organizations to integrate ES considerations into support programs and land use planning. SAGARPA and SEDER with CONANP reach an agreement for identifying good agricultural practices. Willingness of relevant federal and state organizations to utilize environmental, biodiversity and ES indicators for assessing agricultural projects in the project’s four intervention areas, particularly as they relate to GAP and good practices for natural resource management Interest on the part of local authorities and communities to integrate ES considerations into their work |
| Outputs: - Regional inter-institutional working group to support the integration of biodiversity and ES considerations in state and federal support programs and land use planning in the project’s intervention area. - Integrating the outcomes of the on-going programs assessing, valuing and monitoring ecosystem services from 1.2 into development policy-making and planning in the Oaxacan Mixteca. - Mainstreaming of biodiversity, including ES tools and options into federal and state support programs and land use plans in the Oaxacan Mixteca. - Baseline data for the development of comprehensive land use plans applicable to the project intervention area. - Environmentally sound land use plans for sustainable development in the project’s intervention area, taking into account the outputs provided by the on-going programs assessing, valuing and monitoring ecosystem services under 1.2. - Revised existing land use plans or being developed in the Oaxacan Mixteca to include ecosystem services considerations, taking into account outputs provided by the on-going programs assessing, valuing and monitoring ecosystem services under 1.2. - Pilot system of compensation for ecosystem integrity provided by local communities, farmers and other stakeholders. - ES indicators for assessing the agricultural projects of SAGARPA and SEDER in the project’s intervention area, particularly as they relate to GAP and good practices for natural resource management. |  |  |  |  |  |  |
| Component 3: Piloting biodiversity friendly programs on the ground [GEF funding - $1,920,000; cofinancing - $6,149,815] |  |  |  |  |  |  |
| Outcome 3.1: Local stakeholders apply the ecosystem approach for planning and implementation of productive activities and biodiversity conservation | Number of trained producers that apply the ecosystem approach in planning and implementing productive activities and in biodiversity conservation Surface area of lands applying integrated land use planning of good practices in agriculture and natural resource management Application of productive protocols based on models from 1.2 for rural development based on the ES approach and good practices in agriculture and natural resource management Number of projects resulting from support to rural community planning processes Number of local tourism strategic routes, tour operators and hotel operators promoting alternative tourism. Number of persons trained, certified and hired as local ecotourism guides Products with potential for marketing strategy of conservation goods and services | Local stakeholders are not applying the ecosystem approach in productive activities and biodiversity conservation. Baseline assessment to be finalized in PY1 Baseline assessment to be finalized in PY1 Community planning is at an incipient stage in the project intervention area, in particular regarding ES and BD considerations The development of alternative tourism based on biodiversity, natural attractions and agro-ecosystems is at an incipient stage. No marketing strategy in the region for certified products derived from sustainable management and conservation of natural resources and ecosystem services | 50 local stakeholders apply the ecosystem approach in planning and implementing productive activities and in biodiversity conservation 5,000 ha of land including productive and conservation areas above baseline Five on the ground applications of models for rural development based on the ES approach and good practices in agriculture and natural resource management. 10 community planning processes in priority communities in the project intervention area, 2 regional natural resources committees planning process. One alternative tourism strategic route based on biological diversity, natural attractions and agroecosystems. 10 local stakeholders are trained and certified as local ecotourism guides | 100 local stakeholders apply the ecosystem approach in planning and implementing productive activities and in biodiversity conservation 10,000 ha of land including productive and conservation areas above baseline Ten on the ground applications of models for rural development based on the ES approach and good practices in agriculture and natural resource management. 30 community planning processes in priority communities in the project intervention area, 2 regional natural resources committees planning process. Two alternative tourism strategic routes based on biological diversity, natural attractions and agroecosystems. 20 local stakeholders are trained and certified as local ecotourism guides A technical proposal for the marketing of goods and services related certification programs | Lists of training assistance. Verification by project staff recorded in planning and follow up field logs and local initiative reports List of participants in the watersheds models for rural development Acceptance letters by local stakeholders of the value of utilizing the ecosystem approach Meeting agreement participating communities records Meeting agreement records of Tlaxiaco, Huajuapan, and Mixtec River Committees, meetings agreements records SAGARPA, SEDER, and CONANP to provide verification Verification by SECTUR of integration of alternative tourism into state and local plans and strategies Mid-term evaluation and terminal evaluation report | State and local authorities and local organizations are open to receiving capacity building in the integration of the ecosystem approach for planning and implementation of productive activities and biodiversity conservation. Receptivity of private sector actors to establishing and promoting alternative tourism Certification by CONANP Local communities and federal, state and local authorities can agree to work together in the establishment and implementation of the pilot demonstration projects |
| Outputs: - Start-up manual for local stakeholders in the project intervention area on the ecosystem approach for planning and implementing productive activities and biodiversity conservation. - Educational materials in each of the following areas that are adapted to the Oaxacan Mixteca: (1) good agricultural practices (GAP) and (2) good practices in natural resource management. - Educational materials on the sustainable use of biodiversity, based on the ethno-biological experiences of the local people. - Educational materials on the importance of preventing the illegal collection and use of wild biota. - Supportive audio-visual training materials on GAP and good practices in natural resource management. - Revised start-up manual and supportive educational materials on the ecosystem approach for planning and implementing productive activities and biodiversity conservation for local stakeholders that take into account project developments, findings and results, for use in project replication. - Cooperative agreements with rural community planning processes, particularly within the regional natural resources committees and in priority communities in the project’s intervention area, for promoting the integration of biodiversity conservation, ES considerations and sustainable management of agriculture and natural resources. - Agreements on priority actions, programs and projects requiring the ecosystem approach through participatory rural community planning exercises. - Strategy for mainstreaming alternative tourism based on biodiversity, natural attractions and agro-ecosystems in state and local tourism programs. - Alternative tourism strategy for the project’s intervention area based on biological diversity, natural attractions and agroecosystems. - Trained and certified ecotourism guides for the Oaxacan Mixteca. - Ten micro-watersheds that can serve as models for rural development based on the ES approach and good practices in agriculture and natural resource management. - Trained local stakeholders, particularly farmers and local communities, at the 10 pilot demonstration projects in the intervention area on the application of the ecosystem approach for planning and implementing productive activities, natural resource management and biodiversity conservation. - Technical assistance to producers for the marketing of goods and services that are the product of GAP and GNRMP, including lama-bordo techniques, exploring opportunities for participating in related certification programs. |  |  |  |  |  |  |
| Outcome 3.2: The supply of key Ecosystem Services is secured, improving ecosystem resilience and leading to improved livelihoods | Surface area of degraded lands and ecosystems that have been rehabilitated or are in process of rehabilitation Surface area of increase in natural vegetation cover, which reflects an improvement in the provision of ecosystem services, including carbon sequestration, availability of water, soil rehabilitation and biodiversity conservation Use of fuelwood efficient stoves Use of lama-bordo agricultural terraces for cultivating native plants such as maize, chile, squash, amaranth, and cacti, among others Surface area covered by rehabilitated lama- bordos Comparative quantitative and qualitative data on soil quality within and outside lama-bordo agricultural terraces | Ecosystem services provided by fragile ecosystems in the Mixteca of Oaxaca are in a state of deterioration as a result of growing population pressure, deforestation and unsustainable practices in agriculture and natural resource management, further exacerbating the livelihoods of local and indigenous communities. Lama-bordo agricultural terraces, while widespread in the Mixteca during the precolombian period, were largely abandoned as an agricultural management system after European contact. | 4500 ha of degraded lands reforested, rehabilitated or in the process of rehabilitation 5 communities use fuelwood efficient stoves including the establishment of fuelwood plantations based on native species. 5 pilot demonstration projects for rehabilitating lama-bordo systems, testing, monitoring and demonstrating 20 Trained local producers in the use of lama-bordo techniques. | 9000 ha of degraded lands reforested, rehabilitated or in the process of rehabilitation 10 communities use fuelwood efficient stoves including the establishment of fuelwood plantations based on native species. 10 pilot demonstration projects for rehabilitating lama-bordo systems, testing, monitoring and demonstrating 40 Trained local producers in the use of lama-bordo techniques. 5 communities of the use of lama-bordo terraces as an agricultural management approach | Participant list with reforested and rehabilitated areas. Meeting agreement participating communities records Acceptance letters by local stakeholders Lists of training assistance Technical documents and reports lama-bordo system Technical evaluation of fuelwood efficient stoves Project progress reports Mid-term evaluation and terminal evaluation report | Communities agree to utilize lama-bordo management systems |
| Outputs: - Degraded lands reforested - Degraded lands and ecosystems rehabilitated or in the process of rehabilitation in project intervention areas. - Knowledge and information on lama-bordo agricultural systems for soil conservation, improved productivity and the cultivation of native plants traditionally used that contribute to improved family nutrition. - Knowledge and information on cultivation of traditionally used native plants that contribute to improved family nutrition particularly through the use of lama-bordo agricultural systems. - 5 pilot demonstration projects for (1) rehabilitating lama-bordo systems, (2) testing, monitoring and demonstrating the use of lama-bordo production techniques and their compatibility with sustaining ecosystem services and (3) training local producers in the restoration of lama-bordo terraces and in the application of lama-bordo agricultural practices, including the use of traditional native crops. - Trained local producers in the use of lama-bordo techniques. - Utilization of fuelwood efficient stoves in ten communities, including the establishment of fuelwood plantations based on native species. |  |  |  |  |  |  |
| Outcome 3.3: Improved land use planning and management practices lead to increased habitat connectivity for globally significant biodiversity within the project intervention area as assessed and monitored under outcome 1.2 | Advancement in the processes for the establishment of voluntary reserves and related management plans Advancement in the processes for the establishment of biological corridors, and their management plans, connecting protected areas Number of persons trained for implementation of management plans for AVDCs and biological corridors | Detailed baseline information on the status of degraded lands and ecosystems as on connectivity of habitat area and corridors in the project intervention area will be established under OUTCOME 1.2 in PY1 and monitored henceforth | Potential Community Conservation Areas identified; 5 Certification process for establishing AVDCs (Areas Voluntarily Destined for Conservation). Potential communities for the establishment of biological corridors Establishment of one biological corridor connecting protected areas with well preserved forests. | 10 Certification process for establishing AVDCs. 5 Management plans for AVDCs. Establishment of 2 biological corridors connecting protected areas with well preserved forests Management plans for one biological corridor. 10 Trained local stakeholders participating in the implementation of management plans for AVDCs and biological corridors | Technical documents and reports for potential community conservation and biological corridors Communities agreement for AVDCs CONANP´ AVDCs certification process files Management Plans Technical documents Management Plans communities accepted letter GIS and data base | Local communities are open to the possibility of establishing voluntary Community Areas for Conservation and biological corridors. |
| Outputs: - Identification in consultation with priority communities potential Community Conservation Areas that could be certified as Areas Voluntarily Destined for Conservation (AVDCs); - Identification in consultation with priority communities of areas for the establishment of biological corridors connecting protected areas with well preserved forests; - Application of environmentally sound land use plans developed under project component 2 in the establishment of AVDCs and biological corridors. - Network of certified Areas Voluntarily Destined for Conservation. - Biological corridors connecting protected areas with well preserved forests. - Certification process for establishing AVDCs. - Certification process for producers within biological corridors applying the ES approach. - Management plans for AVDCs. - Management plans for biological corridors. - Trained local stakeholders participating in the implementation of management plans for AVDCs and biological corridors |  |  |  |  |  |  |
| Component 4: Outreach and dissemination [GEF funding - $860,000; cofinancing - $843,250] |  |  |  |  |  |  |
| Outcome 4.1: Project findings, tools and methodologies made available to state and federal decision makers as well as the public, and relevant interest groups | Public and private sector organizations at the state, federal and local levels have been provided with information materials and tool kits on project findings, tools and methodologies | An inventory of ES materials found that very little of practical use has been disseminated to state and federal decision makers, stakeholders and the public. | Tool kit for the application of ES tools and methodologies for decision-makers at the state and federal levels. Tool kit in Spanish and the Mixteco language on ES tools and methodologies and good practices in agriculture and natural resource management for use by local communities. | Systematization of methodologies and tools developed by the project, as well as results and findings. Tool kit for the application of ES tools and methodologies for decision-makers at the state and federal levels. Tool kit in Spanish and the Mixteco language on ES tools and methodologies and good practices in agriculture and natural resource management for use by local communities. | Records of dissemination of project findings, tools and methodologies Press conferences, press releases, publication launches and other public events for disseminating project findings and information Training workshops and activities on project findings, tools and methodologies with state and federal organizations and stakeholders Mid-term evaluation and terminal evaluation report | State and federal decision makers and stakeholders outside the State of Oaxaca are open to learn about project findings, tools and methodologies. |
| Outputs: - Systematization of methodologies and tools developed by the project, as well as results and findings. - Outreach and dissemination strategy for upscaling of project impact based on the systematization of project tools, methodologies, results and findings. - Information materials on project findings, tools and methodologies for (1) state and federal decision-makers, (2) stakeholders and (3) the public. - Educational and public awareness materials on the provision of ecosystem services to productive sectors in the Mixteco language. - Tool kit for the application of ES tools and methodologies for decision-makers at the state and federal levels. - Tool kit in Spanish and the Mixteco language on ES tools and methodologies and good practices in agriculture and natural resource management for use by local communities. |  |  |  |  |  |  |
| Outcome 4.2: Coordination and cooperation established with UNEP Ecosystem Management Program (EMP) | Dynamics of consultations between the project and UNEP EMP Exchanges with UNEP EMP on the Project outreach and dissemination strategy | Ecosystem management is a new priority within UNEP’s programme of work. This type of coordination and cooperation is a recently launched activity by UNEP’s Division of Environment Policy Implementation. | Coordination and cooperation is proceeding according to the project workplan. | Project findings, results and products provided for the knowledge base of UNEP’s Ecosystem Management Program | Mid-term evaluation and terminal evaluation report | A positive climate exists for exchanging knowledge and experience between the project and UNEP EMP. |
| Outputs: - Ongoing systematic consultations and coordination of project personnel with related and synergic initiatives and with UNEP EMP in the development and implementation of an outreach and dissemination strategy based on the systematization of project tools, methodologies, results and findings. - Project findings, results and products provided for the knowledge base of UNEP’s Ecosystem Management Program. |  |  |  |  |  |  |

Annex B: Responses to Project Reviews (from GEF Secretariat and GEF Agencies, and responses to comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF)

GEF Secretariat:

No issues pending at the time of PIF clearance for the CEO endorsement stage.

STAP: Consent

“STAP welcomes this science-based project to mainstream biodiversity conservation into natural

resource management, including through developing and applying new tools to inform decisions about

Ecosystem Services. STAP has no comment on the science aspects of this PIF.”

Council:

July 20, 2009 (Rev.07-22-09)

COMMENTS FROM GERMANY

76. (Project)... can be supported without a need for further comments.

Annex c: consultants to be hired for the project using gef resources

| Position Titles | $/ person week* | Estimated Person weeks** | Tasks to be performed |
| --- | --- | --- | --- |
| For Project Management |  |  |  |
| Local |  |  |  |
| National Project Coordinator | 690 | 260 | Coordinate, manage and monitor project implementation; coordinate and oversee the preparation of FSP outputs; manage FSP finances, oversee overall resource allocation, and, where relevant, submit proposals for budget revisions to the PSC and UNEP. |
| Publicity specialist | 350 | 54 | Promote publicity and public awareness of the project’s objectives, goal, activities, outputs and results through the preparation and dissemination of press releases and information materials and radio and other media programs. |
| Administrative assistant | 280 | 260 | Support the National Project Coordinator (NPC) and the Project Management Unit (PMU) on all administrative matters. |
| Technical assistant | 290 | 247 | Follow-up with implementing partners on project implementation and monitor progress towards the achievement of outputs and results. |
| Secretary | 185 | 260 | Provide secretarial support to the NPC and PMU. |
| International |  |  |  |
| Component 2 |  |  |  |
| 1 consultant | 580 | 130 | Provide guidance and technical assistance to all project activities addressing the distribution and provision of ES and the development and application of methodologies and tools for monitoring, assessing and valuing ES. |
| Component 5 |  |  |  |
| 2 consultant | 975 | 12 | Midterm evaluation |
| 2 consultant | 1015 | 14 | Final evaluation |
| Justification for travel, if any: project monitoring will require field missions to the project intervention areas. Some project coordination meetings may take place in Mexico City. |  |  |  |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Component 2 |  |  |  |
| 1 consultant | 580 | 260 | Develop and follow-up on the implementation of the workplan of the project’s Inter-institutional Working Group. |
| 1 consultant | 580 | 130 | Assist in the coordination of project activities with SAGARPA and SEDER on the promotion and application of GAP and GNRMP in existing social and economic support programs; work with SAGARPA, CONANP and CONAFOR in the development of indicators for sustainable agricultural development in the Oaxacan Mixteca. |
| 1 consultant | 460 | 121 | Develop and follow-up on the implementation of the workplan of the Project Stakeholder Advisory Committee; support project coordination with CDI and civic groups, including CRRN and CCRM. |
| 1 consultant | 690 | 35 | Prepare training, educational and information materials on ES methodologies and tools appropriate for stakeholders in the Oaxacan Mixteca. |
| 1 consultant | 580 | 156 | Provide technical assistance to the preparation of new land use plans for the four project intervention areas, particularly the 10 priority micro-watersheds. |
| 1 consultant | 690 | 52 | Provide expert legal advice on legal considerations that need to be taken into account in the preparation of new or the revision of existing land use plans. |
| 1 consultant | 580 | 260 | Analyze and propose options on the form of a fund for compensation for ecosystem integrity for the consideration of the PSC; prepare a strategy for resource mobilization for such a fund; mobilize resources for the fund for compensation for ecosystem integrity. |
| 1 consultant | 290 | 260 | Process information generated by the project on the mainstreaming of biodiversity conservation and ES into social and economic support programs in the Oaxacan Mixteca; develop, maintain and service the project’s website, with special emphasis on inter-institutional cooperation, outputs, results and related events. |
| Component 3 |  |  |  |
| 1 consultant | 580 | 130 | Integration of application and testing of good practices in agriculture (GAP) and natural resource management (GNRMP) in 10 pilot demonstration projects in priority micro-watersheds and 5 pilot demonstration projects on the use of lama bordo techniques. |
| 1 consultant | 460 | 130 | Processing of information and data compiled and generated by the pilot demonstration projects into GIS and other electronic formats. |
| 1 consultant | 460 | 139 | Integration of social, cultural and anthropological considerations into the implementation of productive and natural resource management activities by stakeholders, particularly local and indigenous communities and women; analyze and monitor the needs and concerns of participating local stakeholders; provide suggestions for improving project delivery and interaction with local stakeholders. |
| Component 4 |  |  | Activities to be assigned |
| 1 consultant | 580 | 43 | Compilation and systematization of projects findings and lessons learned; preparation of the project replication strategy. |
| 1 consultant | 580 | 34 | Preparation of educational and information materials |
| Total Person weeks |  | 2,987 |  |
| International |  |  |  |
| Justification for travel, if any: the specialist in resource mobilization will need to travel, as required, to meet with potential donors. Other consultants will have to travel to the project intervention areas to carry out their work. Some coordination meetings may take place in Mexico City. |  |  |  |

* Provide dollar rate per person week.    ** Person weeks co-financed by GEF (as part of total person weeks).

Annex d:  status of implementation of project preparation activities and the use of funds

- explain if the ppg objective has been achieved through the ppg activities undertaken.

The PPG objective has been achieved satisfactorily through the activities undertaken. Five studies were prepared and their results presented, providing useful information for designing the project proposal. Two workshops were carried out providing important inputs for the project preparation studies and for designing the project results framework. Ten project target sub-watersheds were identified and agreed upon among project partners. Project design and proposal preparation (Project Document including appendices and CEO Endorsement Request) were concluded.

- describe findings that might affect the project design or any concerns on project implementation, if any:

Several risks that might affect project implementation were identified during the PPG phase and presented in the project document. Probably the most relevant finding in this sense during the PPG phase is that the support from municipal authorities needed by watershed committees is still weak. While this will be a major challenge the project will continue to face during its implementation, the necessary considerations have been made in the design of the project regarding actions to address this issue, as described in the project document.

- provide detailed funding amount of the ppg activities and their implementation status in the table below:

| Project Preparation Activities Approved | Implementation Status | GEF Amount ($) |  |  |  | Co-financing ($)** |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Amount Approved | Amount Spent to date** | Amount Committed | Uncommitted Amount* |  |
| 1. Process development, meetings and workshops | Completed | 24,400 | 21,000 | 3,400 |  | 23,498 |
| 2. Construction of the baseline | Completed | 27,200 | 27,200 |  |  | 99,873 |
| 3. Design of the project, development strategy, definition of activities, projects, working areas and funding sources. | Completed | 3,200 | 3,200 |  |  | 103,208 |
| 4. Design of a communication and information strategy | Completed | 3,200 | 0 | 3,200 |  | 0 |
| 5. Definition of a Follow-up and Evaluation Plan | Completed | 7,200 | 7,200 |  |  | 0 |
| 6. Formulate a financial and co-financing plan | Completed | 4,200 | 4,200 |  |  | 0 |
| 7. Drafting of final Documentation | Completed | 5,000 | 5,000 |  |  | 0 |
| 8. Local transport, office costs and others | Completed | 25,600 | 25,600 |  |  | 5,147 |
| Total |  | 100,000 | 93,400 | 6,600 |  | 231,726 |

* Any uncommitted amounts should be returned to the GEF Trust Fund.  This is not a physical transfer of money, but achieved through reporting and netting out from disbursement request to Trustee.  Please indicate expected date of refund transaction to Trustee.

** Estimated as of November 2009

annex e:  calendar of expected reflows

Provide a calendar of expected reflows to the GEF Trust Fund or to your Agency (and/or revolving fund that will be set up).