Project Identification Form (PIF)

Project Type: Full Size

the GEF Trust Fund

Submission Date:  18 December 2009

| Indicative Calendar* |  |
| --- | --- |
| Milestones | Expected Dates mm/dd/yyyy |
| Work Program (for FSP) | Feb. 2010 |
| CEO Endorsement/Approval | Nov. 2010 |
| Agency Approval Date | March 2011 |
| Implementation Start | June 2011 |
| Mid-term Evaluation (if planned) | June 2013 |
| Project Closing Date | June 2016 |

* See guidelines for definition of milestones.

part i:  project IDentification

GEF Project ID:      	Project duration: 60 months

gef agency Project ID:

Country(ies): Mexico

Project Title: Fostering sustainable and competitive production systems consistent with the conservation of biodiversity

GEF Agency(ies):

Other Executing partner(s): CONABIO

GEF Focal Area (s):

GEF-4 Strategic program(s): BD-SP5 - Fostering Markets for BD Goods and Services

Name of parent program/umbrella project (if applicable):

- Project framework

| Project Objective: To conserve and protect nationally and globally significant biodiversity in Mexico through improving and mainstreaming sustainable management practices in the productive landscape in priority ecological corridors. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Investment, TA, or STAb | Expected Outcomes | ### Expected Outputs | ### Indicative GEF Financinga |  | Indicative Co-Financinga |  | Total ($) c =a + b |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |
| 1. Sustainable Production Chains and Biodiversity Conservation Mainstreaming | Investment | A. Producer use of green practices throughout their production chain increases in six priority biological corridors B. Area of land being managed compatible with biodiversity maintenance and conservation criteria increases in priority biological corridors C. Existing land-use planning instruments contribute to the management, conservation and sustainability of biological corridors | 1. 120 producer groups expand use of green practices in production chains and ecosystem services 2. 1,800 new producers trained and mainstreaming green practices into productive chains/ecosystem services 3. 10% of production landscape in six priority corridors is managed using green practices and/or protected through planning instrument(s) 4. 30 Technical Service Provider systems consolidated, strengthened and linked with green production chains | 4,590,000 | 30% | 10,700,000 | 70% | 15,290,000 |
| 2. green Production and Markets | Inv/TA | A. Access to national and international markets increases for green products B. Cooperative arrangements foster marketing of green products C.green producer associations' capacities improved for technical production, business mgt., and marketing | 1 Market information system established for green production chains 2. At least 5 production chains comply with green standards and labeling and are marketed 3. Four cooperative marketing arrangements for green goods/services are functioning 4. 20 producer's associations trained and equipped to produce goods and services that comply with verifiable green standards | 3,631,364 | 49.5% | 3,700,000 | 50.5% | 7,331,364 |
| 3. Institutional Strengthening and Standards for green Production | TA | A. Institutional capacities to support green production and financing are strengthened B. Standards developed for green production and are in use C. South-south cooperation with neighboring country institutions promotes coordination of green markets development | 1. Public-private program(s) established for promotion of commercial standards and marketing green products/production systems 2. Five green standards developed and adopted for select products 3. Third-party verification mechanisms for producer compliance with green standards developed and in use 4. Instrument(s) for financial support for green production chains/products established and in use 5. Regional program for training and technology transfer between Mexico and neighboring country institutions developed and linked to priority corridors | 2,298,000 | 50% | 2,300,000 | 50% | 4,598,000 |
| 4. Management and Monitoring |  | A.Project Mgt. and Monitoring contributes to successful implementation of project activities to support thematic outcomes | 1. Project management unit and systems, including monitoring system are fully operational throughout project’s tenure | 1,168,818 | 31.9% | 2,500,000 | 68.1% | 3,668,818 |
| Total project costs |  |  |  | A11,688,182 | 37.8% | B19,200,000 | 62.2% | 30,888,182 |

a   List the $ by project components.  The percentage is the share of GEF and Co-financing respectively of the total amount for the component.

b  TA = Technical Assistance;  STA = Scientific & Technical Analysis.

B.    Indicative Co-financing for the project by source and by NAME (in parenthesis) if available, ($)

| Sources of Co-financing | Type of Co-financing | Project |
| --- | --- | --- |
| Project Government Contribution | Cash (US$19,200,000) | Mexican Government |
| GEF Agency(ies) |  |  |
| Bilateral Aid Agency(ies) |  |  |
| Multilateral Agency(ies) |  |  |
| Private Sector |  |  |
| NGO |  |  |
| Others |  |  |
| Total Co-financing | US$19, 200,000 |  |

C.  Indicative Financing Plan Summary For The Project ($)

|  | Previous Project Preparation Amount (a) | Project (b) | Total c = a + b | Agency Fee |
| --- | --- | --- | --- | --- |
| GEF financing |  | 11,688,182 | 11,688,182 | 1,168,818 |
| Co-financing |  | 19,200,000 | 19,200,000 | n/a |
| Total |  | 30,888,182 | 30,888,182 | 1,168,818 |

D.   GEF Resources Requested by agency (ies), Focal Area(s) and country(ies)1

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Project (a) | Agency Fee (b)2 | Total c=a+b |
| Total GEF Resources |  |  |  |  |  |

1   No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

2   Relates to the project and any previous project preparation funding that have been provided and for which no Agency fee has been requested from Trustee.

part ii:  project JustiFication

- State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

Mexico is classified as one of the top five “megadiverse” countries representing approximately 12 percent of the world’s biodiversity, compared to only 1.5% of its land surface, and with high levels of endemism,. However, at the national level, only 12.9% of priority terrestrial sites for biodiversity (identified by Mexico’s biodiversity gap analysis for the Convention on Biological Diversity) actually coincide with federal, state and municipal natural reserves (3.91% of national territory),. This is also true in south and southeast Mexico, its Mesoamerican region, which has 29 protected areas covering 3.9 million hectares, . Mesoamerica is considered a global “hotspot” in terms of biodiversity, having not only a high level of species richness, but also being one of the most threatened regions in the world. According to Conservation International rates of ecosystem destruction, biodiversity loss and land degradation are high in Mesoamerica, and much work remains to be done to scale up protection measures to address these threats.

High priority ecoregions and biomes in Mesoamerica include lowland rainforests and moist forests, temperate cloud forests, dry forests, wetlands and savannas. Together, these forest formations comprise the largest continuous forest area in all of Mexico (and Mesoamerica) and the second largest in the world. In Mexico, these forests contain a significant portion of endemic flora and fauna in Mexico’s Mesoamerican region, .  In particular, Mexico’s Mesoamerican Biological Corridor (MBC) provides habitat to 173 bird species that are either threatened or at risk of extinction .

Expanding formal protected areas in Mexico is expensive (establishment and maintenance) and often difficult due to potential conflicts with private and communal land owners in the area. Moreover, studies suggest that formal protected areas alone are insufficient to protect biodiversity; as more than half of all species are found in the productive landscape. This means that biodiversity conservation efforts must include farmers and other producers in the productive landscape, if they are to be effective. Over the past decade, the conservation focus in Mexico has shifted to embrace this concept by promoting sustainable production and resource use in lands outside of protected areas. Conservation initiatives working with producers help to ameliorate the fragmentation of habitats, increase socio-ecosystemic connectivity and ensure the long-term sustainability of the productive landscape.

The GEF/IBRD Mexico Mesoamerican Biological Corridor project (2002-2009) and the GEF/UNDP Mesoamerican Biological Corridor project (1996-2006) were some of the first efforts in the region to focus on biodiversity-conservation mainstreaming in productive landscapes. The IBRD project promoted biodiversity protection and sustainable use through the establishment of five biological corridors comprising 6.76 million hectares in four states, and helped to preserve ecosystem connectivity between 24 protected areas. The project also worked to improve institutional capacities for efficient management of biodiversity-conscious development programs; and to improve livelihoods of small-scale producers in more than 400 communities by increasing sustainable forms of land use.

Despite these achievements, biodiversity in Mexico’s Mesoamerica and its established corridors is still threatened by urbanization, infrastructure, tourism, small-scale farming and poor forest management.  Forests are converted to agricultural use (including sun coffee and cacao) or pasture, or replaced by forest plantations. These changes result in habitat destruction, soil erosion, contamination of water, ecosystem fragmentation and species loss.  Threats to the region’s ecosystems are from urbanization, infrastructure, tourism, small-scale farming and poor forest management. At the same time, because most of these producers (and communities) are impoverished and marginalized, their management decisions are often heavily influenced by short-term economic needs (i.e. relative prices of different crops), which frequently ignore long-term sustainability issues and environmental concerns.

To help end the cycle of poverty and resource depletion, the private sector and markets need to play a greater role in encouraging sustainable production.  According to the 2008 World Development Report, complementary investments in market infrastructure and institutions and dissemination of research and knowledge will be needed where environmental benefits from diversification would tilt the balance in favor of alternative cropping patterns and production systems. Since the end of the 1990s, there has been a gradual increase in organic agricultural production, sustainable use of wildlife, sustainable community forestry and ecotourism in Mesoamerica due to a growing demand for goods and services considered compatible with sustainability criteria.  However, in Mexico, the market opportunities presented by alternative production systems that are compatible with biodiversity conservation are limited. Constraints for sustainably-produced (green) products include: (i) yields that are lower compared to conventional systems, due to low intensity production and weak technological appropriation; (ii) producers operating in small groups that share products and production systems; (iii) competition between producer groups; and (iv) the majority of the products have limited value added due to producers’ low capacity to ensure compliance with certifiable or green production standards.

Building on the foundation and corridor context of the Mexico MBC project, the proposed project focuses on green product and market development in biological corridors through socially and environmentally responsible production and marketing of goods and services, with a specific focus on the protection of biodiversity. Project activities will be carried out in corridors in the states of Chiapas, Campeche, Tabasco, Veracruz, Guerrero, Oaxaca, Michoacan, Quintana Roo and Yucatan.   Productive sectors targeted by the project are those that: (i) are well established in the corridors and represent opportunities to take advantage of significant market demand (including opportunities for diversification of products within sectors and on a given land holding); and (ii) can contribute to greater socio-environmental benefits through fostering their green production, including: cacao, coffee, cattle raising, forestry, honey, tourism, and chicle/gum, among others.

The project design incorporates lessons from both the regional and national MBC initiatives, including: (i) reducing asymmetries and promoting symmetries among project partners and implementation processes to increase efficiency and effectiveness; (ii) taking advantage of partner and participant strengths in order to improve technical and institutional capacities; and (iii) harmonizing diverse systems, procedures, policies, plans, programs and individual projects in order to provide a collective foundation for growth and integration.

The Global Environmental Objective is to conserve and protect nationally and globally significant biodiversity in Mexico through improving and mainstreaming sustainable management practices in the productive landscape in priority ecological corridors. Comprised of three components, the project goes beyond sustainable production capacity-building in order to help identify green markets, to improve organizational capacity of producer associations by aligning their technical production and developing their business management and marketing skills, to foster the harmonization of standards for green production, and to support regional cooperation through activities for south-south cooperation among the MBC countries.

Working with small-scale producer associations to implement this vision, the project will help communities in the corridor benefit by using their natural resources to overcome poverty and increase the competitiveness of the region, while maintaining or improving conditions for biodiversity. By supporting enhanced corridor integrity and connectivity, it will also contribute to reducing the region’s vulnerability to climate change by preserving the resilience of regional ecosystems.

The project’s three objectives are complementary and correspond to the first three project components. Project activities would be carried out in the productive landscape of six priority biological corridors in the states of Chiapas, Campeche, Tabasco, Veracruz, Guerrero, Oaxaca, Michoacan, Quintana Roo and Yucatan. Target beneficiaries are community producers and producer associations, about 30% or more of which are indigenous people.

Component 1. Sustainable Production and Biodiversity Conservation Mainstreaming. The aim of the component is to mainstream green practices into production chains in order to conserve biodiversity of global and national importance. The component would seek to have about 10% of the target area landscape incorporate green practices and/or protected through planning instruments by closure.

Component 1 would work with about 120 producer groups already employing green practices in production chains to expand, diversify and improve such activities, and with apx. 1,800 convential producers to adopt green practices into their production chains. GEF financing would be used to provide about 10-30% of competitive green production grants to community producers, with the remainder of the financing provided by existing state programs available through SAGARPA, CONAFOR, CDI, other agencies, and beneficiaries. Seed money for technical assistance would be available to help producers develop high-quality proposals needed to access grant resources.The main productive chains for which grants would be available include forestry, agro-forestry, silvo-pastoral systems, non-timber forest products, spice cultivation, coffee, cacao, beekeeping, gum extraction, and bananas, among others. Factors such as global and national conservation value, biodiversity, connectivity, threat levels, costs, suitability of goods produced and logistics, among others will be considered in the selection of specific proposals for interventions. Detailed eligibility criteria will be finalized during project preparation and agreed on at appraisal.

The project would also work with national institutions to catalyze the use of existing land-use planning instruments to promote biodiversity conservation in the target corridors. A range of such instruments already exist in Mexico; the main ones being the Community Land-use Zoning Plans (CONAFOR), Ecological Zoning Plans (SEMARNAT), Wildlife Management Area Plans (SEMARNAT), and Sustainable Municipal Rural Development Plans (SAGARPA). Because these zoning instruments have legal status, areas zoned through their use for purposes such as sustainable production or conservation are highly regarded and enforced by law.

Training would be provided to producers through Technical Service Providers (TSPs), who would themselves be required to be trained and registered with the project. Several TSP systems already exist in Mexico for forestry and various agricultural activities, though some still need to be created. The project would work with the existing TSP systems to ensure they include technicians with the requisite profile for training producers in specific green production chain practices. In cases where TSP systems are lacking, the project would design, develop and initiate the implementation of the systems, so that producers would have access to needed technology to implement green practices. By project closure, about 30 TSP systems would be fully functioning to support green production chains.

Component 2: green Production and Markets. The overall aim of the component is to improve and expand market opportunities for green goods (from the project area) at both national, local and international levels, and thereby enhance the economic sustainability of the production chains. It would seek to achieve this by helping producers to organize and equip about 20 producer associations to enable them to produce goods and services that comply with verifiable green standards. (By forming alliances, the groups will be able to achieve economies of scale needed to enter and successfully compete in markets.) The project would co-finance studies, technical assistance, legal and administrative fees to help organize the associations and equipment required to make them operational. Organized alliances would be eligible for training in themes such as marketing, advertising, contract negotiation, access to credit/financial support, feasibility studies, business planning, etc.

The component will also develop “green labeling or market branding” initiatives and help to identify and develop market niches for green products. By project closure, about four cooperative marketing arrangements for green goods and services would be fully operational, and at least 5 production chains would be expected to be in compliance with green standards, marketing their products, and have indicative green labeling. A public-access market information system would be developed to help green producers and second-tier producer associations identify potential market opportunities and information needed to develop them. Public awareness campaigns would  be financed, in order to raise consumer awareness of the importance of the “green products” and to underscore their value.

Component 3. Institutional Strengthening and Standards for green Production. The objective of this component is to build institutional capacities to support and encourage the use of green products (and green production chains). Although productive activities are carried out by the private sector, most green producers in the project area lack the skills, tools and experience needed to promote their products effectively. With this in mind, public-private outreach and promotion programs would be developed in concert with producers, second-tier associations, and government agencies to promote commercial standards and further consumer awareness of green products and production chains, encourage sales and expand market opportunities.

In order to distinguish and promote “green products” in markets, the component would develop “green standards” and “market brands” for at least 5 products/production chains in cooperation with technical experts, producers and public institutions. (Standards or brands would have to meet strict environmental, socioeconomic, health and cultural criteria.) In addition, to ensure compliance with standards and inspire consumer confidence,  third-party verification mechanisms for the green standards would be developed and implemented.

Because most green producers lack the necessary capital to transition from convential to green practices, financial instruments would be developed to support such efforts. GEF incremental funding would be used for the design of the instruments, while local funds would cover the actual financing. Presently under consideration are proposals for adjustments to existing government-finance programs in order to support green production chains, guarantees to underwrite loans to producers (the vast majority of which cannot comply with conventional lending norms) and others.

Because corridors extend across national boundaries, a regional program for training and technology transfer between Mexico and neighboring country institutions linked to the priority (project) corridors would be established and implemented. This will help to provide a corridor-consistent approach to management needed for biodiversity conservation, and the development of international marketing initiatives for green production chains and their products.

Component 4: Project management and monitoring. Component 4 provides the technical and fiduciary support elements to ensure efficient execution of the project through administration, monitoring and evaluation, planning and coordination.

- Describe the consistency of the project with national/regional priorities/plans:

The proposed project is consistent with a variety of national priorities and plans, including: The National Development Plan 2007-2012 and its strategies to promote ecotourism for conservation and economic development in rural areas and the sustainable management of natural resources through productive projects in rural areas. Through the on-the-ground investments and activities to promote harmonization of sector programs for green production and marketing, the project falls directly in line with several aspects of the National Environmental and Natural Resources Program 2007-2012 (SEMARNAT), including its focus on establishment of biological corridors, restoration of degraded and deforested landscapes, promotion of synergies among production and conservation-oriented government agencies, as well as its specific attention to supporting the mission of the Mexico Mesoamerican Biological Corridor (to increase connectivity of ecosystems in the corridor via sustainable use initiatives, integration of public policies and the coordination of local governments, citizen participation, producer groups and especially indigenous peoples). Moreover, the Special Concurrent Program for Sustainable Rural Development 2007-2012 coincides nicely with the proposed project via its goal to preserve and sustainably use ecosystems and to reverse their deterioration by incorporating actions for soil and biodiversity conservation, particularly in agricultural activities. It also contributes to an important goal of the Special Climate Change Program 2009-2012: to increase conservation and sustainable forestry management, to enhance connectivity of ecosystems and priority biodiversity areas so that natural systems may prove more resistant and resilient to the potential effects of climate change.

- Describe the consistency of the project with gef strategies and strategic programs:

The project responds to the Operational Programs for Biodiversity Ecosystems (OP3) and Mountain Ecosystems (OP4) within the GEF’s Biodiversity Window. GEF Biodiversity Strategic Priorities underlie the fundamental concept of the project, in particular SP4: Strengthening Policy and Regulatory Frameworks for Mainstreaming Biodiversity and SP5: Fostering Markets for Biodiversity Goods and Services. The project directly supports the conservation of biodiversity of global importance through developing market incentive measures by combining productive, socioeconomic, and environmental concerns within the context of the Mexico’s Mesoamerican Biological Corridor, strengthening the integration of biodiversity conservation in production sectors important in Mexico’s Mesoamerica.

By consolidating the production and marketing of environmentally and socially sustainable (green) cacao, coffee, cattle raising, forestry, honey, tourism and chicle the project would help reconcile biodiversity conservation with the needs of local (primarily indigenous and rural poor) communities. This would be achieved, among others, by resolving problems associated with inadequate business skills of producers in Mexico’s MBC and buyers in national and international markets. This includes: (i) the lack of information that producers have regarding markets, including the appropriate environmental and social criteria increasingly demanded by markets and of the MBC products demanded by buyers; (ii) attaining an acceptable quality and volume of products for sale in international markets through appropriate and efficient technical production and cooperation between producer groups; (iii) weak or inadequate quality of marketing techniques; and (iv) the perceived lack of interest or knowledge on the part of major buyers to engage with community actors within their marketing supply chains. Sustainable production and management of the above-mentioned sectors in line with internationally recognized best practice and certification programs is fundamental to underpinning national and regional strategies for biodiversity conservation in Mexico’s MBC. Moreover, the project integrates the on-the-ground activities and the development of such capacities and markets into strategies for strengthening institutional capacities and sector policies: creating national standards for green products and creating mechanisms for third-party verification (policy and regulatory framework), as well as developing public-private programs to increase promotion of commercial standards and marketing of green products and production systems.

- justify the type of financing support provided with the gef resources:

The GEF grant will provide the needed incremental investments that would be more difficult to attain through government budgetary or non-governmental sources for the coordinated investments in technical production, organizational capacity-building and coordination, standards harmonization and development of private-public programs necessary to achieve sustainable biodiversity conservation through successful integration of Mexico’s MBC small-scale producers into green markets. The proposed GEF financing will complement counterpart investment resources provided by the GoM, which have been allocated to the Mexico MBC to continue supporting its achievements.

- Outline the Coordination with other related initiatives:

At the regional level, the project complements three major initiatives in the Mesoamerica region, and will coordinate with them. They are:

- the Regional Cooperative Program for Technological Development in Coffee Growing in Central America (Programa Cooperativo Regional para el Desarrollo Tecnológico de la Caficultura en Centroamérica or PROMECAFE), executed by the Inter-American Institute of Development Assistance for Agriculture (Instituto Interamericano de Cooperación para la Agricultura or IICA) which provides technical assistance for the sustainable cultivation of coffee;

- ii) the Program for Integrated Management of Ecosystems in Indigenous Peoples and Communities (Programa de Manejo Integrado de Ecosistemas en Pueblos Indígenas y Comunidades or PMIIE), implemented by the Indigenous and Campesino Coordinating Association for Central American Community Agro-Forestry (Asociación Coordinadora Indígena y Campesina de Agroforestería Comunitaria Centroamericana or ACICAFOC) and working on biodiversity conservation themes in the Mesoamerican Biological Corridor through strengthening the capacities of indigenous peoples and campesino communities;  and

- The Latin American Agro-Ecological Movement (Movimiento Agroecológico Latinoamericano or MAELA) a stakeholder group which includes civil, campesino, academic and consumer organizations addressing productive green concerns.

The project will also coordinate with a number of IBRD investments and GEF projects, including the following:

- SINAP/GEF/IBRD project The Natural Protected Areas System Project which aims to provide protection to select natural areas; and the Integrated Ecosystem Management Project (Three Ecoregions GEF/UNDP) which aims to create new protected areas;

- the recently approved Needs Assessment and Priority Setting for the Conservation (EA GEF/UNDP) which will provide guidance for expansion of the national protected area system;

- a proposed GEF/UNDP Project to be executed by the Rainforest Alliance, Transforming management of biodiversity rich community production forests;

- GEF/IBRD/Pronatura’s Non timber forest products of ritual use extractive reserve model (Sacred Orchids) which is working on the sustainable production dimension of orchids;

- IBRD Forest Carbon Partnership Facility, which is working with the government in the development of strategies and enabling activities for the reduction of deforestation and degradation; and

- IBRD/GEF/Conafor Payment for Environmental Services Project, which provides payments to land-holders and communities to provide protection to high-value environmental areas for ecosystem service, principally water.

The project will also take advantage of existing land-use planning and zoning instruments to further the development of sustainable green production chains and conservation activities in the project area’s productive landscape, including:

- Community Land-use Zoning Plans (CONAFOR);

- Ecological Zoning Plans (SEMARNAT);

- Wildlife Management Area Plans (SEMARNAT); and

- Sustainable Municipal Rural Development Plans (SAGARPA).

Finally, the project builds on experiences and lessons learned for sustainable coffee production and markets (El Triunfo GEF/IBRD) and the reorientation of public investment in connectivity areas between relevant national protected areas executed by the Regional and Mexico-Mesoamerican Biological Corridors and their stakeholders.

- Discuss the value-added of GEF involvement in the project  demonstrated through incremental reasoning :

Estimates for protection of the target corridors’ ecosystems (both in quantity and quality) included in the project area are below international levels suggested by IUCN and most conservation professionals. Many critical ecosystems are threatened by unsustainable development including human settlements, tourism and infrastructure as well as increased transformation to intensive agricultural production, primarily for exports.  Under this scenario habitats would continue to be reduced and viable populations of threatened species will slowly disappear without the incremental investments necessary to link producer groups with green markets and thus stimulate a critical mass of alternative production systems that are compatible with conservation.

While there is potential for payments for environmental services  to complement this project’s activities, they will only be available for a small portion of the corridor and do not currently cover sustainable agricultural production.

The productive landscape of Mexico’s MBC, which harbors the bulk of the country’s biodiversity, is currently shaped by market forces, which discourage investments in sustainable production systems on a scale necessary for long-term conservation.  Moreover, non-governmental efforts in green production are dispersed and small-scale. While other efforts to improve green production in sectors such as coffee, cacao, and timber are well established, innovative investments are needed to diversify production and develop new markets in order to protect against fluctuations in prices, which can lead to negative impacts on the environment.

Given their non-traditional and innovative nature , GEF funding will provide the needed incremental investment to develop sustainable green production chains, including appropriate technology, capacity-building for technical production, coordination of producer groups, assisted development of marketing strategies dissemination, and community land use planning. Moreover, to ensure that biodiversity benefits are accruing and to strengthen certification and branding efforts, GEF incremental investment will support the development of a comprehensive monitoring and evaluation/verification system.  GEF resources will also assist in identifying additional bottlenecks in production chains including national and regional policies needed to promote sustainability. As a result, producers will be trained to use tools allowing them to access growing national and international markets through improved information, better technical assistance and farming technology, expansion of branding and marketing efforts with increased production volumes, and better quality/value added products. This will translate into increased corridor connectivity and improved habitats for nationally and globally significant biodiversity.

The proposed amount of $11.69 million represents the Mexican Government’s estimate of the incremental cost required to achieve expected global benefits that would not be fundable through existing programs. This investment would also contribute to establishing a framework to channel ongoing investments and to leverage new investments in the forestry and conservation sectors of Mexico; improving their application to sustainable production would generate greater economic stability to complement the substantial social and environmental gains made through previous GEF and GoM community-conservation project.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved, and if possible including risk mitigation measures that will be  taken:

1.	Increase in frequency of extreme weather events due to climate change poses threats to MBC ecosystem integrity and stability. By working in productive landscapes to improve sustainable natural resource use, the project will be contributing to increased connectivity of ecosystems and habitats (particularly between formal protected areas). This includes practices such as reducing erosion from farms, increasing forest cover with native species, and expanding sustainable forestry practices. As a result, the project will contribute to increasing vulnerable ecosystems’ (in addition to protected areas’) resistance and resilience to climate change.

2.	Lack of interest in participation by producers. While the previous Mexico MBC project has been widely publicized in the region, there may be communities in some priority intervention areas that are not familiar with its specific objectives for improving sustainable use and producer livelihoods. This may especially be the case in those states where new corridors are planned (Tabasco, Oaxaca, Veracruz). Moreover, there may be skepticism regarding the stability of green markets to provide increased incomes. Mitigating this potential risk will be for the project to establish strong outreach, dissemination and capacity-building programs while helping to integrate producers into green markets.

3.	While the project aims to integrate producer groups into green markets by helping to develop organizational capacity and second-tier producer associations, an additional organizational layer may add complexity to the production chain. The risk can be mitigated by ensuring good participating, optimizing use of existing producer group structures and leadership capacities (to feed into the second-tier producer associations), and promoting transparent communication and decision-making. Participatory approaches will be used in addition to the strengthening of existing coordination and land-management structures for productive landscapes.

- describe, if possible, the expected cost-effectiveness of the project:

The project is expected to be highly cost-effective because: (a) it supports a market-driven approach based on green rewards, which has been proven to be a cost-effective approach to the sustainable management of natural resources and conservation of biodiversity; (b) it has very low direct costs, as it builds on the institutional arrangements  and financial resources already in place to reorient rural development ministry investments toward niche markets; and (c) though protecting biodiversity through market incentives requires a significant initial investment to remove barriers, it tends to be self-sustaining. National protected areas, in general, are not self financing and require continued financial support.

The national implementing agency, CONABIO, is an Inter-Ministerial Commission mainly dedicated to develop, maintain and update the National System of Biodiversity Information (SNIB). As a high level commission chaired by the Head of State and which includes representatives from a range of sectors (foreign relations, energy, national economy, agriculture, livestock, rural development, fisheries, etc.) CONABIO is well placed to provide the necessary coordination between this and other related initiatives through its multi-sectoral steering committee, which will increase the project’s cost effectiveness.

- Justify the comparative advantage of GEF agencY:

The World Bank has a long and successful partnership with the Mexican Government in environmental, forestry and biodiversity concerns, including several highly successful projects and best practices. Moreover, the Bank has been working with the government since 1992 in biodiversity issues. Relations are established with a wide range of government institutions, and the Bank can mobilize staff rapidly to assist the government on the proposed project.

Working together, Bank managed projects contributed to the creation of the Natural Protected Areas Commission (CONAM) and the National Protected Area Trust Fund (through an initial GEF contribution). The National Forestry Commission (CONAFOR) has implemented two flagship IBRD forestry projects (Community Forestry I and II) which have been recognized as international best practices. CONAFOR is presently implementing the  IBRD/GEF Payment for Environmental Services Project and working with the Bank in the development of the country’s Climate Change Adaptation Strategy and the National REDD Strategy (through the Bank’s Forest Carbon Partnership Facility). In 2008, CONAFOR absorbed the activities initiated by the successful GEF Community and Indigenous Biodiversity Conservation Project (implemented by NAFIN). Within CONABIO, the Bank implemented the GEF Mesoamerican Biological Corridor Project, which closes in December 2009. At the regional, the Bank is working with Mexico (CONAM), Belize, Guatemala and Honduras in the Mesoamerican Barrier Reef System.

The Bank also conducted analytical work with the Mexican Government including a Public Expenditure Review for the Agriculture and Rural Development Sector, and is currently preparing a Development Policy Loan with the agriculture ministry (SAGARPA), the main partner in the implementation of the proposed new GEF operation. Over the last few years, the Bank has fostered a number of international-level contacts and working relationships with importers/buyers to find markets for sustainably produced products associated with the IBRD investments.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the country endorsement letter(s) or regional endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Claudia Grayeb Bayat | GEF Focal Point and Director General of North America, Asia-Pacific, and the Caribbean | Treasury (Secretaría de Hacienda y Crédito Público) | October 9, 2009 |

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Steve Gorman, GEF Agency Coordinator, The World Bank |  | December 18, 2009 | Jocelyne Albert Sr. Regional Coordinator The World Bank | 202-473-3458 | jalbert@worldbank.org |

Project ID number will be assigned by GEFSEC.

Select only those focal areas from which GEF financing is requested.

Include project preparation funds that were previously approved but exclude PPGs that are awaiting for approval.

Endemism on the national level: 50-60% of plant species (15000 species); 32% of mammals; 10% of birds; 57% of reptiles; and 65% of amphibians.

CONABIO. 2006. Capital natural y bienestar social. Comisión Nacional para el Conocimiento y Uso de la Biodiversidad, México.

CONABIO. 2009. Capital natural de México, vol. II: Estado de conservación y tendencias de cambio. Comisión Nacional para el Conocimiento y Uso de la Biodiversidad, México.

Urquiza-Haas, T., M. Kolb, P. Koleff, A. Lira-Noriega, and J. Alarcón. 2000. Methodological Approach to Identify Mexico’s Terrestrial Priority Sites for Conservation. Gap Analysis Bulletin No. 16:61-71.

Mesoamerican Mexico includes the country’s southern states that fall within the neotropics, including Yucatan, Quintana Roo, Campeche, Chiapas, Tabasco, Oaxaca, Veracruz, Guerrero, etc.

CONABIO. 2003. El Corredor Biológico Mesoamericano y el Corredor Biológico Mesoamericano en México. Biodiversitas No. 47:1-7.

Myers, N., Mittermeier, R., Mittermeier, C., Fonseca, G., Kent, J. 2000. Biodiversity hotspots for conservation priorities. Nature 403: 853-858.

CI. 2004. Perfil de ecosistema. Región norte del hotspot de biodiversidad de Mesoamérica. Belice, Guatemala, México. Critical Ecosystem Partnership Fund. 64 pp.

For example, endemic species found in Mexico’s MBC include 2,941 endemic plants, 22 endemic bird species including birds such as the cordoniz yucateca (Colinus nigrogularis) and the colibrí cola hendida (Doricha eliza). In addition, endemic mammals and amphibians include the rata arborícola (Tylomys bullaris), the Thogessa genowaysi bat, and the salamander Ixalotriton níger, among others.

Rodríguez, P. 2008. “Sección 2. Biodiversidad en el Corredor Biológico Mesoamericano-México: diversidad de especies y de ecosistemas.”, p17-35. En CONABIO. 2008. Importancia del capital ecológico de la región del Corredor Biológico Mesoamericano-México: evaluación de la biodiversidad, ciclo hidrológico y dinámica de la cobertura forestal. Centro de Investigación en Geografía y Geomática – CentroGEO. 95 pp.

Threatened species and species at risk of extinction are two categories included in the Norma Oficial Mexicana NOM-059-SEMARNAT-2001, which determines the categories for Mexican species of fauna and flora at risk. In Mexico’s MBC, the IUCN identifies seven bird species that are either endangered or critically endangered.

Brandon, K., L.J. Gorenflo, A.S.L. Rodrigues, and R.W. Waller. 2005. Reconciling biodiversity conservation, people, protected areas, and agricultural suitability in Mexico. World Development 33:1403-1418; Cantú, C., G. Wright, M.J. Scott, and E. Strand. 2004. Assessment of current and proposed nature reserves of Mexico based on their capacity to protect geophysical features and biodiversity. Biodiversity Conservation 115:411-417; Ceballos, G. 2007. Conservation priorities for mammals in megadiverse Mexico: The efficiency of reserve networks. Ecological Applications 17:569-578; Ortega-Huerta, M.A. and A.T. Peterson. 2004. Modeling spatial patterns of biodiversity for conservation prioritization in North-eastern Mexico. Diversity and Distributions 10:39-54.

2008 World Development Report. Moreover, participatory approaches involving farmers and communities are especially important for natural resources management because of the enormous agroecological diversity in less-favored areas and the need to select and adapt technology to fit local needs and conditions. Community approaches can provide the secure property rights and collective action for improving natural resource management.

Through a coordinated, regional effort, the GEF/UNDP Mesoamerican Biological Corridor project created a framework to conserve important Mesoamerican ecosystems throughout Central America; ecosystems that are also home to hundreds of thousands of poor, marginal communities (many of them indigenous). Biological corridors increase connectivity of ecosystems and fragmented habitats outside of protected areas by promoting sustainable use programs and activities that are compatible with conservation goals. As such, they have served as important planning and conservation tools for sustainable development in the region.

The five corridors include: Selva Maya-Zoque in Chiapas (2.0 million hectares); Sierra Madre del Sur in Chiapas (0.77 million hectares); Sian Ka’an – Bala’an K’aax in Quintana Roo (1.35 million hectares); Calakmul – Bala’an K’aax in Campeche (1.46 million hectares); and Costa Norte de Yucatan in Yucatan (1.18 million terrestrial hectares and 0.45 million marine hectares).

It is partly due to the scale and pace of this habitat loss and fragmentation (which occur throughout the Central American region) that Mesoamerican ecosystems are considered “critical sites” in terms of biodiversity. K. Miller et al., 2001. En busca de un enfoque común para el Corredor Biológico Mesoamericano, WRI-WWF-CATIE, Washington DC, USA.

Eighteen percent of those corridor areas with forest cover in 1990 were deforested by 2000, principally on the Yucatan Peninsula, and with more than 51% of those areas with forest loss having annual rates of deforestation greater than 4%. The annual deforestation rate of the entire Mesoamerican biome is 2%. In addition, from 1990 to 2000, forest with some form of fragmentation increased from approximately 40% to 57%. At the same time, 28% of corridor surface area recuperated forest cover with an annual rate greater than 1%, mostly in jungles of the Yucatan Peninsula and areas adjacent to the corridors. Mora, F. 2008. “Sección 4. Caracterización de la cobertura forestal en el Corredor Biológico Mesoamericano-México: patrones espaciales en la pérdida y fragmentación de bosques.”, p17-35. En CONABIO. 2008. Importancia del capital ecológico de la región del Corredor Biológico Mesoamericano-México: evaluación de la biodiversidad, ciclo hidrológico y dinámica de la cobertura forestal. Centro de Investigación en Geografía y Geomática – CentroGEO. 95 pp.

CCAD. Estrategia Regional Agroambiental y de Salud de Centroamérica 2009-2024.

This is especially the case in Canada, the United States and the European Union.

Corridors established by the GEF/IBRD Mexico MBC project are located in Chiapas, Campeche, Quintana Roo, and Yucatan. Corridors in Tabasco, Veracruz, Guerrero, Oaxaca and Michoacan are to be delineated for purposes of the project, using Mexican funds. For example, the identification of priority sites for biological corridors in Tabasco is already well advanced. Three corridors are proposed, which will cover 1.4 million hectares and connect four protected areas representing 1.05 million hectares.

Cacao is cultivated primarily in Tabasco and Chiapas, largely by indigenous communities. However, it is vulnerable to market prices and in times of low demand, cacao production may be replaced by more lucrative and environmentally-damaging activities, including extensive cattle ranching. Diverse shade cacao systems support greater levels of biodiversity than other tropical crops and they are suitable for reforesting areas that have been clear felled. Moreover, they are a good option for small producers given their lower production costs and provision of additional environmental goods including organic material, firewood, medicine, food and building material.

In Mexico, there are over 280,000 coffee producers, the majority of them indigenous people living in marginalized zones. Over 80% of production is earmarked for export, with Chiapas being the main national producer. International coffee prices in traditional markets have decreased due to overproduction, prompting farmers to choose more lucrative production activities in the short term. However, Mexico is also the world’s leading producer of certified organic coffee, international demand for which has increased at an annual rate of 15% over the past decade. Shade coffee systems (as a certifiable production process) have greater biomass, more nutrients and biodiversity, fewer weeds and pests and a better water and microclimate balance.

From 1940 to 2004, the area used for cattle raising in Mexico rose from 75 to 272 million acres, while the number of head of cattle rose from 25 to 75 million. While extensive cattle raising has been extremely popular because of low initial investment (i.e. forest clearing), it is highly inefficient, resulting in a low yield of only 22 to 73 pounds of meat per acre. As evidenced by the GEF/WB Regional Integrated Silvopastoral Approaches to Ecosystem Management project (P072979), intensive cattle raising systems provide both significant biodiversity and social benefits.

Of the 140 million acres of forests and woods in Mexico, 80% are communally owned and belong to approximately 8,500 ejidos and communities with an estimated population of 12 million inhabitants, many of whom are indigenous people living in areas with high rates of marginalization. While Mexico has the world’s greatest diversity of pine species (for example) numbering over 50, it also has one of the highest rates of deforestation: it is estimated that between 914 and 1,780 thousand acres of woodland are lost annually.

Mexico produces 57,000 tons of honey per year and is the world’s sixth largest producer. While half of this is consumed nationally, annual per capita consumption is barely half a pound and the country remains the world’s third largest exporter. There are currently about 40,000 beekeepers nationwide, with over 30% of production being concentrated in Yucatan, Campeche and Quintana Roo: 17,000 beekeepers managing over 0.5 million beehives. Mexico is also the world’s third largest organic honey exporter with 1,400 tons in 2006. New market opportunities exist in the differentiation of honey varieties, especially increasing production of honey from the native Royal Maya bee, which can generate prices of $200 pesos per pound. In the past few years, world market trends have shown that consumers prefer a product clearly identified by its blossom or origin – another market opportunity requiring training in production, certification and labeling.

In Mexico, ecotourism has experienced a 25% annual growth rate over the last two decades; it is a kind of tourism that attempts to bring visitors into contact with nature, preserve the environment and improve the well-being of local populations, in many cases serving as an important supplement for other resource based livelihoods. With the Yucatan Peninsula as one of the most popular tourist destinations in Mesoamerica, there are ample opportunities to develop a robust and sustainable ecotourism industry with the proper training and investments.

The chicle tree is one of the most common in the Yucatan Peninsula’s Atlantic forests and in certain areas, there are up to 75 per acre. Rubber extraction is currently the second most important forest activity in the region, exceeded only by the lumber business. It involves approximately 2,200 chicle tappers working in a wooded area of 2 million acres of rainforest using a certification program based on international criteria of the Forest Stewardship Council, and which produces 300 tons of chicle annually. With support for more small-scale production and expanded marketing, production could reach at least 1,000 tons. Chicle extraction is a crucial economic activity for the inhabitants of the Gran Peten and chicle tappers are zealous guardians of the chicle tree and its environmental surroundings.

Escardi, F. 2008. Biodiversity and responsible consumption. Mesoamerican Biological Corridor-Mexico; CONABIO; Semarnat; Fomento Ecológico Banamex, Gaia Editores, Mexico, 112 pp.

SAGARPA: Secretary of Agriculture, Fisheries and Food; CONAFOR – National Commission of Forestry; CDI – National Commission for Indigenous Peoples’ Development.