Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund:  GEF TF

PART I: Project Information

| Project Title: | Strengthening of National Capacities for the implementation of the “Nagoya Protocol on Access to Genetic resources and the Fair and Equitable Sharing of Benefits Arising From their Utilization to the Convention on Biological Diversity.” |  |  |
| --- | --- | --- | --- |
| Country(ies): | México | GEF Project ID: | 5738 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 5375 |
| Other Executing Partner(s): | SEMARNAT, CONABIO, IMPI, CDI | Submission Date: | March 27, 2014 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) | 36 |
| Name of parent program (if applicable): - For SFM/REDD+ - For SGP | N/A | Agency Fee ($): | 216,895 |

A.  indicative Focal AREA STRATEGY Framework:

| Focal Area Objectives | Trust Fund | Indicative Grant Amount | Indicative Co-financing |
| --- | --- | --- | --- |
|  |  | ($) | ($) |
| - OBJECTIVE FOUR: Build Capacity on Access to Genetic Resources and Benefit Sharing (ABS) | GEF TF | 2,283,105 | 8,429,862 |
| Total Project Cost |  | 2,283,105 | 8,429,862 |

- indicative Project Description Summary

| ### Project Objective: ### Enhance in Mexico in a participatory manner, the capacities of national authorities (SRE, SEMARNAT, SAGARPA, CDI, SE), as well as the legal and administrative framework in relation to genetic resources, associated traditional knowledge and benefit-sharing, according to institutional conditions for the implementation of the “Nagoya Protocol on Access to Genetic resources and the Fair and Equitable Sharing of Benefits Arising From their Utilization to the Convention on Biological diversity ” (NP). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative ### Grant Amount ($) | ### Indicative Co-financing($) |
| 1. Adjusting the legal framework and establishing public policy measures that regulate the access utilization of GR and associated TK arising from the fair and equitable benefit-sharing. | TA | 1.1. Bill proposal amends the national ABS legal framework | 1.1.1.- National Legal Framework Analysis and Diagnosis; of conceptual aspects and technical and operative aspects to determine the scope and interpretation of the standards in effect, determine gaps and inconsistencies, identify areas of interest of FG Agencies as well as their regulatory needs and objectives to be attained regarding GR. | GEF TF | 184,666 | 413,200 |
|  |  |  | 1.1.2. Bill proposal aligns the national ABS framework with the Nagoya Protocol. |  | 59,796 |  |
|  |  |  | 1.1.3. Awareness and training of at least 37 key lawmakers on access to GR and benefit- sharing. |  | 119,591 |  |
|  |  | 1.2. National Strategy for conservation and sustainable use of GR, including associated TK. | 1.2.1 Proposal of a Post 2015 National Strategy for conservation and sustainable use of GR, developed and accepted by the stakeholders, |  | 184,666 |  |
| 2. Strengthening of national institutional capacities | TA | 2.1.- The national Focal Point and National Authorities have been identified and possess the capacity to execute the NP. Capacities of national focal point and national authorities on ABS improved by at least 30% as measured by UNDP´s ABS capacity development score card | 2.1.1.- At least 24 Officers of the National Focal Point and National Authorities (SEMARNAT, PROFEPA, CONANP, SAGARPA, SEconomía/IMPI, SRExteriores, CDI, CONABIO) trained in: a) Legal Instruments (measures and actions) existing in the national framework in effect to comply with NP provisions. b) Application of Good Practices Manuals on the sustainable use and management of genetic resources (GR) to facilitate the implementation of the NP among users and suppliers c) Monitoring the utilization of GR, including different research, development, innovation, pre-commercialization or commercialization stages. | GEF TF | 369,331 | 412,995 |
|  |  |  | 2.1.2.- Inter-institutional mechanisms to facilitate monitoring of access to GR, benefit sharing and compliance with the NP. These mechanisms include: a) A database with information on access permits (that takes into account the national regulation to comply with the NP) to follow up access requests, which shall be fed by each agency. This database will be related to GR Monitoring and Supervision System and associated Traditional Knowledge (TK). |  | 179,387 |  |
|  |  |  | b) Assessment and selection of ABS checkpoints |  | 89,693 |  |
|  |  |  | c) Creation of the National Access and Benefit-Sharing Clearing-House in order to comply with Article 14 of the NP. |  | 89,693 |  |
| 3. Protecting traditional knowledge and improving the capacities of indigenous and local communities and other stakeholders to generate social awareness on conservation and sustainable use of biodiversity, GR and associated TK, as well as benefit-sharing arising from their access and utilization. | TA | 3.1.- Community protocols to facilitate ABS | 3.1.1Community protocols drafted in a participatory manner with indigenous and local communities | GEF TF | 335,484 | 7,202,245 |
|  |  | 3.2.- Traditional knowledge registry | 3.2.1 Traditional knowledge registry proposal drafted in a participatory manner with indigenous and local communities |  | 257,121 |  |
|  |  | 3.3 80% of the indigenous and local communities targeted by the program is aware of the TK registry and community protocols | 3.3.1 Guidelines for the protection of traditional knowledge associated with GR taking into consideration the findings of the “Consultation on mechanisms to protect traditional knowledge, cultural expressions, natural, biological and genetic resources of indigenous peoples ” , among others. 3.3.2 Sensitization and awareness program including training and dissemination material (brochures, trifold leaflets, manuals, posters, etc.) on the importance of conservation and sustainable use of biodiversity and associated traditional knowledge. 3.3.3 Knowledge, attitudes and practices (KAP) assessment surveys targeting indigenous and local communities assess their awareness on ABS issues, including the project´s proposal to protect traditional knowledge |  | 304,958 |  |
| Subtotal |  |  |  |  | 2,174,386 | 8,028,440 |
| Project Management Cost (PMC) |  |  |  | GEF TF | 108,719 | 401,422 |
| Total Project Cost |  |  |  |  | 2,283,105 | 8,429,862 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
| National Government | CONANP | In-kind | 45,000 |
| National Government | DGSPRNR | In-kind | 198,172 |
| National Government | DGGFS | In-kind | 47,000 |
| National Government | DGVS | In-kind | 116,738 |
| National Government | PROFEPA | In-kind | 19,181 |
| National Government | CONABIO | In-kind | 79,482 |
| National Government | SFNA | In-kind | 110,688 |
| National Government | UCPAST | In-kind | 91,615 |
| National Government | UCAI | In-kind | 46,244 |
| Bilateral Aid Agency(ies) | GIZ-CONABIO Project | Cash | 7,425,742 |
| GEF Agency | UNDP | Cash | 250,000 |
| Total Cofinancing |  |  | 8,429,862 |

D. indicative trust fund Resources ($) Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount ($) (a) | Agency Fee ($) (b) | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF TF | Biodiversity | Mexico | 2,283,105 | 216,895 | 2,500,000 |
| Total Grant Resources |  |  |  |  |  |  |

- In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this table. PMC amount from Table B should be included proportionately to the focal area amount in this table.

E Project preparation grant (ppg)

The most recent and relevant program reports and instruments on the subject in Mexico,  identify the development and implementation of the legal framework on access to GR as a priority, complex, segmented, incomplete and outstanding area; thus it is important to make a diagnosis of the legal framework on GR and fair and equitable sharing of benefits arising from their utilization.

Please check in the appropriate box for PPG as needed for the project according to the GEF Project Grant:

Amount Requested ($)       Agency Fee for PPG ($)

$50k for projects up to & including $1 million	      	       ___25,000________         ___2,375_____

PPG AMOUNT requested by agency(ies), focal area(s) and country(ies) for MFA and/or MTF Project only

| Trust Fund | GEF Agency | Focal Area | Country Name | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| GEF TF | UNDP | Biodiversity | México | 25,000 | 2,375 | 27,375 |
| Total PPG Amount |  |  |  |  |  | 27,375 |

PArt ii: project JustiFication

A. Project Overview

A.1. Project Description

1) Global environmental problems, root causes and barriers that need to be addressed

- International treaties, in particular environmental treaties, require national application mechanisms to allow compliance with legal provisions to inure to the benefit of proper application of the treaty in harmony with national laws.

- In 1993, Mexico endorsed the CBD, whose three objectives include: conservation of biological diversity, its sustainable utilization and sharing of benefits arising from the utilization of GR.

- Article 15 of the CBD sets forth the Recognition of sovereign rights of States over their natural resources; the authority to determine access to GR rests with the national governments and is subject to national legislation. This means the international community has already recognized the role and importance that GR have.

- To that effect, and in order to regulate the contents of the said provision, and to reach the third objective of the CBD, the Contracting Parties decided to engage in negotiations to develop an international instrument capable of regulating its content, namely, the NP.

- The NP will allow the development of the provisions of Article 15 of the CBD and at the same time, to achieve the third objective of the CBD, fair and equitable sharing of benefits arising from the utilization of GR.

- The NP sets forth that in the exercise of their sovereign rights, national governments are responsible for establishing (legislative, administrative or political) measures to make certain that prior informed consent is obtained to grant access to their GR and guarantee that the benefits arising from their utilization are shared in a fair and equitable way.

- There is a high degree of sensitivity regarding illegal appropriation of GR and associated traditional knowledge. At the political arena, such sensitivity has been the reason for which the debates in the last 10 years have not been able to generate yet, consensus over wide and systematic legal measures, necessary to regulate access and fair and equitable sharing of benefits.

- Up to date, only the Forest Legislation amended in 2006, has included a procedure to obtain prior informed consent for cases in which the protection or utilization activities in a forest environment are tied to traditional knowledge. Insufficient implementation of access and fair and equitable sharing of benefits in the national context has limited the development of research on the use of GR and associated TK, as well as the involvement of the national and foreign private sector. One of the main problems is that the change in the intended use of collections for research purposes to commercial use is not regulated; in addition, research and development processes are oftentimes conducted in a jurisdiction other than those in which the access to resources was granted. Thus, information exchange between user countries and their suppliers to verify legal and legitimate use and access is essential.

- The country has not been able to implement the objective with regards to fair and equitable sharing of benefits which is part of one of the CBD objectives and the foundation for the preparation of the NP. For this end, new agreements between suppliers of biological and genetic resources and research institutes, private companies and social enterprises interested in their use, are required. To date, there are few specific experiences of due processes in the world that define fair and equitable benefit-sharing; these scattered cases have been systematized recently for their analysis and dissemination. In particular, the new provisions in the NP require a structured experience exchange between GR and associated TK suppliers and users that generates inputs for new procedures at institutional, academic and social levels.

- The ratification of the NP by Mexico, and the instrumentation of the NP will enable the protection, conservation and sustainable use of such resources, thus, an extended diagnosis of the national legal framework is necessary in order to determine the regulatory, normative and promotion needs on access to GR and fair and equitable sharing of benefits arising from their utilization. This will require the involvement of the Mexican society as a whole to sensitize them and make them aware of the joint responsibility on their capitalization and conservation.

- The problem is that access to GR, their utilization and possible sharing of benefits arising from such utilization do not occur necessarily at the same time and in the same space, thus monitoring of such activities becomes complex and therefore fair and equitable benefit sharing is complex as well.

- In Mexico,  the government authority responsible for the protection, conservation, regulation and sustainable use of natural resources according to Article 32 bis of the Organic Law of the Federal Government (LOAPF, as abbreviated in Spanish), is SEMARNAT. The above, is considering the legal power granted by the LOAPF to several Central Public Administration Agencies and state-owned public administration entities.

Threats:

- Despite the fact that Mexico has a long history of negative impacts on its natural capital, favorable substantive changes and progress have been achieved in recent years for its protection. These changes have laid the foundations for conservation and sustainable management of such capital. Nevertheless, the transition to environmental sustainability has faced severe obstacles; the changes required to achieve it should be expanded and consolidated. It is necessary to establish specific goals on conservation, sustainable management and restoration and achieve though comprehensive, coordinated and cross actions of public policies, the appreciation of biodiversity and its environmental services.

- Mexico’s natural heritage displays symptoms of a deep anthropogenic impact that has generated an environmental crisis; therefore, changes in the economic growth and promotion of productive activities that have brought about the irrational use and overexploitation of biodiversity, and a severe deterioration of ecosystems and their environmental goods and services the country unequivocally depends on for its continuous development and wellbeing of the people, are imperative.

- Wildlife shows signs of a major problem such as climate change and anthropogenic activities, which are causing severe changes in the ecosystem functioning. Likewise, loss and deterioration of habitats, together with other direct factors such as the global climate change have increased the opportunities for the establishment of exotic invasive species and have also increased the risk for people to contract infectious diseases, causing severe damages to ecosystems and human health with high economic, environmental and social costs. In economic terms, it has been estimated that the monetary costs of environmental deterioration in Mexico (including natural disasters) are substantive, with an annual estimated cost for the period between 1996-2010, ranging from 7 to 10.6% of the GDP; this number could increase significantly if the loss or impairment of ecosystem services is considered in all its dimensions; however it has not been possible to estimate this.

- In the context of access to GR, a coordinated effort between all three government levels and all the other sectors of society as well as increased capacity for inter-institutional and multidisciplinary work is required.

- In the absence of a legal framework in total agreement with the principles and precepts of the NP, the authorities that should address the implementation of this international instrument lack the legal instruments, the organic structure and specific personnel to help manage GR. In addition to scarce dissemination and information related to GR, whether associated or not to TK, the society as a whole has not been empowered by the biodiversity richness of our country and has therefore not assumed joint responsibility in its use and conservation, and this is the reason this project is important.

- Insufficient institutional capacities of national authorities (SEMARNAT, SAGARPA, CDI, SE, among others), in addition to the lack of a legal and administrative framework that is sufficient and adequate in terms of access to GR, associated TK and benefit-sharing threaten the effective implementation of the NP.

Core problem:

- Overall, public action has not been able to identify and establish institutional mechanisms to guarantee proper appreciation of biodiversity and it environmental services, which is required to stop the main deterioration processes.

- The lack of specific and comprehensive regulations on access to GR and fair and equitable sharing of benefits arising from their utilization has led to:

- Improper utilization and misappropriation of biological and genetic resources (Bio piracy) due to the lack of a proper legal and administrative framework o due to the lack of knowledge and capacity of the stakeholders.

- Failure of potentially successful projects that could create benefits for rural communities in our country, due to the inability to   “change the intended use” of collected resources, that the legislation in effect does not conceptualize.

- The appreciation of biodiversity and its environmental services have not been considered so far as core topics that should be common and shared in joint responsibility by the sectors of the federal public administration and that have a greater territorial impact for all three levels of government.

Long-term solution

- In regards to the implementation of the NP, this Project will help to strengthen, on one hand, the capacities of civil servants to get to know the instrument and its implications, considering that national institutions will have to be strengthened with the increase in the number of civil servants, including the creation of areas focused permanently on the applying the Protocol; and on the other hand, it will help  to the train indigenous peoples, people in communal lands, communities and other property owners and holders, as well as other stakeholders.

- The project will strengthen the implementation of and compliance with the NP offering greater legal certainty and transparency for GR suppliers and users by providing elements for the creation of a national legal framework that promotes and fosters prior informed consent to access and use GR and associated traditional knowledge, while strengthening the opportunities for fair and equitable sharing of profits arising from their utilization, based on mutually agreed conditions. The above will favor developing incentives for conservation of biological diversity and sustainable use of its components; promoting sustainable development and will contribute with the efforts by the international community to stop the loss of biodiversity and avoid misappropriation of GR and associated TK.

- The association of this Project with the Project funded by the German Technical Cooperation Agency (GIZ, as abbreviated in German)

- “Governance on Biodiversity Fair and Equitable Benefit-Sharing Arising from the Use and Management of Biological Diversity” will support the Executive Power to address those areas to create capacity which were established as priorities by the government and this will provide the Project with the capacities necessary to effectively implement the NP.

- The Project is intended to lay the foundations of the long term-public policy (after 2015, Aichi Target 16 scope) by providing the tools necessary to avoid misappropriation of GR, as well as those necessary to make effective the fair and equitable sharing of benefits arising from their utilization.

- The National Strategy resulting from component 2, will set the Road Map so that the Executive Power, with a  State Vision,  may determine the National and Budgetary Program(s) required to achieve the planned and ordered implementation of the NP.

- Additionally, regulatory and administrative measures arising from this Project, will establish a favorable regulatory environment so that projects on access to GR, whether associated to TK or not, may be able to set mutually agreed conditions to allow the fair and equitable sharing of benefits arising from their utilization.

- The administrative issue on regulatory management will be solved once the National Strategy, adopted and implemented, establishes budgetary programs and job openings that empower regulating authorities to make decisions.

- The following actions will help to overcome the following barriers in the implementation of the NP in our country, and will be conducted throughout the Project execution period:

| Barriers | Description |
| --- | --- |
| - Limited inter-institutional capacity to monitor the utilization of the RRGGs. | Inexistent collaboration mechanisms between SEMARNAT-which is currently in charge of regulating access to GR- and relevant authorities in the utilization of resources ( including those who grant intellectual property rights such as the Mexican Institute of Industrial Property-in case of patents) and SAGARPA, in case of certificates to obtain vegetable varieties -; health notifications and authorizations granted by the Federal Commission for Protection against Sanitary Risks (COFEPRIS, as abbreviated in Spanish) guaranteeing that in the utilization of GR, prior informed consent exists and that mutually agreed conditions defining sharing of benefits arising from the utilization have been established. |
| - Scattered, insufficient and inadequate national regulatory framework. | Current legal framework limited and asymmetrical, with limited effectiveness not favoring compliance with the NP. Legal framework issued prior to the adoption and ratification of the NP in our country. |
| - Scarce knowledge of relevant stakeholders on access and utilization of GR and Fair Benefit Sharing. | Lack of information regarding the legal framework in effect and the existence of the NP, in addition to historical and cultural inertia, as well as unfair practices of some stakeholders, leading to decreasing access and improper and undue utilization of GR and inequitable sharing of benefits |

2) Baseline scenario and associated baseline projects:

Currently the Environmental Sector has limited staff and facilities to address the issue of access to genetic resources, and there is currently no unit specifically dedicated to this issue on full time.

Although the GEF project will take advantage of existing Mexican resources and capacities spread across key institutions of the environmental sector, it is clear that the GEF project will strongly build upon and closely be coordinated with the Biodiversity Governance Project executed and funded by the GIZ. This initiative with a budget of 6 million Euros was initiated in 2013, as a result of a joint collaboration between the Governments of Mexico and Germany. Through this project, CONABIO and GIZ seek to support Mexico´s efforts in the field of fair and equitable sharing of benefits arising from the use and management of biological diversity. Through this 5 years technical cooperation project, which started in January 2013 GIZ will focus on building capacities among key stakeholders in the use and management of biological and genetic resources that constitute an important natural heritage for current and future generations of Mexicans. The funds will be directly implemented by GIZ.

A strong focus of this initiative will be given to the development of south-south  exchanges of experiences, community to community visits as well as on the delivery of training courses on the ground, participatory community based workshops and targeted courses to field officers, local governments, state institutions and private companies operating in the field. This initiative is also expected to support the development of case studies and the systematization of field experiences. The three components of the GIZ initiative are: 1) Governance of ABS, 2) In situ conservation and promotion of fair and equitable sharing of benefits arising from the use and management of biological diversity and 3) Incentives for sustainable use.

The GIZ project will provide a very solid base to work with the GEF project in a collaborative way towards further strengthening the national enabling environment. While the GIZ will be able with its important resources to cover a large portion of the territory through on the ground activities, the GEF project will be able to address systemic capacity, policy and legal issues at the national level which wouldn’t be addressed without the GEF investment otherwise. Through its first component the GIZ project will be able to fund the systematization of international experiences  and look at different governance models applied in different regions of the word. In particular the GIZ will  support the development of comparative  legal assessments based on global experiences which the GEF project will be able to use to develop the national legal framework and push through the system the declaration of new norms and regulations. Under the first component the GIZ will also support the development of sectorial guidelines and will also put a strong emphasis on the promotion of community participatory workshops to systematize local norms of use of local biodiversity and  established procedures guiding the local use of natural resources. The GIZ project will also support workshops with the academic sector to establish codes of conducts on ABS in line with disposition established by the Nagoya Protocol. Furthermore under its component 2 the GIZ project will support the inclusion of ABS criteria in the management plans of selected protected areas and will conduct comparative analysis between different regions of the world on how ABS norms can contribute to the conservation in areas of high BD value.

Linked to the second component of the GEF project which focuses on capacity building, the GIZ investment will allow to develop training workshops at community level to review rights and obligations related to ABS. The German investments will also support studies that will serve to feed the development of national monitoring and control systems for the use and access to GR and associated TK. Linked to the third component of the GEF project, the GIZ will support the testing and implementation of community protocols in different regions of the country. It will also support the awareness raising and the creation of capacity of local communities on value chains and provide technical advice to pilot communities. It will also support the capacities of local communities to organize themselves and promote the dialogue and alliances with private partners. Finally the GIX project t will also support the development of local development plans taking into account the use and access to GR and ABS norms.

| ### GEF component | ### Contributions of GIZ Project |
| --- | --- |
| Component 1 | Systematization of international experiences and identification of different governance models applied in different regions of the word Comparative legal assessments based on global experiences Sectorial guidelines Community participatory workshops to systematize local norms of use of biodiversity and established procedures guiding the local use of natural resources Workshops with the academic sector to establish codes of conducts on ABS Development of ABS criteria for inclusion in protected area management plans Regional comparative analysis on the use of ABS norms for the conservation of high BD value areas |
| Component 2 | Training workshops at community level to review rights and obligations related to ABS Development of national monitoring and control systems for the use and access to GR and associated TK |
| Component 3 | Testing and implementation of community protocols in different regions of the country Awareness raising and technical guidance to pilot communities Capacity development for local communities on value chains Support to local communities to organize themselves and promote dialogue and alliances with private partners. Local development plans taking into account the use and access to GR and ABS norms |

3) Proposed alternative scenario with brief description of expected outcomes and components of the Project:

Given the complexity related to conservation and sustainable use of biological diversity, and considering that biological diversity is an important trigger for economic development of Mexico, it is not possible to deny that there are economic factors that jeopardize biological diversity within the national territory, where economic agents maximize the use and exploitation of such richness, putting the environment and biological diversity at risk, including GR and associated TK.

To that effect, having ratified the NP, it is imperative that Mexico to has the legal and administrative amendments in place to make conservation and sustainable use of biological diversity possible as well as to strengthen national and international capacities on access and utilization of GR.

Alternative Scenario: The Project has been designed to overcome such obstacles, through the following complementary components:

Component 1: Strengthening national institutional capacities.

For the effective implementation of the NP, it is necessary to have national focal point and national authorities officers trained in (legal/administrative) instruments at least 24 Officers of the of  national focal point and national authorities on ABS, in the environmental sector should be trained officials from the following areas: National Commission of Natural Protected Areas, General Direction of Primary Sector and Natural Renewal Resources, General Direction of Forestry and Soil, General Direction of Wild Life, Federal Agency of Environmental Protection, National Commission for the Knowledge and Use of Biodiversity, Undersecretary of Foment and Environmental Regulation, Coordination Unit of Social Participation and Transparency;  improved by at least 30% as measured by UNDP´s ABS capacity development score card, measures and existing actions in the national framework in effect to comply with protocol provisions. They should be able to apply national good practices manuals on the use and sustainable management of GR to facilitate the implementation of the NP among users and suppliers. Likewise, they should have capacities to monitor the utilization of genetic resources at the different research, development, innovation, pre-commercialization or commercialization stages.

Mexico should have also inter-institutional mechanisms to facilitate monitoring of access to GR, sharing of benefits and compliance with the NP. As a proposal, these mechanisms should include:

a) A database with information on access permits issued to follow up access applications, fed by each agency. Such database should be related to the GR and associated TK Monitoring and Supervision System.

b) Assessment and selection of ABS checkpoints to define what will be the best monitoring plan.

c) The creation of the National Access and Benefit-sharing Clearing-House in order to comply with Article 14 of the NP.

Component 2 Reforming or adjusting the legal framework and establishing administrative or public policy measures that regulate access, utilization of GR and associated TK arising from the fair and equitable sharing of benefits

It is necessary to have the proper national legislation on access to GR and sharing of benefits arising from their utilization to comply with the NP, not only to fulfill its objectives, but to avoid undue utilization and misappropriation of GR in our country.

Mexico has used a preliminary diagnosis to determine whether the national legislation in effect is adequate and sufficient to comply with the legal provisions of the NP. Nevertheless, considering the complexities of the instrument within the country, new stakeholders and regulatory standards have been identified with regards to its application. Thus, it is necessary to conduct a more extensive analysis and diagnosis of the national legal system to identify gaps and inconsistencies that may reduce effectiveness of and compliance with the Protocol as well as new institutional challenges for its implementation.

Some of the conceptual aspects that may be examined in depth in a new diagnosis include:

- Analysis to identify how to align the NP objective with the national legal system

- Analyze and diagnose Mexico’s role as part of the NP and its relationship with international treaties and instruments as a state party to such treaties.

- Analyze the scope of “Special Considerations” referred to in Article 8 of the NP in terms of the national legislation in effect.

- Analyze and diagnose Mexico’s role in the Access and Benefit-sharing Clearing-House, and information sharing.

- Analyze Mexico’s role in technology transfer, international collaboration and cooperation plans.

- Diagnose present legal and regulatory conditions, that is to say, identify gaps and inconsistencies in general laws, Mexican standards, Mexican Official Standards, institutional collaboration agreements, inter-institutional agreements, guidelines, certification bodies, verification units, among others, for the effective application of the NP.

- Diagnose institutional needs for the proper implementation of the NP, including human, material, technological and financial resources necessary to this effect, taking into account what is set forth in the National Development Plan 2013-2018, which considers Strategy 4.10.4 Promoting Sustainable Exploitation of natural resources in the Country; to guarantee the implementation of the NP in coordination with other international treaties signed by Mexico.

The result of the extensive analysis and diagnosis with regards to Output 2.1.1 could be the development of elements to fill possible legal gaps and inconsistencies between the national legal system and the NP.

The abovementioned elements could guide the Legislative Branch and/or suggest adaptations to the national legislation to address obstacles that reduce the effectiveness and compliance with the Protocol in our country.

Some of the main components considered necessary to be included in and/or to amend the national legal system to be able to apply the NP are the following:

a)	Mechanisms and/or plans to guarantee fair and equitable sharing of benefits arising from their and utilization or GR and associated traditional knowledge;

b)	Mechanisms and/or plans on access to GR;

c)	Mechanisms and/or plans on access to traditional knowledge associated to GR;

d)	Mechanisms and/or plans to participate in cross border cooperation;

e)	Mutually agreed terms and their compliance mechanisms;

f)	Prior informed consent;

g)	Consideration for communal protocols and customary laws, etc.;

h)	Legal determination of national competent authorities and national focal points;

i)   Monitoring mechanisms for the utilization of GR;

Component 3: Protecting traditional knowledge and improving the capacities of indigenous and local communities and other stakeholders to generate social awareness on conservation and sustainable use of biodiversity, GR and associated TK, as well as benefit-sharing arising from their access and utilization.

It has been noticed that in order to strengthen and empower indigenous and local communities it is necessary to disseminate guidelines to protect traditional knowledge associated to GR, based on the findings of the “Consultation on mechanisms to protect traditional knowledge, cultural expressions, natural, biological and genetic resources of indigenous peoples ”. Therefore, the following actions should be taken:

- Diagnosis to identify in the 67 indigenous and local communities those who want to participate in the develop of cultural community protocols to facilitate ABS.

- Knowledge, attitudes and practices (KAP) assessment surveys targeting indigenous and local communities assess their awareness on ABS issues, including the project´s proposal to protect traditional knowledge.

- Generate information Exchange mechanisms that guarantee the right to Consultation and Prior Informed Consent of indigenous and local peoples.

- Develop of cultural community protocols for the protection of traditional knowledge associated to GR.

- Dissemination and adoption of Guidelines for the protection of traditional knowledge associated with GR taking into consideration the findings of the “Consultation on mechanisms to protect  traditional knowledge, cultural expressions, natural, biological and genetic resources of indigenous peoples ” , among others by government agencies and indigenous and local communities.

- Study to determine the biodiversity status in indigenous and local communities

- Design differentiated sensitization and awareness programs according to the biodiversity status in their territories, with cultural and linguistic relevance.

- Implement sensitization and awareness programs on the importance of conservation and sustainable use of GR and associated traditional knowledge.

- Study to identify indigenous and local communities that have GR and associated traditional knowledge subject to protection by the NP.

- Sensitization and awareness program including training and dissemination material (brochures, trifold leaflets, manuals, posters, etc.) on the importance of conservation and sustainable use of biodiversity and associated traditional knowledge.

- Design communal protection rights.

- Implement sensitization and awareness programs based on NP objectives and scope.

4) Reasoning, incremental cost and expected contributions from baseline, GEFTF, LDCF / SCCF and co-financing;

The GEF Project will aim to  overcome the obstacles for efficient management of access to GR and associated TK to promote conservation of biodiversity in Mexico and will substitute the country’s fragmented regulatory framework. The support requested from the GEF represents a profitable approach to generate global environmental benefits due to the extensive genetic diversity of wild and domestic species present in Mexico (that have been accessed from time immemorial) and limited resources available. The FG is determined to develop GR and associated TK management strategies that are expedite and profitable for all the stakeholders of the regulatory chain. Priority will be awarded to the creation of capacities of all stakeholders to provide them with solid elements for decision making and to negotiate prior informed consents and mutually agreed terms to empower indigenous and local communities while promoting a regulatory climate that fosters the development of productive projects with national and international environmental benefits.

Nationally, the Project will promote the implementation of institutional coordination mechanisms that will help to organize access and utilization of GR and associated TK plans, regulating the sharing of benefits arising from their utilization.

The Project also seeks to create national capacities that will empower GR Suppliers to be users as well of such resources and the TK to obtain benefits that are shared within their own communities.

The activities related to the GIZ-CONABIO Project are complementary to the eligible actions for the support by the GEF, so that they will work in coordination and will provide each other with constant feedback.

5) Global Environmental Benefits (GEFTF, NPIF) and adaptation benefits (LDCF / SCCF), sustainability and potential for scaling up.

- Mexico is one of 12 mega-diverse countries in the world, with high percentages of endemic species, ecosystem diversity, and genetic variability in many taxonomic groups.  The proportion of species endemic to Mexico is outstandingly high: 57% of flora, 11% of birds, 30% of mammals, 48% of amphibians and 45% of reptiles. With over 11,000 km of coastline and territorial waters of 231,813 km2, Mexico boasts high marine biodiversity and productivity; there are 1,616 coastal marine fish species, and levels of endemism are estimated at 20% for the Gulf of California and 15% for the Caribbean, Gulf of Tehuantepec and the north of the Gulf of Mexico.

- This project will contribute significantly to the conservation and sustainable management of this biodiversity. The actions set out by the project to  improve the legal framework in Mexico on ABS,  to establish proper coordination and control mechanisms and to bring up the capacities of all relevant stakeholders in the country, will have incremental benefits in terms of improved conservation of globally important biodiversity in this megadiverse country.  By collaborating with the GIZ which will promote set-asides and improved management in key habitat of critically engendered species, this initiative will also contribute to conserving forest ecosystems and other key hotspot of biodiversity in the country thus contributing to reduce rates of carbon emissions resulting from the loss and degradation of terrestrial and coastal carbon sinks. The cumulative effect of these actions will enable Mexico to protect important biological and genetic resources which have enormous potential for application in biomedicine as well as in other areas from which the impact could be global while at the same time contributing to promote the resilience of natural ecosystems in the country and support national policies on adaptation to extreme climate events based on improved management of natural resources.

6) Innovation, sustainability and scale-up potential:

- The development of the National Strategy and a regulatory framework consistent with the NP will complement the current actions of the Government to promote sustainable development based on the sustainable use of the country’s natural capital as well as the transition to the development of bio-economic projects as prioritized by the current administration. This approach is new for Mexico. Traditionally the environment sector and the economic/productive sectors works separately and often with opposite visions. The vision developed by the government related to bioeconomy would be supported through the development of an appropriate ABS framework and a solid National Strategy and could serve to bridge the gap between sectors that have traditionally operated in a very polarized way.

- In addition, the FG it will have access  through the partnership between the GEF project and the GIZ initiative to solid elements and tools to justify the development  of adequate institutional mechanisms  to address, follow up and properly implement the NP, as well as the necessary regulations developed based on the products resulting from this project.

- Through this initiative, the project proponent will promote   that the new permits for the access to GR would be taxed differently and identify the necessary mechanisms so that the resources generated will be  redirected to the competent national and federal authorities

- Community protocols for the implementation of the NP in indigenous communities constitute a unique tool for innovation that favors community involvement in decision making and promotes legal access and fair and equitable sharing of benefits. For a multicultural country as Mexico (69 different indigenous cultures) it is a big challenge to develop protocols which consider all the different cosmovisions and community practices related to GR and TK. Once these protocols are ready they could be shared by Mexico with other megadiverse and multicultural countries, mainly through south-south cooperation mechanisms in order to preserve the GR and TK globally.

- The project, in close coordination with GIZ will also take advantage of the work involved with the development of a national legal framework to look at ways to support the creation of a national BS fund especially to support cases where the identification of beneficiaries is difficult. The resources coming from this fund could be used to support the conservation of high diversity federal areas (not protected areas) or to promote capacity building among diverse communities.

- The project will promote the inclusion of budget lines and necessary policy provisions in the key institutions to support funding and facilitate GR regulations after the project ends. This will build upon awareness raising including a detailed national cost benefit analysis on the contributions to the Mexican economy generated by the improvement of the national capacities to implement the NP and to regulate access to GR and its use . This will also build upon and complement the mechanisms for financial sustainability both developed through previous GEF-funded projects in Mexico implemented by the World Bank as well as  by current  UNDP implemented projects ( on protected area resilience, IAS and endangered species).

The project will also ensure to include specific attention to gender related issues. In particular, the project will make sure that negotiation between different stakeholders, capacity building programs and the design of community tools and outreach program will include analysis of gender dimensions in order to maximize the potential positive impacts of this project on  the economic and social status of women and youth.

# A.2. Stakeholder Identification:

# The project is intended for the creation of capacities for federal officers of: SEMARNAT (UCPAST, DGVS, DGGFyS, UCAJ, UCAI and Delegations); PROFEPA and their delegations; a CONANP and the ANPs; SRE, CONABIO, CDI, IMPI and Civil Society. Interested sectors are intended to act as recipients of training, they will eventually take part in decision making on ABS.

# On the other hand, all sectors involved will be indirectly benefited with the regulatory work (building the Legal/Administrative Framework, adaptation of the implementing authority structure), as all federal agencies will have to train their officers, to build and strengthen their organic-administrative structure for the proper application of the Legal/Administrative Framework on access to GR, resulting in the benefit of the population as a whole by having the necessary elements to  manage, exploit and use in a sustainable manner biological and genetic resources.

| INSTITUTION / STAKEHOLDER | ROLE / TYPE OF COORDINATION |
| --- | --- |
| Ministry of Environment (SEMARNAT) | Promoting GR agenda among different sectors; establishing regulatory measures on GR and ABS |
| National Commission for Knowledge and Use of Biodiversity (CONABIO) | Educational materials; data management; remote monitoring; risk analysis, National Focal Point to the Intergovernmental Committee for the Nagoya Protocol on Access and Benefit Sharing |
| National Commission for Natural Protected Areas (CONANP) | Protect and administrate Mexico's Protected Natural Areas |
| Ministry of Agriculture, Livestock, Rural Development, Fisheries and Food (SAGARPA) | Regulates plant genetic resources for food and agriculture |
| Federal Environmental Protection Agency (PROFEPA) | Law enforcement to protect wildlife. |
| Mexican Institute of Industrial Property (IMPI) | Protect industrial property rights and to promote and disseminate the benefits the IP system. |
| National Commission for the Development of Indigenous Peoples (CDI) | Guide, coordinate, promote, support, foster, monitor, and assess programs, projects, strategies, and public actions to attain integral and sustainable development and full enjoyment of the rights of indigenous peoples and communities |
| Ministry of Foreign Affairs | Responsible for the country’s foreign policy. Its aim is to expand and deepen the political, economic, cultural and cooperation links with the world’s various regions |

# A.3 Risks

# Awareness and joint responsibility of the Mexican society supported by this Project may foster conservation of ecosystems, promoting at the same time, sharing of benefits arising from the access to GR. The society will also benefit from that, since it is well known that preserved natural systems act as biotic barriers against extreme natural events such as hurricanes, floods, and other whether events.

# Likewise, promoting in situ preservation of GR offers many advantages, promotes genetic variability of natural populations, guarantees their long-term persistence, and in some cases, helps them adapt to other environmental changes produced by events such as the Climate Change and desertification. Furthermore, a preserved system will promote Food Security for Mexicans.

# It will be necessary to implement sensitization measures and to create awareness of the NP contents in the civil society and policymakers.

# Although the FG truly believes in the importance of implementing this project, and legislators know and are convinced of the importance of the proper implementation of the NP, the present global economic environment may affect the availability of financial resources that Mexico has intended to allocate to this Project.

| Risk | Level | Mitigation Measures |  |
| --- | --- | --- | --- |
| Govt. agencies unwilling to share information and data. | M | At project start and through component 1, formal collaboration agreements and procedures will be outlined based on specific targeted needs for information exchange s.(such as inter-ministerial agreements, MoUs, etc. between SEMARNAT and IMPI, SEMARNAT and CDI or IMPI, CDI and SEMARNAT) |  |
| Conflicts of interest and different priorities of stakeholders constrain implementation of activities | M | A participatory national needs assessment will be conducted to identify the needs and priorities of all relevant stakeholders. This exercise will involve dialogue and joint planning exercises and will help to detect and mitigate any risks of conflicts early on in the process. Close coordination and information exchange will be ensure with the GIZ project who will among other support the development of sectorial assessments and guidelines |  |
| Stakeholders identified not participating in Project implementation. | M | Activities under component 2 and 3 are intended to raise the awareness of the different stakeholders and increase the participation and commitment with the Project´s overall objectives. In selected cases, specific and targeted awareness raising and outreach activities will be implemented in collaboration with the GIZ project. Also the project will ensure direct and regular communication mechanisms with the key stakeholders. |  |
| Coordination mechanisms for the Project operation among relevant stakeholders are not generated. | M | The project will promote periodic high-level inter –agency meetings involved in ABS to share information, provide with update on project progress and identify the necessary commitment mechanisms and procedures to secure full ownership of the personnel in charge of operationalizing different subcomponents of the project. The project will also seek to establish an inter-ministerial commission led by the Ministry of Foreign Affairs. |  |
| Insufficient funding to continue necessary access to GR regulation after the project ends | H | Through component 1, the project will promote the inclusion of budget lines and necessary policy provisions in the key institutions to support funding and facilitate GR regulations after the project ends |  |

# A.4. Coordination

The project was identified during the process of the National Portfolio Formulation Exercise as one of the initiatives to help meet Mexico’s commitments in the national implementation of the CBD work programs, as well as to generate strategies to face the principle threats to biodiversity identified in Mexico’s 4th Report to the CBD. As an integral part of the National Portfolio, the project has natural links with the other initiatives in the Biodiversity focal area, with direct institutional and thematic links with the initiatives on Strengthening Management of the PA System to Better Conserve Endangered Species and their Habitats and Enhancing National Capacities to Manage Invasive Alien Species (IAS) by Implementing the National Strategy on IAS. Both of these initiatives are complementary and should provide opportunities for synergy in the biodiversity portfolio. Finally, the project’s design builds on the experience of other capacity development projects such as the Capacity Building for the Implementation of the Cartagena Protocol on Biosafety and the National Capacity Self-Assessment project. # Notwithstanding the above, it was determined that the coordination mechanisms between the stakeholders participating in the execution of the Project should be generated jointly, taking into account the conditions, interests and needs of such stakeholders.

B. Description of consistency of the project with:

# B.1 National Strategies and Plans or reports and assessments under the relevant conventions, if applicable, for example

# In 2009, the Fourth National Report to the Convention on Biological Diversity, Mexico reported:

# " .. The Legal Status of obtaining biological materials in Mexico is still incipient, with large gaps and uncertainties that raise debate on issues where there is regulation, institutional fragmentation leads to overlapping, not always consistent between the legislation.

# Regulating access to genetic resources is hardly mentioned in environmental legislation, constituting a legal missing has nearly paralyzed bioprospecting biodiversity. Although some prospecting activities based on traditional knowledge continues, the complexity of implementing the CBD this is reflected in the absence of requests to the federal government and even in the absence of prior informed consent by those who have taken that knowledge and those samples have rights under the legal framework in the country ... ".

# It also noted that " ... in Mexico important efforts were made , manifested in numerous initiatives , projects and programs from the Environmental Sector and from multiple areas of the Federal Government to protect the components of biological diversity , promoting sustainable utilization ; respond threats facing ; maintain the goods and services it provides; protect traditional knowledge, innovations and practices , to promote just and equitable sharing of benefits arising from the utilization of genetic resources , and ensure the availability of adequate resources ... "

# However, while the legal gaps remain unaddressed at national level, the situation has changed in the international context with the adoption of the PN in 2010 and its ratification by Mexico.

# The Project submitted for consideration is compatible with international instruments and will allow our country to address in a proper manner the implementation of the NP, encouraging the use and conservation of biological diversity, GR and associated TK, generating joint responsibility plans in the community as a whole, with the institutional and legal structure for the attainment of the aforementioned objectives. It is therefore aligned with the CBD and Aichi Target 16.

# The project submitted for consideration is compatible with the provisions of the National Development Plan 2013-2018 (PND), in several strategies contained therein; however in Strategy 4.4.4 regarding “Protecting the natural heritage, all courses of action are aimed at preservation and sustainable use of natural resources in general; Strategy 4.10.4. Promoting sustainable exploitation of natural resources in the country, sets forth the course of action: Establish the instruments to rescue, preserve and potentiate GR,” is more specific to the protection of GR; and finally Strategy  2.2.3 Foster wellbeing of indigenous peoples and communities by strengthening social and economic development respecting the expressions of their culture and exercise of their rights, includes the course of action: Promote policies for sustainable exploitation of natural resources occurring in indigenous regions for the preservation of the environment and biodiversity, building upon their traditional knowledge. On the other hand, Goal 5 of the PND sets forth: “Mexico with Global responsibility shall be a positive and proactive force in the world, a nation serving the best causes of humanity. Our global performance should incorporate the national reality and internal priorities, framed in the other four National Goals, so that these can be a distinctive agent of foreign policy. We hope our nation strengthens its voice and presence in the international community, and recovers the leadership for the benefit of the great global causes. We reassert our commitment with free trade, moment of capital, productive integration, safe movement of people and attracting talent and investment to the country. We have to draw a course of action consistent with the new global realities, to overcome the challenges we face.” Thus, the project is framed in the national priorities. The Environment and Natural Resources Sectorial Program (PROMARNAT 2013 -2018), officially published on December 12, 2013 includes two action lines directly related to the issue:

# "4.3.7 To promote the sustainable use of biological resources and associated traditional knowledge, and the fair and equitable sharing of benefits" and "4.6.1 Promote the development of the regulatory framework to implement new protocols to the CBD.". With the sectorial commitment formalized in PROMARNAT, the implementation of the PN is planned to be completed during this sexenium.

# B.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities:

# Through the effective strengthening of national institutional capacities, we intend to implement the NP having a direct effect on preservation and sustainable use of national biodiversity, including GR, and associated TK.

# On the other hand, the funds for this project will be allocated to training for the application of Good National Practices Manuals on the sustainable use and management of GR, as well as to facilitate the implementation of the Nagoya Protocol among users and suppliers. We intend to monitor the utilization of GR at different research, development, innovation, pre-commercialization or commercialization stages, through the design and execution of inter-institutional mechanisms to facilitate monitoring and access to GR, benefit sharing though databases with information on access permits, diagnosis on the information available to different check points, in addition to the creation of the National Access and Benefit-Sharing Clearing-House to comply with Article 14 of the NP.

# Therefore, by strengthening the legal framework and establishing administrative or public policy measures, the access to GR and sharing of benefits arising from their utilization will be possible, in conditions of legal certainty, for those regulated and for national authorities, limiting the discretion of official government acts that may violate the rights of stakeholders in the management of GR and associated TK.

# Hence, the analysis and diagnosis of the national legal framework in conceptual and technical and operative aspects to determine the scope and interpretation of the standards in effect, determine gaps and inconsistencies of such framework, addressing regulatory needs and objectives to fulfill in conservation and sustainable use of GR, through the preparation of a proposal to amend the national legal system that addresses directly or indirectly access to GR and sharing of benefits.

The need to formulate and promote a bill to modify the national legal framework for access to and sharing of benefits in effect has been anticipated for that end, so that it is consistent with the NP. Therefore it is necessary to make legislators aware and train them on access to GR and sharing of benefits.

On the other hand, it is necessary to design a National Strategy for conservation and sustainable use of GR, including associated TK, which will be the reference framework that should encompass the actions of the Mexican State in the medium and long term.

Likewise, strengthening the capacities of indigenous and local communities, and sensitizing the civil society, will help to create social consciousness in conservation of biodiversity, the GR and associated TK, as well as access to benefit-sharing arising from their utilization, taking into account the double role that can be performed by GR suppliers and users. Therefore we have foreseen the development and dissemination of guidelines to protect traditional knowledge associated to GR based con the outcomes of the National Indigenous Consultation conducted by the CDI.

The civil society however, aware and sensitive of the importance of conservation and sustainable use of GR and associated traditional knowledge is involved in an effective way so that it promotes their conservation and sustainable use, taking also into account access to and sharing of traditional benefits; this will be achieved through the design and instrumentation of sensitization programs which will include training and dissemination material on the importance of conservation and sustainable use of GR and associated traditional knowledge on the objectives of the NP.

# B.3  The GEF Agency’s comparative advantage for implementing this Project:

UNDP has worked extensively with the Mexican Government on biodiversity policy issues and environmental management, including mainstreaming of environmental policy across different sectors.  UNDP has served as implementing agency for a number of capacity development initiatives that were successfully designed and carried out in the environment sector. In particular, this project will benefit from UNDP’s experience in-country with inter-sectorial coordination efforts and the development of policy frameworks for biosafety and certified markets. As implementing agency for the SGP in Mexico, UNDP also has a long history of working with indigenous and local communities on biodiversity conservation and sustainable use.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Jorge Muhlia Almazán | GEF Political and Operational Focal Point | Ministry of Finance and Public Credit | March 5, 2014 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator | Signature | Date | Project Contact Person | Telephone | Email Address |
| Adriana Dinu Executive Coordinator and Director a.i. UNDP-GEF |  | March 27, 2014 | Lyes Ferroukhi, Regional Technical Adviser, EBD | +507 302-4576 | lyes.ferroukhi@undp.org |

SRE: Ministry of Foreign Affairs; SEMARNAT: Ministry of Environment and Natural Resources; SAGARPA: Ministry of Agriculture Livestock, Rural Development, Fisheries and Food; CDI: National Commission for the Development of Indigenous Peoples; SE: Ministry of Economy; IMPI: MEXICAN Institute of Industrial Property; CONABIO: National Commission for Knowledge and Use of Biodiversity.

http://www.cdi.gob.mx/index.php?option=com_docman&task=cat_view&gid=85&Itemid=200019

On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

These include the National Strategy on Biodiversity of Mexico published in 2000, the National Development Plan 2013- 2018  and the y el Segundo Country Study, 2009

PPG fee percentage follows the percentage of the GEF Project Grant amount requested.

Part II should not be longer than 5 pages.

Sarukhán, J., et al. 2012. Capital natural de México: Acciones estratégicas para su valoración, preservación y recuperación.

comisión nacional para el conocimiento y Uso de la Biodiversidad, México. Pp.21

Carabias, J., A. Mohar y E. Provencio. 2008. Retos y riesgos en el uso de la biodiversidad, en Capital natural de México, vol. III: Políticas públicas y perspectivas de sustentabilidad. Conabio, México, pp. 285-29

http://www.cbd.int/abs/submissions/icnp-2/questionnaire-cb/mexico-es.pdf

Target 16: By 2015, the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from their utilization will be in effect and operation, according to the national  legislation.

http://www.cdi.gob.mx/index.php?option=com_docman&task=cat_view&gid=85&Itemid=200019

http://www.cdi.gob.mx/index.php?option=com_docman&task=cat_view&gid=85&Itemid=200019

Cuarto Informe Nacional de México al Convenio sobre Diversidad Biológica (CDB) http://www.cbd.int/doc/world/mx/mx-nr-04-es.pdf. Pp. 119.

Plan Nacional de Desarrollo: http://dof.gob.mx/nota_detalle.php?codigo=5299465&fecha=20/05/2013

Programa Sectorial de Medio Ambiente y Recursos Naturales 2013-2018, http://dof.gob.mx/nota_detalle.php?codigo=5326214&fecha=12/12/2013