Project Identification Form (PIF)

Project Type:

the GEF Trust Fund

Submission Date:  November 10, 2009

Resubmision date: November 18, 2009

| Indicative Calendar* |  |
| --- | --- |
| Milestones | Expected Dates mm/dd/yyyy |
| Work Program (for FSP) | N/A |
| CEO Endorsement/Approval | Nov 2010 |
| Agency Approval Date | Feb 2011 |
| Implementation Start | April 2011 |
| Mid-term Evaluation (if planned) | N/A |
| Project Closing Date | April 2014 |

*

part i:  project IDentification

GEF Project ID:      	Project duration: 36 months

gef agency Project ID: P119952

Country(ies): Regional - Africa

Project Title: SPWA - Scaling up the impacts of good practices in linking poverty alleviation and biodiversity conservation.

GEF Agency(ies): , ,

Other Executing partner(s): IUCN, ECOWAS

GEF Focal Area (s):

GEF-4 Strategic program(s): BDSP4 ,BDSP3

Name of parent program/umbrella project : SPWA- Strategic Program for West Africa: biodiversity component

- Project framework

| Project Objective: To strengthen capacities for PA management in the participating countries and enable knowledge management/sharing of good practices in order to consolidate the Strategic Program for West Africa. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Investment, TA, or STAb | Expected Outcomes | ### Expected Outputs | ### Indicative GEF Financinga |  | Indicative Co-Financinga |  | Total ($) c =a + b |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |
| 1.Reinforcement of the regional network of PA managers & experts and extension of the network of key partners | TA | Improvement of PA management capacity in the region Extension of the network of key partners (executing agencies, NGOs, private sector, and Universities involved in community activities around protected areas (buffer zones, corridor) | - A High level regional training program on PA management - 50 PA managers trained and available at national and regional levels (including a virtual network) - 10 training modules developed and training sessions held. - 1 preparatory study to develop a high level regional program on PA management by internet - One regional meeting including all partners (to combine with the energy component of the west Africa program) - A Forum on economic initiatives in and around protected areas in West Africa established conducted - A directory of local and national NGOs involved in PA management developed | 500,000 | 41 | 710,000 | 59 | 1,210,000 |
| 2. Knowledge Management and Information Dissemination | TA and Inv | • Best practices and approaches in biodiversity conservation linked to poverty alleviation and growth analyzed • Partners at regional, transboundary, and local levels are better equipped to link biodiversity conservation projects to poverty alleviation (and vice versa). • Dissemination of information to protected area managers and decision-makers. | - Good practice guidelines, toolkits and information resources are available based on review of past projects and emerging lessons - Roster of experts on Biodiversity conservation and management identified and available on request to countries - An e-platform (webpage host) created by IUCN as an information exchange and knowledge sharing platform. -Publications and dissemination of communication documents (reports, leaflets, brochures…) on the west Africa program - Presentations and articles developed for targeted workshops. | 360,000 | 51 | 350 000 | 49 | 710,000 |
| 3. Project management and Monitoring | - Project is administered effectively and efficiently. - Portfolio monitoring system in place with common indicators to measure a consolidated impact. |  |  | 40,000 | 50 | 40,000 | 50 | 80,000 |
| Total project costs |  |  |  | A,900,000 |  | B1,100,000 |  | 2,000,000 |

a   List the $ by project components.  The percentage is the share of GEF and Co-financing respectively of the total amount for the component.

b  TA = Technical Assistance;  STA = Scientific & Technical Analysis.

B.    Indicative Co-financing for the project by source and by NAME (in parenthesis) if available, ($)

\

| Sources of Co-financing | Type of Co-financing | Project |
| --- | --- | --- |
| Project Government Contribution | In- kind | 400,000 |
| GEF Agency(ies) |  | 0 |
| Bilateral Aid Agency(ies) |  | 0 |
| NGO (IUCN-PACO) | Grant | 400,000 |
| Others (Beneficiaries) | In-kind | 300,000 |
| Total Co-financing |  | B1,100,000 |

C.  Indicative Financing Plan Summary For The Project ($)

|  | Previous Project Preparation Amount (a) | Project (b) | Total c = a + b | Agency Fee |
| --- | --- | --- | --- | --- |
| GEF financing | 0* | A 900,000 | 900,000 | 90,000 |
| Co-financing | 0 | B1,100,000 | 1,100,000 |  |
| Total | 0 | 2,000,000 | 2,000,000 | 90,000 |

* A PPG request for USD 50,000 will be submitted shortly.

D.   GEF Resources Requested by agency (ies), Focal Area(s) and country(ies)1

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Project (a) | Agency Fee (b)2 | Total c=a+b |
| Total GEF Resources |  |  |  |  |  |

1   No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

2   Relates to the project and any previous project preparation funding that have been provided and for which no Agency fee has been requested from Trustee.

part ii:  project JustiFication

- State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

Threats to biodiversity in West Africa have been a subject of major international concern over the last three decades. Although the drivers of habitat and species loss often extend across national borders, most efforts focused locally on a few targeted sites or nationally in a few key countries. Investments through bilateral and multilateral initiatives have made some achievements in securing a few important protected areas and strengthening capacity of civil society organizations and government agencies. Based on records in the World Database on Protected Areas there were a total of 164 listed protected areas in West African countries in 2003, totaling an estimated 55 millions of ha or 6.3% of the land area. The challenges faced in this sub-region reinforced the need for a programmatic approach to biodiversity conservation that will enable integration of efforts across multiple scales and national borders, to take full account of the magnitude and extent of fragmentation across ecosystems. As a result the West Africa program for Biodiversity was approved in November 2008 with the immediate aim is to assist countries in the region to build projects based on their identified priorities in order to enhance the implementation of their biodiversity strategies and policies. Practical and action-oriented projects with measurable impacts were conceptualized under the program.

The overall objective of the West Africa program for Biodiversity is to scale-up biodiversity conservation and sustainable use in West Africa looking for socio-economic benefits in a context of poverty alleviation and growth. The program has been developed around three main priority areas: (i) Poverty reduction among communities residing in and around protected areas, (ii) Mainstreaming biodiversity in production landscapes and sectors, and (iii) Consolidation of protected area networks. There are several projects that have been developed under the West Africa program including in Ghana, Gambia, Guinea Bissau, Guinea, Sierra Leone, Liberia and Benin to contribute to the priorities and overall objective of the program. The program’s objective includes a strategic approach with a focus on enabling an environment for improved advocacy for and harmonization of biodiversity conservation management across the region, capacity building, and strengthened knowledge exchange and learning processes between countries.

# This MSP has been developed under this above mentioned West Africa Biodiversity program and proposes to focus on strengthening capacities within the participating countries, to enable a platform to share experiences (knowledge management) with all partners (cofinancing partners, Council members), and to enable dissemination of information beyond the program and thus contributing to scaling up the impacts of good practices in linking poverty alleviation and biodiversity conservation. Therefore this capacity building initiative will not only allow the PA managers to apply the expertise gained through trainings and workshops but will allow knowledge sharing between the various projects and partners under the program which would not otherwise happen. This project will be coordinated with existing efforts undertaken by IUCN (through the IUCN training program in West & Central Africa for protected areas managers) in the region with different bilateral and private donors (FFEM, FIBA) and provides the ground for a long term IUCN approach on capacity building in the region.

The objective of this proposed project is to strengthen capacities for PA management in the participating countries and enable knowledge management/sharing of good practices in order to consolidate the Strategic Program for West Africa.

Key Outcomes

- Strengthened capacities for PA management in the region

- Best practices and approaches in biodiversity conservation linked to poverty alleviation and growth are disseminated to protected area managers and decisionmakers.

- Partners at regional, transboundary, and local levels are better equipped to link biodiversity conservation projects to poverty alleviation (and vice versa).

The project as designed includes three components as described below:

Component1: Reinforcement of the regional network of PA managers & experts and extension of the network of key partners

Strengthening capacity in the region lies central to any efforts towards coordinating experiences within a regional network. This component aims to (i) strengthen the capacity of Protected Area Professionals and Experts in West Africa through an innovative training program (linked to the IUCN training program in West & Central Africa for protected areas managers) and, (ii) extend the network to key-partners involved in nature resource management in and around protected areas (NGOs, Universities) through providing a regional platform, to enable  improvement of PA management capacity in the region. It is emphasized that this project  will not only bring together a number of actors in each of the participating countries themselves, but also the GEF Secretariat, the GEF Agencies and regional / sub-regional organizations (both governmental and non-governmental), as well as relevant multilateral and bilateral donors. This approach will allow to enlarge the scale of existing initiatives such as IUCN’s ones, and will involve key stakeholders whom are not yet participating to the movement towards PAs management improvement.

Component 2: Knowledge Management and Information Dissemination

As a second step the analysis and dissemination of experiences and information is crucial to the scaling up of good practice. This component will support a knowledge network of various institutions that will facilitate the sharing of methods and approaches to combine global biodiversity conservation and poverty reduction efforts and also facilitate the dissemination of related information.

More specifically this component will provide the opportunity to deliver results and information beyond the actors involved in the program to scale up results of the program and the projects. It will enable analysis of best practices and approaches in biodiversity conservation linked to poverty alleviation and growth (e.g need for any revised institutional and policy environment linking biodiversity conservation and poverty alleviation issues; promotion of practices of biodiversity conservation in productive landscapes;  the role of traditional authorities in biodiversity conservation, Communities linked to the voluntary carbon finance market as an incentive to sustain improved nature management, economic environment to biodiversity conservation etc). Lessons learnt in many places of the region, through projects or states initiatives will be spread out in the region, but also initiatives developed around the world and that may be relevant. This work will involve as far as possible IUCN regional experts, who are recognized experts on biodiversity issues and give their time and experience on a benevolent basis.

Component 3: Project Management and Monitoring

Main outcomes of this component are expected to be:

- Project is administered effectively and efficiently.

- Portfolio monitoring system in place with common indicators to measure a consolidated impact of the overall program.

Overall the activities as designed under the project will promote learning, information exchange and capacity building at the regional level, and encourage direct support to the protected area management sector as a result of good practices and lessons learned. The proposed project will ensure that the Strategic Program for West Africa is consolidated and monitored.

- Describe the consistency of the project with national/regional priorities/plans:

The West Africa sub-region is endowed with a rich biological heritage. The seventeen participating biodiversity-rich countries have supported the development of the biodiversity component of the West Africa Program. This proposed MSP has been developed as part of the program and draws linkages to all country level national priorities and plans.

Notably however at the regional level, building on the initiative of the New Partnership for Africa’s Development (NEPAD)  and the African Ministerial Conference on the Environment, West African countries have demonstrated their strengthened interest and commitment to work jointly on common environmental objectives with the adoption of a Resolution on the sub-regional environmental action plan for the environment initiative of NEPAD for West Africa  by the ministers of West African countries the at a meeting held in Accra, Ghana, on June 25-27, 2007. Specifically, the adopted resolution called upon the GEF to support implementation of the West Africa Sub-regional Environmental Action Plan of the NEPAD. Special care will continue to be taken to work very closely with the key institutions in the region, as was the case, for example, in developing the Action Plan.

- Describe the consistency of the project with gef strategies and strategic programs:

The proposed project developed under the Strategic Program for West Africa (SPWA) responds directly to the objectives of the Biodiversity Area Focal Strategy and Strategic Programming for GEF-4. Given the nature of this project the issues are cross-cutting over the strategic priorities. It would in particular address Strategic Objective 1: to Catalyze Sustainability of Protected Areas, and be linked with SP4: Strengthening the Policy and Regulatory Framework for Mainstreaming Biodiversity and SP3: Strengthening Terrestrial Protected Areas Network.

- justify the type of financing support provided with the gef resources:

The GEF resources will support both technical assistance and small investment activities designed within the project (see project framework  in section A.

- Outline the Coordination with other related initiatives:

The proposed project aims to act a glue between the different regional, transboundary, and national projects, by developing an operational network of professionals, involved in PAs management, and their key partners, including scientists, private sector, donors, NGOs, and has been developed in a consultative manner with the countries and the partners in the region. This should be seen as a reinforcement of already on-going initiatives in the region such as the work lead by IUCN in West Africa on PAs management effectiveness and focuses on capacity building and knowledge management. This work has already permitted to identify and train a roster of experts on PAs management issues, to set up high level or modular training courses, to develop new or to translate already existing best practices manuals, to implement PAs assessments in several countries and to develop, on this basis, local or transnational projects to improve PAs management and its effect on biodiversity conservation, local populations involvement and so poverty alleviation where and when possible. Thus, the proposed project, which is only a MSP, will not have to start from nothing, but will be able to maximize already on-going work and will give the opportunity to improve the actions scale and to involve more stakeholders, including non targeted at this stage by IUCN like donors or GEF agencies. In particular, it will allow improvement of the e-platform developed by IUCN (www.papaco.org) and the many tools that have been set up already (newsletter, data basis, thematic publications) in order to get more efficiency for lobbying towards decision makers. As IUCN works on many other issues in the region, this project (component 2) will also give the opportunity to link different theme related to PAs, such as climate change (and energy consultations), populations livelihoods improvement, landscapes management. Overall it will add a strong value in influencing decision makers at all levels.

- Discuss the value-added of GEF involvement in the project  demonstrated through incremental reasoning :

Under the baseline scenario the several initiatives that have been developed under the West Africa biodiversity program by multiple partners would continue to be implemented in a scattered manner. Though these national level investments will have impacts on the ground, they will however not contribute to knowledge sharing and further lessons learnt from one project will not benefit the others.

Incremental support from GEF and its co-financing partners offers a real opportunity to strengthen capacities and knowledge sharing within the West Africa Region in order to ensure complementarity among country-level and regional projects, in particular with  respect to protected area conservation  and management in West Africa. Given that a reasonably large amount of financial resources are being targeted at various activities under the West Africa Program, collaboration between the large numbers of stakeholders is likely to enhance the effectiveness of the financial support provided. This GEF MSP project will promote learning and information exchange at the regional level to ensure that lessons from successes and failures of country and regional level investments are adequately disseminated. This will form the basis of any future replication or scale-up of activities. As it will be strongly linked to already on-going initiatives at regional scale, the value of this funding is clearly to enhance the networking and the lesson learnt dissemination all over West Africa, while involving some key partners that are not already in the loop. In that sense, the GEF funding will realize, at minimal cost, what other initiatives have not yet targeted and will improve at the end the overall picture in the region.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved, and if possible including risk mitigation measures that will be  taken:

Detailed risk analysis and identification of risk mitigation measures will be carried out as part of the preparation of the individual projects that fall under the umbrella of the Strategic Program.

- describe, if possible, the expected cost-effectiveness of the project:

Given the programmatic nature of the West Africa Program, this proposed MSP project is expected to be highly cost-effective in the sense that it will play a catalytic role amongst the different initiatives under the Strategic program and even beyond this program. It will help efficiently foster partnerships and synergies amongst the on-going and under preparation activities in the participating West Africa countries and will provide a potential for a high multiplier effect. Thus the MSP will maximize the impacts of individual projects under the West Africa Biodiversity program.

- Justify the comparative advantage of GEF agency:

The World Bank is the Lead Agency for the Biodiversity component of the West Africa Program. It has been fully involved in the preparation of this regional program, in close coordination with the countries and the all other technical and financial partners. Moreover, the World Bank has an active portfolio in the Protected Area management thematic sector given that the West Africa sub-region is endowed with a rich biological heritage. The various projects developed within the program have been conceptualized with a view to mainstream them within the country’s sector work and dialogue and are therefore aligned with the WB’s strategic and lending portfolio in the participating countries. In this context, the Bank is ideally placed to help ensure that biodiversity conservation receives sufficient attention in high-level policy making and in the regional context.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S):

This project has been requested by the countries in West Africa and approved as part of the GEF West Africa Program – subcomponent Biodiversity. The program has been endorsed by Ministers of the region. No formal letters of endorsement are requested for this project.

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Steve Gorman GEF Executive Coordinator The World Bank |  | November 10, 2009 | P. Agostini AFR Regional GEF Coordinator | x37620 | pagostini@worldbank.org |

Response to comments in the GEFSEC Review sheet of November 17, 2009

Comment - Calendar and project duration: That seems difficult to deliver all outputs in 24 months. Moreover, this project is going to glue individual projects under the Strategic Program for West Africa. The project needs to be developed on at least 3,5 years (the program completion date is in November 2015).

Response: The project duration is expected to be 3 years. The duration and associated milestones have been revised.

Comment - Project title: coordination is not the purpose of the project. Moreover, this is not an eligible activity for a GEF grant. Please, remove the word "coordination" in the outcomes (table A, p1), and in the text (p4).

Response: Yes it is clarified that the project is not focusing on regional coordination per se but at enhancing capacities of and knowledge sharing of good practices between participating countries of the West Africa Biodiversity program. The document has been edited to remove any non-clarity on the issue. Also note that the title of the project does not indicate any coordination aspect and hence has been retained.

Comment- Please, correct the table C (indicative financing plan summary): 2 cells are wrong.

Response: Corrected.

Project ID number will be assigned by GEFSEC.

Select only those focal areas from which GEF financing is requested.

Include project preparation funds that were previously approved but exclude PPGs that are awaiting for approval.

During its Regular Sessions, including those of 2004 in Tripoli, Libya and 2006 in Brazzaville, Congo, the African Ministerial Conference on the Environment has consistently requested GEF enhanced support to Africa. This request was reiterated again in the form of a Declaration during the recently held 12th Session of AMCEN in Johannesburg, South Africa on 12 June 2008.