REQUEST FOR BIODIVERSITY enabling activity

Proposal for Funding Under the GEF Trust Fund

part i:  project IDentifiers

| EA Title: | National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in South Africa |  |  |
| --- | --- | --- | --- |
| Country(ies): | South Africa | GEF Project ID: | t.b.d. |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 4894 |
| Other Executing Partner(s): | Department of Environmental Affairs (DEA) | Submission Date: | August 10, 2012 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) | 42 |
| Check if applicable: | NCSA NAPA | Agency Fee ($): | 22,000 |

- EA framework

### EA Objective: To integrate South Africa’s obligations under the Convention on Biological Diversity (CBD) into its national spatial, development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

| ### EA Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Grant Amount ### ($) | ### Confirmed Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
| 1) Stocktaking and national target setting | TA | - By end of 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By end 2012, national targets in response to the global Aichi Targets are developed. | 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner. This will include the following Strategic Study: - A National Biodiversity Framework which sets out the priorities for action by local, provincial and national government, statutory bodies and civil society in implementing the NBSAP 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to South Africa’s reality and helps develop provincial and national monitoring and reporting capacity. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, South Africa taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). | 30,000 | 45,000 |
| 2) NBSAP update | TA | - By 2014, South Africa’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP | 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for South Africa, anchored into national development frameworks, is revised and updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAP for South Africa is submitted to the CBD preferably within the deadline set by the COP; this will include the following Strategic Studies: - Priorities for national and provincial implementation of South Africa’s National Protected Areas Expansion Strategy, linked to the CBD’s Programme of Work on Protected Areas (PoWPA) and linked to government mandates and delivery agreements with resource mobilization for this covered under Component 3 - Local TEEB (The Economics of Ecosystems and Biodiversity): Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research pieces needed to make the case for action based on valuation and/or the anticipated cost of inaction - Exploring and costing options for Ecosystem-based adaptation to climate change in South Africa, linked to government priorities for job creation and poverty reduction - Development of a ‘biodiversity-centred’ development impact analysis for key economic sectors: assessing the stakes for biodiversity of sectoral economic development, and the opportunities for conservation and sustainable use in South Africa | 138,000 | 150,000 |
| 3) National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms |  | - By 2013, complete the establishment and improvement of a national clearinghouse mechanism - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment | 3.1 A National implementation framework for the new NBSAP is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBSAP; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) the resources needed for the implementation of the NBSAP and NBF priorities are estimated and fed into the EU-funded UNDP pilot project on biodiversity finance in South Africa which includes a baseline assessment of existing finance for biodiversity and a quantification of the funding gap. 3.2 An effective, user-friendly and easily updatable country-driven CHM web-gateway, integrating key biodiversity information in existing sites, is developed; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. 3.3. Immediate CBD reporting obligations are met by South Africa in a timely manner, in particular the Fifth National Report to the CBD by 31 March 2014. 3.4 An institutionalised framework for reporting to the CBD, including requirements for data sourcing, monitoring and reporting, is agreed through the Ministerial Technical Committee’s Working Group 1, outlining responsibilities of units and staff in the national Department of Environmental Affairs as well as provincial conservation authorities, with resourcing requirements determined for these ongoing functions to enable ongoing budgetary allocations. | 40,000 | 76,000 |
| Subtotal |  |  |  | 208,000 | 271,000 |
| EA Management Cost |  |  |  | 12,000 | 85,000 |
| Total EA Cost |  |  |  | 220,000 | 356,000 |

- Co-financing for the EA by source and by name

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | Department of Environmental Affairs (DEA) | Grant | 288,000 |
| GEF Agency | UNDP (support from the Johannesburg Service Centre and contribution* from the UNDP/EU project on Biodiversity Finance to the TEEB study)** | Grant | 68,000 |
| Total Co-financing |  |  | 356,000 |

*	Support from the UNDP Environment and Energy Policy Advisor for approx. 15 days throughout the duration of the project. This co-financing contribution was estimated at $18K and serves as co-financing to this proposal.

**	Concurrent activities from the EU/UNDP Biodiversity Finance Project were estimated at $50K and also serve as co-financing to this proposal.

- Grant  Resources Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name | EA Amount (a) | Agency Fee (b) | Total (c)=(a)+(b) |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF TF | Biodiversity (Focal Area Set Aside) | Global | 220,000 | 22,000 | 242,000 |
| Total Grant Resources |  |  |  | 220,000 | 22,000 | 242,000 |

- EA Management Cost

| ### Cost Items | ### [GEF only] Total Estimated Person Weeks | ### Grant Amount ($) | ### Co-financing ($) | ### EA Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 0 | 0 | 85,000 | 85,000 |
| ### International consultants* | 0 | 0 | 0 | 0 |
| ### Office facilities, equipment, vehicles and communications* |  | 9,000 | 0 | 9,000 |
| ### Travel* |  | 0 | 0 | 0 |
| ### Others**: Project Audit |  | 3,000 | 0 | 3,000 |
| Total |  | 12,000 | 85,000 | 97,000 |

*   Details to be provided in Annex A.     ** Other items to be clearly specified.

Additional information for Table D, if applicable:

If costs for office facilities, equipment, vehicles and communications, travels are requesting for GEF financing, please provide justification here:

The bulk of project management costs will be borne by the Government of South Africa, primarily through the engagement of a Project Technical Coordinator to lead the project in all of its activities for a period of 3 years. The estimated costs of this engagement is $225K, noting that roughly one third of the coordinators’ tasks are considered managerial and represents the amount of $85K included in the above table under ‘Local consultants’. The rest of the tasks are technical and the estimated costs of technical inputs by the Coordinator are considered part of the co-financing to project components. The Department of Environmental Affairs will avail office facility and connectivity to the Technical Coordinator (as well as other project consultants), but this contribution is in-kind and has not monetised in the above table. The GEF is being requested to finance some IT equipment to the project's long-term consultants (refer to Annex A for a list), plus communication services and the project audit. Refer to the Total Budget and Workplan in Annex C for more details on the GEF’s project management costs.

part ii:  Enabling Activity JustiFication

A. Enabling Activity Background and Context (Provide brief information about projects implemented since a country became party to the convention and results achieved):

South Africa is diverse not only in terms of people and culture but also in terms of our biological resources and ecology. With only 2% of the world’s land area, the country is home to 6% of the world’s plant species and mammal species, 8% of bird species and 5% of reptile species, many of which are found only in South Africa. With nine biomes ranging from desert to grassland to forest, South Africa has a huge range of habitats, ecosystems and landscapes. We have three of 34 globally recognised biodiversity hotspots: the Cape Floristic Region, which falls entirely within our boundaries; the Succulent Karoo, shared with Namibia; and the Maputaland-Pondoland-Albany hotspot, shared with Mozambique and Swaziland. Our seas straddle three oceans, the Atlantic, the Indian and the Southern Ocean, and include an exceptional range of habitats, from cool-water kelp forests to tropical coral reefs. The southern African coast is home to almost 15% of known coastal marine species. The climate is mainly temperate and dry, with an average annual rainfall of only 464 mm. However, there are large variations in temperature and rainfall across the country. Rainfall in the west falls mainly in winter, while the eastern parts receive summer rainfall. South Africa is a water scarce country and droughts are common. Due to the abundant sunshine and high evaporation rates, only about 9% of rainfall, on average, reaches rivers as run-off, compared to the worldwide average of 31%. Most of the freshwater is produced to the east of the country, with more than 60% of the river flowing arising from only 20% of the land area. The SA population, estimated at 48 million people (SA Yearbook 2008/9) is diverse in every way. Classified as a middle income country, SA is the largest economy in Africa, with a stock exchange in Johannesburg, that ranks among the 10 largest in the world. Despite this, and despite over 15 years of effort by government to address the socio-economic imbalances created by the past, income distribution is highly skewed and poverty is still wide-spread, and more than 30% of the population living below the poverty line (Sonjica 2009). In the past, the economy was based chiefly on primary production and extraction of resources, particularly minerals. In recent decades, the South African economy has shifted away from primary sectors, with secondary and tertiary sectors becoming more important. Just over half of the population lives in urban areas. Although most major cities and towns are characterized by modern infrastructure and well-developed financial, legal, communications, energy and transport sectors, they also include large (and growing) informal settlements that lack basic services and infrastructure and in which poverty, unemployment and associated skills are rife. Rural areas, in which agriculture has traditionally provided the economic mainstay, generally have more limited infrastructure and development than urban centres and are characterized by extremely poor infrastructure, high levels of poverty and very few economic opportunities. In addition to its own intrinsic value, South Africa’s biodiversity provides an important basis for economic growth and development, for example, by providing a basis for the fishing industry, rangelands that support commercial and subsistence farming, the horticultural and agricultural industry based on indigenous species, the tourism industry, locations for the film industry and commercial and non-commercial medicinal applications of indigenous resources. Threats Important is the need to keep biodiversity and ecosystem functions intact to ensure the ongoing provision of ecosystem services on which socio-economic development is based. The social and economic costs of not managing ecosystems in a sustainable manner are high, as demonstrated through threats such as accelerated land degradation and ecosystem loss, habitat destruction as a result of development and land use changes, increased infestation by invasive alien species, decline in species loss, reduction in water quantity and quality and the deterioration of air quality. Economic sectors which are critical to national development and job creation, but which often have a negative impact on biodiversity and ecosystem functioning, particularly when poorly planned or sited, include mining, agriculture, plantation forestry and the development of residential and tourism infrastructure, as well as commercial fishing. Illegal hunting and poaching also have a negative impact on biodiversity, threatening particular species such as rhino and abalone. Institutions responsible for managing biodiversity The Department of Environmental Affairs (DEA) is the primary custodian of the environment in South Africa, but this responsibility is shared. Biodiversity is also an important function of other departments such as Department of Water Affairs, Department of Agriculture, Forestry and Fisheries, and a number of other institutions, public and private at national, provincial and local level. DEA has two public entities: a national parks authority (SANParks), mandated with the management of the country’s national protected areas, and the South African National Biodiversity Institute (SANBI), which is responsible for a range of functions related to biodiversity research, planning, mainstreaming, policy advice and programme co-ordination. The Protected area system, mainstreaming measures, biosafety issues and ABS South Africa’s protected area network currently falls far short of sustaining biodiversity and ecological processes. In this context, a National Protected Area Expansion Strategy (NPAES) was developed of which the goal is to achieve cost-effective protected area expansion for ecological sustainability and increased resilience to climate change. The NPAES highlights ways in which we can become more efficient and effective in allocating the scarce human and financial resources available for protected area expansion. It sets targets for protected area expansion, provides maps of the most important areas for protected area expansion, and makes recommendations on mechanisms for protected area expansion. The common set of targets and spatial priorities provided by the NPAES enable co-ordination between the many role players involved in protected area expansion. With respect to its conservation management structures, South Africa has 13 management authorities responsible for the 294 state protected areas at national and provincial levels. In order to assess the effectiveness of management authorities to manage their parks, a Management Effectiveness Tracking Tool was developed in order for management authorities to measure their future performance. Barriers to the effective implementation of the CBD strategic plan at the national level Some of the barriers to effective implementation of the CBD strategic plan include: - Low priority of biodiversity issues in the South African political agenda due to other pressing needs such as education, health, service delivery, rural development. - The NBSAP has not previously been explicitly linked to government priorities in terms of delivery agreements, socio-economic development priorities and funding requirements, and emerging government approaches through the “green economy”, and climate change response strategies. - Much biodiversity conservation work has been carried out in global biodiversity hotspots through GEF and other funding, but this is uneven across the country and has not yet prioritised areas where high poverty and high ecosystem productivity coincide. - Gains made through bioregional programmes with donor funding have resulted in many of the targets of the NBSAP being addressed. Some gains were sustained beyond the funded period and functions embedded into provincial and local government, but many challenges remain, particularly the challenge of resourcing biodiversity stewardship work with communal and private landowners. - Provincial conservation authorities and municipalities lack skills and resources to tackle biodiversity management mandates – and it is at these levels that many critical decisions are taken affecting biodiversity - In particular, provincial authorities have a limited emphasis on monitoring and limited capacity for monitoring in relation to achieving targets set out in the NBSAP and NBF. - Lead agents have lacked capacity and human resources to implement the NBSAP and NBF fully. Many of the priorities have been tackled, but not in a systematic way, with priority actions being allocated, costed and resourced. - Intergovernmental relations on biodiversity conservation are often characterized as weak. There is a gap between national and other levels regarding communication to achieve common goals and how decisions will be made. Working Group 1 of the Ministerial Technical Committee (MINTEC) was in the past a positive initiative for promoting this coordination, but not always used to maximum effect in this regard. - There is a large amount of new legislation to comply with, and a lack of clarity on mandates, responsibilities and functions. - Progress has been made in mainstreaming biodiversity into spatial and development planning at local and provincial levels, but much work remains to be done, particularly in relation to major economic sectors such as mining, agriculture, forestry and fisheries. Other relevant background information on the country’s Biodiversity planning process South Africa currently has four key national policy tools that guide biodiversity planning and management, each outlined below: - National Biodiversity Strategy and Action Plan (NBSAP) - National Spatial Biodiversity Assessment (NSBA) - National Biodiversity Framework (NBF) - National Protected Areas Expansion Strategy (NPAES). 1. NBSAP and target setting In response to requirements of the CBD as well as national needs, South Africa developed an NBSAP that was published in 2005. The development of the NBSAP, which was made possible by financial support from the GEF through UNDP, was an intensely participatory process led by the national Department of Environmental Affairs (DEA) between 2003 and 2005. Six task team workshops brought together a wide range of expertise and interests, and the draft strategy was debated in two national consultative workshops, additional workshops in the provinces and with NGOs, CBOs and municipalities. The NBSAP sets out a comprehensive framework and long-term plan of action for the conservation and sustainable use of South Africa’s biodiversity and the equitable sharing of benefits derived from such use. Achievements of the NBSAP were that it created a legal instrument for monitoring and reporting, and set clear targets, time frames, and lead agents. The CBD targets for 2010, the NBF 2013 targets, and the CBD 2020 targets have provided a continuous focus on biodiversity issues. Coordination structures have been created and many of the outcomes have been achieved. Some of the weaknesses in the process and ongoing challenges of implementation are highlighted in the barriers section above. 2. NSBA and spatial priorities The NBSAP included a spatial component, the National Spatial Biodiversity Assessment 2004, which provided the first comprehensive national assessment of the status of biodiversity at the ecosystem level – across terrestrial, freshwater, estuarine and marine ecosystems. The NSBA used systematic biodiversity planning techniques to determine the conservation status of ecosystems and to identify national priorities for conservation action and more detailed planning. As far as can be established, South Africa was the first country to include a comprehensive spatial assessment as part of its NBSAP. The NSBA, carried out by SANBI under the leadership of DEA, provides clear biodiversity targets, spatial priorities and indicators that can be fed into a wide range of other environmental reports and plans at national and regional scale. Through its focus on ecosystems – represented by vegetation types – as well as species, it is well suited to inform a landscape approach to biodiversity conservation and ecosystem resilience. The NSBA has provided an important tool for monitoring, and has also provided the national context for the development of provincial and local spatial biodiversity plans and the basis to assess the adequacy of the current protected area network. The NSBA also provides some of the key headline indicators for the National Biodiversity Monitoring and Reporting Framework, currently under development by DEA and SANBI. The framework deals with pressures on biodiversity, the state of biodiversity (ecosystems and species), and responses (including financial and human capacity to respond to challenges). It will shortly be updated by the publication of the 2012 National Biodiversity Assessment, which will feed into the new NBSAP. 3. NBF and priorities for action The NBSAP and the NSBA together informed the development of the National Biodiversity Framework (NBF), which is a requirement of the Biodiversity Act, and was published in 2008 and gazetted in 2009. This effectively gives the NBSAP some legal standing, another feature that sets the South African NBSAP apart from those in many other countries. The NBF draws together the key elements of the other documents, focusing attention on immediate priorities for action, both spatial and thematic. Its purpose is to provide a five-year framework to co-ordinate and align the efforts of the many organisations and individuals involved in conserving and managing South Africa’s biodiversity. While the NBSAP is comprehensive, the NBF focuses attention on the most urgent strategies and actions that can make the greatest difference. It identifies 33 priority actions for the period 2008 to 2013, organised according to the five strategic objectives of the NBSAP. The NBF will be reviewed at least every five years, providing an opportunity to take stock of progress, review priorities and realign efforts. The NBF has been written in such a way that it is useful to organs of state (both those whose core business is biodiversity conservation and those whose is not), government-led programmes, NGOs and the private sector, particularly production sectors whose activities impact most heavily on biodiversity, providing the basis for engagement with these sectors on the location of development, the type of development, and the consumption of natural resources in the development process. 4. NPAES and expanding protection As in many other countries, the existing protected area network in South Africa reflects a history in which the location of protected areas was driven by factors that often had little to do with biodiversity importance or representation of species or ecosystems. The result is that some ecosystems and species are well protected while others are severely under-protected, and the protected area network excludes some key ecological processes. South Africa’s National Protected Areas Expansion Strategy (NPAES) has been developed, building on the NSBA, as a tool to achieve cost-effective protected area expansion that enhances ecological sustainability and resilience to climate change – the latter through having more, larger protected areas; connecting them with natural corridors in the landscape, and focusing some management actions on resilience, adaptation and mitigation needs. The NPAES provides maps of the most important areas for protected area expansion with a focus on areas that capture the full range of biodiversity pattern and ecological processes, climatic gradients, a wide range of microhabitats, and natural corridors such as coastal, dune and river corridors. Although South Africa is not unique in having a protected areas expansion strategy, the NPAES has some innovative characteristics, including that: it sets ecosystem-specific protected area targets, so that not all hectares count equally towards meeting the targets; it is underpinned by a systematic biodiversity plan that identifies focus areas for protected area expansion based on the ecosystem-specific targets; it explicitly incorporates climate change design principles in identifying the focus areas for protected area expansion; it covers both terrestrial and marine habitats; and it is a nationally agreed and ministerially approved tool. The NPAES recommends two main mechanisms for securing land for protection – acquisition and contract agreements, including through biodiversity stewardship. - National Reporting to CBD. Reports; Date of Submission to CBD Secretariat; Current Status*; Comments. National Biodiversity Strategy and Action Plan; 06-06-2006; Submitted; Currently outdated. Revision of NBSAP; -; Not started; Funding being applied for herein. 1st National Report; 27-02-1998; Submitted; -. 2nd National Report; 06-09-2004; Submitted; -. 3rd National Report; 07-03-2006; Submitted; -. 4th National Report; 24-04-2009; Submitted; -. - Capacity Needs Assessments carried out YES NO. Start Date (dd-Mmm-YY): December 2004; End Date (dd-Mmm-YY): 01 December 2008. Please list all of the CBD Program of Work and cross-cutting themes that were addressed in the Biodiversity Enabling Activities Capacity Needs Assessments:; Dates. Integration of biodiversity issues into sectoral and cross sectoral plans; 2008. In-situ conservation, Ex-situ conservation, Sustainable use; 2008. Minimizing adverse impacts; 2008. Monitoring, Research, Technical, scientific co- operation and information sharing; 2008. Access to genetic resources, biotechnology and distribution of its benefits; 2008. Financial resources to support obligations; 2008. Incentive measures; 2008. 3) Clearing House Mechanism (CHM) established?; YES NO. CHM link(s):; www.environment.gov.za www.sanbi.org www.sanparks.org. Is the CHM website maintained up to date?; YES NO. How many people currently operate and maintain the national CHM? n/a; Not yet estimated. How many people visited the national CHM website in the past 12 months? n/a; Not yet estimated. Note: A stand-alone CHM site not been established as yet. Sites for several national institutions that manage biodiversity exist and are maintained up-to-date – e.g. the Department of Environmental Affairs (DEA), SANBI, SANParks, but also others not mentioned here. The plan is the establish a single mechanism, like a gateway, but with links to existing sites, or to establish a set of pages under DEA, also with links to other relevant sites..

B. Enabling Activity Goals and Objectives (The proposal should briefly justify the need for the project.)

The Baseline Project: The Current NBSAP and the new CBD Strategic Plan The new CBD Strategic Plan, adopted at CoP-10 in 2010 in Nagoya, clearly addresses the need for updating NBSAPs, stating in Target 17 that “By 2015, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan.” The strategic plan also covers a range of issues that will need to be incorporated into the revised NBSAPs, including guidance to countries to: a) fully realise the value of biodiversity and ecosystem services, and incorporate these values into national and local development and poverty reduction strategies (Targets 1 and 2); b) increase the global terrestrial protected area estate from 12% to 17% and the marine estate from 6% to 10% (Target 11); c) restore and safeguard key ecosystem services, especially for water, health and livelihoods (Target 14); and d) strengthen ecosystem resilience to climate change and promote ecosystem-based approaches to climate change adaptation and mitigation (Target 15). While South Africa’s current NBSAP and NBF are comprehensive and have clear national targets, these were set in the context of the CBD’s 2010 targets and their implementation has not been comprehensively monitored or implemented. There is a need for South Africa to review its own national targets in the context of its commitment to the CBD, given the new Aichi biodiversity targets set for the period 2011-2020 at the 10th Conference of the Parties to the CBD in Nagoya in October 2010. In addition, the time period covered by the current NBSAP and NBF will expire soon. Then there is a need to build on the good work started in South Africa and tackle more effectively the global challenges in the “second generation” of NBSAPs around incorporating valuation of biodiversity and ecosystems services into national development planning and poverty reduction strategies. And to continue the work begung linking biodiversity and adaptation to and mitigation of climate change. In addition, all of the barriers to effective implementation of the previous NBSAP and NBF, as discussed above, need to be tackled, not just through the production of a new document, but through an NBSAP development process that builds capacity of national, provincial and local role-players for effective implementation, monitoring and reporting. The most recent NBSAP for South Africa was completed in 2005. This version of the NBSAP addresses the following topics as indicated in brackets, after each one, but in relation to the CBD’s 2010 targets, and has not been updated for the CBD Strategic Plan’s Aichi Targets for 2011-2020 - A plan for integrating the value of biodiversity into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems (Target 2) (see Outcome 1.1. of current NBSAP) - A plan for creating incentives and removing harmful subsidies (Target 3) (see Outcome 1.3 Activity 1.3.11) - A plan for developing landscapes that have sustainable production and consumption and ensure the use of natural resources falls well within safe ecological limits. (Target 4) (see Outcome 5.2) - A plan for fully implementing the Programme of Work on Protected Areas, including increased protection and landscape/seascape connectivity (Target 11) (see Outcome 4.4) - A plan for restoring and safeguarding ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being (Target 14) (see Outcome 4.4.1) - A plan for strengthening ecosystem resilience and the contribution of biodiversity to carbon stocks, including the restoration of at least 15 per cent of degraded ecosystems (Target 16) - A plan for the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources (Target 20) Proposed Response and Rationale: The new generation of BD EA. This project seeks to fully incorporate the above issues into the NBSAP. This ‘new generation’ of NBSAP will help set a regional standard of excellence by creating a national road map for achieving the Aichi Targets. Special emphasis will be placed on mainstreaming biodiversity into development plans, incorporating protected area networks and sustainable production systems into ecosystem-based climate adaptation and resilience plans, and creating sustainable finance for biodiversity conservation through the full valuation of key ecosystem services. The project will also link in to the European Union-funded project managed by UNDP on “Building Transformative Policy and Financing Frameworks to Increase Investment in Biodiversity Management” which is being piloted in eight countries including South Africa. The project manager for the NBSAP project will be repsonsible for making the links between these two projects. Alignment with Focal Area Outcome(s): BD5 Objective: Integrate CBD Obligations into National Planning Processes through Enabling Activities (herein serving as the ‘Project Development Goal’): Focal Area Outcome 5.1: Development and sectoral planning frameworks at country level integrate measurable biodiversity conservation and sustainable use targets. The Project Objective is: To integrate South Africa’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020. This will be achieved through the following Outcomes (corresponding to components described in detail below): - Outcome 1 – A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets - Outcome 2 – The NBSAP is revised/updated, building on the new National Biodiversity Assessment and incorporating a new National Biodiversity Framework and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience - Outcome 3 – National frameworks for resource mobilization, Convention reporting and exchange mechanisms are established and strengthened. Refer to Part I, Table A and to the next section for more details. How the project plans to build national capacity Enabling Activities are considered foundation activities within the framework of the GEF. The ultimate goal of Biodiversity Enabling Activities is to build national capacity across the board for biodiversity management. The effective achievement of global biodiversity benefits depend on the development of national capacity for managing biodiversity. The more robust this capacity is in a given country, the more effective the national implementation of the CBD will be. Enabling Activities are considered foundation activities within the framework of the GEF. The ultimate goal of Biodiversity Enabling Activities is to build national capacity across the board for biodiversity management. The effective achievement of global biodiversity benefits depend on the development of national capacity for managing biodiversity. The more robust this capacity is in a given country, the more effective the national implementation of the CBD will be. The approach to building of national capacity in this proposal follows the guidance from the GEF Strategic Approach to Enhance Capacity Building (2003) under the GEF’s cross-agency Capacity Development Initiative. Three levels of capacity were identified: individual, organizational and systemic. Quoting from a recent GEF publication on the theme of capacity (GEF 2010): “At the individual level, capacity development refers to the process of changing attitudes and behaviors, most frequently through imparting knowledge and developing skills through training. However it also involves learning by doing, participation, ownership, and processes associated with increasing performance through changes in management, motivation, morale, and improving accountability and responsibility. Capacity development at the organizational level focuses on overall performance and functioning capabilities, such as developing mandates, tools, guidelines and management information systems to facilitate and catalyze organizational change. At the organizational level, capacity development aims to develop a set of constituent individuals and groups, as well as to strengthen links with its environment. At the systemic level, capacity development is concerned with the “enabling environment”, i.e., the overall policy, economic, regulatory, and accountability frameworks within which organizations and individuals operate. Relationships and processes between organizations, both formal and informal, as well as their mandates, are important.” In this light, this project will build national capacity in South Africa in the following manner: Individual; The NBSAP revision process should draw from and contribute to the processes currently working to develop individuals’ capacity in the sector - including the Biodiversity Human Capital Development Strategy (a joint initiative by SANBI and the Lewis Foundation), the Environmental Skills Sector Plan and HCD Strategy (Department of Environmental Affairs), the Global Change Grand Challenge HCD Strategy (Department of Science and Technology), the Draft Training and Education Strategy for the Water Sector and the HCD Strategy for Natural Resource Management (WWF-SA). Individuals’ capacity will also be developed through their participation in working groups on aspects of NBSAP revision, on sectoral strategies and on guiding specialist studies. In particular, members of MINTEC’s Working Group 1 will be designated as focal points for their organisations in the NBSAP redevelopment process, and the process of helping to shape and implement the new NBSAP will help them develop their own individual capacity... Organizational; Having such an NBSAP focal point within each organisation would help also to develop organizational capacity, particularly in the provincial conservation authorities (parks boards / designated provincial departments), where roles and responsibilities in terms of NBSAP revision and implementation, as well as biodiversity monitoring and reporting, will be clearly defined through this project, and the resource implications in terms of financial and human resources will be explicitly tackled. Different provinces may take different routes to building institutional capacity to involve a broad range of stakeholders in supporting the provincial conservation authority on NBSAP implementation, including relevant provincial departments, municipalities, NGOs and CBOs and building on existing structures where appropriate, for example using the Mpumalanga Grasslands Programme provincial structure, broadening the mandate of the Eastern Cape Implementation Committee, or establishing a new KwaZulu-Natal Implementation Committee. The process of participating in NBSAP revision and implementation would not be limited to the provincial conservation authority, as the authority would ensure two-way reporting and feedback between the national (e.g. MINTEC) and emerging provincial structure, developing the institutional capacity of all the organizations involved.. Systemic; To the extent that the process of revising the NBSAP and NBF is able to establish clearer responsibilities and mandates for monitoring, reporting and implementing biodiversity and ecosystem management activities, this will improve the overall enabling environment for biodiversity conservation in South Africa. This will also be achieved through the results of the specialist studies becoming available for use as tools, for example, valuation studies, sectoral strategies and resource mobilization strategies, the latter linking with the EU-UNDP project on Biodiversity Finance. Systemic capacity for biodiversity management will also be built through the revision of the NBSAP, NBF and NBA in providing overall national targets and priorities for implementation, that will guide the work of government and civil society organisations and the individuals who make them up..

C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A).

Detailed Description of Activities per Project Component / Outcome The description that follows has been organized in five modules (I -V), following the GEF’s guidance, but which for the sake of simplicity were grouped within the three already mentioned Components / Outcomes. The following are modules: Component; Outline of modules for NBSAP Revision and Related Activities; Indicative percentage of total GEF funding in the proposal. 1; I. Preparation; 7%. II. Setting national targets, principles, & main priorities of the strategy; 7%. 2; III. Strategy and action plan development, including strategic studies; 63%. 3; IV. Development of Implementation plans and related activities; 20%. V. Institutional, monitoring, reporting and exchange; 13%. Component 1. Stocktaking and national target setting Key Outputs expected under this component includes the following: 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in a participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to South Africa’s’s reality, and helps develop provincial and national monitoring and reporting capacity. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through the 5th national report, and through other means. 1.4 In an iterative manner, South Africa taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership , Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal , among other relevant ones). Key Outcomes: - By end 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By end 2012, national targets in response to the global Aichi Targets are developed. Key Products or publications resulting from activities (may be combined into a single document): - Brief Action-Oriented National Biodiversity Framework for South Africa, reviewing biodiversity planning processes in South Africa and including requirements for implementation of the new NBSAP - Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 Key Activities (I-II): A key result from these activities will be the preparation of a revised or new National Biodiversity Framework which sets out the priorities for action by local, provincial and national government, statutory bodies and civil society in the revision and implementing the NBSAP. The government will finance the bulk of the costs of consultations with a subsidy from GEF. The TOR for the Stocktaking study & National BD Framework are contained in Annex E. - Preparing for the NBSAP revision - Taking stock of the NBSAP and identifying barriers to its implementation: This activity will focus on rapidly but accurately taking stock of existing plans, policies and practices, and of the root causes of biodiversity loss, understanding the current drivers behind these threats, as well as the key aspects of the policy environment that are barriers and challenges to effective implementation of the current NBSAP. Based on existing studies and analyses, the emphasis of this activity will be on identifying key gaps in the existing NBSAP, understanding the primary drivers and root causes, and identifying the means of overcoming existing barriers and challenges. - Stakeholder consultation and participation: This activity will focus on ensuring a robust consultative process that engages representatives from national, provincial and local government, statutory bodies, non-governmental organizations, community-based organizations, traditional authorities, representative structures of communal and private landowners, and representatives of commercial production sectors. The aim is to develop and sustain a participatory process in order to increase the likelihood of successful implementation of the NBSAP. This is especially important relative to the goals of mainstreaming biodiversity into national development plans, and promoting resilient landscapes that include production sectors. - Setting targets - Setting targets and priorities: This activity focuses on setting specific, measurable, achievable and time-bound targets for the South Africa’s new NBSAP based on the global Aichi Targets, including targets on restoration of ecosystems, protected area coverage, overall biodiversity loss, and other aspects of the Strategic Plan. This activity, which is linked to priority setting among different aspects within the NBSAP, will be completed by CoP-11 (or shortly after). Component 2. NBSAP Update Key Outputs expected under this component includes the following: 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for South Africa, anchored into national development frameworks, is updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. 2.2 The updated and fully endorsed NBSAP for South Africa is submitted to the CBD within the deadline set by the COP. It will include the following strategic studies to be financed by Government and the GEF: - Priorities for national and provincial implementation of South Africa’s National Protected Areas Expansion Strategy, linked to the CBD’s Programme of Work on Protected Areas (PoWPA) and linked to government mandates and delivery agreements with resource mobilization for this covered under Component 3 - Local TEEB (The Economics of Ecosystems and Biodiversity): Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research pieces needed to make the case for action based on valuation and/or the anticipated cost of inaction - Exploring and costing options for Ecosystem-based adaptation to climate change in South Africa, linked to government priorities for job creation and poverty reduction - Development of a ‘biodiversity-centred’ development impact analysis for key economic sectors: Assessing the stakes for biodiversity of sectoral economic development, and the opportunities for conservation and sustainable use in South Africa Key Outcomes: - By early 2014, South Africa’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP Key Products or Publications resulting from activities - Second National Biodiversity Strategy and Action Plan for South Africa - Sub-product 1: Implementation Priorities for the NPAES - Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research needs - Sub-product 3: Ecosystem-based adaptation Study: Options and costs of nature-based solutions to climate change in South Africa - Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry Key Outcomes: - By 2014, South Africa’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP. Key Activity (III) - Developing the NBSAP This step will seek to achieve the following: (i) Developing the strategy and actions to implement the agreed targets though national consultations; (ii) Planning for implementation of the NBSAP and NBF by national, provincial and local government, and statutory bodies through responsibilities agreed on through MINTEC Working Group 1, and with plans for resource allocation in place; and (iii) Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations, including ongoing mainstreaming into the Green Economy, the Presidential Jobs Fund and the Expanded Public Works Programme. While the project will focus on updating all aspects of NBSAPs, it will place particular emphasis on those aspects that are both highlighted in the 2011-2020 CBD Strategic Plan, including the following: - Assessing and integrating ecosystem services through economic valuation: The study on the Economics of Ecosystems and Biodiversity (TEEB) has drawn attention to the global economic benefits of biodiversity and ecosystem services and to the growing costs of biodiversity loss and degradation. South Africa has conducted a number of studies of the value of biodiversity and ecosystem services. There are some gaps remaining, however, particularly around quantifying the costs of inaction in certain areas and the trade-offs which can be made in specific economic sectors which may enable higher societal gains in the long term. In addition, the findings of studies have often not been translated into key figures, simple take-home messages for policy-makers or specific pitches to potential buyers of ecosystem services. Currently, DEA is supporting a consultancy study that will look at the issue of biodiversity valuation nation-wide, although results will take 1-2 years to become available. Furthermore, the new multi-country EU-funded UNDP pilot project on Biodiversity Finance will be looking at valuation issues in South Africa as part of an overall assessment of biodiversity finance. Hence, the work under this project will be primarily to compile the information and analysis on valuation emanating from these initiatives – and from other past ones – and compile relevant data on it that will contribute to the updated NBSAP. An Environmental Economist (national consultant) will be contracted to assist in combining the results from existing and on-going studies in order to prepare the ecosystem valuation chapter of the NBSAP. The consultant will also work together with the Technical Coordinator, the rest of the project team, DEA staff and partners to convey a meeting aimed at discussing the results of the consultancy and validate the proposed NBSAP valuation chapter. - Specific steps in the process of assessing ecosystem services through valuation may include: - Identify and assess the full range of values of key ecosystem services within the country, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the national TEEB valuation results, the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g., water, carbon, soil retention, nutrient recycling, recreation, among others), and existing global and regional maps and overlays of key ecosystem services - Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use. - Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods; as well as quantifying the costs of inaction in particular cases. - Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives, as well as through the removal of negative incentives (those that contribute to the drivers of biodiversity loss). - Mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies: Mainstreaming has been defined as the internalization of biodiversity conservation goals into economic and development sectors, policies and programmes, such that they become an integral part of their functioning of these sectors. The project will develop a mainstreaming study for the purpose on the NBSAP update. - As part of this process, the project will focus on the following sectors: Agriculture and Livestock Plantation Forestry Fisheries Mining and Gas - The Project will also focus on the following development areas / topics: Land-use management, including spatial and infrastructural development planning Development finance Poverty alleviation Rural development and livelihoods Food security Gender Job creation and the green economy Climate change mainstreaming - Specific steps in this process may include: - Forming partnerships between relevant stakeholders interested in biodiversity conservation issues and in development issues - Explicitly identifying key stakeholders’ interests, and desired outcomes - Identifying potential conflicts and trade-offs, and work towards mutually acceptable solutions, including strategies that serve mutually beneficial interests and achieve mutually beneficial outcomes - Embedding and institutionalizing these strategies in the institutions, policies, agreements, programs and mechanisms of each sector - Incorporating climate change issues into NBSAPs: The previous NBSAP did not adequately address aspects of climate change, but this was addressed through the National Protected Areas Expansion Strategy (NPAES) which provides a map of 44 important focus areas for protected area expansion – areas that capture the full range of biodiversity pattern and ecological processes, based on systematic biodiversity planning. In addition to improving representation of species and ecosystems in the protected area system, the strategy aims to achieve cost-effective expansion that enhances ecological sustainability and resilience to climate change. The strategy ties in with the international movement towards recognition of the role an expanded protected area network can play in climate change mitigation and adaptation, and hence highlighting the need for (i) having more, larger protected areas; (ii) connecting protected areas with natural corridors in the broader landscape, and (iii) focusing some management actions inside protected areas on resilience, adaptation and mitigation needs. The NPAES provides maps of the most important areas for protected area expansion with a focus on areas that capture the full range of biodiversity pattern and ecological processes, climatic gradients linking upland and lowland area, a wide range of microhabitats, natural corridors such as coastal, dune and river corridors, and potential climate refuges, such as mountain ravines and south-facing slopes that provide cooler and often more moist habitats that can be colonized by species under pressure from changing climates. South Africa also follows a landscape approach – keeping corridors and other areas of natural vegetation beyond formal protected areas intact in order to maintain ecosystem services that are threatened by the impacts of climate change. This is not based on systematic and detailed mapping of where all species or ecosystems are likely to move, but rather on a general understanding that securing corridors of well-managed, natural or near-natural habitats is critical to capturing environmental gradients that allow plant and animal species to move in response to climate change. The activity as part of this project will go beyond the NPAES and focus on whole production landscapes, exploring and costing options for ecosystem-based adaptation to climate change in South Africa, linked to government priorities for job creation and poverty reduction. The aim is to inform the new Strategy on the basis of sound analysis on the interface Biodiversity & Climate Change. A second step will include the costing of priority adaptation options and resilience linked to the management of living resources. Component 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms Key outputs expected under this component includes the following: 3.1 A National implementation framework for the new NBSAP is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBSAP; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) the resources needed for the implementation of the NBSAP and NBF priorities are estimated and fed into the EU-funded UNDP pilot project on biodiversity finance in South Africa which includes a baseline assessment of existing finance for biodiversity and a quantification of the funding gap. 3.2 An effective, user-friendly and easily updatable country-driven CHM web-gateway, integrating key biodiversity information in existing sites, is developed; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. 3.3. Immediate CBD reporting obligations are met by South Africa in a timely manner, coordinated by the Project Manager, in particular the Fifth National Report to the CBD by 31 March 2014. 3.4 An institutionalised framework for reporting to the CBD, including requirements for data sourcing, monitoring and reporting, is agreed through the Ministerial Technical Committee’s Working Group 1, outlining responsibilities of units and staff in the national Department of Environmental Affairs as well as provincial conservation authorities, with resourcing requirements determined for these ongoing functions to enable ongoing budgetary allocations. Key Products or publications (maybe combined into one): - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy - Fully functional CHM Gateway for South Africa, based on best international practice on the matter In connection with the above outputs and deliverables, and as a result of the activities outlined below, South Africa will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By 2013, complete the establishment and improvement of a national clearing-house mechanism - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment Key Activities (IV - V): - Developing implementation plans This activity will focus on developing an overall plan for implementing the NBSAP. Key project consultants for this activity are the Technical Coordinator, the Environmental Economist and the Capacity Assessment Consultant. This implementation plan will include the following components: - Developing an overall implementation plan: The primary output of this activity is an overall implementation plan that delineates major steps, responsible parties, costs for main activities, expected outcomes and a timeline - Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan: South Africa’s PoWPA implementation plan will be based on the NPAES and the priorities for implementation outlined through the strategic study in Component 2, linking these to Aichi Target 11 of the CBD’s Strategic Plan, and the resource mobilization strategy in this component (see below). - Securing sustainable finance for NBSAP implementation: Article 20 of the Convention mentions the need for Parties “to provide, in accordance with its capabilities, financial support and incentives in respect of those national activities which are intended to achieve the objectives of this Convention.” In the past few years, there has been a wide proliferation of innovative biodiversity finance mechanisms, such as payments for ecosystem services, conservation trust funds, biodiversity offsets and bio-carbon funding, among many others. South Africa is still in the early stages of exploring these mechanisms. This activity will therefore focus on the following, building on some costing work done for the current NBF, and identifying how to create synergy and overlap with the EU-funded biodiversity finance framework pilot through UNDP: - Identifying the existing financial gap for implementing the NBSAP - Identifying potential sources of revenue for filling these gaps - Assessing the feasibility for these revenue sources - Developing a detailed plan for operationalizing these revenue sources. - Assessing and strengthening capacity needs: One of the primary areas of enabling activities is the assessment of capacity needs. The decisions at CoP-10 place new and ambitious demands on countries, including requirements to protect and sustainably manage their lands and water, to develop comprehensive plans that integrate climate change into their land use, development and sectoral plans and strategies, and to develop appropriate biodiversity and climate policies, laws and incentives. This activity will ensure that South Africa develops a road map for strengthening these specific capacities, and will build on existing capacity needs assessment, particularly the findings of the 2008 National Capacity Self Assessment, which identifies detailed gaps in individual, organisational and systemic capacity levels. - Institutionalizing, monitoring and reporting - Monitoring and reporting on the status of biodiversity under climate change scenarios: Monitoring and reporting on the status of biodiversity is a key aspect of several Programmes of Work within the CBD. To date, efforts to monitor and report on the status of biodiversity have been sporadic and have typically not taken into full account the status and trends of biodiversity, the status of effective conservation, the contribution of ecosystem services (such as water and carbon), and the likely impacts of climate change on biodiversity and ecosystem services. Through this project, South Africa will further develop the emerging National Biodiversity Monitoring and Reporting Framework to ensure that future monitoring and reporting on the status of biodiversity and ecosystem services is comprehensive, and fully incorporates climate change issues. This aspect is linked to the implementation of the NPAES. - Developing clearinghouse mechanisms (CHM): Of the 90 countries that accessed funding under the Fourth National Report joint global project (UNDP-UNEP/GEF), only 44 had national CHM sites, and of those, 25 were kept up-to-date (data from 2010). At the same time that CHMs are largely out of date, reliance on digital information has increased exponentially. South Africa is no exception. Although an effort was made to establish a Clearing House Mechanism in 2002/03, there is no institutional memory left as to the detail thereof. This aspect of the project will help develop an effective, user-friendly and easily-updatable CHM that will enable South Africa to effectively share information nationally, regionally and globally. This could be done through a section on the existing website of DEA or through the development of a gateway that combines information from DEA’s, SANParks’ and SANBI’s sites, or channels to the information on these sites with a specific focus on biodiversity scientific and technical matters and other subjects that would be relevant in exchange mechanisms. The project will also work in collaboration with the CHM of the Secretariat of the CBD, to ensure that lessons and information are disseminated globally. - Developing a permanent framework for reporting to the CBD: Parties to the CBD committed to submitting a fifth national report by 2014. In this project, South Africa will submit a 5th National Report that fully covers the NBSAPs, key changes in the status and trends in biodiversity status, threats and conservation, and will develop a long-term reporting framework that will enable the country to better track changes over time, including clear responsibilities and resource requirements. Collaboration and synergies with related initiatives South Africa has a large and active GEF biodiversity portfolio and many of the flagship projects were implemented with UNDP and the WB. The project Technical Coordinator, the host initiations and the UNDP Country Office will ensure that this enabling activities project can benefit from technical synergies with other GEF projects. These synergies will be created primarily with the following projects: - New UNDP-GEF protected areas project through the GEF-5 cycle: Synergy here will be around the expansion of the protected area estate and tackling climate change adaptation and mitigation goals, part of what the GEF-5 project will aim to do, and part of the targets set in the new NBSAP - New UNDP-GEF mainstreaming project through the GEF-5 cycle: Synergy here will be around the work in production landscapers with local government to influence land-use planning and decision-making, part of what the GEF-5 project will do, and art of the targets set through the new NBSAP - EU-funded pilot on biodiversity finance frameworks and methodologies: Synergy here will be around feeding the resources needed for the implementation of the NBSAP and NBF priorities into the EU-funded pilot in SA which includes a baseline assessment of existing biodiversity finance and a quantification of the funding gap, as well as identification of new sources of finance. South Africa’s NBSAP can build on the EU-UNDP pilot, and will therefore not need to cover all of these areas. - Human Capacity Development Strategy projects (see above): Synergy here will be around identification of needs and opportunities for developing capacity of institutions and individuals through these various strategies and feeding these into the NBSAP capacity development identification of needs. - Development of Biodiversity Placements through the Presidential Jobs Fund and continued expansion of Environmental Public Works Programme and its Wage Incentive: Synergies here will be around incorporating the results and findings of this work into the mainstreaming of biodiversity objectives into national development planning through the NBSAP. Collaboration with all of the above projects will be ensured by using them as a source of knowledge and information for the overall biodiversity planning process. The project managers and staff of the above mentioned projects will be invited to Biodiversity EA project events. They will be requested to make presentations, showcase active projects and avail essential information and data for preparing the products foreseen under this project, in particular the new NBSAP and the 5th National Report. This will maximise exchanges and reciprocal input. In the case of already completed but yet relevant projects, useful lessons will be extracted and projects may also be showcased. The above mentioned list is but a small sample of active projects, programmes and initiatives with which the EA project can seek synergies and collaboration with. South Africa counts on many others, the inclusion of which would make the list too extensive. The implementation of wider stakeholder engagement activities under the project’s Component 1 will lead to the exploration of all viable partnerships with relevant projects, programmes and initiatives. Project implementation arrangement: The project will be implemented over a period of 2 years. The Department of Environmental Affairs (DEA) is the government institution responsible for the implementation of the project and will act as the Executing Agency. UNDP is the GEF Agency for the project and accountable to the GEF for the use of funds. The project is nationally implemented (NIM), in line with the Standard Basic Assistance Agreement (SBAA, 1994) between the UNDP and the Government of South Africa, and the (current) Country Programme Action Plan (CPAP) for 2007-2010. The overall responsibility for the project implementation by DEA implies the timely and verifiable attainment of project objectives and outcomes. DEA will provide support to, and inputs for, the implementation of all project activities. DEA will nominate a high level official who will serve as the National Project Director (NPD) for the project implementation, proposed as the National Focal Point for the CBD, who will liaise with other relevant focal points, for example, on Biosafety, RAMSAR, CITES and the PoWPA. The NPD will chair the Project Steering Committee (PSC) and other relevant stakeholder, sectoral and working groups under the project, and be responsible for providing government oversight and guidance to the project implementation. The NPD will not be paid from the project funds, but will represent a Government in kind contribution to the Project. Working closely with DEA, the UNDP Country Office (UNDP-CO) will be responsible for: (i) providing project assurance services to government (ii) recruitment of project staff and contracting of consultants and service providers, if this formally is requested by government; (iii) overseeing financial expenditures against project budgets approved by PSC; (iv) appointment of independent financial auditors; and (iv) ensuring that all activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures. A UNDP staff member will be assigned with the responsibility for the day-to-day oversight over and assurance on project implementation and finance. A National Project Steering Committee (PSC) will be convened by DEA, and will serve as the project’s coordination and decision-making body (Project Board). The PSC will include representation of all the key project stakeholders, and could be based around Working Group 1 of MINTEC, with additional representation, for example, from civil society. The PSC meetings will be chaired by the NPD. It will meet according the necessity, but not less than once in 12 months, to review project progress, approve project work plans and approve major project deliverables. The PSC is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document. The day-to-day administration of the project will be carried out by a Project Coordinating Unit (PCU), comprising a Project Technical Coordinator, who will be located within DEA’s offices. Project consultants will be recruited using standard UNDP recruitment procedures. The Technical Coordinator will manage the implementation of all project activities, including the work of other consultants and service providers. She/he will liaise and work closely with all partner institutions to link the project with complementary national programs and initiatives. The Technical Coordinator is accountable to DEA, and the PSC for the quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds. Comparative advantage of UNDP in South Africa with respect to this project: UNDP has historically been the largest GEF implementing agency in terms of assisting countries in undertaking biodiversity enabling activities, having assisted more than 100 countries with it through several projects. The GEF2 global project ‘Biodiversity Support Programme’ was jointly implemented with UNEP and has set the stage at the global level in the field of biodiversity planning among GEF eligible countries. Furthermore, UNDP assisted South Africa in the preparation of its existing NBSAP. The Government of South Africa has requested UNDP assistance in designing and implementing this project, due to UNDP’s track record globally in supporting enabling activities for biodiversity, as well as its extensive GEF project portfolio in Southern and Eastern Africa, and South Africa specifically. UNDP has an established Country Office in Pretoria with well-developed working relationships with the key stakeholders of the project. It counts on two professional staff dedicated to the Environment and Energy portfolio. Past and ongoing projects implemented through UNDP include the CAPE project, the Agulhas Biodiversity Initiative, The National Grasslands Programme, to mention a few. Moreover, the project will benefit from the presence of in Pretoria of the UNDP/GEF Regional Coordination Unit and a Regional Technical Advisor dedicated to Biodiversity and Ecosystem Management. Furthermore, UNDP will be availing the services of a UNDP Environment and Energy Policy Advisor, based in the UNDP Regional Service Centre in Johannesburg, who will participate in key events and make contributions to the project by commenting on drafts studies, TOR and other products. UNDP also has extensive experience in integrated policy development, human resources development, institutional strengthening, and non-governmental and community participation. Project’s alignment with UNDP’s programme for South Africa The overall UN System in South Africa and UNDP are in the process of aligning their programming in South Africa. This project is aligned with the UNDAF and the CPAP (both current and new) because it contributes to an enabling environment for sustainable development – based on the sustainable use of natural resources and biodiversity in order to promote socio-economic development for all South Africans. Under the new United Nations Development Assistance Framework (UNDAF) and the new Country Programme Action Plan (CPAP) for UNDP, is concerned with ensuring that environmental assets are well protected and enhanced. Under this outcome, UNDP will be supporting the Government of South Africa’s ongoing efforts to promote sustainable use of natural resources, mitigate environmental impact and explore new solutions and opportunities for inclusive growth. The project is aligned to the SA-UN Strategic Cooperation Framework 2013-2017 (SCF) and the Country Programme Document 2013-2017(CPD). Outcome 2 is particularly relevant for this project: “Government integrates environmentally sustainable development approaches into policies aimed at reducing poverty and promoting equitable socio-economic development acknowledged the need for sustainable management of environmental assets, protection and enhancement of natural resources as key priorities for government”. Stakeholder involvement in the implementation of the project The stakeholder involvement element is embedded in the description of several activities within this proposal which will have a consultative and participatory character. Indicatively, the following is a non-exhaustive list of key stakeholders in the process: - Department of Environmental Affairs (DEA) - South Africa Biodiversity Institute (SANBI) - South Africa National Parks (SANParks) - Department of Agriculture, Forestry & Fisheries - Department of Water Affairs - Department of Economic Development - Department of Mineral Resources - Department of Tourism - Department of Traditional Affairs - Department of Women, Children & People with Disabilities - CSIR Council for Scientific and Industrial Research - C.A.P.E – Cape Action for People and the Environment - Grasslands and SKEP (Succulent Karoo) Bioregional Programmes (among other similar programmes) - Provincial governments - WWF‐SA World Wide Fund for Nature ‐ South Africa - CREW - Custodians of Rare and Endangered Wildflowers - BWI - Biodiversity and Wine Initiative - FSC - Forestry Stewardship Council - LepSoc Lepidopterists’ Society of Africa - MRC - Medical Research Council - Plus several other relevant stakeholders A full stakeholder involvement plan will be developed in connection with the preparation of the UNDP Project Document that will operationalise this proposal at the level of UNDP, allowing South Africa to access the funding. This plan will include national and provincial government departments, local government, statutory bodies, non-governmental organizations, community-based organizations, traditional authorities, representative structures of communal and private landowners, and representatives of commercial production sectors. More specifically, the participation of NGOs and CSOs stakeholders in the implementation of this project will be ensured in every stage of it. NGOs and CSOs in South Africa are very active in the environment arena. They play an important advocacy and ‘watchdog’ role with respect to biodiversity management and in some cases represent the interests of poor or marginalised or communities. Many of these organisations count on extensive networks of stakeholders and have produced research data that can help enrich the products that this project will be concerned with. These advantages will be explored in full during project implementation. The participation of indigenous and traditional groups in the project will be ensured by organizations that represent these groups and through their participation in working groups and project events. “The various ‘First Nations’ indigenous groups in South Africa are collectively known as Khoe-San, comprising the San people and the Khoekhoe. The San groups include the Khomani San residing mainly in the Kalahari region, and the Khwe and !Xun residing mainly in Platfontein, Kimberley. The Khoekhoe include the Nama residing mainly in the Northern Cape Province, the Koranna mainly in Kimberley and Free State Province, the Griqua residing in the Western Cape, Eastern Cape, Northern Cape, Free State and Kwa-Zulu-Natal provinces and the Cape Khoekhoe residing in the Western Cape and Eastern Cape, with growing pockets in Gauteng and Free State Provinces. South Africa’s total population is around 50 million, with the indigenous groups comprising just over 1%. In contemporary South Africa, Khoe-San communities exhibit a range of socio-economic and cultural lifestyles and practices.” Furthermore, South Africa is making progress with respect to ABS policies and legislation. In addition, the Indigenous Knowledge Systems Policy has been approved and under implementation since 2004. It provides for fair and adequate compensation of indigenous people and local communities for their contribution to the protection and conservation of biodiversity, research and outcomes involving their knowledge. The project coordination will ensure that the voice of indigenous and traditional groups will be duly heard and taken into consideration in the preparation of the new NBSAP. Specific COP guidance on the matter, linked to implementation of the Convention’s Article 8(j), will be followed. Gender marking The South African government has stated that it supports the mainstreaming of gender into all fields, particularly on issues that have a strong impact on the quality of lives of women and girls, including climate change, biodiversity and sustainable land management. The South African Government is a signatory to the three Rio Conventions: namely the CBD (Convention on Biodiversity), the UNFCCC (UN Framework Convention on Climate Change), and the UNCCD (UN Convention to Combat Desertification). South Africa holds a strong view that all of these conventions should be implemented in a manner that reflects women’s perspectives and has gender provisions mainstreamed into it. Some areas of globally significant biodiversity and many areas of high ecosystem productivity coincide with rural areas that have high population densities and high poverty rates. In these areas there are many female-headed households as a result of migration of men to the larger cities for work, and it is often women who bear the brunt of poverty, and who may depend closely on biodiversity and natural resources for day-to-day survival. With appropriate interventions and support, this provides an opportunity for rural development where women can take the lead in the sustainable management of biodiversity. Government aims to ensure gender equality and social justice through utilization of land, restoration of ecosystems goods and services, prevention and mitigation of the effects of land degradation, ultimately enhancing livelihoods of whole communities. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men. Furthermore, gender marking implies the production of the following data by the project's year 2 and by its end: - Total number of full-time project staff that are women - Total number of full-time project staff that are men - Total number of Project Board members that are women - Total number of project Board members that are men - The number jobs created by the project that are held by women - The number jobs created by the project that are held by men

D. Describe, if possible, the expected cost-effectiveness of the project:

The proposed GEF project will ensure that the new NBSAP will guide all stakeholders and partners in the conservation of the country’s living resources. This is one way of making optimal use of biodiversity planning resources. The project combines GEF funding with UNDP co-financing and an essential government contribution in order to achieve the project’s objective without duplication efforts, but to ensure the application of resources in the most critical areas. The government’s contribution to the project includes the financing of a Project Technical Coordinator and of the time of staff from DEA to help coordinate the project. DEA will support a number of project activities directly, including the contracting of consultants when needed. This is will complement well the items to be financed by GEF and which are detailed in the Total Budget and Workplan in Annex C. In addition, DEA staff will also help in the organization of and participation in Project Board meetings, plus other work related to reporting, workplan approvals, signing off on CDR reports, RDPs, reviewing APRs/PIRs. The cost-effectiveness of the proposed activities will further be ensured by combining government internal, national and international expertise. GEF funding of consultation costs will be kept to a minimum, as government can finance much of it from existing resources. Other options have been considered, e.g. sub-contracting a NGO or parastatal to assist in NBSAP update as an entire ‘package’ of services to be rendered. High costs in fees from service providers would make such option less cost effective, coupled with the risk of biasing a document such as the NBSAP, which is supposed to reflect broad societal views on the national strategy for biodiversity. The project adopts the least-cost means of achieving the project’s objectives and follows the activity norms and cost benchmarks defined by GEF guidelines. It will be built upon the strong foundation of the previous developed NBSAP, Capacity Assessments and National Reports.

E. describe the budgeted M&E Plan:

Type of M&E activity; Responsible Parties; Budget US$ Excluding project team staff time; Time frame. Inception Meeting; Project Coordinator UNDP CO UNDP GEF; $8,000; Within first two months of project start up. Inception Report; Project Team UNDP CO; None; Immediately following IW. Measurement of Means of Verification for Project Purpose Indicators, Project Progress and Performance (measured on an annual basis); Oversight by Project Manager Project team; To be finalized during the inception phase and determined as part of the Annual Work Plan's preparation.; Annually prior to ARR/PIR and to the definition of annual work plans. Simplified Biodiversity Enabling Activities Annual Project Review / Project Implementation Report (APR/PIR); Project Team UNDP-CO UNDP-GEF; None; Annually. Quarterly progress reports; Project team; None; Quarterly. CDRs; Project Manager; None; Quarterly. Lessons Learned Log; Project Manager UNDP CO Programme Staff; None; Quarterly. Terminal Report; Project team UNDP-CO; Printing costs only, if any; At least one month before the end of the project. Lessons learned; Project team UNDP-GEF Regional Coordinating Unit (suggested formats for documenting best practices, etc.); To be determined as part of the Annual Work Plan's preparation.; Yearly. Audit; UNDP-CO Project team; $3,000 in total To be included in the CO audit plan.; Yearly. TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses; US$ 11,000.

F. Explain the Deviations from typical Cost Ranges (where applicable):

-- n/a--

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the country endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Zaheer Fakir | GEF Operational Focal Point | Department of environmental affairs | August 6, 2012 |

B. Convention Participation*

| Convention | Date of Ratification/ Accession (mm/dd/yy) | National Focal Point |
| --- | --- | --- |
| CBD | 04-Jun-1993 | Ms. Judie Combrink and Ms. Malta Qwathekana |

*To be filled for NCSA proposals only

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Biodiversity Enabling Activity approval.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec, UNDP/GEF Executive Coordinator |  | August 10, 2012 | Fabiana Issler, Regional Technical Advisor for Biodiversity, Africa, UNDP / EBD | +27-12-3548182 | fabiana.issler@undp.org |

Annex A. consultants to be hired for the Enabling Activity

| Position Titles | GEF only $ / Person Week* | GEF only Estimated Person Weeks | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management |  |  |  |
| Local |  |  |  |
| Project Technical Coordinator – financed by government for a total of 3 years or 156 weeks in total (budget reserved is approx. $225K / 3years) Roughly 1/3 of the tasks are managerial and are described here, 2/3 are technical (described below) | n/a | n/a | Managerial tasks - Objective To undertake the general administrative requirements of the project, including those related to project management and funding. The key tasks are: - Ensure that project Objective, Outcomes, Outputs and Activities are executed in a timely and appropriate manner. - Develop annual work plans and budgets, and submit these to the Steering Committee and to the UNDP Country Office for approval. - Develop TORs for consultants for technical assistance services, and other types of service provision works, as well as specifications for materials as required by the project, in consultation with the National Project Director. - Facilitate, guide and monitor the work of consultants, and approve/clear their deliverables in association with the Project Committee. - Organize and assist in project related activities, where required. These may include planning for meetings, local and national workshops, consultations, trips, and other project related activities. - Establish and maintain linkages with national and projects, programmes, initiatives, international organizations and persons which/who can be of assistance to the objectives of the project. - Provide timely reporting of project status as required by the Project Committee and the UNDP. - Maintain records of Project Committee meetings, decisions, actions etc. - Coordinate with other initiatives and programs whose outcomes and outputs are relevant to this project’s objectives. - Any other duties assigned by the Project Committee that have direct relevance to the project. |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Project Technical Coordinator – 2/3 technical tasks described here (same post as above) | n/a | n/a | Technical tasks - Objective: To lead the overall process of the stocktaking, stakeholder consultation, national target setting and the development of the NBSAP and be responsible for the timely drafting and finalization of the NBSAP. The key tasks are: - Serve as team leader for other consultants involved in the NBSAP and be overall responsible for the timely drafting of the document for submission to the CBD Secretariat; strictly adhering to the deadlines agreed to; and ensuring quality control. - Ensure that the inception meeting results in a clear roadmap on the scope of services and project tasks to be accomplished under the guidance of the National Project Director (in DEA) and working together with key project partners (e.g. SANBI, SANParks) and the UNDP technical staff. - Submit draft and revised versions of all studies and reports of the NBSAP activities to the National Project Director and key national partners (e.g. key deliverables) and to UNDP technical staff (e.g. the Simplified APR/PIR and other required monitoring report), as per reporting timelines agreed upon at the inception meeting. - Play a pivotal role in developing a work plan and coordinating the input and outputs of all consultants, as well as overseeing the technical quality of deliverables. - Ensure that all Climate Change-related issues highlighted in the second National Communication to the UNFCCC that affect biodiversity (adaptation) or affected by biodiversity (mitigation) are integrated and addressed in the final NBSAP. - Ensure that all lessons learnt in the mainstreaming of biodiversity into the production sectors are incorporated into the NBSAP. - Identify implementation partners for the undertaking of the various activities and develop an overall implementation plan. - Submit a final draft to the Steering Committee (Project Board) through the National Project Director, incorporating stakeholder inputs and guidance provided. Contribution to the following deliverables: - Brief Action-Oriented National Biodiversity Framework for South Africa, reviewing biodiversity planning processes in South Africa and including requirements for implementation of the new NBSAP - Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for South Africa - Sub-product 1: Implementation Priorities for the NPAES - Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research needs - Sub-product 3: Ecosystem-based adaptation Study: Options and costs of nature-based solutions to climate change in South Africa - Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy - Fully functional CHM Gateway for South Africa, based on best international practice on the matter Qualifications and experience: Should have an advanced degree in environmental or natural sciences (e.g. MSc), economics, social sciences, management, with professional exposure to biodiversity management issues. Proven track record of drafting relevant materials in with biodiversity as a topic (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy, timeliness and technical quality. Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences. Knowledge and understanding of the relevant UN Convention, Previous experience in the development of NBSAPs. |
| NBSAP Communications and Editorial Officer* | 961.538462 | 52 | Objective: To be the focal point for all editorial and communication tasks in connection with the BD EA project and the person primarily responsible for the development of a communication and outreach strategy for the NBSAP. Key tasks are: - Play a central role in the process of collecting views and formulating documents that will be the key products from the BD EA project, by working under the technical and strategic guidance of the Project Technical Coordinator, but also by working in close collaboration with the relevant working groups and stakeholders. - Develop a stakeholder consultation and participation plan that will ensure that the NBSAP development process is participatory, increasing the likelihood of its successful implementation. - Work on the preparation of base documents and presentations for technical meetings. - Based on the results from the stock-taking and target-setting activities, develop proposals for presenting South Africa’s national targets, developed in line with Aichi global targets, to policy-makers, opinion leaders and the wider public in general - Help shape the structure and priorities of South Africa’s updated NBSAP in close collaboration with other NBSAP consultants and working groups. - Play a key role in editing and organising the key chapters of the NBSAP and its implementation plans. - Review in detail the contributions from service provider (in particular the strategic studies in Annex E) and find ways to integrate the content into the NBSAP and related products. - Help conceive and regularly produce content to South Africa’s new CHM, feeding it on a weekly basis with news, feeds, photos, documents and other. - In collaboration with technical experts, design a user-friendly monitoring system and report on the status of biodiversity on the basis of national targets with a view to widely disseminating this monitoring system and its contents to the public. - With a view to validating and widely discussing national commitments with respect to implementing the CBD at the national level, carry out consultations on the proposals for the national targets, working with provincial representatives, government counterparts, NGOs, CBOs, experts from research and academia, plus other relevant stakeholder to define national objectives and priorities. Responsible for the following deliverable: - Communication and outreach strategy for the NBSAP - Editorial quality of the Second National Biodiversity Strategy and Action Plan for South Africa (including the sub-products as applicable) - Content and appearance of the CHM Gateway for South Africa Contribution to the following deliverables: - Brief Action-Oriented National Biodiversity Framework for South Africa, reviewing biodiversity planning processes in South Africa and including requirements for implementation of the new NBSAP - Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for South Africa (including the sub-products as applicable) - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy - Fully functional CHM Gateway for South Africa, based on best international practice on the matter Selection criteria: should have an advanced university degree in language, social communication, journalism or related field, with a focus on environmental management issues, with a minimum of 5 years of experience, in particular with respect to editorial and communication. Knowledge and understanding of the relevant UN Convention, the existing NBSAP and environmental issues in South Africa are an advantage. |
| Environment Economist (Facilitator of the Local TEEB activities) | 1,000 | 13 | Objective Ensure that the expected synergy and collaboration between the EU-UNDP Biodiversity Finance project and the Enabling Activity Project for South Africa is well articulated and effective in practice. Play a key role in the ecosystem valuation activity and in the preparation of the NBSAP financing plan. Key tasks are: - Carry out a desk review of existing studies and on-going studies in South Africa that identify and assess the value(s) of key ecosystem services within the country, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, based on e.g. (e.g., water, carbon, soil retention, nutrient recycling, recreation) - Research existing global and regional maps and datasets that also touch upon the issue of key ecosystem services - Liaise with on-going initiatives (the DEA supported valuation study and the EU-funded UNDP pilot project on Biodiversity Finance in order to obtain data, information and analysis that can be used to compile the NBSAP chapter on valuation - Based on the above, prepare a draft for the NBSAP chapter on valuation of ecosystems and biodiversity - Work with the remainder of project consultants and DEA to organize a workshop/meeting with the aim of presenting the findings. - Conclude the preparation of the mentioned chapter - At a second (likely with additional funding and when the NBSAP is prepared and implementation plans are being developed), draw up a cost estimate for implementing NBSAP. - Carry out research to identify appropriate institutional donors, including trust funds, non profits and government agencies. - Identify funding opportunities and follow-up on them. - Establish links with potential donors (communicate with them, invite them to participate in project activities, submit concept papers or proposals) - Collaborate with associate organizations in fund raising and promote the development of joint proposals - Survey national and provincial agencies, civil society organizations, institutions and other funding sources to obtain short and long-term funding. - Develop a structured database to manage information on all prospects and donors to enable follow-up and evaluation. - Develop a financing plan with specific mechanism for ensuring revenue and fund raising in the short, medium and long term. Contribution to the following deliverables: - Brief Action-Oriented National Biodiversity Framework for South Africa, reviewing biodiversity planning processes in South Africa and including requirements for implementation of the new NBSAP - Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for South Africa - Second National Biodiversity Strategy and Action Plan for South Africa - Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research needs - Sub-product 3: Ecosystem-based adaptation Study: Options and costs of nature-based solutions to climate change in South Africa - Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy |
| Capacity Development (Government financed for approx. 15 weeks) | n/a | n/a | Objective Play a key role in defining, in terms of capacity, technology and finance needs, how the implementation of the NBSAP will be made feasible in South Africa. He/she will look at the current systemic capacity engaged in biodiversity management and outline realistic goals for how this capacity can be further developed in tandem with the effective implementation of the Strategy. The development of Overall Implementation Plans for the NBSAP will also include the assessment and strengthening of capacity needs. Key tasks are: - Make a significant contribution to the Outputs 3.1 and 3.4 of the project: - Assist in the conceptualization of the Monitoring and Reporting Framework for the NBSAP. - Assess extent of role clarity and the level of implementation and enforcement of the CBD and its COP guidance across all primary and secondary stakeholders in central government, NGOs/CSOs, including women and indigenous groups. - Determine the level of willingness to take responsibility and provide leadership in ensuring relevant CBD obligations and activities are fulfilled. - Assess whether the identified primary and secondary duty bearers have the necessary human resources to meet the specific obligations. - Assess the pattern and efficacy of participation at regional technical committees and COP meetings. - Based on international best practice, recommend the most suitable institutional and/or accountability structure for the effective implementation and coordination of NBSAP implementation at the national and sub-national levels. - Identify and prioritise the capacity development needs required to effectively implement the NBSAP at all levels within central government and with the involvement of NGOs/CSOs, women’s and indigenous groups. - Generate recommendations for capacity enhancement at all levels. - Generate recommendations to enable the rationalisation of capacity and efficient resource allocation during implementation with other MEAs. This will build upon the results of the UNDP/GEF National Capacity Self-Assessment exercise, but taken a few steps further. - Develop the blueprint of a Capacity Development Programme and Training Action Plan for effective implementation and coordination of the NBSAP at all levels and involving all targeted stakeholders for capacity building. This will be one of the implementation plans of the new NBSAP. Contribution to the following deliverables: - Review of the Biodiversity Planning Process in South Africa and the mechanisms to promote biodiversity conservation and sustainable use. - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP Selection criteria: University degree (preferably advanced) in a discipline such as Human Resource Management or Public Administration. Proven experience in Skills Assessment, Capacity Development and Training. Minimum 5 years experience in institutional/organisational development and change management. |
| Facilitation of stakeholder engagement (Government financed, 6 consultants for approx. 3 weeks each) | n/a | n/a | - Lead the tasks of logistical organisation of key project events. This implies helping organise them by compiling lists of invitees, sending out invitations, composing the agenda, booking venues and ensuring payment, confirming the presence of authorities, the contribution from keynote speakers, resource persons and others. - Reach out to provinces, through provincial governments, on the NBSAP update activities, distributing materials, organising provincial events and following up on inputs from provinces and implementation. - During project events, facilitate working sessions. - Prepare reports on project events. Complete TOR will be developed in due course. |
| International |  |  |  |
| UNDP Environment and Energy Policy Advisor (Johannesburg Service Centre) | n/a | n/a | Objective Participate in key project events and Contribute to the following deliverables: - Brief Action-Oriented National Biodiversity Framework for South Africa, reviewing biodiversity planning processes in South Africa and including requirements for implementation of the new NBSAP - Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for South Africa - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy - Fully functional CHM Gateway for South Africa, based on best international practice on the matter |

Note: *  $ per person weeks included herein with several digits for longer term assignments to avoid round-up errors.

Annex B. Chronogramme of activities

| Comp | Modules | Guiding activities under each module | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | COP 11 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | COP 12 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1 | I. Preparation | 1. Rapid stocktaking and review of relevant plans, policies and reports |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2. Identification of stakeholders; consultations and awareness |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3. Rapid assessment of the causes and consequences of biodiversity loss highlighting the value of biodiversity and ecosystem services and their contribution to human well-being |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
|  | II Setting national targets, principles, & main priorities of the strategy | 4. Setting national targets, principles, & main priorities of the strategy though national consultations |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | III. Strategy and action plan development | 5. Developing the strategy and actions to implement the agreed targets though national consultations |  |  |  | x | x | x | x | x | x |  |  |  |  |  |  |  |
|  |  | 6. Application of the NBSAP to sub-national entities through sub-national and local consultations |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |
|  |  | 7. Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations |  |  |  |  | x | x | x | x | x |  |  |  |  |  |  |  |
| 3 | IV. Development of Implementation plans and related activities | 8. Development of a plan for capacity development for NBSAP implementation. |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |
|  |  | 9. Technology needs assessment |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |
|  |  | 10. Development of a communication and outreach strategy for the NBSAP. |  |  | x | x | x | x | x | x | x | x | x |  |  |  |  |  |
|  |  | 11. Development of a plan for resource mobilization for NBSAP implementation |  |  |  |  |  |  | x | x | x | x | x |  |  |  |  |  |
|  | V. Institutional, monitoring, reporting and exchange | 12. Establishment/ strengthening of national coordination structures |  |  | x | x | x | x | x | x | x | x | x |  |  |  |  |  |
|  |  | 13. CHM development. |  |  | x | x | x | x | x | x | x | x | x |  |  |  |  |  |
|  |  | 14. Development of indicators and monitoring approach |  |  |  |  |  |  | x | x | x | x | x |  |  |  |  |  |
|  |  | 15. Fifth national report |  |  |  |  |  |  |  |  |  | X | x |  |  |  |  |  |

Annex C. UNDP Total Budget and Workplan

| GEF Component (Outcome) /Atlas Activity | Resp. Party/ Impl. Agent | Fund ID | Donor Name | ERP / ATLAS Budget Code | Atlas Budget Description | TOTAL Amount (USD) | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comp 1. Stocktaking and national target setting | NIM | 62000 | GEF-10003 | 71600 | Travel | 8,000 | 8,000 |  |  | a |
|  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 20,000 | 20,000 |  |  | b |
|  | NIM | 62000 | GEF-10003 | 72500 | Supplies | 2,000 | 2,000 |  |  | c |
|  | GEF Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  | 30,000 | 30,000 | 0 | 0 |  |
| TOTAL ACTIVITY 1 (Comp 1) |  |  |  |  |  | 30,000 | 30,000 | 0 | 0 |  |
| Comp 2. NBSAP update | NIM | 62000 | GEF-10003 | 71300 | Local Consultants | 13,000 |  | 13,000 |  | d |
|  | NIM | 62000 | GEF-10003 | 71400 | Contractual Services - Individ | 50,000 | 10,000 | 25,000 | 15,000 | e |
|  | NIM | 62000 | GEF-10003 | 71600 | Travel | 8,000 |  | 8,000 |  | a |
|  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 5,000 |  | 5,000 |  | f |
|  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 20,000 |  | 20,000 |  | g |
|  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 20,000 |  | 20,000 |  | h |
|  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 20,000 |  | 20,000 |  | i |
|  | NIM | 62000 | GEF-10003 | 72500 | Supplies | 2,000 |  | 2,000 |  | j |
|  | GEF Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  | 138,000 | 10,000 | 113,000 | 15,000 |  |
| TOTAL ACTIVITY 2 (Comp 2) |  |  |  |  |  | 138,000 | 10,000 | 113,000 | 15,000 |  |
| Comp 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms | NIM | 62000 | GEF-10003 | 71600 | Travel | 8,000 |  | 4,000 | 4,000 | a |
|  | NIM | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 30,000 |  | 20,000 | 10,000 | k |
|  | NIM | 62000 | GEF-10003 | 72500 | Supplies | 2,000 |  | 1,000 | 1,000 | l |
|  | GEF Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  | 40,000 | 0 | 25,000 | 15,000 |  |
| TOTAL ACTIVITY 3 (Comp 3) |  |  |  |  |  | 40,000 | 0 | 25,000 | 15,000 |  |
| Project Mgt | NIM | 62000 | GEF-10003 | 72400 | Communic & Audio Visual Equip | 3,000 | 1,000 | 1,000 | 1,000 | m |
|  | NIM | 62000 | GEF-10003 | 72800 | Information Technology Equipmt | 6,000 | 6,000 |  |  | n |
|  | NIM | 62000 | GEF-10003 | 74100 | Professional Services | 3,000 | 1,000 | 1,000 | 1,000 | o |
|  | GEF Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  | 12,000 | 8,000 | 2,000 | 2,000 |  |
| TOTAL ACTIVITY 4 (Project Management) |  |  |  |  |  | 12,000 | 8,000 | 2,000 | 2,000 |  |
|  | SUB-TOTAL GEF |  |  |  |  | 220,000 | 48,000 | 140,000 | 32,000 |  |
|  | GRAND TOTAL (in cash) |  |  |  |  | 220,000 | 48,000 | 140,000 | 32,000 |  |

| Budget Notes |  |
| --- | --- |
| a | Subsidy from GEF for domestic travel by key participants in (i) the Stocktaking and Target Setting (Inception) Workshop (Component 1); (ii) the NBSAP update workshop (Component 2); and (iii) NBSAP provincial dissemination & exchange workshops (Component 3). |
| b | Stocktaking study National BD Framework (GEF contribution). Refer to TOR in Annex E |
| c | Various supplies - Stocktaking meetings and consultations (Component 1) |
| d | Short-term national consultant: Environment Economist (Local TEEB Facilitator) (lump-sum $13K) |
| e | Long-term national consultants: NBSAP Communications and Editorial Officer, part time (50%) for 2 year at $25K per year. |
| f | Local TEEB Study (GEF contribution). Organise a meeting to take stock of the valuation study lead by DEA and to ensure the coordination of activities among that initiative, the BD EA project and the UNDP/EU Project on Biodiversity Finance. |
| g | 21st Century PAs Study (GEF contribution). Refer to TOR in Annex E |
| h | Ecosystem-based adaptation Study (GEF contribution). Refer to TOR in Annex E |
| i | Biodiversity-centered sectoral development Study (GEF contribution). Refer to TOR in Annex E |
| j | Various supplies - NBSAP update process (Component 2) |
| k | National and Provincial workshops |
| l | Various supplies - provincial exchange program under Component 3 (NBS impl. Plans) |
| m | Communication costs of the project unit |
| n | IT equipment for the project's long-term consultants. |
| o | Project Audit |

Annex E. Technical Assistance Service Provision: TOR for launching a Request for Quotes

Knowledge and Capacity Building Services for integrating new global biodiversity guidance into South Africa’s sectoral planning frameworks, climate change response and biodiversity planning and management practices in general, including the management of protected areas

Introduction

As per the Total Budget and Workplan (TBW) in Annex D of this proposal, four output-based consultancies are planned under the project. This Annex describes the work under each of them. The content herein will form the basis for prepare complete Requests for Quotes for each of them. Below is the overview:

| # | Title of the Output-based consultancy | Amount reserved in the TBW ($) | TBW Budget Note reference |
| --- | --- | --- | --- |
| 1 | A National Biodiversity Framework which sets out the priorities for action by local, provincial and national government, statutory bodies and civil society in implementing the NBSAP | $20,000 | b |
| 2 | Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA) | $20,000 | g |
| 3 | Exploring and costing options for Ecosystem-based adaptation to climate change in South Africa, linked to government priorities for job creation and poverty reduction | $20,000 | h |
| 4 | Development of a ‘biodiversity-centred’ development impact analysis for key economic sectors: assessing the stakes for biodiversity of sectoral economic development, and the opportunities for conservation and sustainable use in South Africa | $20,000 | i |

The proposed consultancies may combine national and international expertise and may be assigned to a centre of excellence, NGO or consultancy company that can avail or put together the required specialist staff.

The complete Requests for Quotes prepared by UNDP normally have the following structure:

i.	Instructions to Offerors

ii.	General Conditions of Contract

iii.	Terms of Reference (TOR)

iv.	Proposal Submission Form

v.	Price Schedule

In this annex, only the TOR are described. The remainder of the chapters of the Requests for Quotes will be completed before launching the tenders.

The complete TOR for Requests for Quotes will include the following headings (Sections):

(1) Summary

(2) Background

(3) Objective of the Consultancy

(4) Scope of Work

(4) Expected Results

(5) Duty station

(6) Requirements to the documents

(7) Responsibility

(8) Qualification requirements

(9) Available information

(10) Selection Process

Section 1 of the TOR is the same for all four output-based consultancies and it is presented further down. Its contents may be further detailed in Section 2, though this is not included here (may be prepared later or suppressed). Sections 5, 6 and 7 are also common to all four output-based consultancies and are included after the description of Section 1. Sections 8, 9 and 10 will be completed before launching the tenders.

The number of minimum mission days and schedule of payment are to be completed when composing the final documentation for the Request for Quotes.

The complete scope of the work and the specific tasks for all of the proposed consultancies will also be fully developed during the project’s inception phase.

Common Sections to all four TORs

(1) Summary

South Africa is in the process of implementing a GEF biodiversity planning project whose objective is to integrate the country’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process. This will be achieved in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020, including the Aichi Targets for Biodiversity.

The following key outcomes are sought as part of the project:

1) A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets. A key product will be:

- A National Biodiversity Framework which sets out the priorities for action by local, provincial and national government, statutory bodies and civil society in implementing the NBSAP

2) South Africa’s National Biodiversity Strategy and Action Plan (NBSAP) is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience. The development of the NBSAP will be supported by the development following key studies:

- Priorities for national and provincial implementation of South Africa’s National Protected Areas Expansion Strategy, linked to the CBD’s Programme of Work on Protected Areas (PoWPA) and linked to government mandates and delivery agreements with resource mobilization for this covered under Component 3

- Local TEEB (The Economics of Ecosystems and Biodiversity): Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research pieces needed to make the case for action based on valuation and/or the anticipated cost of inaction

- Exploring and costing options for Ecosystem-based adaptation to climate change in South Africa, linked to government priorities for job creation and poverty reduction

- Development of a ‘biodiversity-centred’ development impact analysis for key economic sectors: assessing the stakes for biodiversity of sectoral economic development, and the opportunities for conservation and sustainable use in South Africa.

3) National frameworks for resource mobilization, Convention reporting and exchange mechanisms, including the Clearing House Mechanism (CHM) of the CBD, are established and strengthened

The ultimate goal of the project is to build national capacity within the topic of biodiversity planning. This implies procuring knowledge and capacity building services due to the specificity of the topics at hand and the technical requirements.

Hence, a Request for Quote is being launched in view of having services rendered by a group of specialized consultants within the following areas of expertise:

[Areas of expertise are specific to each consultancy]

(2) Background

[To be added when composing the final documentation for the Request for Quotes]

(5) Duty station:

- [According to the specificities of each consultancy]*

*Note: all travel expenses should be included into the breakdown of contract total amount by submission of financial proposal.

(6) Requirements to the documents

- Draft and final documents should be submitted in English in MS Word (2007 and later). Used font: Arial, size: 12;

Presentational documents should be prepared in Power Point.

[May be complemented when composing the final documentation for the Request for Quotes]

(7) Responsibility

- Agrees the above results with Project Technical Coordinator;

- Works in close collaboration with the remainder teams of experts and consultants involved in the Biodiversity Enabling Activity Project

- Ensures timely and quality execution of the Terms of Reference (after due finalisation, validation and agreement); and

- Ensures unconditional implementation of requirements of the contract.

[The above is generic and may be expanded as needed]

Specific Sections for each of the three TORs

[Annex E-1]

Output-based Consultancy 1:

A National Biodiversity Framework which sets out the priorities for action by local, provincial and national government, statutory bodies and civil society in implementing the NBSAP

Areas of expertise: Ecology, conservation, protected area management, mainstreaming, policy analysis with focus on biodiversity.

Proposals and quotes from qualified companies, centres of excellence, parastatals or NGOs should be presented as a package of services, including honoraries, travel expenses and administrative costs.

(3) Objective of the Consultancy

Prepare, through a widely consultative process, a National Biodiversity Framework for South Africa as a key product from the project’s Component 1.

(4) Scope of Work

A National Biodiversity Framework sets out the priorities for action by local, provincial and national government, statutory bodies and civil society in the revision and implementing the NBSAP. It is a brief document and in this manner accessible to the public in general. It must reflect consensus on the elements that the country wishes to emphasise in the NBSAP and in its implementation.

South Africa has a very positive experience with the preparation of a National Biodiversity Framework as a preparatory activity to the compilation of the NBSAP. This was the case with the previous NBSAP. Given that the NBSAP to be prepared is the second one for the country, there is a need to take stock of the implementation of the first NBSAP and of related biodiversity planning activities. This may include convention reporting, preparation of sub-national strategies, bio-regional strategies, the preparation of specific reports related to the CBD’s Programmes of Work and cross-cutting themes, capacity assessments etc. This analysis will allow for the identification of barriers to the overall implementation of the strategy at the country level.

The following step will include the establishment of biodiversity targets for South Africa in light of the Aichi Targets. While South Africa’s current NBSAP and NBF are comprehensive and have clear national targets, these were set in the context of the CBD’s 2010 targets and their implementation has not been comprehensively monitored or implemented. There is a need for South Africa to review its own national targets in the context of its commitment to the CBD, given the new Aichi biodiversity targets set for the period 2011-2020 at the 10th Conference of the Parties to the CBD in Nagoya in October 2010.

As a result of the above steps, the National Biodiversity Framework will be prepared and validated.

The consultancy will carry out the following tasks:

- Desk review of existing plans, policies and practices with respect to the management of biodiversity in the country.

- Outline or review the root causes of biodiversity loss, understanding the current drivers behind these threats, as well as the key aspects of the policy environment that are barriers and challenges to effective implementation of the current NBSAP. Special attention should be paid to emerging threats and changes in tendencies. The framework of threat classification by the Millennium Ecosystem Assessment can serve as inspiration.

- Identify key gaps in the existing NBSAP, analysing the primary drivers to biodiversity loss and their root causes

- Identifying the means of overcoming existing barriers and challenges.

- On the basis of previous work aimed at integrating CBD targets to biodiversity planning, review targets that were set for South Africa and make proposals for how these can be adapted and added to for reflecting the new global Aichi Targets at the national level.

- Seek advice from MINTEC Working Group 1 (in case the consultative group is not the same the WG1) on the composition of the broad group of stakeholder to consult in connection with the revised National Biodiversity Framework.

- Organise consultation meetings with the consultative group to present key products. The group may be composed of representatives from national, provincial and local government, statutory bodies, non-governmental organizations, community-based organizations, traditional authorities, representative structures of communal and private landowners, and representatives of commercial production sectors.

- Validate key products together with DEA and the project Technical Coordinator and the consultative group.

- Submit all required information for finalizing the National Biodiversity Framework for South Africa, including the agreed national targets for biodiversity management, in light of the global Aichi Targets, according to agreed deadlines.

The consultancy will also contribute to the following Outputs of the Enabling Activity project:

Output 1.1: Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner.

Output 1.2: In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to South Africa’s reality and helps develop provincial and national monitoring and reporting capacity.

Output 1.3: The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means.

Output 1.4: In an iterative manner, South Africa taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones).

(4) Expected Results

Be primarily responsible for the following deliverable:

- Brief Action-Oriented National Biodiversity Framework for South Africa, reviewing biodiversity planning processes in South Africa and including requirements for implementation of the new NBSAP

- Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020

These may be combined into a single document.

[Annex E-2]

Output-based Consultancy 2:

Integrating the challenges to Protected Areas in the 21st Century into the NBSAP and the national implementation of the CBD’s Programme of Work on Protected Areas (PoWPA)

Areas of expertise: Ecology, conservation, protected area management, economics, policy analysis, law and other relevant subjects.

Proposals and quotes from qualified companies, centres of excellence, parastatals or NGOs should be presented as a package of services, including honoraries, travel expenses and administrative costs.

(3) Objective of the Consultancy

Provide knowledge and capacity building services to the government of South Africa, as well as to other key stakeholder involved in the process of reviewing the country’s previous biodiversity planning processes, to integrate the challenges to South Africa’s Protected Areas into the country’s new NBSAP and into the country’s implementation of the CBD’s Programme of Work on Protected Areas (PoWPA).

(4) Scope of Work

To the extent possible, the work under this consultancy will be based on existing studies and analyses. It will depart from the existing NBSAP, but it will also look at any advances in knowledge development in the field of biodiversity in South Africa. This is particularly important, as the existing NBSAP dates from 2006 and because a National Protected Area Expansion Strategy has been prepared and approved after a thorough consultation and scrutiny process. The NPAES is in many respects a visionary document, which takes into account the need for improving the ecological representation of key ecosystems and species in the protected area (PA) estate, including within scenarios of climate change. Much of the focus is also on the sustainability of the proposed expansion.

However, the PoWPA is concerned with a number of other aspects of PA management than merely the design of the estate. There is therefore a need to complement the work under the NPAES with these other aspects.

The consultancy will cover the specific themes and objectives related to the planning and implementation of the CBD’s Protected Area Programme of Work on Protected Areas (PoWPA) in South Africa. The themes may include: Protected Area (PA) design (in many respects already covered in the NPAES), site and PA system management, ecological monitoring, management of PAs in changing climatic regimes, policy, legal institutional and socio-economic frameworks for effective PA systems, PA finance, PA site governance, in particular the engagement of riparian community in PA management.

The consultancy is expected to make a significant contribution to the Study on ‘Integrating the challenges to 21st Century Protected Areas into the NBSAP and the national implementation of the CBD’s PoWPA’.

The consultancy will also contribute to the following Outputs of the Enabling Activity project:

Output 2.1: A National Biodiversity Strategy and Action Plan (NBSAP) for South Africa, anchored into national development frameworks, is revised and updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience

Outputs 1.1: Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner.

Output 1.2: In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to South Africa’s reality and helps develop provincial and national monitoring and reporting capacity

Output 1.3: The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means.

Key tasks are:

- Stocking of existing plans, policies and practices in South Africa that result in biodiversity conservation or loss – the focus will be on protected areas (PA) management and the work under it will build on the Elements and Goals of the PoWPA and how they are being implemented in South Africa. The former are:

Element 1:  Direct Actions for Planning, Selecting, Establishing, Strengthening, and Managing, Protected Area Systems and Sites

Element 2:  Governance, Participation, Equity and Benefit Sharing

Element 3:  Enabling Activities

Element 4:  Standards, Assessment, and Monitoring

- Identify the root causes of biodiversity loss within South Africa’s PAs by first identifying the threat and then the drivers behind the threats, as well as the role played by PAs in averting those threats.

- Identify the key barriers and challenges in the policy environment to effective management of PAs in South Africa with focus on the systems and on sites.

- The (UNDP) Capacity Development Scorecard for the Management of Protected Areas Systems will be applied in an analytical fashion to identify specific capacity barriers at the individual, organisational and systemic levels. Other tools, including on PA finance and the site management effectiveness (METT) can also be applied across the entire system of Pas, if not yet done. The GEF SO1 Tracking Tools includes both and may provide a more in-depth insight into the status of the system, and of the barriers faced at different levels.

- The PoWPA E-learning Curricula for protected area management will be explored, in terms of how it can contribute to improving capacity for it in South Africa. These are available at www.cbd.int/protected.

- The consultancy will ensure that South Africa taps into and participate in relevant knowledge fora and databases for protected area management. The goal is to identify the challenges to South Africa’s PAs in the 21st Century.

- Identify the means to overcome existing barriers and challenges to integrating the challenges to 21st Century Protected Areas into the NBSAP and the national implementation of the CBD’s PoWPA in South Africa.

- Provide inputs of technical nature de help South Africa define a set of national targets in response to the Aichi Targets and a means to track the implementation of the CBD Strategic Plan 2011-2020 at the national level.

- Take an active part in the technical and editorial work that will help South Africa develop its new NBSAP.

- Organise consultation meetings with the consultative group to present key products. The group may be composed of representatives from national, provincial and local government, statutory bodies, non-governmental organizations, community-based organizations, traditional authorities, representative structures of communal and private landowners, and representatives of commercial production sectors.

- Validate key products together with DEA and the project Technical Coordinator and the consultative group.

- Submit all required information for finalizing the National Biodiversity Framework for South Africa, including the agreed national targets for biodiversity management, in light of the global Aichi Targets, according to agreed deadlines.

(4) Expected Results

Be primarily responsible for the following deliverable:

- NBSAP Sub-product 1: Implementation Priorities for the NPAES

Make a contribution to the following deliverables:

- Second National Biodiversity Strategy and Action Plan for South Africa

- Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research needs

- Sub-product 3: Ecosystem-based adaptation Study: Options and costs of nature-based solutions to climate change in South Africa

- Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry

- Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP, including a resource mobilization strategy

- Fully functional CHM Gateway for South Africa, based on best international practice on the matter

[Annex E-3]

Output-based Consultancy 3:

Exploring and costing options for Ecosystem-based adaptation to climate change in South Africa

Areas of expertise: Ecology, conservation, protected area management, climate change modelling, adaptation, economics, econometrics.

Proposals and quotes from qualified companies, centres of excellence, parastatals or NGOs should be presented as a package of services, including honoraries, travel expenses and administrative costs.

(3) Objective

Ensure that climate change considerations (both threats and opportunities) become integrated into South Africa’s NBSAP. The key concerned activity is: “Incorporating climate change issues into NBSAPs” under Component 2 – the key focus being on the options and costs of nature-based solutions to climate change in South Africa (or Ecosystem-based adaptation).

(4) Scope of Work

The consultancy is expected to make a significant contribution to the Study on ‘Exploring and costing options for Ecosystem-based adaptation to climate change in South Africa, linked to government priorities for job creation and poverty reduction in South Africa’.

Key tasks are:

- Take stock of key climatic risks and vulnerabilities that will affect South Africa’s ecosystems and the services that they render, as well as species (and groups of species), interspecies’ relationships and, if applicable genetic diversity. In connection with it, assess their resilience.

- Based on options for improved ecosystem management and restoration with a view to gradually withstanding the likely impacts of climate change on biodiversity, prioritise the best opportunities and costs. The following should be primarily on focus:

- No-regrets adaptation options

- Low-regrets adaptation options

- Win-win adaptation options

- Flexible or adaptive management options

- Assess the adaptation and socio-economic co-benefit of the different options.

- Based on the best availably cost coefficients for improved ecosystem management and restoration, estimate the costs of adaptation based on the options which can be reasonably pursued with tangible societal benefits. Inspiration should be sought in government priorities for job creation and poverty reduction in South Africa and in flagship programmes such as ‘Working for Water’, ‘Working for Wetlands’, ‘Working on Fire’, ‘Municipality and Grasslands’, among others.

- Assess the opportunity cost of pursuing the proposed Ecosystem-based adaptation in the South African context. This may include comparing the proposed options with no action on ecosystems and with other approaches to adaption (e.g. infrastructural, behavioural).

- Within the theme Ecosystem-based adaptation in South Africa identify topics and areas requiring more research, making recommendations on it.

- Organise consultation meetings with the consultative group to present key products. The group may be composed of representatives from national, provincial and local government, statutory bodies, non-governmental organizations, community-based organizations, traditional authorities, representative structures of communal and private landowners, and representatives of commercial production sectors.

- Validate key products together with DEA and the project Technical Coordinator and the consultative group.

- Submit all required information for finalizing the National Biodiversity Framework for South Africa, including the agreed national targets for biodiversity management, in light of the global Aichi Targets, according to agreed deadlines.

The consultancy will also contribute to the following Outputs of the Enabling Activity project:

Output 2.1: A National Biodiversity Strategy and Action Plan (NBSAP) for South Africa, anchored into national development frameworks, is revised and updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience.

Outputs 1.1: Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner.

Output 1.2: In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to South Africa’s reality and helps develop provincial and national monitoring and reporting capacity.

Output 1.3: The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means.

(4) Expected Results

Be primarily responsible for the following deliverable:

- Sub-product 3: Ecosystem-based adaptation Study: Options and Costs of nature-based solutions to climate change in South Africa

Make a contribution to the following deliverables:

- Brief Review of the Biodiversity Planning Process in South Africa

- Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020

- Second National Biodiversity Strategy and Action Plan for South Africa

- Sub-product 1: Implementation Priorities for the NPAES

- Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research needs

- Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry

[Annex E-4]

Output-based Consultancy 4:

Development of a ‘biodiversity-centred’ development impact analysis for key economic sectors:

Assessing the stakes for biodiversity of sectoral economic development, and the opportunities for conservation and sustainable use in South Africa

Areas of expertise: Environmental economics, finance and biodiversity mainstreaming.

Proposals and quotes from qualified companies, centres of excellence, parastatals or NGOs should be presented as a package of services, including honoraries, travel expenses and administrative costs.

(3) Objective

Provide knowledge and capacity building services to the government of South Africa, as well as to other key stakeholder involved in the updating of the country’s NBSAP, with focus on a key sub-product expected from the process: The Study on the ‘Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry’.

(4) Scope of Work

The consultancy is expected to make a significant contribution to the Study on ‘Advances in Sectoral Mainstreaming in South Africa: Biodiversity-centered sectoral development Study’.

The consultancy will also contribute to the following Outputs of the Enabling Activity project:

Output 2.1: A National Biodiversity Strategy and Action Plan (NBSAP) for South Africa, anchored into national development frameworks, is revised and updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience.

Outputs 1.1: Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner.

Output 1.2: In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to South Africa’s reality and helps develop provincial and national monitoring and reporting capacity.

Output 1.3: The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means.

The work under this consultancy will build on two cross-cutting themes under the CBD, which are of high relevance for South Africa: (1) Impact Assessment; and (2) Biodiversity for Development.

Impact Assessment is process of identifying the future consequences of a current or proposed action. It is used to ensure that projects, programmes and policies are economically viable, socially equitable and environmentally sustainable. Work under the Convention seeks to support efforts to adequately reflect biodiversity considerations in impact assessments. Guidance developed under the Convention helps to decide which aspects of biodiversity may need to be monitored and how to carry this out in a cost-effective way.

Biodiversity for Development is a joint initiative involving the CBD Secretariat and UNDP. The aim is to ensure that biodiversity conservation and sustainable use are integral to national and regional economic and social development policies, legal frameworks, development plans and implementation systems.

The CBD provides access to a number of guiding and training materials aimed at developing the capacity of Parties to more effectively assess the impact of different productive sectors on biodiversity and make a win-win link between these and the conservation and sustainable use of biodiversity. This material can be explored by departing from the following sites: (1) www.cbd.int/impact and (2) www.cbd.int/development.

A key output expected from the Biodiversity Enabling Activities Project for South Africa is the ‘anchoring’ of the new NBSAP into the national development frameworks for the country. This implies the full integration of new aspects of the CBD strategic plan into South Africa’s NBSAP, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience.

This consultancy will play a pivotal role in structuring the Biodiversity-centered sectoral development Study by sourcing data and training national stakeholders to become more knowledgeable on the impacts of productive activities on biodiversity and on the theme ‘biodiversity for development’ (“B for D” as called in short).

Specific Tasks will include:

- Become familiar with the descriptions of Key Activity III (Developing the NBSAP) in the GEF proposal for the Biodiversity Enabling Activities for South Africa and derive from there the tasks that pertain to this consultancy

- Analyse data and technical information, including economic, relevant for the tasks: in particular for impact assessment and the development of targets and strategies related to biodiversity links to the following key productive sectors: (i) agriculture, including livestock management; (ii) plantation forestry; (iii) fisheries; and (iv) mining and gas. As part of the analysis, also look at the links between the following development areas / topics and biodiversity, but without losing the focus on the key sectors; (a) land-use management, including spatial and infrastructural development planning; (b) development finance; (c) poverty alleviation; (d) rural development and livelihoods; (e) food security; (f) gender; (g) job creation and the green economy; (h) climate change mainstreaming.

- Based on the above, prepare and deliver training sessions lasting 5 days for a target audience comprised of government officials, technical staff in government and NGOs/CSOs engaged in the project, women’s and indigenous groups’ leaderships. The training will focus on “Biodiversity-centered Sectoral Development in South Africa”. The seminal SANBI-UNDP publication Biodiversity for Development: South Africa's Landscape Approach to Conserving Biodiversity and Promoting Ecosystem Resilience, with focus on the Cape Floristic Region, will also be presented. Where applicable, the materials from the mentioned CBD websites will be drawn in, presented and discussed. Training sessions are expected to be lively, interactive, and include case studies focused on real-life issues and solutions, always contextualized to the reality in South Africa.

- Play a leading role in preparing the publication Biodiversity-centered sectoral development Study, but in collaboration with the consultative group, the Project Technical Coordinator and other project team members and consultants.

(4) Expected Results

Be primarily responsible for the following deliverable:

- Sub-product 4: Analysis of biodiversity impacts and opportunities in key economic sectors – focus on agriculture, fisheries, plantation forestry

Make a contribution to the following deliverables:

- Brief Review of the Biodiversity Planning Process in South Africa

- Biodiversity Targets for South Africa: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020

- Second National Biodiversity Strategy and Action Plan for South Africa

- Sub-product 1: Implementation Priorities for the NPAES

- Sub-product 2: Assessing and capturing value in ecosystems’ goods and services in South Africa – analysis of primary research needs

- Sub-product 3: Ecosystem-based adaptation Study: Options and costs of nature-based solutions to climate change in South Africa

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

Geodata.rrcap.unep.org

www.teebweb.org

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources.

For more on these and other global biodiversity hotspots see www.conservation.org.

This committee, which is supported by technical working groups, facilitates co-ordination between the national and provincial departments responsible for environmental management and biodiversity conservation. Working Group 1 deals with Biodiversity and Heritage.

GEF, 2003:  “Strategic Approach to Enhance Capacity Building”.  Global Environment Facility. See also: GEF Evaluation Office, 2006:  “Evaluation of GEF Capacity Development Activities.  Approach Paper”.  GEF EO.

GEF Capacity Development Initiative, Global Support Programme for National Capacity Self-Assessment, 2010: “Monitoring Guidelines of Capacity Development in GEF Operations”.

E.g. the new or revised National Biodiversity Framework may include the establishment of Aichi Targets for South Africa and the

The actual submission of the NBSAP to the CBD Secretariat is the responsibility of the government of the Republic of South Africa, not UNDP.

Petersen, C and B. Huntley. 2005. Mainstreaming Biodiversity in Productive Landscapes. Working Paper 20. Washington DC: GEF.

These services are over and above the GEF fee. They will be rendered by non-UNDP/GEF staff. They are hence part of UNDP’s co-financing to the project.

Paragraph extracted from www.iwgia.org as a direct quote.

See e.g. www.cbd.int/traditional.

With reference to the applicable procurement process for the type of services being sought and budget allocated to financing them.

If procurement will be carried out by DEA, their tender templates and norms will apply.

www.teebweb.org

A key source of information is www.cbd.int/report but also South Africa’s CHM, if one is in place.

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

Geodata.rrcap.unep.org

See www.cbd.int/protected.